## Checklists
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
section | Door openings
checkpoint | Timber size and treatment
checkpoint | Lintels nailed of and strapped ?
checkpoint | Lintel hieght from ground - allowance for acustic floor
checkpoint | Opening aligned to upper and lower floor
check point | Opening width correct
check point | service riser installed
checklist | Interior Frame - Timber
section | Wall type
checkpoint | Wall location as per plan based off nearest grid
checkpoint | Plumb - check wall for plumb start and finish
checkpoint | Square to next frame
checkpoint | Door openings the right size
checkpoint | Bolts to bottom plate
checkpoint | Nogs installed around service penetrations as required?
checkpoint | Top plate bolted off as required
checkpoint | Service nogs as per mark up - are they required ?
checkpoint | DPC under bottom plate
checkpoint | Ceiling level nogs required of in place
checkpoint | DPC to steel connection is it required
Section | Promat
checkpoint | Confirm board type
checkpoint | Fixings used - photo in board and on fixing box
checkpoint | fire seal behind board on floor joint
checkpoint | fire seal to underlsab edge
checkpoint | Penetrations dealt with ?
section | Roof
checkpoint | Rafters installed on centres
checkpoint | Rafter packers installed
checkpoint | truss hold downs in place
checkpoint | purlins at correct centres
checkpoint | purlin fixings in place
checkpoint | Pentrations installed and in correct place
checkpoint | Plywood installed
checkpoint | plywood screwed off at centres and screw type
checkpoint | H3.2 packer installed to plywood edge
checkpoint | Soffit nogs in place
checkpoint | Facia board attached
checkpoint | Ridge beam connections done
checkpoint | Confirmation of fxings used

## Care Building -structure
Aria Bay - Base build
Level | area on floor / Grid | lists required
level 1 -
| Grid C | Interior framing | Door opening
| Grid B | Interior framing | Door opening
| Grid 11 | Interior framing | Door opening
| Grid G | Interior framing | Door opening
| Grid F | Interior framing | Door opening
| Grid 6 | Interior framing | Door opening
| Grid 7 | Interior framing | Door opening
| Grid 01 | Interior framing | Door opening
| Grid 00 | Interior framing | Door opening
| Grid 12 | Promat install
Level 2
| Grid C | Interior framing | Door opening
| Grid B | Interior framing | Door opening
| Grid 11 | Interior framing | Door opening
| Grid G | Interior framing | Door opening
| Grid F | Interior framing | Door opening
| Grid 6 | Interior framing | Door opening
| Grid 7 | Interior framing | Door opening
| Grid 01 | Interior framing | Door opening
| Grid 00 | Interior framing | Door opening
Level 3
| Grid C | Interior framing | Door opening
| Grid B | Interior framing | Door opening
| Grid 11 | Interior framing | Door opening
| Grid G | Interior framing | Door opening
| Grid F | Interior framing | Door opening
| Grid 6 | Interior framing | Door opening
| Grid 7 | Interior framing | Door opening
| Grid 01 | Interior framing | Door opening
| Grid 00 | Interior framing | Door opening
Roof | Grid A | Roof exterior
| Grid D | Roof exterior
| Grid 12 | Roof exterior
| Grid H | Roof exterior
| Grid 10 | Roof exterior
| Grid 00 | Roof exterior