## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Interior Frame - Timber |  |  |  |  | Yes | Interior Frame - Timber | 21c6f55a-e568-48a1-a327-2532ee46d7d3
checkpoint-group |  |  | section | Wall type
checkpoint-status |  |  | checkpoint | Wall location as per plan based off nearest grid
checkpoint-status |  |  | checkpoint | Plumb - check wall for plumb start and finish
checkpoint-status |  |  | checkpoint | Square to next frame
checkpoint-status |  |  | checkpoint | Door openings the right size
checkpoint-status |  |  | checkpoint | Bolts to bottom plate
checkpoint-status |  |  | checkpoint | Nogs installed around service penetrations as required?
checkpoint-status |  |  | checkpoint | Top plate bolted off as required
checkpoint-status |  |  | checkpoint | Service nogs as per mark up - are they required ?
checkpoint-status |  |  | checkpoint | DPC under bottom plate
checkpoint-status |  |  | checkpoint | Ceiling level nogs required of in place
checkpoint-status |  |  | checkpoint | DPC to steel connection
checkpoint-status |  |  | checkpoint | Wall stopping installed and bolted off
checklist-flat |  |  | checklist | Window openings |  |  |  |  | Yes | Window openings | 256b810d-898d-4436-99a5-0c9c858f5006
checkpoint-status |  |  | checkpoint | Tapes installed ?
checkpoint-status |  |  | checkpoint | Lintels nailed of and strapped ?
checkpoint-status |  |  | checkpoint | Sill height from ground
checkpoint-status |  |  | checkpoint | Lintel height from ground
checkpoint-status |  |  | checkpoint | Opening aligned to upper and lower floor
checkpoint-status |  |  | checkpoint | Opening width correct
checkpoint-status |  |  | checkpoint | rebates in place
checklist-flat |  |  | checklist | Roof |  |  |  |  | Yes | Roof | 8c1f9ac6-ce62-456f-a1e7-b288efc07929
checkpoint-status |  |  | checkpoint | Top plates install - including ribbon
checkpoint-status |  |  | checkpoint | Truss mark out from plan
checkpoint-status |  |  | checkpoint | truss hold downs in place
checkpoint-status |  |  | checkpoint | purlins at correct centres
checkpoint-status |  |  | checkpoint | purlin fixings in place
checklist-flat |  |  | checklist | Greenstop install |  |  |  |  | Yes | Greenstop install | e84b07aa-f113-444f-9ac5-15cc680b4897
checkpoint-status |  |  | checkpoint | Board type install
checkpoint-status |  |  | checkpoint | Fixings used - photo in board and on fixing box
checkpoint-status |  |  | checkpoint | fire seal behind board on floor joint
checkpoint-status |  |  | checkpoint | Joints taped
checkpoint-status |  |  | checkpoint | Fixings spacing correct
checkpoint-status |  |  | checkpoint | Penetrations dealt with
checkpoint-status |  |  | checkpoint | CLD batterns in place
checklist-flat |  |  | checklist | Promat Install |  |  |  |  | Yes | Promat Install | e8737ded-4bc5-4669-b823-4564caf5fbd9
checkpoint-status |  |  | checkpoint | board type install
checkpoint-status |  |  | checkpoint | Fixings used - photo in board and on fixing box
checkpoint-status |  |  | checkpoint | fire seal behind board on floor joint
checkpoint-status |  |  | checkpoint | fire seal to under slab edge
checkpoint-status |  |  | checkpoint | Penetrations dealt with ?
checklist-sectioned |  |  | checklist | Exterior Frame - Timber |  |  |  |  | Yes | Exterior Frame - Timber | ecb514e0-38e7-4dd0-b25f-b5115e4a50a9
checkpoint-group |  |  | section | Wall
checkpoint-status |  |  | checkpoint | Wall location as per plan based off nearest grid
checkpoint-status |  |  | checkpoint | Plumb - check wall for plumb start and finish
checkpoint-status |  |  | checkpoint | Square to next frame
checkpoint-status |  |  | checkpoint | Overhanging slab or aligned to upper floor
checkpoint-status |  |  | checkpoint | Nogs installed around service penetrations as required?
checkpoint-status |  |  | checkpoint | Bolts to bottom plate
checkpoint-status |  |  | checkpoint | Nogs installed around service penetrations as required?
checkpoint-status |  |  | checkpoint | Top plate bolted off as required
checkpoint-status |  |  | checkpoint | Service nogs as per mark up - are they required ?
checkpoint-status |  |  | checkpoint | DPC under bottom plate
checkpoint-status |  |  | checkpoint | Promat in place and completed
checkpoint-status |  |  | checkpoint | DPC to steel connection
checkpoint-status |  |  | checkpoint | Packing to steel been top and bottom done ?
checkpoint-status |  |  | checkpoint | Nogs for cladding installed ?
checkpoint-status |  |  | checkpoint | Promat sections - inspected prior to covering