## matrix_quality
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Communications - Horizontal Cable (TERs)
| Scope |  |  | Communications
Rows
|  | TERs - TER 1 | dynamic | Communications | TERs | TER 1
|  | TERs - TER 2 | dynamic | Communications | TERs | TER 2
Columns
|  | Cabling is not susceptible to mechanical damage |  | Cabling is not susceptible to mechanical damage.
|  | Cable is dressed on cable pathways with velcro |  | Cable is dressed on the cable pathways with velcro.
|  | Apply a plastic wrap printed label to each end of the cable |  | Apply a plastic wrap printed label to each end of the cable.
|  | Cable terminated into a faceplate or surface mount block |  | Cable is terminated into a faceplate or surface mount block.
|  | Cable terminated into correct patch panel reflected in communication cabinet elevations |  | Cable is terminated into the correct patch panel reflected in the communication cabinet elevations.
|  | Patch panel, faceplate/surface mount block are labelled correctly with a traffolyte |  | The patch panel, faceplate/surface mount block are labelled correctly with a traffolyte.
Communications - Horizontal Cable (BAF - Basement/Ground)
| Scope |  |  | Communications
Rows
|  | BAF - Cabinets - Basement - BDR1-4B44.01 | dynamic | Communications | BAF | Cabinets | Basement | BDR1-4B44.01
|  | BAF - Cabinets - Basement - BDR2-4B40.16 | dynamic | Communications | BAF | Cabinets | Basement | BDR2-4B40.16
|  | BAF - Cabinets - Basement - FDR\SPLIT RACK-4B44.02 | dynamic | Communications | BAF | Cabinets | Basement | FDR\SPLIT RACK-4B44.02
|  | BAF - Cabinets - Basement - FDR\SPLIT RACK-4B44.04 | dynamic | Communications | BAF | Cabinets | Basement | FDR\SPLIT RACK-4B44.04
|  | BAF - Cabinets - Basement - FDR\SPLIT RACK-4B44.03 | dynamic | Communications | BAF | Cabinets | Basement | FDR\SPLIT RACK-4B44.03
|  | BAF - Cabinets - Basement - FIELD HUB-4B43.06 | dynamic | Communications | BAF | Cabinets | Basement | FIELD HUB-4B43.06
|  | BAF - Cabinets - Basement - FIELD HUB-4B48.04 | dynamic | Communications | BAF | Cabinets | Basement | FIELD HUB-4B48.04
|  | BAF - Cabinets - Basement - FIELD HUB-4B43.08 | dynamic | Communications | BAF | Cabinets | Basement | FIELD HUB-4B43.08
|  | BAF - Cabinets - Ground - ASNET RACK-4056.4 | dynamic | Communications | BAF | Cabinets | Ground | ASNET RACK-4056.4
|  | BAF - Cabinets - Ground - DAFF SPLIT RACK-4056.77 | dynamic | Communications | BAF | Cabinets | Ground | DAFF SPLIT RACK-4056.77
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.21 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.21
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.07 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.07
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.09 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.09
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.23 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.23
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.2 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.2
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.17 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.17
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.15 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.15
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.16 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.16
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.18 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.18
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.14 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.14
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.08 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.08
|  | BAF - Cabinets - Ground - FDR\SPLIT RACK-4044.19 | dynamic | Communications | BAF | Cabinets | Ground | FDR\SPLIT RACK-4044.19
|  | BAF - Cabinets - Ground - FIELD HUB-4042.13 | dynamic | Communications | BAF | Cabinets | Ground | FIELD HUB-4042.13
|  | BAF - Cabinets - Ground - PATCH ROOM-4056.67 | dynamic | Communications | BAF | Cabinets | Ground | PATCH ROOM-4056.67
|  | BAF - Cabinets - Ground - SERVER ROOM-4056.36 | dynamic | Communications | BAF | Cabinets | Ground | SERVER ROOM-4056.36
|  | BAF - Cabinets - Ground FLB - FLB 1-FIELD HUB-4042.12 | dynamic | Communications | BAF | Cabinets | Ground FLB | FLB 1-FIELD HUB-4042.12
|  | BAF - Cabinets - Ground FLB - FLB 2-FIELD HUB-4042.14 | dynamic | Communications | BAF | Cabinets | Ground FLB | FLB 2-FIELD HUB-4042.14
|  | BAF - Cabinets - Ground FLB - FLB 3-FIELD HUB-4042.15 | dynamic | Communications | BAF | Cabinets | Ground FLB | FLB 3-FIELD HUB-4042.15
|  | BAF - Cabinets - Ground FLB - FLB 4-FIELD HUB-4042.04 | dynamic | Communications | BAF | Cabinets | Ground FLB | FLB 4-FIELD HUB-4042.04
|  | BAF - Cabinets - Ground FLB - FLB 5-FIELD HUB-4042.02 | dynamic | Communications | BAF | Cabinets | Ground FLB | FLB 5-FIELD HUB-4042.02
|  | BAF - Cabinets - Ground FLB - FLB 6-FIELD HUB-4042.03 | dynamic | Communications | BAF | Cabinets | Ground FLB | FLB 6-FIELD HUB-4042.03
|  | BAF - Cabinets - Ground FLB - FLB 7-FIELD HUB-4042.01 | dynamic | Communications | BAF | Cabinets | Ground FLB | FLB 7-FIELD HUB-4042.01
Columns
|  | Cabling is not susceptible to mechanical damage |  | Cabling is not susceptible to mechanical damage.
|  | Cable is dressed on cable pathways with velcro |  | Cable is dressed on the cable pathways with velcro.
|  | Apply a plastic wrap printed label to each end of the cable |  | Apply a plastic wrap printed label to each end of the cable.
|  | Cable terminated into a faceplate or surface mount block |  | Cable is terminated into a faceplate or surface mount block.
|  | Cable terminated into correct patch panel reflected in communication cabinet elevations |  | Cable is terminated into the correct patch panel reflected in the communication cabinet elevations.
|  | Patch panel, faceplate/surface mount block are labelled correctly with a traffolyte |  | The patch panel, faceplate/surface mount block are labelled correctly with a traffolyte.
Communications - Horizontal Cable (BAF - Level 2/Level 3)
| Scope |  |  | Communications
Rows
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.18 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.18
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.12 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.12
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.17 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.17
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.13 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.13
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.14 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.14
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.03 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.03
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.15 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.15
|  | BAF - Cabinets - Level 2 - FDR\SPLIT RACK-4244.04 | dynamic | Communications | BAF | Cabinets | Level 2 | FDR\SPLIT RACK-4244.04
|  | BAF - Cabinets - Level 2 - FIELD HUB-4241.08 | dynamic | Communications | BAF | Cabinets | Level 2 | FIELD HUB-4241.08
|  | BAF - Cabinets - Level 2 - FIELD HUB-4244.20 | dynamic | Communications | BAF | Cabinets | Level 2 | FIELD HUB-4244.20
|  | BAF - Cabinets - Level 2 - FIELD HUB-4241.01 | dynamic | Communications | BAF | Cabinets | Level 2 | FIELD HUB-4241.01
|  | BAF - Cabinets - Level 2 - FIELD HUB-4243.02 | dynamic | Communications | BAF | Cabinets | Level 2 | FIELD HUB-4243.02
|  | BAF - Cabinets - Level 2 - PATCH ROOM-4256.21 | dynamic | Communications | BAF | Cabinets | Level 2 | PATCH ROOM-4256.21
|  | BAF - Cabinets - Level 3 - FDR\SPLIT RACK-4344.10 | dynamic | Communications | BAF | Cabinets | Level 3 | FDR\SPLIT RACK-4344.10
|  | BAF - Cabinets - Level 3 - FDR\SPLIT RACK-4344.09 | dynamic | Communications | BAF | Cabinets | Level 3 | FDR\SPLIT RACK-4344.09
|  | BAF - Cabinets - Level 3 - FDR\SPLIT RACK-4344.01 | dynamic | Communications | BAF | Cabinets | Level 3 | FDR\SPLIT RACK-4344.01
|  | BAF - Cabinets - Level 3 - FDR\SPLIT RACK-4344.06 | dynamic | Communications | BAF | Cabinets | Level 3 | FDR\SPLIT RACK-4344.06
|  | BAF - Cabinets - Level 3 - FDR\SPLIT RACK-4344.02 | dynamic | Communications | BAF | Cabinets | Level 3 | FDR\SPLIT RACK-4344.02
|  | BAF - Cabinets - Level 3 - FIELD HUB-4344.08 | dynamic | Communications | BAF | Cabinets | Level 3 | FIELD HUB-4344.08
|  | BAF - Cabinets - Level 3 - FIELD HUB-4342.02 | dynamic | Communications | BAF | Cabinets | Level 3 | FIELD HUB-4342.02
|  | BAF - Cabinets - Level 3 - PATCH ROOM-4346.02 | dynamic | Communications | BAF | Cabinets | Level 3 | PATCH ROOM-4346.02
|  | BAF - Cabinets - Level 3 - SERVER ROOM-4356.29 | dynamic | Communications | BAF | Cabinets | Level 3 | SERVER ROOM-4356.29
Columns
|  | Cabling is not susceptible to mechanical damage |  | Cabling is not susceptible to mechanical damage.
|  | Cable is dressed on cable pathways with velcro |  | Cable is dressed on the cable pathways with velcro.
|  | Apply a plastic wrap printed label to each end of the cable |  | Apply a plastic wrap printed label to each end of the cable.
|  | Cable terminated into a faceplate or surface mount block |  | Cable is terminated into a faceplate or surface mount block.
|  | Cable terminated into correct patch panel reflected in communication cabinet elevations |  | Cable is terminated into the correct patch panel reflected in the communication cabinet elevations.
|  | Patch panel, faceplate/surface mount block are labelled correctly with a traffolyte |  | The patch panel, faceplate/surface mount block are labelled correctly with a traffolyte.
Communications - Horizontal Cable (BAF - Attic/Plaza/Car Park/Airside Apron West)
| Scope |  |  | Communications
Rows
|  | BAF - Cabinets - Attic - FIELD HUB-4401.01 | dynamic | Communications | BAF | Cabinets | Attic | FIELD HUB-4401.01
|  | BAF - Cabinets - Terminal Plaza - FIELD HUB TYPE 2-FIELD HUB-2 | dynamic | Communications | BAF | Cabinets | Terminal Plaza | FIELD HUB TYPE 2-FIELD HUB-2
|  | BAF - Cabinets - Terminal Plaza - FIELD HUB TYPE 2-FIELD HUB-4 | dynamic | Communications | BAF | Cabinets | Terminal Plaza | FIELD HUB TYPE 2-FIELD HUB-4
|  | BAF - Cabinets - Terminal Plaza - FIELD HUB TYPE 3-FIELD HUB-1 (FDH1) | dynamic | Communications | BAF | Cabinets | Terminal Plaza | FIELD HUB TYPE 3-FIELD HUB-1 (FDH1)
|  | BAF - Cabinets - Terminal Plaza - FIELD HUB TYPE 3-FIELD HUB-3 (FDH2) | dynamic | Communications | BAF | Cabinets | Terminal Plaza | FIELD HUB TYPE 3-FIELD HUB-3 (FDH2)
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-1 (FDH1) | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-1 (FDH1)
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-2 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-2
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-3 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-3
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-4 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-4
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-5 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-5
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-6 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-6
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-7 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-7
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-8 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-8
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-9 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-9
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-10 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-10
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-11 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-11
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-12 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-12
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-13 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-13
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-14 (FDH2) | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-14 (FDH2)
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-15 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-15
|  | BAF - Cabinets - Car Park 1-4 - FIELD HUB TYPE 2-FIELD HUB-16 | dynamic | Communications | BAF | Cabinets | Car Park 1-4 | FIELD HUB TYPE 2-FIELD HUB-16
|  | BAF - Cabinets - Airside Apron West - FIELD HUB TYPE 2-NCS1 | dynamic | Communications | BAF | Cabinets | Airside Apron West | FIELD HUB TYPE 2-NCS1
|  | BAF - Cabinets - Airside Apron West - FIELD HUB TYPE 2-NCS2 | dynamic | Communications | BAF | Cabinets | Airside Apron West | FIELD HUB TYPE 2-NCS2
|  | BAF - Cabinets - Airside Apron West - FIELD HUB TYPE 2-NCS3 | dynamic | Communications | BAF | Cabinets | Airside Apron West | FIELD HUB TYPE 2-NCS3
|  | BAF - Cabinets - Airside Apron West - FIELD HUB TYPE 2-NCS4 | dynamic | Communications | BAF | Cabinets | Airside Apron West | FIELD HUB TYPE 2-NCS4
|  | BAF - Cabinets - Airside Apron West - FIELD HUB TYPE 2-NCS5 | dynamic | Communications | BAF | Cabinets | Airside Apron West | FIELD HUB TYPE 2-NCS5
|  | BAF - Cabinets - Airside Apron West - FIELD HUB TYPE 2-NCS6 | dynamic | Communications | BAF | Cabinets | Airside Apron West | FIELD HUB TYPE 2-NCS6
Columns
|  | Cabling is not susceptible to mechanical damage |  | Cabling is not susceptible to mechanical damage.
|  | Cable is dressed on cable pathways with velcro |  | Cable is dressed on the cable pathways with velcro.
|  | Apply a plastic wrap printed label to each end of the cable |  | Apply a plastic wrap printed label to each end of the cable.
|  | Cable terminated into a faceplate or surface mount block |  | Cable is terminated into a faceplate or surface mount block.
|  | Cable terminated into correct patch panel reflected in communication cabinet elevations |  | Cable is terminated into the correct patch panel reflected in the communication cabinet elevations.
|  | Patch panel, faceplate/surface mount block are labelled correctly with a traffolyte |  | The patch panel, faceplate/surface mount block are labelled correctly with a traffolyte.