## Resources
Warnings | Type | Id | Name | Values | Prompting Name | Resource Id
| checklist |  | ITP-CIV-Cement Treated Crushed Rock (Supply and Install) Rev 0 | itp | ITP-CIV-Cement Treated Crushed Rock (Supply and Install) Rev 0 | 048b8a88-3c4e-454d-8be6-bed9acacbb4c
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 2728c32a-9d8c-4a9e-820e-390cf1a229ef | Document Title: ITP-CIV-Cement Treated Crushed Rock (Supply and Install)
| note | b94006c5-8005-4d99-b2a0-43b4ff1eb5e2 | ITP Description: Cement Treated Crushed Rock (Supply and Install)
| note | c0823e1b-9c45-4242-b6de-325977e25c21 | Document Number (in Teambinder):
| note | 10935f5b-33e7-423e-8fe0-2c5aa073c571 | Discipline (e.g. CIV/STR/RAIL: CIV
| note | 225b50af-ba15-4839-adee-e8340119ffba | Revision Number: 0
| note | 0c40ba5d-d63a-4665-bf18-47faab1abd31 | Revision Date: 44161
| note | e13daa08-5549-41e5-9384-f289847d1927 | ITP created by: Jadan Halkett
| note | 77db2d10-821c-4333-8adb-6cba87c67f99 | ITP approved for use by: Josie Pavlou
| note | cc53e270-1491-40ab-9195-b4c2576b5976 | 1.1 VicRoads Section 306 Oct '19
| note | e72da206-809d-46e5-a494-72fb585194c8 | 1.2 IFC Drawings
| note | ff0d1d45-fbfb-4dcd-9c3b-e81c4d3ea703 | 1.3 Code of Practice 500.12
| note | 283f0714-500c-4c5c-affa-7a40a289be6d | 1.4 VicRoads Section 815 July '16
| section |  | Preliminaries / Preconstruction
| checkpoint |  | 2.1 Check that current revision drawings are being used
| note | e44cd44a-4268-45f0-abad-5b6cef724715 | REFERENCE: Project Drawings / Drawing Register
| note | dd72b72f-7bda-4541-ac6e-a10c5e36a671 | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
| note | 8395d893-c2b9-4a46-90e7-8761fce36165 | METHOD: Document review
| note | c3fc3c50-4b45-4310-b3cf-00f5d8a246f2 | FREQUENCY: Prior to commencement of works
| note | e0adde2e-f327-415b-9444-2469b2fda7be | CATEGORY: AP
| note | c07d0ea0-119d-46a1-b9f0-7136a4a8211b | RESPONSIBILITY: Site Engineer / Site Foreman
| note | 5d44232b-2b75-43ad-a0e4-c4b9cbf080d5 | VERIFYING DOCUMENTS: Latest Revision Drawings
| textbox | 66e251f9-8195-4abe-aa28-5b00c9296c45 | Date Completed:
| checkpoint |  | 2.2 Submit Mix Design - Cement treated crushed rock (CTCR) mix
| note | d6aa6649-b2da-4620-9a31-5d08a1734910 | REFERENCE: VicRoads Spec. Cl. 815.05
| note | 93d2b346-c8f8-4afe-b9fa-eaef37df5960 | VicRoads Spec. Cl.306.04
| note | 1dc7abee-23e5-4cb3-8c30-89fb71862957 | ACCEPTANCE CRITERIA: Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
| note | f54537cf-912e-43de-b686-2e227d358ebf | CTCR shall comply with Section 815 & 821
| textbox | e0bec2fb-ebb9-4303-a9aa-a9d03f67de66 | Team Binder Approval Number:
| note | 65a419c6-4271-404c-9aff-cbdf87f9167a | METHOD: Document Review
| note | 5e48716b-6f13-4ea4-b74b-d24dd747535f | FREQUENCY: Once per material type, prior to commencement of works
| note | bd2013d6-bf4f-4b28-8286-ed0792b8d47b | CATEGORY: HP*
| note | 44e90819-e074-496c-82c5-feafa484bdcc | RESPONSIBILITY: Site Engineer
| note | 49c9c758-32c2-4e62-9bb8-b41e41e8188a | VERIFYING DOCUMENTS: Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
| textbox | 98b6d478-bbb8-4426-ac55-9284aa6ca98d | Date Completed:
| checkpoint |  | 2.3 Survey Set-out
| note | b1e7eeb6-959b-48cb-a8b6-ed0497b51223 | REFERENCE: IFC Drawings
| note | 06ca5bec-ae5b-4507-aadc-e9f4762a3866 | ACCEPTANCE CRITERIA: Survey to set out works in accordance with IFC Drawings
| note | e8d3db0b-7c08-4bb1-aa3c-51b6c58f0eff | METHOD: Measure Visual
| note | 5f8968e3-0c01-4007-a4ff-4ca663756b87 | FREQUENCY: Each Lot
| note | 75545377-285f-42dc-a092-437ba6da840c | CATEGORY: IP
| note | 15d0210c-36a9-4fe1-9b12-5b83a14ba8e2 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | eb87b6ba-da71-4bb3-8f30-9f1735bd6a60 | VERIFYING DOCUMENTS: This ITP
| textbox | 3dc9c473-e006-4f92-8e0f-e9fce36e629a | Date Completed:
| checkpoint |  | 2.4 Previous Layer Level Conformance
| note | 41372cad-80d6-444b-998e-7bea742372c8 | REFERENCE: IFC Drawings
| note | 2083334b-8ea7-4c0b-8895-7193f30c0680 | ACCEPTANCE CRITERIA: Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements.
| note | 0c1f7b05-88ed-4a87-b5e6-bd9b78bb56fd | Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved.
| note | 58ebb9a3-0ab9-4067-bee5-66546f7913a9 | METHOD: Document Review
| note | 74b76423-b4e8-42aa-b5f4-fc17283c6e43 | FREQUENCY: Each Lot
| note | de8b71ff-91ff-4c0b-aec3-87e6631fb9c9 | CATEGORY: IP
| note | 2730f78c-1ca3-4b10-b276-fb0bb9da0b7b | RESPONSIBILITY: Site Engineer
| note | 625f1b7a-2713-4bf5-8dbf-f9f092b60132 | VERIFYING DOCUMENTS: This ITP
| textbox | 6a837e20-4808-439f-bd46-e81b80612bc9 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.1 Lot Size
| note | 63538342-270c-4d2d-b926-0fa4f32c60c4 | REFERENCE: VicRoads Spec. Cl.306.03(b)
| note | e46ccc6c-886d-4271-b256-96476df07a8e | ACCEPTANCE CRITERIA: The maximum size for a single lot shall be considered a single layer of 4000m2
| note | b01a344a-ff07-4863-a61b-d9297cfee136 | A lot shall consist of a single layer of pavement material placed on the same day
| note | ece984e6-862f-4378-958a-8b0248043f78 | METHOD: Site Inspection
| note | 0dd8853f-d058-4aca-9f57-d6498039d058 | FREQUENCY: Each lot
| note | eaaef7a4-826f-41a2-8843-36a94430efa2 | CATEGORY: IP
| note | 55b82171-d8e0-477d-a002-c91e0e125fb3 | RESPONSIBILITY: Site Engineer
| note | 33243bac-80ff-4a2e-b1af-9db3242e831b | VERIFYING DOCUMENTS: Signed ITP Attach: Lot Map
| textbox | 61be7c30-53da-4343-a555-1fe911c58dd4 | Date Completed:
| checkpoint |  | 3.2 Hold Point - Alternate Binder (if applicable)
| note | 04271575-6a54-4efa-bcef-29cc04dd1328 | REFERENCE: VicRoads Spec. Cl.306.09(a)
| note | 2a8f074f-7dfa-4163-8f44-c9dadc571572 | ACCEPTANCE CRITERIA: If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method.
| textbox | e7dd218f-32e0-44fd-a48e-3c5114641f3b | Team Binder Approval Number:
| note | d690dfc4-013b-447f-8fed-0bfb6ecc0778 | METHOD: Site Inspection
| note | 3aab17ce-9115-42a1-9b3b-9c1a1e63db3d | FREQUENCY: Once per material type, prior to commencement of works
| note | e4f09d5d-8887-4add-b8a5-6b437e37231a | CATEGORY: HP
| note | c6eee93c-16f1-41b4-b29b-a8f5e9139fcd | RESPONSIBILITY: Site Engineer & Nominated Authority
| note | 1c7e0e7c-0ead-45d9-9d8f-2b9c2a533a05 | VERIFYING DOCUMENTS: Issue to TeamBinder: Test Records
| textbox | ce7a326c-3dd7-43bb-bf96-662254f1df57 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Transverse Joints
| note | 167959fd-36de-4dc9-8517-40ed18e5be3a | REFERENCE: VicRoads Spec. Cl.306.08(a)(c)
| note | 4fdfbbdd-81b3-41c0-ac02-d0357f0de785 | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
| note | 179f139d-b502-44c4-95c3-b8e48b8e52b1 | In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m
| note | 2a66a615-5a88-483b-b8b8-aad11760b152 | Transverse joints offset from one layer to next by not less than 2 metres
| note | 6dc614a7-a104-4d78-a5af-e3dfc6987a9c | METHOD: Site Inspection
| note | 5f4303e8-b0f1-49d6-b5dd-4fbd36c71e20 | FREQUENCY: Each Lot
| note | e91fae06-2ba0-4a23-b577-9f17e8ea63e8 | CATEGORY: IP
| note | 8f3407c1-3a0c-4107-b1ba-8294e9935a21 | RESPONSIBILITY: Site Engineer
| note | 3dd61d92-ae7b-4537-adf8-a43a2c344c04 | VERIFYING DOCUMENTS: This ITP
| textbox | abd9b302-3a4a-491d-b918-b199aba28cfc | Date Completed:
| checkpoint |  | 3.4 Longitudinal Joints
| note | 553d2830-0f0a-479b-b03d-ee46bd67c0b6 | REFERENCE: VicRoads Spec. Cl.306.08(a)(d)(e)
| note | c477b70e-a352-4ddf-a5cf-86187a43bcd9 | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
| note | 88c8bdba-94c4-4d02-a519-bf7f495a4355 | Longitudinal joints offset from one layer to next by not less than 150mm
| note | 271ee25a-7c97-4613-852f-b6d8111e798c | Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
| note | dbc03b76-e8f3-44ef-be59-2310b837ae7f | METHOD: Site Inspection
| note | 9afecc27-7fee-439d-b14a-5d8d303aa3b2 | FREQUENCY: Each Lot
| note | 826007af-f4c5-4aed-83b8-ce5e8846f655 | CATEGORY: IP
| note | b9714283-c4a0-451b-8c33-86312250769d | RESPONSIBILITY: Site Engineer
| note | 0d0b0691-70dc-4c95-84de-ae8f201cf71b | VERIFYING DOCUMENTS: This ITP
| textbox | bef842fe-97a6-4e20-852e-68a6c1f09775 | Date Completed:
| checkpoint |  | 3.5 Layer Thickness
| note | 629f0c74-f5a6-4fe0-80fe-94efd4928ac6 | REFERENCE: VicRoads Spec. Cl.306.11
| note | c1fdb1c8-7839-42df-a048-fd7e54fc4b51 | ACCEPTANCE CRITERIA: Compacted layer thickness should be not less than 100mm and not greater than 180mm.
| note | 59f156f6-6cf1-48f1-898c-52be53496139 | METHOD: Site Inspection
| note | 36f46112-ac0b-4bd4-8b68-e686f96125c6 | FREQUENCY: Each Lot
| note | 77214094-3346-4817-bac9-47a1901b5f04 | CATEGORY: IP
| note | d2a89428-6acc-4c32-b720-3a0aca8c6d4f | RESPONSIBILITY: Site Engineer
| note | a7857a62-35da-4354-9deb-7c9d5c613afd | VERIFYING DOCUMENTS: This ITP
| textbox | c8b1dd13-e7bc-4d08-84d3-caee8c1c80a5 | Date Completed:
| checkpoint |  | 3.6 Delivery, Placement and Working Time
| note | a487c7ba-57b3-4bc6-b1f4-a9a0ec390f2f | REFERENCE: VicRoads Spec. Cl.306.07
| note | e344c299-4946-4180-b109-f1feaf0f3720 | VicRoads Spec. Cl.306.09
| note | 13c041ab-ee93-4d7f-b20c-5ac76b733748 | Table 306.091
| note | d4ced295-a451-43b7-8689-ec4f14d47454 | ACCEPTANCE CRITERIA: Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specification requirements.
| note | 7227fc32-0ef2-4acb-9dc1-30179f94ce85 | Working Shall Not be more than specified for each binder:
| note | 8b4d7931-470d-4883-bd4d-e8a67b2c2a78 | Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept)
| note | 31c4a79b-7ce7-46d2-ad1f-518b20a38ebd | Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept)
| note | 0f344e0f-3897-4d0d-8d83-795c67400457 | Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept)
| note | 2e261089-6f09-4f08-8f99-180afe7a83e4 | METHOD: Site Inspection
| note | 50feae44-435a-4165-a136-1238101ba7cc | FREQUENCY: Each Lot
| note | 3a01bbac-f743-4c6d-8ed9-854533093416 | CATEGORY: IP
| note | cec13b99-561a-4228-beb4-ffcb7b9b8131 | RESPONSIBILITY: Site Engineer
| note | 33e5b154-79cb-4f75-93bf-e89a44973dfc | VERIFYING DOCUMENTS: This ITP Attach: Delivery Dockets
| textbox | a69b18b0-32c5-4131-9188-328f464bbebb | Date Completed:
| checkpoint |  | 3.7 Water
| note | a6bf891d-0980-49c0-8563-171c94956cf1 | REFERENCE: VicRoads Spec. Cl.306.06
| note | 4f98664e-0878-4ca2-85df-65a5b0706c9d | ACCEPTANCE CRITERIA: Except for the purpose of curing, no water shall be added to the cementitious treated material.
| note | 542381d8-628c-443d-8b15-632fc79ffffb | Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
| note | dca59e0d-361f-4d17-84e5-bca8d7a8ab05 | METHOD: Site Inspection
| note | 1b5fb575-9730-424a-a643-27a2d32b18be | FREQUENCY: Each Lot
| note | 6a08945f-a12f-4673-b6a7-9e8904209efe | CATEGORY: IP
| note | 00073f44-7b0e-4a14-8f3d-ce7ae62c4723 | RESPONSIBILITY: Site Engineer
| note | c47bb4d5-162b-48b0-bf01-e4c530d23314 | VERIFYING DOCUMENTS: This ITP
| textbox | 8b97d2cc-8b8e-4faf-9095-492dff8fddda | Date Completed:
| checkpoint |  | 3.8 Cementious binder content & UCS requirements
| note | 9d76b1bb-12fc-436a-83cb-bc2f9f543312 | REFERENCE: VicRoads Spec. 815.10
| note | 41eb5000-10e3-404a-8c51-e14d08ade888 | ACCEPTANCE CRITERIA: Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7days
| note | 39563927-8177-4c5e-85f2-a8b57921a4fa | METHOD: Testing
| note | 8422961c-a963-42e6-bff9-7f95d0efa673 | FREQUENCY: Each Lot
| note | ba79eb18-36ab-40ea-b076-350f296ec50d | CATEGORY: IP
| note | bc328067-79e9-4b48-8062-73c39e6262c2 | RESPONSIBILITY: Site Engineer
| note | db02a584-bf89-4bb5-b7d5-d400542ccf74 | VERIFYING DOCUMENTS: Test report
| textbox | f9293f8d-c13d-4833-a062-c95f9a59b1a0 | Date Completed:
| checkpoint |  | 3.9 Compaction - Modified Compactive Effort
| note | 1fb10397-3979-413f-a0c0-a1d0cba01fad | REFERENCE: VicRoads Spec. Cl.306.05
| note | 35f2ee87-68b7-43f8-963e-88b87fd377de | VicRoads Spec. Cl.306.09(a)(b)
| note | 707c6550-ab91-4a65-8d34-7e2cf11babb5 | ACCEPTANCE CRITERIA: Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content
| note | 8220c73f-e504-42a5-887d-2456e2e872ec | Scale A:
| note | 89036ea5-52f6-439a-a653-427ff3fd8dd4 | No. of tests per lot shall be 6
| note | 97389888-e218-4d2c-a84f-2593a35ea271 | Characteristic value of density ratio > 96%
| note | 28eb5c90-5e73-40dd-b8ca-f8474fcb9981 | Scale B:
| note | 68727f2b-3566-406f-ad9a-8c07d977a425 | No. of tests per lot shall be 3
| note | a08a9748-6a44-4fe0-9a84-dd8f8ccf373a | Mean density ratio > 96%
| note | db4ee612-4e34-4f1a-8dc4-0ae0257d3098 | METHOD: Document review
| note | 7880b474-619f-4c00-9d37-d8e948946f74 | FREQUENCY: Each Lot
| note | 8bac1c2e-08d3-412d-b5f8-16a3d83e9296 | CATEGORY: IP
| note | a564f8af-7d8a-41cf-9fd6-28c7cdc4e8e5 | RESPONSIBILITY: Site Engineer
| note | b6b9bd33-78a8-4431-919e-6e31ad8b5792 | VERIFYING DOCUMENTS: Attach: Test Report
| textbox | 000bad02-ef61-496b-9bf4-f1ea2d690609 | Date Completed:
| checkpoint |  | 3.10 Test Rolling
| note | ea7b1da6-cd10-42fb-af6a-7ac124ac3fbf | REFERENCE: VicRoads Spec. Cl.306.10
| note | ab64ec9e-cbe8-471d-94fe-323ee37c3c2e | Table
| note | 63288f04-d990-46ae-8be6-ace1747b28bd | 306.091
| note | 9c511e7a-b64e-4c27-82cd-412f777360c0 | ACCEPTANCE CRITERIA: Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
| note | cd947135-fba8-4e3f-92ee-624913da8083 | METHOD: Site Inspection
| note | 3b5f5636-ba0b-4c69-b5e9-c2b4688154f5 | FREQUENCY: Each Lot
| note | 562d2bc8-6912-4225-b0bb-c28d65d67442 | CATEGORY: HP
| note | bdcbf170-b543-4021-9255-769b297b4c48 | RESPONSIBILITY: SE, NA
| note | 2a55e6e4-bf94-4e54-a373-81ddb889bb44 | VERIFYING DOCUMENTS: This ITP
| textbox | fdbe01f8-aad5-406a-a6af-75a037d8c5dd | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post Construction
| checkpoint |  | 4.1 Surface level
| note | e827da59-3913-4d03-a746-4544eac31297 | REFERENCE: VicRoads Spec. Cl.306.03(c)
| note | a7708a7d-2d90-425b-aced-52957e3526f2 | ACCEPTANCE CRITERIA: No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase
| note | a512571e-68a7-41a2-b1eb-ceb529c26819 | METHOD: Document review
| note | 6293b549-1356-4d02-bd09-a6ed271454e2 | FREQUENCY: per/lot
| note | 984fa07e-9c92-4af2-8252-b33b31db01a4 | CATEGORY: IP
| note | 34e0fc64-d364-4825-9904-0d3a8ee23657 | RESPONSIBILITY: Site Engineer
| note | a995b1c9-1a61-43ee-9b3a-a2ea81f2db78 | VERIFYING DOCUMENTS: Attach: Straight Edge Verification records
| textbox | d4c6cb2e-21a1-4d49-ad6d-7645f61d508f | Date Completed:
| checkpoint |  | 4.2 Survey Level
| note | 6f6e4ba1-e5d9-4f62-8fff-e94873772cb0 | REFERENCE: VicRoads Spec. Cl.306.03(b)
| note | 936fb76a-19f2-46b4-bffc-9c798ffee127 | Table 306.032
| note | c495b62d-b253-4c18-bd44-01a1842adfa5 | ACCEPTANCE CRITERIA: Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
| note | 551dec16-f21e-4169-9c3b-beaf51f3189a | Scale A:
| note | cb507e82-30db-46ea-a6df-2dadbde099af | Subgrade:
| note | 75119037-0500-4b73-bca2-c574e2a36aa0 | Mean value of all level readings to range between +5/-15
| note | 27695619-e5d3-4be0-b247-84d0befa509d | Standard deviation of all level readings to be less than or equal to 12
| note | 02e97248-b8d1-4efa-a4f3-b6beab6d08fb | Subbase:
| note | df48c307-32b8-4dd6-a59b-5946845ecc1d | Mean value of all level readings to range between +4/-8
| note | a935054f-7865-459e-8511-bbd518b1ecce | Standard deviation of all level readings to be less than or equal to 8
| note | 43c5cd5f-d446-425f-b384-2b23a55377cb | Scale B:
| note | f7c627b9-08a2-4bda-885e-4f9fd8ed2619 | Subgrade:
| note | 211bf883-3256-4976-a664-637491a28369 | Mean value of all level readings to range between +5/-25
| note | 3211777e-50be-4b32-b635-bd4695cb2b82 | Standard deviation of all level readings to be less than or equal to 15
| note | 88a55862-9d49-494b-ae5d-7d5a62ca2a79 | Subbase:
| note | 34d51f82-7531-4e4e-80dd-c3e766edb9ae | Mean value of all level readings to range between +6/-12
| note | 8e5eb8a0-b10f-4f05-83dd-9f6dbe7a8cff | Standard deviation of all level readings to be less than or equal to 13
| note | 399f9c60-73b4-4b5b-9c5c-9a8aefc8d8c6 | Scale C:
| note | 4111c922-9466-4bfc-b5f6-197d9dbfe4a9 | Level Tolerances
| note | aa8077bf-ba1d-4851-a940-71776eb20fe7 | Subgrade +15 to -25mm
| note | 78918539-961b-45c7-b479-66bd6d5ad031 | Subbase +10 to -25mm
| note | 60eda570-ea97-4c66-a6a3-b313cb3a1b6e | METHOD: Document Review
| note | 0c237166-9768-4195-9b99-420300eb4b22 | FREQUENCY: Scale A: 80 points per lot Scale B: 40 points per lot
| note | 2b3ed00f-3949-43e7-8e9f-cea308ad3e2b | CATEGORY: SCP
| note | 8d9306a4-354f-4b71-8c87-23a7708a2b8b | RESPONSIBILITY: Site Engineer
| note | 2600c9ef-46ef-44bf-9086-0b52ba65373a | VERIFYING DOCUMENTS: Attach: Survey Report
| textbox | 5d91d10a-54ca-4c50-b59f-c6261a561fed | Date Completed:
| checkpoint |  | 4.3 Non-conformance Report (NCR) Closure
| note | ee8ef630-1088-4eba-8b4e-428023b491b5 | REFERENCE: MRPA Quality Management Plan
| note | acc3e638-56ec-4e1b-946d-077d038afc06 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder.
| note | 4e85cd05-8715-4045-95cd-d1d763499fe4 | METHOD: Document Review
| note | c98df145-a099-457d-af20-e8d77fd2870b | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 0f67e618-377b-40a7-81c5-b434a626f9f3 | CATEGORY: HP*
| note | 5b05ca21-b2d1-4cd0-bcab-b08a09568b1e | RESPONSIBILITY: SE/PE/SPE
| note | 41d5db0b-102b-4adf-889a-aeef3ede2aef | VERIFYING DOCUMENTS: This ITP
| textbox | 69517db4-d39f-411f-83f6-02aed8fc8f92 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | b4110418-6bd3-4c52-a7b4-866ebbd8bca6 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | d4f37320-fe48-4b9d-a3ec-b863495e9346 | Name:
| textbox | 13b513f0-05d9-49c0-8f9b-99bc8ac836f4 | Position:
| textbox | ebbc04ab-127a-441f-88ae-4e3ca2ce31cb | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1 | itp | ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1 | 075c1554-a764-4d0b-83f6-21ec909014a6
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | df6e5860-a8c0-46ef-b0e9-b50c710b3c3b | Document Title: ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding)
| note | 27d7c09b-0a30-4e4c-989e-5afb140c43b8 | ITP Description: Footpaths & Shared User Paths - 1 (Set-out & Bedding)
| note | faafacbc-e50c-4c0f-b6b2-7b90613ff3fb | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | d8278300-f0b1-4c81-9338-f775899aaf3c | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 0f4c47f3-c9d9-4a49-ac0b-8509bd499d54 | Revision Number: 1
| note | 8946eaba-5d08-4961-81cc-0b43e58ddd7a | Revision Date: 22/06/2020
| note | 6d4e6f6f-dd7c-47fc-9926-57d8c2635706 | ITP created by: Mike Freeman
| note | 616fd8e1-ec6f-4b95-bbda-e651f0a34138 | ITP approved for use by: Mike Freeman
| note | 64e7f2fc-2bca-4aa9-8ec2-9cc0813eb098 | 1.1 VicRoads Section 304 August 2013
| note | 1b6fa4b8-0681-4156-ba1e-a98d76274d6a | 1.2 VicRoads Section 703 June 2018
| note | dfdc0725-7308-4a1e-a638-37cf8ea5dc41 | 1.3 VicRoads Section 812 July 2016
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Bedding Material Placement & Compaction
| note | bc4fe215-0219-449d-a91e-ee6360be4dc8 | REFERENCE: IFC Drawings
| note | 79187ff6-ab8e-4d19-9ad3-d4d07fa22eb2 | 703.21
| note | 4334864a-8fb1-4de1-b0cf-06f1f09eafd3 | 812.04
| note | 426a36d7-85a7-47e4-94ab-3183b01715c8 | ---------------------------------
| note | da905385-af2d-4abc-b724-6c10eeddbfa2 | ACCEPTANCE CRITERIA: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
| note | 348c7dcf-aaeb-4db1-bd0c-6761a6ff3914 | Material is registered with VicRoads in accordance with Code of Practice RC500.02.
| textbox | 665f0261-b7b3-4fe1-81e9-d6a62b85c8ca | Enter: Teambinder Material Approval number
| note | 15e0c0ab-0fbf-4f9a-b4af-aa3b35530872 | ---------------------------------
| note | f592d3ca-a7af-4348-9419-4d04767791a1 | METHOD: Document Review
| note | 70ca8d7d-7ffd-4bbd-badc-8091e6b0d310 | ---------------------------------
| note | 0f1f3997-762c-4123-a1e6-19e32819a498 | FREQUENCY: Once, for each mix design, prior to placement of material
| note | f00abc87-b680-4342-b344-24cc4c0af82b | ---------------------------------
| note | f10b7c4e-903b-43b8-a4d8-ad1196d5c1a8 | CATEGORY: HP
| note | b506bca6-911a-4154-822c-c9b5500fedfe | ---------------------------------
| note | 293f46f5-d825-433a-98e5-1772a0fd8c7a | RESPONSIBILITY: Nominated Authority
| note | 96f529cf-0739-40cb-9a71-559ac3f60d50 | ---------------------------------
| note | 7c496635-c50f-4af1-94d7-5728f6f2e299 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | e7482285-0ce7-4973-b199-65c844e671dd | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 3.1 IFC Drawings
| note | 69ecf87c-28fc-4ba6-816f-978f9c52ed22 | REFERENCE: MRPA Quality Management Plan
| note | 6c0ccb2b-9618-40ef-b232-7257090c73a9 | ---------------------------------
| note | 342e6d73-d55d-4450-8870-a96ac50c6abf | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | e5c166dc-05c7-48f0-9b57-3addbeb6bdef | ---------------------------------
| note | acf5d695-d192-4f95-a872-6c47f1c166c8 | METHOD: Document Review
| note | 45b0dba1-842f-4855-9bfb-044f7d535684 | ---------------------------------
| note | 3993ea00-b73e-475c-b5a4-90dcf18aac19 | FREQUENCY: Prior to starting Works and at regular intervals
| note | 085f8423-1603-4955-87d1-a4a76775daa8 | ---------------------------------
| note | d928c19f-94aa-4b52-9e35-7199c7cbe44a | CATEGORY: HP*
| note | b891ef99-907b-4152-9955-99ec167bfdb6 | ---------------------------------
| note | d0d4fd6f-c335-460a-835c-f5ecaafcf571 | RESPONSIBILITY: All
| note | eea84289-3282-48ea-93b5-b69d813cc177 | ---------------------------------
| note | ab9bf456-097c-41c0-8ad9-c302a9d32f25 | VERIFYING DOCUMENTS: This ITP
| textbox | 4bf3c3fc-660e-4667-8357-db3926f88cb6 | Date Completed:
| checkpoint |  | 3.2 Survey Set-out
| note | 3063a7db-e5fe-4a32-9f4a-befdfb9af0a4 | REFERENCE: IFC Drawings
| note | 3c9380ae-11c0-4841-b8f6-c59724371215 | 703.17
| note | dc70cd36-6206-4070-9a4b-e60806e8868e | ---------------------------------
| note | 70f32943-fbae-4e6b-954e-95e2bed83448 | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
| note | b50817f9-1a4f-4f8a-aa8f-6f35a0c49782 | The Nominated Authority will review and confirm the set out.
| note | ef555c11-6895-44a6-90a3-f9ea6e5966d6 | Attach: Survey Report
| note | e3ac6cc6-54cb-4789-b8eb-b536058da9f2 | ---------------------------------
| note | 957b28f4-e258-494a-af7a-5f635d12d2e4 | METHOD: Document Review Measure Visual
| note | 812fa366-b719-4dee-a4ee-c977596f64f5 | ---------------------------------
| note | 7ee318da-fd14-4018-8aac-da78465230a5 | FREQUENCY: Each lot
| note | b5fd7453-4a26-446e-ba06-07a423d3508f | ---------------------------------
| note | 3c80f156-2e98-4535-83c7-7eb273c362fd | CATEGORY: HP
| note | b226fc73-f179-4ebe-833a-734f0aeb8583 | ---------------------------------
| note | 369cbbe8-1cd0-4071-a7de-bca3dba1591f | RESPONSIBILITY: Nominated Authority
| note | f619cd9f-10ed-4e6d-a9ec-abd8ce89e377 | ---------------------------------
| note | 7f31d847-cf4d-469f-8638-d6ecf92e746b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ae2d4c00-0d81-4ffd-8725-796325c1c9a2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction Activities
| checkpoint |  | 4.1 Site Clearing & Grubbing
| note | 55861937-38f9-441d-83fd-5b7796ee9673 | REFERENCE: IFC Drawings
| note | dc10a2c4-96e2-400b-a97d-eb4f56cd52e2 | ---------------------------------
| note | 5f2597d6-4d11-4a22-a714-a41d07ecbc91 | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
| note | 7e5efc49-a85f-4969-acca-0cd2c01e79fa | Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
| note | 4597a426-fc15-46e7-9cc2-cd2b30039d80 | ---------------------------------
| note | 39b4b61a-98dc-4721-976f-669d1afa9914 | METHOD: Document Review Visual
| note | f8f4535a-25b4-4541-9787-f8d52ce099f2 | ---------------------------------
| note | 4a59452f-01a0-48c8-81a7-d9cff8c485e5 | FREQUENCY: Where applicable
| note | 4f7b4b37-f9ec-4bbb-b7d8-b188870dc15b | ---------------------------------
| note | 81163045-c097-45a2-9dc5-2a1e58617765 | CATEGORY: IP
| note | 27d8c5ca-8069-431f-bda7-e5a7e3cc579c | ---------------------------------
| note | 80cca4b1-62f6-4200-a8f6-ce12f3111425 | RESPONSIBILITY: SE/PE/SPE
| note | fd652cf5-2461-4502-9f56-7d2cf2a30fab | ---------------------------------
| note | 2387c339-ee85-4381-812d-7374cb181db8 | VERIFYING DOCUMENTS: This ITP
| textbox | a4890e36-66b4-4649-9b00-320bb5ca39a3 | Date Completed:
| checkpoint |  | 4.2 Excavation
| note | 8999c62a-ed2e-4b98-9460-ccea34398f9b | REFERENCE: 703.20
| note | 73d8a76a-fd11-411a-8e4f-892127b7644f | ---------------------------------
| note | 0ec65509-03e0-4e38-bdf7-5f1de92ec021 | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
| note | 7c51c6fe-a593-4ca4-8eb4-8ab101ddff1c | Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
| note | 3a1b6e62-c1c2-4e80-a454-4c79b9931ddf | Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
| note | 4421b1dd-0fdd-4d54-9b9e-c387cc8b3e0a | ---------------------------------
| note | 5fde335c-932c-4b88-8e98-bc290c276264 | METHOD: Visual Measure
| note | a40d4976-83a6-4cc1-b911-a1c6a1d4d0d5 | ---------------------------------
| note | 4937a5cd-b9f6-49e8-835a-ea25ce8e8c2c | FREQUENCY: Each lot
| note | 45555d2b-38dd-4fab-8122-6672ee02c1e1 | ---------------------------------
| note | d280efbe-09a5-4289-b18d-4942a81ff446 | CATEGORY: IP
| note | 050584fa-d4e7-4baf-8fe1-0c4eecc501b7 | ---------------------------------
| note | 8615a753-9b8c-491d-b38d-84d94e47bdd3 | RESPONSIBILITY: SE/PE/SPE
| note | b4df9c9a-cc8d-4303-bd77-88a5adb956cf | ---------------------------------
| note | 2683dcd7-388f-46c9-8290-8456ddf06b6f | VERIFYING DOCUMENTS: This ITP
| textbox | 506d0cee-c13d-4e32-86fd-6ac0b2db2af0 | Date Completed:
| checkpoint |  | 4.3 Pavement Thickness Increases for Crossings
| note | b12a31bd-a6cb-4a09-be11-1af0dd269677 | REFERENCE: IFC Drawings
| note | fcab9874-8bd7-4ff2-9f3c-946c17a64c24 | 703.16
| note | 5a011c9d-6884-46ae-b0f1-daa2b7574771 | 703.24
| note | a89f04d4-e7dc-4b71-a43a-49ef471fa7d6 | Relevant Council Drawings
| note | 4fb305ab-89da-47a8-a0f7-1ca975ba7f28 | ---------------------------------
| note | 7f4640aa-7c10-4897-86d5-6fdaed4602d7 | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
| note | e3524cdc-772c-4a61-b13b-88a4f2f0150f | i. Pram crossings
| note | 1045dffa-049d-43a9-92ac-1138536bd970 | ii. Vehicle crossings (residential and/or commercial)
| note | 82e27c84-14f6-4b5c-a2ff-05c21b4f71d9 | iii. Established / existing mature trees
| note | a2a1ce74-a418-44ae-bc6c-6523485d2720 | Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
| note | 7ce2536a-ff4b-451b-b0f3-dbafd40d0fa0 | ---------------------------------
| note | 32580380-6e18-4a47-acc0-963108e25c31 | METHOD: Visual Measure
| note | 661f97f8-64c2-421e-8b1c-1d30fa28230a | ---------------------------------
| note | 76cfb9f7-84fa-4410-b754-5c35a8b8b3cc | FREQUENCY: Where applicable, each lot
| note | 55b9df0d-3ce6-4608-88a4-ffa50726022a | ---------------------------------
| note | 623f3320-c922-41fa-9bd4-6ebe7ed75b85 | CATEGORY: IP
| note | bc21ca8e-630b-4daf-9b25-0ba872f17d36 | ---------------------------------
| note | 9a933599-1e4a-4c53-8f3b-ed96948e971e | RESPONSIBILITY: SE/PE/SPE
| note | 4c9a4306-4398-41d7-b5ca-6d8d75e7b11e | ---------------------------------
| note | 2765e8ae-c2aa-4232-9bfd-8936e8a1d96a | VERIFYING DOCUMENTS: This ITP
| textbox | e9af31dc-6795-4b83-a02c-f9a94de36341 | Date Completed:
| checkpoint |  | 4.4 Bedding Material Placement & Compaction
| note | 626711a8-f4fd-46d9-a06d-4517f13a7e03 | REFERENCE: 703.21 304.05
| note | 336e2105-be4e-4232-8dc9-a076f95f74db | ---------------------------------
| note | f572a752-326a-42e9-90ef-5f0b4bced4a3 | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings):
| note | c2237d01-24b1-49c8-b0f7-73febb72fb43 | Shared Use Paths: ≥150mm thick
| note | 6a3b1382-101f-4ce1-ba34-f7bb291e8d0c | Footpaths: ≥125mm thick
| note | a853100d-2c7a-41c7-a588-a989a6df2d25 | Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
| note | 1a34b6d5-14ea-48a0-a468-edf3f0a9850c | The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
| note | 51d94565-8a7e-4fe9-872e-d08ac495a902 | All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
| note | f8e0b47c-ddbc-4c57-b81d-dd541488e3e3 | Attach: Bedding Material Delivery Dockets
| note | 60832e5c-cfe3-4c2f-960d-7e327e6aa627 | ---------------------------------
| note | 97b5ddee-82e5-49ec-b734-36c14bcf0e95 | METHOD: Visual Measure
| note | aaba2828-d401-4b8e-ab5f-0a402e7615ee | ---------------------------------
| note | 780c99f2-efd8-4189-afc7-3f94e7432845 | FREQUENCY: Each lot
| note | cf2a94d5-8ad6-4054-9f6f-71d709a0d5a8 | ---------------------------------
| note | cbe51c9f-1f3a-42c6-9c0a-49b784bc3de3 | CATEGORY: IP
| note | 767bb7ae-5f27-492e-a165-3da4bb2d6da0 | ---------------------------------
| note | ee8fc03d-92e5-41c9-bbec-993c90b5fb7c | RESPONSIBILITY: SE/PE/SPE
| note | 108f1027-80ae-42fc-b66a-9a363b20827f | ---------------------------------
| note | cf5c7e38-e1e7-4b3e-ba89-e306419fc8ab | VERIFYING DOCUMENTS: This ITP
| textbox | 214e1597-82ab-4686-961b-75ed293e3f7a | Date Completed:
| checkpoint |  | 4.5 Shared User Path - Compaction Testing
| note | a3ff0fad-29c7-4a73-be5c-77f40472af71 | REFERENCE: 703.21
| note | 3b760cc1-2114-4bd0-a273-897907a217a5 | 304.08 (a) & (b)
| note | b0f12faa-1068-4916-8e88-18dd8c558af6 | 304.11 (a)
| note | cbf87a36-d277-4490-8f3d-de287c98c616 | ---------------------------------
| note | 9f8e8a9f-0f7e-4f02-b475-a8f909bde41c | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
| note | 594026f8-a821-467a-8de2-f9e46921c0c8 | Scale of Surface Level Measurement = Scale B
| note | 225b8762-68dc-4bed-899b-0972dc62f5a2 | Optimum Moisture Content = ≤85% (1 test)
| note | 747783a6-0679-453b-becf-b07fdf0401a8 | Characteristic Density Ratio = 98 (6 tests)
| note | cea8647b-594c-4fd8-948c-9e4041e2adc9 | Attach: Moisture Content Test Results
| note | e6986921-c87c-43e7-89bc-e0e086587e63 | Attach: Density Test Reports
| note | 8958e8e6-ff5c-40b0-9752-088833e64c05 | ---------------------------------
| note | 552a41ff-bcf4-447c-bfe2-c41e881f7e16 | METHOD: Document Review Visual
| note | 745b26df-6b1d-4529-8e1e-03c4ba3392c9 | ---------------------------------
| note | df9fd800-0b2f-409a-ba13-82eea96bd546 | FREQUENCY: Where applicable, each lot
| note | 80e2cfde-147e-4ca3-8817-42f6ff4954e1 | ---------------------------------
| note | 02b7a91d-c7ad-4c52-ac57-2eb81d669e8d | CATEGORY: IP
| note | d560dce8-1918-4a62-852f-86884521c6ad | ---------------------------------
| note | 233a1d36-0585-42ae-b34f-100bb282347e | RESPONSIBILITY: SE/PE/SPE
| note | 7e4c6bc6-9be7-4e0c-8c6e-7a6f0915862f | ---------------------------------
| note | 8991567c-e772-428b-abf2-d6d470302535 | VERIFYING DOCUMENTS: This ITP
| textbox | 823303ae-52d9-45b6-9d79-4e05c75619a9 | Date Completed:
| checkpoint |  | 4.6 Shared User Path - Shared User Path - Proof-rolling
| note | caeb759e-334c-45d8-9527-82ffc167fee0 | REFERENCE: 703.21
| note | d1cf5d98-d554-413a-82bd-ac0ea15ef8b9 | 304.08 (b)
| note | f7fa7661-7d05-47ef-836a-fb7d69f34afc | ---------------------------------
| note | 9dfae3c5-83c5-4f4a-b672-47e832bc85a5 | ACCEPTANCE CRITERIA: Bedding material to be compacted and proof rolled before any construction.
| note | 882ec4cb-59e2-4bde-9855-44c877ad6af6 | Withstands Test rolling without visible deformation or springing.
| note | c6931603-28d9-48ea-80fd-b7424ba8c358 | ---------------------------------
| note | 8a9fb31e-bdf6-49de-b904-d4371bea56f2 | METHOD: Document Review Visual
| note | 18a70d0e-9b42-4885-882c-c61f77662b5c | ---------------------------------
| note | 81d2f4a1-fdd8-4866-a5df-8ca95d821561 | FREQUENCY: Where applicable, each lot
| note | 67723b50-92e9-4f2b-a02d-a43fd95231eb | ---------------------------------
| note | f16e6e32-310a-4f03-bd9b-b1a0754a9575 | CATEGORY: HP
| note | 98a6e3af-5032-48f8-80fc-b9fa36416984 | ---------------------------------
| note | 849344be-6e48-4e06-b7bc-0cde4cfb22f5 | RESPONSIBILITY: Nominated Authority
| note | 6200bcbe-d259-4098-b439-23d5684c5277 | ---------------------------------
| note | 5f6db2b5-a02c-4fcb-ace7-417361f1c7b0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | a9b3b2f1-d813-4ab5-98b0-9d5703e5e570 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-construction Activities
| checkpoint |  | 5.1 Shared User Path - Post-compaction Testing
| note | c086f9da-1c01-4837-b6fe-64b31db0d0c3 | REFERENCE: 703.21
| note | ee66173f-4ed8-434f-bc19-dd360cd2b1a1 | 304.1
| note | 8aa40b65-652b-45a8-b874-e3433a952e09 | 304.11 (a) & (c) (ii)
| note | 1770a07b-e366-4df0-85d2-e96968b81367 | ---------------------------------
| note | 6adc830b-8d20-4389-a90c-a6d6642ce9fe | ACCEPTANCE CRITERIA: Following completion of compaction, material shall be tested for post-compaction grading & Plasticity Index (PI).
| note | aea35c1e-9c3c-4085-a4f1-a8ea4e81e742 | The test samples to be used for post-compaction grading and PI tests shall be a combined sample made up from six randomly selected increments extracted from the lot of pavement construction being assessed.
| note | 5184ad77-9a38-48a5-94e8-b56cf6f8add9 | Post-compaction Grading:
| note | e584d7ed-d1af-42b9-ad6b-753f165b558a | % passing 26.5mm sieve = 100
| note | 38d8a6eb-2576-4d74-a56e-24526e38e2cc | % passing 19.0mm sieve = 95 - 100
| note | a44b6292-80ac-4120-95ec-a4444314ffd0 | % passing 13.2mm sieve =75 - 95
| note | aa375acd-c138-4e8f-877c-c12e9dea583d | % passing 9.5mm sieve =60 - 90
| note | f05cc31e-db8f-489f-ac3e-bd67fa0a5dee | % passing 4.78mm sieve =42 - 76
| note | f7ec7560-cbe4-4cb3-9f20-f0758ab57653 | % passing 2.36mm sieve =28 - 61
| note | 52cf6335-9054-46ba-8f6a-557e21a01fa5 | % passing 0.425mm sieve =14 - 29
| note | 146c1914-2b6f-438a-99f6-f52140f3ce05 | % passing 0.075mm sieve =6 - 14
| note | 9586b144-9b6a-4e52-a4ef-b69280746d70 | Post-compaction Plasticity Index (PI) = 0 - 10
| note | ddaaf7fe-783d-4b02-bea5-77f822c1d8a5 | Attach: Sieve Analysis
| note | e06cd8ba-6629-40f0-a9eb-fc273b314601 | Attach: Plasticity Index Test Results
| note | 985e34d7-29dc-4902-bfc7-d475da9cd9ee | ---------------------------------
| note | 24f73b9b-4ce3-4bc8-ab71-5f9b1cabca76 | METHOD: Document Review Visual
| note | 22625af8-94cb-4c94-84b5-b774fc531efd | ---------------------------------
| note | 2c45ba87-bca6-4ac1-98db-a39e678da72f | FREQUENCY: Where applicable, each lot
| note | b8a9fad8-d551-4ca7-9aac-b34bfafe27df | ---------------------------------
| note | 0c24fc79-208d-4f75-b534-e0a8671373bb | CATEGORY: IP
| note | 48e3b6a5-ed37-432e-b805-66794d2348bd | ---------------------------------
| note | 89b21342-5b6f-42a6-bc75-dc872830c8aa | RESPONSIBILITY: SE/PE/SPE
| note | 93a15688-2a29-4b61-b215-18c4f8d564a0 | ---------------------------------
| note | 58f5eec5-7636-47d6-b88a-84ce81d1f4cb | VERIFYING DOCUMENTS: This ITP
| textbox | 34898a3a-4b68-4a2b-9dda-84cc6f0912a3 | Date Completed:
| checkpoint |  | 5.2 Non-conformance Report (NCR) Closure
| note | fd33ddf7-c8c2-4604-9a64-78b026563c42 | REFERENCE: MRPA Quality Management Plan
| note | 2b6b8f8b-c3c5-4b74-8ab4-17d7ed9c6832 | ---------------------------------
| note | 7617b3f9-a0f2-4661-8b14-ef64b45bfb0f | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | cf93a354-9a64-4157-baf7-9a869f2d623a | ---------------------------------
| note | 27879f59-889d-4eac-97cb-7636bef18792 | METHOD: Document Review
| note | aafb6a09-c0fd-42e6-9685-4db06b4e1774 | ---------------------------------
| note | b97194ca-12ed-461e-bdbe-517b06b7e95a | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 87d72e43-33e2-4e9b-bd79-8d063bea0c96 | ---------------------------------
| note | 10ad5d0d-0aac-418e-a7aa-adaa32f61e7b | CATEGORY: HP*
| note | e6c3802a-2c0c-4134-803a-12d7b4e336aa | ---------------------------------
| note | 9688392c-30a2-41c6-875e-f7ff9f044186 | RESPONSIBILITY: SE/PE/SPE
| note | 17f4d3b7-dc21-4dec-bfd3-4b2628c01148 | ---------------------------------
| note | f1093ecf-1d4d-42c3-86ed-a5e3556e00c7 | VERIFYING DOCUMENTS: This ITP
| textbox | e5144224-3a48-4f7c-b15d-ff48cf1c5f95 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 83108cc8-031f-476b-911c-80a76e4bfc0f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 7563d58b-1ee6-4ae4-a609-96ae62170ba1 | Name:
| textbox | 50990cef-f25c-4e7b-99ea-3c7040e69861 | Position:
| textbox | 4ceb1dc4-7706-4de9-be1c-98d457f54bdf | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-Track & Civil-Track Removal & Construction Rev 2 | itp | ITP-Track & Civil-Track Removal & Construction | 1490259f-4569-4cd9-95e4-d3d9f8808c70
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | fe71c228-f392-5788-a053-aaa460d0c2ba | Document Title: ITP-Track & Civil-Track Removal & Construction
| note | 9fa396ef-4bcb-5c62-be25-d549b494efef | ITP Description: Track Removal & Construction
| note | 017fafd3-6399-51f8-ac33-95f09df5972a | Document Number (in Teambinder): N/A
| note | d90f65d8-b419-5667-a7a2-88a84710c443 | Discipline (e.g. CIV/STR/RAIL): Track & Civil
| note | 3e2c5f82-580f-53f2-905f-df277796a11f | Revision Number: 2
| note | 8d423d1a-2b41-583a-a0da-0c72a03d329c | Revision Date: 14/11/2022
| note | 14ea0b67-865a-5e7d-ae2b-db8c60942919 | ITP created by: Jake Argentaro
| note | a93b58ed-0ad9-569a-a267-06ccdbf94596 | ITP approved for use by: Jihad Chahda
| note | 5c3a2a48-09eb-5c5b-9e81-619ad419cae6 | 1.01 Non Dependent
| note | 6740dd4f-fe05-5a81-97c1-f1df25af7ebf | Reference: Robinsons Road Track & Civil IFC Drawing Set MRP-DPK-072-00-CPW-0060
| note | 5f3afe37-403d-5a3e-96db-2f9cc50d4f88 | 1.02 Non Dependent
| note | b9242c11-cbfe-53ae-9b0c-2f2c69b9c656 | Reference: NIST-2654 Ballast
| note | 74171eb8-97fe-5331-b0bd-489a62a91c3b | 1.03 Non Dependent
| note | bc25eb53-5ccc-523a-bbc5-a73e6b089939 | Reference: NIST-2651 Sleepers and Fastenings
| note | 501042ae-24da-5427-8ec4-c25b1eaa2b6d | 1.04 Non Dependent
| note | 6aef0b3d-384c-5fa2-bfdf-34207f3524c2 | Reference: NIST-2650 Rail
| note | 27c7f075-324c-50a8-91ff-64ab98f7e60e | 1.05 Non Dependent
| note | 031c07a5-fa0a-5975-bc97-73384e164b6a | Reference: NIST-2630 Track Construction
| note | 78be47bf-62e7-5e73-a3c4-023a3b2e5fe4 | 1.06 Non Dependent
| note | bc5646a5-e27e-597a-95c4-a74aa62ddb64 | Reference: NIST-2706 Track Geometry
| note | cf71795b-4faf-5e18-99ca-283a7b5589c1 | 1.07 Non Dependent
| note | c7064332-3117-564e-9d6f-0e8c659cba18 | Reference: NIST-2659 Earthworks and Drainage
| note | 7e532e0d-0568-5ae5-8870-c92a93f68222 | 1.08 Non Dependent
| note | caec20f7-10da-59a6-8330-11e5e20475a5 | Reference: NIST-2618 Track Design
| note | f0292260-24af-5d84-bbc2-c16248c5d7c4 | 1.09 Non Dependent
| note | 79c0c6af-fbfb-5c1b-b12e-0449457ed172 | Reference: NIFO-2650.5 Aluminothermic Weld Record
| note | ff8f16c7-44b6-5de2-9fc7-f56236b2bde7 | 1.10 Non Dependent
| note | 38bb72b9-f95a-52a4-a1da-c052cd25f7ce | Reference: NIFO-2690.3 Certificate of Track for Operation
| note | 47a160a3-7058-5a7c-8e91-cdecfc401055 | 1.11 Non Dependent
| note | 03e09822-6833-50ab-9094-2374f7a94d12 | Reference: NIST-2703 Inspection and Assessment: Rail and Rail Joints (External)
| note | 37e48496-4ba2-51c4-a983-df38dfed2568 | 1.12 Non Dependent
| note | 7d8a0f1c-b05e-52fa-8ecf-4ab5836f3547 | Reference: NIST-2704 Inspection and Assessment: Rail (Internal)
| section |  | Preliminaries
| checkpoint |  | 2.01 Obtain and submit Material Certificate of Compliance for Track Materials: Track Rail, Track Sleepers, Track Jewellery, Geofabric, Ballast Matting, Ballast 60mm Aggregate, Welding Kits, Welding Crucibles
| note | 9492474d-3b6e-54ae-9668-bdc0a1f2d28b | REFERENCE: IFC Drawing(s)
| note | 43caa996-e407-5f23-90df-7037131b70db | Track Constrction Site Mudmap
| note | c00a3268-5354-5f3b-a695-c3676ed19cb9 | Bill of Materials
| note | 0b163176-26e7-5752-8ea5-2be2a7e578d3 | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration.
| note | 514c8d7a-c29c-5a98-a1c0-0d03443270ad | Attach: Manufactuer Cetificates of Compliance.
| note | 696f2859-6c94-5566-9bb0-ff39a89f405c | Welding materials shall comply with specification NIST‐2650 Rev3 Section 9 and AS1085.20 "Railway Track Material: Welding of Steel Rail.
| note | f98d51d2-e868-5fb1-909a-4b19a4c81acf | METHOD: Review Document
| note | 3ae79c3a-c07c-531c-8a17-698123717f8e | FREQUENCY: Once
| note | c9abc68c-3099-51db-b968-f77eddc65a01 | CATEGORY: HP
| note | dbfc503e-09b8-5964-a0f7-fb0a01731f22 | RESPONSIBILITY: Site/Project Engineer
| note | 6aec8459-587d-5659-985b-84717447a101 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b7d0e97c-f329-5bbb-ba87-63d45b06d18a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.02 Submit Welding Procedure/welding qualification welders Record
| note | 6da5e295-1e0d-548d-9455-40abce9dd31d | REFERENCE: NIST-2650 Rail AS 1085.20 Welding Rail Steels
| note | 16a30e9a-6749-53c8-8aaf-4b37c7f823c5 | ACCEPTANCE CRITERIA: Qualified personnel & welding accordance with manufacturers specs.
| note | 3f130e7d-b9fb-50af-9253-3e15f719b69c | METHOD: Review Document
| note | 8434b0c8-a58e-541a-b1b9-51c628e28658 | FREQUENCY: Once
| note | 91fb3e2c-efb5-50f0-b7fd-c3a3cdcb454a | CATEGORY: HP
| note | db297551-101d-5c63-b1d7-a08719915c56 | RESPONSIBILITY: Site/Project Engineer
| note | 4662c506-9f6b-541f-9fc0-0ee5e95593f7 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 27dc2ab9-07b4-58cc-aa22-b9cae1dfad2b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.03 Inspect supplied items upon delivery
| note | 9db08a13-9761-5583-82bf-5480c89b693e | REFERENCE: Bill of Materials
| note | c0e52ce5-3960-5b4d-a2bd-8d21dbd0d90e | ACCEPTANCE CRITERIA: No damage or debris on components
| note | 65d7291f-cd8d-5b21-a4d2-19dcb037a607 | Validate total number and type of components matches drawing
| note | fda89d9b-9090-5099-af36-9ad430e83954 | Attach: Photos on site;
| note | 38330e39-ff49-5e30-b67a-664bea4cd582 | – Track Rail
| note | 385ea741-1b3e-5139-817c-bbe0f444a23c | – Track Sleepers
| note | 745e2e9b-ba56-5f1c-bbdd-3c6dcbfbc2f2 | – Track Jewellery
| note | b9e7f69a-59c8-5b85-81bc-9ef5ecbfd88e | – Geofabric
| note | e954e9bc-cbcb-5bbe-913d-4cd4172df4c4 | – Ballast Matting
| note | 03f92a01-6228-5d35-b278-c7c79de1ad19 | – Ballast 60mm Aggregate
| note | c712f2f1-5250-5fe6-a1f0-5c02b48d9ed2 | – Welding Kits
| note | 01fae6da-0195-5bdf-92bf-293c0188698d | – Welding Crucibles
| note | cd815732-3159-5e18-bee3-f6dfdac744b7 | METHOD: Visual, Measure
| note | 62cd6901-48cc-57b8-aa8c-066775b2b2ca | FREQUENCY: Per delivery
| note | e53c2d50-0a22-586f-8593-e0e017089514 | CATEGORY: IP
| note | d55495a3-b7d8-5ba4-92dc-cd55c50a41ea | RESPONSIBILITY: Site/Project Engineer
| note | 9522a19e-95d3-52d5-ba3d-a4a9c31a0f89 | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | 050c1a4d-47be-5137-9b13-00b3c065d0b5 | Date Completed:
| checkpoint |  | 2.04 Confirm extent of track removal required for civil works
| note | eb57d9c6-c535-5175-819c-5ce9cb2d7ca8 | REFERENCE: IFC Drawing(s)
| note | c983be11-2094-5886-982e-87a30fa16ebf | Track Constrction Site Mudmap
| note | e20741d0-9afe-5940-8e5b-cdbb444c7178 | ACCEPTANCE CRITERIA: Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site
| note | 4b05291c-190b-58d8-af49-011f86f7f339 | Pre-removal survey of existing track alignment
| note | 770c6c1c-b9f8-5fd4-8541-f3c09c2fde91 | METHOD: Visual, Measure
| note | 11317848-be2d-5a10-a56e-7b54a896b3f0 | FREQUENCY: Once
| note | ed91bb8d-1a14-5db6-be1d-5cda916ba415 | CATEGORY: IP
| note | 93b8ce88-84ad-52c6-a0bb-299b62a33b9e | RESPONSIBILITY: Site/Project Engineer
| note | de76df75-cb15-5c2c-9e83-ee76a10b3465 | VERIFYING DOCUMENTS: This ITP
| textbox | 25bc41dd-ec10-5c5a-8b0a-8a00d606fcd9 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.01 Deconstruct and remove track componends, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
| note | 3e7d400d-1328-5545-88f7-389d4b51c86b | REFERENCE: IFC Drawing(s)
| note | 94b59c95-bd04-5462-b34a-fe82c296861a | Track Constrction Site Mudmap
| note | 11a3297d-7dcf-527e-97f6-109464af7f91 | ACCEPTANCE CRITERIA: Track structure to be removed to the designated limits as identified.
| note | 821c5b72-01b9-5a49-95c3-36289b5f8ba6 | Visual confirmation of removal on site
| note | dc1387c5-6124-5c4e-99dc-bc81170a0251 | METHOD: Visual, Measure
| note | 3876d9d9-168b-55b5-ac52-3ea482f2a58f | FREQUENCY: Once
| note | 47e96fbd-2bc4-5e11-9d33-69fff3572eb6 | CATEGORY: IP
| note | ecaee8d5-07e9-5c77-85fb-d901e27a3f7b | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | 30d415eb-a0c7-53f0-a0ee-c5959a74ed0d | VERIFYING DOCUMENTS: This ITP
| textbox | 94e32396-102d-57c6-989a-a82446243ff0 | Date Completed:
| checkpoint |  | 3.02 Earthworks completed and site handed over from Civil Contractor
| note | 2098268a-147c-5051-ad54-73b0ccb4bf65 | REFERENCE: NIST-2659 Earthworks and Drainage
| note | eca5e7f5-9283-55bd-9806-d229ea3f5230 | ACCEPTANCE CRITERIA: Confirmation of completion of underlying ITP(s)
| textbox | 37fe4ef6-e36d-5177-b996-36aae2971de0 | Underlying ITP reference:
| note | d33abcd5-3ea1-5cde-a747-8146ae438969 | METHOD: Visual, Measure
| note | 4e2ff31e-a2ad-5c81-a9cf-2d75b7453329 | FREQUENCY: Once
| note | 886a2817-7482-507a-99ef-d36b80580897 | CATEGORY: IP
| note | 2d83d5c2-2f1e-5cd1-8024-b7ede8ae08b0 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | 214fa0c5-be17-509b-8cf4-bccb738c0da3 | VERIFYING DOCUMENTS: This ITP
| textbox | b405e6ae-8da9-5754-a94f-c96149c71643 | Date Completed:
| checkpoint |  | 3.03 Installation of Ballast Shock Matt
| note | b6d8111e-02b8-569e-8ee6-45cd5c041a95 | REFERENCE: IFC Drawing(s)
| note | 740d9326-8a28-53b4-a1c3-1935ac807272 | NIST-2654 Ballast
| note | af418141-8d5a-513b-b723-0e31b2d3bc77 | ACCEPTANCE CRITERIA: Ensure all area of bridge deck is covered with ballast shock matt and matt fastened together with approved tape
| note | ee3ee44a-d1f0-53eb-94d0-585b396a5a3d | Attach Site Photo:
| note | 9769e828-d472-5ced-a588-be9b948a4ae2 | – Installed Ballast Matt
| note | 743ca8bd-106a-5f2c-827c-24e1960fc903 | METHOD: Visual, Measure
| note | 93e33485-444d-5862-a188-da49609d7638 | FREQUENCY: Once
| note | eb6af000-5af2-5b55-ae9a-2f317f2e9338 | CATEGORY: IP
| note | ecc3cc2f-dbc4-58cb-b519-4b0bdd123947 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | 5f623f45-8357-5192-a75c-a0f84fcc792b | VERIFYING DOCUMENTS: This ITP
| textbox | b623e1aa-e3c8-5c80-a142-111f559f4963 | Date Completed:
| checkpoint |  | 3.04 Installlation of Bottom Ballast
| note | 500b02cb-f9f0-5bf1-9617-5e4d5753bddb | REFERENCE: NIST-2654 Ballast
| note | 42e4a5a5-094e-5031-9935-3d55308e0d7b | ACCEPTANCE CRITERIA: Overal Minimum 300mm bottom ballast depth
| note | e5dae58d-7bb0-5632-b52c-bb5e89ed7a84 | Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate
| note | f3589e50-bc55-53c7-8320-d8a7d408c929 | Bottom Ballast to be left 20mm below final design level
| note | e5d79bcf-c05f-559f-931f-3aa8d64d5524 | Tolerance:
| note | 5a18d94c-9d61-55ab-96c4-20d2dd7f5fda | Under sleeper -0mm/+25mm.
| note | a37515ce-0773-54ee-9266-d5fb6a09de2a | Attach Site Photo:
| note | 654fc5db-0614-5c2b-8956-d1f3dcbf171e | – Installed Bottom Ballast Layer
| note | 48878e6c-25e3-50ba-b81c-83cac4cc7a2d | METHOD: Visual, Measure
| note | 37463a0c-9fed-59d7-b2f7-ae933e3e6a0f | FREQUENCY: Once
| note | f94a74ff-f62d-50ae-bc61-e8316d46edb1 | CATEGORY: IP
| note | 22cd232d-15d3-519b-89e8-3be7c7886891 | RESPONSIBILITY: Track Surveyor, Track Supervisor, Site/Project Engineer
| note | 49f532c0-48a1-50fc-9c60-4d8333bf319f | VERIFYING DOCUMENTS: This ITP
| textbox | 64eaaa49-91dc-50ca-9745-729b91f58fa2 | Date Completed:
| checkpoint |  | 3.05 Laying of Sleepers
| note | 0e9130b4-42ca-57b5-b524-27560fab18e5 | REFERENCE: NIST-2651 Sleepers and Fastenings
| note | 2e86acd4-00b9-5c6a-a172-aa99eeb8a351 | ACCEPTANCE CRITERIA: Sleepers square at nominal 685mm +/-25mm for open track
| note | e20e7eb8-d68f-51de-88cf-0ab410c24ccd | Sleepers square at nominal 600mm +/-25mm through level crossing
| note | 4a58aae8-0ae3-5cdd-8f94-d6e2115c4b21 | Attach Site Photo:
| note | 3f396de4-b031-583f-bbd7-ab40ca891279 | – Laid Sleepers
| note | 8dec7047-7442-520b-bf72-3c2965db6d58 | – Sleeper Spacing Measurement
| note | b908b1ce-aa3b-5755-9916-f827b3217cfc | METHOD: Visual, Measure
| note | 6944ff6a-24ef-5449-89f6-bec167bb412d | FREQUENCY: Once
| note | e6007bbb-a51e-5890-8c4b-7554f409496a | CATEGORY: IP
| note | 30aaacf4-301f-5ec8-8394-1cf60ade8529 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | dfc43bf5-cca5-5e3d-a78a-f2068ffc5463 | VERIFYING DOCUMENTS: This ITP
| textbox | 582f42e5-425c-5d15-8272-35f80a303131 | Date Completed:
| checkpoint |  | 3.06 Rail & Fastening Installation
| note | a87fba2d-556a-57cd-85df-8e028f44c1c7 | REFERENCE: NIST-2650 Rail
| note | 719c885c-7919-5353-b83f-547ed2493237 | NIST-2651 Sleepers and Fastenings
| note | 0308f1de-9950-5811-896c-2a4cb39b8a24 | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
| note | 7456ead6-618d-514a-a067-c323069d392a | Serviceable used rail shall be tested in accordance to NIST-2650 Rev 3 Section 6.3 and NIST-2704:
| note | 036925b7-6e03-5790-acb6-898a9e034725 | – Running rails in main lines shall be ultrasonically tested for internal defects, using rail flaw detection apparatus Attached to rail bound or hi-rail plant in accordance to NIST-2650 Section 6.1.1;
| note | e1eb9fb7-afff-56d6-9849-1b3a4e3df5af | – Manual ultrasonic testing shall be carried out within 30 days of completion of all new alumina-thermic and flash-butt welds on passenger lines in accordance to NIST-2650 Section 6.1.2 and AS1085.20 Appendix F4.
| note | 3d4944b5-1ab1-52cc-87e3-e3feec0565ee | New Rail lengths installed to be as per approved Robinsons Road Rail Weld Plan
| note | 11ab8bab-9099-58cd-aa1c-c7fa4f623c86 | Rails to be painted with Mirrortoned paint within areas of temporary roadway
| note | 0101628d-6075-53ec-8d41-3b48641f24bf | Gauge of track to be checked upon installation of fastenings
| note | dcd0fc56-5a2b-5df6-8688-b1fe6779ec05 | Gauge +4mm/-3mm
| note | a2f9f043-929c-50e9-a1ee-65db57841102 | Gauge Variation over 2m 4mm
| note | eaa62dc7-031d-583b-acad-f662790d67ea | Attach Site Photo:
| note | d6d80546-31a2-5eb8-a8b5-5fe4951b1f5b | – Laid rail
| note | 2a3c13b1-600e-5b56-9a8c-a5a355c1c3ce | – Rail joint to exisiting weld measurement
| note | 48dcf338-e582-52c5-b393-eb503b0ab61a | – Rail joint between sleeper bay measurements
| note | 2bac45e2-df10-54f7-9560-613fc736d21d | METHOD: Visual, Measure
| note | 1816d24b-1ac2-51cb-a7ad-4b160853ac8c | FREQUENCY: Once
| note | 36a178dc-63e8-5998-8f89-deb027b3b285 | CATEGORY: IP
| note | 853be2de-824e-543e-9d0c-0803be5c9e10 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | b44df622-4354-5984-b43b-973d0c4f532e | VERIFYING DOCUMENTS: This ITP
| textbox | 4a910703-fffe-5a16-b85b-2e4ecc43b564 | Date Completed:
| checkpoint |  | 3.07 Track Tamping
| note | f6268356-6e70-5b75-a737-5b02a44f7fb9 | REFERENCE: NIST-2630 Track Construction
| note | 7a250159-3de9-500e-ac33-fdfc689f01f6 | NIST-2706 Track Geometry
| note | 69ca19e3-b227-589f-ac0c-3bfcdbd05719 | ACCEPTANCE CRITERIA: Tamping Ensures Track Geometry Tolerances are not breached (dimentions are in mm);
| note | b5b95e75-294b-509c-95e8-246339872208 | Line (10m Chord) +/-5mm
| note | d04cfbb7-b43a-5e3e-ad54-d2c735aa2b0d | Twist (3.5m Chord) +/-5mm
| note | 7fb2a2b1-050e-5a5e-977b-d8f4bba635ad | Twist 10m (Chord) +/-10mm
| note | 603ad463-9ca1-563d-ae7f-0d09641873c9 | Cant +/-5mm
| note | 79f58710-f0c0-587e-9ce0-4a6045ea067b | Top (10m Chord) +/-5mm
| note | 83fac846-9342-5e2e-9d16-38e63c6c17d3 | Alignment +/-20mm
| note | 1571e580-240f-5dff-9b5d-3713335a758d | Survey measurment of RL of top of rail head
| note | 9cbd48ba-9ce2-5684-91b2-579d5bdc3386 | A minimum horizontal clearance of 3.0m from track centreline to structure.
| note | 00664322-4ba0-5fd1-9960-d14017a0d0b0 | Attach;
| note | 9435ec41-4ac0-51c1-acc3-31e9beb9a816 | – Tamping Geometry Recording
| note | 11504b85-9f51-5249-8e60-4c1d59b33807 | – Survey RL measuring sheet
| note | 96b8e696-1ec5-583e-a6b6-2de35ee958c9 | Attach Site Photos:
| note | ebbc232c-c7b9-5535-b588-bddecff8ba09 | – Tamping Activity
| note | 2e626c1d-a85a-57c7-8b13-0d1908c729ee | – Structual Offset Measurement
| note | bb76a344-0b6c-581d-b78d-137584dfff33 | METHOD: Visual, Measure
| note | b381e24d-831e-5ac4-a5e8-8ee90088cee4 | FREQUENCY: Once
| note | 6d5919c0-bfed-5e7b-b234-39837b9ab66f | CATEGORY: HP
| note | 211145c6-af73-5807-a3cd-0e9e382f3e2c | RESPONSIBILITY: Track Surveyor, Track Supervisor, Site/Project Engineer
| note | 3ac5e0f4-53d2-5918-8087-1cadde736cf4 | VERIFYING DOCUMENTS: This ITP
| textbox | 201e1d88-018b-5bce-8d72-ced937114f41 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.08 Regualting and Ballast Profile
| note | 8fa32e4a-6834-5599-b442-92dde602a23d | REFERENCE: NIST-2630 Track Construction
| note | 9bbcf626-8fea-50c9-8a47-1ccc6724dfa3 | NIST-2706 Track Geometry
| note | c683a7a5-349a-5a3f-8efd-40eaa1f4ef59 | NIST-2654 Rev 2 Section 7
| note | ced6fbce-bda7-5a64-8a23-d5c7f0ec5ff2 | ACCEPTANCE CRITERIA: Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter, to minimum depth of 300mm below underside of sleeper nominally.
| note | 61d0c902-2b13-5dd1-a6f1-a392b0f059aa | No Ballast to be on top surface of sleepers or aorund rail Fastenings
| note | c6a43a08-7edd-5cba-9639-48916e548b06 | Attach Site Photos:
| note | 2d948478-a697-56f9-810a-d94163fc5e56 | – Ballast Shoulder Measurement
| note | 31b4d9b7-7166-5b01-85a2-12bc65ce6252 | – Rubber Panels free of ballast materials
| note | 6e7c0265-56c7-574c-b06e-e5022ab893de | METHOD: Visual, Measure
| note | 7b2416aa-0370-58d4-b29b-4beb2a6f60a1 | FREQUENCY: Once
| note | 3ed76556-fe8f-5f87-a77c-446b34add3de | CATEGORY: IP
| note | 6ae89bf1-a638-598c-b033-8f0a5ad21976 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | f1852fbb-745a-56d5-ad6b-f298937597da | VERIFYING DOCUMENTS: This ITP
| textbox | 8f89ab00-58cc-55e9-822d-d3864edd7a55 | Date Completed:
| checkpoint |  | 3.09 Aluminothermic Welding
| note | 2ce30e9a-258d-5fc2-b08c-26ecbc29b343 | REFERENCE: NIST-2650 Rail
| note | 56a72622-6870-5141-8670-3c8c97e4d076 | NIFO-2650.5 Aluminothermic Weld Record
| note | 9f268a30-5d8c-52eb-9ff3-5e3c2dc884d4 | NIST-2650 Rail Use, Laying and Adjustment
| note | 9304251e-bd7c-5192-9055-5568c3448ee9 | ACCEPTANCE CRITERIA: Welds to be lined and finished to alignment standard
| note | 408f8f15-6d0b-527f-b713-38213d60d640 | Tolerance:
| note | ae358bbb-1f68-575f-a42b-3ee53ad29231 | Gauge Face +1.0/-0.5mm
| note | 52eace13-a2d4-58eb-8acb-604e89bd8000 | Running Face +0.6/-0.0mm
| note | bd87115c-5724-5a67-ad13-4aad6774f1bb | Welds shall be:
| note | d1717b75-abb8-5af0-83ad-c9a79e0ae113 | – A minimum of 65mm between rail end to be welded and edge of first bolt hole.
| note | 5b35a16a-7f50-5894-8ad8-c7c6a4639eb1 | – Welds must be located at least: ‐3m from a bridge abutment, ‐3m from a level crossing, clear (at least 5 sleepers) of change in track stiffness , ‐3m from any other weld, ‐3m from a rail end at a joint, ‐+/‐ 50mm from centre of bay between sleepers.
| note | e5394e0f-d6bf-56a5-8504-21f98cef15c9 | – The weld identification number (Record Sheet No.) must be legibly marked with white paint on the rail web, near the weld. Free welds must be painted black on the web prior to applying the weld identification number; welder identification (initials), weld number, year shall be clearly marked.
| note | 007cc57a-d033-55ce-b3e4-81dce28dcd7b | Verify Aluminothermic welding carried out in accordance with AS1085.20
| note | 6d7b232d-13ab-5617-bdb4-4e4d0e0d4b8e | Aluminothermic Weld Return Form to be completed
| note | ef0d7916-4d7d-5f1c-843d-0629f4ecf1d4 | Attach:
| note | 7c1f63ad-c638-517a-b129-f3497f51abf9 | – Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6).
| note | 4880b7b9-3271-5fd6-ba41-11058dd7bb12 | Attach Site Photos:
| note | 4fb3207b-55a2-52a4-a5f3-94c18c1731cc | – Welding Aligning
| note | d93bd82c-fe57-59eb-9ff6-966b5e225c3e | – Welding Process
| note | 4e746092-7268-5cdc-aed4-2754bb34dfc6 | METHOD: Visual, Measure
| note | 6e364f03-6725-567f-97be-2e9f6948795d | FREQUENCY: Each Weld
| note | add31f36-1afe-582a-b6de-d0f02bc5ad67 | CATEGORY: IP
| note | 008aace6-87cd-5026-96ff-e0d2364045b3 | RESPONSIBILITY: Track Welder, Track Supervisor, Site/Project Engineer
| note | 33362801-2d26-5e4c-b502-408f62a756d8 | VERIFYING DOCUMENTS: This ITP, NIFO-2650.5 Aluminothermic Weld Record
| textbox | bedfc3e9-516c-5924-baa9-f43f82cb6bf6 | Date Completed:
| checkpoint |  | 3.10 Track Stressing
| note | 3f5d5516-fd80-5d0a-a7bb-8def3f0d5ba9 | REFERENCE: NIST-2650 Rail
| note | 83c00f36-9915-52ee-8f78-e7d8dd47c436 | NIFO-2650.5 Aluminothermic Weld Record
| note | 387f6de6-90dc-57cb-9e0b-79b4ca1647bd | NIST-2650 Rail Use, Laying and Adjustment
| note | 3a1be670-544d-518e-a9e9-13d20d53f181 | ACCEPTANCE CRITERIA: Stressing Rail in line with V/Line Rail Welding Process
| note | 9e9e766f-efb4-5a04-8a07-efba40d14dc5 | Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
| note | b002be8a-fb8f-5c99-b2a3-9628282f3342 | Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
| note | 37023b58-0e42-50da-b3df-0c2f6730fac8 | Reference Marks recorded pre and post tensing of rail, creep monument recordings to be undertaken prior-to and following rail cutting in accordance to NIST‐2708 Rev2 Section 6 and Appendix A.
| note | b7eb2627-3585-5e51-a2e5-18de62ab5a17 | Aluminothermic Weld Return Form to be completed
| note | 31b48ca4-4edd-533a-9a09-f733757d533c | Attach:
| note | bde6d46d-b855-56d2-90dc-394fc6c1d516 | – Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6).
| note | ab545087-1a67-5c51-a14d-78c82d805f9c | Attach Site Photos:
| note | 42d3a880-40e5-5e13-91c5-a90548cc619b | – Stressing Activity
| note | d53f4d54-13da-511a-852a-10ca7e704753 | – Before/After Reference Mark Measurments
| note | f8f34d1b-0d0e-564e-82e4-96e4e2e4a037 | METHOD: Visual, Measure
| note | a3a5d7c3-4585-535b-8f22-239ee2b97c00 | FREQUENCY: Each Restress module
| note | 496a3f61-be02-5bb6-bdc4-8d82f139ee15 | CATEGORY: IP
| note | 14510f01-3a84-5ebf-ab12-36c26f8c9378 | RESPONSIBILITY: Track Welder, Track Supervisor, Site/Project Engineer
| note | f024f311-d9fd-5738-8ef2-c486a56bbe89 | VERIFYING DOCUMENTS: This ITP, NIFO-2650.5 Aluminothermic Weld Record
| textbox | 44ac6f19-5322-5b6d-b959-2d32f7527541 | Date Completed:
| checkpoint |  | 3.11 Weld Ultrasonic Testing
| note | 33746393-0672-5e9e-b6f7-0a446bcc4a63 | REFERENCE: NIST-2650 Rail
| note | 522962cb-3a3b-596f-abd4-c8879aad50f4 | NIFO-2650.5 Aluminothermic Weld Record
| note | 4df9df17-03ad-5f52-89f9-37a276d6db12 | NIST-2703 Inspection and Assessment Rail and Rail Joints (External)
| note | c620e5de-e13c-5a36-8c72-2f7c43974130 | NIST-2704 Inspection and Assessment Rail (Internal)
| note | fb162309-48df-5950-ab2a-49ce22ae1006 | ACCEPTANCE CRITERIA: Ultrasonic testing to be carried out in accordance with NIST-2650 Rail
| note | 4193c6dd-9e61-5994-bcbf-8767cc73f3ea | – Testing Procedure: Olympus Epoch 650 Ultrasonic Flaw Detector or approved equivalent.
| note | 13e48cff-f00b-5383-824e-a44c4ae699fb | The cross section of the area of the head and web shall be completely scanned;
| note | dce24e08-a194-503d-b789-f773d5e63310 | • The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
| note | 90b29488-4aa0-59f8-923d-24a7c147e85a | • Welds shall be scanned to both directions.
| note | 3361f888-fbff-5015-957d-97496a0a82d7 | No classified internal defects found
| note | 17d32a5b-a91b-5d5f-9aa2-ff837616977d | Final weld geometry to be assessed
| note | ef1a6e18-3e7d-5c61-94bb-6bafaffcf413 | Tolerance:
| note | 3e17b2b7-6597-5b8f-960e-0627c7db383d | Gauge Face +1.0/-0.5mm
| note | ffb0ba95-d2ea-5652-8b75-4a4bd5ed2c57 | Running Face +0.6/-0.0mm
| note | 7849c4f9-e04e-562f-85b0-8ed55c2671f9 | Aluminothermic Weld Return Form to be completed
| note | 021b0feb-03ed-5c35-9d58-bd9abb9e5e5d | Attach
| note | 562678a6-0bc3-5bf7-bd63-e00a0013b73f | – Aluminothermic Weld Return Form
| note | 30a513b2-27cd-548d-a914-2efa8312ffe9 | – Aluminothermic Weld Test Report
| note | 64ed601a-bef2-5bd4-9b62-95b97987237a | Attach Site Photos:
| note | 4182b490-ff40-5fb4-bb95-871d743f7042 | – Welding Aligning
| note | 4f915cd1-c7e5-51f3-8922-4570cc3fa9a4 | – Welding Process
| note | 7b05d470-43ff-59b8-8f90-6ae0210adfeb | METHOD: Visual, Measure, Test
| note | e2d0298e-2d79-5c0c-83f7-e1dc14575f04 | FREQUENCY: Each Weld
| note | 1cb7f2de-118b-5bf3-b9fb-292607329ad1 | CATEGORY: HP
| note | 02074ff2-7ffe-508d-84e1-589d9c94855d | RESPONSIBILITY: Weld Tester, Track Supervisor, Site/Project Engineer
| note | 8507af8b-4ac0-56a0-8f27-755c5847b52a | VERIFYING DOCUMENTS: This ITP, Ultrasonic Inspection Report
| textbox | 509ff0bb-c222-519d-b173-8b6182741cda | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.12 Installation of Epiflex
| note | 30492555-ea2c-5168-9da0-99a33a70c4d4 | REFERENCE: IFC Drawing(s)
| note | 39d8897e-c70e-53e1-b3bb-ad4a210d9051 | NIST-2650 Rail
| note | 92c181df-7baa-5e65-a85f-7eb207166d2c | ACCEPTANCE CRITERIA: Install Epiflex rubber stripping along length of rail to be located within temporary roadway
| note | 4d7ed476-1200-5fcc-b1e3-33ef159be906 | Insure all fastening clips are properly secured with applicator and geofabric is laid over sleepers/ballast in areas to be asphalted
| note | f5c132ae-ab54-5197-a243-dab0c885006c | Attach Site Photo:
| note | aff89142-c339-5123-8c05-e3bbb9c92c96 | – Epiflex
| note | 705040eb-ba61-5e8c-9997-b4a1ae65fe81 | – Geofabric
| note | 926a60c9-00e7-57af-9320-fefece9b1f70 | METHOD: Visual, Measure, Test
| note | 8f662593-1b7c-5893-bd8f-be40a08d50b3 | FREQUENCY: Once
| note | dbf3d330-2bbf-5a43-b68f-6a76b9c3d655 | CATEGORY: HP
| note | 85790162-fb63-5c21-8d0c-1ead843303b1 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | c755f356-bfac-5253-b9ed-4ab4817bf0a2 | VERIFYING DOCUMENTS: This ITP
| textbox | cd539445-a9bd-5136-8323-1d1105143d53 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.13 Installation of Guard Rail & Guard Rail Nose
| note | 3eb4c527-704c-586f-ad80-b13045a25fc4 | REFERENCE: IFC Drawing(s)
| note | 4a2f3cca-b59e-5004-b012-bb3b560e5c6e | NIST-2650 Rail
| note | a8c625c8-adb8-5703-b100-794561b5607b | ACCEPTANCE CRITERIA: Install guard rail and guard rail nose as per IFC design
| note | 098da31d-7f28-5756-8f64-03f654a47829 | Guardrail to be installed with alternating fastening pattern
| note | f6b0aafc-6078-5283-9ba0-0f8a99bbd4b6 | Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion
| note | 88ba236c-246e-565d-b165-0a41d3ec20e9 | Attach Site Photo:
| note | 3d543930-d962-5ebe-87f3-b70d0b42c25e | – Guard rail installed
| note | ce434b74-ffb1-519e-8b7d-0e49183858bf | – Guard rail nose installed
| note | ba2306b7-cf90-542e-a46d-ee69d6b8b000 | METHOD: Visual, Measure, Test
| note | 2ecaa5ef-634b-53f3-9b00-b732a13ff30e | FREQUENCY: Once
| note | cf4fe317-3ddb-5a82-ba4c-3e9e57a29acc | CATEGORY: HP
| note | 186235b0-f7ca-5d50-a10e-75843ac09809 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | e7d79eab-dcb1-5730-93e3-e4d0d45e228d | VERIFYING DOCUMENTS: This ITP
| textbox | 6bc93f72-b763-5854-8b73-aa80027ed9de | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.01 As-built Survey
| note | 50f67dcd-7ed9-5468-81d1-2f51437e7178 | REFERENCE: IFC Drawing(s)
| note | 90599d77-f19c-5e63-8dc9-06c4b4f3209b | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
| note | e56755d3-ae2a-5b82-9e5d-3f51486220d9 | Attach: Survey Report, Engineering Asset From
| note | cf8a1ef1-d223-5934-8230-d79b1c064c32 | METHOD: Survey, Document Review
| note | 21337482-b7c7-52b3-95a2-cfd2fc530967 | FREQUENCY: Once
| note | aea149c0-7942-5cad-873a-e01a5573f6f7 | CATEGORY: IP
| note | 618303f8-1a79-5899-b04b-43b986c8ea6b | RESPONSIBILITY: Track Surveyor, Site/Project Engineer
| note | 3ecb12aa-297b-58ac-9883-f402b99bcd0e | VERIFYING DOCUMENTS: This ITP
| textbox | 1fbd5551-5ceb-5072-8fd4-7918746169de | Date Completed:
| checkpoint |  | 4.02 Track Certification
| note | 3048c5dd-d280-5c7d-973d-fbc6e46730a1 | REFERENCE: NIFO-2690.3 Certificate of Track for Operation
| note | e2be4d97-9d53-578f-840c-123f95e208f2 | ACCEPTANCE CRITERIA: Attach :
| note | 7997b489-f2fa-5029-9450-01b68610852b | – Track Geometry Conformance Certificate
| note | 318c8117-3c42-548e-9c8b-e5a99762b598 | – Track System and Component
| note | 7235d579-4754-52b9-9812-9ebd56fe05b0 | Attach Site Photos:
| note | ac9396f6-5dbe-5160-b951-f86b1e0329fa | – Before/After Photo of worksite
| note | 361333f9-95fa-5aa2-8945-74a688a5528c | METHOD: Visual, Measure, Doument Reivew
| note | 8ecd295f-fa8a-54e4-bde4-0dd8bfc17a33 | FREQUENCY: Once when all occupation works complete
| note | 93fef98f-5e45-5b72-9e8e-423b2f091546 | CATEGORY: HP
| note | 2b2d4863-0507-588c-bd07-2ace50a38727 | RESPONSIBILITY: Track Certifier, Site/Project Engineer
| note | 74f1441b-d7c6-55ea-ab45-0e9050e6088e | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 89d0a953-1552-5a3d-820e-08e63466e2bd | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | c32485f1-5092-5d9a-af43-71dc386be0b5 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 6ebda7ec-10fd-540c-8730-843ac388be4d | Name:
| textbox | c1d4f6a8-07f3-5561-b801-c7be322bea4c | Position:
| textbox | a4dbfa46-377e-5243-a6f2-7796e062f4c5 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Structural Concrete Crack Repair Rev 0 | itp | ITP-STR-Structural Concrete Crack Repair Rev 0 | 17e82c88-f696-4260-b5a3-0fdb39db11de
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 94265fa4-3532-46ee-b138-1b6aab23d3b3 | Document Title: ITP-STR-Structural Concrete Crack Repair
| note | 575ec356-8fff-4894-94f6-510a2e9562d1 | ITP Description: Structural Concrete Crack Repair
| note | 78d1c8c7-f19a-413e-a50c-bf74e97da78c | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 4eb493e3-f1f8-4482-b5f3-ac545fee579f | Discipline (e.g. CIV/STR/RAIL): STR
| note | a0e3a926-b4c7-4c2b-a8f7-0f62e2e40897 | Revision Number: 0
| note | 9cc2e852-e145-4368-9011-b128e7783903 | Revision Date: 6/11/2020
| note | 9dcca10c-d2ad-4448-a536-0e2bf0bd11ad | ITP created by: Mike Freeman
| note | a503ae7e-f05b-4499-9039-40897052a822 | 1.1 VicRoads Section 610 June 2019
| note | 496b90ba-1bad-4f73-84c0-54d3cdf91b41 | 1.2 VicRoads Section 687 August 2018
| note | ef7bd48c-036c-4692-9996-0a8deaa93995 | 1.3 VicRoads Section 686 November 2018
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 2.1 Assessment of Cracks
| note | 289c88c3-cb79-4bb1-be29-135590743903 | REFERENCE: 687.01
| note | 1a6f19ee-5043-4d1c-b60c-0852d6d870d5 | 610.24 (b)
| note | 45f2c8a4-737a-48d9-9022-0694fc2e0876 | ACCEPTANCE CRITERIA: The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years practical experience in the diagnostic assessment and investigation of concrete structures.
| note | b983dd3d-c4e9-4b57-8ea1-78685f14cc73 | Cracks to be determined either as active or inactive.
| textbox | b6d01287-d7b4-42ed-9546-5ca89e1044ac | Enter: Teambinder Correspondence Approval number
| note | 069739dc-da8e-4c93-a0f6-3eba0bac586e | OR
| note | 8dfdbae1-5288-43f2-b56c-e79c35f420ac | Attach: Correspondence
| note | 096e33ee-8cff-4979-9ecb-2e129bb70e60 | METHOD: Visual Measure
| note | 9128c11d-7630-4a7b-ba27-7097b8222a6a | FREQUENCY: For each element, prior to Works commencing
| note | 3167e338-8b57-4d76-9822-e42864404e0c | CATEGORY: HP
| note | c25d0dc7-4215-48bc-b57d-dfca08507b95 | RESPONSIBILITY: Nominated Authority
| note | c2822dad-0a85-44c4-8da6-64b05497d954 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | e9f52530-6a95-48cb-ae60-7ae397c8a886 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Work Procedures
| note | c3ebd756-b0ea-43b6-a2e7-eec10796d9c1 | REFERENCE: 687.01
| note | 93087e7c-9968-496f-a7b8-8716948def22 | 687.09 (a)
| note | 3ddbbacd-c0f0-4fc1-a294-9be7b1962cab | 610.24 (b)
| note | 1c314d4f-48a2-48f3-928d-d6b440a2e21d | ACCEPTANCE CRITERIA: The Contractor shall submit a crack repair procedure/procedures for review to the Nominated Authority.
| textbox | 9ec6cf01-6b3a-40c5-9a96-c1b981f43727 | Enter: Teambinder Correspondence Approval number
| note | 5b9e21ee-8390-4ad9-8186-336baab39b97 | METHOD: Visual Measure
| note | f786a9da-9cfc-4bab-8160-6f663ba5d6bd | FREQUENCY: For each repair methodology, 14 days prior to Works commencing
| note | 6ab9a21c-9c66-4e13-99b4-b65282922cc7 | CATEGORY: HP
| note | ab385755-6668-4c91-966b-506bb1d8fd84 | RESPONSIBILITY: Nominated Authority
| note | b3019f89-3976-494d-aa92-2af0bc9fba94 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | e2e7b272-e9b5-4329-bf39-3809d99e7df7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Preliminaries - Materials
| checkpoint |  | 3.1 Flexible Sealant Selection - Active Cracks
| note | 28b9709a-b4af-4e1d-b26e-991443f94377 | REFERENCE: Product TDS
| note | 12aafe24-1605-44ff-903e-28a9c8c0da4a | 687.05 (c)
| note | c5ac0a50-b606-48e5-ae9b-4065a1fded23 | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | fcb72c9d-efe1-4510-aa0f-6de92b7f62f1 | i. provide for a minimum expectant movement of ±25%;
| note | 4b0abca2-6f4f-493d-85e3-e0316fbb33da | ii. Whether or not the repair/sealant is subject to traffic (trafficable or non-trafficable)
| textbox | 3143d0b6-3004-4435-a3ad-c37e2e3b5283 | Enter: Teambinder Material Approval number
| note | fa266b36-43cb-42d6-a4c2-5d31b3249b41 | METHOD: Document Review
| note | ac8e5003-774e-4651-a3d7-ee874aba4301 | FREQUENCY: For each product, prior to Works commencing
| note | 98708a78-c3ae-454a-ab63-e44dc2a1af7e | CATEGORY: IP
| note | c86e0bc2-3b29-4a7e-9b56-4875fabc92c1 | RESPONSIBILITY: Nominated Authority
| note | ba773a1d-62dc-4ca3-afd3-eb80802eb22f | VERIFYING DOCUMENTS: This ITP
| textbox | 3fac8438-7694-460a-adea-d0cacd9489c4 | Date Completed:
| checkpoint |  | 3.2 Epoxy Mortar or Paste Selection - Inactive Cracks
| note | e0749e26-09dc-46a9-9635-08be97620f0a | REFERENCE: Product TDS
| note | 796b0d29-a7d5-4d2e-9f86-1a86f52eb53e | 687.05 (b)
| note | 05e81675-6e75-4a58-b6cf-a001d34d553c | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | eed24813-189f-4c90-bc59-767ce72ad3cc | i. compressive strength @ 7 days ≥60MPa;
| note | 92582809-733a-4ade-9be4-044d0ad237ac | ii. tensile strength @ 7 days ≥25MPa;
| note | 27332ba3-1f49-4f95-b498-91f8545d34dc | iii. flexural strength @ 7 days ≥30MPa;
| note | aef8fd08-7e8e-49d1-9535-8fd4c6f8caf2 | Note: For the routing and sealing, injection nipple/entry port placement and surface sealing applications only.
| textbox | b3bf7134-41ca-4286-9627-d566ae07902e | Enter: Teambinder Material Approval number
| note | 30bd85fb-0e97-413c-8166-4c84af70b3f5 | METHOD: Document Review
| note | c9bc086c-63de-4209-80ad-d7ef189cb81b | FREQUENCY: For each product, prior to Works commencing
| note | 6b32ef7c-d4ba-49f1-9218-09eb3feca7d2 | CATEGORY: IP
| note | 20c18a15-b58c-4a1e-928e-d207e288ac9e | RESPONSIBILITY: Nominated Authority
| note | 9fa8612b-9552-4a23-8f3e-3d079c80f27f | VERIFYING DOCUMENTS: This ITP
| textbox | c54ad1ee-5183-49e7-b61a-3b90ac5b5fb7 | Date Completed:
| checkpoint |  | 3.3 Epoxy or Polyurethane Resin Selection - Inactive Cracks
| note | 4fec2f22-80a0-4afe-9d54-e8d0635e7160 | REFERENCE: Product TDS
| note | 11724934-e137-4178-aa99-eca22148d742 | 687.05 (a)
| note | 9ffad2ec-c318-4f20-b8f5-a67ac2e543fa | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | 7e38c5e3-abf6-4aa9-89a7-464f166a7e07 | i. viscosity @ 20°C - 23°C 650cps max.
| note | 976b2c08-2305-4285-ad3b-a73076e6a025 | ii. compressive strength @ 7 days ≥60MPa;
| note | e1e2721a-31b1-4fa5-8ed6-d24b0317e62a | iii. tensile strength @ 7 days ≥25MPa;
| note | cf4e647c-7e7d-441d-8841-f3072ccfc0fd | iv. flexural strength @ 7 days ≥50MPa;
| note | 8cfc90f1-2175-47d9-a4d5-663160f4dca3 | v. adhesive strength at crack edges @ 7 days ≥2.5MPa (or concrete failure)
| note | 67b54ddf-b4f4-41c7-bd04-44c3301fd3f1 | Note: For the resin injection or gravity fed applications only.
| textbox | fc075260-c05a-454e-99fc-24e46cd41271 | Enter: Teambinder Material Approval number
| note | ae29eb3c-bc95-408b-ab3a-c9c515e5c62c | METHOD: Document Review
| note | 86a4d6d0-7aa4-41f2-8934-da90e15da6a0 | FREQUENCY: For each product, prior to Works commencing
| note | e46f8461-c7c6-4944-b713-87763ba8708b | CATEGORY: IP
| note | 33cde6a1-172e-44e8-867a-39871f487c9c | RESPONSIBILITY: Nominated Authority
| note | 7ef3e9d4-6699-4636-b7d2-cab2e1458082 | VERIFYING DOCUMENTS: This ITP
| textbox | 9b056580-c2a4-4951-8380-8b1ccc4b4690 | Date Completed:
| checkpoint |  | 3.4 Silane Selection - Inactive Cracks <0.2mm Width
| note | bdae566e-19ad-4c9a-97fd-be88e6a98ce4 | REFERENCE: Product TDS
| note | 982f7222-c1af-4553-893f-41cf7827a44b | 687.12
| note | 5899b627-7713-4770-8b91-cd533b9a8e20 | 686.05 (h) (i)
| note | e6727523-c43b-41f5-b2eb-62b2e7454467 | 686.05 (c) (iii) (1 - 5)
| note | e889f7d4-d355-4210-a95d-bbee70a06839 | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | dc5e116f-2237-41ed-b938-c636d6508098 | i. active ingredient: ≥95% (penetrant)
| note | 791d994a-3959-4d40-920e-d069d6e9c46f | ≥80% (solid silane)
| note | f504ad46-5ab2-4293-a674-ad8db95da868 | ≥80% (silane crème)
| note | 6bbbb97d-bed5-4d09-9496-b69436d0ffe4 | ii. penetration depth: 5mm min. iii. contain a fugitive dye to enable coated areas;
| note | a875676a-38f0-4ea8-8ff4-70d900ebbce0 | iv. be compatible with a film-forming top coat;
| note | c4a61b09-58ac-4c87-850f-a09abf757859 | Note: For the protective coating of inactive cracks ≤0.2mm in pre-stressed elements and exposure classifications B2, C & U only - 0.2mm cracks are acceptable in other precast elements and exposure classifications.
| textbox | c47f6f5f-23bf-4753-b70f-a9446eb1ead8 | Enter: Teambinder Material Approval number
| note | 7d9335ca-3140-499e-9c3e-dab531963415 | METHOD: Document Review
| note | 28eeb6d3-3701-4d57-a9e7-fa48b900e94c | FREQUENCY: For each product, prior to Works commencing
| note | aefd62c6-78e2-4cea-837c-0abd40eef148 | CATEGORY: IP
| note | 5a91e273-6fc3-4aa8-9c0a-0acebb8a0b73 | RESPONSIBILITY: Nominated Authority
| note | 240cc9f9-6d33-4673-9767-b3388b79281d | VERIFYING DOCUMENTS: This ITP
| textbox | 2ff749f5-d93d-4050-adb7-e97f89eff43b | Date Completed:
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 Contractor Competency
| note | 382d3db1-5072-43bd-bd9e-b8a695e226e3 | REFERENCE: 687.04
| note | da7e6a49-f4c6-4c9d-964f-6614a79f1e6c | ACCEPTANCE CRITERIA: Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application.
| note | 050739a7-51d0-48b1-b11f-351579704212 | Documented evidence to be available.
| note | 5a8bbd6a-ccaa-496f-b433-6e873bf09c72 | METHOD: Document Review
| note | b7741e71-4eff-49fb-9a02-fc36174c106b | FREQUENCY: Once, for each personnel, prior to starting Works
| note | a2670dec-22fe-41fc-95d2-f19bf2697ce1 | CATEGORY: IP
| note | 15eb57f1-9b3f-4837-a761-5a7c42e79771 | RESPONSIBILITY: SE/PE/SPE
| note | 20104ba3-7358-45e5-9f59-64bc93b00232 | VERIFYING DOCUMENTS: This ITP
| textbox | 81ca06ff-83ce-468c-9adb-6ec274d39c63 | Date Completed:
| checkpoint |  | 4.2 Injection Equipment
| note | 5fe65c9e-0ec2-483e-b73d-6d7e3ccc3365 | REFERENCE: 687.06 (a)
| note | 009a554a-e2df-4d26-bcf6-d537d0a7261d | 687.09 (c) (iii)
| note | 419cf0ab-6070-4897-bab7-27e326cd2114 | ACCEPTANCE CRITERIA: Injection equipment to be simple, easy to handle guns with pressure regulation or limitations in the operating range and be simple to clean and maintain.
| note | 7c2657d0-5ff0-43fa-8fb3-dd88d5438f11 | Nipples/entry ports to have shut off valves or at least the ability to be capped to prevent leaks or air travelling back into the crack.
| note | 0971117e-6cf5-4253-8557-2b5807461a7b | Note: This ITP does not cover special purpose, multi-component injection pumps.
| note | f54337da-490b-402e-944d-9c1e18db4b55 | METHOD: Visual
| note | 99056ac9-3da2-4c9c-a581-1e2ea3333fae | FREQUENCY: Once, prior to starting the Works
| note | 43d768d3-c53f-48bc-b83b-8f61be9abdeb | CATEGORY: IP
| note | ce760e01-3c29-45e6-9a07-dd75f7386cdb | RESPONSIBILITY: SE/PE/SPE
| note | ece85286-4f51-4db0-a717-62b5f009c437 | VERIFYING DOCUMENTS: This ITP
| textbox | 45dd5ac8-8269-443d-af0b-d2342e3be9f7 | Date Completed:
| checkpoint |  | 4.3 Weather Conditions
| note | c5b6e35f-7df5-45ba-bd7d-62048d8b90fb | REFERENCE: 687.05
| note | a893b65c-293a-4362-a2a8-595dcec752ad | 687.09 (c) (i)
| note | 62c7f6d8-61cf-4f28-ba9c-cb90259345b0 | ACCEPTANCE CRITERIA: Repairs are not to be undertaken when the ambient temperature is below 5°C or 5°C on a falling thermometer, or above 35°C.
| note | 625e4a54-5fdf-4da6-b3d4-ffa403489ace | Cooling the materials is allowed should the need arise if temperatures inadvertently rise during the repairs.
| note | 9cb67591-4389-4312-89db-f76fe32fa157 | METHOD: Visual Measure
| note | 98f4557e-dd6c-4043-abda-c3c661a92e26 | FREQUENCY: Prior to each repair
| note | d3f2d222-fae9-488f-b79c-1df40a1181bf | CATEGORY: SP
| note | 0b13b5e1-bc75-44f1-9dc8-876c2e94e056 | RESPONSIBILITY: SE/PE/SPE
| note | b54a8dbd-3dea-4326-b3e6-e46c223ffefa | VERIFYING DOCUMENTS: This ITP
| textbox | d4b894e3-c99d-41fa-82a5-180c450ca1d1 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 5.1 Surface Preparation
| note | ed44c84b-b6a1-478f-8214-ede4f11bbb4c | REFERENCE: 687.08
| note | 214f8b5b-1cdd-4dfa-97a6-dc31ae5c1675 | ACCEPTANCE CRITERIA: Cracks and surfaces located within 50mm each side of the crack to be cleaned of all loose particles, dirt, dust, curing compounds, grease or efflorescence by appropriate means.
| note | d65df8fe-861a-4e0c-9f6a-911b5143507e | Where cracks and surrounding areas have been moistened during the cleaning process, sufficient time or accelerated drying-out needs to occur unless the crack repair materials are water tolerant.
| note | b8f5585c-93c9-4b4b-af74-555ef789b2e3 | METHOD: Visual
| note | 8a2449c9-be23-4915-87e2-9fedec7d1f0d | FREQUENCY: Each crack
| note | 6ff8dd9c-b14b-4b38-9330-4bbf03d75f2c | CATEGORY: IP
| note | e7b79811-b82c-4c1e-a491-a1ea72dd38fb | RESPONSIBILITY: SE/PE/SPE
| note | 1565a177-62a5-4bca-98e8-b064d0bcb334 | VERIFYING DOCUMENTS: This ITP
| textbox | 26c3583e-aa16-43e0-aea1-e67d9054bf12 | Date Completed:
| checkpoint |  | 5.2 Active Crack Repairs - Route & Seal Method
| note | 0170a84a-e839-44ae-9c25-6dfab0e3de93 | REFERENCE: Crack Repair Work Procedure
| note | 69021f1f-3591-47f8-aa6c-ec0d5b5e9e2c | Product TDS
| note | f8a0b38a-27ac-438e-82b5-0cb432b36dcc | 687.10 (b) (ii)
| note | b13c3d33-9dcc-4caf-bdd6-87942fcd4dcd | 687.15 (a - d)
| note | 730441a5-83a1-4b40-a8d9-3aebae2075fd | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
| note | 81e19198-ac1f-42e6-ae1d-26d1770574d3 | i. All materials in date and mixed as per the Product TDS;
| note | a648b976-d964-470d-9f8f-86b5e776f97b | ii. Saw cuts to be at a width to depth ratio of 2:1 and rectangular in section;
| note | e55e6486-4632-4fe5-9766-2294e3d4bd75 | iii Surface dust to be removed;
| note | 8f014470-6e44-488a-aacb-43a41d92f007 | iv. Bond-breaking tape to be placed at the base of the chase/reservoir to limit sealant interface to 2 no. faces;
| note | 1e4edf8c-1907-4474-b080-f2a69d786c17 | v. Where required, masking tape to sides of the adjacent surface to create a neat finish;
| note | 98b712d0-c1e8-4f82-8fc8-9013bce01f23 | vi. Sealant gunned or tooled into the saw cut to completely fill the void;
| note | 8d6bf374-8124-4230-8e74-5736835225af | vii. Product shaped with a suitable tool to recommended profile;
| note | 4c686b5a-64c3-4c2c-8ba6-bf3879ad41f3 | iix. Repair to be protected from damage or adverse weather while curing;
| note | e6602f9e-d56c-4696-a5ff-7401f55b118b | METHOD: Visual
| note | 83e0f314-249c-45e5-860d-586ce3d4f654 | FREQUENCY: Each active crack
| note | 88cbb4fd-ac8c-412a-af84-d876697919d2 | CATEGORY: WP
| note | 04bb8da8-5e46-478c-a6fc-330f67cbee3f | RESPONSIBILITY: SE/PE/SPE
| note | 98fd27b3-790c-4d86-b981-08b19e56588b | VERIFYING DOCUMENTS: This ITP
| textbox | 87921142-da16-4ebe-9c22-831aa21d5706 | Date Completed:
| checkpoint |  | 5.3 Inactive Crack Repairs - Route & Seal Method
| note | 0245e576-1078-4a4e-99cf-b3943fbaa458 | REFERENCE: Crack Repair Work Procedure
| note | 70f950c7-d8e3-496e-a90b-72a55b76c7f8 | Product TDS
| note | 3c2ef426-edc6-491c-b696-83f55bd2e409 | 687.10 (b) (i)
| note | 610f6a3b-346c-461a-b409-9fcd267507e9 | 687.15 (a - d)
| note | 0efb70d2-2652-497b-9952-d194a18726e3 | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
| note | b3df6f55-874c-4fd6-8bf8-f21a9cb15c31 | i. All materials in date and mixed as per the Product TDS;
| note | 1e1121f3-8262-436d-b42e-1c265f7a4051 | ii. Saw cuts to be at a minimum width and depth of 10mm and V-shaped in section;
| note | 3d461820-1a91-4508-9369-ea3a056eb467 | iii. Surface dust to be removed;
| note | 0f209285-0da6-45d5-b5ce-86e218ccc0d6 | iv. Epoxy mortar / paste placed into the saw cut to completely fill the void;
| note | 3f8a3909-3247-41b0-87fe-c6220af4db2d | v. Product finished flush with the surrounding surface;
| note | 5f6aea55-d8ac-4770-a883-5cdc80ffb9db | vi. Repair to be protected from damage or adverse weather while curing;
| note | e37206d1-4429-4460-b7f1-54970c68e603 | METHOD: Visual
| note | acab8993-1b74-48df-aced-4a4ddef2a68b | CATEGORY: IP
| note | 89e3730d-75bf-4c48-a61c-78cd89b2b3a4 | RESPONSIBILITY: SE/PE/SPE
| note | 0ec58da1-8b74-4992-8a79-999d41b35886 | VERIFYING DOCUMENTS: This ITP
| textbox | 3e3d6199-0238-450f-a12c-8d691323c088 | Date Completed:
| checkpoint |  | 5.4 Inactive Crack Repairs - Gravity Fed Method
| note | 1e673559-921d-4840-bcf1-ee9bbe04e77c | REFERENCE: Crack Repair Work Procedure
| note | c8eae499-5a6f-4957-8272-3896632d6f94 | Product TDS
| note | ab4ddc9c-0246-4d9f-924e-f1ad2a83c9a3 | 687.11 (b) (i - ii)
| note | 153d3b0b-1bdf-42c9-82d6-98415261f5ab | 687.15 (a - d)
| note | 84b018e6-069b-4b19-9212-8ed72def21d8 | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
| note | 92707d11-9470-436c-ae9d-d763095b98e8 | i. All materials in date and mixed as per the Product TDS;
| note | 9a9a7f8d-0513-4394-b94b-b67d78f85b93 | ii. Where required, a water-tight reservoir, to be created with silicone or polyurethane sealant;
| note | a831425e-46c8-4532-93b7-f2d143aa64a0 | iii. Epoxy resin to be poured onto the crack and either sufficient amount contained in the reservoir (if used) or worked back and forth by suitable means (such as a broom) until no more material can be absorbed;
| note | 9a9a4bdf-37d4-48e7-8a40-0d740eff6049 | iv. Excess material and reservoir can be removed as the epoxy resin gels;
| note | 8ac22796-6d1d-44cd-bc71-fa1efb9e6806 | v. Repair to be protected from damage or adverse weather while curing;
| note | 2c053c15-9301-480c-b403-7a2022148d67 | METHOD: Visual
| note | 3333b7d8-06ea-4fb3-9ecf-426ae6ba68c0 | CATEGORY: IP
| note | 9020f4b5-77c8-4647-bb47-0483214ee08d | RESPONSIBILITY: SE/PE/SPE
| note | 44a3a7a2-ef44-48a9-ba40-1b40fd29d316 | VERIFYING DOCUMENTS: This ITP
| textbox | 289c6f63-ccd5-4120-95e6-7591fcf8807b | Date Completed:
| checkpoint |  | 5.5 Inactive Crack Repairs - Injection Method
| note | 2e4cd91c-dd1d-4351-8e6f-959f569d8010 | REFERENCE: Crack Repair Work Procedure
| note | 929ef712-cbcd-4b6f-9755-9a2f209726dc | Product TDS
| note | d6e19d87-812f-42ca-8a3f-d64e25fc6091 | 687.09
| note | 08cd1f5f-834c-4b5b-898f-5ebad22d9af8 | 687.14 (a)
| note | d454200d-a8a6-4f67-aba3-bfc7bbe46dcf | 687.15 (a - d)
| note | bba4b23a-942f-4417-87e9-44533c9c0eda | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
| note | f58e036e-3cba-49e7-a5ad-eb80fcf99ae5 | i. All materials in date and mixed as per the Product TDS;
| note | 80538e64-92f8-49c0-bea0-f0d0dab24316 | ii. Each nipple/entry port coated in epoxy mortar or paste to create a water-tight seal to the entire perimeter;
| note | 6b4ff6c5-2937-4789-8e12-0671a842c8dc | iii. Nipple/entry port placement central over the cracks at 200mm spacings maximum (where cracks are through the full section, nipple/entry port placement shall stagger);
| note | 9c3b42cc-161b-40c2-aa58-d738cbeddafa | iv. Epoxy mortar or paste applied to the surface of the crack in between nipples/entry ports and the full height of the crack if within tolerance to eliminate resin leakage);
| note | ab8446b8-798d-4b02-957d-0c8065bfe079 | v. Once the epoxy mortar or paste has fully set, connect the injection gun to the lowest nipple/entry port (for vertical cracks) or at one end of the crack (for horizontal cracks);
| note | 585c7184-d163-4d3e-9c47-9950e59e16cf | vi. Initiate the injection, applying pressure until resin can be witnessed entering the next nipple/entry port;
| note | 5d05ebe7-6c72-44d6-bf12-d8f939c91bed | vii. Stop pressure and close the valve of the engaged nipple/entry port and connect to the nipple/entry port where the resin appeared, working either upwards (for vertical cracks) or along the crack (for horizontal cracks) until all nipples/entry ports have been filled;
| note | c057186c-80c0-4a06-8d26-89321e7b5797 | iix. Repair to be protected from damage or adverse weather while curing;
| note | f47ea97c-19a1-4062-b6da-4ff0e0f9d89e | METHOD: Visual
| note | 71c65faa-7df0-4a8d-816d-508adedd14a5 | CATEGORY: IP
| note | cf8713e3-2db6-4463-9773-16c609ef5032 | RESPONSIBILITY: SE/PE/SPE
| note | 48cbd537-56d3-41e1-ab75-1f1058838e51 | VERIFYING DOCUMENTS: This ITP
| textbox | 3dc05aec-b804-44a0-902a-8dc5735da97c | Date Completed:
| checkpoint |  | 5.6 Inactive Cracks <0.2mm Width Repairs - Penetrant Coating Method
| note | f1d8b37c-3f07-43f5-a754-3e64aca07fd5 | REFERENCE: Crack Repair Work Procedure
| note | b60bd3a5-7eed-4397-ace8-ba75bd5f5e7d | Product TDS
| note | ed90a81d-7641-466a-8b29-528bb86cbc57 | 686.07 (a) (i)
| note | 88423983-3c39-4383-87c9-fb8654eae26a | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
| note | 1695dbfe-ce0d-404b-8d45-8a1a8bccea36 | i. All materials in date and mixed as per the Product TDS;
| note | a5a444bc-852e-402f-b335-7e426c40914c | ii. Silane to be applied with an airless sprayer (for penetrant) or brush (for Solid Silane or Silane Crème) , working from low to high areas and approximately 150mm beyond the extent of the crack;
| note | 2a1d7079-a653-4882-bc8c-a29f366a31b9 | iii. Application rates to be as per the TDS for each type of product ensuring wet appearance;
| note | 3b7f40e7-e65c-45b5-9267-c0f25ed6659b | iv. Re-coating if required;
| note | d3481639-dad6-45f7-a1bf-e3571da98765 | v. Repair to be protected from damage or adverse weather while curing
| note | 668fe425-cdf1-4139-9ea2-461a2fa21efa | METHOD: Visual
| note | 2ef21ef5-af57-48aa-9393-f8f67036b48a | CATEGORY: IP
| note | 90021838-ff02-40f5-98a4-e735956797d1 | RESPONSIBILITY: SE/PE/SPE
| note | 2df65762-93bc-40ec-b5bd-99de538c4599 | VERIFYING DOCUMENTS: This ITP
| textbox | 765c5953-feaf-465e-b341-afd1dec7ea5b | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Curing & Finishing
| note | e1b6c1e2-e5ea-478d-a9da-ded8761b87df | REFERENCE: Crack Repair Work Procedure
| note | efa8ac9c-16df-406a-b477-7c2623c48f78 | Product TDS
| note | 20c7007f-e8ae-4e5d-9921-9fe6464730b5 | 687.15 (a - c)
| note | b588dfe6-2f19-4573-8797-6755ab563ab9 | ACCEPTANCE CRITERIA: After the repair materials have cured in accordance with the manufacturer's recommendations, any surface seal, nipples/entry ports and repair materials can be removed by suitable means.
| note | f138eb0b-11f0-4468-ae6b-7d9c3021e8cc | The surface shall be ground smooth, leaving no traces (indentations or protrusions) of a repair and if the repair location remains exposed, a fairing coat can be applied where not being coated with a pigmented coating system.
| note | d27d6db8-2cd1-4b55-89ec-4e788d4fe307 | METHOD: Visual
| note | 5b4cc1a2-74ef-4d88-acae-79e739f2b93f | CATEGORY: IP
| note | 7d840a86-c33a-47d2-8f79-15484629f371 | RESPONSIBILITY: SE/PE/SPE
| note | f285e3db-59b0-4df6-a02e-9d33b3eb4506 | VERIFYING DOCUMENTS: This ITP
| textbox | 72308daf-6f10-43e3-a3bd-9ba8941faf05 | Date Completed:
| checkpoint |  | 6.2 Repair Verification
| note | d3ddb97e-b69c-45de-9644-5de541e1afe8 | REFERENCE: 687.16
| note | 0f89ac12-606b-4169-9860-5afedfe10839 | ACCEPTANCE CRITERIA: After 7 days minimum, 75mmØ core samples shall be taken to verify cracks are fully sealed.
| note | 77539d8e-ef0e-408e-a345-23c0e2ab41d9 | Cores to be located in conjunction with a covermeter to avoid reinforcement and approved by the Nominated Authority.
| note | 97c3b197-fd83-46ca-9f7f-b1a4e7874f5c | 2 no. cores for the first 25m of crack and an additional 1 no. core sample for each 50m of crack or part thereof.
| note | 37a126ac-7dcb-4c14-a934-12eb6bcf36ea | Core holes to be filled as per the cementitious repair ITP.
| note | 2cd11e63-48e0-4e4e-8fe7-fb9952130a82 | Attach: Photographs of Core Samples
| note | 22892494-3036-4bfa-a76d-b1e1cb08b145 | Complete: Structural Concrete Cementitious Repair ITP
| note | 480d7c03-8810-41dd-a6d9-0d43273d6a94 | METHOD: Visual
| note | 9017f0df-5da7-43cd-89f5-6a7c866c8313 | CATEGORY: WP
| note | e740700d-2c41-47cf-ba47-2611e0e98ec8 | RESPONSIBILITY: Nominated Authority
| note | 82a76cf7-085d-4dbd-83a1-4186532b034f | VERIFYING DOCUMENTS: This ITP
| textbox | b2db52b6-12b8-4966-aa26-5f30c322e8f7 | Date Completed:
| checkpoint |  | 6.3 Non-conformance Report (NCR) Closure
| note | 1a12e3e7-2d51-40ce-9bf1-0677310f23a3 | REFERENCE: MRPA Quality Management Plan
| note | 82254b86-9c8e-439a-92ca-546a9958794e | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 1d4e3e54-0edd-4970-bab0-e00b03c00c34 | METHOD: Document Review
| note | 7856a70e-c44e-48eb-8034-58d187681470 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 328b3252-103d-4416-b3f4-aa5d8c3b8d33 | CATEGORY: HP*
| note | 793cbc1a-7f06-4141-b511-2bb9b772dee4 | RESPONSIBILITY: SE/PE/SPE
| note | ac774976-9cd5-42e6-8514-47e7f718c518 | VERIFYING DOCUMENTS: This ITP
| textbox | 4b98ac98-27cb-49bb-a857-be08fb57d974 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | e43cea26-af46-4605-b641-6c0c9bc342b4 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | b5d1211f-c62c-4765-996a-269f68086182 | Name:
| textbox | f2b08544-0693-4c59-9fc7-527a272d8864 | Position:
| textbox | 10dac392-776a-4730-ad90-6170aa37c2e2 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Structural Fill (Supply and Install) Rev 0 | itp | ITP-CIV-Structural Fill (Supply and Install) Rev 0 | 1f0bc234-3f51-4637-bd00-1a0c544d6877
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | bfaef0fc-935f-408e-a219-124018b2d25c | Document Title: ITP-CIV-Structural Fill (Supply and Install)
| note | e926581c-308c-4eb8-8dbc-b0617f534138 | ITP Description: Structural Fill (Supply and Install)
| note | 061274f7-752d-4a87-b31d-6b074b6aa678 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 6f4fee37-1000-46f6-920f-e5f783e682fe | Revision Number: 0
| note | e7e7392a-1927-4e4d-8e9c-418f7996f70b | Revision Date: 1/06/21
| note | f7b88afe-94dc-4dab-ade8-2b16f891df42 | ITP created by: Matthew Dib
| note | 38ddcda9-54c5-4114-b8b6-73b9188051ec | ITP approved for use by: Aldrin Guinchoma
| note | 99089467-972d-4b56-b839-bfbc4ebbcee5 | 1.1 VicRoads Section 204
| note | 76edcb9a-c61f-4cad-a6e2-e19d088b2069 | 1.2 IFC Report and Drawings
| section |  | Preliminaries
| checkpoint |  | 2.1 Structural Fill
| note | 54218d18-0670-44da-b072-7a96a0c2bc9f | REFERENCE: Section 204.04
| note | ecd8f733-453e-408b-afa0-7c99321b6fc9 | Table 204.141
| note | a83af239-0850-46c7-9793-076775ff9c9a | IFC drawings
| note | 96ea7acf-18a9-4ba7-99ee-9d806be51931 | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
| note | b01c6ac1-e7be-4b5a-a805-ef8a7ee7b005 | Scale B
| note | 6baf2a52-4409-4d55-afb1-f0395a0b7be0 | CBR ≥ 6%
| note | 1e047f44-ea5d-4611-88af-5f1ba86bcc54 | Swell ≤ 1.5%
| note | a3fd63f6-8b03-4f6d-9bcc-c3ebc3ad8cd0 | PI (LL) = 6 - 25
| note | 3c45f271-7026-4209-a3df-d4cd48d71011 | Internal Friction Angle = 28*
| note | 7a0ec44b-b691-4c47-81bb-309cc5cf0e51 | Effective Cohesion = 5kPa
| note | 678d3854-f079-404f-acff-a74efc562dbe | Unit weight =20 +/- 2 kN/m3
| note | e11c48f3-78b1-4fb4-b8ea-6cbbd97da342 | Grading:
| note | bb382948-7a78-49ef-b2db-0c29983ff227 | % passing 75.0mm sieve = 100
| note | bd637efc-ae4c-4f24-b13f-d64c9f63eb4a | % passing 4.75mm sieve = 40 - 80
| note | 68672389-38f6-4d39-b362-f729b7890178 | % passing 0.075mm = 10 - 40
| note | 0ef67374-3471-4de4-b539-f6d4e5d9ce1d | Attach: Test Certificates, Delivery Dockets
| textbox | fe5eee66-0108-40b4-80bf-0bfed5d1f74c | Enter: Teambinder Approval number
| note | 382075c1-2133-4671-8a80-6b2886f807f9 | METHOD: Review and Verify
| note | b49ec64a-34e4-424b-8c42-31f5aabcad32 | FREQUENCY: Once per material type prior to commence of works
| note | 09742acd-034e-4409-ac12-edac51b68d9b | CATEGORY: HP
| note | 6b9ccfaa-77d6-46b3-a297-4e722d8ee09e | RESPONSIBILITY: Nominated Authority
| note | 5584229f-0f7b-4fbd-9ce0-ef4da7f51bc8 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ed2a9cd1-4fb4-4c53-993e-676f753e2f98 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | d6c2c387-1bec-49d3-8188-ed098eee2df1 | REFERENCE: Section 204.03
| note | 2aad9695-ba76-4198-bb92-1793c7ce40a8 | IFC drawings
| note | 167d4993-afed-4b05-9dac-29b3ffba81d6 | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
| note | 36284b18-22ea-449d-adbf-47d0f35e3fce | METHOD: Measure , Visual
| note | 2aa9537b-cb9d-4259-8e06-5419ce7e5185 | FREQUENCY: Each element
| note | d75aa49c-e1e8-40ae-be02-7f4dabeb4fa1 | CATEGORY: IP
| note | 429beb88-f505-4d0d-85fe-79262ddd6cc4 | RESPONSIBILITY: SE/Site Supervisor
| note | 0a96d43c-3131-4dcf-9046-e877a4347119 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 6659c5df-b1dd-4f7a-aa3f-85bdc86cadc3 | Date Completed:
| section |  | Fill Activities
| checkpoint |  | 4.1 Structural Fill Placement
| note | 207fff33-39f4-45c7-bb8d-51cd299c7653 | REFERENCE: Section 204.10 (d) (ii)
| note | e2abe109-b660-4988-888c-aa1dd1032802 | IFC Report and Drawings
| note | d0225f84-c4e3-4b3b-9136-9226bd34b90d | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness.
| note | c9457ad2-c1ad-4e97-85b7-8994cc39b898 | Extent of fill placement to be as per IFC Report and Drawings
| note | 0d1e3e51-1286-48fd-88c4-311d8bc08314 | METHOD: Visual
| note | 9ed70481-473c-4820-bc94-14cae7098d34 | FREQUENCY: Each lot
| note | 407c1a5a-bdd1-4aba-81e4-05c73438045c | CATEGORY: IP
| note | 4d56ad1a-cf47-4f7c-ac3f-0c302c66c7ad | RESPONSIBILITY: SE/Site Supervisor
| note | 644a5022-fd03-4722-a32f-f4b7adffab11 | VERIFYING DOCUMENTS: Sign ITP
| textbox | d721470b-e561-4e44-87d7-781a6192f71e | Date Completed:
| checkpoint |  | 4.2 Keying of Layers
| note | 162f787d-813b-497b-8280-9f3e3540bf58 | REFERENCE: Section 204.10(d)(i)
| note | e2b7864c-debc-415d-b3a7-b40a7e211717 | ACCEPTANCE CRITERIA: Each layer of fill shall be keyed into the layer above by creation of a textured surface.
| note | 4eff8daa-223c-41f8-acb2-873a2054f67c | METHOD: Visual
| note | 57f55466-2f77-4a09-a2c8-b5abdc858234 | FREQUENCY: Each lot
| note | d7a8bf08-bc98-4818-b0f8-8542d09e4e5d | CATEGORY: IP
| note | 41d0502c-0926-44f6-aaa6-d1db9ca0fb58 | RESPONSIBILITY: SE/Site Supervisor
| note | c7ba581a-3eda-42b9-acdd-818a0cd608c2 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 905e2ec8-9e48-48e4-86b6-71ecf6cc994e | Date Completed:
| checkpoint |  | 4.3 Proof Roll
| note | c0650dab-ab3d-463c-8b88-f1e903795288 | REFERENCE: Section 204.13 (b) (i)
| note | 1de5982f-3f67-4bec-a88e-b481438af4ac | Section 204.12
| note | 11f28bd1-e31a-4d27-8588-fe07994968a7 | ACCEPTANCE CRITERIA: Withstands Test rolling without visible deformation or springing.
| note | 28a3722b-20d3-453e-80bb-9c1880d573ff | No fill to be placed until the area has been reviewed and approved.
| note | df0038f0-4965-49df-bd55-fd1628c557f1 | METHOD: Visual
| note | 2c5ed92f-dfcd-46f4-9dbe-bb306d4bd577 | FREQUENCY: Each lot
| note | d0836696-decd-4564-b1a8-c93421a833f7 | CATEGORY: HP
| note | 4baefb03-68d3-462d-8bec-9cbee19b2ac1 | RESPONSIBILITY: Nominated Authority
| note | 49035d3e-9036-4145-9e4f-c9be3828c110 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | edb5b389-efd8-477e-8752-e403f53aa806 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.4 Compaction Testing
| note | 568100fd-1c57-4080-a701-bfdbb9491553 | REFERENCE: Table 204.131
| note | 2408610a-ecef-41a5-9e54-31aa54a5020c | Section 204.13, 204.14
| note | b04e0364-94e5-4305-940f-93b667e8e9ba | ACCEPTANCE CRITERIA: Frequency = 6 tests per lot
| note | 46b5085b-2020-40fe-8a4f-88bba9119541 | Lot = One day's production or 5,000m2, whichever is the lesser
| note | 3d476110-c6e2-477f-b6a3-ee3caea70ec9 | Characteristic Density Ratio =
| note | a4d2d89e-ac72-470d-ab19-3052b6f05ac3 | 95% minimum when more than 400mm below top of Type B Fill
| note | 94943b23-0246-49dd-a748-932069a8a58a | 98% minimum when within 400mm of top of Type B Fill
| note | 1a560c88-dff8-4b14-b3ec-d893b57bf35f | Attach: NATA Compaction Test Report
| note | 3c6afb8b-ba78-4414-b37b-12bd5cc07ae4 | METHOD: Document Review
| note | f73e9bac-a3d4-4839-bbc6-005ccb0fbb23 | FREQUENCY: Initially test every lot until three consecutive achieve passing results. , Min. every 2nd lot of like material and work
| note | d624dc98-2b56-4362-a47b-a7dc0f7bf316 | CATEGORY: IP
| note | f6a82a89-0f30-45ec-994d-d3b19bd06e89 | RESPONSIBILITY: SE
| note | 1a6e97e3-8a00-45d5-b12c-a05c71de0c54 | VERIFYING DOCUMENTS: Sign ITP , NATA Compaction Test Report
| textbox | 9378a3ac-bbf5-4596-903d-8c5638d9ca01 | Date Completed:
| checkpoint |  | 4.5 Post Compaction Material Property Testing
| note | 4f9bc460-9012-40ae-a78b-dd364266c532 | REFERENCE: Table 204.041
| note | 42a53456-418e-4325-b0d2-4a9516bc79a0 | RC 500.2
| note | 23a720cd-6e52-42ed-8aa3-3bfe33e2a5b7 | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
| note | ba8d1dc2-e519-4362-8f7b-5e8e3bde7266 | Scale B
| note | 9b6bc83b-f9a6-48ed-abf8-3cba154c4d3e | CBR ≥ 6%
| note | 111d7250-74bc-4677-b41b-4a4b0f3cf652 | Swell ≤ 1.5%
| note | f823a585-23a5-402d-ae67-bcd53f07140b | PI (LL) = 6 - 25
| note | 1987220d-d9bf-4c63-ad7a-2da0a7ea69dd | Internal Friction Angle = 28*
| note | 3b261c82-d8f0-4c5a-8c38-35cf29138f80 | Effective Cohesion = 5kPa
| note | b10f1cca-912f-4ef3-9f12-27e8c47d8983 | Unit weight =20 +/- 2 kN/m3
| note | 0dbcb3db-ac7c-4973-a3df-540b038bcdfa | Grading:
| note | 468cdec0-43d8-4a42-9e4b-8fb4d9384c86 | % passing 75.0mm sieve = 100
| note | 0a8b0001-1055-4877-89ca-eccc1423be70 | % passing 4.75mm sieve = 40 - 80
| note | 019c6d4a-a229-43e2-bada-3b1300de0f15 | % passing 0.075mm = 10 - 40
| note | 2e91a2fc-4862-4a14-8a22-dbf01b0fef7e | Attach: NATA Material Test results
| note | c3d7da00-56c6-432e-b565-917ec5ef1fed | METHOD: Document Review
| note | d64c026f-0fc3-4f74-b779-9a22e3de5b53 | FREQUENCY: to be tested once post compaction
| note | 2630a627-9604-4cea-92e6-7c9c3c5da537 | CATEGORY: IP
| note | a8481419-ddcf-402c-a11b-0879f11ee874 | RESPONSIBILITY: SE
| note | ae821168-ef04-4b9c-8e3e-88e07397e793 | VERIFYING DOCUMENTS: Sign ITP , NATA Material Test results
| textbox | 6092d2e4-9816-4e83-b1c8-c1a294bbcf0f | Date Completed:
| checkpoint |  | 4.6 Preparation of final surface
| note | ce9bfb2c-aa22-4abc-9b63-071d18f67cb6 | REFERENCE: Section 204.15
| note | b2ac77c9-c0a0-4606-a18e-1a1c9954debc | ACCEPTANCE CRITERIA: The top of the subgrade surface shall be prepared to level and shape to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
| note | 7014ae3a-9982-4e4d-a3c8-47c4729cdf38 | METHOD: Visual
| note | 18882bb4-2d64-4baa-aea8-7135dfa06c27 | FREQUENCY: Top layer
| note | acb00f7e-75f7-4748-aec3-cc22c53c97c4 | CATEGORY: IP
| note | e370a197-57c3-4ec4-b461-b9e3490a169f | RESPONSIBILITY: SE/Site Supervisor
| note | 24c997e1-bd3f-41db-b81b-37948f30b1af | VERIFYING DOCUMENTS: Sign ITP
| textbox | 7e4b6467-74df-4db3-a7fc-5aa622b88017 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 As-built Survey
| note | c0fa483c-3aeb-4fa6-872e-58afc0a3d403 | REFERENCE: Section 204.03 (h), 204.16
| note | 510b451d-e389-4f80-b62e-0107ca31323e | ACCEPTANCE CRITERIA: Scale B:
| note | 2859571b-4f18-4e89-a93b-460d66c478d9 | Min. No. of Measurements Per Lot: 40
| note | e924e8ac-f4b1-44b9-b97a-24bdae8745a9 | Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
| note | 5b59e886-35d9-4d91-9425-842b1c905553 | Attach: Survey As-builts / Survey Report
| note | 719609d0-8b83-4f37-b9ad-33d4114bbabb | METHOD: Document Review
| note | 4a6e0c74-eba1-4704-bd00-49a1e6c4b9d8 | FREQUENCY: Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
| note | ca133f91-e3e3-43f8-bd12-091fe80e0a59 | CATEGORY: IP
| note | 962f41de-f6d6-4cd9-803b-823e98eef678 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | c82029bb-2633-44a7-833e-0ac970da1397 | VERIFYING DOCUMENTS: This ITP , Survey Conformance Report
| textbox | c5917c43-a20e-4c6c-86d1-0d4d44f17ef0 | Date Completed:
| checkpoint |  | 5.2 Non-conformance Report (NCR) Closure
| note | 4034073a-3090-4f8e-807a-abb1bd4e7713 | REFERENCE: MRPA Quality Management Plan
| note | c5445170-3553-455b-bfb8-ac1623dc4fa8 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 25446fed-df4e-41a0-b20e-ff20c0571fc9 | METHOD: Document Review
| note | e9a3bcef-3047-4563-8d99-2fabf8da6672 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | d18427a7-c9df-4a67-9438-6ce0fc51a69d | CATEGORY: HP*
| note | e71aad62-af06-4c1b-b43f-1095a2c1970a | RESPONSIBILITY: SE/PE/SPE
| note | 580058b3-f084-4f26-9122-bb25c23c359a | VERIFYING DOCUMENTS: This ITP
| textbox | 28004c64-8aba-4522-9405-afe6edaee20c | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | cd70cf15-94bd-41f0-8908-b2e984ca9bd8 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 00978a5f-9a40-48d1-ba49-fab43f5ef093 | Name:
| textbox | 999bec48-33fb-4214-a627-e6db2b57dd02 | Position:
| textbox | 2c217529-c54a-4747-b489-73d3de33a080 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-General Safety and Guard Fence Rev 0 | itp | ITP-CIV-General Safety and Guard Fence | 20917be0-c3cb-4cd6-90cd-956506720680
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | ce3f6757-37bd-5480-988c-68faac58becf | Document Title: ITP-CIV-General Safety and Guard Fence
| note | b90fd963-9715-54b0-aed9-d2d2567d3a0b | ITP Description: General Safety and Guard Fence
| note | d25a07d3-a04b-56dc-b48d-06c0cb44ade0 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 146d3efd-19b3-5a76-a86c-57a51b73870e | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 0411d68b-7e60-5eaa-aeb8-f9e1398adbe9 | Revision Number: 0
| note | 57a007a3-79d7-5c9b-bb24-9d1bdc0dedb0 | Revision Date: 12/10/2022
| note | 9f5dd304-af6f-58c0-9327-0302a05bf7d7 | ITP created by: Romualdo Magpantay
| note | bfc5446d-2194-5da0-8fbf-69cc36ee71db | ITP approved for use by: Romualdo Magpantay
| note | 10bd48c5-25cb-5df0-ae98-a5b8b5320665 | 1.1 - Non Dependent
| note | 3414c016-9563-5161-b382-1735f55536f8 | Reference Documents:
| note | 45b2d903-4d3b-5688-88ff-e934c68f232e | • Vic Roads 707 Austroad
| note | 112bc17b-925a-5180-8621-09c08f6762c3 | 1.2 - Non Dependent
| note | f9d918d0-9bd3-507d-928c-7548a099979d | Reference Documents:
| note | f1966c49-9e12-5a4d-a225-066ea49c31a1 | • Vic roads traffic engineering manual Vo.2
| note | dfbb29ee-8bf3-5486-9a7f-f008b7009e5e | • MRP-057-C-AUR-DRG-11-ADR-CFN-0155
| note | 4d6ed184-f7ba-5cb4-be20-7bf56ed50007 | 1.3 - Non Dependent
| note | 26d0d5bf-78af-5b26-a018-f810c1a62da5 | Reference Documents:
| note | 6b62ac2d-4c43-5348-94aa-8ed982156288 | • AS1725.1/NIST 2662
| note | 4abc7377-ca6a-56b4-abd8-1057c6583be2 | 1.4 - Non Dependent
| note | 89b5bf88-19f0-5477-ae7b-b593a45458df | Reference Documents:
| note | c1c89a8d-b0a6-507f-82b4-917775069d71 | • MRP-057-C-AUR-DRG-60-ADR-CPW-0152 SAST-3281
| section |  | Materials
| checkpoint |  | 2.1 Submit materials and components conformance certificates by subcontractor for fence, gates and stock grids(Steel Columns, Cladding, Handrails, Chain Wire Mesh etc
| note | a4b4a0c4-5226-50e8-9e05-6b0d39162078 | REFERENCE:
| note | 283a8b22-8f5e-5787-865d-d15496b52737 | Vic roads 707.03 c,d, g,h & K
| note | a6245a6c-aaee-569f-8c6e-7e1816ca90ee | AS/NZS 4680
| note | b1339490-7eac-5748-b766-c4b17557a146 | AS 1725
| note | 88ba8ca9-f9cf-5f53-9f07-af782a4fd254 | Austroad
| note | d7002756-fc76-51fc-9321-ef2fcded023e | – – – – – – – – – – – – – – – – –
| note | 42332952-6f5d-5402-9a6e-3c570ed590d9 | ACCEPTANCE CRITERIA:
| note | 01551cf2-9af8-50be-bfd1-74033e7ab6e4 | • Verify supplied materials and components comply with the Specification
| note | b12a4091-0ab0-5143-95d7-4d5c0204c3aa | • Submit signed Certificates of Compliance
| note | 7e36da6e-fdef-597c-854f-83d6f8188287 | • Chain wire shall comply with AS 1725 requirements
| note | 523ce391-22c9-5b58-b8b1-45a4861aff76 | • Steel posts (minimum yield strength of 195 MPa)to be hot dipped galvanised in accordance with AS/NZS 4680
| note | 8dfbae36-33fe-5001-abf7-fcff2497b59a | • Timber post and chain Link
| note | 244c43c6-14e9-50d0-8ba5-81be1a67389e | • Welded mesh
| note | a110a5ff-a9f0-5c97-86e9-4956a2d395cb | – – – – – – – – – – – – – – – – –
| note | d78988f2-6793-5e8b-9fee-c71e469cc34b | METHOD: Document review
| note | c2d044d0-f6c6-527b-9db4-4c7045ad1203 | – – – – – – – – – – – – – – – – –
| note | 57cac74c-649a-5513-b771-89196c648bdb | FREQUENCY: Per type
| note | e96c1ea6-68ae-5ad8-9852-5a2a2605daf5 | – – – – – – – – – – – – – – – – –
| note | a23b10e9-a466-5e1b-806f-c8e66c3cefcd | CATEGORY: HP
| note | e1d0d321-1238-53d6-b35a-0a1be003cf6b | – – – – – – – – – – – – – – – – –
| note | fd7c9f18-ccd7-5041-82f7-51a939fb7877 | RESPONSIBILITY: SE/Site Supervisor
| note | 8a570d73-b4d5-5264-89a9-ef28dcbd9d32 | – – – – – – – – – – – – – – – – –
| note | 3c052305-d817-5a97-ae36-6aa5482b811b | VERIFYING DOCUMENTS: Certificate of Compliance
| textbox | 443c8ee9-f87b-56ea-9a3c-5d1894cebb09 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Concrete
| note | f2b71e6c-f502-5177-9668-39860c5e1456 | REFERENCE:
| note | da5ac934-9a0d-573a-9506-c10e69f00370 | IFC Drawings
| note | 2f05c829-8ee8-57dd-9779-3b96a2e4ab5d | AS3972
| note | 225cccf9-45d1-5239-8e99-5e8b663292e6 | – – – – – – – – – – – – – – – – –
| note | 5e318bbb-52e7-523f-9065-cfd9ba0c4b46 | ACCEPTANCE CRITERIA: 25 MPa concrete to be used as per IFC drawings. All cement to be GP or GB or SR complying with AS3972.
| note | 3227d07a-0a04-5013-82c9-bf5ee83b5853 | – – – – – – – – – – – – – – – – –
| note | 90783d5c-80d8-5f01-8de9-07487e02e9f9 | METHOD: Document Review
| note | 5d0408f9-6cdc-52c7-8335-740ecff2e04d | – – – – – – – – – – – – – – – – –
| note | 9d868536-fa1e-597c-b177-b378b01d9d96 | FREQUENCY: Each Mix
| note | e3c81cab-d3b9-51dd-9688-d0816d4cafb0 | – – – – – – – – – – – – – – – – –
| note | 9e8aad8b-45f7-5dcb-b8ea-df44bd03a790 | CATEGORY: HP
| note | a2e464b3-d678-5d78-9d55-8c0ed7f432b7 | – – – – – – – – – – – – – – – – –
| note | b42cac4f-7161-5fca-bd46-eaca9d9dd8dc | RESPONSIBILITY: SE/Site Supervisor
| note | ece1225b-bd11-5bd4-94af-a65dd2dab534 | – – – – – – – – – – – – – – – – –
| note | 0ef68187-69f6-5984-8878-5d0fe9c97831 | VERIFYING DOCUMENTS: Certificate of Compliance
| textbox | 43f90541-f956-57ee-bd65-3a251b1dfae0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Check materials upon delivery
| note | c9c00933-7fc4-5f19-93c8-8510c27820a8 | REFERENCE:
| note | d0812938-be62-54ea-b2a0-3434ebdfd0d8 | Vic roads 707.03 c,d, g,h & K
| note | 3d5a232d-a629-5372-82d9-f5fb1319f765 | AS/NZS 4680
| note | b5e9a1b4-908a-5202-a61e-8e15df67a28b | AS 1725
| note | 083a559f-457e-55cf-a0d8-b2b7930eb008 | – – – – – – – – – – – – – – – – –
| note | 2987736c-f01b-5519-904d-5e75cf395865 | ACCEPTANCE CRITERIA:
| note | 5dbb8814-2d02-59cf-a5f6-34a7a8fcb8e1 | • Components are as per purchase order/s & delivery docket/s
| note | 4534f37f-2f68-515b-acde-5b641c2fc0b7 | • Free from damages/defects
| note | 106ccf88-29e4-540c-b9cb-aba5bdce0a46 | – – – – – – – – – – – – – – – – –
| note | efe9356c-aaa7-51d5-810a-435ada2c083f | METHOD:
| note | 584851be-7467-5dd8-8367-d43adb29fd64 | Measure
| note | b778e6cb-0c3e-5ee5-9f26-c875e6150705 | Visual
| note | 5b071cce-76bf-588c-b452-2e0e7a9918ed | – – – – – – – – – – – – – – – – –
| note | 5b42eb44-d719-52e2-af41-265214f9b449 | FREQUENCY: Per delivery
| note | 6a9fbead-a575-5ee6-a6c7-dee9ad6b12c0 | – – – – – – – – – – – – – – – – –
| note | d512c7db-b8ba-5bb2-b04d-c1ae88eb096e | CATEGORY: IP
| note | e1051a18-e00b-56af-92c0-18337c7aab35 | – – – – – – – – – – – – – – – – –
| note | 44b58a25-3866-572a-9f33-c3d26bf24770 | RESPONSIBILITY:
| note | bb365024-0ab5-5931-9c26-5a499eca7729 | Surveyor
| note | d925ec21-8bad-5bae-aae6-961d823a1608 | SE/PE/SPE
| note | 3fc7deb2-de78-59cd-93c9-1cfa43dc2fed | – – – – – – – – – – – – – – – – –
| note | 02ff8cd2-e7b8-5561-a27f-59eac3923d86 | VERIFYING DOCUMENTS: This ITP
| textbox | e279372f-a506-5c64-aed0-86935ac1a41b | Date Completed:
| section |  | Pre Installation work
| checkpoint |  | 3.1 Survey Set-out
| note | 9a32708a-3268-5ab7-a08d-2f64892e235b | REFERENCE: IFC Drawings
| note | 15c73619-7202-5a76-b31a-b24356248693 | – – – – – – – – – – – – – – – – –
| note | cf882448-b29b-5aa5-8604-6ea40c601dbc | ACCEPTANCE CRITERIA:
| note | 628c37aa-5a44-5713-8275-a69f6e6f67d3 | Survey to set out the following but not limited to: existing contours, levels and features, surface pits
| note | d18a316e-3e37-52d8-a3b9-4a0fd020779f | • Establish Pegs or equivalent to define the boundary of fencing
| note | 20f4d1b1-cf3d-5b7a-8f8c-7b870993b3c8 | • Fences shall be constructed on the boundary of the infrastructure lease or wihin the infrastructure as necessary
| note | 3d04bc01-0d33-5700-876f-a330617ba2c6 | – – – – – – – – – – – – – – – – –
| note | a2e7aba6-af8d-5001-993e-f5030a7ebf6d | METHOD:
| note | 6dd61b0a-9e2b-594b-b650-824daae4caa5 | Measure
| note | 33522c94-a388-557d-9781-246c55cf5bc1 | Visual
| note | b21f01f4-6564-51e5-8b2d-61e75dba1853 | – – – – – – – – – – – – – – – – –
| note | 1a95587a-b113-5004-aaf1-867004c74597 | FREQUENCY: Per Area
| note | 3c0f0646-2e8f-5cef-9e6b-4c0060065d38 | – – – – – – – – – – – – – – – – –
| note | 59b5a61d-06e6-5dd6-bd7b-18882d4b27d5 | CATEGORY: IP
| note | c0541577-62b7-52da-9098-7911d38f8840 | – – – – – – – – – – – – – – – – –
| note | 66ff30d0-8707-5a26-9ae4-c0a74774403b | RESPONSIBILITY:
| note | c9f046a9-14d9-594c-81a7-33cf256e021e | Surveyor
| note | 78550c1f-c0f5-583f-9de3-2befc2e3e5d5 | SE/PE/SPE
| note | b0f66c6c-4386-52f2-a974-ab8e03e43413 | – – – – – – – – – – – – – – – – –
| note | 74013d62-7706-5a32-bac2-004f3d5a59f4 | VERIFYING DOCUMENTS: This ITP
| textbox | 74a985ee-8682-5c77-87ed-101c0c89014c | Date Completed:
| checkpoint |  | 3.2 Remove existing fencing (if applicable)
| note | 35e96f31-a170-552a-be9c-e96a2c7adae2 | REFERENCE: Vic roads 707.07
| note | e9e21c94-9fcd-554a-8436-b8a0aea501be | – – – – – – – – – – – – – – – – –
| note | b86ff84c-18d6-58cf-bb5c-bcc7a3d776ea | ACCEPTANCE CRITERIA:
| note | f12edb72-2b09-52d9-bb81-57df0703d698 | • Backfill and compact all holes left after removal in 150mm max layers to same relative compaction as adjoining ground material.
| note | 441f5833-cf0c-542b-b7b9-1f266b79879d | • Total length of fence removed:
| note | 1f1368c4-3244-5103-8aa7-183ebdc86c60 | – – – – – – – – – – – – – – – – –
| note | 66ae87e6-8c0c-59a2-90c3-4aad07fea845 | METHOD: Visual
| note | cc50159e-ad4b-545e-8453-6f6a7d32dbb5 | – – – – – – – – – – – – – – – – –
| note | 00e10a2d-a47c-5971-95ad-3dee9d82c3b3 | FREQUENCY: Per Area
| note | 93f6c9ba-3c56-5ee1-9822-2c79372d80e7 | – – – – – – – – – – – – – – – – –
| note | 65f05137-8f60-5100-9aa3-0f8956d338e3 | CATEGORY: IP
| note | a35da1a2-6b47-594e-9085-110d0b01b50f | – – – – – – – – – – – – – – – – –
| note | 0df0f04e-2eab-5b22-8606-d51d7e90c63f | RESPONSIBILITY: SE/Site Supervisor
| note | 581e0cfa-7970-557f-8b6f-ff1ecb7bed0e | – – – – – – – – – – – – – – – – –
| note | e5193277-e21d-50a6-b45c-ace5cce8ab5b | VERIFYING DOCUMENTS: This ITP
| textbox | d804a1c3-b8de-59eb-9587-cd57e8875266 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Neatly excavate/drill holes for posts
| note | 733f4108-d4e0-5512-b63e-6f7fc7c7d7c1 | REFERENCE: IFC Drawings
| note | 62aafb59-8cce-5926-9d9c-2895d3960e87 | – – – – – – – – – – – – – – – – –
| note | 349c6973-84fa-5da4-8255-6ed85f083ce3 | ACCEPTANCE CRITERIA:
| note | a0579d85-255e-5d05-95aa-80ed065fbdbd | All open excavation should be fenced.
| note | e9fec84a-5bf5-5327-89eb-d98ec96798f7 | Follow asset owners guidelines for work around their service.
| note | d657b935-69e6-5046-ae6b-bf0a50763b8b | Post holes to correct dia. and to the concrete footing as shown on the appoved drawing see item 4.3.
| note | e8b7d291-51cf-51cd-bf8f-dfb9bcf84248 | – – – – – – – – – – – – – – – – –
| note | 27c727a0-e6e8-5495-863c-7d1b60b49386 | METHOD: Visual
| note | 013be81b-9f9f-5843-ab57-08a80b2d64be | – – – – – – – – – – – – – – – – –
| note | 6786fda6-21b6-56c8-8e62-d3d7f97aba02 | FREQUENCY: Per lot
| note | a5c474bc-8dc6-5326-beec-557c131017bd | – – – – – – – – – – – – – – – – –
| note | 47fa988e-f72a-589f-b7ba-53d75a0f6fc2 | CATEGORY: IP
| note | efe4567a-8c08-5576-a321-420a8eb3e372 | – – – – – – – – – – – – – – – – –
| note | c86d49c1-0c99-55c2-83c4-09f3d8b78ae3 | RESPONSIBILITY: SE/Site Supervisor
| note | 44369884-cbe7-5a3c-adb6-0da470a8a019 | – – – – – – – – – – – – – – – – –
| note | da0bc0e6-eb28-5c82-90a9-667b633cf225 | VERIFYING DOCUMENTS: This ITP
| textbox | 4e0c551f-98e3-5e71-8f87-0523dedce282 | Date Completed:
| checkpoint |  | 4.2 Ground Conditions
| note | 958e9c80-17bb-507f-a044-ae7d91544047 | REFERENCE: IFC Drawings
| note | 8dc78270-23dc-5e4f-bd78-456781f31ab0 | – – – – – – – – – – – – – – – – –
| note | 3d6db5e2-33ca-5e73-b0a7-43fbaef4958f | ACCEPTANCE CRITERIA:
| note | 073e3faf-2740-5bcf-93e6-58c6d3fc793a | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
| note | 9023b6d2-412b-5d9e-b080-779a7dfd5db8 | If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
| note | 744ab7ad-af5d-5b85-a62c-c48d605134c6 | – – – – – – – – – – – – – – – – –
| note | 4577c4bc-fb5c-501b-a073-0fd0383f5cd9 | METHOD: Visual
| note | 43f0d0c3-bb0a-5d8d-8b47-c425fe0eaa7b | – – – – – – – – – – – – – – – – –
| note | 400e4300-9c81-5f39-9f2c-397ac3cea16b | FREQUENCY: Per lot
| note | 55c43eca-ea93-5a3a-8189-8ff0f588d6dd | – – – – – – – – – – – – – – – – –
| note | c54d2086-5fc0-58d0-af92-19a777ed1f0a | CATEGORY: IP
| note | e92d7ae3-220a-5c9a-8323-fff23cb3fa98 | – – – – – – – – – – – – – – – – –
| note | 49df813d-1654-5006-b28a-3e1076008f16 | RESPONSIBILITY: SE/Site Supervisor
| note | cac7226b-3183-59fa-aa24-1c7c9f4331d2 | – – – – – – – – – – – – – – – – –
| note | 2c1505b1-f820-52d7-9314-51a025ae9c95 | VERIFYING DOCUMENTS: This ITP
| textbox | 3053fb11-6f04-5bd6-9410-1e7ed50298bf | Date Completed:
| checkpoint |  | 4.3 Post Foundation (Weld/ Mesh)
| note | e75bfd31-d2f7-5cd5-a052-8c218e6ac462 | REFERENCE:
| note | bfe6e37e-565f-5015-9c6f-32e949dbeba0 | IFC Drawings
| note | 6b12f710-b01b-5776-9e6d-1439d2fbcdce | VicRoads Section 707.04e
| note | 65710999-1c73-5f03-803e-b8ee91e7b68e | – – – – – – – – – – – – – – – – –
| note | de30b9e9-6529-5c42-9dff-1f6ef0ff46e6 | ACCEPTANCE CRITERIA:
| note | 62ae0d0c-33e2-557f-ae1c-e9454284e26e | Concrete footing shall be set as shown in drawing or to be 600mm depth and 200mm in diameter.Minimum 550mm embedment.
| note | 295c324b-def4-54a5-aada-1656de8bd615 | Top of concrete crowned to shed water.
| note | 81ff9d9a-7693-5efe-a346-8062b092e268 | Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete
| note | e5fbda9d-9f32-5f89-b3f7-91987eb75275 | – – – – – – – – – – – – – – – – –
| note | f5dca471-d655-551f-8753-e3e4bf57d8ab | METHOD: Measure
| note | 83397b4e-3583-5856-9cf7-211d372e155b | – – – – – – – – – – – – – – – – –
| note | 56829c60-47e6-5e72-b388-141f4a4f50d8 | FREQUENCY: Per lot
| note | 6151ebb1-a5ab-5be1-b49f-9172bb55af9f | – – – – – – – – – – – – – – – – –
| note | e1ee903a-5863-549d-b772-90192391566a | CATEGORY: IP
| note | 93d270d5-c370-5367-a8d7-ed130c65e6dd | – – – – – – – – – – – – – – – – –
| note | 76313991-a503-5cc4-8237-223d5d1a2376 | RESPONSIBILITY: SE/Site Supervisor
| note | 0bc4cfc4-4073-59b9-b55a-81e152573266 | – – – – – – – – – – – – – – – – –
| note | 71a8c343-3b95-5fff-a9d7-0a74e212ed73 | VERIFYING DOCUMENTS: Post and concrete dockets
| textbox | 898af719-4d03-52cd-992a-aed7ce5b201a | Date Completed:
| checkpoint |  | 4.4 Post Foundation (Timber post with Chain link- guard Fence)
| note | 8a886257-37a6-5f17-bd77-312921751aa4 | REFERENCE:
| note | 5d6c4059-61c9-5fde-b58b-0f13d06603a0 | IFC Drawings
| note | d193e1a6-ed58-5a0e-a4b7-22ee0fd9abbe | VicRoads Section 707.04d
| note | 94fc1d8b-b7e0-53f9-9f9f-411925a6930a | Austroad
| note | d9fc5698-4eb0-5f4d-848d-d8ed9b9fad3d | – – – – – – – – – – – – – – – – –
| note | 3092d645-dbcf-5b9c-b688-540bf9d4a1b5 | ACCEPTANCE CRITERIA:
| note | 57ff1c68-b593-51da-8f93-4d59504ba398 | Concrete footing for end post at 750mm depth and 600mm depth for all posts.Diameter of 250 to be used. Minimum embedment of 300mm.
| note | d75cfb92-15aa-55ca-851a-699b3ba7842f | Top of concrete crowned to shed water.
| note | f433b384-f102-5463-b19d-078e0140a502 | Footing to manufactures detals
| note | c32f6c63-e5df-515a-9532-13395bf1f176 | Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete
| note | 7cc2976c-f81d-5167-b3f4-be3bb5f333a2 | – – – – – – – – – – – – – – – – –
| note | fc0cfd3c-7630-55ac-8b85-ea8c3ff4653b | METHOD: Measure
| note | 4d29ffca-8f35-518b-bf06-9f37b87423a2 | – – – – – – – – – – – – – – – – –
| note | d8d0d640-e541-5770-be37-455d4663650e | FREQUENCY: Per lot
| note | 1b71f2fd-a367-59f7-8adf-739f54d9b66a | – – – – – – – – – – – – – – – – –
| note | a181be14-9084-5d75-999e-095f938eb399 | CATEGORY: IP
| note | 3faf6416-26f5-5ac6-b39a-4552c91156bc | – – – – – – – – – – – – – – – – –
| note | 70574c73-a9ec-5044-98d2-41ac04e24f0f | RESPONSIBILITY: SE/Site Supervisor
| note | 409a305f-65c3-5347-b9d6-666b94e450f3 | – – – – – – – – – – – – – – – – –
| note | 9e02636f-e886-58e9-a0c8-c499cfecaebd | VERIFYING DOCUMENTS: Post and concrete dockets
| textbox | 28cd842a-91c2-5f19-9df2-983d604775da | Date Completed:
| checkpoint |  | 4.5 Post Installation
| note | e1cf4002-b472-5a22-8dbc-9fb68c3e271f | REFERENCE: IFC Drawings
| note | 0e6bd91d-a1cb-5eb0-ad2a-7b878bc59f36 | – – – – – – – – – – – – – – – – –
| note | 5676dda3-254b-5fca-95fc-1fa97e6c847b | ACCEPTANCE CRITERIA:
| note | fff61956-1089-50a7-bfa9-9f6a0497c6ab | Maximum post spacing to be 3330mm for both end panel and intermediate panel.
| note | 97a6bdc0-4546-5d42-b54e-de65fb8117a8 | Max. post height 1890mm above ground level.
| note | 19c0fe5e-099e-5f77-92df-d1c5aa541171 | Galvanised weather cap installed on all posts.
| note | 3c7e7a2f-f248-5671-9c42-e376ea8ac26d | Posts to be installed vetically within 1 in 50 plumb.
| note | 540345a1-cab2-55f2-9079-ca99ac4e2950 | Black powder coated post and rails.
| note | 93bb2b6e-29f3-5731-af94-eb09d0d5115d | Wooden post 100mmX200MM guard fence post with two 36X18mm slotted holes X445mm height
| note | e37224b3-f5ae-5f99-9f9a-4eaa33d75ffb | – – – – – – – – – – – – – – – – –
| note | 7f495bb1-bf6f-5bc7-bf4e-b06cade9882b | METHOD: Measure
| note | de4f1b35-4c6b-5107-ab81-c9d8b0f92a15 | – – – – – – – – – – – – – – – – –
| note | 08d0440e-ff86-5fd2-9f7b-a08bf5d820cf | FREQUENCY: Per lot
| note | a1ab3468-0dc0-530e-9348-3be125cf17c2 | – – – – – – – – – – – – – – – – –
| note | adabe96b-b40c-5ee6-9c45-bb5d810bfef5 | CATEGORY: IP
| note | 0f2e07b6-4d83-5b58-954d-c14bed315f4e | – – – – – – – – – – – – – – – – –
| note | 3f80a675-cbcd-5948-9047-eba79e2ddde1 | RESPONSIBILITY: SE/Site Supervisor
| note | 8671e59a-1cd4-5813-ad4a-08b5c38e2c60 | – – – – – – – – – – – – – – – – –
| note | a82d567b-bf49-5de2-99ea-2cff65e8fbad | VERIFYING DOCUMENTS: This ITP
| textbox | 133454d0-b70e-5150-a680-0e35b2f8ffb9 | Date Completed:
| checkpoint |  | 4.6 Chain Wire Mesh Installation
| note | 98539974-562b-5230-91c4-ac3eb3dfef3f | REFERENCE:
| note | 38d8ad66-beba-5a75-bc88-58a71f0e8e69 | IFC Drawings
| note | cda75177-45bf-5537-8bb3-d151e20390d0 | VicRoads Section 707.04
| note | ebb096f0-5d02-53ff-853a-67640251d2a2 | – – – – – – – – – – – – – – – – –
| note | 47244479-65d7-5a66-9427-681e9b523c2d | ACCEPTANCE CRITERIA:
| note | ae25ec59-c4a5-5f41-ad1a-1b98c2aac070 | Chain-wire mesh 3.15 heavily galv. wire with nom. 50 pitch (W10Z) to be tightened and fastened to post and line wires (Support cable single 4mm Heilcoil and diagonal bracing cable twin 3.15 twisted)
| note | ce354506-eca2-59e5-9b64-f8861e71de1e | Chain wire to be fastened with 2.5mm dia. galv. tie wire or clips. Spacing to be not more than 400mm intervals on line posts and not more than 500mm intervals on line wires.
| note | 224611d4-6421-5537-80da-117ef6daf099 | Weld mesh fence to have balck powder coated finish and /or chain link fence to be black PVC coated with balck powder coated post and rails.
| note | 66e5418e-17ab-5362-bde9-ede1c46ad329 | – – – – – – – – – – – – – – – – –
| note | 0feab572-c4a1-5210-8def-794c83c219b7 | METHOD: Visual
| note | ee3471a1-2ac5-5a8e-b993-ad5d71ff6969 | – – – – – – – – – – – – – – – – –
| note | 3e28c12f-2ee4-5d37-8417-7961b2a5f358 | FREQUENCY: Per lot
| note | 6efc7dc6-49ee-5144-998d-65e88a186140 | – – – – – – – – – – – – – – – – –
| note | 63952159-4966-5429-a6b3-7eba022fc818 | CATEGORY: IP
| note | 06ff59d6-1c0f-524e-bb4c-a98a6df53235 | – – – – – – – – – – – – – – – – –
| note | ba5524ea-8fa5-55fb-9733-adae5c83f254 | RESPONSIBILITY: SE/Site Supervisor
| note | 6cd4a350-e7e4-5cb6-ba25-3e644e00e140 | – – – – – – – – – – – – – – – – –
| note | 0717b184-48e5-523e-b740-d929819220d7 | VERIFYING DOCUMENTS: This ITP
| textbox | 4b6fb639-6163-5c82-8770-d9464ec70ad0 | Date Completed:
| checkpoint |  | 4.7 Bracing
| note | e07046bd-9692-55e7-8126-3360be3d44e5 | REFERENCE: IFC Drawings
| note | 10dac721-af6c-5674-81b8-42dce47f5ee6 | – – – – – – – – – – – – – – – – –
| note | 73b6f350-38e5-59e3-8aae-205e2ce0c87a | ACCEPTANCE CRITERIA:
| note | 21882c14-84b9-5287-a26c-da9ca84c5806 | Tee Clamp T5032 and Cross clamps used on posts.
| note | 5965c7af-0a77-5307-80f7-faf31f6230ca | Bracing to be installed on both sides of the fence at the fence corners
| note | 6a1ccca4-9053-543a-8354-25338bcddffa | – – – – – – – – – – – – – – – – –
| note | 0945b879-09e5-5001-a5b2-a02fc0a98780 | METHOD: Visual
| note | dd81c37f-c98b-551c-8513-243026107512 | – – – – – – – – – – – – – – – – –
| note | e7bf8567-2498-559f-8142-b515a4b225b9 | FREQUENCY: Per lot
| note | 9671866a-5b30-58e1-8386-b7b79e63cfbf | – – – – – – – – – – – – – – – – –
| note | 64bbcbfa-6fae-5e73-9e2f-77854ea4da0b | CATEGORY: IP
| note | c627fa5b-9b7d-5f29-a78b-7e91eebb2dbe | – – – – – – – – – – – – – – – – –
| note | 25f3fd8a-ded9-5b9d-9da1-9e46caabaecc | RESPONSIBILITY: SE/Site Supervisor
| note | 2d147b64-2c99-5f57-a341-a2cf13adb8cc | – – – – – – – – – – – – – – – – –
| note | 078487c9-c919-5f7c-8d48-806d404d8649 | VERIFYING DOCUMENTS: This ITP
| textbox | af264cea-bccd-5649-b950-fd488efa4498 | Date Completed:
| checkpoint |  | 4.8 Install Gates
| note | 72f1aa31-21af-53fe-a8e0-616982e3ac62 | REFERENCE:
| note | 9a69928d-d52d-5379-a9c5-8b2e9030eb76 | IFC Drawings
| note | f4222686-4a63-546c-8e0f-37e2948c2514 | AS 4680
| note | 6b0d27e3-5d1a-5087-aa11-b46ca0743df0 | VicRoads Section 707.03(h)
| note | 93fa095d-37e0-5402-a31d-a7c70f14aa18 | AS1742.7
| note | f4eddacb-ed66-5c01-bfa1-12f50563622a | Vic roadsTraffic Engineering manual Vo.2
| note | 8837879e-eb65-5b0b-834e-002505ebf047 | Victrack Design requirements
| note | 0b90843f-f8e3-5436-bec0-9e70b6f76eb4 | – – – – – – – – – – – – – – – – –
| note | e0f17b47-54c2-518a-b373-d2f2aa3997e4 | ACCEPTANCE CRITERIA:
| note | 252052d3-a3f3-519f-8303-0bff31e99a9a | Gates shall be standard proprietary manufactured items with galvanized tubular steel frame
| note | 82130735-d106-5fbf-9491-93e2a702bd68 | For VictracK:4200 opening double gates located at private access roas entrance
| note | 7458ae14-213f-5c2c-a628-99e4a54c565b | Hinges, catches and other fittings for gates shall be standard proprietary manufactured items fabricated from grade 250/300 structural steel and hot-dipped galvanized -
| note | 4062a78b-ae75-5102-8092-d0f03d925f2d | All gates are to be inward opening towards the rail easement.
| note | 98a3bea5-195f-5f2e-8252-7a2e9843d6a7 | All gates to have signs as listed facing outward and all sign fixing to be vandal proof.
| note | f8573c4b-b01c-5138-9146-919b0285b68a | – – – – – – – – – – – – – – – – –
| note | a9397e32-4cdf-56f4-82f7-2ae41e04ca89 | METHOD: Visual
| note | 7d8138c1-266d-52f3-9036-19811efad7d0 | – – – – – – – – – – – – – – – – –
| note | 3231b458-e1fb-5d0f-b7aa-337d80fc28b8 | FREQUENCY: Per lot
| note | 21c466ad-c434-558f-b52c-9adb96b76582 | – – – – – – – – – – – – – – – – –
| note | 4829bf6d-524d-5476-a9a4-ac5b40d4bec5 | CATEGORY: IP
| note | abf17493-934d-5f9e-b660-c2fd321b4ff1 | – – – – – – – – – – – – – – – – –
| note | f8ea95c1-0900-5154-9c12-86009abcfd05 | RESPONSIBILITY: SE/Site Supervisor
| note | 1cc95e01-f188-5886-bb8a-f559044b5901 | – – – – – – – – – – – – – – – – –
| note | 07bbb73b-8512-5dd4-882d-1f9dd3c06e99 | VERIFYING DOCUMENTS: This ITP
| textbox | f833da2c-6e0d-5b8e-b1b7-5edbb58bf3c4 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 Fence Height and Track Clearance
| note | af675950-2836-5d71-9ed4-0ff8a327ac6b | REFERENCE:
| note | 1572bd57-51bb-5881-a1c1-81a7fb343abe | IFC Drawings
| note | 81de793b-1c30-58a8-afa4-facec75d9e22 | VicRoads Section 707.08
| note | 9536ebc6-ead1-5f22-b1df-5e4f79974a87 | – – – – – – – – – – – – – – – – –
| note | c8e7aac6-d936-5894-9fa5-2d3040cd473b | ACCEPTANCE CRITERIA:
| note | 28904873-976a-5c29-8b6f-0bd2ca5b927a | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
| note | b0fb2179-b680-52a7-b68d-a7c6379ba38a | Vertical tolerance of ± 20mm from the design line, longitudinal line tolerance of ± 20mm in plan view, tolerance on verticality to be 1 in 50.
| note | 075c7ca1-862a-542e-9777-495f3c02978e | – – – – – – – – – – – – – – – – –
| note | 45311e0d-a71c-5ec5-8a60-5a69003acb26 | METHOD: Measure
| note | c287e80f-ba1e-5655-a9ae-47776f98acc9 | – – – – – – – – – – – – – – – – –
| note | cabbeadb-0ed8-596b-aa45-22896bbfc0b3 | FREQUENCY: Per lot
| note | 731d1a22-bd27-5842-9362-c3804053180d | – – – – – – – – – – – – – – – – –
| note | 9b8899e9-3bd2-5c82-8838-e1ec10a3edbd | CATEGORY: IP
| note | 33f8ffb6-3b31-5c1c-a8f2-f9f17320d65c | – – – – – – – – – – – – – – – – –
| note | 796ae6b9-16c1-5815-88ee-b8ca58cef8f3 | RESPONSIBILITY: SE/Site Supervisor
| note | d84c5a57-bba4-5cc4-a7a1-32a59c23ed1c | – – – – – – – – – – – – – – – – –
| note | 24c9ed83-1f82-5260-8b08-4772235f63aa | VERIFYING DOCUMENTS: This ITP
| textbox | 32060e9a-af6a-56ae-9693-625109341b68 | Date Completed:
| checkpoint |  | 5.2 As-built Survey
| note | 346b18a7-55b7-5726-9d56-1c0189c4e953 | REFERENCE:
| note | d9900064-a500-55c9-b950-fce980ed2cbd | As Built Drawings
| note | d988cf78-2a94-52e9-9267-78bac08ca7c8 | Asset Change form
| note | 19f9a8fd-cf94-56b5-a5eb-c01efa4aaa56 | VicRoads Section 160.A8
| note | adc993c6-4261-54cd-8a28-c08b1d7442a6 | – – – – – – – – – – – – – – – – –
| note | a4147b06-76ad-57c0-81d8-9bcbe70a2336 | ACCEPTANCE CRITERIA:
| note | b3747ef7-cebc-5d46-a7c7-07839edc9251 | Survey activities undertaken to validate correct construction
| note | 2e64d3ce-960f-50e1-b9fd-afb8cc62ea08 | Attach:
| note | 2da0645f-f143-5cfb-bcd7-6b487641737a | – Survey Report
| note | bce3e37b-2cf8-578d-9473-772a83ef58cd | – Engineering Asset From
| note | 1191a8ee-e7fa-59b5-a954-a51c01456ccc | – – – – – – – – – – – – – – – – –
| note | 11262c8d-4c29-5cf8-b9a7-92d4f0d1cba2 | METHOD:
| note | 342af1de-8d38-58b9-8e59-cbb32cb514d0 | Survey
| note | fc89d471-2509-582e-93b0-afc1b7849dcc | Document Review
| note | bb28fc41-e8b3-5186-8284-19008c3727da | – – – – – – – – – – – – – – – – –
| note | 1aa90ac8-a567-5676-a202-d6d18e7bb795 | FREQUENCY: Once
| note | 23fa7108-1c5c-50a6-9524-1779a502def3 | – – – – – – – – – – – – – – – – –
| note | 80e717ff-a081-5109-912b-b96e02fdd6d3 | CATEGORY: IP
| note | 3d379e40-2515-5dc2-a36d-4320f6e2e650 | – – – – – – – – – – – – – – – – –
| note | 6cbbe97e-da7a-577d-8b8d-d3d34f380958 | RESPONSIBILITY:
| note | 47173a63-f872-5871-8e4c-130c9b9b3862 | Track Surveyor
| note | b8966faa-4c1c-50ab-9f98-fedd9bae208d | Site/Project Engineer
| note | 30055809-cfa7-519a-966d-7cc48552aa2f | – – – – – – – – – – – – – – – – –
| note | 21e13957-9e52-56ee-ae93-bff0d2e8a4dc | VERIFYING DOCUMENTS: This ITP
| textbox | 4b32f474-329f-5912-a53a-e6ed94ee1d7c | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 237644ea-54d2-5120-a3ea-02368e0ee0ca | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | c1cba1ad-ebc3-5680-96d1-f5ce5bc2eb83 | Name:
| textbox | 72be8177-24ec-5180-b9a4-7fa0c33a660f | Position:
| textbox | 37b2b326-9e63-545a-b863-e33833c21e2b | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Grout Pedestals & Bearings Rev 0 | itp | ITP-STR-Grout Pedestals & Bearings Rev 0 | 28b08d55-648b-4e8f-85d0-30a3e82486b2
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 4dd9acf7-0e05-4e7b-a76f-89562db69dc9 | Document Title: ITP-STR-Grout Pedestals & Bearings
| note | 91da737c-46df-42f4-9295-4e74b87f6f54 | ITP Description: Grout Pedestals & Bearings
| note | 09ed3498-ff71-435c-b89d-5e36f45ff31a | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | a4055b08-120a-4355-a7f4-f02e5b4cfd6a | Discipline (e.g. CIV/STR/RAIL): STR
| note | d09ecc4e-9f8e-4ae0-b33a-0a7792bb00dd | Revision Number: 0
| note | c06879b8-91ce-49fb-9e4d-ec97abe01f17 | Revision Date: 14/04/2020
| note | 1a10f18b-e4c9-43f0-883c-b242fd2ec522 | ITP created by: Mike Freeman
| note | 6d6c1905-7a80-44b1-983a-3d380302accf | 1.1 Reference VicRoads Section 610 November 2018
| note | 642b7ec0-1538-4482-beab-c03828a49e4e | 1.2 Reference VicRoads Section 610 March 2019
| note | 820a3a32-a46a-42f2-9f9a-5ebc967253a8 | 1.3 Reference VicRoads Section 610 June 2019
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Product Selection
| note | 71431e8d-3bfb-47d6-b10d-0518c3e83179 | REFERENCE: IFC Drawings
| note | b1115e6e-acc5-4fe9-98fc-83dc3d61b4eb | 610.28
| note | 820d30fb-df50-4aec-bf21-21a0b7584041 | 610.33
| note | 79d2c525-023a-44bb-80e8-7b978b60ce4d | ---------------------------------
| note | d79b59d4-1626-4ec1-a645-04a24a930297 | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | 055f2a9c-2948-4e6f-bfcd-3ad9fc714cf7 | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
| note | 0427a312-f6cf-4117-b7cf-c8069dd059ab | ii. have the required strength at 28 days as noted on the IFC drawings.
| note | 62db0505-9245-4283-b507-525f48b5a393 | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
| note | 7cfff605-f3e8-4c03-b140-f5116c652932 | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
| textbox | 7dc68426-bbcf-43b3-99a8-62e3ac798927 | Enter: Teambinder Material Approval number
| note | f88966e5-c6b4-41f5-ac93-de343424a079 | ---------------------------------
| note | 88e0f2a1-f479-463f-98d4-6cb7f3155942 | METHOD: Document Review
| note | 93de0e62-186e-424d-a81a-20bcbd3df201 | ---------------------------------
| note | e0e4e433-da96-42b9-99b7-3b9cf341ba49 | FREQUENCY: Once, for each product, prior to placement of product
| note | d5e4fa0a-90e5-4677-ab73-b1d799959129 | ---------------------------------
| note | dd15df7f-4c0e-460e-84d5-57ec1cd79a18 | CATEGORY: IP
| note | d5fb30a8-4b85-4589-b891-5c386aae4b1b | ---------------------------------
| note | 10dda394-7fe3-4a32-a828-17fffbee515f | RESPONSIBILITY: Nominated Authority
| note | 19b94f05-1e30-4bfd-b1d8-f172144c5bf0 | ---------------------------------
| note | 3dd9d5db-2d7d-49b2-af8d-01421e0168cc | VERIFYING DOCUMENTS: This ITP
| textbox | 84025396-e906-46fb-83b4-15a6718d6d92 | Date Completed:
| checkpoint |  | 2.2 Curing Compound
| note | 1a4b16f9-23fd-4f4a-b0d6-ece43c3aaab8 | REFERENCE: 610.23 (d)
| note | c2d8ad92-27d9-4698-b693-d6f96bd15c10 | ---------------------------------
| note | 6b85fa59-8b7b-4fb5-bd90-e6eb13106921 | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| note | 2c8bd1bc-d98a-42f0-bafb-8d6aa3709aab | Note: This may be the same product used for the concrete curing
| textbox | 04f34b39-f7af-4e26-af29-051ebb30d615 | Enter: Teambinder Material Approval number
| note | 649150eb-04b1-4fa3-b59c-1f3f130177c2 | ---------------------------------
| note | 9b8e6d18-0f02-43db-9618-ec0e37f72d4c | METHOD: Document Review
| note | dd512f1f-70f9-4dbc-85a0-715763b72381 | ---------------------------------
| note | 68f777be-2d12-4e87-aeb6-014844dfd5a1 | FREQUENCY: Once, for each product, prior to placement of product
| note | 9d1675b8-1562-4fda-abe7-e473b80f805e | ---------------------------------
| note | 05394268-5732-43a7-92a9-2769e399ab57 | CATEGORY: IP
| note | d8a46715-e48f-40b8-add8-510045bcd3ad | ---------------------------------
| note | 77304e91-b1b4-4334-9d80-b5e222b37cad | RESPONSIBILITY: Nominated Authority
| note | fbffa804-fa6a-49c6-9243-505e2ad779c2 | ---------------------------------
| note | 1a9ac34e-0b74-4026-9c32-5bcebc1a13af | VERIFYING DOCUMENTS: This ITP
| textbox | 521858d5-0b3c-42d5-a3aa-ca349fcc1b1b | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Curing Methodology (for Concrete, Grout and Mortar)
| note | 8058aaae-07a0-42ec-ae79-f5d708d40be7 | REFERENCE: 610.23 (a)
| note | 770e4bbe-e539-47e9-aa24-3e4478f8d211 | ---------------------------------
| note | d928d8e0-d55f-4dfc-a7dd-efc5e45e9185 | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
| note | 75f18139-bcbe-47e6-9427-824bb6056bcc | Note: This may be the same document used for the concrete curing.
| textbox | b1bf04d8-0245-481f-bdbf-aeb2811cdfe2 | Enter: Teambinder Correspondence Approval number
| note | fdd751ae-0d8b-44e2-bf64-1ed18463db1b | ---------------------------------
| note | e8b8b5ea-0d04-4aa3-abfa-8c25367e1cb8 | METHOD: Document Review
| note | b875a025-cde1-4a75-983c-029e5db04bb2 | ---------------------------------
| note | dc023b48-553d-4448-a881-80bf8c383deb | FREQUENCY: Once, 4 weeks prior to placement of product
| note | 8ee6c76b-47bd-4e89-bf9b-fc762eeadd5f | ---------------------------------
| note | 53ca9c4e-8097-4b8b-905e-86f5ae69fcf9 | CATEGORY: HP
| note | 187cf180-b8e6-4698-b0cf-4e429be1e4d2 | ---------------------------------
| note | 015d471b-4ee6-4d72-8150-b0baf5bb452e | RESPONSIBILITY: Nominated Authority
| note | 530f3c94-f6e2-4ed6-b6a4-7624b3fb8af5 | ---------------------------------
| note | d72f6723-5478-4f7b-bb88-2993099f49c7 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b9960d6f-8e9c-4888-ac15-6239fc9e7139 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 IFC Drawings
| note | f24f69ac-9dd4-422f-8af2-e5ffd6d95422 | REFERENCE: MRPA Quality Management Plan
| note | 38c9d738-57a5-475b-ae8a-90eb85bc4165 | ---------------------------------
| note | 8e55c4c1-6951-4ef9-879e-26b8322c1556 | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 9811b88a-709c-4aec-8694-5ea7e05769e8 | ---------------------------------
| note | b66332b7-586e-4894-a063-a9623d960a7d | METHOD: Document Review
| note | 34c2efac-f7c3-4220-bba6-4e6c48eb40a3 | ---------------------------------
| note | 4a028a95-6009-4982-aa18-db65bd913d3f | FREQUENCY: Prior to starting Works and at regular intervals
| note | 1c6e5cb2-2603-4c42-8153-6201489444cb | ---------------------------------
| note | 3645238f-7808-417b-9bbd-0c86c48f2640 | CATEGORY: HP*
| note | 3b080dd1-3929-438b-bcff-f58925695a44 | ---------------------------------
| note | 416e3b93-a193-4c85-b564-6e093bb940e2 | RESPONSIBILITY: All
| note | 9084c612-273d-4b12-bc29-5a9e424068b9 | ---------------------------------
| note | fe7833a3-1114-496d-901e-e682e5b746f6 | VERIFYING DOCUMENTS: This ITP
| textbox | 3c40760b-0718-41e9-8c0f-acfb21ae77eb | Date Completed:
| checkpoint |  | 4.2 Survey Set-out
| note | 369a6bfe-c6d8-4b19-aa13-0ac081055651 | REFERENCE: IFC Drawings
| note | e07485fa-5aae-4399-9595-17431fe3c841 | 610.46 (a),
| note | 0ce546a3-5d3d-44b9-b1c4-003c4fac0452 | Table 610.462
| note | 816a63d6-dd65-4dac-a14a-38be1aa73003 | (Nov 2018)
| note | 6e68b0f4-e75f-4d7e-b085-bc742cafe447 | 610.47 (a)
| note | ad7fc1ae-7cca-4e0a-a245-84a9550329a2 | Table 610.472
| note | dc6c8cd8-d877-41ca-b438-e117cc3c545e | (March/June 2019)
| note | ef4a682b-e936-4fa1-8602-c38c6114e949 | ---------------------------------
| note | f7111c68-4909-4198-bc37-1f739c3eab1a | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
| note | 84fff597-75ac-458b-90e8-a6822c01a6cd | Note: Different revisions of 610 have different clause numbers
| note | ddf9e83a-cc50-4e39-934f-f848118815ce | ---------------------------------
| note | 54a8629d-1f96-43da-b3e6-60ff13705238 | METHOD: Measure, Visual
| note | b6f45b18-eb08-405b-9daa-41867f1c415d | ---------------------------------
| note | 4727c57e-dba6-401f-bf03-479849922da4 | FREQUENCY: Each element
| note | e742afcb-96b2-432b-a72c-5ba24c7098bf | ---------------------------------
| note | 4e0ed584-a54c-4a6d-be6c-b8eb0d81afe6 | CATEGORY: IP
| note | 16cb7157-f016-49b9-86ac-97f34d3e4b04 | ---------------------------------
| note | 73af80e7-5663-46d1-8e3e-d4dec63960e1 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 145b240c-2d56-4142-bdda-8491365b65d9 | ---------------------------------
| note | a8489aac-dbb3-413e-9e5a-3aa9a0dc37ea | VERIFYING DOCUMENTS: This ITP
| textbox | 1eabbaa1-a894-47c7-949d-67942858e929 | Date Completed:
| checkpoint |  | 4.3 Construction Joint
| note | d00fa500-5106-464c-b1fe-f00180d1dc62 | REFERENCE: IFC Drawings
| note | 66eff939-c6d8-4090-b707-ec54c5045ff6 | 610.2
| note | 2b875bb3-7b53-4e89-919c-02469b04e2e6 | ---------------------------------
| note | 701dd2f8-2834-4b60-b0c2-bfacd12882e6 | ACCEPTANCE CRITERIA: Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
| note | 4f09ac85-cbe1-43e6-aa03-675c6eb57880 | Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
| note | 8e141ef0-746c-452d-a174-6ee7d894a4e3 | ---------------------------------
| note | 64097dec-63be-4eec-b43b-260fd5a319a4 | METHOD: Measure, Visual
| note | 2af66b43-7e91-4e15-954c-1527610fd685 | ---------------------------------
| note | af4a7f8e-e2b8-444a-9bca-8944f1b6f7de | FREQUENCY: Each element
| note | b4a3b8bb-d0ec-4b7c-bdbb-d54eb3edc2b0 | ---------------------------------
| note | d1fcfae1-226e-45c6-a7b8-2d1cf7cc57c0 | CATEGORY: IP
| note | 946ac162-bd26-4e26-9dae-823b20fad9de | ---------------------------------
| note | e4c811ed-0ed9-478a-b9d0-8bc2d39ef950 | RESPONSIBILITY: SE/PE/SPE
| note | e2a6688f-f91d-4abf-8c7d-12c171603255 | ---------------------------------
| note | a25a4fc3-9400-4f03-91d3-a00643645b31 | VERIFYING DOCUMENTS: This ITP
| textbox | 87c7a8f3-0338-4880-85fc-800cca8bc39e | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 5.1 Formwork Construction & Placement
| note | 3468212b-8b21-401d-af18-1535a2a0c5a5 | REFERENCE: IFC Drawings
| note | 5c2f5a61-9812-444f-930c-5400a1db627f | ---------------------------------
| note | 1c36afa1-1df2-4ba7-a4f7-fa8c63fdc8bf | ACCEPTANCE CRITERIA: Dimensions in plan as per drawings (typically +50mm all around).
| note | 0481189a-46d6-4d41-b962-d917ead12f61 | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
| note | 1193f167-2b55-434e-a7e0-de0a5f66f8c9 | Any cast in componentry (ferrules, conduit etc.) secure.
| note | 6e74d530-042e-46fa-a9bb-c1edcb0acedd | ---------------------------------
| note | 838301b7-6bcc-49b9-aab9-5451917a1f7e | METHOD: Measure, Visual
| note | 8ed14f2c-7f08-49a4-b820-172ac7ca4ad1 | ---------------------------------
| note | f6ff4466-bd9d-40e7-a1b5-bcb7704446df | FREQUENCY: Each element
| note | a27638f5-8f13-46a1-a3d6-b63afeb77e59 | ---------------------------------
| note | 86af0933-cf1a-48c7-b7f4-1d7379624c05 | CATEGORY: IP
| note | 9de4e11e-493a-4409-92a4-662a435a0e66 | ---------------------------------
| note | 19b033ff-8ed9-409b-bf4c-29cde9323411 | RESPONSIBILITY: SE/PE/SPE
| note | aa403202-4afc-4e92-af5c-4bafbc231906 | ---------------------------------
| note | 1cceea89-759c-439a-84b2-472c27e82b75 | VERIFYING DOCUMENTS: This ITP
| textbox | b34130e2-d731-4af9-b571-c5019033e1ca | Date Completed:
| checkpoint |  | 5.2 Pre-pour Inspection
| note | 9d9c3a8b-98b9-4bc3-8227-4283ac1ba370 | REFERENCE: IFC Drawings
| note | 2d8dfbc3-f05e-4e4f-9569-1d20790cca99 | 610.2
| note | 552cd04d-07c5-483c-a1e4-0842f9701de5 | ---------------------------------
| note | 09c89e85-4ea0-49b5-a3f1-2317f31e8604 | ACCEPTANCE CRITERIA: Formwork location and RLs comply.
| note | 5c903287-5aa9-4222-b45c-470bb7e6361b | Any reinforcement has the required cover.
| note | 62c7f6e5-d67d-4105-b28f-9c2f6902e580 | Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
| note | 0127c21d-f714-4303-b836-f7eb8a60627a | ---------------------------------
| note | 61fa233d-7f7a-4ce0-aca4-ab8e20416762 | METHOD: Measure, Visual
| note | 6fc20ee4-366e-4a09-932c-f599326e0d0e | ---------------------------------
| note | c9f46ffc-6e17-49d5-abf0-c5b91b345983 | FREQUENCY: Each element
| note | f823fbd5-4bbf-45ec-bc16-ef9d408a53e7 | ---------------------------------
| note | 1e250d1b-0813-4c9b-b19c-82d73d215696 | CATEGORY: IP
| note | 11207510-a884-4c01-ab40-180c7df381da | ---------------------------------
| note | 74402b5c-e0cb-4c40-8ef8-1c2f93183678 | RESPONSIBILITY: SE/PE/SPE
| note | 4be1060f-1d1e-4da0-95e1-687d963cfe9e | ---------------------------------
| note | 339844c5-7e7f-4c5e-b74c-21ff4536ca1c | VERIFYING DOCUMENTS: This ITP
| textbox | 48af33a6-1a90-4f8d-a7ad-25ef3151aec9 | Date Completed:
| checkpoint |  | 5.3 Weather Conditions
| note | 41a12a18-e8f2-4113-913b-7cc312506f4c | REFERENCE: 610.17
| note | 9f669c4d-8908-42f0-99a7-4a3197b09b48 | 610.17 (a) & (e)
| note | d57bce2a-3936-4e86-87b6-39a8ab5c50b2 | Table 610.171
| note | 7a94edbc-b954-4e92-b5eb-3f2cc6f9f7c6 | ---------------------------------
| note | c207b308-5c75-457c-98f9-7e1792fd8178 | ACCEPTANCE CRITERIA: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | 2fd6cde1-b683-4d0d-8f00-b9616754fb54 | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | 677f1392-2c6a-422b-bf1b-2376230fc465 | Record: Required information on the Grout Pour Record.
| note | c457433c-ef95-4ebe-b714-0537c84d70b6 | ---------------------------------
| note | 36feec68-867f-4326-8762-cf17f8a7be3c | METHOD: Measure, Visual
| note | b9d8925e-18e0-4b4d-99ab-8c763aee41ed | ---------------------------------
| note | 6df3643b-1d88-4985-b04f-028315c4b3e7 | FREQUENCY: Each element
| note | 4026238e-c681-4fdb-b9d8-3e388b85d53d | ---------------------------------
| note | 7a304177-e340-4ca0-9ce3-c1ba150e9828 | CATEGORY: IP
| note | e3a3d844-5666-4a8a-9406-c43f13b89160 | ---------------------------------
| note | a0934c12-5ed1-4a4c-be9d-5d89a0f88947 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 381b53e9-79fa-454c-80e1-4561fc179c3c | ---------------------------------
| note | 5b6b2837-18cc-43a9-8b53-eb398ee23349 | VERIFYING DOCUMENTS: This ITP
| textbox | f85f3e95-3070-4635-9c19-8bdf3eb6e799 | Date Completed:
| checkpoint |  | 5.4 Mixing Product
| note | 62c5ff2b-db42-461a-ae4a-b13ad9dda418 | REFERENCE: Product TDS
| note | 357983b3-4129-4f31-8d8d-937fee5b1627 | 610.28
| note | 3b1fe7fc-f025-4c30-ac2d-d8d472d8aaf7 | ---------------------------------
| note | 94cd88d2-659d-4b82-b224-40b108b2c7bf | ACCEPTANCE CRITERIA: Size of mixer should match the application.
| note | d832c4cf-2bce-44ec-95b6-5e349f1f2445 | Only whole bags to be mixed with potable water.
| note | 0d572403-3b8b-42af-a23f-f2c246eeb897 | Volume of water matches the required amount for flowable consistency and accurately measured.
| note | 81fc89b2-6573-4316-bbab-fe04346332b5 | Product poured into the mixer slowly.
| note | 9e8a177d-dd71-44f3-a448-12ac7f8efaf5 | Mixing time as per TDS so that a smooth, even consistency is obtained.
| textbox | 9c912128-1cf9-4052-b9ec-79ecf9d96d0e | Enter: Required information on the Grout Pour Record.
| note | c465e64f-3a32-45eb-b557-94fa1706b7ef | ---------------------------------
| note | 4abdd61c-7960-4694-9035-d76999e37896 | METHOD: Measure, Visual
| note | 5febf784-f8b2-4e6b-988b-d6672562f8cf | ---------------------------------
| note | 6468d08e-3215-41da-aec3-18fa18568eca | FREQUENCY: Each batch
| note | b5b8cdb5-3bd2-4977-b74d-f14d2a914f30 | ---------------------------------
| note | 6416024d-db80-4047-9bbd-0199baa4bd1f | CATEGORY: IP
| note | fd91dc0d-66f5-423d-a3f7-15fd282ba27e | ---------------------------------
| note | 7413ad29-1413-4ad2-80d3-ee30d9404bc4 | RESPONSIBILITY: SE/PE/SPE
| note | bb267cef-3d75-45fa-b54d-a6a9beeb121f | ---------------------------------
| note | 47621344-61a3-49ee-b33c-569cbd2efc09 | VERIFYING DOCUMENTS: This ITP
| textbox | 99e3e667-c9be-40ee-afe5-254bd31056f8 | Date Completed:
| checkpoint |  | 5.5 Product Testing - Compressive Strength Cubes
| note | 3612c556-04c9-41be-b5fe-35007d795004 | REFERENCE: 610.28
| note | 3e15f98e-8d10-4c39-b66b-5051c08acf5c | 610.33
| note | d80bb033-43d2-465b-aad7-cd124e221d22 | ---------------------------------
| note | 9c04fcdb-c6ac-46cc-9edd-8963cc2107dc | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
| note | a25d600a-f89e-48ca-a087-d8e3125a2a62 | Testing is be in accordance with the following frequencies:
| note | 7ff65cdd-7d93-4c1b-9982-f96cb691bf46 | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| note | 0af1fa84-3d87-4f2e-b5c6-4cb55035cf17 | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| textbox | 34a73ecb-d34c-4cbb-96d6-625c5c76f1fc | Enter: Required information on the Grout Pour Record.
| note | 81800232-538d-4bc0-b888-902ae13947eb | ---------------------------------
| note | 18cec192-7aee-4705-acd4-33a77c86849b | METHOD: Test
| note | 369ff5f4-f8d9-49c8-a803-8797c33deb8f | ---------------------------------
| note | d45de0e0-d29c-45a0-8c6d-c95a131162e6 | FREQUENCY: Each element
| note | 68b7452c-7bf4-4def-bbf4-1d54defca6eb | ---------------------------------
| note | 79e4dd75-8bc7-4390-aa8d-2ee03828280f | CATEGORY: IP
| note | 363d2fe8-707c-4083-a0b1-a2986909dd93 | ---------------------------------
| note | e10e12f3-4845-439e-b0e9-413ba5173c8e | RESPONSIBILITY: Tester SE/PE/SPE
| note | f54b49a7-90b7-4595-960d-c903667438e3 | ---------------------------------
| note | 0cd86247-ff6d-4b17-9dce-ba71508bf4cf | VERIFYING DOCUMENTS: This ITP
| textbox | ba19677f-1f52-4754-89b1-c9d3c7107ade | Date Completed:
| checkpoint |  | 5.6 Placement & Compaction
| note | 0bdaeece-ac04-4970-8a6d-c9e9c005b74a | REFERENCE: Product TDS
| note | 31d4ae86-cb03-4859-9464-67c8fd90485a | ---------------------------------
| note | 928afe18-ad44-4e68-a688-75c091779126 | ACCEPTANCE CRITERIA: All batches are traceable.
| note | 8f433f4a-8312-44da-a8ee-93c5e9be47b0 | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
| note | b3ae9147-78e3-4277-a5ac-f1fc5ea9d047 | Product should flow to all areas and self consolidate.
| note | 9d7cb0dc-c3c0-43d0-888d-746f72a9a272 | Product that stiffens or is showing signs of stiffening shall not be used.
| textbox | 2e92d58b-6c38-4cfb-99ff-3a35ff4af23b | Enter: Required information on the Grout Pour Record
| note | ec075ac1-b6cd-4f56-b1ea-b8f7037ae45e | ---------------------------------
| note | 8891acb0-dda3-47ff-9b5d-b2469ae64aee | METHOD: Visual
| note | 6225fc4c-9795-48ef-89db-26291baf95b7 | ---------------------------------
| note | 4fa24237-0df0-4d18-a41d-cb9918b26795 | FREQUENCY: Each element
| note | 73da03f2-332e-4f1b-85b5-39d8d4f9e1da | ---------------------------------
| note | 3239aecf-4d9e-4596-aba5-915f4e6d3e78 | CATEGORY: IP
| note | 6b18175f-9ce8-41da-9548-ee0b3c76a969 | ---------------------------------
| note | 454f622a-214f-43ee-8868-433ceea8fec3 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | f05f9dd7-7554-4681-b795-addf428ac6c1 | ---------------------------------
| note | 4ae9991c-a337-4ce2-8eb7-4a4e787e99b4 | VERIFYING DOCUMENTS: This ITP
| textbox | 63d803a1-5bfb-4f63-a3f2-7fa49ad9ac54 | Date Completed:
| checkpoint |  | 5.7 Surface Finishes
| note | 77f1bf3f-2bad-4631-a597-ad07a356b543 | REFERENCE: 610.28
| note | 9f5e7d75-ca4f-4039-8230-0e52a3b6fec3 | ---------------------------------
| note | 1c00a77d-4b7b-4930-a694-c6f8345e62d2 | ACCEPTANCE CRITERIA: Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
| note | 79e73d95-f209-4a76-974e-265f65a4841f | ---------------------------------
| note | ad620fa6-f063-4f5f-8d89-455a8c1ed410 | METHOD: Visual
| note | 4a6da960-eee9-42c8-9d6e-321a1ff0e4c4 | ---------------------------------
| note | bc1bfcb2-f329-4c55-9e23-598105ded743 | FREQUENCY: Each element
| note | 9c44c35e-2b8b-4631-8b73-34d297f5b024 | ---------------------------------
| note | e8b4525c-b89a-4699-94f9-f7bca2856d15 | CATEGORY: IP
| note | 707db069-e522-47b5-a56c-91f883ac0170 | ---------------------------------
| note | 7aceaa08-f665-4c51-bc7d-6a61da1f7044 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | cd391b06-4954-4ba1-bef8-1c6f8efaa4ed | ---------------------------------
| note | d10ec90e-aa46-41ee-bed5-df26f842e4ed | VERIFYING DOCUMENTS: This ITP
| textbox | 1bb8c6c4-2356-4b8c-a011-557c28e78a2b | Date Completed:
| checkpoint |  | 5.8 Curing
| note | c5ed8d30-b7d1-45e6-903e-6047e139309b | REFERENCE: Curing Methodology
| note | 2c27c4c7-8c2a-482c-89d8-c90b87d8480d | 610.23
| note | 65f389f2-0565-4dd9-a9af-cd04716ac656 | Table 610.231
| note | fad91218-84fb-44db-9232-9ec27dabb9b9 | ---------------------------------
| note | d106935d-cf26-4c22-9e99-60dab2248fb7 | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
| note | 060bf272-66d6-4724-81d2-d8a077ea48bf | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | 7c5828ae-a1ff-48b8-8b53-231b7d50035d | ---------------------------------
| note | 045c5316-c803-418d-b22d-b92f12c7daee | METHOD: Visual
| note | 7b0112b3-a93c-40a8-b91c-230c0d245510 | ---------------------------------
| note | e2c1fe36-ed23-45d4-a72d-ac262254cbdb | FREQUENCY: Each element
| note | 116b88e4-6c65-40e7-a786-7b205ea855f3 | ---------------------------------
| note | a03dcfd6-b813-4fcc-98e4-83cf4fea834d | CATEGORY: IP
| note | 5ea7460f-28d5-40e4-9ae4-65a9099954a4 | ---------------------------------
| note | a139ee3d-332a-495e-a881-1db0dbfebe07 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | ef1f228f-bbd1-4d22-9e92-b8fb7aa00364 | ---------------------------------
| note | a256b742-c8cf-48b0-844f-72067da3cbd5 | VERIFYING DOCUMENTS: This ITP
| textbox | 4e64f0b0-949c-48df-9e81-e4173d68d91d | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Compressive Strength Test Results
| note | 67314c3a-2c22-4f88-ad67-4256fcf52934 | REFERENCE: IFC Drawings
| note | 558e8317-98c8-4574-9880-1e4c6d8609b9 | Product TDS
| note | b486a1be-73e1-4917-ab7d-975ffc0eed23 | ---------------------------------
| note | b7142bb8-4112-4052-83b7-09ff4bcdd05c | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
| note | 664a4f04-2152-4946-a35b-987702d6da10 | 28 day compressive strength per sample comply with the design strength.
| note | a708a088-93b2-4949-b3c9-48e44257309f | Attach: Compressive Strength Test Results
| note | f8afb7d3-b82f-486c-9f31-c61642740d28 | ---------------------------------
| note | ef5e5eb6-9898-4cb6-a585-a6e0c2212580 | METHOD: Document Review
| note | 213df565-3536-4283-b1e8-cdf94dc07338 | ---------------------------------
| note | 9539a6c9-abf2-4db2-a2d8-b1483ef8f1be | FREQUENCY: Each cube
| note | b2c1e90f-9f89-4ffb-b42a-56e571ca601e | ---------------------------------
| note | c746d5b9-d05f-4688-bbb7-8a9d12bc888d | CATEGORY: IP
| note | b9389a94-9c89-4862-84fa-73a777cc9fa2 | ---------------------------------
| note | ec0be58e-adb1-47b2-9d45-34780e005e01 | RESPONSIBILITY: SE/PE/SPE
| note | a1f48c90-f95e-4088-9a4d-4e582b918da3 | ---------------------------------
| note | 9d1e84e9-a7df-4d3c-92dd-5e0e29af5894 | VERIFYING DOCUMENTS: This ITP
| textbox | 1c4fab6d-d3ba-409c-9e0e-3f02ab82b494 | Date Completed:
| checkpoint |  | 6.2 As-built Survey
| note | 6b26d005-7be2-46b3-aa03-33ce96dc4a04 | REFERENCE: IFC Drawings
| note | 568c8538-48f1-4abe-8191-806d581d2bc4 | 610.46 (a),
| note | d1a1b92f-2c1d-4403-950e-dd25cfc63f0f | Table 610.462
| note | e9bc4779-157c-49b7-945d-9619ca44a7a1 | (Nov 2018)
| note | f4a6ca3d-caba-4602-ad46-40e27da06dc3 | 610.47 (a)
| note | 0aaf6a87-0c2c-4ab1-8ef3-a4dc4fd86cc4 | Table 610.472
| note | c0962709-f98f-4b64-a44b-ac8af409a2bb | (March/June 2019)
| note | fbf39f1e-1903-47be-9b5d-d29d186bb9ff | ---------------------------------
| note | f0cae71b-40f6-474c-8625-c8205ecdbabe | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
| note | 43bb2c1f-69ea-46c0-a28f-cf91782bec6d | Reduced level ±2.5mm
| note | 768ef8e6-3f95-4302-8e43-dea40b852362 | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
| note | cfb785c8-6e38-48bd-96ce-c7d474b1ed24 | Deviation from flat surface ±1mm
| note | 90eb1208-acf8-4d7d-987f-dbc91cdd75c9 | Note: Different revisions of 610 have different clause numbers
| note | f0ad0355-b9a7-4a62-bb2f-d91820b649da | Attach: Survey As-builts / Survey Report
| note | ec378961-3424-4e7c-952b-740a3359fb74 | ---------------------------------
| note | cf4b198d-1401-4129-ad97-530bb578c634 | METHOD: Document Review
| note | 29a174f8-38fc-449c-821b-306f5cdc771a | ---------------------------------
| note | 7aa76585-5320-432a-a7b2-8144e3f27ed5 | FREQUENCY: Each element
| note | f03b3d2d-db38-4cc1-b750-f507177f0d4b | ---------------------------------
| note | 24e421dc-f3af-4e84-94b6-7b2404deca9e | CATEGORY: IP
| note | 2556907d-f468-48ac-a836-3c6c93dd8b36 | ---------------------------------
| note | 41826db3-717a-474c-b119-02a2bac4937e | RESPONSIBILITY: Surveyor PE/SE/SPE
| note | 55de4665-f8e1-4897-8e29-86815f5e30e9 | ---------------------------------
| note | 164e12cb-586d-43e6-a1b8-7f5a54a7f34f | VERIFYING DOCUMENTS: This ITP
| textbox | c52accff-af6e-40a9-b803-73b3bf310885 | Date Completed:
| checkpoint |  | 6.3 Non-conformance Report (NCR) Closure
| note | d9fb0f0c-7c37-4a1a-aac5-f75050feb686 | REFERENCE: MRPA Quality Management Plan
| note | e5b11fcd-00a0-4f11-a758-e9fbfed2dba0 | ---------------------------------
| note | 760eb6b4-bdd1-49aa-a217-4fed73278992 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 355a4e39-0c72-4c29-805d-80afc1426133 | ---------------------------------
| note | c794aff5-0428-4feb-ab67-261945c2ce7d | METHOD: Document Review
| note | d9dc4d83-8e41-45d0-aa8b-2c905e76dfde | ---------------------------------
| note | bcb90547-784f-4011-8709-d45cb2553059 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | e728c138-5dcb-47db-ac5b-012e4f1bfe63 | ---------------------------------
| note | f674bf4e-1ad5-4505-83a6-250f654e192c | CATEGORY: HP*
| note | ed04d055-9b1a-4344-9599-8d737161e066 | ---------------------------------
| note | 330c09ed-5752-4a21-b388-6656ec54c191 | RESPONSIBILITY: PE/SE/SPE
| note | ea014314-f7fa-478a-93c0-ed8f2c1229de | ---------------------------------
| note | efee61d1-7c0f-4320-bf83-b796c36e3d19 | VERIFYING DOCUMENTS: This ITP
| textbox | 7ee43e31-127d-425e-b713-c0dd53b86101 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 13a47ac7-cf7a-446d-8afb-fd9761741d54 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 059dd5bd-bbcb-4222-9e30-d26a0ad7c0d5 | Name:
| textbox | a2418551-e33c-42ae-9eee-c3cc8ecb2aad | Position:
| textbox | 325bee08-f221-4a1b-8292-d85994bfc486 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-RSS Wall - Panel Install Rev 2 | itp | ITP-CIV-RSS Wall - Panel Install Rev 2 | 2df13cb0-f6bc-46c1-be59-53ccdab8e545
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 0a993cce-3bd7-4466-9019-e3801422cb84 | Document Title: ITP-CIV-RSS Wall - Panel Install
| note | 4f84d57d-dc3c-4867-ba00-cd3da485654f | ITP Description: RSS Wall - Panel Install
| note | 7823ec8e-625e-40ba-9511-cafcf95fd263 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 903f97de-bd6e-4f08-9966-7decc0ed809e | Revision Number: 2
| note | c4df0ecc-8f09-4d8b-9468-378d569c4ca9 | Revision Date: 10/11/20
| note | 3b7b0a0b-0800-44ac-8a08-3d6e2184d691 | ITP created by: Khalid Kamel
| note | 6317495e-1790-42d8-84ac-e57d8491138c | ITP approved for use by: Josie Pavlou
| note | 5f4533cd-6795-48df-811f-e480967f190f | 1.1 VicRoads Section 682 Nov 18
| note | 177d23db-3052-4786-a39f-728c635575b8 | 1.2 VicRoads Section 620 May 09
| note | fa52a2a9-68e3-4048-aab6-0c44d6c12081 | 1.3 VicRoads Section 702 July 19
| note | bd375d9c-85df-4575-9743-1180cd8a73fc | 1.4 VicRoads Section 210 Nov 18
| note | 71703935-eef9-4556-91f9-db2b66a076fa | 1.5 IFC Drawings
| note | 5ae7a909-db93-4f22-b61a-223b74895c00 | 1.6 Temp Works IFC Drawings
| section |  | Pre Construction Activities
| checkpoint |  | 2.1 Pre Construction Checks
| note | 746b6066-4c7e-4ee6-a5fb-521910876193 | REFERENCE: VicRoads Specification 682.17
| note | 58064740-3602-44f4-b6de-01b89e5c7944 | VicRoads Specification 682.20
| note | 49cc6a65-4f23-4d85-962e-d2893108348f | VicRoads Specification 682.21
| note | 57f6a175-dd87-4035-9f1f-750799955c83 | ML19057-C005-S000 to 027
| note | a1d3fbf4-b78a-47e8-8486-617b0836e17e | MRP-DPK-045-00-CSW-0033
| note | d4971ca0-b589-41fc-a88b-9b6a586de848 | ACCEPTANCE CRITERIA: Check panels for damage just prior to installation.
| note | f3093117-5504-46a4-b159-415215b2b522 | Strength of Levelling pad shall reach 25 MPa prior to placement of panels (if applicable)
| note | d4b7a96b-eb4f-4aae-ab04-03d48eb491d7 | Strength of Strip Footing shall reach 20 MPa prior to propping panels (if applicable)
| note | c7d5c593-4233-4a1c-8ba6-6ad9bd0e521d | METHOD: Measure Visual
| note | 92e08a21-88ce-45f9-bcfd-4e43ab784192 | FREQUENCY: Each Lot
| note | 98faf4f9-0456-4f10-b3b8-b067f27374cf | CATEGORY: IP
| note | 008eed29-6bb8-4bb2-a091-9c81674fda96 | RESPONSIBILITY: SE/PE
| note | 75b31c09-843d-4f5b-9ff1-b7b344b9033d | VERIFYING DOCUMENTS: This ITP
| textbox | c0658f47-2387-4608-bd13-cb0bf9b622b4 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 3.1 Placement of Panels
| note | f66c79d5-415a-496e-9b49-9c06c51e5d9f | REFERENCE: VicRoads Specification 682.17
| note | 56779dcf-395b-4aeb-a2f7-413dd4f23317 | VicRoads Specification 682.20
| note | 38e17a62-7367-4c40-9f27-5be715905c0e | VicRoads Specification 682.21
| note | 1d2abad9-5449-49b1-9221-d608397f4f73 | ML19057-C005-S000 to 027
| note | 32aa27af-a94e-48a5-a2a8-ca3a85b21e18 | MRP-DPK-045-00-CSW-0033
| note | ff8681f5-9af1-4b29-99ce-a6be2825153f | ACCEPTANCE CRITERIA: Panels to be placed in the locations as marked on the drawings. Base of panels to be placed as per the survey marks.
| note | df69bfd3-c1df-4533-8903-584f37e3617f | Each facing panel shall be temporarily and securely supported during and after its erection until the adjacent fill material has been placed and compacted. As per Temporary Works IFC Design.
| note | c2f2764f-5e33-4b52-9be2-1467dd454fa2 | Place 3 x 19mm rubber bearing pads per panel as per design drawings.
| note | 298ed1a6-69a6-4236-a2f8-94cfe8663fc7 | Place 9 x 19mm rubber bearing pads for deflection panel as per design drawings.
| note | 887b3cf6-840d-4aba-8d18-639cc3e9568e | Where backing blocks are used, place 19mm Rubber bearing pad and 3mm shim between vertical face of panels at 1m centres
| note | 68e031ad-3db3-4013-ba6f-4d5bfbab2fe0 | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course.
| note | 5225ace1-7d75-40d2-aa01-83779880ca5f | METHOD: Measure Visual
| note | e6e44abe-9cad-4f20-80d9-e045e32610a1 | FREQUENCY: Each Lot
| note | 916ba783-bd37-462b-828a-5ce49de9d27b | CATEGORY: IP
| note | b05783e0-920f-4342-8e75-7baa9d098fcc | RESPONSIBILITY: SE/PE
| note | 61eef143-dd5e-4b92-a4d4-866be22c79cb | VERIFYING DOCUMENTS: Signed ITP
| textbox | 71f5048e-5309-45b5-a5b2-5731fa11a848 | Date Completed:
| checkpoint |  | 3.2 Placement of Geofabric on Precast Panels
| note | 6b398e06-bcd2-41e1-a72b-d7baaf2dbcc1 | REFERENCE: MRP-DPK-045-00-CSW-0033
| note | 804cddea-b971-4688-9c8f-aeb42063986c | ACCEPTANCE CRITERIA: Geofabrics shall be placed between vertical and horizontal joints of the precast panels as per IFC Drawings
| note | e47688d5-82d4-4c75-b872-dc8c10dd19fc | METHOD: Measure Visual
| note | a9f66220-bd4a-48ba-a351-fd113302e424 | FREQUENCY: Each Lot
| note | 13a84846-35c3-4ead-8701-7172a65bfb37 | CATEGORY: IP
| note | 70f40101-43ba-4128-87a7-9fcbd9c3951e | RESPONSIBILITY: SE/Site Supervisor
| note | f40e408f-3f5b-4474-8c5c-31944befca1d | VERIFYING DOCUMENTS: This ITP
| textbox | c4267013-a56d-4c25-a1ca-0bf3bca08352 | Date Completed:
| checkpoint |  | 3.3 Drainage items
| note | 992b513c-9e08-40b2-b46e-ede405578b3a | REFERENCE: IFC Drawings
| note | 4251fa78-a049-4d57-bba8-758a555cb2ae | Section 702
| note | 048d6d67-fa66-4a7a-aefa-ef1d7171076b | ACCEPTANCE CRITERIA: Weepholes in RSS Panels 500 nom above finished surface level at 30m centres.
| note | faa29342-3bec-4ce1-98e6-0b6638a773ee | 1no. 150mm wide vertical strip drain (Prodrain PD20 or approved equivalent per 2m wide RSS Facing Panel.
| note | 8fe713ff-239d-48d4-80d5-f83dfeedcdc8 | 300x300 granular backfill in geotextile bidin A64 around 100dia. perforated plastic pipe. Subsurface drainage pipe shall be Category 1 (Class 1000). Perforations shall be a max. width of 1.5mm and min. length of 150mm per m2.
| note | b0ce08f2-46c4-4430-948c-b928c5cdc8da | Recycled concrete aggregate shall not be used as a drainage layer.
| note | b0dbe442-7d8f-4b68-924e-d69d97df6e37 | METHOD: Measure Visual
| note | 2797f5d6-e289-4303-8881-5d7afcdabc4e | FREQUENCY: As Required
| note | b93a8f99-a62d-48a3-8946-d64971759614 | CATEGORY: IP
| note | ad309860-4463-40c9-9e34-053680e005e4 | RESPONSIBILITY: SE/Site Supervisor
| note | f4a28ea8-f3c5-4978-8b58-5392e4fdc9ca | VERIFYING DOCUMENTS: This ITP Attach Delivery dockets for: Geotextile, granular fill, subsurface pipe and strip drain
| textbox | e0bd68fd-1d30-4e62-aa2f-541c60ed9fea | Date Completed:
| checkpoint |  | 3.4 Placement of Backing Blocks
| note | e1d7314a-84d1-4f60-83f0-8dcd6762f08a | REFERENCE: MRP-DPK-045-00-CSW-0033
| note | 8c049a6c-e955-4c34-8190-65b0d3d0c127 | ACCEPTANCE CRITERIA: 200x150 Precast Backing Blocks shall be placed as specified in the design drawings
| note | 3f07e301-1ef4-47ae-ba76-bfffdb5dce8c | METHOD: Visual
| note | 7d0148a6-d28d-4fca-ace6-05b0188a0b24 | FREQUENCY: Each Lot
| note | fca9d61a-4eba-4118-96b7-4f35cbc7caa6 | CATEGORY: IP
| note | 12e574e9-abc4-4edc-a30a-5ce727948908 | RESPONSIBILITY: SE/Site Supervisor
| note | c9640840-45b6-4565-805b-16c5beacd8ca | VERIFYING DOCUMENTS: This ITP
| textbox | 1183e042-0ccc-43ec-8e33-9a4e62bff193 | Date Completed:
| checkpoint |  | 3.5 Galv. Folded Plate
| note | 522764e3-4b9b-4751-a562-473e6c13c352 | REFERENCE: IFC Drawings
| note | 143bf50b-0256-441a-b1ae-753749386af2 | ACCEPTANCE CRITERIA: Galvanised folded plate fixed to abutment only. Refer to Package 32.
| note | aba4ca71-ee4c-4e6d-93e9-aeb754c0d909 | Galvanised folded plate shall not be fixed to RSS Wall facing panels
| note | 184819ba-7fb3-4c47-994e-05decc3e221b | METHOD: Visual
| note | 4d8ba284-a577-4a69-bb3d-80f63d1e6c26 | FREQUENCY: As Required
| note | 74bef678-6037-4008-9631-27f7aae1d940 | CATEGORY: IP
| note | 44972073-ecb2-47d4-ac2e-4f24384bfa5f | RESPONSIBILITY: SE/Site Supervisor
| note | c1e628d8-fe21-4f93-925e-ced8d3883def | VERIFYING DOCUMENTS: This ITP
| textbox | 4091c5db-f3a1-4911-b5aa-8d7a9998b729 | Date Completed:
| checkpoint |  | 3.6 Mark-up Panel for Select Fill and Strap Install
| note | baaffb51-f546-4045-8d91-60ec9d384d9d | REFERENCE: Vist-A-Wall Installation Guide
| note | fdf3c502-a1aa-4212-8a10-954830534402 | ACCEPTANCE CRITERIA: Each panel shall be marked to indicate the required straps per row
| note | 90f1fe45-f974-43a5-8011-9fe7e7c23213 | Back faces of the panels shall be marked with design locations as per the elevation drawings (Wall Number, Row and Column)
| note | dc712b56-4a3b-4f1f-b70b-0f176916ca58 | Anchors shall be marked to identify the locations of the strap connection as detailed in the design and construction manual
| note | 9ae2b270-12fd-4538-aebb-36d21a0da2ce | Layer numbers and thicknesses to be marked on the back face of the panels.
| note | 1a459452-dfb8-49d9-a4f3-8e3d2099e88c | METHOD: Visual Measure
| note | ef2270c1-390a-47a3-90ad-18a514876188 | FREQUENCY: Each Lot
| note | b7f7bfbc-e3ba-490d-a07a-83d9131319d6 | CATEGORY: IP
| note | 5a374230-f37d-452e-bec0-5e615d8b6937 | RESPONSIBILITY: SE/Site Supervisor
| note | ce61c3fb-2359-4db5-91f3-f499332633a7 | VERIFYING DOCUMENTS: This ITP
| textbox | 20f7164e-0485-4750-bafc-4ab0978af2e9 | Date Completed:
| checkpoint |  | 3.7 Traceability of Precast Units
| note | fb097308-5bce-4bdd-88af-95beb28e7fe6 | REFERENCE: VicRoads Specification 620.09
| note | 16edc669-8134-4765-bce4-49caadab5cb3 | MRP-DPK-045-00-CSW-0033
| note | cb47dcb2-1216-4f2a-8a42-06e8ffa7d11e | Panel Manufacturer Quality Assurance
| note | f66e6559-c8cc-428d-9802-acf1593372e5 | ACCEPTANCE CRITERIA: The final location of each panel is to be recorded.
| note | 0c1ce6e9-95f3-4510-97a4-be9d999130d1 | For each panel the date of manufacture, production lot number, panel type and date installed is to be marked on the back of the panel and recorded on the lot map.
| note | 51357020-72b1-422a-9433-6a07d8b0bbd1 | METHOD: Visual Document Review
| note | eba0561c-3f74-43f6-bf92-9b1224e48bb0 | FREQUENCY: Each Panel
| note | 54fb4348-c578-4121-96ec-efb5ae77c74f | CATEGORY: HP*
| note | c46ac2e4-92af-4459-a902-3e088f43b224 | RESPONSIBILITY: SE/PE
| note | 32ef89ea-f8b3-4df0-b944-ab3ceb4347cd | VERIFYING DOCUMENTS: Marked-up elevation drawings (or similar) This ITP
| textbox | 87f25316-79f8-413a-8e2e-313baed67510 | Date Completed:
| checkpoint |  | 3.8 Wall Position
| note | 9f8e687d-89e1-4930-903d-95cac39de1df | REFERENCE: VicRoads Specification 682.17 and 682.20
| note | 253648d2-bde5-4dfe-8f5d-18540db3c393 | MRP-DPK-045-00-CSW-0033
| note | a153481d-3582-4c48-8231-aae4002f1e9a | ACCEPTANCE CRITERIA: The level and alignment of each course is to be checked progressively and recorded.
| note | d32a7435-2e95-44e6-86c1-226d3fa7a981 | Ensure the verticality of the RSS wall shall lean backward a min slope of 1(H) in 40 (V)
| note | c8087f65-62ce-4817-873f-69f7b83c3a66 | Wall Tolerances shall be as follows;
| note | 8bfd9ff3-1dbd-4af4-8ca1-ef44d869ee20 | Plan position at base of wall = ±15mm
| note | ab33e2bb-7e5c-4210-9074-54b13031b748 | Relative displacement of adjoining panel faces = <15mm
| note | 496b10a2-757f-46db-be04-43188a9b8c0a | Local deviation wall face 3m straight edge = <15mm
| note | 4a76e962-e44c-4d82-8138-d30dd92eb61e | Tolerance on position at top of wall = <5mm per 1m wall height
| note | 720a7ee4-3713-4895-919e-a3633a53fd2d | Wall level = ±20mm
| note | ca0a9d3e-4faa-4950-87c2-71f15d3b564d | Variation of gap width = <5mm/m and <10mm/full length.
| note | f0dc0c89-a620-42b9-a699-d07321165a21 | METHOD: Visual Document Review
| note | 113cb92d-a3ac-4dbf-a21e-ccccbe7031a4 | FREQUENCY: Each Lot
| note | 05ee6372-ebed-4bb3-9202-c6494f2d6e69 | CATEGORY: IP
| note | b5e1dacf-8907-4a3f-a0f6-cd28086b7165 | RESPONSIBILITY: SE
| note | ff14576e-309b-4d5c-94f9-c133845ebffe | VERIFYING DOCUMENTS: This ITP Survey Data for completed Wall (to be attached to final lot)
| textbox | a37dbe4f-6a3b-45d1-85e9-70c3c5e50448 | Date Completed:
| checkpoint |  | 3.9 Wall Monitoring
| note | 6c5892fc-0721-4040-8a48-6b525bc8b724 | REFERENCE: VicRoads Specification 682.21
| note | fdf13ca5-aa48-4e88-98c8-3cc4a1515ad6 | ACCEPTANCE CRITERIA: Survey Reflective Markers are to be placed on the exposed face of panels above FSL in a 2m x 5m grid pattern covering the whole face of the RSS.
| note | 18172797-5195-4035-ba5c-fcee59050187 | Monitoring shall commence once the first panel is placed. The frequency shall be:
| note | 2e8c300b-9aa6-493f-b771-239e98b89a91 | a) During Construction - Twice per week (bottom row of panels only)
| note | 9ff891c7-f3ba-43ee-8e94-7b359960de0e | b) During Construction - Once per fortnight (other panels)
| note | 8c317482-0fa3-4b89-b15b-0cc7a352259e | c) Once per month for first six months immediately following completion of the wall
| note | 92f3cdcd-cd5a-4772-8f2b-6987a540f071 | METHOD: Measure
| note | 427d8d3c-5356-4dc7-872c-f1abaa7bb26e | FREQUENCY: Each Lot
| note | 02557b10-ce9c-4849-aec7-fe2a880b9fe6 | CATEGORY: IP
| note | b0d57b7f-1e24-40dd-99c6-29021500251f | RESPONSIBILITY: SE/Surveyor
| note | 86a3f412-a0d5-4c3d-8e5d-7892846cd101 | VERIFYING DOCUMENTS: This ITP
| textbox | 9094b7a2-2d71-4c26-9c5e-71d4789d5ae6 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | c0054b03-ee5e-4424-866b-b413bf8d34c0 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | b3349b41-0c2c-4b41-a686-79ddc3578912 | Name:
| textbox | 23f52d7e-b930-4820-94f0-bc903f5f5ce4 | Position:
| textbox | 28e0f060-57ef-4447-8921-00bc1d4524aa | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Supply & Installation of Street Lighting (Vic Road) Rev 1 | itp | ITP-CIV-Supply & Installation of Street Lighting (Vic Road) Rev 1 | 350967ce-8601-4a03-9052-056d09813749
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 9f2fc251-ac40-5c79-9b7c-cb47aab97616 | Document Title: ITP-CIV-Supply & Installation of Street Lighting(Vic Road)
| note | 83fb017d-ad97-5991-9f91-5dfd128376e5 | ITP Description: Supply & Installation of Street Lighting(Vic Road)
| note | fda54d1e-0867-5f7b-af9a-02f3beae1ed9 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 25947844-ac1f-5f47-bd97-95e7e56f6f5e | Revision Number: 1
| note | 027f22c6-7f2f-564a-b92c-1f66f67ecea1 | Revision Date: 9/10/2020
| note | c7903568-91cc-5fa4-b473-e28d66121bcc | ITP created by: Romualdo Magpantay
| note | 09c77780-4f86-50b6-842f-78215dfbfb55 | ITP approved for use by: Romualdo Magpantay
| note | 07f18ac4-4dfb-54fb-af29-3136333424c7 | 1.1 VicRoads Section 731 June 2017
| note | 2e5e1f55-1f6a-51c9-a940-d024335e0c28 | 1.2 VicRoads Section 733 April 2019
| section |  | Preliminaries
| checkpoint |  | 2.1 Obtain and review manufacturer documentations for the supply of materials
| note | b7a45ba0-2673-5042-8f65-cd18aa06af80 | REFERENCE: Vic road 733.02
| note | 8cdab499-a878-5394-be25-b7188b403e44 | AS/NZS 2053
| note | 26258ecb-4530-5d9f-94ca-15358b36c7a0 | AS/NZS 1345
| note | d437e03b-99a3-54b3-bf1e-2e26701ed061 | Vic road 731.02
| note | e98fd3ee-38fe-51a1-9d9d-8532f6ba8a09 | AS/NZS 3000
| note | 8544606f-f3e7-5178-8dd7-cf955ce9e18d | Vic road 630.07
| note | 25c886e4-81be-53e2-916e-c545913b06dc | AS 1627.1
| note | 1c74ae76-60cc-5a0f-a778-27db06be02d1 | AS 1627.4
| note | c3070b77-24a1-54fa-89df-4fc291ef2abf | AS/NZS 1554.1
| note | c8ea83f1-282b-517b-8b33-293c21115c95 | AS 1214
| note | 55d6e14e-b4fa-50ee-9790-3e2c78bb126d | ACCEPTANCE CRITERIA: Materials comply with Vicroad Section 733.02,731.11, 630.07 and relevant specifications.
| note | b5a6e837-95c7-575e-9ed2-a0d8aa320bda | All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
| textbox | 55ad077f-0db4-5a5d-a776-f71c1d0e9947 | Teambinder Material Approval number:
| note | c4de7493-a562-5332-a8d4-7e4cd5168824 | METHOD: Document Review
| note | b97eaf04-7e43-5d18-9b22-ea45affb4c27 | FREQUENCY: Per Source
| note | be8df2ba-a6b7-5749-bd6f-65f454f05af1 | CATEGORY: HP*
| note | b9e11048-fadb-5916-942a-50ec76786801 | RESPONSIBILITY: Nominated Authority
| note | a038f592-f644-5601-97cd-e7dc5818cbc1 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 10ee32a8-4128-543d-a3f9-528748efdde8 | Date Completed:
| checkpoint |  | 2.2 Inspect supplied items upon delivery
| note | 9dde647a-6783-59f8-bba1-2259d3474c19 | REFERENCE: QMP
| note | 5302c179-2ea5-5165-b3da-a7ce74df931d | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
| note | b7b14919-45ee-5fd9-9fb9-956ab4d0f167 | METHOD: Visual /Site Inspection & Document Review
| note | b47dd0f5-7abb-5148-af14-a4103dcdcf38 | FREQUENCY: Per Delivery
| note | 5d436434-46b5-59e6-8879-cf71fbdfba1a | CATEGORY: IP
| note | 33c5d7ac-338f-573c-a158-a1d5c21d2f31 | RESPONSIBILITY: SE/PE/SPE
| note | f73fcc81-658a-53a2-8abd-abefd1b973fe | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | 36215a10-b8d7-5088-a830-a7a17ca6756e | Date Completed:
| section |  | Conduit Pit Installation
| checkpoint |  | 3.1 Conduit & pit installation
| note | 1b10a811-c7e7-5de4-b256-45a3b5460f7e | REFERENCE: Vic road section
| note | f78fa4e5-67ae-5be3-aaf9-7ac753b30007 | 733 April 2019
| note | a94f577f-1537-5cce-ac93-c3d52d6f48a2 | ACCEPTANCE CRITERIA: This Item will be completed under the checklist conduit & pit Installation (Road)
| note | 023d2e91-26db-5707-bf89-1b053fb84772 | METHOD: Document Review
| note | a6ee1e31-39f8-516a-9480-ea6238c8ac41 | FREQUENCY: Per Lot
| note | 6020c0f2-9882-55d6-9562-9873bd850047 | CATEGORY: IP
| note | ddf15e05-281c-5c43-9d3a-df1ee1114b9b | RESPONSIBILITY: SE/PE/SPE
| note | b7311e76-5e70-53bc-8c1e-b23a248c82d9 | VERIFYING DOCUMENTS: This ITP
| textbox | ccfdf138-60c0-5a26-9de2-66f9d2c4254a | Date Completed:
| section |  | Foundation
| checkpoint |  | 4.1 Prepare the plinth foundation(Excavation & levels)
| note | 8566f7cd-6d49-5f87-ab8e-250c73e265e5 | REFERENCE: VicRoads Standard Drawings
| note | 0235649d-2bdd-5cf1-9139-90c6f0d72060 | IFC
| note | 63bfd129-4fc3-51f7-8890-25103b4b5f42 | ACCEPTANCE CRITERIA: Check levels conform to relevant drawing depending on type of pole to be installed.
| note | 71a10ddc-ecf3-5820-a614-976ace3b1176 | METHOD: Visual Survey
| note | 34aad458-861e-5910-955d-9179cebd6132 | FREQUENCY: Per Lot
| note | b22b448f-99c3-57eb-9050-f2eef7454385 | CATEGORY: IP
| note | a6021849-6c00-518f-9b6c-809ed3250da7 | RESPONSIBILITY: SE/PE/SPE
| note | bc434160-6276-5b83-b3ec-ee5019b983bd | VERIFYING DOCUMENTS: This ITP
| textbox | d12e6fc5-82ea-5698-ad2c-e459813cc5bb | Date Completed:
| checkpoint |  | 4.2 Installation Street lighting pole bases
| note | cadecaf9-cbb3-5cec-b05c-e268fa53bb22 | REFERENCE: VicRoads Standard
| note | 6d90cdac-3e90-558d-a307-35bc047cb9e2 | Cl731.11
| note | 590d5d8c-c08d-5618-830a-7a5ca69571ae | VicRoads Standard
| note | 7d1b0d66-c394-5fbd-835f-623f743892be | Cl731.6
| note | 5a5f6bef-2830-52bf-b4eb-6d059225501b | VicRoads Spec
| note | 970a496a-a540-5ae0-acc0-4e0f6e93bd77 | Cl733.6
| note | aab25a28-e7d4-5101-a434-81a470ad215d | ACCEPTANCE CRITERIA: Pits located 1 metre in advance of, and 1 metre off the line of the pole and in accordance to TC-1210,TC 1220 & TC-1230. A two(2)meter of spare length of each cable shall be left coiled in each pit.
| note | b0ff1d55-c856-5778-b48f-b8b5fdb5a692 | The slip plane of a slip base pole is to be located 75mm ± 25mm above the surrounding finished surface level
| note | 6030f019-ccaf-5cb8-9cae-59d693fd32dc | All poles/luminaries to be individually earthed to the earth cable in the pit
| note | 946fbae2-5b6a-5414-8166-921dc9137261 | METHOD: Visual /Site Inspection & Document Review
| note | b1d34850-fabb-5db0-a582-5d16044ddb9a | FREQUENCY: Per Lot
| note | dfb6fccd-5fd5-5539-87a9-41312bda1023 | CATEGORY: IP
| note | 9de45378-003a-5585-a5ca-c318abf07dae | RESPONSIBILITY: SE/PE/SPE
| note | dc2f5c29-a735-557c-842b-ce89506d2a5d | VERIFYING DOCUMENTS: This ITP
| textbox | be153e71-fe44-53fa-923f-de9fe083c046 | Date Completed:
| checkpoint |  | 4.3 Installation of frangible poles (Slip base and Impact Absorbing)
| note | bcb2eeaf-ce63-5bf5-a83e-ba356460ac3a | REFERENCE: VicRoads Specs.
| note | 6a956539-7b03-5e17-8c26-32de5afc1549 | Cl 731.06b
| note | e6439c8f-e15d-539b-8603-a4ce27d67abd | Requirements
| note | f0f6af1b-c20a-5a1a-87ef-fc563c091827 | TC-1065
| note | 0e0a6367-c6b7-52cc-9b1f-8aaf2025342f | TC-1066
| note | 6ed09031-d689-514f-8999-efdb974ad82a | TC-1072
| note | 71968160-803c-50cd-a524-68c6be1d9259 | TC-1071
| note | 223d672d-6e41-58f1-974e-57d675386cf9 | TCS014 Supply of Frangible street lighting poles
| note | 66a05387-415a-57f5-819a-87dc112073ae | ACCEPTANCE CRITERIA: The slip plane of a slip base pole is to be located 75mm ± 25mm above the surrounding finished surface level as per VicRoads Standard Drawing TC-1072
| note | 31cd76a1-9869-51a3-9cda-be315a935bdf | The holding down bolts and nuts on the flange are to be slackened of one at a time and re-tightened using a torque wrench to 40Mn for Main nut (Half Nut) and 90Nm for Lock nut (Full Nut)
| note | f6a9f99d-4108-551b-b935-be703b0fbc37 | Record torque of each Slip Base pole in report
| note | b8b3b31b-740f-5b03-8490-d75daab47a11 | Locking nuts to be installed on all hold down bolts
| note | 05ab7172-df4c-57d0-a416-fa159d434800 | Lock nuts to be installed on Slip base as per VicRoads Drawing TC-1065: Slip base pole assembly, Ground set mounted and VicRoads Drawing TC-1064a: Impact Absorbing
| note | 85bc0096-90c8-58ee-b3df-883ae322f678 | METHOD: Visual /Site Inspection & Document Review
| note | 6d7c77da-9129-5de7-ae66-b535a1650d9f | FREQUENCY: Per Lot
| note | a9bbb5c3-8fd9-5bae-9f03-5d4845a72969 | CATEGORY: IP
| note | 3823c11b-3ff6-5561-824e-77e25b42db4b | RESPONSIBILITY: SE/PE/SPE
| note | 1304871b-4646-5abc-85b6-7648f7fc7dc2 | VERIFYING DOCUMENTS: This ITP
| textbox | 491b9feb-ff49-5391-8bcb-e167fe401e7a | Date Completed:
| checkpoint |  | 4.4 Erection of Street lighting columns
| note | fa60713a-09fa-562a-a8dc-8ad9273724c0 | REFERENCE: VicRoads Standard Drawing
| note | 88fdb992-004b-5781-b561-7f10caaee0b0 | TC-1068
| note | 81d1b97f-4450-514e-8535-c4ffc0377acd | ACCEPTANCE CRITERIA: Installed on rigid columns as per VicRoads Standard Drawing TC-1068: Rigid Street Lighting Pole
| note | 78211b3c-e5a1-5b7c-955c-7668a286046b | METHOD: Visual /Site Inspection & Document Review
| note | 511bea86-3242-5b89-9cdb-86f7eb6cfe5b | FREQUENCY: Per Lot
| note | 40323b2c-ac0b-517d-ab06-c8a40b59ff5f | CATEGORY: IP
| note | 949caf18-6c92-56d0-88e0-144a6cda0c91 | RESPONSIBILITY: SE/PE/SPE
| note | 427114a6-71ca-5641-a5fa-d31fc41e57cb | VERIFYING DOCUMENTS: This ITP
| textbox | 7e50b91a-dcda-5117-90b5-8409aae70dfe | Date Completed:
| checkpoint |  | 4.5 Assembly of outreaches and luminaires
| note | 118f946a-a3de-5957-b6ea-7121a802bbd2 | REFERENCE: VicRoads Specs.
| note | 4479d024-b465-503c-a758-63cf025fa0cd | Table 731.061
| note | d28d6b2f-2ec9-5e52-87a9-0a16b829847e | Requirements
| note | d153a41b-6b6a-56d9-87f0-a1d1649564b2 | TCS065
| note | 7a7e6dfd-7c0c-54c6-8431-e19de87374ac | ACCEPTANCE CRITERIA: Outreach bracket to be installed to the pole spigot using the clamping bolt assemble
| note | 67ad9f36-3a20-5bf9-b8de-75ef962a21ec | Bracket and luminaire to align at right angles to vehicle path on road
| note | cf2bf1fd-7b39-574d-85fd-dd89bf5c750d | Luminaire orientation to comply with Table 731.061 from VicRoads Standard, Section 731 - Road Lighting Installation
| note | 8fb64b44-d3a6-57c9-b5e4-0bbe79e47f75 | Luminaires to conform to TCS 065 - Supply of LED Road Lighting Luminaires
| note | 8be99ae9-9322-5b51-a637-7036c9f2e062 | Luminaires shall be supplied with the PE cell bypassed or deactivated
| note | 8b53a4b8-261b-5d98-968f-c07740b28f7b | FREQUENCY: Per Lot
| note | a8d00280-8a29-5239-8622-f51746d1c0ea | CATEGORY: IP
| note | 7eda63a2-e530-5796-b27a-4552023a9100 | RESPONSIBILITY: SE/PE/SPE
| note | 058ce4b9-e60b-5a47-a16b-6c344b760c5a | VERIFYING DOCUMENTS: This ITP
| textbox | b18c83a4-dcd2-58f6-b66b-63d4b0ba4d6d | Date Completed:
| checkpoint |  | 4.6 Installation of lighting distribution cabinet
| note | df4f8bf4-3e3c-5f52-9032-ce54ce543dfa | REFERENCE: VicRoads Specs
| note | b0b92154-b212-52b7-8bf8-410b7f761529 | Cl.731.11
| note | 27163b69-7448-5580-9bd6-4a12199a9b81 | IFC Drawing
| note | d8db5e05-417a-50dc-bed0-a97b527943a3 | ACCEPTANCE CRITERIA: The lighting distribution cabinets shall be supplied and installed in accordance with VicRoads Specification TCS 043 - Specification for Distribution Box for Road Lighting Power Supply.
| note | 11c79983-6513-5d0e-87a7-2261e84a77cd | The foundation of the distribution cabinet shall be installed as specified in VicRoads Standard Drawing TC-1062.
| note | 134aa135-a5ea-5230-9126-dd3d334d5f60 | Distribution cabinets shall be located not less than 5 metres from any carriageway and where possible beyond the clear zone for the particular road. For any distribution cabinet within the clear zone, the Contractor shall provide traffic barriers to protect the distribution
| note | 8d2818e4-8659-549b-a4fc-cd96f19c263f | METHOD: Visual
| note | fbd4ba66-6769-5851-949a-0b4f5af46673 | FREQUENCY: Per lot
| note | fa507e7e-0c1b-5d85-b002-7fd01c090cb6 | CATEGORY: IP
| note | 56e59190-69a2-5bf4-b16f-dc36ece2e229 | RESPONSIBILITY: SE/PE/SPE
| note | 520daed1-9093-5825-996d-6500631ebbe8 | VERIFYING DOCUMENTS: This ITP
| textbox | 1b3c27de-dd35-5a3a-b58c-fda7b2044b44 | Date Completed:
| checkpoint |  | 4.7 Installation of cabling
| note | f858d2e4-da67-52b7-92b0-f6ce4de858f0 | REFERENCE: VicRoads Specs.
| note | 2af15e7a-03d3-52a0-a1aa-a8a511403d4a | Cl.731.11
| note | ed485249-0186-5114-8630-6babfc4eeac0 | ACCEPTANCE CRITERIA: All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules)
| note | 561ff339-47df-5867-aca1-1a4b2f86ddf3 | Each pole to be cables from the pole circuit breaker
| note | 25e1b111-68e1-5072-911f-4ef88d2e3374 | All electrical cable joints to be waterproof
| note | 765a6164-4b52-5b67-b739-7c2db31f8938 | JUP, JUMA or slip base pole: Cable to be supported by nylon cord or steel catenary. Cable to be attached the support wire with cable ties, no less than intervals of 4m
| note | 1c991f8f-9568-5e9b-90a9-57cf5ff49e4e | IA pole: Cable to be supplied through flexible conduit fitted inside the pole from cable termination access door to pole spigot.
| note | 4d77597d-8bee-59c5-b393-55972eff9c3b | Cable for trunk electricity supply from “point of supply” to distribution box to be not less than 16mm square 4 core, three phase copper XPLE cable
| note | 18e275a5-30a6-57c0-81c5-953c91992d4d | METHOD: Visual & Document Review
| note | e3a2bfc3-18f2-57f6-aa27-11c4e1adf50e | FREQUENCY: Per Lot
| note | f3639c03-872d-5a23-b100-b94017c95006 | CATEGORY: IP
| note | 19486acd-ac3a-5ec3-a8bb-8ecba8a974b5 | RESPONSIBILITY: SE/PE/SPE
| note | 0ccc38f2-2c02-5fdb-a90e-1ffb890ad4aa | VERIFYING DOCUMENTS: Test Certificate This ITP
| textbox | d865f5b7-5176-5b99-9c1f-aeb18b4834a6 | Date Completed:
| checkpoint |  | 4.8 Labelling of Assets
| note | 7a94a26f-371d-5eeb-ac06-01e4606d1b90 | REFERENCE: VicRoads Specs.
| note | fc78cd68-896f-5d5d-a642-636b0ff12dde | Cl.731.12
| note | 9497d87f-a117-55be-9161-245806a2e16f | ACCEPTANCE CRITERIA: Labels fixed to poles as per VicRoads Section 731.12
| note | 6814456a-0940-5017-ad76-a426815cf5ab | METHOD: Visual /Site Inspection & Document Review
| note | 52b5bb9a-6a83-50e2-b5f5-fa7dd9b2d170 | FREQUENCY: Per Lot
| note | bc51c95b-d96a-53fe-a64a-7d0db207c58c | CATEGORY: IP
| note | a69dd3bc-1357-5ffb-aee8-eb5a64783b56 | RESPONSIBILITY: SE/PE/SPE
| note | 12899437-a10b-5bea-95fd-adeff7c455df | VERIFYING DOCUMENTS: This ITP
| textbox | 8d6c63a8-bb19-5045-9bed-7d04e81fb528 | Date Completed:
| section |  | Completion
| checkpoint |  | 5.1 Commissioning & testing(if Applicable)
| note | c036d5c6-1289-554a-80d1-0d97d664564b | REFERENCE: VicRoads Specs.
| note | 13aa85dd-08ee-5ffa-9d25-37c414814154 | Cl.731.16a & c
| note | 50aa8e8e-631b-548b-80e4-c51c01fdff0c | ACCEPTANCE CRITERIA: Upon final acceptance, the Contractor shall switch on the lighting installation at the distribution cabinet in automatic mode, and record the time, date and meter reading for contractual, warranty and power supply purposes and supply this record to the Superintendent within 48 hours
| note | 464c25e0-912a-5035-a162-5d8b210fc792 | METHOD: Commissioning & testing
| note | 79759c98-ee26-5018-b186-e7b83acacc3a | FREQUENCY: Upon completion of each section
| note | 0e2bedb6-a457-5713-925d-3ec400351102 | CATEGORY: HP*
| note | 62e84783-5b41-5234-8103-ffd57730bd32 | RESPONSIBILITY: SE/PE/SPE Services Engineer
| note | 6ff19609-1b21-514e-a348-c3bbc38c51d2 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | cb6d2ac4-0474-56bc-8e0e-ca0af7451b5b | Date Completed:
| checkpoint |  | 5.2 As-Constructed Plans
| note | 23678107-748b-5f50-83b1-57226b9d2b45 | REFERENCE: VicRoads Specs.
| note | 616f116c-c474-5627-82a0-054753d9c8fe | Cl.731.16d
| note | 9aa72170-76fd-5969-9831-97ac185e5406 | ACCEPTANCE CRITERIA: The Contractor shall supply to the Superintendent two copies of ‘As-Constructed’ plans along with a USB drive or other approved storage medium containing the CADD drawing files, and the same shall be supplied by the Contractor to the local distribution company if appropriate.
| note | 5ce64fef-4c69-5785-9890-674e61043bf0 | METHOD: Document Review
| note | 1e363ffe-8b5d-579e-a808-248507f2d4fd | FREQUENCY: Upon completion/ Work area
| note | 8a43b5ea-5a54-5f56-b59c-20865ff2b909 | CATEGORY: AP
| note | 8421b4ad-8d57-5eb2-a276-0abc7c08c6f5 | RESPONSIBILITY: SE/PE/SPE
| note | af3617d5-3f14-5bcb-a2aa-d279432761ce | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | eb4b2096-7143-5e89-bc37-d431e53a11f8 | Date Completed:
| checkpoint |  | 5.3 Non-conformance Report (NCR) Closure
| note | be088f24-3825-5963-af40-eef00ad0337c | REFERENCE: MRPA Quality Management Plan
| note | 8b6e5543-9e16-5e86-a0de-d209c9580930 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | e0edf05c-e00c-5f90-a5b5-949833018f88 | METHOD: Document Review
| note | 8975aac2-db7e-5351-998b-8252b19a7c75 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | eaedba04-0026-5950-9565-e3814b0051b1 | CATEGORY: HP*
| note | 9b2402b9-d119-5b0b-96a2-9c1d264290c5 | RESPONSIBILITY: SE/PE/SPE
| note | 45fc9581-a5d8-5baa-b808-d709f0ca998f | VERIFYING DOCUMENTS: This ITP
| textbox | 116c894f-6e6e-5743-83af-69eaed2f3549 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | c8f627b6-8111-5515-8260-4449eebf565a | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 69036ba6-b4ca-5e97-8e52-e24ee3676805 | Name:
| textbox | 1e17ef6e-d8ff-56f6-a435-cb6a96e3ddbf | Position:
| textbox | fb181b2d-bca8-5cc3-a72f-89463ac4f13d | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Subgrade Preparation - Road Rev 0 | itp | ITP-CIV-Subgrade Preparation - Road Rev 0 | 36067b3b-ac35-45f0-b777-d9d263ae1aba
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 5a443e98-eeee-4e3f-9be8-3242c4451ae8 | Document Title: ITP-CIV-Subgrade Preparation - Road
| note | ef7cdc88-044e-4f15-96b0-6bb2c534b173 | ITP Description: Subgrade Preparation - Road
| note | ed6f1a7b-863f-41a3-a861-6559bb95fc6b | Discipline (e.g. CIV/STR/RAIL): CIV
| note | c527188d-f1b4-4431-9590-aff945cd8b5d | Revision Number: 0
| note | ff9e77a9-15a3-4050-a182-21801058b527 | Revision Date: 9/07/2020
| note | e5e29786-0745-40ec-b851-cc328468bc4b | ITP created by: Patrick Cusenza
| note | adecd949-c24d-4441-8476-8d14caaa0ff9 | ITP approved for use by: Josie Pavlou
| note | 375e5772-2e64-4d39-bc45-44ea22cc7850 | 1.1 VicRoads Section 204
| note | e0be1925-85ba-4369-a271-179c397d4eb8 | 1.2 VicRoads Section 173
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 2.1 Survey Set-Out
| note | 69460805-18b0-48c7-875b-ef06f4c8b751 | REFERENCE: IFC Drawings
| note | e5c15f27-4fdb-4c3b-b62d-629c240979ab | ---------------------------------
| note | 283979a3-8e1b-4b4f-8af0-6307995841e6 | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
| note | b98d8d6d-36da-4d43-96b2-487b3adc9da6 | ---------------------------------
| note | f520c2c1-c375-46cb-a77a-f0195f2cec24 | METHOD: Verify
| note | 89a3b763-ef55-451c-b72a-d8991844215d | ---------------------------------
| note | 34c1686a-adb5-4a70-a99c-632c7a5f3ff3 | FREQUENCY: Prior to commencement of excavation
| note | 342cb149-cfde-435f-aebe-3b67c118fa54 | ---------------------------------
| note | 3344bd5a-ffa3-4026-8c55-9772b906c1c5 | CATEGORY: IP
| note | 10f2cf4f-446a-4b06-8a1a-583614f08a69 | ---------------------------------
| note | 33465e18-6e34-43a7-8f77-70e22db39ac7 | RESPONSIBILITY: SE/Surveyor
| note | 1bc2a237-a0e4-49ad-9029-0eeaf89dd82f | ---------------------------------
| note | dc246345-7478-463d-b738-83b12a3bf859 | VERIFYING DOCUMENTS: This ITP
| textbox | 45a61604-166d-4c3c-9e67-c2ce925c8378 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.1 Subgrade Material Properties
| note | bcd90432-723a-42ce-af61-e7343f1479cd | REFERENCE: Section 204.06 e)
| note | adfd80bb-f421-49df-8e56-c6a6c7e32076 | ---------------------------------
| note | a2b71dfe-e888-464e-9f62-263eaa9ff740 | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type A.
| note | 626fcf02-c817-438e-996d-c78562befc07 | Assigned CBR ≥ 3% and Swell ≤ 1.5%
| note | 834023a0-78f4-4670-b61c-221e8a80d6ec | Max Permeability = 5X10-9 m/s
| note | f053b6f7-5a76-41bd-8ef6-adc5c34386c2 | Grading: 75.0mm 100%
| note | 17dd8858-5719-4ed1-bc3c-6c960588ba8b | 4.75mm 40-80%
| note | a30216c6-b475-4533-a289-4b0f3c54c3be | 0.075mm 10-40%
| note | ba56de3f-685e-475a-9ad0-3bcf6078d3ea | If parameters are met, rip and re compact to a depth of 150mm.
| note | ea6a0dfe-13fa-469a-a4a6-790cedfbd6f3 | If parameters not met, remove 400mm of material and replace with conforming Type A fill.
| note | 5ad1f5a2-160e-4bd8-ba20-4e781d577bb8 | ---------------------------------
| note | ee608293-4242-4765-b68e-ec29ce7162d7 | METHOD: Test Point
| note | 2e0d590b-6f7f-4f36-9056-f557db09ffef | ---------------------------------
| note | b7b5d2dd-eafb-46f0-8a0e-af93848af30d | FREQUENCY: Each lot
| note | 3a28323b-08cc-486a-b095-d8c2606e8799 | ---------------------------------
| note | a3d54a3e-005e-4807-ad63-12566bfebe11 | CATEGORY: TP
| note | dbeeaac9-cb35-43b6-a138-113904c414e6 | ---------------------------------
| note | 16356778-fe78-4f24-8eaf-17dfb34bb604 | RESPONSIBILITY: SE/Site Supervisor
| note | 6bf14e96-8fa1-4dc7-9225-f65a7e0e34de | ---------------------------------
| note | b4934a76-bacf-498b-8d96-f02d8303637c | VERIFYING DOCUMENTS: Sign ITP Test Report
| textbox | ac698a2d-c8b1-485d-8ccb-8b52677b7ea3 | Date Completed:
| checkpoint |  | 3.2 Inspection of Subgrade Material
| note | 291d48b8-6054-4a33-bd1a-4324f05750b3 | REFERENCE: Section 204.06 c)
| note | 53a27b73-ab45-43ee-9072-8dbe8950a8a5 | ---------------------------------
| note | 63e6c8f4-6daa-4665-b793-1e96eb39d7d5 | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
| note | 610f2fd7-bd5c-4bbc-a060-e49c4855e396 | ---------------------------------
| note | 1d4effe7-7990-40e4-98c9-b032ada30615 | METHOD: Verify
| note | 0bec1380-6c6d-4f0e-87cc-52640c56ce93 | ---------------------------------
| note | af271780-5353-47d4-afa9-361ed9e8e520 | FREQUENCY: Each lot
| note | 26aa37d6-2328-4041-a70b-71f2bbc0a9b7 | ---------------------------------
| note | 38130d39-7b63-4ee3-825a-8107f41199c8 | CATEGORY: HP
| note | 972f91f8-2866-48e1-9a60-e511509c4f02 | ---------------------------------
| note | 34e5bd21-a79b-46c6-937e-3b565d99906a | RESPONSIBILITY: SE/Nominated Authority
| note | 81bd533f-c162-4713-8bd6-d1e6d9c166a8 | ---------------------------------
| note | bde83b8c-a0b4-467a-a4ef-c1192acbb1af | VERIFYING DOCUMENTS: This ITP
| textbox | 3def7115-a4c6-49f1-a0ec-3043ce50e5f1 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Material classified as silt
| note | a6611c4c-379d-4200-9c5d-23d457a5d24c | REFERENCE: Section 204.04 b)
| note | 3993c8a7-bbb4-4287-bcec-81325c836001 | ---------------------------------
| note | 5e5cf9d3-bf21-4174-8764-b90c426c6576 | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
| note | cf7753a3-57f2-44ca-af3e-cb6f92bfcabb | ---------------------------------
| note | 1473c44b-a3ff-421f-ae3a-23412c4e658e | METHOD: Document Review
| note | 1d28e892-fc0a-4cc6-bb7e-05c50aa999e5 | ---------------------------------
| note | 44eadefd-d2bd-4615-81b3-775532fa9839 | FREQUENCY: Prior to commencing
| note | 7e42bdd6-822d-444e-963b-04b9b3a5540e | ---------------------------------
| note | 5116353e-0600-4aa9-97f9-36e4352e80ce | CATEGORY: HP
| note | c0266da6-2ea0-4606-8821-b933bda95498 | ---------------------------------
| note | 938cfefc-bf5d-48d8-a38b-c7274ba275c9 | RESPONSIBILITY: SE/Nominated Authority
| note | ed0e401f-61cd-47aa-9628-169ca73f3fdb | ---------------------------------
| note | 3eb664a6-a73c-4684-b424-0a1b373af428 | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation Signed ITP/ records
| textbox | 3f6fcda7-3a25-4bc6-bca4-76216c0b4dd2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Acceptance of Rock Subgrade (where applicable)
| note | a062582b-3033-4826-9d1b-02c8ce8bcc1c | REFERENCE: Section 204.06 f)
| note | 9fb599da-2ec4-4deb-80fb-1bc0fa7f619c | ---------------------------------
| note | e1aeb5a4-5e6b-4ce9-a657-aaf81f2409a9 | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
| note | d3faf053-f137-4b0d-8096-796ed7afde0b | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
| note | d6d6bfe1-eff3-4393-bf96-3900fda127b8 | ---------------------------------
| note | 9624800c-64df-40c2-b756-45c102b7e39d | METHOD: Site Inspection/ Document Review
| note | 4f04177c-3546-4113-949a-0fd2be36a832 | ---------------------------------
| note | 304a377c-7c31-47db-9faf-25c5cb352688 | FREQUENCY: Prior construction of the regulating layer
| note | ffd61933-6693-4608-93fd-ab0806a0d2bc | ---------------------------------
| note | e8cc5abe-c86a-4987-b39c-f62c64c38132 | CATEGORY: HP
| note | 639a1e7a-aa92-4118-97ff-ad79a3b1f557 | ---------------------------------
| note | 253c0961-d50e-451e-903b-9de20fc38c85 | RESPONSIBILITY: SE/Nominated Authority
| note | ca8af37c-5c84-47e6-a583-ce026bbe3852 | ---------------------------------
| note | 38fb5826-3e1f-43cd-a0ed-5cc994bfd3ba | VERIFYING DOCUMENTS: This ITP
| textbox | d5ce517a-c4f6-40ad-ab8f-0aeb12380183 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.5 Unsuitable Material
| note | 278acc45-ae0f-4e14-a007-90833560091b | REFERENCE: Section 204.07 d)
| note | 616ee7cb-e43c-494b-b5e8-736ec9185476 | ---------------------------------
| note | 01fea66d-0b38-4481-b799-3ecd20a646a9 | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
| note | 09178dc3-0761-4977-b968-1a1be2850d4a | ---------------------------------
| note | d55aca79-5d9d-4aa8-9732-99a1857f2edd | METHOD: Visual inspection
| note | 2e577878-4d4b-4dfe-84b0-b5d2d999f1b1 | ---------------------------------
| note | 6551e173-04bf-4fb7-8859-77278ffab405 | FREQUENCY: Each lot
| note | 331b861d-5884-4391-b0c9-0438e71b2892 | ---------------------------------
| note | 7560aad4-106f-4ca2-a4ea-bdd860af33f2 | CATEGORY: HP
| note | 37f5251c-e5e3-46da-ac84-dc38bd0af98e | ---------------------------------
| note | af3d26ca-fbba-416b-b8e4-4adff3c125bb | RESPONSIBILITY: SE/Nominated Authority
| note | 3fdeab15-1ee4-48bc-bc60-238bc6fee621 | ---------------------------------
| note | 9f5012ec-9c93-47df-b8d0-17e0f0b71fef | VERIFYING DOCUMENTS: This ITP
| textbox | d7c1b28c-c032-491e-8719-b5c699a5b510 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.6 Unsuitable Material
| note | ba4f7574-ce92-473f-bab3-061b15471624 | REFERENCE: Section 204.06 h)
| note | a409acce-763b-4fc2-beeb-d4f27a55fa1f | ---------------------------------
| note | 53aea90f-3593-4828-8c38-75214f92a9cf | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
| note | b6d1dd48-fe3d-42d2-8475-12efb54cc9ca | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
| note | 5f5ccf1c-f4a0-4572-90be-5eabfe5d7543 | ---------------------------------
| note | 5430b623-eeba-42ed-b31f-a9d980339f0d | METHOD: Visual inspection
| note | 864b1a01-4e90-4547-8474-ed6e4f226334 | ---------------------------------
| note | 1802fc0a-1356-41d0-840a-6b6450523400 | FREQUENCY: Each lot
| note | 7f0075df-40ee-426f-9841-725a344c60f5 | ---------------------------------
| note | 648f1dcb-ad60-4385-aacd-f8c164137f25 | CATEGORY: HP
| note | 683940e6-ad52-4b09-bef7-6a0dcb41cfa1 | ---------------------------------
| note | 061c11ba-3036-4b60-9eca-bda4d16c9460 | RESPONSIBILITY: SE/Nominated Authority
| note | 1744fc40-dbb3-42a0-8df5-ba079cf80a93 | ---------------------------------
| note | 06fd8faa-b156-4c36-a8e7-ee4216374122 | VERIFYING DOCUMENTS: This ITP
| textbox | 2a23f214-6248-4993-aafb-a605db4ad0d8 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.7 Cut to Fill Zones
| note | 24eab164-ef0d-4b2e-8944-305656cdeb9f | REFERENCE: Section 204.06 g)
| note | b71aa3b3-aec8-4ced-ae0e-ad4fc98af7b2 | ---------------------------------
| note | 8ad66217-d0de-449b-a65f-d50073a77585 | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
| note | 250f548f-e929-44e4-af09-9a0b9c0ac50c | ---------------------------------
| note | 76da708f-83fa-4a86-9608-da483b5da76d | METHOD: Site Inspection
| note | 43fa03c0-dc10-481d-983e-d9f60106fa24 | ---------------------------------
| note | b2a8bf95-dca5-4f6e-91f9-729decc434c0 | FREQUENCY: Each lot
| note | cea74848-50f9-400a-b30e-4fc9ec5f69d9 | ---------------------------------
| note | 958eb4f9-c3a7-4e10-8fb3-48f7d829b9b2 | CATEGORY: IP
| note | e8bbcdc2-bceb-4a97-b997-d0e7b4d432c4 | ---------------------------------
| note | 0ecc8e99-1e90-435a-8850-93d974c929ce | RESPONSIBILITY: SE/Site Supervisor
| note | c3a8c8f0-56fa-4104-8670-dacdc4180599 | ---------------------------------
| note | a5e72e2f-3155-40f7-aeb8-966f62b0ae08 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 1dce2182-7b09-49d1-86e1-74ce8cc1dcd5 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.8 Proof Roll
| note | 55fd725e-9b7b-4814-813e-e7063fa1cf2e | REFERENCE: Section 173
| note | c9e60443-3c84-42c0-9b12-284863dd9352 | ---------------------------------
| note | 01190730-3cec-4cad-aff9-d3f466b507b5 | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
| note | 1cd36d6e-01c0-4023-bd02-25dde7d89076 | ---------------------------------
| note | 6669e4aa-45ca-4a92-b2e7-828c6b92d8da | METHOD: Visual inspection
| note | 46d1f2a0-7620-4435-9406-c684d85fd9c9 | ---------------------------------
| note | 3edd1b48-c97a-40a3-b6ff-af761a3dfcf9 | FREQUENCY: Each lot
| note | a67553bd-c570-4d14-8866-549554f888a3 | ---------------------------------
| note | 98a20f46-71de-4a1b-b35a-808ff0e14291 | CATEGORY: HP
| note | d84f2b24-d1c1-4372-a376-64e1033539d1 | ---------------------------------
| note | 75af242b-90f7-41c2-80e5-98bf8012dc83 | RESPONSIBILITY: Site Engineer/Superintendent
| note | a917a391-66f1-439a-a42c-3ed0c12684ad | ---------------------------------
| note | 680beda6-8229-45bf-b5cd-06ea6a0edf29 | VERIFYING DOCUMENTS: This ITP
| textbox | e755ef51-0848-4efc-aab9-64b8df101670 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.9 Compaction Testing
| note | 94a46269-e81e-4b04-9875-fbfe4b36a0bf | REFERENCE: Table 204.131
| note | c6f57f0f-5bd1-4c79-ae0b-71b5146afd60 | ---------------------------------
| note | f1fec17c-9b40-4f54-8181-42c29028743d | ACCEPTANCE CRITERIA: Type A Material placed within 400 mm of top of Type A Material
| note | 8d2f95ab-fdaa-4a1c-90db-be5f8c10c16e | Scale A: Characteristic Density Ratio 99%.
| note | 395f56ab-9064-41dd-9189-49d4d199e629 | Scale B: Characteristic Density Ratio 98%.
| note | 9c100142-1fd1-4c99-8296-34e6fae72f4c | Ripped and re-compacted material below Cut Floor Level
| note | cf9fb9d9-5892-466d-a76c-6bc44b47417a | Scale A: Characteristic Density Ratio 99%.
| note | 4a163674-5ee4-4707-b6ae-9cc49576386d | Scale B: Characteristic Density Ratio 98%.
| note | df21fa2b-22a0-4438-9112-dfa178f49980 | Note: Princes Highway is Scale A, South Gippsland Highway is Scale B
| note | 83127e83-6a7c-4223-841c-4c514c17c417 | ---------------------------------
| note | 76093e9c-2d4c-4fad-b96a-41199b935f1e | METHOD: Test Point
| note | f2571850-d7f0-4664-8c67-841cc1ac3eb6 | ---------------------------------
| note | ebf11775-456e-462b-80d8-1bfe5f59c38b | FREQUENCY: Each lot
| note | 21a9a4ac-79a1-4d42-a0ab-70ca1190bc46 | ---------------------------------
| note | a2e0f777-3a99-4298-a6f0-fbadba0dd944 | CATEGORY: TP
| note | a21eb30f-7963-49c5-b3bf-38f8d70376a2 | ---------------------------------
| note | fb1fb048-8ff2-45e7-bcc2-661cc4596bec | RESPONSIBILITY: Site Engineer
| note | 5da74fd1-e222-4b78-93c0-f7c910f31bc3 | ---------------------------------
| note | e9f15121-3960-402d-9cb5-e5dfcc0e2e7e | VERIFYING DOCUMENTS: Test Records Lot Register
| textbox | 144c5de4-749b-4f76-a740-360725f22e48 | Date Completed:
| checkpoint |  | 3.10 Post Compaction Material Property Testing
| note | 109d301c-e968-49b6-8e5c-16e5a6c78e08 | REFERENCE: Table 204,041
| note | 54556256-5b7d-470c-9844-e74338a41343 | Table 204.141
| note | b625db54-4bd5-4f4f-bbc3-d09731b67cb7 | Section 204.14 a) or b)
| note | 0e3151d4-5b70-4d13-9fc9-140955b66309 | ---------------------------------
| note | d0225445-6ba9-43c2-8e1d-35bcf29c1e7a | ACCEPTANCE CRITERIA: Material Properties:
| note | a5f08f78-4977-4fcd-b869-fb38a49c7741 | CBR ≥ 3% and Swell ≤ 1.5%
| note | 563f5c2d-9a20-4f5b-b02e-ceb32ed7a08a | Max Permeability = 5X10-9 m/s
| note | 91a9ac66-1200-4391-b7d3-8dca2e09010f | Grading: 75.0mm 100%
| note | 93868bb8-dfef-4cda-bb38-817b63b2ba09 | 4.75mm 40-80%
| note | a3c63830-da22-44b7-815a-a3d8deacba4e | 0.075mm 10-40%
| note | 429c07e4-7566-44b6-887a-e5d81f8b1cb8 | Max. PI x%Passing 0.425mm = 1000
| note | 6b248fd0-88fc-4c8e-9799-8e76c5556051 | PI = 6 to 25
| note | 0f09ec0b-2d3e-4be6-82c1-bdd117359c60 | Scale A:
| note | b5795287-ae3f-47c1-ae09-d5aa5d99589e | CBR & Swell
| note | 723cf9d9-fe7d-44d2-8c63-996bfccc56b2 | Initial - 1 Lot Test to determine Assigned CBR and swell
| note | b855b712-df14-4f46-97d9-405d4841041c | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
| note | ce0f6c51-0605-4df3-8078-02eb181d217c | Max Permeability
| note | 095220c6-efd3-400d-826f-8763b92a5d5e | Initial - 1 test per 2 lots
| note | d2bb38a1-0e5f-4fa5-9c53-67c4e9d7aacc | Reduced - 1 test per 4 lots
| note | 9db2fb99-7089-493a-acd4-714b8a29d388 | Grading:
| note | 398f3f9a-bd89-49bb-8873-573a0739764d | Initial - 1 test for each lot tested for compaction
| note | 19b148da-6da3-4edb-baf6-ec1b47c73a51 | Reduced - 1 test for every second lot tested for compaction
| note | 1ecf60e6-2317-447b-a3fd-36fadd00b87f | Max. PI x%Passing 0.425mm & PI
| note | 1a4da99b-14f9-402d-99c3-4563dbf90aab | Initial - 1 test per 2 lots
| note | 51bc1979-b982-4d8a-9b67-6b310900ea11 | Reduced - 1 test per 4 lots
| note | 8e806be0-8ffa-499d-b6f4-6178bb665e7e | Scale B:
| note | 57f5e2a5-0a14-42dd-87ea-cd4cc8418303 | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
| note | cfe23ac3-a1b6-4511-8907-029a540d51c1 | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
| note | 939ae965-d54f-4e66-b5fa-7e4e62194e86 | ---------------------------------
| note | 3058ee3f-8ebb-4c23-a586-1568c26b4932 | METHOD: Review Document
| note | ea293b5b-d090-4e0a-9912-d8b6a52b1c2f | ---------------------------------
| note | 18fc3631-9d54-4d73-8496-d26020b3a73e | FREQUENCY: Refer to Section 204
| note | 0e2d7b55-bc1e-4b90-b050-6df0364127b2 | ---------------------------------
| note | f38a770b-722d-4076-b91f-ce58ccb67c21 | CATEGORY: IP
| note | 07683f0c-5d70-40d1-8c2a-d217ab2ef482 | ---------------------------------
| note | c53769bd-451c-4a82-a8ba-3751d4d44be4 | RESPONSIBILITY: SE/Site Supervisor
| note | 74bed452-04f0-4369-946d-a847d8d65c1f | ---------------------------------
| note | 87718fd2-4561-490b-858d-72e987e51ccf | VERIFYING DOCUMENTS: Sign ITP Attach Material Property Test Report
| textbox | 6ad402d8-11b2-4b7f-9baf-6d20918d2c9c | Date Completed:
| section |  | Type A Fill/Verge Activities (if applicable)
| checkpoint |  | 4.1 Type A Placement
| note | 44a9e4bf-640c-4628-8dae-f9e6bae54df6 | REFERENCE: ITP-CIV Type A Fill - Road (Suppl and Install)
| note | cb47c005-c814-44da-85d8-754f3bbfa3c4 | ---------------------------------
| note | 8a987322-171e-4cc7-b845-eb9cdb836188 | ACCEPTANCE CRITERIA: If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
| note | 4776c8c4-8845-4563-8654-ad216fc49adb | ---------------------------------
| note | ec4e0425-dae4-4d97-9647-33b8b2525004 | METHOD: Visual
| note | ae19609d-ffb2-4db8-801e-0339be684886 | ---------------------------------
| note | ec3ec073-6ae8-4720-9c6a-234d99beb0a8 | FREQUENCY: Where Applicable
| note | b2d5551a-c2f6-4ee6-8826-ecbfcfbd8b1c | ---------------------------------
| note | 7c8a2eff-007e-437c-b2d8-b7bbed2f409e | CATEGORY: WP
| note | 1daa1515-785d-466c-8010-a9470cae206b | ---------------------------------
| note | 1b236390-4c9b-4c86-871b-03dbfc2ebcd8 | RESPONSIBILITY: SE
| note | 012e7a2e-0106-43be-abb2-830bf23a27bd | ---------------------------------
| note | eaff1f1d-6372-473d-a9dd-d9553c63fc43 | VERIFYING DOCUMENTS: Sign ITP
| textbox | f79d297a-c18e-42df-a7e0-097fb88c6b47 | Date Completed:
| section |  | Post Construction Activities
| checkpoint |  | 5.1 Survey Conformance
| note | beaf9c04-57c3-4f3a-ad0b-7a2e113c8249 | REFERENCE: VicRoads 204.03f,g and h
| note | 525bdc9a-360c-47e2-9c8b-1764c9220b1a | ---------------------------------
| note | 7baa59cf-f3be-43e3-85e0-7c63ec204499 | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
| note | 2956b201-c736-48d3-9b83-8395760e91f4 | Level tolerances (Scale A - Princes Highway):
| note | ef8e256d-64f2-48a0-9cf6-5d68224b1cf6 | Range x = +5, -15mm
| note | daa69796-b57b-44da-9e22-f181cefa6fa9 | Max S = 12 mm
| note | c48dad98-cb0f-40bf-936a-44d406449841 | 80 measurements per lot
| note | fba8d91e-ecff-45bb-bce2-2da2db3c1a2e | Level tolerances (Scale B - South Gippsland Highway):
| note | 5c045091-ac15-44ca-9fbd-77cdc5b770d0 | Range x = +5, -25mm
| note | 82a8d1e9-d2ab-4f69-9b6f-39e1e165adb9 | Max S = 15 mm
| note | f3dac0e6-803a-4172-a4a8-f509508c9419 | 40 measurements per lot
| note | 50640a57-d39c-4c8e-b179-6504ef12f1cb | ---------------------------------
| note | 25900d4d-1a5b-40e6-a025-1db673de6c78 | METHOD: Review Document
| note | f9f53c53-64be-4c35-a18b-028cb365d7dd | ---------------------------------
| note | fc29d7ed-7120-4464-a822-e5d7c11faf31 | FREQUENCY: Each lot
| note | 423fb580-9e33-473b-9e71-883287ca5687 | ---------------------------------
| note | b9dc579e-1e8b-49be-a948-7f5f69b0a900 | CATEGORY: SCP
| note | c5a60527-009d-4f63-ae4d-2b0cbc5659bf | ---------------------------------
| note | 2f6c07a4-7e35-4b7e-a0af-921cad8187ff | RESPONSIBILITY: SE/Surveyor
| note | 14332360-4501-4a18-8566-340d0d8f4b7f | ---------------------------------
| note | 9135fd40-48b4-4318-a548-6ff71f5b5f71 | VERIFYING DOCUMENTS: Sign ITP Attach Survey Report
| textbox | c33736b9-f91f-404b-914f-828d8c0b8ac2 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 7352f203-f288-49a3-8df6-7c6f3bf37c2e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 3b0c0446-9819-4e24-adf1-911fbd8bc622 | Name:
| textbox | fffd9801-1c36-4a00-9992-0b9202f87e05 | Position:
| textbox | 6073dc2e-28be-4660-80eb-919436d833c1 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | itp | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | 362ef263-135a-41ed-b05a-b1aff714553a
| section |  | 1 - Referenced Documentation
| checkpoint |  | Reference Documentation
| note | 7d269e0e-1cd0-5a92-abc5-d41875e360bf | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
| note | 4a46ab9d-63fd-59f6-bb0e-81695a1e4e94 | ITP Description:Concrete Coatings (Protective &/or Decorative)
| note | 48fcf328-cf4e-5a8e-8122-3dbb5ae945ba | Discipline (e.g. CIV/STR/RAIL): STR
| note | 674aa0ac-7eaa-5563-a513-bfb879ea66aa | Revision Number: 2
| note | 53a2e04d-973f-5975-acc2-2d131dd703e3 | Revision Date: 11/12/23
| note | 2fd3da35-f812-5de2-b178-1c783ec62b05 | ITP created by: Mike Freeman
| note | b5169f07-f027-5735-8c58-edb4f1ec0692 | ITP approved for use by: Mike Freeman
| note | edc6eb83-bf6b-522e-869d-4c514b0f0c1a | 1.1 VicRoads Section 685 November 2018
| note | 913f3bbf-97ed-535d-b318-d2dff1d1b7bf | 1.2 VicRoads Section 686 November 2018
| section |  | 2 - Preliminaries
| checkpoint |  | 2.1 - Anti-graffiti System Selection
| note | 754d7867-8870-59ce-8dbd-53557b30759d | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
| note | 4e07b2da-63ae-52e5-963a-9d3cce66f666 | – – – – – – – – – – – – – – – – –
| note | 36015b54-63e0-57cb-bcdf-612f6793a700 | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
| note | 96bd5166-c3b8-582e-8947-ba3eddf4ce71 | i. be either a film-forming or a penetrant system ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification) iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses (film-forming): WFT total = 175µm min. OR WTF per coat = 88µm min. DFT total = 100µm min. vii. adhesion to substrate (film-forming): 0.75MPa min. viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
| textbox | 48c4542f-887f-59d4-85bd-edb5dd436776 | Enter: Teambinder Material Approval number
| note | 5904154f-fb50-5d13-8069-f8faad0a4312 | – – – – – – – – – – – – – – – – –
| note | 3dc99c44-d02f-5ba8-aa12-c6ba9fd0f75e | METHOD - Document Review
| note | b007fb24-85e6-594e-8ad0-bd402b3c1f5f | – – – – – – – – – – – – – – – – –
| note | 04e52cce-a6e1-5de7-8f7e-70d624f6cbcb | FREQUENCY - Once, for each coating system, 14 days prior to application
| note | 1ebc1e06-26c8-59ce-9ad0-50ba993c50b2 | – – – – – – – – – – – – – – – – –
| note | e7f8ebe7-4938-59df-8676-929186e58f0a | CATEGORY - HP
| note | 41bb9c5b-4001-54c5-a915-2126978fb208 | – – – – – – – – – – – – – – – – –
| note | 978fed09-697d-5cd9-8748-69e7c686b640 | RESPONSIBILITY - Nominated Authority
| note | e1d62eae-1d32-5245-98fa-4655fab85ff0 | – – – – – – – – – – – – – – – – –
| note | e67314f4-51c7-5e28-abf3-b0f5eee13594 | VERIFYING DOCUMENTS - ConQA Hold Point Release
| textbox | 781ee9f5-f7f2-5d78-b2fa-6ed37f1bf104 | Date Completed:
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 - Decorative & Anti-carbonation System Selection
| note | fd448d48-0141-5440-ab24-d8a9ceb5dee7 | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
| note | 6f90523d-f751-5911-96d4-8123ea42a8a0 | – – – – – – – – – – – – – – – – –
| note | 7b1040fd-8ec7-500b-8fa7-e1e082de5894 | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
| note | aec22b3b-ea6d-55dc-8ece-ee0becd1f514 | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
| textbox | c8b33167-8e55-55f6-8619-73ca88cc6fe1 | Enter: Teambinder Material Approval number
| note | 56960410-d56b-572e-b6ac-893c5b60c697 | – – – – – – – – – – – – – – – – –
| note | 5ce3f82f-cffd-5a1a-800c-cebdc02e9c9e | METHOD - Document Review
| note | 22d295ce-1b02-5e9d-adcd-aba8b61ce537 | – – – – – – – – – – – – – – – – –
| note | b30d1dae-1e41-5791-85aa-a9b740a288b9 | FREQUENCY - Once, for each coating system, 21 days prior to application
| note | 0133ac84-07cf-53c6-b62d-4ad57a327112 | – – – – – – – – – – – – – – – – –
| note | 282b0787-0013-5623-855a-628144940634 | CATEGORY - HP
| note | 32d1e173-79ca-55e4-891d-99f887ee5696 | – – – – – – – – – – – – – – – – –
| note | 866c10bc-5a2a-58e5-9d42-218cadd7387b | RESPONSIBILITY - Nominated Authority
| note | 112fa360-a59d-5c98-8cd9-45691ae491aa | – – – – – – – – – – – – – – – – –
| note | b8f3d637-0111-5a69-932b-84e47b0505b1 | VERIFYING DOCUMENTS - ConQA Hold Point Release
| textbox | 6e83368a-8517-5b5c-86e8-7e96fba4f95c | Date Completed:
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
| note | b9b2f3d4-05c4-518d-a10b-2ef04c263b39 | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
| note | 567a3b8e-e12b-5ee7-91d4-eabd4c7044a4 | – – – – – – – – – – – – – – – – –
| note | 27c80a7b-a08f-5f68-840c-a5863543be84 | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
| note | 454e16a8-350c-5869-981d-84d0cb928a5f | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
| textbox | ae4a2cbe-0891-5f65-afb3-57dc0b30c1f8 | Enter: Teambinder Material Approval number
| note | 54af77ab-c2a2-5c35-9fa6-6c6dc52f967c | – – – – – – – – – – – – – – – – –
| note | b76d94a4-cc7d-5bd3-8755-50fc786ae336 | METHOD - Document Review
| note | ae394e8b-60b5-59b1-802b-607c4f2bd20c | – – – – – – – – – – – – – – – – –
| note | 411acccc-258d-5fa1-9745-7255ada0f1c3 | FREQUENCY - Once, for each coating system, 21 days prior to application
| note | 6b54044e-7eec-5094-8051-e6fee00e5d3a | – – – – – – – – – – – – – – – – –
| note | d9b4e16e-d2e3-5b01-9319-f0677fe2d20f | CATEGORY - HP
| note | 62c0c56c-860c-5ed0-8d5e-16cd97bc4584 | – – – – – – – – – – – – – – – – –
| note | da111279-34c7-5c05-a99e-0f7fe518232f | RESPONSIBILITY - Nominated Authority
| note | f423e1c1-f4ee-5f75-8025-57cbc56c4c99 | – – – – – – – – – – – – – – – – –
| note | ae6d141d-d41c-536d-8250-21e80e7f3f94 | VERIFYING DOCUMENTS - ConQA Hold Point Release
| textbox | 257d7c0f-0670-54bc-810d-25277e5718ca | Date Completed:
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
| note | f8ad5bcd-e0ad-5653-bcd5-d5004319e07b | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
| note | 406938be-9b0e-533e-a42d-707bbe54adde | – – – – – – – – – – – – – – – – –
| note | 89bdd11d-91e6-5a8a-b234-8670c07abb6f | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
| note | 2f2d3730-3454-565a-94aa-f1d99415b76c | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat ii. all coats to be compatible with each other Penetrants: iii. active ingredients: Silane = at least 95% Solid silane & silane cream = at least 80% Silane-siloxane & siloxane = not specified iv. application rates: Silane = 2 applications of 0.3L/m² min. Solid silane & silane cream = 1 application of 0.4L/m² min. Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS Film-forming coat: v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) vi. to be water or acrylic based, solvent-free vii. to be non-yellowing, colour-fast and not subject to fading viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure ix. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 200µm min. x. adhesion to substrate: 0.75MPa min. xi. able to bridge cracks up to 0.3mm wide xii. able to be re-coated within 24 hours xiii. have a minimum pot life of 1 hour xiv. compatibility to an alkaline surface xv. equivalent air thickness >150m xvi. equivalent concrete thickness >450mm xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s xviii. Water vapour equivalent air layer <4m xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
| textbox | e691a854-1407-56fe-bef2-025fb42be7a5 | Enter: Teambinder Material Approval number:
| note | 660ff69b-1f23-5148-8a93-d36cabd8959b | – – – – – – – – – – – – – – – – –
| note | 38536c4c-957c-583d-91bc-a7c4a5665290 | METHOD - Document Review
| note | 7f9d9111-2b6c-5183-92e5-d842fac1e698 | – – – – – – – – – – – – – – – – –
| note | 6219f20e-8bdf-588a-8071-4fbb4aab529b | FREQUENCY - Once, for each coating system, 21 days prior to application
| note | 7e1963a7-b15c-52b0-8eab-698b2f295af9 | – – – – – – – – – – – – – – – – –
| note | a299e4f9-6248-59b3-b91a-a966d5690ef4 | CATEGORY - HP
| note | ef852e1d-e7ed-5090-b0ef-5dd324f435e7 | – – – – – – – – – – – – – – – – –
| note | f3c70fb5-bacc-5cc3-a03d-a74e8a03e54e | RESPONSIBILITY - Nominated Authority
| note | ff76337a-59cf-5406-b472-ca8e67666f72 | – – – – – – – – – – – – – – – – –
| note | ef200d04-f8b0-573a-be73-d5940e75a179 | VERIFYING DOCUMENTS - ConQA Hold Point Release
| textbox | 99ec31b7-1c89-5856-bf8f-1d291684df2d | Date Completed:
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.5 - Quality Documentation
| note | 01c48075-017f-529e-9a70-e87e8290d3fe | REFERENCE - 685.05 686.04
| note | a8dd5687-a597-5571-a14e-439985f69221 | – – – – – – – – – – – – – – – – –
| note | 2a7aff65-f229-5a95-be61-49e5e0950960 | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
| textbox | 21007912-7ae4-5dc3-a1d8-da089b3f4f88 | Enter: Teambinder Hold Point number
| note | 5b8e58d5-be14-57a0-b49e-50a4e823ac0d | – – – – – – – – – – – – – – – – –
| note | cec43701-49aa-5c7a-9944-8280638b2701 | METHOD - Document Review
| note | 34c0a64c-1de4-5098-a813-bb4b470573f3 | – – – – – – – – – – – – – – – – –
| note | 9388e694-ef4f-5dcb-b735-aebc68323b36 | FREQUENCY - Once, for each coating system, 21 days prior to application
| note | 8c27a2eb-4376-5c2b-ade3-53db739e3245 | – – – – – – – – – – – – – – – – –
| note | a95deb97-e0ee-520e-9562-0beb339c2b29 | CATEGORY - HP
| note | 86737bf7-868b-5d16-9749-d81445efd6fc | – – – – – – – – – – – – – – – – –
| note | 8aee0827-3984-50e1-b181-62d1d3f4c647 | RESPONSIBILITY - Nominated Authority
| note | 77e14b2a-a04b-5ba2-a691-d3176050d820 | – – – – – – – – – – – – – – – – –
| note | 04196a12-1c4c-5536-8fcc-1388e85fe656 | VERIFYING DOCUMENTS - ConQA Hold Point Release
| textbox | fb516fb9-db71-5959-8dfb-bd7461e78abe | Date Completed:
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.6 - Coating Personnel & Equipment
| note | 2bb5f640-a7ce-59f5-bc29-e6165c477239 | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.19
| note | 37a000b7-9a7e-5e49-9b7a-c8c3e04b15b6 | – – – – – – – – – – – – – – – – –
| note | 0a0659a8-3b11-50db-b567-88770cd890ec | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
| note | 768a9726-a320-5389-89ac-c9ee4487b661 | – – – – – – – – – – – – – – – – –
| note | 33a70441-97fd-5cb9-8451-c8613634e8f8 | METHOD - Document Review
| note | 3cf307e6-b6c3-5a35-8de9-baf031eeb768 | – – – – – – – – – – – – – – – – –
| note | 93f829ec-806d-5d32-b4eb-6effab5323c7 | FREQUENCY - Once, prior to application.
| note | fdcc2a77-ed07-57a1-9bc5-5ade48302161 | – – – – – – – – – – – – – – – – –
| note | f3022832-daa8-566d-a0c0-1c2f6fb11526 | CATEGORY - IP
| note | 7fbfafef-50c0-58bd-9436-93b1ea6cbddc | – – – – – – – – – – – – – – – – –
| note | ddb20a36-1243-5881-8f33-f02a2d215fa3 | RESPONSIBILITY - SE/PE/SPE
| note | 3131565f-75bd-5bf2-9e7d-0d421e7e0cc2 | – – – – – – – – – – – – – – – – –
| note | 2662aa74-c8dc-5698-acd8-26a3cb948ac6 | VERIFYING DOCUMENTS - This ITP
| textbox | c8525244-6fc5-508e-8adb-a932ea4c5867 | Date Completed:
| checkpoint |  | 2.7 - Protection of Adjacent Works & Property
| note | 155c784f-ff3d-56a5-a8c6-4af35e5ea4a8 | REFERENCE - 685.17 686.10
| note | f4e5d787-03f9-5800-bf78-35e0dcfe9e98 | – – – – – – – – – – – – – – – – –
| note | 819834e9-7dcb-53b8-bc52-7bafbc94ab77 | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
| note | caf58060-b468-55fe-a790-5d9c9ec0525c | – – – – – – – – – – – – – – – – –
| note | 6a5f7e47-6983-53ac-8ed9-503796a1e3b5 | METHOD - Visual Document Review
| note | a8afed93-870e-5af9-a830-70a5d817fb44 | – – – – – – – – – – – – – – – – –
| note | 49b7a203-0d3a-5a4f-8f40-0abff141815a | FREQUENCY - Where applicable, 2 days prior to application.
| note | 04f33422-6543-5d5a-ac8c-1554c87f3ffe | – – – – – – – – – – – – – – – – –
| note | 14eaa722-2d9b-5070-82b1-9b870c2e23c4 | CATEGORY - HP
| note | 7de9d6a2-a24e-52de-98cd-0949f15cfc38 | – – – – – – – – – – – – – – – – –
| note | a8e1ec77-4d1e-5774-a6d2-435fb88b0d78 | RESPONSIBILITY - Nominated Authority
| note | c3118771-3a5f-5d3c-8ce7-6d6041e9dedc | – – – – – – – – – – – – – – – – –
| note | 87c60b9e-141c-5df2-a4b9-bb495d75232b | VERIFYING DOCUMENTS - ConQA Hold Point Release
| textbox | 82108ef9-07e4-54db-93a2-507a425bc698 | Date Completed:
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.8 - Minimum Concrete Curing Period
| note | 2f20ebd4-4aaf-5c0b-b31a-752cc27d9b7f | REFERENCE - 685.08 686.16
| note | e055fec3-41e6-505e-a2bd-236e39ced789 | – – – – – – – – – – – – – – – – –
| note | a30505cf-b016-5a03-a6b2-110c50410b8e | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
| note | daca14b6-c603-5176-aecb-c5d42710585f | Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
| note | 6db48fb6-ce7d-57d6-a36b-e71fc6b6af3e | – – – – – – – – – – – – – – – – –
| note | 464366fc-b97e-5321-96cf-897f628bae06 | METHOD - Visual Document Review
| note | 7e9d28f0-fba3-5394-8dec-371550dd00c2 | – – – – – – – – – – – – – – – – –
| note | 9d876f3a-38fe-55e9-8e32-63fc564eb033 | FREQUENCY - Once, prior to application.
| note | 816ffd18-78fc-5ff7-9f19-fe2d0cc9f337 | – – – – – – – – – – – – – – – – –
| note | a4663f70-df1a-53e3-b1b5-02eeb66073c4 | CATEGORY - IP
| note | c034c8da-e562-5417-b6bf-b71204fcb7ce | – – – – – – – – – – – – – – – – –
| note | 0b361644-139c-5b43-8dde-16d8be7309e4 | RESPONSIBILITY - SE/PE/SPE
| note | 28134284-c6d9-5149-afb9-67a6eaaea75c | – – – – – – – – – – – – – – – – –
| note | ff07c8c5-fd32-589d-88d2-2378bc69110e | VERIFYING DOCUMENTS - This ITP
| textbox | 6f167f00-298c-50e0-9d8b-462f08c0aee6 | Date Completed:
| checkpoint |  | 2.9 - Trial Application (or Past Performance) Inspection
| note | db3c73fb-79b2-5236-8a5b-eba7aedadd3f | REFERENCE - 685.11 686.13
| note | 1fbe9fce-0965-53de-b8d0-ab738ca07b3a | – – – – – – – – – – – – – – – – –
| note | 9c4a49a4-1dad-5655-89dc-03ebd2811a0c | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
| note | ae50b6a2-eaa2-5364-a09a-c4058d287230 | Attach: Inspection Photographs OR
| textbox | 8b5091b7-b26c-5e4f-8f44-0ec60fc02cc8 | Enter: Teambinder Hold Point number
| note | 55b41267-1fb6-5789-ac4a-fcf7ef258bda | – – – – – – – – – – – – – – – – –
| note | 44224803-78d6-5d6d-80cc-ef710e8ba84d | METHOD - Document Review
| note | 010895a9-bb6f-55a7-b814-594c246b8a9a | – – – – – – – – – – – – – – – – –
| note | e9bc5f44-f454-5ec6-a4f5-8d36fd62baa5 | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
| note | 67df4abd-ab09-5d10-837a-c45e4405b157 | – – – – – – – – – – – – – – – – –
| note | 8dc99c0c-e807-5a85-868b-167a84c8ac6c | CATEGORY - HP
| note | 80c49d5e-3dbb-5d99-9c29-2118327c0127 | – – – – – – – – – – – – – – – – –
| note | 67b58dbf-30ed-5228-aee6-9ffd853af286 | RESPONSIBILITY - Nominated Authority
| note | 7397a4f0-6df9-507c-b8a5-097ad7a5b533 | – – – – – – – – – – – – – – – – –
| note | 8dfb16d0-79e2-5e1f-91cf-7ae8492cea7f | VERIFYING DOCUMENTS - ConQA Hold Point Release
| textbox | 3234187d-94bb-568c-a11d-39fe5d2f1a55 | Date Completed:
| signoff |  | AUTHORITY HOLDPOINT
| section |  | 3 - Pre-application Activities
| checkpoint |  | 3.1 - Material Records
| note | f4b676e5-d2ce-5b1d-8646-a802f5b658bb | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 686.12
| note | 61187568-de0d-5c63-9054-0c7ef5dcc374 | – – – – – – – – – – – – – – – – –
| note | 6b3689f4-13ed-571d-be04-e1cd09a21914 | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
| note | 9027a9c4-2dd7-5ac0-b516-c6c29a65b78d | Product beyond the manufacturer's shelf life shall not be used. Each product shall be traced to final location.
| note | 118b6f59-8fca-5b1a-80bc-6bf411dfaa79 | – – – – – – – – – – – – – – – – –
| note | 050feba5-fc2b-578a-b887-88f185011f10 | METHOD - Visual
| note | 3faa44dc-65ed-57e5-9b0c-97563cc7849f | – – – – – – – – – – – – – – – – –
| note | 14ad93d5-76c9-5921-ae21-ffecd29600eb | FREQUENCY - Prior to application
| note | 67b8dfd5-d806-56fc-870e-cf481b146632 | – – – – – – – – – – – – – – – – –
| note | df9ea46a-bd98-5fc6-abec-5e5067b97d96 | CATEGORY - IP
| note | 95a1cbad-09f5-5230-a9b1-d3d552457f55 | – – – – – – – – – – – – – – – – –
| note | 9cd2df16-6a8f-50bd-8e75-de71c0f79b34 | RESPONSIBILITY - SE/PE/SPE
| note | 15e562f7-bd16-551e-9b8c-2414051d63b6 | – – – – – – – – – – – – – – – – –
| note | b4199c71-3f9a-5909-a15d-bf6b39f227bd | VERIFYING DOCUMENTS - This ITP
| textbox | c5925757-d876-588e-825b-4fd06dda77ee | Date Completed:
| checkpoint |  | 3.2 - Weather Conditions
| note | 85d44ffa-324d-5b27-ae43-19018f1dd047 | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
| note | 69da04fb-1fe4-5f5b-a613-f5cdfb8bec28 | – – – – – – – – – – – – – – – – –
| note | 48d01f54-e5fd-523d-b045-012c63ed2a37 | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
| note | 888d395b-2c8c-5721-b22c-ecd93ba8cac9 | i. windy conditions where spray/splatter may be generated ii. when wind-borne debris is likely to contaminate the uncured surface iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate vii. when the substrate surface is wet or damp (unless it is required for the coating system)
| note | 366df352-c577-5128-bade-33bf59e50ffc | Weather conditions are to be recorded.
| note | 6794a87e-b055-545b-9689-9d5cf87c7103 | – – – – – – – – – – – – – – – – –
| note | 99193ce6-4e14-58c0-87bb-07ebd9ac7b2c | METHOD - Visual Measure
| note | 8dc3b200-d8d3-5dd5-a3d8-1e8915b5cd9b | – – – – – – – – – – – – – – – – –
| note | c807c330-93a4-5b66-9972-35693ec02987 | FREQUENCY - Prior to application and every 4 hours per shift
| note | 652380cd-b367-51bb-89f9-49f77a0a0c04 | – – – – – – – – – – – – – – – – –
| note | a3ef8e30-f265-5aec-9c4b-1200473ab63d | CATEGORY - IP
| note | 1c68652d-0a36-5557-956d-ffa8e91a912a | – – – – – – – – – – – – – – – – –
| note | 53782877-f775-5322-bddd-073a65d01d7a | RESPONSIBILITY - SE/PE/SPE
| note | a4df299b-04fd-5b3e-934f-08d51133dda5 | – – – – – – – – – – – – – – – – –
| note | de3a8cff-b015-5a11-a829-e18db6806f4d | VERIFYING DOCUMENTS - This ITP
| textbox | 99bebd89-caee-5d93-b9c8-cc0838cdcff6 | Date Completed:
| checkpoint |  | 3.3 - Surface Preparation
| note | 045aed30-c5c3-5b4d-a08a-05918fc290d4 | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
| note | 19c8d26a-3249-5b73-91af-fc7189571036 | – – – – – – – – – – – – – – – – –
| note | 53c8afee-4467-5c3e-936e-9e896d11c130 | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
| note | ff9cc233-8def-5a99-abdf-c630719f5de7 | – – – – – – – – – – – – – – – – –
| note | f6d55d00-66da-5a4c-a426-b4e5593c5189 | METHOD - Visual
| note | 9b4b2774-67ce-56fd-ae59-9c49caa702da | – – – – – – – – – – – – – – – – –
| note | 9894c8f9-3fe7-5155-a8c5-04f71d1add47 | FREQUENCY - Once, prior to application.
| note | 33a8de1c-b557-5e9d-b25b-e2b663132fa5 | – – – – – – – – – – – – – – – – –
| note | 56fbf9c8-fb46-5ed2-809e-39d2bb36a587 | CATEGORY - IP
| note | fe37ebfc-8704-5df5-8c7d-0efdd929d926 | – – – – – – – – – – – – – – – – –
| note | 3754c69b-cbe1-5096-af01-42ccb333e5e6 | RESPONSIBILITY - SE/PE/SPE
| note | 6de20832-5621-5dde-92b1-2c04db6bb7bf | – – – – – – – – – – – – – – – – –
| note | 3df83cf2-87fa-515c-966a-474b92cc4191 | VERIFYING DOCUMENTS - This ITP
| textbox | 9825a65d-5f84-59e1-8399-9928df3eb68e | Date Completed:
| checkpoint |  | 3.4 - Surface Moisture Testing
| note | 54dd2758-9034-5bf4-a143-e105ee7c778a | REFERENCE - 685.12 (a) 686.14 (a) (iii)
| note | ef306ddb-68c3-56e8-a406-5c383d79e997 | – – – – – – – – – – – – – – – – –
| note | 2fde8f3b-0300-58ef-8e10-f0673f6f496b | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
| note | d32f6649-3665-5a98-8f8c-16c23096c2ef | – – – – – – – – – – – – – – – – –
| note | d0cecd25-6967-5721-98e6-957fa44ff195 | METHOD - Test
| note | 9dc4b194-9c04-5680-86bd-633e6146682f | – – – – – – – – – – – – – – – – –
| note | c9794f2a-8154-54c0-a900-98c91f3dd8ef | FREQUENCY - Immediately prior to application, test 1m²
| note | 812978a5-e9fb-5139-a59e-023e5fe93cc9 | – – – – – – – – – – – – – – – – –
| note | 7ea76aad-7433-5e96-8001-dc42dbea8736 | CATEGORY - IP
| note | 7d02190a-2c14-527d-9048-22f04b16f1f8 | – – – – – – – – – – – – – – – – –
| note | db78d603-91d5-5803-a279-9d92744e8d42 | RESPONSIBILITY - SE/PE/SPE
| note | 4c822d04-2b16-5931-9020-578b47472938 | – – – – – – – – – – – – – – – – –
| note | 9db724b4-b6f2-53d5-a50e-5350b0573ebb | VERIFYING DOCUMENTS - This ITP
| textbox | 3d34be89-5335-53cd-8296-41f0277215f5 | Date Completed:
| section |  | 4 - Application Activities
| checkpoint |  | 4.1 - Method of Application
| note | d3f5d787-e436-5650-9f91-ed8ff0e1dbab | REFERENCE - Coating System TDS 685.07 686.07 686.09
| note | a6111f2c-5715-5615-af85-9d475d26d396 | – – – – – – – – – – – – – – – – –
| note | 287374ef-efcf-52ef-ae34-afbd9f23d298 | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
| note | aae5cbcb-4b1b-5c5a-a45d-b50ef0b8a9e4 | Attach: Coating Application Record
| note | c1145510-0381-5c5f-a546-ad5a0352eb26 | – – – – – – – – – – – – – – – – –
| note | 7870586c-d0e7-5d46-9372-33811e9d98cf | METHOD - Visual Measure
| note | 05bbb813-6e9e-511f-8d50-5edff9c991e8 | – – – – – – – – – – – – – – – – –
| note | 234ca688-01c9-5bf7-a4ef-ce30cf774152 | FREQUENCY - Each coat
| note | 9c6455a2-890e-55a5-9ea0-153109f6c181 | – – – – – – – – – – – – – – – – –
| note | 8a2b9410-de57-5533-928e-ca09486dfef2 | CATEGORY - IP
| note | a223c4e1-3b4e-5161-9f7d-1405d622bce7 | – – – – – – – – – – – – – – – – –
| note | ee57dee7-794c-59ac-993c-bf08d19bb4bc | RESPONSIBILITY - SE/PE/SPE
| note | d97b5162-cb57-5ddc-a72d-53200a4d416d | – – – – – – – – – – – – – – – – –
| note | 2b7f0871-e4a4-5f2a-905f-e9dececd09d5 | VERIFYING DOCUMENTS - This ITP
| textbox | 1417ca74-a3c2-5358-8ac7-b0e240e38ede | Date Completed:
| checkpoint |  | 4.2 - Wet Film Thickness (WFT) Testing
| note | ea7cbbce-b509-53f9-bac6-174563523516 | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
| note | fef39c99-e000-56b1-8066-29ac844b45eb | – – – – – – – – – – – – – – – – –
| note | b4e79c92-c84d-558f-9ce5-585cf804091d | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
| note | 1556dfc3-0c19-5c71-8d0a-49905b8bb28e | Attach: WFT Test Results
| note | ceffc581-9374-5bc1-adb8-dd7674646183 | – – – – – – – – – – – – – – – – –
| note | 6b2b37ca-ea0d-529d-ad79-4af69688a3d7 | METHOD - Test
| note | 32357408-77b9-5dc5-80ac-1ff341ac4b17 | – – – – – – – – – – – – – – – – –
| note | 854f114b-d280-5f2f-b41f-670653ee06f9 | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
| note | bb3f361d-a5f4-5c44-ad1c-17c3d0d298dd | – – – – – – – – – – – – – – – – –
| note | b9ffa7c8-2214-562a-bbfa-ca9940be4590 | CATEGORY - IP
| note | a273d883-3560-5764-a568-1f956d039eff | – – – – – – – – – – – – – – – – –
| note | 1ea3a008-c0d6-56d8-ad04-58c405d4a98c | RESPONSIBILITY - SE/PE/SPE
| note | 5ed1228e-75e9-5d54-bbe9-c87f977f8cb6 | – – – – – – – – – – – – – – – – –
| note | 76ca6d0e-1b24-550a-afa3-0f77736a0312 | VERIFYING DOCUMENTS - This ITP
| textbox | 000287bc-8e99-538e-862c-e8324543262c | Date Completed:
| checkpoint |  | 4.3 - Inspection & Defect Identification
| note | d0894135-4593-51ee-8246-30339358fb6a | REFERENCE - 685.07 685.13 (d) 686.07 686.15
| note | 3b7b52f1-3e36-5357-be4f-f1561b643a59 | – – – – – – – – – – – – – – – – –
| note | 1fb3ebeb-2231-5546-ae35-5ad263729f56 | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
| note | 818dcab7-2085-5d9b-b735-180cac904b8a | – – – – – – – – – – – – – – – – –
| note | ea7a854f-6c37-500b-a3cf-0156a106fce9 | METHOD - Visual
| note | feeb3536-2b9f-566f-ad1d-31781096c6ab | – – – – – – – – – – – – – – – – –
| note | 347f4ee7-25a3-5fca-863d-6a8fd1b9546d | FREQUENCY - After each coat
| note | f2f377f8-acb8-5ecf-b7d3-b5d55297978e | – – – – – – – – – – – – – – – – –
| note | fabcc205-ddb5-5a46-902c-83f372f2aa38 | CATEGORY - IP
| note | 33581b43-2f1b-534c-8a4d-89f1e9864f0f | – – – – – – – – – – – – – – – – –
| note | 50fd8ddd-61d4-5d8f-b46b-c19903b0a3cf | RESPONSIBILITY - SE/PE/SPE
| note | 275ca1e6-f4ae-57f6-8547-efe28e37d08f | – – – – – – – – – – – – – – – – –
| note | 3e0cec08-9281-5025-9130-8834e02f564e | VERIFYING DOCUMENTS - This ITP
| textbox | 8db94da9-8dcd-5405-9ea9-d255f9e02a33 | Date Completed:
| checkpoint |  | 4.4 - Drying and Curing
| note | 28dde064-737c-59f4-86d9-127c0b3d556f | REFERENCE - Coating System TDS 685.17 686.09
| note | 3038564c-57ec-5911-a679-7acde198d840 | – – – – – – – – – – – – – – – – –
| note | 9ab0b8a7-e348-53e7-ad23-7d52adc69622 | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
| note | 94fd6290-f988-54c7-b7b9-09860bf3ed6c | – – – – – – – – – – – – – – – – –
| note | e78ff3b3-8114-5af0-a182-46399dbc6e5b | METHOD - Visual
| note | 91ca73e4-c633-55fb-9528-9e5e25f490c8 | – – – – – – – – – – – – – – – – –
| note | fd10349b-ba1d-5139-8f8d-8261718a0009 | FREQUENCY - After each coat
| note | cf21442d-d181-578f-8db6-eb5157e1dad9 | – – – – – – – – – – – – – – – – –
| note | e3524e40-c9f7-536f-9ac0-2e9a2ec19b2e | CATEGORY - IP
| note | 0ee11d94-d577-5eeb-a2ab-e04bb428bc75 | – – – – – – – – – – – – – – – – –
| note | f689218e-d79c-562f-bc38-730f764fa5f0 | RESPONSIBILITY - SE/PE/SPE
| note | 5fdffa32-921a-5b92-b210-0f0586eb3262 | – – – – – – – – – – – – – – – – –
| note | 6acfcdec-4954-5e51-b195-e357d5eef268 | VERIFYING DOCUMENTS - This ITP
| textbox | a7ddc624-d554-56d3-92fd-850d04e4310f | Date Completed:
| section |  | 5 - Post-application Activities
| checkpoint |  | 5.1 - Clean-up & Waste Disposal
| note | 9d71a5ce-0d21-5c39-8784-298077ac18af | REFERENCE - 685.09 (c) 686.10
| note | 570d8a93-4ced-55a6-9c9a-ad35e5546c73 | – – – – – – – – – – – – – – – – –
| note | 13691a64-b84b-5b06-a543-607360b488a8 | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
| note | eaea6e89-b98f-56f8-b236-fc61a5b08dfd | – – – – – – – – – – – – – – – – –
| note | 5a22fba0-7ec1-5af0-a05f-5986560b37ab | METHOD - Visual
| note | a163964e-0603-5f31-9495-3f1265fae614 | – – – – – – – – – – – – – – – – –
| note | 42e6bde5-0395-5dd7-9a7f-862d0653d046 | FREQUENCY - At completion of Works
| note | eb87560e-23cf-5db2-9df0-36b154ba4603 | – – – – – – – – – – – – – – – – –
| note | 5579f4bf-1c81-5292-b032-43c3dde6c6f0 | CATEGORY - IP
| note | b4128a97-ee07-5f05-ab62-c3a025c96f87 | – – – – – – – – – – – – – – – – –
| note | 509a3330-31cc-5fb0-8720-8ec037b55009 | RESPONSIBILITY - SE/PE/SPE
| note | 2b6e726b-e1c3-5129-8ca2-accd69754d67 | – – – – – – – – – – – – – – – – –
| note | b6b13cf1-57eb-5bde-8526-69b04f521f37 | VERIFYING DOCUMENTS - This ITP
| textbox | c878d1e5-7d54-544b-9d80-43554d0138c4 | Date Completed:
| checkpoint |  | 5.2 - Dry Film Thickness (DFT) Testing
| note | 8cbfa3cd-2c7e-5cfc-9283-616cd1ae1646 | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
| note | 3f334219-cf4b-5821-906c-9fbe6affbbe3 | – – – – – – – – – – – – – – – – –
| note | 4b9d8c52-c3a2-5ce7-b7b2-2b4215b7b391 | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
| note | 2b569e4b-f6d1-56f3-8537-656d66811b7a | No more than 15% of the readings shall be less than 90% of the required thickness.
| note | 470cd878-7f5e-5d66-b9bb-6d4c8716b225 | Attach: DFT Test Results
| note | d1e55126-d2ba-5a32-b888-dfb020a8a2f6 | – – – – – – – – – – – – – – – – –
| note | ddf3e0d6-cad0-5c2a-9f58-e6e315c02ab0 | METHOD - Test
| note | 83ed8873-2c68-570f-ade0-33862f9d816f | – – – – – – – – – – – – – – – – –
| note | 8c83fc0c-b440-5245-9de6-5b51cc0027c3 | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
| note | 3a9c8dbf-ee1b-548f-bea9-4fe757da9ad8 | – – – – – – – – – – – – – – – – –
| note | 340b1567-b48d-56ab-be9c-84a649f79bf5 | CATEGORY - IP
| note | c26ec932-f5bf-5801-871a-d323de067e1b | – – – – – – – – – – – – – – – – –
| note | 9bf9c37c-ac06-5499-8223-7cbc42673584 | RESPONSIBILITY - SE/PE/SPE
| note | a9ae7406-db27-5936-ab38-9ea60e8ce598 | – – – – – – – – – – – – – – – – –
| note | ec7e54c0-a6f5-5426-9b11-7d01ad6daa1f | VERIFYING DOCUMENTS - This ITP
| textbox | a9f85d4b-4e47-572a-9a14-bb798cb67c15 | Date Completed:
| checkpoint |  | 5.3 - Adhesion Bond Strength Testing
| note | 2c39166f-2bd5-5da9-b641-5cb57c2a5054 | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
| note | ffc2faba-0624-554a-9a0e-826564b0022f | – – – – – – – – – – – – – – – – –
| note | 2bba3ae7-f12a-5f9d-9e19-41ed91c587d4 | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
| note | ff988068-9652-5cb2-9914-f06796fe85f3 | Attach: Adhesive Bond Strength Testing Results
| note | 0b5d5ca3-525d-5470-80ce-b3c651dca4a8 | – – – – – – – – – – – – – – – – –
| note | b52ce605-315b-58cd-8e2c-55fa43e023db | METHOD - Test
| note | 46868af7-223c-5510-ae85-d61035db44f2 | – – – – – – – – – – – – – – – – –
| note | 68ee50a2-51b2-5503-8a4a-395287b79439 | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
| note | 68f2294d-cbe6-5514-ac6b-4df748aa5a7c | – – – – – – – – – – – – – – – – –
| note | 8f791514-dc7e-580a-bdd1-1ed1d0fbae95 | CATEGORY - IP
| note | b0755983-e4dd-5ddf-b7ba-c2ec74b59d26 | – – – – – – – – – – – – – – – – –
| note | 82550fd3-5d16-5398-b9ce-dbb81dd5ddec | RESPONSIBILITY - SE/PE/SPE
| note | dacdf0b4-9c99-5490-8033-290506c4a565 | – – – – – – – – – – – – – – – – –
| note | 8d25eede-07c2-5b10-9a80-66f4bfbee20e | VERIFYING DOCUMENTS - This ITP
| textbox | 0a4ba1b2-5acd-5fd7-942e-793579873071 | Date Completed:
| checkpoint |  | 5.4 - Penetration Depth Testing
| note | 9aa66049-c645-53fd-8465-d327836a21f0 | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
| note | b1ff0ec5-5633-5fe2-baba-add5b46a097d | – – – – – – – – – – – – – – – – –
| note | 8a271cfd-6c23-5226-a38f-f548d81c24f7 | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
| note | 37c083d1-05cc-50f5-8350-dd2afb22f763 | Attach: Penetration Depth Testing Results
| note | 984e54af-74ce-519b-8fca-a01f4d702c5c | – – – – – – – – – – – – – – – – –
| note | d9fddca3-adb4-56ab-863a-f3a3b5e2de6e | METHOD - Test
| note | b41d9df7-5830-5800-af8c-759156857229 | – – – – – – – – – – – – – – – – –
| note | 0f59b614-daac-5b15-a270-c96d0abdd082 | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
| note | 80f02e9e-4482-50f8-8f6b-8a6f7c2464c9 | – – – – – – – – – – – – – – – – –
| note | 72284558-24ea-532d-badf-a772a7d8923e | CATEGORY - IP
| note | 24d7e1d6-d219-5828-83aa-e24a1d319198 | – – – – – – – – – – – – – – – – –
| note | da042b9b-494b-52a5-9d32-3de550e8c404 | RESPONSIBILITY - SE/PE/SPE
| note | b26ddc75-2289-5422-9194-fc7b3668c983 | – – – – – – – – – – – – – – – – –
| note | aea0b6fd-c600-51c5-9aa4-33912d48ee73 | VERIFYING DOCUMENTS - This ITP
| textbox | cf9b526e-dd03-5bcc-a031-250eacfb2c22 | Date Completed:
| checkpoint |  | 5.5 - Non-conforming Coatings
| note | 292810ec-de8d-5c0f-8113-0287a4adce86 | REFERENCE - 685.14 686.17
| note | 8c258926-d21a-59fe-8334-23db89b7f76d | – – – – – – – – – – – – – – – – –
| note | 97f4fc44-1a16-54f6-b981-7fa6f8d6bcf5 | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
| note | 9cdffbac-9a48-5319-b8ab-cc81382dda8b | – – – – – – – – – – – – – – – – –
| note | 392e5948-9fcf-5780-87dd-85d7adcea221 | METHOD - Visual
| note | cf7a6e5f-e763-5dae-8bf9-adc507f0c184 | – – – – – – – – – – – – – – – – –
| note | c26cac94-9499-5a59-95e8-2194b1ac317c | FREQUENCY - Where required
| note | cac0283b-2952-52b9-8c44-84968d6ebc8d | – – – – – – – – – – – – – – – – –
| note | 147c73df-f9d0-52c5-90ec-e25b94b9ead4 | CATEGORY - IP
| note | ed365efc-fd58-5a7f-9dd7-be313ef85d22 | – – – – – – – – – – – – – – – – –
| note | cfbb5cf7-d84a-5581-807d-00bdf8d3d73c | RESPONSIBILITY - SE/PE/SPE
| note | af796b06-f94a-5f5e-881e-9773a3ea49d9 | – – – – – – – – – – – – – – – – –
| note | fb89a66a-cfc3-5612-b1a9-d2c0c943982a | VERIFYING DOCUMENTS - This ITP
| textbox | d443229f-9198-515a-940e-8bf7abd8b1c8 | Date Completed:
| checkpoint |  | 5.6 - Coating Application Guarantee
| note | 3fd28336-687d-525e-b89b-8c0084685835 | REFERENCE - 685.06 (b) 686.05 (a)
| note | 2e76c2d2-6c96-5f70-b873-cc892cd31a2a | – – – – – – – – – – – – – – – – –
| note | 99aa702c-8e82-50c3-83c6-6a72baae177e | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
| note | c1717734-9627-5c68-ae23-194d8777d2ce | Attach: Coating Application Guarantee
| note | 59c15c99-a63e-5e6d-8b29-3bf2057ef2e7 | – – – – – – – – – – – – – – – – –
| note | 8d405379-45b3-522c-a988-da930cd851f2 | METHOD - Document Review
| note | 653413ec-ba74-5f39-bd5f-abe681dce39b | – – – – – – – – – – – – – – – – –
| note | 6f062680-4bea-5f45-88a3-bbbe4c54ec30 | FREQUENCY - At completion of Works
| note | a55aef3c-ed9c-597d-9cc8-8653a9f8fbaf | – – – – – – – – – – – – – – – – –
| note | 4057026c-e20d-5a94-b0db-eebceb7508ec | CATEGORY - SP
| note | 766bb97b-7570-5f14-bd33-744d460bc04e | – – – – – – – – – – – – – – – – –
| note | 58835576-e9cd-5089-ba76-fe6da50d1856 | RESPONSIBILITY - SE/PE/SPE
| note | 05494828-4ce2-54d1-ae79-a866634ddc80 | – – – – – – – – – – – – – – – – –
| note | 909bc57f-ce64-515f-932f-ff5e26064ada | VERIFYING DOCUMENTS - This ITP
| textbox | 9e6b9c78-b0b6-5dac-b90e-3c7362e2b88c | Date Completed:
| checkpoint |  | 5.7 - Repair to Damaged Coating
| note | 9b232167-5378-5ec1-bbf8-9839afa73d36 | REFERENCE - 686.17
| note | 042f5cee-a777-5193-b0e4-1c65aed2077b | – – – – – – – – – – – – – – – – –
| note | 4ca7ae6a-272d-5ce5-b190-b706cc73bf20 | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
| note | 64276e75-e898-5a81-971a-71099b273192 | – – – – – – – – – – – – – – – – –
| note | ac883adf-6f7a-5fba-ae83-ca0146f75d82 | METHOD - Visual
| note | fc5446a9-1d55-5c61-8a9e-2c3ad41ebd5d | – – – – – – – – – – – – – – – – –
| note | c3fd73d6-694a-5d17-9e62-da8ad93646b9 | FREQUENCY - Where required
| note | 6de6e7a0-8d21-55ef-8e1d-6663e7a60545 | – – – – – – – – – – – – – – – – –
| note | c73a1e0e-e9c9-5e0b-9655-97f8203f6366 | CATEGORY - IP
| note | 160aa69c-6c52-599c-910e-1022ddbbd214 | – – – – – – – – – – – – – – – – –
| note | 046ad349-63e5-5de4-b537-a175c03e36c5 | RESPONSIBILITY - SE/PE/SPE
| note | 0fe78963-b9df-5bd1-8630-ee7898c40ff9 | – – – – – – – – – – – – – – – – –
| note | 1ce66f3c-da67-5309-9cb3-9c5a694d5388 | VERIFYING DOCUMENTS - This ITP
| textbox | d451a6db-d19b-5c72-b867-d0432b816e8d | Date Completed:
| checkpoint |  | 5.8 - Non-conformance Report (NCR) Closure
| note | 05a9b8e8-b6fe-5134-8867-8a3b304da58c | REFERENCE - MRPA Quality Management Plan
| note | 369ba62b-1b4d-5c87-ba57-c1a91bad4c54 | – – – – – – – – – – – – – – – – –
| note | 7a1a9ce8-7053-5f44-8ab7-5d8ba530ab83 | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | cad8324c-e13a-55d8-864e-41ccbfa3c65c | – – – – – – – – – – – – – – – – –
| note | bb187ad2-6f49-5334-8180-8c14731a141b | METHOD - Document Review
| note | aec39d4a-e0a0-57fd-bd80-c28cb6424dd8 | – – – – – – – – – – – – – – – – –
| note | 27a388e0-728c-5a0b-919e-65a917a8ae7c | FREQUENCY - Once, prior to closure of this lot / element / Work area
| note | 644174c1-51b7-5435-9738-2497a4be07d1 | – – – – – – – – – – – – – – – – –
| note | 0442c6a4-2eb8-526a-be36-274a6d139ffa | CATEGORY - HP*
| note | f2fc8ad2-bc39-585c-9d13-b81badf8b530 | – – – – – – – – – – – – – – – – –
| note | af9c1b03-994b-5d4f-a802-42956e33b8dd | RESPONSIBILITY - SE/PE/SPE
| note | c02e42e7-8f99-564a-ae49-ab56c41d1e45 | – – – – – – – – – – – – – – – – –
| note | b72ab6c6-8946-5dfa-a9d7-5e5c9fdbde23 | VERIFYING DOCUMENTS - This ITP
| textbox | 6105ba2a-986d-5ed1-a1ab-d62fb09b27f0 | Date Completed:
| checkpoint |  | Final Inspection
| note | 1dd11581-0ec0-5285-9200-26ed461e6b56 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 3fd055a9-513a-5f68-b8a4-281898179bea | Name:
| textbox | ffb92dd2-2974-5729-9a80-41d92f10fdb5 | Position:
| date | af70ef70-b9b2-5fd4-9104-da38c7c764a6 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Pump Station (Supply and Install) Rev 1 | itp | ITP-CIV-Pump Station (Supply and Install) | 389776cd-c43c-4d77-8c8d-a49ed9d0593c
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | f6820a04-6bab-5f5a-a330-23c43afdae50 | Document Title: ITP-CIV-Pump Station (Supply and Install)
| note | 0823a1e3-75f3-5a85-9108-13d975020af6 | ITP Description: Pump Station (Supply and Install)
| note | 806e45f1-8d17-56b5-9da6-2c4147416ee7 | Document Number (in Teambinder): N/A
| note | 16ee3bb3-6dfa-5b0e-95d1-65fd13403b5c | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 7f0091a1-ebe7-5821-9b38-08c3388832d2 | Revision Number: 1
| note | 8431639e-efc7-5ef1-a556-ec0174a549f7 | Revision Date: 16/01/2023
| note | 723c2b78-f3bc-592c-a915-a8909a09ce75 | ITP created by: Paolo Oliva
| note | 5bf07130-cbf3-53fb-aa87-844ea2b5ad33 | ITP approved for use by: Pradeep Talasila
| note | a6bca739-9a8f-58d4-b1d4-993fc2024d20 | 1.1 Non Dependent
| note | 5594f3c0-18d4-58bb-aeed-31ee9782d21b | Reference: VicRoads Section ### Month Year
| note | ae40c0ae-60a2-53d0-80c2-154f52bad247 | 1.2 Non Dependent
| note | 58608008-8cce-5bdc-951e-bed29786dbf1 | Reference: VicRoads Section ### Month Year
| note | 1b5536f5-d53c-5270-9bd8-e28f353993f0 | 1.3 Non Dependent
| note | eb0b54fe-9233-58e4-8417-939783ad82d3 | Reference: VicRoads Section ### Month Year
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 2.1 Drawings approved
| note | b7140d24-b8d3-5f12-8406-e2786e38b81e | REFERENCE: IFC Drawings
| note | a11218b2-bc23-5f2d-9546-1a0883921dc9 | ACCEPTANCE CRITERIA: Signed drawings for construction
| note | 72115e1c-d45a-5f56-8fbc-302c8be17476 | METHOD: Visual
| note | 19e98f74-685d-5b34-a9c8-2058d43233d3 | FREQUENCY: N/A
| note | e588fd75-cc39-5474-b5f5-15e57b1d05af | CATEGORY: IP
| note | a913e548-e32e-55d0-9fc4-e7baed850bcd | RESPONSIBILITY: SE/PE/SPE
| note | 39a3ac1c-4784-50bb-8783-2ea0cf6fa058 | VERIFYING DOCUMENTS: Signed drawings for construction
| textbox | a963f568-0d65-56da-aad6-6ab2cfa3b156 | Date Completed:
| checkpoint |  | 2.2 Penetration Drawings Checked
| note | 5dde2e4f-02f2-5c1c-a066-aeb8b120f88c | REFERENCE: Shop Drawings
| note | 60b5b544-5243-5381-aa72-779b0cbb954b | ACCEPTANCE CRITERIA: Authorisation by Aquatec Engineer
| note | d9776449-ecba-5b2c-88df-355e9f2ba4c4 | METHOD: Dimension Check
| note | ae2fbba0-3557-5071-ab13-89f3a4714a68 | FREQUENCY: N/A
| note | 47e16374-cf68-5033-b7a5-36dec0593021 | CATEGORY: IP
| note | 062fde37-0988-58f7-a114-f8a5c06aaa5e | RESPONSIBILITY: SE/PE/SPE
| note | 4cde6439-6911-5ab9-af5e-f805209be305 | VERIFYING DOCUMENTS: Authorisation by Aquatec Engineer
| textbox | 22e8b4e4-bc5d-5ed2-b50e-e82081001d1c | Date Completed:
| checkpoint |  | 2.3 Craning and excavation details created
| note | 326a989f-b3d7-5050-a589-2a8bb9da9604 | REFERENCE: Lift Plans
| note | 8c477dcc-a018-5e03-9391-362e517ac32a | ACCEPTANCE CRITERIA: Craning and excavation document # issued to client for reference.
| note | aae0904a-3629-5284-bbf2-8da6a33a60ae | METHOD: Calculation Check
| note | 78e916ae-c559-5837-bc8b-cd29ec47010c | FREQUENCY: N/A
| note | e14feb37-2d86-58c6-b0fb-114f7729f546 | CATEGORY: IP
| note | 026d43a2-e653-5143-8bb7-53cca36ecacd | RESPONSIBILITY: SE/PE/SPE
| note | 6c212122-08fa-515d-888e-62c36b6b75d7 | VERIFYING DOCUMENTS: Manufacturer Component Specs
| textbox | f11ab3a2-962e-5988-a76e-90d149f86f47 | Date Completed:
| checkpoint |  | 2.4 Pre-Cast Concrete Product Control
| note | 1dd758c8-87a6-57f1-bbc2-c6ef96963180 | REFERENCE: Australian Standards
| note | a5f12565-2cd3-5616-ad81-6978fd8df83e | ACCEPTANCE CRITERIA: Concrete Test Report
| note | 980d6956-3ae7-5975-a703-3259d6637306 | METHOD: QA test by manufacturer
| note | 21ec074f-87c1-5256-b07a-fbceeb6c443e | FREQUENCY: During Manufacturer
| note | 26265ea0-87d8-5c22-91ae-b4d06d56c9d8 | CATEGORY: IP
| note | 10e62497-9339-58cd-b1d6-2ad3478f3e27 | RESPONSIBILITY: SE/PE/SPE
| note | ed41c3ae-d062-5c93-9ffa-53411ae43d24 | VERIFYING DOCUMENTS: Concrete Test Report
| textbox | 41545aa8-3750-523a-ade2-deb74a392137 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Check concrete components are correctly loaded on truck
| note | 31ad4dfc-0b04-5833-80e7-0f87cee43b8d | ACCEPTANCE CRITERIA: Approved by Project Manager or Engineer
| note | 3e30aaf5-b811-54f1-bef1-5de989689382 | METHOD: Visual
| note | 9059a625-6618-57d9-8137-13dd953e33c6 | FREQUENCY: Checked prior to dispatch
| note | 76cdc631-f5ef-5e3f-8eb3-39e3c8e6e950 | CATEGORY: IP
| note | 5b07d811-65a7-5254-80fa-c92ac1d78327 | RESPONSIBILITY: SE/PE/SPE
| note | a6a0bb45-b6fd-5601-9964-720411f0a502 | VERIFYING DOCUMENTS: Photos
| textbox | b8b3c0df-e4b4-5386-8729-598b3170c6e0 | Date Completed:
| checkpoint |  | 4.2 Installation of Concrete Pump Station Components
| note | 607b0742-2925-5d0e-a655-41b49277c5aa | REFERENCE: Approved Drawings
| note | 1e1f01d8-22f2-569e-b9ac-0b1819d1125a | ACCEPTANCE CRITERIA: Signed Civil Installation Site Record
| note | 621d5dc1-ef32-5f25-9244-45e2938a3832 | Relevant Photos
| note | 2c7eabfc-4c1b-53f7-946b-84c32d46984c | IFC Drawings marked up to 'AS CONSTRUCTED'
| note | 3c917d50-e50a-5937-8d27-b4bffa906a51 | METHOD: As per Civil Installation Site Record
| note | ff4337bc-9ea2-5c13-86f0-f7ffa4d87b60 | FREQUENCY: Continuosly during phase
| note | 6f261639-477c-5758-a1b4-96045566490e | CATEGORY: N/A
| note | 75820f1b-74d1-56a0-8125-e41333ec63f3 | RESPONSIBILITY: SE/PE/SPE
| note | b568e1d2-36a5-583f-ae75-533d1cbd3328 | VERIFYING DOCUMENTS: Civil Installation Site Record
| textbox | fd59b358-84bd-539b-93b9-614e6089e0e8 | Date Completed:
| checkpoint |  | 4.3 Installation of fixtures to pump station
| note | 17d3dc55-da7c-5775-b860-be109638235a | REFERENCE: Approved Drawings
| note | a828efef-b23a-5a48-8692-ce7607a151d5 | ACCEPTANCE CRITERIA: Signed Mechanical Fit Out Site Record
| note | a849d274-3220-50f2-bb76-1c7c701e7997 | METHOD: As per Mechanical Fit Out Site Record Document #
| note | 58ecb78a-2323-5ef8-9faf-2bd58bc1954a | FREQUENCY: Continuosly during phase
| note | f6727317-3296-5e23-9607-fc4685f8f143 | CATEGORY: N/A
| note | 1a12d74c-2040-5ac5-8dfb-43f513c97005 | RESPONSIBILITY: SE/PE/SPE
| note | 8b8be5ca-e10e-550a-be0d-21e68eb133ba | VERIFYING DOCUMENTS: Mechanical Fit Out Site Record Document #
| textbox | 981f4326-eb8c-536e-a306-13d411ff2d29 | Date Completed:
| checkpoint |  | 4.4 Fabrication of switchboard
| note | 99687ae1-9cab-5c3e-8a93-2938c788ce87 | REFERENCE: AS3000
| note | 1b480243-1b1d-5591-955e-8da77cedd525 | ACCEPTANCE CRITERIA: Signed FAT Sheet
| note | 3e257c6f-b294-5aa1-bb3d-8ce460ffd013 | METHOD: Review Manufacturers ITP
| note | f8c84eb3-b560-54ed-ad40-8c515a7ab78b | FREQUENCY: Continuosly during phase
| note | 5763c8d0-d896-55d4-99ba-ed0e77503a61 | CATEGORY: N/A
| note | 61bb399f-19a3-542b-a2c2-8ca4bc071801 | RESPONSIBILITY: SE/PE/SPE
| note | a86b1d9f-b0d0-5f73-b90f-b5f8ec302a8c | VERIFYING DOCUMENTS: AQT FAT Test Sheet - Switchboard
| textbox | aba22039-6513-56d9-a741-a7698a3ff774 | Date Completed:
| checkpoint |  | 4.5 Installation of Switchboard, Mains Cabling & Metering Application
| note | 01469ca8-e27b-549f-8094-30365882766a | REFERENCE: AS3001
| note | da64a43b-af4b-54e8-b3c5-42b05014d504 | ACCEPTANCE CRITERIA: Signed Eletrical Site Record
| note | b55915aa-bf79-56a5-8fcf-8767c373a647 | Relevant photos
| note | 5b5009e9-bd82-5eec-8bfc-d2bfc9087c45 | Certified Certificate of Electrical Safety
| note | 325cfd4e-a22e-56a3-8a62-16b4d4158e4a | IFC Drawings marked up as 'AS CONSTRUCTED'
| note | b9ed02eb-9bc5-5962-9efd-318e1b9aa369 | METHOD: As per Electrical Installation Site Record
| note | b42ea082-78a6-53f3-baaf-b3a43bf8d6a3 | FREQUENCY: Continuosly during phase
| note | fe358e87-3e24-5ff4-90fa-78d5e8070f01 | CATEGORY: N/A
| note | 280bea60-b468-554c-b409-12c027320bce | RESPONSIBILITY: SE/PE/SPE
| note | fa65f032-4210-5264-92b7-b9ff76f4151f | VERIFYING DOCUMENTS: Electrical Site Record, Certificate of Electrical Safety
| textbox | 851fefca-f7ce-545a-97a1-a1bd9d618fad | Date Completed:
| checkpoint |  | 4.6 Installation of pumps and other electrical equipment
| note | c756c394-33bc-5683-9208-4199e10c1794 | REFERENCE: AS3002
| note | 948e9c48-c60e-599e-9edc-b5caf607566e | ACCEPTANCE CRITERIA: Signed Eletrical Site Record
| note | 9cf48861-422a-57a7-b61f-70af283430a6 | Relevant photos
| note | cc14ce98-2a9c-5838-a997-eb1fcafdcd4a | IFC Drawings marked up as 'AS CONSTRUCTED'
| note | ae92e188-a3e0-5e8b-8dfe-aba20cacee7d | METHOD: As per Electrical Site Record
| note | 51c06114-e298-5c3b-ae03-03a1fa95faf5 | FREQUENCY: Continuosly during phase
| note | ea501776-d532-583f-8e3e-a4656730f95a | CATEGORY: N/A
| note | 135bd398-9289-51ec-b21a-ab19691fc2e3 | RESPONSIBILITY: SE/PE/SPE
| note | 550e5b99-3f7d-5a38-82a2-c218f6a64516 | VERIFYING DOCUMENTS: Electrical Site Record
| textbox | 96aff68e-d75f-57af-87f2-8024218efe60 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 Non-conformance Report (NCR) Closure
| note | cb2a9d0b-a521-5fee-a1e9-811e22e55a6a | REFERENCE: MRPA Quality Management Plan
| note | d37c0ea4-3a6f-550c-8995-37e60aa104e5 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 02387ab2-b19b-5a6b-bed7-f38e499810a0 | METHOD: Document Review
| note | 8bba1cca-6022-5b39-b667-bac66de605c4 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | e92ef016-47a1-5c55-a872-7f2ae6e0eba5 | CATEGORY: HP*
| note | 55179821-56bf-5c52-8db4-7e4bf0a8ed5d | RESPONSIBILITY: SE/PE/SPE
| note | 74fea9ff-3a33-5491-9282-bcec0077e559 | VERIFYING DOCUMENTS: This ITP
| textbox | 82993ece-9182-54c6-9789-1a616d77a9aa | Date Completed:
| checkpoint |  | 5.2 Commissioning of Pump Station
| note | ccaae162-d00b-5f51-ae43-948c146421ae | REFERENCE: Approved Drawings
| note | f901856b-4f34-5d44-852c-a7abe25a8648 | ACCEPTANCE CRITERIA: SAT Form Completed and Signed
| note | 6ee4c3be-8d8f-5fcf-aad1-d6af613c2f18 | METHOD: SAT Form Used
| note | b31aac6d-0d94-5b8c-bef8-ad7fbe3dcf9d | FREQUENCY: Continuosly during phase
| note | 69950f2c-d548-59e7-8758-bd5050451909 | CATEGORY: N/A
| note | ff330ee2-8894-5b87-b02e-d7ad22f1178b | RESPONSIBILITY: SE/PE/SPE
| note | 10370010-bb86-5066-9e72-4e2c6b4d72b2 | VERIFYING DOCUMENTS: SAT Form Used
| textbox | 8dbc9db1-339d-513f-a7a7-951825156a40 | Date Completed:
| checkpoint |  | 5.3 Sub-contractor ITP attached and Signed-off
| note | 28e3eaef-9e93-5ec3-a546-77c18a669648 | CATEGORY: HP*
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 7125935d-349d-5c7e-853f-a0f35aeeb3ed | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 9ff5d9cd-d631-54d3-934a-11010fb2c4b3 | Name:
| textbox | e7eeda7d-4542-5256-bd25-b6accec1097c | Position:
| textbox | 4420fd3c-acf5-5dc4-a556-b4732e440e0b | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Traffic Signals - Civils (Supply and Install) Rev 1 | itp | ITP-CIV-Traffic Signals - Civils (Supply and Install) Rev 1 | 40810908-b4b6-4c43-82b6-7fbe8e106ea1
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | a63e4238-3240-54b9-8991-6106bce9e7a2 | Document Title: ITP-CIV Traffic Signals - Civils (Supply and Install)
| note | 97ba0c9e-bd15-5ab6-8234-79a1a95750ae | ITP Description: Traffic Signals - Civils (Supply and Install)
| note | 030e5057-4d3b-5611-a25f-6da8b175ac48 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 5be41757-6953-5eb1-880a-4b4fffd0bf7d | Revision Number: 0
| note | 94a769e6-5d18-58ec-b37d-2d4c37502758 | Revision Date: 15/02/2022
| note | fc99bdf9-c97c-5b5a-82a0-4d5f1869c932 | ITP created by: Saaf El-Zubaidi
| note | 67e4d237-ca39-5507-a303-0ec823bb7764 | ITP approved for use by: Josie Pavlou
| note | f4052b83-c7dc-5bff-8e61-5230902bac47 | 1.1 VicRoads Section 730 October 2013
| note | b37d011b-c2c3-53dc-b470-8890c72d2997 | 1.2 AS3000
| section |  | Preliminaries
| checkpoint |  | 2.1 Vic Roads Site Plan
| note | 876ac8db-3187-5bc8-a9b0-5faedc68e3b5 | REFERENCE: Table 730.041
| note | ea103dc1-3e3e-51ad-bf65-8951344ad692 | ACCEPTANCE CRITERIA: Scope of works, equipment requirements and placement of equipment shall be as shown on the VicRoads Site Plan
| note | d6ae2f75-5d1a-5d83-bf70-0c87f7ec68e8 | METHOD: Review Document
| note | 871e9346-8fa1-5ba9-bc25-a4c24e1d2c65 | FREQUENCY: Prior to commencement
| note | 48f6d724-de6d-5d00-9940-6ab9b1aa9736 | CATEGORY: IP
| note | 4fbc3c7b-db4c-5555-bbe0-0f5d8decd1aa | RESPONSIBILITY: SE
| note | 706ae505-b104-5800-9899-2616e570886c | VERIFYING DOCUMENTS: Attach: VicRoads Site Plan
| textbox | 30df8244-1b99-5c3c-bcf1-888f3584a573 | Date Completed:
| checkpoint |  | 2.2 Subcontractor Prequalification
| note | eafd55fc-f657-5226-8364-0027d38ea959 | REFERENCE: Section 730.01 (c)
| note | 333a7b33-b15e-532e-ba58-d3928407aa1c | ACCEPTANCE CRITERIA: All works associated with the installation and commissioning or remodel of traffic signals shall be undertaken only by contractors that are pre-qualified at the STS level under the VicRoads contractor pre-qualification scheme.
| note | c31d9417-fe6a-5d3f-99ad-8ca4d9b4bb31 | METHOD: Review Document
| note | 4dcccf57-ac51-5ada-92a8-b542e193c13b | FREQUENCY: Prior to commencement
| note | 5fefbec1-6935-5a55-b016-22f9bcfcc67a | CATEGORY: IP
| note | 286f55e4-89a8-521c-890e-aa0c7a8e50f2 | RESPONSIBILITY: PE
| note | 3c9e8d27-cc4c-5207-bfa2-4a74a93b1b00 | VERIFYING DOCUMENTS: Attach Subcontractor Prequalification Certificate
| textbox | b14e1173-bd6b-5d5d-8917-b8c254875230 | Date Completed:
| checkpoint |  | 2.3 Material Fabrication and Supply - Traffic Signal Hardware
| note | b7d631da-0b00-56a2-b8d8-97a3058d9b7b | REFERENCE: Section 730.05
| note | 60e25555-3903-56fe-9362-bab494e0c5e5 | ACCEPTANCE CRITERIA: The fabrication and supply of all components for traffic signal works shall conform to all relevant VR Specs and Aus Standards.
| note | dacf4c11-d9fe-5c40-8d38-0410892312ea | To comply with: VR 'TCS' series specs, VR 'TC' series specs, AS1742, AS/NZS3000 and Victorian Service and Installation Rules.
| textbox | d2098e30-c043-5c9a-88ed-f38f4aa680fe | TB Material Approval No.
| note | f0186e9c-0c61-5224-94b4-469151bf7606 | METHOD: Review Document
| note | d0b47b3d-bd05-5d32-ba7a-18d0066a949b | FREQUENCY: Prior to commencement
| note | f5e75ded-bfc9-5d21-bc9d-37aed7429a6f | CATEGORY: IP
| note | c9574611-f324-5207-81d8-ebb75ae60b9d | RESPONSIBILITY: PE
| note | e4acf78d-db36-5124-8650-3336a85fcd25 | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificates
| textbox | 5f8b9ab4-9c8d-5d97-b7db-8cedb088930d | Date Completed:
| checkpoint |  | 2.4 Equipment to be supplied by VicRoads
| note | 6767c5a9-99ca-5e85-a75b-dc0c835a7cf7 | REFERENCE: Section 730.06
| note | 93d7d94e-829e-5fc8-8a03-b5a56cfb6374 | ACCEPTANCE CRITERIA: VicRoads will supply or arrange for the supply of the following items:
| note | 98b27417-4443-548f-a6ce-b43844563c46 | (a) the traffic signal controller and associated vehicle detector units
| note | e4750c23-43a4-5630-b491-f59cf68f8210 | (b) communication devices, such as Dial-IP modems
| note | cfc6b27d-f325-5d7d-9fd6-690e25e87d86 | (c) ‘DUSC’ units.
| note | 230191e7-bf99-5c0b-9212-7e717035c02e | Contractor to provide VR a list of materials at least 20no. working days before delivery is required.
| note | c6ad25a9-159a-5f0e-b09c-abdc0dad83fc | METHOD: Review
| note | 88f7682b-66c2-5fbb-bc61-e277690bb8c9 | FREQUENCY: Once
| note | d8ef2e98-f9ed-5639-a2dc-7e8ae7ca4eb1 | CATEGORY: IP
| note | c597c007-43af-5a6a-8e3f-2407f06e2e96 | RESPONSIBILITY: PE
| note | 005e527d-a3ad-57f9-b7b3-21b30fe6e3f4 | VERIFYING DOCUMENTS: This ITP
| textbox | 4ae26240-ff06-5709-b406-40e1faca4d61 | Date Completed:
| checkpoint |  | 2.5 Equipment to be supplied by the Contractor
| note | 59a5d703-de35-519d-b8b0-92606fc0abe4 | REFERENCE: Section 730.07
| note | dcf41f9e-1c9c-5837-be9f-49b565441c01 | ACCEPTANCE CRITERIA: Contractor shall be responsible for the supply of all equipment, items and peripherals required for the completion of the works.
| note | b28cf57a-3122-500c-b9ac-525220875a9f | Where applicable, all equipment proposed for use shall hold current VicRoads ‘Type Approval’ certification or Product Acceptance. Refer to Item 2.3.
| note | e25b2a7d-ff9a-567a-8a27-b977d6c2c497 | All equipment, materials and fittings supplied by the Contractor are to be new. Contractor to ensure equipment used is compactible with all equipment.
| textbox | 7b18dcac-c730-5a5d-be04-0fbe1f979106 | TB Material Approval No.
| note | 9b874384-7319-5337-874f-54507531a9e3 | METHOD: Review
| note | ef1e9500-5bba-5a46-9bca-9c4805805c8c | FREQUENCY: Once
| note | 7efd6287-df7b-530f-8c61-5a43296a1b24 | CATEGORY: IP
| note | 6da35ce4-25f1-5ab9-929a-de67a1cd90e8 | RESPONSIBILITY: PE
| note | 59d9c0f0-6914-5027-b48a-1af66bdbe1cd | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificates
| textbox | 1d0325dc-dd22-5248-884d-c37cc95cb871 | Date Completed:
| checkpoint |  | 2.6 Concrete Mix
| note | b5fed0f2-a076-55da-b226-a2f210e80b1f | REFERENCE: Section 730.12 a)
| note | 8e05f285-4309-5881-bc9c-13ba6abb7c61 | ACCEPTANCE CRITERIA: Concrete shall comply with AS1379.
| note | fb1944af-be94-53bc-bc4b-49e9df3e138b | Concrete grade to be as per relevant Vic Road Standard Drawings.
| textbox | 52c12714-6cc9-55c3-90bc-694426d4ee10 | TB Material Approval No.
| note | 7ba701fb-02f3-5ca5-8a91-b1cd27b4231f | METHOD: Review Document
| note | e562c6a3-d2c5-5474-9f57-65a4c3ef85c6 | FREQUENCY: Prior to commencement
| note | 6ba1a628-56c1-56dd-8d81-a60ffe4f7e5a | CATEGORY: IP
| note | 21d6662f-ee4a-5ca7-8262-60fee2f7e821 | RESPONSIBILITY: PE
| note | 1f0ad7c8-3e11-5859-8ab5-e7cae9c24276 | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificate
| textbox | feeb9475-2e44-528d-90f0-81aeaef09227 | Date Completed:
| checkpoint |  | 2.7 Material Fabrication and Supply - Electrical components
| note | 20234c3e-e50e-5d72-bf43-ba3d696df4bd | REFERENCE: Section 730.14
| note | 40ce8d94-83c9-5432-8861-a64addf79553 | ACCEPTANCE CRITERIA: All electrical works, conduits, fittings, materials and installations shall comply with the requirements of AS/NZS 3000 Wiring Rules for all traffic signal related works.
| textbox | 4f16a870-0454-5a69-9145-c1644e4d8fb3 | TB Material Approval No.
| note | 796dedab-4a8b-5239-974c-5620d266ff2b | METHOD: Review Document
| note | 660e693e-64a9-59bb-9ea5-44ec864b716a | FREQUENCY: Prior to commencement
| note | 03555e9a-3a4e-557d-97bd-71fe81afb528 | CATEGORY: IP
| note | 49567aa9-1a64-5038-8a72-9ee20f062bb6 | RESPONSIBILITY: PE
| note | ab95a447-cdd4-508a-964c-59ace3246282 | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificate
| textbox | f805d095-0982-5d8f-9f1b-ecfdc1d861e7 | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Pre-Installation Meeting
| note | 07ed778f-6fa3-5716-abdb-a10d99178fb9 | REFERENCE: Section 730.08 (b)
| note | f5bfd807-1aeb-5ed3-8f32-ee817c673851 | ACCEPTANCE CRITERIA: The Contractor shall mark the position of pedestals, poles, controller bases, pits and conduits in accordance with the drawings, in the presence of and with the approval of the Nominated Authority, Vic Roads, service authority and others as appropriate.
| note | 991f5ab7-b23e-54c6-b1ca-32af8ab86aa8 | On satisfactory completion of the pre-installation meeting, the Superintendent will issue to the Contractor a copy of the Pre-Installation Report.
| note | 72b2ce6c-4a46-511c-9c90-c512fc25996a | The Contractor shall not commence installation of the traffic signal pedestals, poles, controller bases or pits until the Pre-Installation Report has been approved.
| note | b887fb9c-1f98-5d4e-bbbb-14461c0f0804 | METHOD: Records
| note | 3edc6952-a7b7-567d-ab22-2cf6681de581 | FREQUENCY: Prior to commencement
| note | 7da70848-2c22-5554-91c4-67edb5c8d4eb | CATEGORY: HP*
| note | 9fd117ef-8d63-5f57-a146-bd6c26fe0eb1 | RESPONSIBILITY: PE, NA and VR Representative
| note | ee967cc5-f836-53ea-9db9-eba2ef69cc6c | VERIFYING DOCUMENTS: Sign ITP , Attach Pre-Installation Report
| textbox | a0119f90-ea99-5899-adca-46a84af739b6 | Date Completed:
| checkpoint |  | 3.2 Service Proving prior to commence of new works
| note | 855f9d39-a3bc-5bc5-881c-4cb1d3824a9c | REFERENCE: Section 730.09 (a)
| note | ed10ebd8-c163-5bd6-a8cc-b74d8b98f7d1 | ACCEPTANCE CRITERIA: The Contractor shall be responsible for locating and proving all underground and overhead services. Any consultation with, and authorisation required from, other authorities under relevant utility regulations and codes shall be the responsibility of the Contractor.
| note | 232a9df9-f230-5b41-9f95-de28176720f3 | METHOD: Review
| note | 7ebbe209-2dd4-5b3d-8ddb-5a38c7d0681f | FREQUENCY: Prior to commencement
| note | 388bdd27-e353-52fe-a8a9-31591b9f5ca1 | CATEGORY: IP
| note | 3a946fea-52ec-5328-b386-430e6e2b7209 | RESPONSIBILITY: SE
| note | 16c0c8be-cd7f-5510-935f-56a62b4ef837 | VERIFYING DOCUMENTS: This ITP
| textbox | c537575d-a5c4-5856-a195-80fb9ad85be3 | Date Completed:
| checkpoint |  | 3.3 Survey Set-Out
| note | b3bd81cd-9705-502f-9173-1f06c869cfc7 | REFERENCE: IFC Drawings
| note | ef153e4e-f642-5301-9e3f-f4ded110e88b | Works Agreement
| note | 578d625f-161c-5803-9876-a767afb09af6 | Section 730.11
| note | dbcd3501-463e-5ff9-9552-26ff21f8f5e4 | ACCEPTANCE CRITERIA: Survey to mark out works as per IFC Drawing.
| note | 367ffc11-6a4c-57d1-944c-fc825a1dcbce | As per Item 3.1 VR to inspect the set out of Pits and Conduits for Traffic Signals prior to commencement of works.
| note | 05353717-562f-52fe-8857-2c7d2a2b2333 | No part of the signal hardware is to be closer than 500 mm behind the face of the nearest kerb line, or closest vehicle path if no kerb is present.
| note | 3e93c520-1f6f-5ddb-81d1-6361e3095081 | The minimum clearance of 5.5 m shall be achieved between the lowest part of a lantern installed on an outreach and the roadway directly beneath it.
| note | d7a30519-c178-5369-97e7-153e92525c42 | METHOD: Visual
| note | 1ff91c55-c9b6-53dc-b45b-35f55fdcda83 | FREQUENCY: Each item
| note | 9c1d26b0-bc92-584e-9ac0-2951ca4d4745 | CATEGORY: HP
| note | 9aa0a9b0-aa41-58cf-a3e8-15385c2d1669 | RESPONSIBILITY: Surveyor, SE, VR
| note | 3469ac0d-f536-57db-825e-d1b6f26f4834 | VERIFYING DOCUMENTS: This ITP
| textbox | 795fb2d1-9e32-5145-b1b3-3f6c95e07f85 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Material Inspection
| note | 2f656b34-3e8e-5654-8bde-7dbe5369b55a | REFERENCE: Design Drawings
| note | 33236b50-963e-5e83-a068-73cb3c3559f4 | 730.05
| note | 1e1c8cf6-9019-5daa-96d9-582a909d5f37 | ACCEPTANCE CRITERIA: Supplied items are:
| note | 7244542a-8206-54a3-a84d-3d0e7167a7f9 | To correct spec, class, size and quantity
| note | 52659fea-d726-5bc4-ac75-e0dbc1285877 | Defect free, safely and securely stored
| note | aa6cc32e-b78a-5803-adab-b9fbc45a1b4d | METHOD: Records
| note | 090173a9-7a04-5caa-aa6d-7da837a96f50 | FREQUENCY: Per Delivery
| note | 617feb89-f060-54d2-8a62-f3ed68130ed6 | CATEGORY: IP
| note | d2f8a090-8b93-5fc3-9ba9-40f6fb1e9087 | RESPONSIBILITY: SE
| note | 6c607fcc-7a3f-54c8-b3ed-37e1f7b74428 | VERIFYING DOCUMENTS: This ITP
| textbox | 13421049-e898-5820-ae21-7509979e268d | Date Completed:
| section |  | Traffic Signal Civil Works
| checkpoint |  | 4.1 Conduit Installation
| note | 0d733472-be78-5ce4-878f-ac17d92dc190 | REFERENCE: Section 730.09
| note | e58ec839-8a4f-573c-a75f-f79b42d1ee0c | Specification 733
| note | 761b1c6e-2237-5c40-bde2-056122cd9eaf | ITP-CIV Conduit and Pit (Roads)
| note | 77c63ade-4bdd-576c-b005-7c82a2ea904c | ACCEPTANCE CRITERIA: All electrical conduit installation works for traffic signals must be carried out by, or under the direct supervision of, a VicRoads pre-qualified traffic signal Contractor and in accordance with the requirements of Energy Safe Victoria.
| note | 19171646-f8cd-5f14-a4f6-f48df9d7bb7c | All communication conduit installation works are to be carried out under the ‘on site’ supervision of a licensed cabler.
| note | c7acf078-a7bb-577f-9cf6-f2db185d2537 | METHOD: Review Document
| note | 0191d971-0ea6-5710-8788-331191f96064 | FREQUENCY: Prior to commencement
| note | f0143c34-1c17-57ce-af85-b0ff7b93d157 | CATEGORY: IP
| note | 72929a28-c24a-509d-ba50-fd52853381a1 | RESPONSIBILITY: SE
| note | acf0cb89-cc66-5876-8ccf-110612aedad8 | VERIFYING DOCUMENTS: Attach Subcontractor Prequal Documentation
| textbox | e52f19c4-6e07-5b1a-97e1-19fd10f2c3b5 | Date Completed:
| checkpoint |  | 4.2 Pit Installation
| note | 6f8a6e30-9c5e-5a83-8dd9-bffe0760fda7 | REFERENCE: Section 730.09
| note | e34cec2d-1df5-55cb-be20-c16e00f33c25 | Specification 733
| note | 3d472c45-5943-5f9e-a678-28f1521ae6b7 | ITP-CIV Conduit and Pit (Roads)
| note | e40fa538-cd57-57ee-80ab-618d5e1f65f2 | ACCEPTANCE CRITERIA: All cable pit installation works for traffic signals must be carried out by, or under the direct supervision of a VicRoads pre-qualified traffic signal Contractor and in accordance with the requirements of Energy Safe Victoria.
| note | e169251b-fa81-53e7-9f03-be96dde036c5 | METHOD: Visual
| note | 781b963e-23f3-5166-a015-54b7fbdcf2c7 | FREQUENCY: Prior to commencement
| note | b37225b5-a60b-5dc1-b508-fb8d46928052 | CATEGORY: IP
| note | d0ec83df-952d-5b16-9fac-e319d0a42e0c | RESPONSIBILITY: SE
| note | c6a00f92-00e7-559d-b0d4-acebc84e0cc2 | VERIFYING DOCUMENTS: Attach Subcontractor Prequal Documentation
| textbox | 0fe2e72c-6729-5944-92c4-7fe6fb11cee7 | Date Completed:
| checkpoint |  | 4.3 Foundations
| note | cbdb0877-eb56-5888-9a44-62e8fc747e3b | REFERENCE: Section 730.11
| note | 3a485d6c-2475-542e-82d5-93741e4837c5 | Design Drawings
| note | ab42ff59-56c9-5146-8a25-623a2f6bf612 | ACCEPTANCE CRITERIA: Foundations shall be constructed in accordance with the drawings and as approved at the Pre-Installation Meeting.
| note | 4387e8c9-2a55-581a-a12a-ad6c62121ed3 | Foundations and footings shall be as specified in the VicRoads Standard Drawings for the specific item of equipment they are to support, as listed in Table 730.111. The standard foundation for an MA, JUMA and JUP shall be a bored pile.
| note | 5aa588e9-ddb8-506a-babd-3f6076a40e1e | METHOD: Visual
| note | fd184950-e054-53eb-9f8d-045ef7838584 | FREQUENCY: Prior to commencement
| note | 017962f8-96e5-5d61-af6c-ebc2f50840ca | CATEGORY: IP
| note | 59ad29f6-068d-5162-915e-eebbe8e1b823 | RESPONSIBILITY: SE
| note | 050c088e-5625-5dc7-bbf3-1b908d747d52 | VERIFYING DOCUMENTS: This ITP
| textbox | ebfb639a-4fa7-5398-899b-ba0e458362e1 | Date Completed:
| checkpoint |  | 4.4 Inspection of civil works
| note | 834de10b-73ff-5e5d-8cf6-f0ea1f173a6c | REFERENCE: Section 730.11
| note | 76855ee7-a316-5624-af63-a1d1f7442cf6 | ACCEPTANCE CRITERIA: All conduit, pit and foundation works shall be inspected by the Nominated Authority and Vic Roads prior to the Contractor covering the works.
| note | a612783e-8033-5dc5-b83f-f7c9fb497938 | METHOD: Visual
| note | 67e1569a-633b-5051-b4ee-5e1dcf0e7f32 | FREQUENCY: Per lot
| note | eb8be3e8-1bc5-57a4-aa22-20d4c655757f | CATEGORY: HP*
| note | 62ad5743-b52b-5591-a93c-a39507f2af04 | RESPONSIBILITY: SE, NA and Vic Roads Representative
| note | b9cf64c2-2359-5070-a03d-4d80d0d0989a | VERIFYING DOCUMENTS: This ITP
| textbox | 4e7df770-f6fc-595c-9af7-57387eeafad9 | Date Completed:
| checkpoint |  | 4.5 Concrete Placement
| note | 80e1b811-e18b-5b2f-b228-6b26c7876708 | REFERENCE: Section 730.12 b)
| note | a1072207-3152-57eb-868b-38340834481a | AS1012
| note | d2dd0675-eab8-5eb2-8e56-3f183a96de80 | AS1379
| note | b8fa1402-ce55-5163-90ba-5294e66ad617 | ITP-CIV Bored Pile
| note | 07746593-6fd0-52ca-8a62-de48465f93e2 | ACCEPTANCE CRITERIA: Where concrete is placed in a bore hole, it shall be compacted with immersion type, high frequency vibrators.
| note | 1bb5818f-7426-56cc-982d-5be3fd4f237d | Concrete shall be placed through a tremie tube, shall not be dropped from a height greater than 2 m and shall be guided away from reinforcement.
| note | 61e687c6-052c-5529-9e7d-3fdc1527114c | METHOD: Visual
| note | fe670a3f-4344-5e20-a62c-40f4fc5e294c | FREQUENCY: Per lot
| note | 1f20e258-6311-58b1-869a-f02094751b75 | CATEGORY: IP
| note | 56281c41-2510-5819-9c97-867f818e4ab7 | RESPONSIBILITY: SE
| note | e47f8af2-70ab-5d1c-b4b8-719f9eef7030 | VERIFYING DOCUMENTS: Attach Concrete Dockets , Attach Bored Pile ITP
| textbox | 4dc1cf71-c3ba-553c-b76c-7eb1b3e6f497 | Date Completed:
| checkpoint |  | 4.6 Concrete Testing
| note | ee3254ac-6563-5e47-967f-7536df166bfa | REFERENCE: Section 730.12 c) & d)
| note | e8a2c252-cd7e-5514-872a-5907fedc9fe3 | ACCEPTANCE CRITERIA: All grade 32MPa concrete shall be sampled and tested in accordance with AS 1012 and AS 1379.
| note | bf8baaa2-dac7-539f-b7d4-fead1d1ab6ff | 1no. cylinder to be tested at 7 day and 2no. Clynders to be tested at 28 days.
| note | 37a7b4d5-7c7b-5052-a2fc-1d4ae4fe4956 | METHOD: Review Document
| note | 25522ac5-c73a-5ff6-8cbc-eb5b3ad658bc | FREQUENCY: Per lot
| note | d748815e-eb3e-5c09-b23a-11f6f3faf14f | CATEGORY: IP
| note | 40481338-e80a-564c-831c-489b7f69ef9e | RESPONSIBILITY: SE
| note | 04776dba-e5d5-5a36-ae88-44cdc4fa3ef8 | VERIFYING DOCUMENTS: Attach Concrete Test Report
| textbox | 6c44c6a7-2516-5cbe-84f1-16ca15e6a662 | Date Completed:
| section |  | Traffic Signal Hardware
| checkpoint |  | 5.1 Standing of Pedestals and Poles
| note | a3c598e2-849f-50cd-a2f3-a37f2c87a00a | REFERENCE: Section 730.13 a)
| note | 30e40c6e-e148-5175-ac8a-7a4923ce5fcb | SD TC-1201
| note | 75ff1565-83fa-57ac-bee4-c199becad732 | Design Drawings
| note | 94425c70-331b-5225-b776-29774dad38ab | ACCEPTANCE CRITERIA: Pedestals and poles shall be installed in accordance with the design drawings and relevant specifications.
| note | a03b1d14-77b2-50c6-a965-51f006e2502a | Pedestals shall not be stood within 48 hours of casting of foundations.
| note | 3302f5fa-49ef-5825-b1ca-932da92cfeee | Poles shall not be stood within 7 days of casting of foundation.
| note | 84ae435a-d1d6-51d9-bc6c-e70454cf4c05 | METHOD: Visual
| note | f2837d4b-0602-5cb1-9d04-bc3cbc934355 | FREQUENCY: Per item
| note | e92bded2-57c4-5b69-9494-cb95d211c792 | CATEGORY: IP
| note | 535177f2-f1cb-5812-9fdd-5851f85cdf60 | RESPONSIBILITY: SE/PE
| note | d7e5935d-5b5c-519b-a6eb-24e2b860f5ec | VERIFYING DOCUMENTS: Sign ITP
| textbox | b36fa9cf-1158-5c6d-b6b6-d5dab8c7cbf6 | Date Completed:
| checkpoint |  | 5.2 Lantern Requirements
| note | cee93a44-9c3b-5194-bff6-5393f0feb385 | REFERENCE: Section 730.13 b)
| note | cdbe2e4d-d165-5d3a-8ea4-3d971c0bb2c2 | ACCEPTANCE CRITERIA: All traffic signal lanterns shall be LED type, excluding minor remodels where QH lanterns are permitted.
| note | a122d4fe-cae2-52ab-9edd-3d9291dbac07 | A mix of LED and QH lanterns is not permitted.
| note | 57ba6118-109c-53ea-9c45-3213741620da | METHOD: Visual
| note | c07613c3-74a2-58ae-92d5-f17d6badeadb | FREQUENCY: Per item
| note | df5ca8db-85c2-5187-8906-113011501a1f | CATEGORY: IP
| note | 428eb7c5-2e54-5781-858b-decaefaecaeb | RESPONSIBILITY: SE/PE
| note | 1d56019e-9363-5f77-844a-7f9566ddde6a | VERIFYING DOCUMENTS: Sign ITP
| textbox | 94a29716-0538-5b05-a4ad-6be72f070037 | Date Completed:
| checkpoint |  | 5.3 Lantern Installation - Mounting
| note | a6bab189-3e52-5749-bb3d-32dd99082655 | REFERENCE: Section 730.13 c)
| note | a648e330-9ea3-5cef-a8c7-fc42b96c6cab | SD TC-1115
| note | 2909f548-a24a-5ab7-9333-27fb7b0b0f01 | ACCEPTANCE CRITERIA: Lanterns shall be mounted vertically using straps securely fixed to mounting brackets.
| note | ad42225d-f63f-5790-931f-32fafc8e8b29 | Upper mounting brackets shall be orientated in accordance with TC-1115.
| note | 854aeec6-b0d6-52c5-83fd-ff0835cc291d | METHOD: Visual
| note | 40c88712-aee2-5ca3-afb1-a9b4d61a2068 | FREQUENCY: Per item
| note | 4fb97f62-0386-5c70-a90b-61959d7189e8 | CATEGORY: IP
| note | 27695b5a-a52a-5527-b410-b6b5b70ef7fa | RESPONSIBILITY: SE/Site Supervisor
| note | 4a6670bb-6528-56c2-a54e-51bdc7b6790a | VERIFYING DOCUMENTS: Sign ITP
| textbox | 084f9585-25cd-5486-83c9-8991b523b3e6 | Date Completed:
| checkpoint |  | 5.4 Lantern Installation - Cabling
| note | ea823afb-cfc2-5fb1-94f5-8f114c90fbd3 | REFERENCE: Section 730.13 c) (vi, vii, viii and ix)
| note | 8f9e9323-17a8-59b2-a0e9-efb9160aa65a | SD TC-1119
| note | 0e68ed33-abf7-50fb-9836-7c545aa51ec1 | ACCEPTANCE CRITERIA: External cables and conduits shall be fixed to pedestals, poles or supports with the desired length as per the relevant standards.
| note | fcb9123f-303a-525e-be2b-33695e05d7a0 | Cable connections to lanterns shall be made with continuous lengths of cable; no joins shall be allowed.
| note | 1f1ac0eb-a1d2-570f-9de8-0d0b1fa13886 | METHOD: Visual
| note | 702e6d9a-6a47-519d-afa9-980735412c1c | FREQUENCY: Per item
| note | 3e3eb8e6-37db-5c35-88ce-f7380bebf1d2 | CATEGORY: IP
| note | 7d059a6b-50fd-5869-b540-e638ea227e1b | RESPONSIBILITY: SE/Site Supervisor
| note | 96da18d0-8f26-5fb7-8cd9-432402ba25d8 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 6aa03ab8-6cb3-59fc-afd2-693fdf0abbcf | Date Completed:
| checkpoint |  | 5.5 Lantern Installation - Mounting Height and Alignment
| note | f41edc43-ad9b-5a88-a8d0-de81e0a070b4 | REFERENCE: Section 730.13 (d)&(e)
| note | 9416dbe4-c933-5141-bbaf-47176c6d0e12 | SD TC-1112
| note | 64822845-dcab-5140-822c-4b5c38244789 | SD TC-1116
| note | c4c68566-0c47-5a7f-9cf7-8ed8d5ac5cff | ACCEPTANCE CRITERIA: Mounting heights for 2A and 2B pedestals are to be as per SD TC-1116.
| note | 02ca4ac2-aebc-528f-93db-c1fbba37280b | Lanterns on the outreach of a MA or JUMA shall be mounted in accordance with SD TC-1112.
| note | dd9dfa41-21ce-52c0-acce-1766d34d84cc | Vehicle lanterns shall be aligned to provide optimum visibility for approaching traffic, and aimed at a distance before the stop line for the following:
| note | bf902b3b-05c0-5f7f-a72c-3f3e923903e1 | Primary - 240m
| note | b50f02f6-9097-5ac8-88b5-6dfec97e654f | Secondary - 150m
| note | 5dd37d49-958d-5996-bbbe-ca8f62209ca9 | Tertiary - 5m
| note | 3050460b-d2f9-5315-abfb-3cc0e62b1d29 | METHOD: Visual
| note | 4f5091da-2e88-5279-9179-3e911af2aab3 | FREQUENCY: Per item
| note | 67aeab50-5157-5990-bdce-d6f260634b92 | CATEGORY: IP
| note | da98063b-b0f2-5f67-add5-1424c99c7ab1 | RESPONSIBILITY: SE/Site Supervisor
| note | fd50d136-91d8-5c96-9ac5-0d4abdafb58c | VERIFYING DOCUMENTS: Sign ITP
| textbox | 54d9c19d-c3e6-5c54-8a1f-01c001429caf | Date Completed:
| checkpoint |  | 5.6 Lantern Installation - Target Boards and Visors
| note | b56471a7-326c-5ee2-a438-abb523559ca2 | REFERENCE: Section 730.131 (f)
| note | ef77055b-e8ce-59ba-b0dc-889c34753bd4 | SD TC-1119
| note | a6e4d93e-0fc4-5551-a964-3bcd5dc72e83 | SD TC-1127
| note | a8625877-6730-58c6-8556-49e32a6d6e1b | ACCEPTANCE CRITERIA: All target boards shall be metal and fitted in accordance with SD TC-1119.
| note | ffd35a1b-5faa-5e00-8b08-b48a0faa8ef0 | Visors for LED lanterns shall be fitted as per the below and Table 730.132:
| note | f7b6a9dc-7204-5904-91a0-10b63cb61469 | MA/JUMA - Visor Type 1 - Both Sides Cutaway
| note | f2eba1ac-8020-5c97-a993-1a994de94298 | L/H Primary - Visor Type 1 - Both Sides Cutaway
| note | c1171a48-a9c0-5a8a-9c54-7ec08c7a87d5 | R/H Primary - Visor Type 1 - Both Sides Cutaway
| note | d3dab149-109b-581f-9081-04f658f0cf66 | Secondary/Tertiary - Visor Type 3 Short
| note | 54739057-5ae9-5903-ae31-03deb087c43e | Pedestrian/Bicycle - Visor Type 4
| note | 91d7e95d-4770-5c5a-bd7d-edc41c7e27f7 | METHOD: Visual
| note | 81f6c023-48c3-5043-bc88-e9f77fc10c26 | FREQUENCY: Per item
| note | 5a6f4608-5a18-5e26-a44c-d5b277b2d53d | CATEGORY: IP
| note | 3947ca95-2854-5b10-9794-916995fcba35 | RESPONSIBILITY: SE/Site Supervisor
| note | aa9baca1-de3d-5f4a-ba40-5a8c0b5b89ff | VERIFYING DOCUMENTS: Sign ITP
| textbox | 4904b9be-0e87-5c6a-a651-de82af2f89de | Date Completed:
| checkpoint |  | 5.7 Installation of Pedestrian Push Buttons and Audio Tactile Devices
| note | 4b871531-f689-5bef-a72d-89c2f7c3b8c0 | REFERENCE: Section 730.131 (g), (h)
| note | dca2f7a4-ef1e-5f41-93c5-926481b9eae2 | SD TC-1116
| note | aa6f6eb2-69b5-588c-a2ca-7436d07b16f6 | ACCEPTANCE CRITERIA: Pedestrian push button assemblies shall be mounted clear of any access openings and such that the centre of the button is 1.0 m above FSL, as shown on SD TC-1116.
| note | 5116b7bd-7f23-54c6-9413-84615013ca83 | The face of the button shall be at right angles to the direction of the associated walk lines. the tactile arrow indicator shall be orientated to indicate the walk direction.
| note | e13ea1fb-8190-5616-b08e-269e96e8a75e | If required, audio tactile units of the type nominated shall be mounted as shown on SD TC-1116.
| note | f90f5bc0-ac7e-5a06-a43d-8bc1f7078e8e | METHOD: Visual
| note | a1c3135d-bd2b-5ad7-88c5-117adbb53b86 | FREQUENCY: Per item
| note | cffd1bda-a527-5ea4-834f-08a9d128caac | CATEGORY: IP
| note | c7ff9120-011e-59bf-9380-c10988103d7a | RESPONSIBILITY: SE/Site Supervisor
| note | deb4af35-93c0-52a6-af61-7179b956763f | VERIFYING DOCUMENTS: Sign ITP
| textbox | 35041b81-230a-50a5-8f8f-9d0660f44480 | Date Completed:
| checkpoint |  | 5.8 Non-Commissioned Lanterns
| note | 00cdfd89-0551-5edb-8eb8-c4dbdaec3ccb | REFERENCE: Section 730.131 (l)
| note | 8e35d43f-8dbc-5c33-a8a7-bc43f8de1c86 | SD TC 1131
| note | e52bede4-35f2-5966-8670-48064f7e020f | ACCEPTANCE CRITERIA: The faces of all installed but not yet operating lanterns shall be covered, specifically 'NOT IN USE' signage on vehicle lanterns that have not been switched on.
| note | 6874d330-13ee-51f0-b197-b8c3c1da2215 | METHOD: Visual
| note | 7e29d447-eada-5feb-973e-3ce37feef8da | FREQUENCY: Per item
| note | d62d5b21-9d6e-5b25-ac58-b35646d07857 | CATEGORY: IP
| note | 48a795f2-fea1-547b-b29b-9c3270d9dfc5 | RESPONSIBILITY: SE/Site Supervisor
| note | 8e38f2cd-f05a-5642-8225-c8aeb33e227e | VERIFYING DOCUMENTS: Sign ITP
| textbox | e519279a-1805-55b6-b7e7-44072d256a41 | Date Completed:
| checkpoint |  | 5.9 Hardware Inspection
| note | 4733cee2-a384-5add-aedf-0bb37399a673 | REFERENCE: 730.131
| note | 697afa01-4e1c-5d02-b1cf-838cf0bd88f0 | ACCEPTANCE CRITERIA: All installed hardware shall be inspected prior to works proceeding by the Nominated Authority.
| note | 34a78e37-0786-53cb-b160-3df8d4c6356a | METHOD: Review
| note | e8b9c75a-67a7-571f-852b-2757ba70a15c | FREQUENCY: Per item
| note | 80e22fde-fa9e-571f-bc69-920f2ee283fa | CATEGORY: HP*
| note | e4ea1f01-eff7-5b46-b103-a4fb87346d47 | RESPONSIBILITY: SE & NA
| note | 7c3e5544-198b-59c3-befa-394e292f3693 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 032139d9-c205-5f30-8aed-c83206e5110e | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 2bcbb234-c746-50f5-8610-f3e9ae81811f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 894880b7-09d7-5a2b-aaa3-92f174d473b4 | Name:
| textbox | a41648d9-2f46-522b-a197-95434cee63ad | Position:
| textbox | 20e6fdf1-1bdf-548d-b20b-4b8dd087cca9 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1 | itp | ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1 | 4635327e-4378-4a15-a313-10ccb5d98df6
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | e71f872c-42f6-4315-bf43-a59c5e2efe53 | Document Title: ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling)
| note | 55a51843-4cf4-48d7-8d1f-30957bc8c66e | ITP Description: Footpaths & Shared User Paths - 2 (Concreting & Back-filling)
| note | 5bc962ac-9198-43b5-ac10-d77ff857a59a | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 213f91a8-a9f9-40cd-a90c-a4469c3ab2cd | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 904df985-89d9-4f99-bc6a-9a2ba3ef12f0 | Revision Number: 1
| note | 553ecfd4-52f5-49ea-bfc0-004329112e97 | Revision Date: 22/06/2020
| note | 40e21d9c-b909-4b91-98d7-3ead6557896d | ITP created by: Lachlan Macready
| note | 07ee7027-0659-45ed-a9f0-3a84944819da | ITP approved for use by: Mike Freeman
| note | 07e878ca-c294-411a-8b63-949f2e2ccb45 | 1.1 VicRoads Section 703 June 2018
| note | 2233c260-6c54-46c0-8364-5471dc738b22 | 1.2 VicRoads Section 610 November 2018
| note | 94367ae2-7731-4cbb-a21b-72da8a58825d | 1.3 VicRoads Section 714 April 2018
| note | 8d87672a-6d47-4180-a1cb-7dbc255111b1 | 1.4 AS1379-2007
| note | b262a28f-8a77-4f37-93a5-ff10377a003f | 1.5 AS3610-2018
| note | 168a7d46-7e60-47bd-b49e-16711cb0969d | 1.6 AS4671-2019
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Concrete Mix
| note | eed12136-4071-43c1-97fc-de474eab3987 | REFERENCE: IFC Drawings
| note | ba8e8aff-a7ab-4a38-837e-ddaddcb1153e | 703.05 (a)
| note | a9724505-858c-4c35-897a-74171562ef50 | 703.07
| note | 0ef98ff4-794d-4710-8deb-7c833e24eb17 | MRPA Quality Management Plan
| note | 6e1b59dd-a3bb-4c3e-81e4-07a30c57e6f6 | ---------------------------------
| note | c2f0cf2b-3f9a-42d9-bf4f-979d7ae91ea4 | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
| note | bd3f7e78-55c6-4f32-b52e-f7d9e7fd5c0a | Paving concrete mix conforms to AS1379.
| note | d14895ad-d615-445b-9a34-922d35554c89 | SUP concrete mix is registered with VicRoads.
| note | e7e3fbe6-78d2-49e0-a4cb-8370f072ad18 | No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
| textbox | 25c4eecd-dcd6-41a3-9984-a7989e1a2a22 | Enter: Teambinder Material Approval number
| note | 6430a9fc-48eb-4d58-bc7b-82a959784726 | ---------------------------------
| note | 9f99c46a-9398-40fd-af51-0bbe1ed22f08 | METHOD: Document Review
| note | 4a389d24-e3f3-4390-b457-9472fc4e2a8a | ---------------------------------
| note | ecfb8415-d1f6-4f3e-9367-565bfaed2308 | FREQUENCY: Once, for each mix design, prior to placement of concrete
| note | 233e294a-5d74-4ed2-b851-81142ed5e3ae | ---------------------------------
| note | d87045b5-8dd8-47e5-8744-62044f6acf6d | CATEGORY: HP
| note | f43c312b-ebbc-4161-9fd2-9df5106907e2 | ---------------------------------
| note | 5258b811-04e5-4d61-b3cb-f6fb9ee02a1b | RESPONSIBILITY: Nominated Authority
| note | ac77d9ae-0da3-41b8-b0a6-38ab3368fcd0 | ---------------------------------
| note | f7471dd0-3d4f-4c51-a751-3b8e56ce38c1 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 667e967d-5ecf-4a92-b45e-0577a0fc2eeb | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Reinforcement Certification (or ACRS Certification)
| note | 98562499-983b-45fd-9f66-c00c3bdbaaa9 | REFERENCE: 703.13
| note | 9c39bdba-942e-4342-af49-3c1ca99faa46 | MRPA Quality Management Plan
| note | 3c7c3087-9d1a-48c6-831d-37e9dfe73ab9 | ---------------------------------
| note | 5da98cf3-29aa-4dfc-a218-088faba99a25 | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
| note | 3761f9fb-e59c-4a4a-9b14-023d31f78d1d | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
| note | 7c5a204f-26ad-486d-9bfb-e5474b981b63 | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | 6b4c6ac9-ff43-4de9-887f-8d1d9b03d603 | Enter: Teambinder Material Approval number
| note | 2ae7c1d5-3168-47d8-9e0d-834b015038a7 | ---------------------------------
| note | 4c0ad25b-644c-42c6-b62c-8160d4b98b70 | METHOD: Document Review
| note | de0dd9ef-2a67-4617-a71e-60735efa3f17 | ---------------------------------
| note | d5e18b32-0a27-4d24-a337-6ee41d13db8b | FREQUENCY: Once for each supplier, prior to placement of order
| note | 84257bad-34b5-43d2-9bff-3d87e70ae5dc | ---------------------------------
| note | 53bc7105-57fe-4a2e-b49b-3cedf6feed06 | CATEGORY: IP
| note | 4e89890f-d4c9-40a9-ba22-995db2ff10fc | ---------------------------------
| note | 78b3c47d-826d-4a02-9980-9f29336fdd1e | RESPONSIBILITY: Nominated Authority
| note | 83bcc8e9-d052-472e-8a3d-3541ed001b68 | ---------------------------------
| note | 8f30a65c-5ef2-4fb6-b781-723d332c6481 | VERIFYING DOCUMENTS: This ITP
| textbox | 6ddfc44b-d165-4aba-9452-b1ffc6001fe8 | Date Completed:
| checkpoint |  | 2.3 Evaporative Retardant
| note | 7e4eac05-6ccf-4d24-aeb0-0a2505e1da19 | REFERENCE: 703.09
| note | 0edd46b1-9685-4b67-b278-1c66d2e13338 | 610.17 (f)
| note | 7d97429f-b5dc-4931-847c-a1bf96ff9162 | ---------------------------------
| note | fd543eba-e73a-41f1-9eeb-c31a5b32cd16 | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
| textbox | 27fa5683-3c34-4073-9f7e-fcc7520f85a8 | Enter: Teambinder Material Approval number
| note | d90848d8-6c6c-4fee-9fb7-aa0e50de3cda | ---------------------------------
| note | 02f501ae-db5f-4089-8827-db0c0daefd47 | METHOD: Document Review
| note | de915b78-1843-4033-83bc-a39df991da57 | ---------------------------------
| note | 9fef0073-70ba-4833-b631-058a1e72be8f | FREQUENCY: Once, for each product, prior to placement of concrete
| note | af16a79d-662c-47a0-834c-4e6146991f49 | ---------------------------------
| note | 997a7cb6-0d66-4c99-9e0b-3c30db3484eb | CATEGORY: WP
| note | b8ded91e-d66e-4240-832c-9bffa7b06083 | ---------------------------------
| note | 674577e4-ae65-4774-a8e9-1c8081898120 | RESPONSIBILITY: Nominated Authority
| note | aee89f52-e4be-405f-a680-4cb351ce879d | ---------------------------------
| note | 94bf6b8a-2773-487a-9135-474a1e3354d6 | VERIFYING DOCUMENTS: This ITP
| textbox | 7a7ee111-51af-4320-8c82-e4b2c1ab1532 | Date Completed:
| checkpoint |  | 2.4 Curing Compound
| note | 8c311983-fd06-4d26-b5e6-e2c2aa81b494 | REFERENCE: 703.10 (a)
| note | bf38ad26-ccd1-4bdf-ab16-beddc1a0c4c0 | 610.23 (d)
| note | 209e4d52-a41a-43e1-8320-26eb4349029b | ---------------------------------
| note | cf6f737b-5fd7-411c-b825-d8d2daa2eb27 | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| textbox | 088b4614-0aeb-4431-84d6-0717c166ea1a | Enter: Teambinder Material Approval number
| note | bd003248-94e1-4ce2-977d-2869ce38f2bb | ---------------------------------
| note | 792b7124-7316-4a4d-8c9d-fee2d48695d8 | METHOD: Document Review
| note | 785f59fd-90d8-4e7b-acd7-8167f02a6537 | ---------------------------------
| note | 36e94589-9d5a-42a7-960a-72c29b69208f | FREQUENCY: Once, for each product, prior to placement of concrete
| note | 41568339-4479-429d-8bb6-6cfee53243c8 | ---------------------------------
| note | bc3b7d2f-13e7-4d9a-9814-3ee5eeb4969a | CATEGORY: IP
| note | 17cd1623-d512-4bc6-9fcb-1214cf0e6d01 | ---------------------------------
| note | c27354cf-f07d-43a0-aa02-b2c2ef5abcfb | RESPONSIBILITY: Nominated Authority
| note | b172b885-be91-4382-b581-87687d365812 | ---------------------------------
| note | 08e469a8-651c-4489-b45c-f9df40c376c4 | VERIFYING DOCUMENTS: This ITP
| textbox | 294edcd0-54d2-4137-8a69-11c812df0450 | Date Completed:
| section |  | Pre-construction Activities
| checkpoint |  | 3.1 IFC Drawings
| note | 7c8d5d66-7327-46d6-93b4-8c10ec6ed52f | REFERENCE: MRPA Quality Management Plan
| note | b4d7feec-8921-4cf7-a99e-9bfe907f2e2b | ---------------------------------
| note | 134ce982-9b9b-4d9a-ba0c-b7cb072ac3da | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 33066f4a-c0da-427c-aac6-4865d1343b0e | ---------------------------------
| note | 5cab495a-b35e-4f8a-83ef-a51a2aed8f23 | METHOD: Document Review
| note | bbb24b57-3382-4961-ad80-b4485c0ed057 | ---------------------------------
| note | be09dcac-689b-41d2-b55d-d706107eea72 | FREQUENCY: Prior to starting Works and at regular intervals
| note | acaf62fd-7040-4233-b916-8d01edeef282 | ---------------------------------
| note | 56a3b33b-b9af-4cba-88ac-5efd1707acd1 | CATEGORY: HP*
| note | 751a8f4d-5c55-44ed-992b-1f0c2ead51fe | ---------------------------------
| note | 23ede68d-d2a5-4cb1-84e9-666e17d6ba4a | RESPONSIBILITY: All
| note | 98ef2bde-f849-4ec9-a699-89bc02630c03 | ---------------------------------
| note | 525759d6-1aa6-47a9-b48c-504002947367 | VERIFYING DOCUMENTS: This ITP
| textbox | 40fdcbf1-f24f-41eb-9f7d-807e0f45d520 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 4.1 Formwork Construction & Placement
| note | 408f780b-84a7-48e9-bc8e-041b2ab50fd7 | REFERENCE: IFC Drawings
| note | 6aa6da5a-1f39-4761-9728-427729ffc3a2 | 703.12
| note | 53f974fd-b30c-4d66-a02a-86556cf20ff3 | ---------------------------------
| note | 962857e4-50ec-4ece-9ff9-bd8247e9ec56 | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
| note | 9c23e6f8-9cfe-4cd0-97d3-eb89bf7c8bfc | Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
| note | 96db35d4-17ce-4763-8ff5-32e916aec90f | Joints in formwork shall be constructed such that loss of mortar is prevented.
| note | 0e32a58b-8518-499f-b511-0d6174f6e47b | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
| note | 013efbc8-7584-47a9-9e23-65c01a1fedfc | ---------------------------------
| note | c4bcfa7a-d416-4bad-ad6c-9a4a967d810e | METHOD: Visual Measure
| note | a1df013f-b89f-4c99-913e-78b9cf1dde1a | ---------------------------------
| note | 6b851ef0-e3b1-4b71-bd5e-6fd4b51336b7 | FREQUENCY: Each lot
| note | f966ffa9-7b60-4203-a1b8-ffd7341e24e8 | ---------------------------------
| note | 6d147b2c-7df7-41f6-b38d-94dfde857666 | CATEGORY: IP
| note | 0fc131de-3515-4937-a3bb-4d1cf7d50424 | ---------------------------------
| note | b37451a6-8a55-4b22-84df-2fabc7be78b9 | RESPONSIBILITY: SE/PE/SPE
| note | 737c48f7-7e48-47d6-99e6-739dac8e82d7 | ---------------------------------
| note | e3b27bbd-b7f4-4c78-8a15-43ff7957e324 | VERIFYING DOCUMENTS: This ITP
| textbox | 6045c473-8683-4986-92db-7c1cdf6bd944 | Date Completed:
| checkpoint |  | 4.2 Construction Joints & Matching Existing Surfaces
| note | 621561c6-e59f-4487-b854-acdb76920af6 | REFERENCE: IFC Drawings
| note | 4104d43c-d53a-428d-b41e-ea5668b19b42 | 703.24
| note | 8a72140a-bc8a-4f51-9d55-afad4ae73329 | Relevant Council Standard Drawings
| note | daeb6929-6c11-4c67-b209-67e287d17a02 | ---------------------------------
| note | b253670b-c644-401c-824d-6564ce1833c9 | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
| note | ed913ffb-810f-454b-85a2-80aef67a2aa0 | Consult the relevant Council Standard drawings for the joint detail, these may require:
| note | 2b37ec34-e812-4fb0-afcd-94c6c54a9510 | i. Concrete cutting of a shear-key
| note | b1f3f8fb-63e0-416a-8f49-50bf98f2ac6c | ii. Surface roughening
| note | 74bd569b-3e4b-4b22-a0ac-502fa2316326 | iii. Drilling and insertion of dowel bars (may also be galvanised)
| note | a9857c27-c51c-49c6-b5c0-51ed15f3a0f5 | iv. Cutting a groove for sealant
| note | 97312197-68cf-4864-a668-450e3dace83a | Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
| note | 24907ddb-5ee7-491d-bb2f-b7ddac153928 | Transitions between different profiles shall be made in accordance with the drawings.
| note | bc640a47-fac6-4428-be29-e0a0808d5073 | Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
| note | cd78a15b-77e6-44ca-9319-4d04f1d765ce | ---------------------------------
| note | 93e7d189-4906-45f4-a9c5-1bb3c167986f | METHOD: Visual Measure
| note | e3540f0a-c81d-4fe3-80e0-91d019347021 | ---------------------------------
| note | 88722b7b-7742-42eb-ad5f-5464ed406ecd | FREQUENCY: Where applicable, each lot
| note | 3173408f-0a84-419b-907c-68dd3a034fae | ---------------------------------
| note | 9cf73a11-f16c-4659-91c3-6283ecca863c | CATEGORY: IP
| note | 2ec20f4d-fc0b-445a-a4fb-0ad0a0f5df92 | ---------------------------------
| note | 7e8a1ace-d6fe-4837-8cba-a1bd321adcd4 | RESPONSIBILITY: SE/PE/SPE
| note | 4416e791-efce-4572-ad1b-47f5b7599504 | ---------------------------------
| note | 217edd6f-8a8f-4f70-8b6b-43b65dccd072 | VERIFYING DOCUMENTS: This ITP
| textbox | f20308cc-79d7-4ff2-ab24-0f841e7bfca6 | Date Completed:
| checkpoint |  | 4.3 Isolation Joints
| note | 7981e081-6023-49dc-959a-78f0d777ed76 | REFERENCE: IFC Drawings
| note | b5a9e92d-a718-4774-a259-2370297dd792 | 703.26 (c)
| note | 92923679-eb7e-4213-989c-c8313db7dbb7 | Relevant Council Standard Drawings
| note | 0deebdcb-0e4c-491b-b227-65777156ac72 | ---------------------------------
| note | 35a8af22-f2e1-4ddf-9f51-d36ce1a4c7ba | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
| note | 7d2ee1ed-4075-47f7-8d8a-08d04ef67a1b | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
| note | e3b36e99-cd6d-4072-8256-5d01f35ceb0b | ii. at any location marked on the drawings
| note | 29bd45ae-6104-41ce-b617-0503dff59aee | The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
| note | bb66aaa6-74bd-401c-9f69-62afe9e4c0d1 | ---------------------------------
| note | 1e1de7af-c131-43f7-ae71-39d9a7f3ecb0 | METHOD: Visual Measure
| note | 1a4dcbad-7bfe-445a-9ef3-d20b5981cd4d | ---------------------------------
| note | 7a500430-a666-4b0d-beee-fc22ed182041 | FREQUENCY: Where applicable, each lot
| note | 354bd5df-214d-470d-9167-c424d1f5cc07 | ---------------------------------
| note | 0b04e346-6555-4c33-a4ec-79e879105d62 | CATEGORY: IP
| note | 4e6fcff7-1408-4b27-a0f4-bd03095baa8d | ---------------------------------
| note | d70f6367-0ba0-4b94-a928-542783e60f3b | RESPONSIBILITY: SE/PE/SPE
| note | e81e5e1a-1868-484d-8979-76097d040e66 | ---------------------------------
| note | 66ddec3c-cdbd-458a-9ee4-fe42e409e6cd | VERIFYING DOCUMENTS: This ITP
| textbox | ec9f6824-c86c-4973-89a7-c2090816a636 | Date Completed:
| checkpoint |  | 4.4 Expansion Joints
| note | 3a08c80a-a64c-46f7-9b11-3ff81702cee7 | REFERENCE: IFC Drawings
| note | fe1fbf80-3db8-40d5-895a-7dd223e35f67 | 703.26 (a) (ii) & (b) (i)
| note | 8104cd54-9144-4d77-8d9d-d10d4af55bbf | Relevant Council Standard Drawings
| note | 918c0b77-74bc-482e-a3e5-36956ba24da3 | ---------------------------------
| note | 52423121-fb2c-402f-9b56-14dff3505c4c | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
| note | 17c0926d-945c-48af-bc29-ed67b5d86bcf | i. on either side of vehicle crossings
| note | 3728ff95-44e2-4472-b768-66f5262a0e07 | ii. at junctions with existing footpaths and shared use paths
| note | 1adff3b5-1ecf-4e63-bf7c-87f36d367a10 | iii. at junctions with bridges
| note | 24b0a45d-9aba-484b-a7d2-b261bd39d579 | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
| note | ae8528c6-1dbc-4647-822b-e60b75841890 | The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
| note | 16e4ae46-db4f-4d25-a81c-27203732e850 | Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
| note | c845caf8-6662-44b7-81da-8a8fa41611fd | Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
| note | 438346d0-701f-4c9f-91c9-bedfea5b644c | ---------------------------------
| note | 30c9eab1-5493-409d-b6be-0e263b7d5ced | METHOD: Visual Measure
| note | f2a948db-aabd-41f8-b806-a5bdbbf45e58 | ---------------------------------
| note | 084c92fc-7eea-49c5-b781-3e213d2a66e0 | FREQUENCY: Where applicable, each lot
| note | 56ed41cf-91d7-4ec1-bde2-8cbc45618e36 | ---------------------------------
| note | 5f3cfa5e-7b6e-4b06-8903-0ef41e9c2dd2 | CATEGORY: IP
| note | 82448220-8287-4a9e-9098-9a634ddcd317 | ---------------------------------
| note | 3d3346a2-5dd3-4084-8276-0a194b3c9256 | RESPONSIBILITY: SE/PE/SPE
| note | 881e174b-e96c-43d2-bed8-02938dd128c3 | ---------------------------------
| note | 22d33661-e0bd-4ea8-9813-4364aaa6bfa6 | VERIFYING DOCUMENTS: This ITP
| textbox | 2e5289d4-1d35-4ef6-94d5-5403cb1fcac7 | Date Completed:
| checkpoint |  | 4.5 Reinforcement Placement
| note | 1ecedffa-a65c-4af9-abc5-adf130aac21e | REFERENCE: IFC Drawings
| note | 24891543-ce76-49f2-b700-e0b7cf8ce65c | 703.13
| note | 31e95e70-39db-4b56-9bcb-7fed3f47534d | ---------------------------------
| note | dd803453-ecda-4700-835e-a41612c25151 | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
| note | 33da0349-32db-479e-b9ae-7d1e41b6cb84 | Any splice lengths achieve the minimum length and are in contact for this length.
| note | 5adb8bc6-55a9-436b-adf1-4756263e3591 | The reinforcement surface condition is free from dirt, debris and damage.
| note | 60cc5baf-338b-4be4-a531-6ce01084503a | The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
| note | 9133d4d7-6b73-468d-965e-832f3968e587 | Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
| note | fee73fe3-6c1f-405b-92ba-a21361bf9a69 | Minimum cover of 50mm at edges has been achieved (including tie wire locations).
| note | 88c2f8e5-b36e-4200-b125-a8a47302a298 | ---------------------------------
| note | e29eef73-c5af-43e7-b464-a97540c56113 | METHOD: Measure Visual
| note | a7519396-8263-475d-940d-3bf183186959 | ---------------------------------
| note | 0a839a40-bd59-40bc-8246-ce821245fa37 | FREQUENCY: Each element
| note | 15f3c5cc-b207-43c9-9ca6-b0beda8db3a0 | ---------------------------------
| note | aaaab1c8-07e7-4cbe-8060-df139ea6e245 | CATEGORY: IP
| note | c86fdece-5a2b-47d0-a55e-f53f08993709 | ---------------------------------
| note | 553a4f0a-925c-44f2-85e8-a5b5c38bcfc1 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 1fdb0bc6-b36b-4946-b1c6-11e0491d2dc9 | ---------------------------------
| note | 9e6f03bf-21d5-441a-a88a-40d0e527290d | VERIFYING DOCUMENTS: This ITP
| textbox | 5979296c-47b8-4055-9148-523ea0b7ae4e | Date Completed:
| checkpoint |  | 4.6 Pre-pour Survey
| note | 53bed2c4-c84a-4ccb-94fc-caedfd203b33 | REFERENCE: IFC Drawings
| note | e939ed62-0528-458c-9e4d-fde72979e756 | 703.15
| note | 5d93b411-dcd1-414a-a81e-86f25582d5be | ---------------------------------
| note | 17eea297-9015-4a87-8662-12806a94f814 | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
| note | 342025a4-235f-4a14-8266-d66a5bf0497d | Erected formwork and base layer within the tolerances below:
| note | 32c72aa6-7c41-4bc4-88ae-9b662cddf787 | Departure from RL = ±10mm
| note | 13121b8c-95fd-4dc0-9ab1-14bc5bf39820 | Departure from alignment = ±10mm
| note | fd7234be-7440-4e7d-83c4-65585949df73 | Rate of change of deviation from RL or alignment = 10mm in 10m
| note | 5fc14115-e500-4ac5-b870-573b48fa4048 | Irregularities in alignment = 5mm in 3m
| note | a70ebdf2-6202-4a4f-8783-dd50c4129e72 | Section dimensions = ±5mm
| note | 53ce4daa-87f0-4f44-94d2-9c3b26bb5fc7 | Section dimensions (less than 25mm) = ±3mm
| note | 7a5f37ce-470f-49dc-a5a5-d79984e82c9f | Width of pavement = -5mm, +15mm
| note | 1cfea96c-1a93-45d4-a38b-b141cefd5ec3 | ---------------------------------
| note | 10b294e8-42f3-4dac-886e-ea0a35f69905 | METHOD: Measure Visual
| note | 0c12db5f-2dc7-4f61-836e-feb0397446b0 | ---------------------------------
| note | c21276c4-ee81-4dd5-a05e-389c9372cfca | FREQUENCY: Each lot
| note | 330ae596-0387-4e97-874d-3fa106dd1e44 | ---------------------------------
| note | f29c781c-35f9-4d33-8d79-c748ead57038 | CATEGORY: IP
| note | e9a3a3a8-71d2-4e14-ad7a-0481f81db558 | ---------------------------------
| note | 0ad533b7-26f0-4258-ac0f-82392bf7c062 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 66ae16dd-ca1a-4087-b91c-a98090db5123 | ---------------------------------
| note | 2a1dfecd-99d3-4849-b53d-1df635046efb | VERIFYING DOCUMENTS: This ITP
| textbox | 51ba7965-5308-4a73-98ac-d7d050f2e646 | Date Completed:
| checkpoint |  | 4.7 Pre-pour Inspection
| note | cd1e33b1-cc66-49da-919f-8886669bf004 | REFERENCE: IFC Drawings
| note | 4d83324e-11fc-41a5-b50e-a87455a10087 | 703.15
| note | 9a6ba483-ec47-4cdf-a2c6-cffd0e4d0141 | 703.21
| note | d54901e4-7106-42a7-b9da-94fd6e2ae711 | ---------------------------------
| note | d1067965-a639-432a-a5ea-003252d480fa | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
| note | 47f535ab-5622-4e81-bd0c-6df2f1e76e16 | Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
| note | 83d5f037-2464-4b98-8420-95e1354df293 | ---------------------------------
| note | 964d117f-bac9-4857-8166-32f137f9d82d | METHOD: Measure Visual
| note | fb4cf554-1994-415c-a820-f8734f450dd6 | ---------------------------------
| note | 17655191-b942-4a56-83f1-c975e0c1ebd1 | FREQUENCY: Each lot
| note | 46ab8c32-223f-401f-8823-547f316b278d | ---------------------------------
| note | ef16bb95-3479-46b5-94ac-3ff0004d78e3 | CATEGORY: IP
| note | 9e2ddcea-a09a-4fab-86d3-57f0bf1f38bc | ---------------------------------
| note | a33f2ee2-37da-4000-be23-922346264565 | RESPONSIBILITY: SE/PE/SPE
| note | 39c95412-62d0-431c-9548-966c0b3a3bdb | ---------------------------------
| note | 0157cf52-20b9-4774-a742-65a935d5516b | VERIFYING DOCUMENTS: This ITP
| textbox | fdb1dc6b-8b1f-492a-9022-bcbe2588e76c | Date Completed:
| checkpoint |  | 4.8 Weather Conditions & Evaporation Limits
| note | e38c734d-c24f-4b7a-b2ee-a1d78406dc49 | REFERENCE: 703.09
| note | 1bae9ab3-7cd1-4b35-a4d8-19265c9f33be | 610.17 (a - f)
| note | 63d28faf-1604-491a-aab1-502108057e2a | Table 610.171
| note | bd78a19f-534c-4669-a4e8-d4a0a31b6202 | ---------------------------------
| note | 8e6f888d-2fb3-405a-b6e2-d2e1fc62001e | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
| note | 93bb96c7-e193-4e17-8a78-87251526bc61 | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | 7a6d2cfe-eba9-417f-be36-1916e7e8c94d | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
| note | 2dfed09f-ec4c-4719-b563-a9dedf843797 | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
| note | 6bc46892-79e8-484e-a5ab-61ae008f5ab1 | Record: Required information on the Concrete Pour Record.
| note | 277f7640-03c7-406a-8521-92bf6129e336 | ---------------------------------
| note | e0cbe1bc-daca-4d92-8ebe-1d0a19aaba93 | METHOD: Measure Visual
| note | 9983f6fc-bed1-49bb-aeae-0383ebbdcf8c | ---------------------------------
| note | 65972df2-efdd-4cba-8f8a-7ff901d76dc4 | FREQUENCY: Each lot
| note | 63dc228d-7635-4e98-b9c9-9b5d0615c057 | ---------------------------------
| note | 5c72c765-b6eb-4fdb-a1f7-8b800588e6d5 | CATEGORY: IP
| note | a69fb8c5-33eb-41cb-9117-d16a8b2ee2a7 | ---------------------------------
| note | 21ed0d3c-e736-4ae4-98f8-3b4058bfa64a | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 397ec0bf-b966-493c-8822-cb24ccd4af25 | ---------------------------------
| note | 64aada0e-7bf7-4bf7-a5d9-0952d36e0f9a | VERIFYING DOCUMENTS: This ITP
| textbox | 28b7d9ec-6b74-423c-abec-7bb9b946917a | Date Completed:
| checkpoint |  | 4.9 Concrete Testing - Sampling Frequencies
| note | f2dab0c6-69c5-4988-b591-63c49f2b8e56 | REFERENCE: 703.11
| note | bffbe978-9049-42c5-913b-67121931e2a9 | 610.16 (b)
| note | 7240eff6-e589-4ee2-bed6-b59c422c81ba | ---------------------------------
| note | bd43e53e-613c-40a6-a679-2381d4afe208 | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
| note | 101105e6-8948-4191-8fd2-a2a37d059cc6 | Shared User Path:
| note | 51cd49e8-e2d3-4f4b-b614-52493be37baa | 0m³ to 10m³ = 1 sample
| note | e25d8d4d-a249-4065-9e4d-23ac488677d9 | 10m³ to 25m³ = 2 samples
| note | 62e03843-15eb-4e4f-9deb-9d7d72dad360 | 25m³ to 50m³ = 3 samples
| note | ed722dd4-e820-44d1-b4a7-8969b9ca88bd | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
| note | e6e8d9de-7cb6-42b9-80a3-fdac16d42287 | For each additional 50m³ and additional sample shall be taken.
| note | 228622a5-b68f-4eb2-a06e-ca4f43e9f5da | Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
| note | 37e6d5ad-2a7a-4b19-a2dc-eaca63a58550 | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
| note | b82c7ae8-b0c0-430b-8bde-324f823b9724 | Footpaths:
| note | 6ec473d9-358f-4493-9e18-0bdc96432720 | 0m³ to 50m³ = 1 sample
| note | ab291b4f-8837-4a7b-adc8-12774c947f00 | Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
| note | 9a212bfb-024e-4510-8164-12e0a2b72e83 | Compressive strength cylinders = 2 no. 28 day strength.
| note | 0d5e5179-b2eb-4747-aef2-f452135f41df | Record: Required information on the Concrete Pour Record.
| note | f408bac7-d94a-4aec-afbd-d021ba7533cb | ---------------------------------
| note | c770adcf-b1c2-444e-bf42-06e9adf5d07a | METHOD: Test
| note | 86b14379-d21e-4fa9-af4f-d8dd0e076d35 | ---------------------------------
| note | 151e5cc8-2b61-4998-a158-c162de196948 | FREQUENCY: Each lot
| note | a7d8deac-b54b-43dc-ac06-e7b708cab5f6 | ---------------------------------
| note | 45b1ef30-96c9-4d2d-a957-2924620ee11d | CATEGORY: IP
| note | d64ae04e-003a-4fb1-b100-02af9b6ad71d | ---------------------------------
| note | 6f04b8fe-a330-4301-a1ac-dfb48d59cee3 | RESPONSIBILITY: Concrete Tester Foreman SE/PE/SPE
| note | a1b17c0d-3da5-42ba-a617-78856db9cd74 | ---------------------------------
| note | 3a22b43e-fc18-48b7-9363-1780a7251890 | VERIFYING DOCUMENTS: This ITP
| textbox | be893ca8-37dd-4762-853d-c46b7750b635 | Date Completed:
| checkpoint |  | 4.10 Concrete Testing - Slump
| note | 44d77a05-a0ba-40c3-8152-4045c70414fb | REFERENCE: 703.11
| note | 473f40e9-f359-445a-a9ea-c1806cfd6894 | 610.16 (c)
| note | 53ade6aa-6914-41c0-9c2d-15b3b74ed8df | ---------------------------------
| note | f7ea99a9-3268-4e3c-bac6-e9448ead3312 | ACCEPTANCE CRITERIA: Slump testing tolerances =
| note | bd9b972a-d7d6-48e7-9faf-bbc8456e5088 | <60mm = ±10mm
| note | 01400972-cae8-4beb-9d46-6682be2a3037 | ≥60mm to ≤80mm = ±15mm
| note | 176a1a5a-0bb4-4804-a24b-491b130f7c88 | >80mm to ≤110mm = ±20mm
| note | 5bb18462-28a3-4351-9323-2c166de0bca3 | >110mm to ≤150mm = ±30mm
| note | 0cd0cdec-0454-415d-b69b-709791051dd8 | >150mm = ±40mm
| note | ae487e24-1166-4c96-aaff-be957b89eb44 | Record: Required information on the Concrete Pour Record.
| note | e38e0645-c5f9-4207-887a-33be5f26eb29 | ---------------------------------
| note | aedd1c10-3702-4ee5-9394-3f93d48443e0 | METHOD: Test
| note | 07a8e808-1bdb-4bd8-9eb9-aa5734ca5489 | ---------------------------------
| note | d9f3dd9d-5165-45ae-b09d-acf9be6b978f | FREQUENCY: Each sample
| note | 1e498cf0-5b61-4811-a060-ae04e8963d87 | ---------------------------------
| note | d058f09f-421d-4163-817e-3cdf72498887 | CATEGORY: IP
| note | 0497ebf8-bac7-438c-8490-004b969d3fd5 | ---------------------------------
| note | e87e8945-edf6-4e71-aed5-0b851b7e679a | RESPONSIBILITY: Concrete Tester
| note | c80f0519-3378-44f8-bdf4-b2608e034996 | ---------------------------------
| note | e0133e5a-9a01-4d1d-bb63-531702c4a593 | VERIFYING DOCUMENTS: This ITP
| textbox | aa050043-6a5a-4464-9d57-849b59556d0a | Date Completed:
| checkpoint |  | 4.11 Concrete Testing - Compressive Strength Cylinders
| note | 4c8817ab-b1ee-4a6c-8511-3af8ed081b00 | REFERENCE: 703.11
| note | c595d52a-5a46-4cea-b576-654c9eca6d12 | 610.16 (d)
| note | d30e07a5-196e-4354-b908-5d9da50b5952 | ---------------------------------
| note | b25e76b1-38f2-40ca-b232-3bc0c5cc9814 | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
| note | 17f0190f-fa31-41cb-be70-b502690047d2 | Record: Required information on the Concrete Pour Record.
| note | 9f696cfd-5808-4448-a6b3-606491fa3b2f | ---------------------------------
| note | 11684d28-952d-4276-b170-dadd58164591 | METHOD: Test
| note | de53c331-2f1a-4f68-be64-510f30340dd7 | ---------------------------------
| note | 3db6d44d-fc69-48b8-aa7b-a9ba7ae4b749 | FREQUENCY: Each sample
| note | e4f22d2e-f12d-40c9-9619-b26c22063e61 | ---------------------------------
| note | 43050026-1d22-4267-8109-ac48ebdd99b0 | CATEGORY: IP
| note | 65481a0e-7425-4310-9926-9ec0b2b483e2 | ---------------------------------
| note | 98c68c37-40d4-4c92-b6a9-9b6e53c39047 | RESPONSIBILITY: Concrete Tester
| note | 3ab7597e-185a-43c2-b3da-04aaccbe5cc5 | ---------------------------------
| note | 99ceec44-16cd-4d46-b70c-d43b8c6b659d | VERIFYING DOCUMENTS: This ITP
| textbox | bcfbc617-c711-44b8-b403-1a9e9525edcf | Date Completed:
| checkpoint |  | 4.12 Supply & Discharge Rates
| note | c9a0a382-21d0-4c99-ac8d-4bb58abf04a1 | REFERENCE: 703.08
| note | 91a46640-c3d8-4775-94e4-7626bb9b99e4 | AS1379 Clause 4.4.1
| note | 2b4bbc1b-8b31-4ddb-8eae-3caa2adef505 | AS1379 Clause 4.2.3
| note | 61bbea6a-88f2-415b-87cf-763f9c14701e | AS1379 Clause 4.2.5
| note | 62fca4e4-4f76-418e-b340-9f7d528ed350 | ---------------------------------
| note | ddd37e8c-0bd6-4400-84f0-10f6e993f73a | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
| note | 68ea05b1-0cab-42f4-9cd5-83ebc4f21944 | Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
| note | 40434d21-46c0-486f-95a5-b66dc81f8aae | Concrete that stiffens or is showing signs of stiffening shall not be used.
| note | 66cb32dc-be09-4213-9b9c-08363586d1e8 | If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
| note | 4db4d4dc-42ed-4456-89d1-144de20ea5c0 | Record: Required information on the Concrete Pour Record.
| note | df02c409-bd73-477f-9ad1-72c023197929 | ---------------------------------
| note | ce28f967-0eee-4181-a22c-177cd243f3a4 | METHOD: Measure Visual
| note | fbb432d9-be41-43fb-92cc-8136bf0842a4 | ---------------------------------
| note | 93ef5980-9661-445f-aaba-9966e157bf9a | FREQUENCY: Each load
| note | cfad3968-e219-4c57-8934-9de174543cd6 | ---------------------------------
| note | d8ad15ee-559b-43c4-8370-6941f560280a | CATEGORY: IP
| note | a9157d63-87c7-4230-aea3-7df07d9b3f49 | ---------------------------------
| note | b5c0d04f-9ea7-46ca-9c71-f10ff6f59e31 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | a32736e3-7d8a-4ca6-8cbf-f2a73076d8cf | ---------------------------------
| note | bd06073f-d0e7-4bae-92c3-bf2b57eabaaa | VERIFYING DOCUMENTS: This ITP
| textbox | e853733c-2c99-4806-bd93-0c6e4eeed230 | Date Completed:
| checkpoint |  | 4.13 Placement & Compaction
| note | cf25eacd-f513-4d3c-b748-d6fc8b0264be | REFERENCE: 703.08
| note | 98143921-faa3-45d1-bf75-d81b45688863 | ---------------------------------
| note | 90102c7f-e0c7-4fb5-af37-f4c0df6f8157 | ACCEPTANCE CRITERIA: All concrete batches are traceable.
| note | 062b12fa-8da4-4bfe-865e-9e469001468b | Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
| note | 509285a4-58fa-42c8-b2ee-8649fef2c0c7 | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
| note | ff21763b-91f3-4367-a839-efa9f7d128e6 | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
| note | 9aecf439-ad08-4e7f-94e6-afab7103a1e9 | Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
| note | f77c0bd5-0035-4bcd-9549-b1e81457bb07 | Vibration continued at each point until air bubbles cease to emerge from the concrete.
| note | b32bd32d-572c-440b-8ab7-381d176a393d | Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
| note | e31478c2-d2e1-4ce7-9d20-5046e870e658 | Record: Required information on the Concrete Pour Record.
| note | 5e78809e-7506-4b11-b025-26a72c761fcd | Attach: Concrete Pour Record
| note | 94eb13f8-c7e4-4abb-b6aa-8d2d0dffe72d | Attach: Concrete Dockets
| note | f58175ef-74f3-4001-8020-439cd0dc838f | ---------------------------------
| note | a5b5f2f1-d1ab-4a69-8c66-171c72e5cd89 | METHOD: Visual
| note | eb07a0ca-a792-4433-97e1-50d02e9d2496 | ---------------------------------
| note | 6109d760-13c1-4f53-a900-57cd77537c0b | FREQUENCY: Each load
| note | 0abdb091-5ca3-43f6-948d-941ae5ba0b6e | ---------------------------------
| note | 4ee4dc13-8573-4475-be51-e3719b59a69e | CATEGORY: SP
| note | bd0630e9-c10a-401a-be64-7ddea16efb91 | ---------------------------------
| note | cdffd630-994d-4772-9dee-d073d9ee237a | RESPONSIBILITY: Foreman SE/PE/SPE
| textbox | 169d8b5c-632d-4f75-8000-07c092a155d9 | Date Completed:
| checkpoint |  | 4.14 Surface Finishes
| note | e57e3c33-2593-4bd3-9222-633ac0c32424 | REFERENCE: IFC Drawings
| note | 610aeda1-db57-4240-91a6-76b92f6d0341 | Relevant Council Drawings
| note | a59d0a7f-9528-4ea3-856a-b663e4468b13 | 703.25
| note | bf837333-7a9c-4ed3-86de-2f64f40da12e | ---------------------------------
| note | 74b86858-96bc-40bb-8893-ba8142eba2a4 | ACCEPTANCE CRITERIA: Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
| note | 16fb5260-9ea1-4f4e-903d-26b53abbb76b | All outside edges of slabs and all joints shall be finished with a suitable edging tool.
| note | a67bee43-401b-4f9b-9de9-d995e31afa6b | ---------------------------------
| note | c4576ffd-9930-4acb-b363-49ac63f67d0a | METHOD: Visual
| note | ecb1a0e2-0c7c-4b06-a933-df63a76443d3 | ---------------------------------
| note | e0d0398b-a6f9-4ff1-96f0-5b0383e0f65b | FREQUENCY: Each lot
| note | bee071f8-36d5-41b0-9159-8f29fbf3ce5a | ---------------------------------
| note | 0a589212-9b2e-4ef4-b2c2-53830dfa1521 | CATEGORY: IP
| note | 35c3f347-cd20-4535-ae4e-9394605841a4 | ---------------------------------
| note | ef4905eb-d21f-4e4c-8b24-2302ea0dbda2 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 7ccf6cfb-4eef-471d-97cc-bfd8300bb89b | ---------------------------------
| note | 65e49aa8-19a8-462f-a200-dc45db3b293f | VERIFYING DOCUMENTS: This ITP
| textbox | 7e56597e-cad9-4320-bbed-bd1257cfe3da | Date Completed:
| checkpoint |  | 4.16 Marking of Conduit Locations
| note | a598c20f-1b12-43a3-9904-ec7b02dc0730 | REFERENCE: IFC Drawings
| note | fab6f630-f268-4495-ad60-37ec83ab68d0 | Relevant Council Drawings
| note | a768163a-0161-4704-9677-c9a18cecf539 | 703.28
| note | 8a72475c-9a37-4518-9bac-bbf47be34c42 | ---------------------------------
| note | 6ba11b5c-79c1-4c63-b2bc-c9ed2b30bd9b | ACCEPTANCE CRITERIA: The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
| note | 263f46a0-168d-4cbe-94a7-bd71f4af92a1 | ---------------------------------
| note | c78510d1-3b37-41c6-a52b-3d89be61d0a3 | METHOD: Visual
| note | ea201d6e-1a35-4bf0-a09b-2a0be535e1ed | ---------------------------------
| note | 3bf9caff-8615-4ff3-885a-3a641121195b | FREQUENCY: Each lot
| note | c39306d7-b12a-4e20-8d5a-313cffcd2341 | ---------------------------------
| note | db1fba75-adb4-4a24-9e13-c0e1ce291a38 | CATEGORY: IP
| note | 3509622b-8db2-4cf6-9d30-784caf38a8f5 | ---------------------------------
| note | 0d613dd0-ab38-4ecf-bbb6-91c7e2a43c70 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 37029378-6354-4964-822c-94d71dac9514 | ---------------------------------
| note | d50b632e-a809-4f78-8516-9d719b914157 | VERIFYING DOCUMENTS: This ITP
| textbox | 08f963d9-25e3-442d-9a47-989b61d12335 | Date Completed:
| checkpoint |  | 4.17 Footpaths - Crack-control Joints / Weaken Plane Joints
| note | 87a67ce6-9001-461a-a988-5e98701e5941 | REFERENCE: IFC Drawings
| note | 468560c2-c23a-40f5-8505-afce2e18e5c0 | Relevant Council Drawings
| note | bac3af98-ff68-4f03-a713-866884542a68 | 703.26 (b) (ii)
| note | 0fac8c7a-717d-4630-a1ee-14bce4c763c7 | ---------------------------------
| note | d807cae2-2f77-4ccc-aed8-e5687c19fab9 | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
| note | 2c622479-8500-4cea-b524-ee1c4cf79e32 | ---------------------------------
| note | 8748a526-60b9-4328-b752-71e1ab1f6657 | METHOD: Visual
| note | ccbef603-aad4-42ad-b57b-e2094e042b6a | ---------------------------------
| note | 777b22fe-4e98-4497-9d4b-82a1fab25cdc | FREQUENCY: Where applicable, each lot
| note | eed8576d-da58-40af-a637-21bc9890db3d | ---------------------------------
| note | 7e746da3-f5c9-45fd-8b90-5ec9b9974ad7 | CATEGORY: IP
| note | 495650a5-53f0-4f86-a30e-be2f6fc62411 | ---------------------------------
| note | 2d82cc03-a81b-4086-b56c-47454790e805 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 7b24368b-8626-47e2-a59e-59bb66b40619 | ---------------------------------
| note | dc4a236c-c0af-45fa-8255-8962035a8849 | VERIFYING DOCUMENTS: This ITP
| textbox | 8eafd9d6-ee07-4104-86ed-40e57c3622b8 | Date Completed:
| checkpoint |  | 4.18 Curing
| note | daf73e5f-9a9c-4b4e-9db8-a33cd0a5f9f5 | REFERENCE: 703.10
| note | 3256a2fb-33bd-4cd3-914c-38ac55fe4443 | ---------------------------------
| note | 96cb89fd-4dd3-4029-8ee1-0af44dda9497 | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
| note | aafde184-518a-472e-9806-271bcf43e6d8 | Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
| note | 37d871c1-9ef7-4ee7-aa70-6859b03e7950 | The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
| note | 887b4a73-9cd5-4589-b430-9256f9467e14 | Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
| note | ca9b9e30-2afe-4a96-8fe0-acd2e1de315f | Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
| note | dac9e088-b818-448b-9252-ba418c3fd9b0 | ---------------------------------
| note | 49f6c12c-ecab-4a9e-9e8d-31694eba8a5a | METHOD: Visual
| note | ce6eb688-276b-44a7-aebb-a23c2b317ef4 | ---------------------------------
| note | d41fdac8-35be-4815-b28c-9c58e4889e74 | FREQUENCY: Each lot
| note | 942bd805-4f3f-4d3a-936f-11a489961ff6 | ---------------------------------
| note | a8e0d679-25ce-4625-966b-06b16ddd4ab1 | CATEGORY: IP
| note | 8cff0cc9-c60f-4d56-bbfa-a4bfd250d07e | ---------------------------------
| note | d716a33f-1f79-4855-a080-d2247899bfdd | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 3255c5e9-74c0-4d3e-be61-0ab43b2d7625 | ---------------------------------
| note | f11e3817-088d-458e-9eda-9fd5ce224154 | VERIFYING DOCUMENTS: This ITP
| textbox | d465321e-d32b-4f11-b880-884736ec3c18 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 5.1 Shared User Paths - Crack-control Joints / Weaken Plane Joints
| note | 7329dadb-b5f5-4b5c-ab97-4400fd10e91b | REFERENCE: IFC Drawings
| note | bc368423-076f-4c86-b4b2-813015cb1608 | Relevant Council Drawings
| note | a14c891b-030a-4d05-a1ef-4f92f87f1c4d | 703.26 (b) (ii)
| note | 401e1c1f-435e-4c14-89b7-64765a42b807 | ---------------------------------
| note | ea56a803-7625-4406-a3a8-c4c2dafa8dd9 | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
| note | 97ffa1bd-fac6-4091-b6ae-49fe4e2b6774 | <20°C = within 24 hours of finishing operations
| note | 367c6a36-dbbb-46b4-8774-842a9dde67b2 | ≥20°C - 35°C = within 4 hours of finishing operations
| note | cfcccacb-c918-416b-9c6f-981a20db8967 | ---------------------------------
| note | 0d2996d7-d306-483b-82b1-a916a3becc19 | METHOD: Visual
| note | bdad8846-ec17-42af-9b12-8702082a7998 | ---------------------------------
| note | 418e7756-20e8-4176-b37c-265ea4fb74f9 | FREQUENCY: Where applicable, each lot
| note | 84b2372a-5ab4-4d4c-b239-52ac80e13df7 | ---------------------------------
| note | bdb78c8c-8ebf-4365-9c8b-cfe5b08560ac | CATEGORY: IP
| note | be1dd102-0b2e-4ddc-bfdc-4a7815109c48 | ---------------------------------
| note | 0f3a4c65-54f4-43bb-a75b-35ab7f5e1309 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | cf100573-f337-4a42-9429-9924c86584e4 | ---------------------------------
| note | ca7e5fa2-84de-43d3-9a06-59e7cc58502b | VERIFYING DOCUMENTS: This ITP
| textbox | 0c843fbd-b025-4668-ac59-d65053d9293e | Date Completed:
| checkpoint |  | 5.2 Protection of Newly Poured Concrete
| note | e4afa30f-36d1-4a6e-a5bf-2b499de3c41a | REFERENCE: 703.27
| note | 611095eb-1566-4c24-a6ec-7c34dbf7c730 | ---------------------------------
| note | afe87f6e-2745-4327-8e42-3ca4c9def8ce | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
| note | bca147c0-3717-47ef-8795-2a85fe5ec430 | Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
| note | 2c80e356-dbbe-45f7-baf8-7dd18d1430d6 | ---------------------------------
| note | d813c039-245a-48a4-a979-a82728d7dede | METHOD: Visual
| note | 07ab5d34-810d-4428-af91-894779a7b70f | ---------------------------------
| note | 7061a582-42b7-405a-9632-a5c92ec43268 | FREQUENCY: Where applicable, each lot
| note | b500c974-d747-4442-baee-0e7cfad150a5 | ---------------------------------
| note | 46718281-78f2-4771-a496-51606675214d | CATEGORY: IP
| note | d33bf862-b971-4ec2-8848-298081225a5a | ---------------------------------
| note | 64935bd1-6028-48cf-b815-cfcb78d390dc | RESPONSIBILITY: Foreman SE/PE/SPE
| note | bd45b5a1-9690-41a0-b97a-9378f17e6f5a | ---------------------------------
| note | 62833124-393d-40a8-b07a-845ce35f6015 | VERIFYING DOCUMENTS: This ITP
| textbox | a8151346-e87f-416e-acd0-68e415ce2ff0 | Date Completed:
| checkpoint |  | 5.3 Stripping Formwork
| note | 3d2ac942-e276-4092-990b-3ee815235c1c | REFERENCE: 703.12
| note | 4b2df7bc-7e42-4695-a7c2-62dd0afbc1c8 | AS3610 Table C2
| note | 12465621-3fc2-4bd5-a272-89ca1d5926ff | ---------------------------------
| note | d153c399-842c-47c2-bca8-664822bc4025 | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
| note | 25efc9d1-abd4-4885-937c-586538ed02a9 | i. 2 days for vertical formwork on external surfaces; and
| note | 1e789a30-751f-4281-98b7-00980ab2652a | ii. 1 day for vertical forms on permanently hidden surfaces
| note | ebc0d186-69b4-48d0-a6b9-2aac219227af | ---------------------------------
| note | 008a6d35-3b9d-47aa-b14d-0f138cc3d835 | METHOD: Visual
| note | bcd9aae5-2472-4c55-b2db-03ac4fa9a7c1 | ---------------------------------
| note | 11e90f2d-4deb-4f56-8902-9c907f242897 | FREQUENCY: Each lot
| note | 2d0ed3c5-4295-4746-8acb-795022de217e | ---------------------------------
| note | 0295e0e0-966e-4678-adae-21ff2ead11f0 | CATEGORY: IP
| note | dc28802f-4568-4f4d-a44e-56ecccaf2c81 | ---------------------------------
| note | b664cdad-109e-4e86-8942-c39fb9883ae3 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 9d7fc65a-e616-44ae-b0f4-feb3ddfd4814 | ---------------------------------
| note | aaf28c1e-b1c9-4566-b646-60b18f811c2f | VERIFYING DOCUMENTS: This ITP
| textbox | 21a61a1c-13b0-4292-86f8-2cf4f43922eb | Date Completed:
| checkpoint |  | 5.4 Backfilling & Pavement Restoration
| note | d34349cc-eb82-4645-b0b2-783749160ae8 | REFERENCE: 703.29
| note | d4855658-41d7-42f7-bb12-dda7064324c4 | ---------------------------------
| note | 3be0cc8a-4ca0-4ee5-b5c4-58af94af2299 | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
| note | af6a0395-4362-46f2-a409-065dde7cb91d | ---------------------------------
| note | 7f818548-5c4c-43dc-b90c-f178bc1fd21d | METHOD: Visual Measure
| note | 1e814697-800b-4b32-881b-00e07c150f45 | ---------------------------------
| note | c4d9533a-0f09-4001-a2e0-9ba9dc2557f2 | FREQUENCY: Each lot
| note | b2abf6df-acd0-4674-b56b-cca4e97c418e | ---------------------------------
| note | 02c45cbf-b432-4c15-9590-9804068ed07b | CATEGORY: IP
| note | 2edb1cf9-916c-4c6a-b18f-7eba207b3f6e | ---------------------------------
| note | d29b79ad-e365-45cd-a7a5-d65877903942 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 6d01e1de-c0cf-49cb-a632-b71c595b45d1 | ---------------------------------
| note | 4baea288-145b-4e3e-9b2a-94c47581146c | VERIFYING DOCUMENTS: This ITP
| textbox | 01857ae4-3c9d-41cb-8fd4-7ba430ea4a77 | Date Completed:
| checkpoint |  | 5.5 Surface Inspection - Cracks
| note | ae3923c4-1838-482e-94eb-d8d08216ed49 | REFERENCE: 703.3
| note | 888196b4-4487-4c31-b9c0-be91fea897fe | ---------------------------------
| note | d060e504-a8e3-4893-b803-3a278f66fac0 | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
| note | 9ff532e8-b32c-4b36-add7-84cc1f830535 | If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
| note | 3d0a290f-2311-4189-93ae-87fdbc148e30 | ---------------------------------
| note | 07ee1cb3-6705-45f7-943d-9a7876743263 | METHOD: Visual Measure
| note | 22b24567-fec2-4518-87ce-afa868a1a41b | ---------------------------------
| note | d8678f47-5295-4a19-ba81-a64478ee4c4a | FREQUENCY: Where applicable, each lot
| note | 10d93f7f-c88d-4651-a7af-b9c2921ccdc4 | ---------------------------------
| note | fb74088a-33ba-4825-90b5-5c20b16e6bc9 | CATEGORY: IP
| note | 76e4a4ee-bb3b-44fc-8d2e-249ffee935d7 | ---------------------------------
| note | 95e900dc-0b28-45f5-8e9d-b8f8da5b212c | RESPONSIBILITY: SE/PE/SPE
| note | ad7d1670-1ec8-43bf-8fa2-3be1b2a566cc | ---------------------------------
| note | 0f7c0c69-26cf-495e-98f4-74d6332a2a6e | VERIFYING DOCUMENTS: This ITP
| textbox | 94940d11-d482-493a-aa3e-7fe848d1cc3a | Date Completed:
| checkpoint |  | 5.6 Surface Inspection - Surface Finish
| note | 061dfd2a-703d-4554-a7b1-ce2890853bd5 | REFERENCE: IFC Drawings
| note | 61f47ecb-ff24-46f1-b255-290e20ad49ef | Relevant Council Drawings
| note | af151f7e-d72d-4e5f-ad37-7743eaeb2ec7 | 703.25
| note | 5ffaca4b-1f3b-4994-8b02-e41840b8a1d7 | 703.10 (a)
| note | a01896cf-3bc1-47b2-9568-4dc1562b4239 | AS3610 Clause 3.2
| note | 103a8ff0-583a-4458-b069-561bfb25f59b | ---------------------------------
| note | 33efca9e-af38-4085-8106-fef7500469c4 | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
| note | 178022d9-b818-4d0a-8f6e-7c88db11f8eb | All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
| note | e1510328-76ea-42ca-988d-8d47de445295 | Class of finish:
| note | 2401c5fa-5061-40cd-ba7e-bf8045af70a0 | Permanently hidden surfaces = Class 4
| note | 5dc427e0-b302-45c8-b9f1-8bd432b6dcef | All other surfaces = Class 3
| note | 6756adf9-0760-47c7-bc7f-be33c4149373 | At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
| note | ecfe1095-bdf5-41a0-8927-6775fffd7ece | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
| note | fb319ce7-dde6-437b-b3b2-f4599d24d506 | ---------------------------------
| note | d8897987-a509-4a66-a13b-8b8234f3ff45 | METHOD: Visual
| note | 69a25d09-cb60-4627-ac46-29613b3afb01 | ---------------------------------
| note | 3fd2cfdd-0604-4733-9bf6-624c1bd77758 | FREQUENCY: Each lot
| note | df394893-c2dc-410f-b51b-0a93a3ae5821 | ---------------------------------
| note | 8886637a-8a02-47a6-addf-767519e9dec6 | CATEGORY: IP
| note | 3595e05c-7875-4a24-a73c-7ed74d6f433d | ---------------------------------
| note | 4cff590d-660d-415c-af12-1ef0698ca807 | RESPONSIBILITY: SE/PE/SPE
| note | 63b9be58-03f2-47e5-a89e-f20eb999878d | ---------------------------------
| note | 70267856-aa0b-4ff0-a3c2-f5af5860085b | VERIFYING DOCUMENTS: This ITP
| textbox | 91c43297-323d-4fc9-9b73-2957c2cca30d | Date Completed:
| checkpoint |  | 5.7 Compressive Strength Test Results
| note | b1142923-fbb6-4e49-b0eb-9ac744ec989d | REFERENCE: IFC Drawings
| note | 83e721c1-a8fe-4815-bc74-010e241849f9 | Relevant Council Drawings
| note | 31af4dee-d05d-42fc-bf38-75bfa475daf9 | 703.11
| note | cc9d1f23-60ff-42a1-94e4-371757a66ee1 | Table 703.111
| note | 024332d4-d66c-4285-8ac5-fc46d3741f9f | Table 610.05.051
| note | 97fafeba-a1db-417a-a3c8-0747f8da7172 | 610.16 (g)
| note | 1868640e-166e-41cc-af27-3eadd2d449ac | ---------------------------------
| note | d8fa6c12-61c6-49e6-a455-6cfa26d3813b | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
| note | bc02ac01-bec5-45a0-99ad-f0a83502a3a6 | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
| note | 198b3bff-2cda-439c-bb02-e5847f82615a | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
| note | 53a603a4-c3c4-4cd6-a0ca-efae621345b8 | Attach: Compressive Strength Test Results
| note | 4a73bffd-dbaf-4b1e-a3ad-f4157fd219c3 | ---------------------------------
| note | a87dbfc1-75e8-4a23-99d6-20a7e8c8c4e0 | METHOD: Document Review
| note | fcdc0aec-a022-4db8-bd91-7e110c7ddedb | ---------------------------------
| note | ab0fc7ec-0c93-4bab-a153-523c32ea4ba7 | FREQUENCY: Each cylinder
| note | 9a1d0d78-2705-4fd5-979a-206da1475be3 | ---------------------------------
| note | 84cebe47-e478-43d2-8498-51dfcea74580 | CATEGORY: IP
| note | 8e51541b-8bac-4776-a27f-a6e02e763cad | ---------------------------------
| note | 56b316b0-5c60-4fbe-b967-a8a3e5e45e01 | RESPONSIBILITY: SE/PE/SPE
| note | 52371cd2-5038-4256-a13e-1bf35d6a2ec6 | ---------------------------------
| note | 91211260-26b7-4e64-933d-13511706b334 | VERIFYING DOCUMENTS: This ITP
| textbox | 61679152-c785-4a2b-9ee6-a2922899834c | Date Completed:
| checkpoint |  | 5.8 As-built Survey
| note | 3d7f9b09-1dce-427e-a008-21cef1e74f00 | REFERENCE: IFC Drawings
| note | ca65457b-f86e-40df-93fd-0d093c2e8871 | 703.15
| note | 8eee844a-f7de-432f-9c85-5e8b7cf7df81 | ---------------------------------
| note | 4ea0a4be-818d-40af-9c18-8d20810d6289 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
| note | 3847a4b0-4d41-44ed-88a6-86fbc2f95a2d | Departure from RL = ±10mm
| note | 40400130-82a2-4807-a0a5-6abbdb88704f | Departure from alignment = ±10mm
| note | c009d510-b231-44c8-a2ee-21db88f3cca1 | Rate of change of deviation from RL or alignment = 10mm in 10m
| note | 65269645-168b-4201-b709-f66b7e3e5862 | Irregularities in alignment = 5mm in 3m
| note | 33bde3ea-68a8-48dd-969d-daef4adcf8f1 | Section dimensions = ±5mm
| note | 9ad3f03f-d452-4a30-a9d6-007411659de5 | Section dimensions (less than 25mm) = ±3mm
| note | 0a1f6e23-0941-4d3c-ac0d-7be1b7f7e2c1 | Width of pavement = -5mm, +15mm
| note | 7d9a4fd6-e38b-4164-96df-436551a930d5 | Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
| note | 40fc8883-12e8-4e1f-a8e2-6f92247c9db4 | Attach: Survey As-builts / Survey Report
| note | a7f4a419-46b7-496f-8b26-5019e91ab806 | ---------------------------------
| note | 431231fc-89c1-47f5-8ea2-810c486dbdce | METHOD: Document Review
| note | eecbec80-8049-45eb-833f-d59d29d6f118 | ---------------------------------
| note | 4a42fc1d-cf73-4abc-995b-63bc2c7cda0e | FREQUENCY: Each lot
| note | 5d8facdf-4dab-4942-94d1-216210f2718d | ---------------------------------
| note | e67d1ffa-9f71-40c6-981a-01ccc034abb1 | CATEGORY: IP
| note | 91802094-8a70-4010-9542-d2762e2a287f | ---------------------------------
| note | dcdcf1dd-669b-41bc-8c7f-924246283236 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 6a5fe4d9-04c4-4655-a37e-9804af20f9b4 | ---------------------------------
| note | 88996478-ff34-42b7-9d0a-84aa70e3c823 | VERIFYING DOCUMENTS: This ITP
| textbox | 046a38a7-f7d5-4e80-89cd-5b8f5160f57b | Date Completed:
| checkpoint |  | 5.9 Non-conformance Report (NCR) Closure
| note | 8fa2f7b9-9ef3-48b3-8e6c-d710a2ee1532 | REFERENCE: MRPA Quality Management Plan
| note | 22b78439-87ce-4941-8df2-9a2c25bc2051 | ---------------------------------
| note | 4820b7d8-7b9f-4660-bf06-9d3d49f55012 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | a0f4e3c9-df0c-4e2a-9ed9-f0bdac6c208f | ---------------------------------
| note | b4c13851-eb0e-4851-9774-a737500bb259 | METHOD: Document Review
| note | cbdcfb71-84c6-4d8f-b847-1924e8cfa778 | ---------------------------------
| note | 64c60370-0246-43e6-bbda-da9c29ebce56 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 3fdc1ba7-b0f2-4899-8d1c-1d0e061316bc | ---------------------------------
| note | df864b75-02bb-4545-ad0b-8781b2f80a00 | CATEGORY: HP*
| note | c9da3be0-5a85-45c6-8f26-a09aa38cb0f7 | ---------------------------------
| note | f983c3a5-7c3f-4811-95b3-ae61b2fbbcbf | RESPONSIBILITY: SE/PE/SPE
| note | 5b0aeab4-9c9b-4a9c-8d1a-2c5233064c7e | ---------------------------------
| note | 50a064a7-a496-4588-a764-df9079d3611a | VERIFYING DOCUMENTS: This ITP
| textbox | 204b8a0b-baba-4f5c-b655-19fb372343b3 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 38d8cbb9-4d55-4133-b4dc-78d3af7df52c | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 090d32bd-d483-4487-87c0-81822b60d6c4 | Name:
| textbox | 1224bc35-bfe2-40d8-9444-455f56c4787c | Position:
| textbox | d6b32225-8d47-4518-a1fe-0db54cb339f2 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | Stormwater - Pipe and Culvert Installation Rev0.0 | itp | Stormwater - Pipe and Culvert Installation Rev0.0 | 46b85ba1-508f-46dd-8e40-f02aeb135d17
| checkpoint-no-value |  | Document Reference
| note | 6a36b10f-153b-4f82-974f-8062bdc8bbbc | VicRoads Standard Section 701 (April 2019)
| note | 967fd870-5097-492c-bb85-b0f782631f79 | VicRoads Standard Section 705 (October 2018)
| note | 232f74ef-500a-4c27-963c-c3f37e910e22 | Revision of ITP template: Stormwater Drainage_00
| note | b5e6390a-657e-42ac-9dee-90a76339c507 | ITP template approved by: Michelle Edgar, October 2019
| checkpoint |  | 3.1 - Conformity with Drawings
| note | 54b40914-46d8-48d5-9dcc-f146912a1981 | Nominated Authority Hold Point is released.
| note | b4aa2071-4e94-4092-85e1-cccad67b57d2 | Position of all culverts have been confirmed by IFC drawings.
| note | f45f696b-b13a-4afa-809a-8b32bc69a1a1 | Notify the Nominated Authority of any design change.
| note | d1c4f73f-1ca0-4b77-8110-b861adfefd34 | - - - - - - - - -
| note | 6e4c2eb5-2188-460a-9890-c08b7dc04d6a | References - IFC drawing
| note | b1260e2b-bc99-4d53-8d36-3206b46cfc70 | - - - - - - - - -
| note | 19bac70d-b359-44f2-a247-6089a880248e | Verification Record - Nominated Authority Hold Point is Released where drainage lines as per IFC drawings.
| checkpoint |  | 3.2 - Pipe or Culvert Details
| dropdown | 252da321-52f7-4a7e-b09c-a195c331f8fb | Pipe Supplier: | Rocla
| dropdown | 18ff51ad-4bf9-4f86-8dd7-4d13205c7148 | Pipe size (mm): | 1050,225,300,375,450,525,600,675,750,825,900
| dropdown | da5815fe-b757-44cd-a3b4-e8b9fdaa4c05 | Pipe Class: | Class 2,Class 3,Class 4
| note | b03a5d5c-962c-4648-9079-3222c145a682 | - - - - - - - - -
| note | 45d27dd8-637e-44c8-8571-daa24eb38d7a | References - 701.04, 701.05
| note | e88ab3fe-384e-4fe1-8baa-c82e1c74cd3a | - - - - - - - - -
| note | 4fda85aa-aa1c-4f17-8f10-f92584743f71 | Verification Record - Refer Teambinder Material Approval for approved proprietary products
| checkpoint |  | 3.3 - Trench Excavation
| note | 9552eca0-1d11-48f3-ad6f-7c25640ce609 | Excavation for the installation of culverts shall include all excavation necessary to prepare the foundation and provide the full depth of culvert bedding.
| note | 05d05e4e-ad7d-4a6a-b16a-7de1db202c77 | - - - - - - - - -
| note | b69ef7fc-afb1-47b9-86c6-9992a1ca14e7 | References - VR 701.14 Table 701.141, VR 701.09
| checkpoint |  | 3.4 - Bedding
| note | 4936c113-811b-4fa8-8c70-f63f92980a0e | Bedding material shall be provided and placed for the full width of the trench. Compacted thickness of bedding material following shaping necessary shall be not less than:
| note | f4019800-babd-41e0-9f20-e59156a93ecc | -100mm where D<1500mm
| note | 95dced09-fd4e-4df5-8d33-269ace1da009 | -200mmwhwere D≥1500mm
| note | ce9f772a-27d5-450a-8032-319593811f45 | - - - - - - - - -
| note | d17b07c9-b369-4ff4-bdf7-96f04a098e75 | References - VicRoads Spec 701.15, IFC drawing
| note | 54777c2b-5a8f-41f1-b723-22501374487a | - - - - - - - - -
| note | 12b1c5e0-ee0e-417c-a076-9b0bc6a78217 | Verification Record - This signed ITP
| note | 29885dc6-1caf-480f-9bae-a9bc14393f81 | Bedding material used is approved by Nominated Authority. Refer Teambinder Material Approval.
| checkpoint |  | 3.5 - Bedding Testing
| note | e332c6ec-683f-4990-9451-b5e5186fde1a | Bedding and back fill materials shall be placed in layers not exceeding 150mm loose thickness.
| note | aae1e3ad-2033-4243-9d7e-ef1a7778146f | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
| note | 177e4ea8-7882-4a74-ae47-fee847033376 | Bedding shall be compacted to refusal using hand held mechanical equipment and material(Swell equal or greater 2.5%)and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
| note | c92d9f51-b47e-4420-a7fa-fac7dd268927 | - - - - - - - - -
| note | a14823b8-1318-485e-938f-34db66492ac4 | Verification Record - Record Test Request Number
| note | cc94cfeb-8cb7-4f87-a7ea-b7ab0a888808 | Attach test reports
| checkpoint |  | 3.6 - Laying
| note | f3feb9ac-ad5f-457c-8696-8ec300b710de | Rebate and socket ends of pipe section and shall be placed facing upstream and be fully entered.
| note | 88ce743b-facb-4a91-9955-a4ec29486bce | The lower portion of the pipe shall be in contact with the bedding and shall be shaped to accommodate the joint collar and supported along its full length.
| note | d6533e21-13c1-4f43-8d00-5f4489729c17 | - - - - - - - - -
| note | 2eabe293-f70a-4647-a22f-787629d34306 | References - VicRoads Spec 701.16, 701.17, IFC drawing
| checkpoint |  | 3.7 - Lifting Holes
| note | 965b44f8-9dd2-4cca-9deb-00c24586c403 | Pipes shall be laid with lifting holes uppermost.
| note | fb038986-b995-4fca-aba0-f061ebc95f71 | Lifting holes shall be plugged or otherwise closed off in accordance with manufactures instructions.
| note | 99628e0d-5d0f-4c75-8f4c-3d5dbfa7bcad | - - - - - - - - -
| note | 289713ad-0048-427c-a5b8-ec7abe4e5a88 | References - 701.17
| note | ad06af26-1b9a-4f76-b5c3-a0ae6059a6d9 | - - - - - - - - -
| note | ecce6505-9b04-468f-99bd-4e2a37ed60b6 | Verification Record - This signed ITP
| checkpoint |  | 3.8 - Survey conformance
| note | 53b0f37a-ce6a-4813-b49a-da504fbb192b | Each run of underground drainage shall be Survey verified prior to backfilling.
| note | cc001f53-1368-4a62-80d2-24c8c50b8b6a | Offset pits to kerb +/- 20mm
| note | f5fa6eaa-6fc6-4f2a-9ba0-53f29a0ea0fd | Plan location pits not adjacent to kerb +/- 100mm
| note | 5a978c6f-9eb7-42c7-9ae4-ef10d1102a7e | Invert level of pipes at pits +/- 50mm
| note | 1aca822b-1849-4abf-93b4-5ac45a8552a0 | Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
| note | cae55f5e-107e-49ab-ab06-5d10579a1567 | - - - - - - - - -
| note | 3fafce2f-0c5e-4e15-b112-6c6279d253c9 | References - VicRoads Spec 701.09, 701.18, IFC drawing
| note | ffb476db-2ea2-4880-acd7-1c31e0813682 | - - - - - - - - -
| note | c9d9acd6-1902-4f25-b2b6-fdb475034e25 | Verification Record - Survey pick-up drainage line. Provide in CAD;
| note | 8ee40512-de23-4677-a1ef-d9a6c5dce8e5 | Plan location pits
| note | 86a55712-99be-4db2-ad8c-73d9d34cfa96 | RL pits
| note | 3b1493c3-125a-488c-b691-a280b7fdcbf1 | Invert level drainage line at pits
| note | 1d279cb7-428f-4118-bd5c-f535f77b0e2a | As-built grade of line
| note | f58ad6d3-a2ea-49af-b0f2-3d644663efb2 | Red-line mark-up drainage plans and long sections to show As-Constructed details.
| checkpoint |  | 3.9 - Requirement for Testing and acceptance of compaction and moisture content(Testing of Backfill)
| note | ee11ed5b-81c1-4d84-96e6-05d7a236471f | Bedding and back fill materials shall be placed in layers not exceeding 150mm loose thickness.
| note | 76dd0dab-208f-4e61-9099-8c56ad1c8452 | Test -minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
| note | 5f119446-1cdf-4db6-ab45-8ce32efbe219 | Backfill shall be compacted to density ratio not less than 97%. material that has a swell equal or greater 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
| note | 14e625a1-fd98-4fa0-adf4-a994400c9b46 | - - - - - - - - -
| note | 85386189-0f9a-47c2-a0f5-da3ac476c30f | References - VicRoads Spec701.19, 701.27, IFC drawing
| note | 18118c67-7601-4686-aa46-f461e000bd60 | - - - - - - - - -
| note | 885a7ff7-a9bb-4930-89fd-5be47fc9d9af | Verification Record - Record Test Request Number
| note | 9ff22b67-d0cc-44a5-8a21-f7f84701b844 | Attach test reports
| checkpoint |  | 4 - Inspection of drainage line
| note | dcee1712-6c35-41f5-a348-cc92e6b5b60a | All Drainage line constructed shall be inspected after completion of earthworks to subgrade level and prior to construction of pavement layers, by independent Testing Organization using closed circuit television(CCTV). The report shall be provided to the Nominated Authority
| note | 92783fed-dc70-4b36-8708-c5499d0ab083 | - - - - - - - - -
| note | 0b804ec2-5229-4591-8877-1dea5c2f1103 | References - VicRoads Spec 701.28, WSA 06-2013
| note | 7ecb9361-6284-4c19-8a82-8c7f512aa128 | - - - - - - - - -
| note | 96356775-3e96-432b-8d02-df32b8af256c | Verification Record - CCTV footage file name and location
| signoff |  | Nominated Authority Hold Point
| checklist |  | ITP-STR-Precast Planks (Supply, Installation & Stressing) Rev 0 | itp | ITP-STR-Precast Planks (Supply, Installation & Stressing) Rev 0 | 4e1ab57a-aaae-4054-8877-566d12b9ea2f
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | f0fe4cc6-74a2-5fe8-9b3f-d554f39172d2 | Document Title: ITP-STR-Precast Planks (Supply, Installation & Stressing)
| note | c663923e-3944-512b-9caa-08786e511d46 | ITP Description: Precast Planks (Supply, Installation & Stressing)
| note | a74a9c84-e7f7-538f-9666-a98d7cbb9fab | Discipline (e.g. CIV/STR/RAIL: STR
| note | 4ac706cd-be22-5c13-addb-9f8f7257479b | Revision Number: 0
| note | 2793680f-6eb3-5c00-9253-a6e2f3737e89 | Revision Date: 08/07/21
| note | 6465ef41-a09d-53a5-9dee-a4622469ebc4 | ITP created by: Thomas Hudson
| note | 4a9f60b2-f9d6-548a-aedc-2c39dc08b430 | ITP approved for use by: Aldrin Guinchoma
| note | fd83dc60-a782-5ac3-b5fe-86fb3dae9326 | 1.1 VicRoads Section 610 June 2019
| note | 3cf79678-6319-54ad-aedf-fad66733261b | 1.2 VicRoads Section 612 November 2018
| note | 39dd9806-0de8-5a5b-b98b-86ab1f43e4d3 | 1.3 VicRoads Section 613 June 2017
| note | 8b815004-6fc8-5eb5-bcc0-12be9fbe9995 | 1.4 VicRoads Section 614 June 2017
| note | f3496343-0a92-5c18-b212-6a2de777bda0 | 1.5 VicRoads Section 620 May 2009
| note | bc4544db-843c-5cf8-bc05-9a65facdcae4 | 1.6 VicRoads Section622 November 2018
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Grout Product Selection - Cementitious (Non- Shrink 32 (min) Grout)
| note | 605ae916-a243-5a12-bd4b-dcdc24e3c76c | REFERENCE: 612.18
| note | 6b8f091b-17a9-5454-bd7d-58a14cd31df5 | AS 3972
| note | aaa49e86-0360-54f9-b21d-6ddef8ae655b | IFC Drawings
| note | 75f5114a-c78c-58c7-ac3b-2b62a786e3b3 | ACCEPTANCE CRITERIA: Cementitious Grout
| note | e4147a41-cae6-5943-8956-3ad01087017f | Details of the materials and the proportions of the grout mixture shall be submitted to the Superintendent for review.
| textbox | 7768af88-742e-5173-9a56-e9de67455336 | Enter: Teambinder Material Approval number
| note | a743c171-6866-563d-a638-c419c4286743 | METHOD: Document review
| note | 0f4e6bcc-e3c5-59f8-8be0-35c029786555 | FREQUENCY: Once, for each product, prior to placement of product
| note | bc1a6491-1c8e-5d77-b5c7-68f5415c4e03 | CATEGORY: HP
| note | 7cea63c8-b594-5c31-969f-5eaae0c10b3a | RESPONSIBILITY: Nominated Authority
| note | 5d0d9b83-8f08-5450-830c-2cdeccb1259b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b9b6aad9-9a55-5848-9980-b2d052489752 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Grout Product Selection - Epoxy (60MPa (min) Epoxy Putty or Megaepoxy PM)
| note | 06edbad6-8d88-5a26-836e-76e88ed09e7d | REFERENCE: IFC Drawings
| note | bf7bf527-a580-5c1b-996a-66a4dac295d6 | ACCEPTANCE CRITERIA: Epoxy Grout
| note | ae99bc35-fd30-5f57-b722-12e6f06dfb2c | Details of the materials and the proportions of the grout mixture shall be submitted to the Superintendent for review.
| textbox | eb2f5005-3b28-5468-ab80-df12df343002 | Enter: Teambinder Material Approval number
| note | 9ebf36a4-8381-5aac-a226-41ccacbc5fdf | METHOD: Document review
| note | 613d3713-da32-5cc8-99d1-f3bc0ecb9834 | FREQUENCY: Once, for each product, prior to placement of product
| note | d3acc884-0a4b-5f3c-91df-d6d0c52f5434 | CATEGORY: HP
| note | 3fdffc9b-623a-52bf-8f2d-f18e676728f1 | RESPONSIBILITY: Nominated Authority
| note | 8f09143d-6204-54e7-8b39-c4ff4be56b1a | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 021e27b2-39d6-5b60-a3d4-ed952e1e410c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 ACRS Certification - Manufacturer's certificate of compliance for Transverse Strands
| note | f19b9d82-afb8-5a70-a396-2602f26c1b9e | REFERENCE: 612.03 (a)
| note | 70b6b82c-725d-5a29-9ce5-56e190dd19eb | AS/NZS 4672
| note | 7cfec8cb-c04e-5b62-bc9d-a77e2d29554d | 612.04
| note | 96a00cab-730e-50a5-bb9b-c53350207963 | ACCEPTANCE CRITERIA: High tensile bar tendons shall be obtained from a supplier who holds appropriate product certification from the Australasian Certification Authority for Reinforcing Steels (ACRS).
| textbox | be616ed7-02c7-53cf-b9e0-ea3596c0e5e7 | Enter: Teambinder Material Approval number
| note | 6531c769-9abb-5dbc-9798-e80914b9542e | METHOD: Document review
| note | 6721048a-6323-536e-a676-e08d6cbb5ea7 | FREQUENCY: Once, for each product, prior to placement of product
| note | 72b09796-f69d-593e-956e-4830fd4ab468 | CATEGORY: HP*
| note | 1835b98a-656d-5b1f-a00a-7f27ccf2b11d | RESPONSIBILITY: Nominated Authority
| note | db1b999b-2fc7-53af-a047-17f96cebcaa4 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | baf6fbc1-534d-5992-9d60-16da6cddee20 | Date Completed:
| checkpoint |  | 2.4 Supply of Anchorage - Manufacturer's certificate of compliance
| note | fd2bc69c-bfdd-5074-8f7c-7a99bee551fc | REFERENCE: 612.04
| note | ccbffef6-5a06-5105-8d34-c3592b88c04e | IFC Drawings
| note | d34d0fa5-ef13-583e-af95-3d932a44b085 | ACCEPTANCE CRITERIA: Anchorages shall be tested for compliance with the requirements of AS/NZS 1314 - Prestressing Anchorages and the test certificates shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for the testing laboratory
| textbox | 7d9aa887-3771-5136-96c8-addaa0ad212b | Enter: Teambinder Approval number
| note | 5ec6f2a9-2745-55b3-a1c1-0742bd8b09ff | METHOD: Document Review
| note | cc7e9db3-628e-5ee9-89a2-dd7c6ce99108 | FREQUENCY: Where applicable, once, install
| note | eaea3c85-3e4a-5b7e-bb92-4d0774c9d15e | CATEGORY: HP*
| note | f31956da-2344-5543-b06e-c51a1f9870f1 | RESPONSIBILITY: Nominated Authority
| note | 959c5763-a7a8-53fc-9987-a537e5f84886 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 5f34efc5-de09-59a9-8d72-7e9ca5822339 | Date Completed:
| checkpoint |  | 2.5 Supply of HD bolts and nuts
| note | ce09c557-0b95-5bbf-bab2-1add42dbf64b | REFERENCE: IFC Drawings
| note | 4291e7b4-41ad-5f3b-bdaa-90854e363e4a | ACCEPTANCE CRITERIA: HD BOLTS SHALL BE PROPERTY CLASS 8.8
| note | 6dd0bea4-4bfc-5dfd-90b2-5ac8f581cf48 | HD BOLT NUTS SHALL BE PROPERTY CLASS 8
| note | 00f037ac-bf7e-576b-8615-a76cb704c247 | ALL BOLTS, NUTS AND WASHERS SHALL BE HOT-DIPPED GALVANISED.
| note | ee9033eb-92e9-5d91-8194-5fbc9afcaec4 | METHOD: Document review
| note | 7d1cbee4-f688-59aa-b472-f8bd9755830e | FREQUENCY: Once for each product
| note | f29e4e74-39fb-5e0c-8813-cf72faee0b1b | CATEGORY: HP*
| note | e123c23b-dc55-56e4-9fa6-5698dfc6e534 | RESPONSIBILITY: SE
| note | fa38fa8e-42af-53b0-aea9-5b29bf658a2b | VERIFYING DOCUMENTS: This ITP
| textbox | 90078446-d179-50c5-8b4e-c07f92ff01ef | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Precast Elements - Planks
| note | 4b1a61ce-d9d3-540e-be22-375c07f40e55 | REFERENCE: IFC Drawings
| note | f87208d7-fc30-594e-9162-bf5261ead2a6 | 610.47 (a)
| note | bbfb63fd-fc3a-577c-9d61-c7a9877d5c10 | Table 610.473
| note | 60e02f4d-fc7a-5006-8dd2-5dc2eab90f45 | (March/June 2019)
| note | 18a02e7f-b4f8-5185-96f1-b834e003deda | 620.03
| note | 13a3b768-08f2-5587-bddf-73733be2ac34 | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
| note | 29ff1123-1c73-5fdb-8fe5-e1102b2499d7 | i. Certificate of Compliance / Birth Certificate
| note | 2cbc05b4-12bb-5bfc-bf89-d9440edecb8f | 1. Concrete strength;
| note | ac61c727-22dd-5e17-8cf6-6552b3a0ffbb | 2.Date of manufacture;
| note | 98e867e5-399a-5b05-8d08-a5ca6aaea472 | 3.Unique Identification number;
| note | 36069b21-af5a-54bb-a722-9605da602ba0 | 4.Mass;
| note | 1ed0d003-c1d6-5a40-8bcb-2b87d5e90a80 | 5.Confirmation of number, type and capacity of lifting inserts;
| note | 5c0b82f4-4bb8-5706-82f8-0b681d638464 | 6.Quality assurance sign-off.
| note | 840029c9-1dda-5e49-ac2f-fb40662ea383 | ii. Compressive strength test results
| note | b5a1f1b7-1692-594c-83ef-968ad653b47d | iii. Precast Lifting Design
| note | f30746f9-3b3f-5826-8eb0-02c4420d0973 | iv. Pre-pour check sheet / ITP
| note | a1c6d798-4943-5deb-82d0-8abe753217af | v. Pre-stressing check sheet / ITP
| note | 6696e3bb-ed21-5af9-a72a-ec07d1b90c7a | vi. Post-pour check sheet / ITP
| note | b3acd227-6744-50bc-a329-07c90a7546b6 | vii. Covermeter check record
| note | 6db666dc-ad3f-594e-be2a-cf62f8ada035 | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.473 (March/June 2019).
| note | e4c18ac3-4bbb-5746-97b3-46cbfe718c3c | Note: Different revisions of 610 have different clause numbers
| note | e7d134c2-fda7-572e-aff9-272759fed9dc | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
| note | fc39d822-c0c8-57bd-ac8f-743b4fa3fd17 | METHOD: Document Review
| note | 72a38c13-7336-53e5-9930-bfe69378efc0 | FREQUENCY: Each element
| note | d8c3d354-9d66-5e4a-b8d3-b45e7ccd7a38 | CATEGORY: IP
| note | 18019eea-f464-5f00-baa6-550967a2d33f | RESPONSIBILITY: PE/SE/SPE
| note | 41f6b723-f633-5a0f-b410-7ca3e8b4bb8b | VERIFYING DOCUMENTS: This ITP
| textbox | 4b8d2c04-3631-577e-9266-d941b6c834ee | Date Completed:
| checkpoint |  | 3.2 Temporary Works Designs
| note | ec0da511-e5b6-5e12-b6ff-9844e7787b37 | REFERENCE: 610.27
| note | 7a2d4e50-0ef3-5920-a2a4-653461fcc333 | 613.04
| note | a336bedd-b6a4-5b2d-a693-e0a050acc311 | 613.05
| note | b9e91e05-4bc7-5853-ab4b-e73ff655e52e | 613.16
| note | 71a463bf-9ec8-584b-8dd5-4d0c9874799c | ACCEPTANCE CRITERIA: All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design.
| note | bdc3e115-d4a1-594b-a78f-0d4da31f708e | Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority.
| note | 9fc3845f-f68e-564f-a59b-34a0b3644dac | Attach: Temporary Works Design
| note | 2349bf0c-c524-564e-b1bf-9fe451438b60 | Attach: Attachment A
| note | 127be11c-7161-5248-af6f-5a7863eda75a | METHOD: Document Review
| note | 8e46870a-135c-5dfa-8575-7fa7f09a551a | FREQUENCY: Where applicable, once, 5 days prior to installation
| note | 5548835d-6485-5c4f-9069-acb4408d572b | CATEGORY: HP
| note | f562830d-c54e-5488-ab6b-18ab7672f804 | RESPONSIBILITY: Nominated Authority
| note | 54afa267-8165-5e3f-8d3c-ba08582f27d0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 904a59f7-8367-5178-9643-f065e4051b65 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Post Tensioning System
| note | 01d978a5-6e38-58cb-895e-6fd208ac0aa6 | REFERENCE: 612.02
| note | 168653d3-66bc-5dd7-be4e-661f10fbfd92 | 612.18
| note | 10cdbb9f-7c9f-50e5-be01-e070296e726d | ACCEPTANCE CRITERIA: Contractor shall submit full details of the proposed Post-Tensioning system to the Superintendent for review. These details shall include (when applicable):
| note | 1bcb5bae-c893-57fe-a2a7-c5d62ed6130d | (a) drawings and calculations that demonstrate the suitability of the proposed prestressing system for the structure.
| note | cb5a61cc-813b-5f72-b78b-a0b50a86485c | (b) source of the tendon;
| note | 6350c641-e02e-5a08-b507-f5f0ff84b3fd | (c) minimum breaking load of the tendon;
| note | 3af1718b-75c3-5f63-bd44-85ea59481d3c | (d) maximum permitted relaxation of the tendon;
| note | 270c1b8f-fed5-5fe1-81d0-309974a12371 | (e) modulus of elasticity of the proposed tendon material;
| note | c32d4b27-7228-53b7-8e63-3791e818751d | (f) maximum values of the friction, curvature and wobble coefficients as defined in AS 5100;
| note | b16800f6-a604-50ea-9b9d-e7e1ab9fff74 | (g) predicted extension for each tendon;
| note | b8ed6e6c-e9a5-52a4-b741-e9be8132fd78 | (h) predicted draw in at anchorages;
| note | fe49b1e0-0bd1-5200-bfd1-2c2e130ed765 | (i) anchorage details including any additional reinforcement at the anchorage zone;
| note | e8b403f2-2b59-5397-a086-19a9f3f21414 | (j) type of duct and duct material;
| note | fc36c78a-dba5-542d-ae91-30eb84440222 | (k) internal and external diameter of duct plus the type of coating;
| note | d0b7416e-3f71-5820-aada-52a0b8e8b43d | (l) method(s) of restraining and joining the duct;
| note | ef9d6b2f-a66d-575b-a700-9446bd5ae2be | (m) proposed tensioning system.
| textbox | 235ff7c5-5135-58fc-bb89-f1958fa5c228 | Enter: Teambinder HP Approval number
| note | 97aa3fa7-b88b-580c-ad62-7272e7bca6f5 | METHOD: Document Review
| note | 53399f6f-8051-5ea9-94e1-1dfbbaeb42f2 | FREQUENCY: 14 days prior to installation
| note | 7e5cf465-4d0f-551e-853e-78915067e62e | CATEGORY: HP
| note | c155fba8-04ae-525f-931e-26abfa0363ee | RESPONSIBILITY: Nominated Authority
| note | 168a0a2c-5ca5-593b-875c-165019cc2f48 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | bae1a958-96f7-54c8-b085-7bd38c9ff635 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 - Installation of Stress Bar & Stressing Methodology - Post Tensioning Equipment - Basis of Measurement of Tensioning Forces - Tensioning Forces Required? - Tensioning Procedure - Grout placement methodology - Mixing & pumping equimpent
| note | 69ea9126-b447-505f-baa6-84467a7f5ad4 | REFERENCE: 612.13
| note | 8481132b-9fe5-590d-84eb-9f67a9961318 | 612.14
| note | 9457c357-4f84-54eb-84b0-930613542de2 | 6.2.15
| note | 641fe6dd-d3e1-585c-b8fd-e379d58f6410 | 612.16
| note | 1256c4a5-732d-53b0-a429-3a44119ac727 | ACCEPTANCE CRITERIA: At least 7 days prior toPost-Tensioning Contractor shall submit following documents to the Superintendent for review. (When applicable)
| note | d6d5dffa-95e7-5b91-afa9-93c1c031f8b4 | 1- calibration certificate
| note | 67830f42-e8ea-5343-89f6-9dc63eb380a4 | 2- calculations for extensions corresponding to the upper and lower limits of the tendon force diagram shown on the drawings
| note | d75cdcc8-8fda-55b8-9e20-9d6f06af286a | 3- Where the coefficients for the adopted prestressing system vary from the values shown on the drawings, the specified tensioning forces shall be revised by the Contractor and submitted to the Superintendent for approval.
| note | 351d58ec-8568-5dd2-ab8c-58b22d716e67 | 4- All stressing operations shall take place in the presence of the Superintendent.
| note | ad68d95f-c396-5f1c-97c5-bb0194135c10 | 5- Details of the materials and the proportions of the grout mixture shall be submitted to the Superintendent for review.
| note | 1ff4656a-09f2-5b30-83e1-f37ee1788809 | 6- The Contractor shall give the Superintendent not less than seven days notice of any grouting operation.
| note | 6df04520-748a-5d4d-b70f-0ef4060b7683 | 7-All grouting operations shall take place in the presence of the Superintendent
| textbox | 6b31faca-8336-5947-91be-ac846efcf7ca | Enter: Teambinder HP Approval number
| note | 307227b2-a8ae-5ee9-a215-c931dfa4c55a | METHOD: Document Review
| note | ebb40dc5-dbae-5922-a5d1-0b6782a7a768 | FREQUENCY: 7 days prior to installation
| note | 70535721-856d-5451-82b0-e497de7960e4 | CATEGORY: HP
| note | 88a168f0-e9b4-58fe-8f30-0d4bb418473f | RESPONSIBILITY: Nominated Authority
| note | 094fc9c6-9132-5531-ae7e-ad9bdb715435 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c4f70628-2c87-55a5-95d3-9d73c6890827 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 4.1 Flowable Cementitious Grout for Crosshead stressbar anchorage recess Compressive Strength
| note | b182c9e0-f272-5c26-a1c4-4daaa58e83e5 | REFERENCE: IFC Drawings
| note | d673f2aa-861c-5ef6-b54a-86e274f51756 | Compressive Strength Results
| note | d123ca64-1d5d-54e0-aaa1-8d611a8ba8ec | MRPA-RFI-000803
| note | a863f88d-8d59-5207-b97a-530399c0ea68 | ACCEPTANCE CRITERIA: Check that the minimum required compressive strength of 15MP a prior to plank install for Plank P4 (10mPa if we use the larger HDPE pad, 250x250mm).
| note | 6640a9b8-18d3-5ef1-bf03-418498f50a3e | No requirements for other planks
| note | 667914e7-5c6c-5f5f-9120-ba4e57a266eb | Complete Test Results
| note | c741ca1f-156b-5651-a7dc-8c66ffa772c8 | METHOD: Document Review
| note | 97ab844d-9352-5d3e-9b7f-507b7738e972 | FREQUENCY: Plank P4
| note | 2b04fca2-0caf-52b2-8970-e4e0cff24331 | CATEGORY: HP*
| note | 5c4eae25-fe5d-5f80-81da-0566593e899e | RESPONSIBILITY: SE/PE/SPE
| note | ba8dd4d3-ca54-5eac-a12d-1c93869edf43 | VERIFYING DOCUMENTS: This ITP
| textbox | 7efafb8f-655f-5564-952a-9d40718b371d | Date Completed:
| checkpoint |  | 4.2 Survey Set-out of Precast Elements
| note | 550eac2f-6bb6-5b63-b21f-40cbe148538b | REFERENCE: IFC Drawings
| note | bdb9acd3-1b32-562c-bd02-0e54a160e9b9 | 610.47 (a)
| note | 97245b61-c652-5bfd-b2f9-5a8c09977a06 | Table 610.472
| note | 93770039-7f86-530a-a0a3-cf6db20e6457 | (March/June 2019)
| note | c1b0322c-2f54-53f1-a0d5-de1b5c1f1d04 | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.473 (March/June 2019) as applicable to the element.
| note | de0cc988-c649-5a70-991c-554f3d2516a0 | METHOD: Measure , Visual
| note | f17d5ee5-8c7c-5bcd-8cf6-fb029a014d3a | FREQUENCY: Each element
| note | 77dfd650-19ee-5fa5-a5be-ef22f57e062b | CATEGORY: IP
| note | 5d18a30e-2f19-5ea5-8276-71e13907fa42 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 2c3c5678-fe7c-58cc-ab68-56dda7b18c85 | VERIFYING DOCUMENTS: This ITP
| textbox | 0f441ee4-3054-519e-b63f-15e0653127c3 | Date Completed:
| checkpoint |  | 4.3 Install Packers & Compressible foam (for integrally cast Precast Concrete & grout)
| note | dbea13ec-258b-5c43-bdb6-c2dc9df634c3 | REFERENCE: IFC Drawings
| note | e4384949-2362-5d51-991f-ed34c778ba99 | ACCEPTANCE CRITERIA: Place the 25mm thk seating pads to the survey marks around each plank location. The packers are to the be precisely levelled to ensure verticality of the plank segment
| note | 94255223-0f51-5e27-83a4-ce719c166f39 | Place & adhere 400mm width x 1m thick HDPE Sheets to plank soffit on the eastern crosshead side
| note | 88369d6e-2ea5-533e-9222-8146356baf6b | Place & adhere 100mm width x 1m thick HDPE Sheets to plank soffit on the Western crosshead side
| note | 06b806d3-d639-5517-8773-669cbd21039c | Place & adhere 10mm thk JointFlex to back of planks
| note | 837327cb-ad5f-573e-ba59-2fa52abfbb63 | Place & adhere 10mm thk JointFlex to ballast kerb side of P1 & P7
| note | 11079cc8-763d-59ff-b435-81717290d05a | Place & adhere 200mm wide 40mm thk compressible layer placed on full length of crosshead to restrain HD bolt grout for crosshead to plank connections
| note | cfef3f5d-0988-555d-8a25-b505dc7b72cc | Nominal spacing is:
| note | 6d5ac6ce-d34b-58fb-8669-ceb0f36787ba | 25mm for crosshead to plank
| note | 82d0067d-61a3-50a9-a7b3-d0b408e5bd01 | 50mm for fender wall to plank
| note | 53117d9e-b117-5a9a-8c5b-142a35a02125 | METHOD: Measure , Visual
| note | 8a24d074-e41a-592a-af94-70fcfa04d25e | FREQUENCY: Each element
| note | 46ae07aa-9cc6-59d3-9b4c-a349e10d435a | CATEGORY: HP*
| note | b466c511-2f36-5488-ba09-4becb3e05822 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 22599b47-1bab-57f0-82ce-b8ba24eb53b5 | VERIFYING DOCUMENTS: This ITP
| textbox | fe839157-9b71-52ab-ba9d-1095f1832b02 | Date Completed:
| checkpoint |  | 4.4 Flowable Epoxy Grout Placement - Western fender wall soffit (grout bed)
| note | 2617ccd8-1c10-5b18-8c17-208466197836 | REFERENCE: IFC Drawings
| note | 52da2efd-2b7f-5d23-8f24-5cadfcbeb1ed | 612.18
| note | e0ca754d-ba98-56f6-8d8f-878fb5544f24 | MRPA-RFI-000803
| note | 06b71566-0ad0-5e79-9cde-106e7f750c75 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | aa3efcc7-435b-5329-a9fb-ef3e9660ce93 | Complete: Grout Pour Checklist
| note | 2349a010-e5fc-5d8f-bbd4-278d8bc8cf9a | Complete: Grout Pour Record
| note | 58bf32cf-82ca-5520-a2fd-905a22d2addf | Complete Test Results
| note | c5961125-b6e2-56fe-9036-485e91e31dcf | METHOD: Visual
| note | 23a5275a-fa2c-5d3c-9918-f7f58bc9bb51 | FREQUENCY: Where applicable
| note | 778dcf8c-37d3-509c-b723-d9a6d2dd90d7 | CATEGORY: HP*
| note | f37236cd-7577-5222-80d3-40bfdb62a1b6 | RESPONSIBILITY: SE
| note | de8f968e-8c35-5c0d-92e9-988c51a642c2 | VERIFYING DOCUMENTS: This ITP
| textbox | 0f540aa6-6420-5088-b8ec-281ad55aa1f3 | Date Completed:
| checkpoint |  | 4.5 Materials Inspection Checklist
| note | 53c84800-122a-5e37-abb3-c18bfbad92ad | REFERENCE: 620.06
| note | c938c580-fc44-5962-a6bb-fcfc26366925 | 620.07
| note | 47bf5154-d368-545d-babb-ca7ebc5f34f7 | MRPA Quality Management Plan
| note | 276e8731-5ea7-53db-92bb-b84119bb54f5 | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
| note | dd28c6f2-e050-568a-b07b-07e1f434dd0f | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
| note | 6ffbb873-ccf7-5786-8a52-643cc227c0f4 | Elements shall have unique identification and orientation marked (if applicable).
| note | 3b8bb7cc-adb8-5e15-81c6-d2c0fbd0417f | Complete: Materials Inspection Checklist in ConQA
| note | 50584e11-d41a-50f4-b5e6-b24cb42200af | METHOD: Measure Visual
| note | 64ce25ab-3058-56f3-af25-5d732b81c844 | FREQUENCY: Each element
| note | 34323fb6-f0bf-5663-929b-cc7270566d0b | CATEGORY: HP*
| note | 72c52311-d215-54ac-8b19-dbc95d1d9357 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 46125859-e8d8-5614-861c-95ff63bd8773 | VERIFYING DOCUMENTS: This ITP
| textbox | 4f456a0e-ed6c-5dd8-aed0-04919dfadb8c | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 5.1 Precast Handling
| note | bd19cc5f-09bb-5525-acfe-b73d1fc89b72 | REFERENCE: 620.07
| note | cc277586-f1d1-5b30-928a-0e7ecf15e852 | Crane Lift Study
| note | 41fea499-8e15-5986-a574-163e65ef173b | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
| note | 2ffc123e-396e-5a7f-8a88-af09b4866b25 | METHOD: Visual
| note | 44e731d3-abd9-5eaa-aff5-cb1eeb69396a | FREQUENCY: Each element
| note | 3c30419b-cd34-5db4-8e53-be59c52f5cd5 | CATEGORY: IP
| note | 97f060ba-4692-5603-b867-308e62c086a9 | RESPONSIBILITY: SE/PE/SPE
| note | e224c0c2-ed43-5b6b-9af1-682f4ec6e04b | VERIFYING DOCUMENTS: This ITP
| textbox | 5fb2fdde-d4c4-5d60-b1ad-7504e879a564 | Date Completed:
| checkpoint |  | 5.2 Precast Placement
| note | a76d5437-52f8-532c-aec7-2d7aa2e8bcfe | REFERENCE: IFC Drawings
| note | 44927c73-86b1-59c5-a1c2-1e60492a6557 | 610.27
| note | 44dfa173-9a7b-579a-accb-6a0d4721d7f7 | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
| note | 112f5140-5a8c-5f27-85ec-d66df5ab04f8 | The nominal gap between elements is as per the IFC Drawings:
| note | b4569bc9-d135-5888-a262-e08bbfb6bf6a | 25mm for crosshead to plank
| note | 12b26b42-34e5-5a75-a79e-88e09eb52011 | 50mm for fender wall to plank
| note | 2154ceed-483c-584e-b2f0-3f78f1320042 | 20mm Between planks
| note | 21ea7b30-5242-5197-af1c-200ca698aa72 | METHOD: Measure , Visual
| note | 9832de60-638c-5b43-a3f7-ba9d3b1c390e | FREQUENCY: Each element
| note | c110e4b8-8163-540c-b569-b5623a065868 | CATEGORY: IP
| note | 15ee6291-d818-56dc-aef0-8df0c6542456 | RESPONSIBILITY: SE/PE/SPE
| note | d11fd64d-45f4-5e26-b1c6-d6593f18ec95 | VERIFYING DOCUMENTS: This ITP
| textbox | 39bdfd13-2ecb-5b10-a0d8-e1b6e1833f15 | Date Completed:
| checkpoint |  | 5.3 Precast Traceability
| note | 504a529f-8eab-53bd-acb1-2c50747d6b2e | REFERENCE: 620.09
| note | 85eaeb5b-52a4-526b-b219-0fb0125c4aca | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
| note | 61a6fc70-6cea-52e3-bcc1-05fe2427cbb4 | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
| note | 16e614e3-e2b6-53df-ac83-785d1c58c500 | METHOD: Visual
| note | 7ecc7d28-daf2-52aa-b346-83c7838c1c6a | FREQUENCY: Each element
| note | 850633d0-beec-5559-80f3-945c8f063561 | CATEGORY: IP
| note | 63ab8b42-fa6b-59af-ad31-28b2033088ef | RESPONSIBILITY: SE/PE/SPE
| note | c594f4bc-4fa5-51c9-99b9-5978f5db0ed7 | VERIFYING DOCUMENTS: This ITP
| textbox | e1ec8ecc-0677-5204-8870-b0c33f1be69e | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 6.1 Falsework Certification
| note | 0af5c07a-aa71-5121-ad53-50edccfed171 | REFERENCE: 613.12
| note | 903be5cb-e3b3-571f-9961-a8c56d3f6194 | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above)
| note | ecac9672-5d62-5e71-b54c-e51cd07d5d8c | Attach: Attachment B
| note | 3b58de30-ce41-5554-9c0d-af10785cad51 | METHOD: Visual , Document Review
| note | af52df86-de67-5a8b-99c7-f465c3d5ea72 | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
| note | 5565f8c3-c770-5ebf-b2a1-4cd42467cd42 | CATEGORY: HP
| note | 1a101c51-6577-5683-8eab-8ec24b6d0258 | RESPONSIBILITY: Nominated Authority
| note | 4ef6b62b-7ed5-5ec2-bfae-ad9a146b252e | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 14351bb0-4b34-5dec-acd4-dc09b6a536ac | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.2 Required strength & age of concrete for stressing
| note | f416406c-5954-5a4d-88ed-2c0b2dbe6ef8 | REFERENCE: 612.11
| note | 3bd659bd-51c2-5ed6-ba75-ee12d47c0119 | IFC Drawings
| note | 6f58e79a-a7ef-5053-b49f-c5f0f153cae0 | ACCEPTANCE CRITERIA: The post tensioning force shall not be applied to a member until it has attained the compressive strength of 40MPa
| note | 6683901a-2e28-589e-9041-eab59d73f67d | Upload Concrete Test Results.
| note | 00e8e4fd-951e-5028-92cc-5a93bf358fd1 | METHOD: Document review Test results
| note | 20d59afe-e23f-525d-a202-0afc17b22434 | FREQUENCY: Before Stressing
| note | fff7459b-9323-50dd-ba5c-c52a9db63d20 | CATEGORY: HP
| note | c60d4fc8-88a7-5f24-8238-00c2bd2db938 | RESPONSIBILITY: Nominated Authority
| note | b43c66b8-bc92-5436-8176-f1ed6eb462f6 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | f75f1cdf-0c07-578a-8d8f-efe1f5f0110e | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.3 Flowable Megapoxy 206 Grout Pour - Plank to crosshead HD Bolt duct
| note | d5c6c554-8bc8-594f-8dee-94b89f3aa2b2 | REFERENCE: IFC Drawings
| note | 08c1b8d5-9272-53e9-907e-839985654c10 | 612.18
| note | e15a338a-6430-54d2-9f6b-0eb182d91954 | MRPA-RFI-000803
| note | 67530b03-e707-586b-ab3d-34e91871beb7 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 32 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 5dab0e2a-6fba-52c2-9382-37b96fc0c700 | Complete: Grout Pour Checklist
| note | 8c906a02-cc29-5817-979b-19fff5f34b7d | Complete: Grout Pour Record
| note | 96356a31-462a-5c0c-841b-3edef85d53a2 | Complete Test Results
| note | 80f36b34-3ffa-57a6-82bc-b0edcc70cc91 | METHOD: Visual , Document Review
| note | fcfbba6e-9932-5dd2-92fa-5ad2fcf033b6 | FREQUENCY: Where applicable
| note | bb8c6fab-7a8a-5cf8-81bc-2bce33933990 | CATEGORY: HP
| note | 89350e39-9b31-5477-bf6f-2672cb268934 | RESPONSIBILITY: Nominated Authority
| note | e9275f7c-41b9-586a-902b-40e2e91cbbf4 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | f17630e2-1497-53a0-9dbb-54715e32e4d6 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.4 Flowable Cementitious Grout Pour - Longitudinal joint between planks
| note | c5c54a62-8c46-5c9e-9c94-5f784c8badb4 | REFERENCE: IFC Drawings
| note | a9f678eb-9e4c-5b13-9ac7-35b3ecf9a6b2 | 612.18
| note | b3e8257e-13a9-5011-9aa6-132b3cad2c32 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 40 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 45017a54-057b-5015-9423-23bc8aabd86f | Complete: Grout Pour Checklist
| note | 29868e3d-e5c0-5897-b752-06cae8051f68 | Complete: Grout Pour Record
| note | 955d9e3f-eb0c-5976-beb4-d926c518ebbc | Complete Test Results
| note | 63c9dd84-3cfd-5546-bc0d-a7c35b06986f | METHOD: Visual , Document Review
| note | 0dca9c1a-e39a-57fe-b4cb-653a6074d2b5 | FREQUENCY: Where applicable
| note | b38bd3f5-0ca6-5031-9c8f-72ec8195e77a | CATEGORY: HP
| note | eb4feb05-008f-5e78-83d2-fa73abf69235 | RESPONSIBILITY: Nominated Authority
| note | a55ada9e-110f-59fa-821a-5330efb4bb83 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c2471059-f260-5d7a-948a-1386fbb93dca | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.5 Required strength for Grout for stressing: Plank to crosshead HD Bolt duct, Longitudinal joint between planks
| note | c47946cc-c9e4-59e5-8db7-74cac838fc16 | REFERENCE: IFC Drawings
| note | 87c3ae0b-b8d1-5952-9f20-db619766ae0b | Compressive Strength Results
| note | b50f2b2f-e9a1-5b90-84d0-ced3475ada00 | MRPA-RFI-000803
| note | 767245a3-1167-53a8-a19e-6e154d9f6897 | ACCEPTANCE CRITERIA: The transverse post tensioning force shall not be applied to a member (planks) until the grout (cementeous/epoxy) has attained the following compressive strength:
| note | 146aa2ee-5c87-5f97-8bb7-06a3e9538af3 | Plank to crosshead HD Bolt duct: of 15mPa
| note | f34cec5f-c8ed-55be-bf36-20fdbe36d403 | Longitudinal joint between planks: of 10mPa
| note | 61463665-18e7-5f0d-aa23-c62215d4f448 | Unless temporary works are in place to secure the planks
| note | c9cdfd24-0bd4-5d02-a18a-609209435e83 | Upload Concrete Test Results
| note | 9894efd1-f424-5935-99c0-fac456eb680e | METHOD: Document review, Test results
| note | 6f2c73e1-60d0-577d-8b94-47eab162b894 | FREQUENCY: Where Applicable
| note | ddda0155-7adb-5c52-adee-c8ffb83d5fdd | CATEGORY: HP*
| note | 1b2fc703-6710-5a84-9e76-01be63d9b4ba | RESPONSIBILITY: SE
| note | f7eaf317-8db1-53fd-94ba-4d8a5ec4c3dc | VERIFYING DOCUMENTS: This ITP
| textbox | 8f48e95c-fec5-572b-b801-3aa1bde4852a | Date Completed:
| checkpoint |  | 6.6 Post tensioning
| note | 2a3683a4-e277-5d29-b118-f6b3898bc2cf | REFERENCE: 612.16
| note | c9890a43-1a59-5be9-980f-eab97d05a86c | ACCEPTANCE CRITERIA: All stressing operations shall take place in the presence of the Superintendent
| note | 64dd1f81-585e-54ab-87d3-ad1c0dde59a0 | The following data shall be recorded where applicable:
| note | e36d7663-c952-52c1-bb30-a2b87734cdf7 | identification number of each dynamometer/gauge, pump and jack
| note | 508e0ad8-8125-51a5-b57d-2731ed2adcdd | identification particulars of tendons
| note | 023805cc-d15f-5994-93cf-5f05bf12afec | initial forces (or pressures) when tendons are marked for measurement of elongation
| note | f85e256c-90bd-5ac5-97c4-c5e1064743c4 | forces (or pressures) together with corresponding elongations obtained at 20%, 40%, 60%, 80% and 100% of the required force
| note | 7c373abd-dc87-5b5c-bcd1-5b298590e3f0 | final forces (or pressures) and elongations obtained on completion of tensioning
| note | 33de7edf-e846-5427-82a9-d1fb9cf2bb39 | residual elongations after release of jacks
| note | 794bfd68-3165-5718-a68e-5991557f7cad | measurement of hog at completion of stressing operation
| note | 89298193-7bd4-58b6-ba64-1970cb6330dd | the nature of any unexpected occurrences and the corrective measures taken.
| note | a0362022-835c-565b-a15d-4186b8712db0 | Completed records shall be submitted to the Superintendent on completion of stressing.
| note | 5e0abadb-4795-5184-b7b4-bacfaf154046 | Attach: Subcontractor post tensioning ITP/check list/tensioning record
| note | 97eba7aa-952a-56cf-a60e-369a592c8486 | METHOD: Document review, Test results
| note | 8daf3e6a-dc47-5fcb-9456-2124165deb27 | FREQUENCY: Where Applicable
| note | 96578082-e79a-5bda-9963-92fca2ee1fd4 | CATEGORY: HP
| note | 59ced39d-d9b9-51f0-b08e-b55eb1500ee7 | RESPONSIBILITY: SE
| note | c9e8827f-e1e2-5432-80fe-007b52d0c632 | VERIFYING DOCUMENTS: This ITP
| textbox | fb69de2d-9dd1-5ad0-ae2b-90f0fe93c071 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.7 Scabble back stress bar recess
| note | 0cab2659-1f22-5f0f-b28a-5ccd763a5eae | REFERENCE: IFC Drawings
| note | 19e644c9-88ff-551e-83ca-bd6730d1d1f1 | 612.18
| note | 4c304240-b013-5fdf-bc95-626628643008 | ACCEPTANCE CRITERIA: Stressbar anchorage recess surface to be scabbled and bonding agent applied prior to casting in situ infill grout.
| note | c0171f98-6cf3-58b9-92e0-c556f0bd9404 | METHOD: Visual
| note | b047b8f0-f287-5583-bb93-54293a31fafe | FREQUENCY: Where applicable
| note | 8882735e-96c8-5336-b066-c23123a72d0f | CATEGORY: HP*
| note | 7b769ad2-29ec-59c9-8288-d6489fb6ce6c | RESPONSIBILITY: SE
| note | 8f9c0ecc-baea-5647-9a34-114c48f2c195 | VERIFYING DOCUMENTS: This ITP
| textbox | be9d418e-3280-56d4-b67f-8c5748fa1679 | Date Completed:
| checkpoint |  | 6.8 Flowable Cementitious Grout Pour - Transvers stress bar ducts
| note | 57adcee6-cae6-50fb-9fdf-eff79d922a2c | REFERENCE: IFC Drawings
| note | 3a7a05f8-cb6d-5770-ace2-694287fbcc5f | 612.18
| note | 24401cf1-9bcf-5fe1-8379-03ddfa9e1f47 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 32 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 4c4ba214-d796-53d0-a29d-b0f5d7d38d9c | The duct shall then be pressure tested and shall be capable of sustaining a pressure of at least 0.7 MPa.
| note | 0276b714-9d41-543a-bc50-01fa83dbf409 | Grout to obtain min compressive strength of 15 MPa prior to loading planks with plant Rail & Ballast
| note | 0d0cd1b6-a65d-51cb-a443-6bad9ae4b2f1 | Complete: Grout Pour Checklist
| note | a88706cd-3c1c-55fd-8bb9-45f41b863637 | Complete: Grout Pour Record
| note | 62bac544-b3da-57f1-ac10-1434e1ea4573 | Complete Test Results
| note | 825315da-743e-5f18-80d6-b1a0eadd8428 | METHOD: Visual, Document Review
| note | b3c0ab52-0491-5823-b9f2-028736f3f358 | FREQUENCY: Where applicable
| note | 25c2866c-f097-5be9-b61c-705251937096 | CATEGORY: HP
| note | 3139bfb4-666c-58fc-aff7-c88bd32c7d12 | RESPONSIBILITY: Nominated Authority
| note | cb6ba245-5782-54df-8a3f-3d1210055ddc | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | f4b538ae-6f32-5921-af31-0305a9fe3bec | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.9 Flowable Cementitious Grout Pour - Plank stress bar recess
| note | 298e10f2-ac90-56dc-8fc4-4eecafafb472 | REFERENCE: IFC Drawings
| note | 23dc1cf6-c066-5e9a-966a-cacf27050d31 | 612.18
| note | 150d295d-7928-5111-a15a-ef503f2363a8 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 40 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 50e0857e-80ed-56aa-a964-8d810dbb8c90 | Complete: Grout Pour Checklist
| note | 041a67f1-9112-51cf-8913-555f6ca965b0 | Complete: Grout Pour Record
| note | 4a67df7d-e98c-5d0d-9aa8-cef49e27a64f | Complete Test Results
| note | 0f9e855c-50a1-56f4-9ab9-992b4336791c | METHOD: Visual , Document Review
| note | 03dcaa82-5f1a-5684-bbbf-1c630c9e0d65 | FREQUENCY: Where applicable
| note | f537e16b-9b1f-5ae8-8972-d7e4665f09fa | CATEGORY: HP
| note | 4b57ca0b-2990-5fff-8b7a-839ff54a65bd | RESPONSIBILITY: Nominated Authority
| note | c8f0107b-1aed-5312-ac08-cc3e5893df13 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b998c234-ec6c-5095-9687-77aa0d681475 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.10 Flowable Megapoxy 206 Grout Pour - Plank soffit and Plank/fender wall interfaces
| note | ee735bbf-bb14-59ef-8c4f-192ef292b9db | REFERENCE: IFC Drawings
| note | 0d702758-b9d8-56f6-9091-9ee4bb29e0b6 | 612.18
| note | 732b46df-ecdf-509f-a84b-dbb8603fff16 | MRPA-RFI-000803
| note | e51cc0e7-24b3-5655-b2cd-75e40159b7bd | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | bc8e69a0-0d7e-5282-8f51-ceb3ae10e726 | Vertical gap: no strength requirement. Horizontal Gap (Soffit of planks): min compressive strength of 25 MPa prior to loading planks with Rail & Ballast
| note | 791767d8-fa90-5f51-9682-8630f6a90352 | Complete: Grout Pour Checklist
| note | 4f674c02-fb12-5269-9202-b45db9687a60 | Complete: Grout Pour Record
| note | 45e9a08f-bd6b-5766-a1af-dd7874154e8a | Complete Test Results
| note | 634baf40-82af-5ac4-804c-66a722052423 | METHOD: Visual , Document Review
| note | 7df207d7-8702-55a8-a7c1-a8b4c8591a5e | FREQUENCY: Where applicable
| note | 97508323-6c9e-520f-a982-d9328e9a9673 | CATEGORY: HP
| note | 20266edf-95ed-501b-9ebe-4fb3071d65bb | RESPONSIBILITY: Nominated Authority
| note | 596b9e92-4a2d-5146-b4bc-3e4e8e363d1d | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 9fe1c5fc-9db4-527f-a0a9-30c1bdfa1942 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.11 Sealant - Plank/fender wall interfaces
| note | b84fe892-5377-53a6-9cfe-1b44d86d926e | REFERENCE: IFC Drawings
| note | 9214609a-97b2-5306-8587-8a50c509895c | 612.18
| note | cd28c497-79b4-5e36-a665-8a78ee95b5a9 | ACCEPTANCE CRITERIA: FINISH TOP OF EPOXY GROUT AND JOINTFLEX 15 NOM FROM TOP AND FILL WITH 50x15 POLYURETHANE SEALANT, SIKAFLEX FILLET OR APPROVED EQUIVALENT
| note | 3f42b44a-2454-5dfa-815f-13ee43e30075 | METHOD: Visual , Document Review
| note | d4550501-a0ab-5ae0-9866-53f65cf9cb7b | FREQUENCY: Where applicable
| note | 03d9632b-07c5-5587-97f1-e461a1586c2a | CATEGORY: HP
| note | f40d851e-7b21-5381-a9cd-c0d1689e398e | RESPONSIBILITY: Nominated Authority
| note | 2a493d1a-0652-5d41-a680-6761523ebed5 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 6edb822e-7116-5552-b4a1-00518a43a577 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.12 As-built Survey
| note | 5fb1af32-447e-5637-bf6e-80785587d789 | REFERENCE: IFC Drawings
| note | 312f8a4e-0119-5055-b590-d70f5fb0f419 | 610.46 (a),
| note | 3db740fb-df54-565e-ad5f-3b2148719213 | Table 610.462 (November 2018)
| note | 8cd7b5df-f247-5b7b-b2b1-d72f07c5d075 | 610.47 (a)
| note | 75bcdeca-38ee-5e1f-8f1e-0e0fd7580034 | Table 610.472 (March/June 2019)
| note | a98b6482-c107-56c9-a893-e86355278acb | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
| note | 2920d7df-1b53-5606-b2e4-7f4a40ff932a | Attach: Survey As-builts / Survey Report
| note | 39759bf8-e655-52c6-bdef-2f7d99be1154 | METHOD: Document Review
| note | ad4480e0-db32-5607-a912-dce81aff6309 | FREQUENCY: Each element
| note | 89aaa1d3-1507-5383-ab9b-c7fe9ac58894 | CATEGORY: IP
| note | 5996d6dc-46c4-584b-93b9-e148e44ee57a | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 0070ac29-1800-5c3e-b5ba-4077db6a372a | VERIFYING DOCUMENTS: This ITP
| textbox | 8a85df1d-ff81-5bc7-b2ab-41ad88aa55b8 | Date Completed:
| checkpoint |  | 6.13 Patching works
| note | 46863d23-c531-5a43-b889-4219a684330a | REFERENCE: Temporary Works Design
| note | d34abe92-e0ab-5137-b83d-26350eff2106 | 613.16
| note | 1a4ba1a2-096a-54a5-bd07-2f70f3cae3f1 | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
| note | 8df8a46f-6926-5aec-ae67-cfacbb0b2832 | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for any repair.
| note | c69e5ed3-a514-58c6-aca8-2123ef1e22f7 | METHOD: Visual , Document Review
| note | 9fddac8e-372a-59f3-b700-88ca76989e8c | FREQUENCY: Where applicable, each element
| note | d19b7e45-e019-5e4f-b5ed-e1fcf127282e | CATEGORY: IP
| note | a7b5eb36-cb82-5b4e-bed8-32b17e8f400b | RESPONSIBILITY: SE/PE/SPE
| note | c7d72a84-974a-5598-92dd-b08e9e6ceddd | VERIFYING DOCUMENTS: This ITP
| textbox | c4aa6877-b93c-5570-89c9-06358acb066e | Date Completed:
| checkpoint |  | 6.14 Non-conformance Report (NCR) Closure
| note | 47a7e940-8e1e-531e-95e2-4003cfa25776 | REFERENCE: MRPA Quality Management Plan
| note | 71567d38-6c7b-5d09-bcce-36bb911e19c5 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 29ff5107-fa07-580c-b0a3-2e6483c85192 | METHOD: Document Review
| note | 569d25b0-9980-5c4d-b2bc-2c681261b66a | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | f44c3b9f-99d0-5643-b51b-a980552d0268 | CATEGORY: HP*
| note | 068df030-372f-5304-83d5-2b8ec06db634 | RESPONSIBILITY: SE/PE/SPE
| note | 026794ba-d11a-5737-be16-a4461a002a5e | VERIFYING DOCUMENTS: This ITP
| textbox | 957220cf-e28d-5ef1-a6dd-159ca2ff5b8a | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | dca18195-a730-50d9-b44b-5c0076e730ad | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 69fba400-3a20-5998-9238-bd203c1533ad | Name:
| textbox | de42f890-bbf4-5946-8f64-8500865efc1f | Position:
| textbox | 398cc7fb-65f9-5adc-974f-d83149a354df | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Line Marking (Supply and Install) Rev 0 | itp | ITP-CIV-Line Marking (Supply and Install) Rev 0 | 518b7d44-a12c-4778-8475-bb9d040a182e
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 55a9e100-b689-4253-ab4f-01e3fd771764 | Document Title: ITP-CIV-Line Marking
| note | e94cf61c-daa6-4098-bfb5-1c25ebe21cdf | ITP Description: Line Marking
| note | 30c779bf-7b18-4e09-a7fd-f243de5f9bb1 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 3b00d9df-5f21-4d35-91f3-c0993a8b03bc | Discipline (e.g. CIV/STR/RAIL): CIV
| note | cfef6f64-aedd-4d30-9771-62268aadd8ff | Revision Number: 0
| note | f9f251b0-f79e-4828-8085-9da780c7b890 | Revision Date: 26/06/2020
| note | 8e5eef1e-06ac-4dc2-94f2-f677c094fc93 | ITP created by: Romualdo Magpantay
| note | b6a0d4db-f8a0-42ec-850c-cb679c641b93 | ITP approved for use by: Michelle Edgar
| note | c9920fc4-5e08-4541-b154-46af2833b169 | 1.1 VicRoads Section 721February 2017
| note | 07fb4fc2-63c9-469e-92eb-c4337ccf99a5 | 1.2 VicRoads Section 175November 2019
| note | 33e039f9-c3e4-4492-bb3b-1bba4caed655 | 1.3 VicRoads Section 853 February 1994
| section |  | Preliminaries
| checkpoint |  | 2.1 Accreditation to Painting Contractors Certification Program
| note | 6bdbfcfa-ea96-4b86-9f7d-bdeb4fce02b7 | REFERENCE: Vic road Standard
| note | bbff891b-e96a-4ea3-969c-5bacf56373f9 | 721.D01
| note | 9bb96dd4-e83c-45dd-8d28-11044a457f33 | ---------------------------------
| note | 4c111545-421a-4529-b931-732aacee43da | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
| textbox | 89c60dc0-33cd-4e8d-aa62-18deeb17149e | Enter: Teambinder Accreditation l Approval number
| note | 157483b3-e31e-4661-8616-131877b32ed3 | ---------------------------------
| note | 8a0076c7-ba1d-4d95-8491-ee1246c3db3c | METHOD: Document Review
| note | 9a2fbdb1-3183-4810-8934-df03355b540e | ---------------------------------
| note | b7e3604e-8b2a-4093-af1a-63b5e9a68ab7 | FREQUENCY: Once
| note | e721f021-aa1b-497e-8731-7112f5a3a940 | ---------------------------------
| note | b94a0db1-eec4-47a5-9b3f-b80aff8ff56b | CATEGORY: HP
| note | 7047b61f-aef7-4106-ae0b-5d973475274f | ---------------------------------
| note | 6380f597-4b3d-4fa7-b619-a1bdc393b502 | RESPONSIBILITY: Nominated Authority
| note | 6fc76b66-de42-4465-822e-75ff0aa3f166 | ---------------------------------
| note | 95e73d17-34c0-49a5-9f8f-f27c31614e84 | VERIFYING DOCUMENTS: ConQA Hold Point Release PCCP Accreditation
| textbox | f559e73e-c19d-4b22-b0e1-756198455e95 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Verify type of marking material as shown on design drawings and shall conform to the Standard
| note | e83e7b11-a451-4aae-8341-1218c47d32cc | REFERENCE: Vic road Standard
| note | 24411727-3731-45bf-bf8f-f44d529bb49f | 721.A05
| note | d9dd3939-061c-47fb-8cb3-7dd5e8fc1bb6 | ---------------------------------
| note | fc052d56-2870-43e7-86d6-7ff8f25018ad | ACCEPTANCE CRITERIA: Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
| note | 0095c676-2bd6-47f0-b57f-97523fd09a23 | Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
| note | 1b65ef05-5659-430f-ae88-272bda1be301 | ---------------------------------
| note | fcb5d5c1-6cf8-47b8-80a5-7c73d4d65ab5 | METHOD: Document Review
| note | c8be1da6-8655-4825-ab81-32685a21642c | ---------------------------------
| note | 93463829-7e25-435b-9265-17d6301f278c | FREQUENCY: Once
| note | 76e4cf2c-7f2c-4d17-a22a-ae5fea99abf1 | ---------------------------------
| note | f193b1be-cd33-4b93-9950-892891903fda | CATEGORY: IP
| note | fd449e31-a896-46f9-91e8-29b6a8763318 | ---------------------------------
| note | ee17551a-b8b5-4f35-bf3c-9bc65094e4f5 | RESPONSIBILITY: SE/PE/SPE
| note | 28189762-f905-4fc1-bd30-e762d7b4ac87 | ---------------------------------
| note | 1f92af44-499d-4171-bf4d-0bda02b51dee | VERIFYING DOCUMENTS: Material certificate
| textbox | ae9a5582-b47e-487a-a5af-df96778d37df | Date Completed:
| checkpoint |  | 2.3 Verify Raised Pavement Markers
| note | 356d921b-ed17-4a36-ba6c-9481b0dd6581 | REFERENCE: Vic road Standard
| note | 956e9c9a-2c8f-428c-ae5d-dccdf633e938 | 721.A05
| note | 84158f4f-b8e5-4b89-92bc-3a75475fdf25 | ---------------------------------
| note | 3e690e3e-7e46-4eb9-a1cd-7bfd458b2a56 | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
| note | 9f37c45a-eaa3-4135-8030-e6be5cc8d6e1 | Enter: Teambinder Accreditation l Approval number
| note | 55eaf976-90fd-4967-ba16-6aa1e6704686 | ---------------------------------
| note | e98a13fe-c205-4a82-a9ef-a0c28009877b | METHOD: Document Review
| note | f9d68d9b-d675-49da-85de-ec0603163a09 | ---------------------------------
| note | 0740c9ce-30be-4fa4-8a62-efc6ba894906 | FREQUENCY: Per Material
| note | a9947f4b-3879-4a87-8e88-2aca3542d46f | ---------------------------------
| note | 0b4e129a-f371-40f6-9b9e-b823fd5fcc2e | CATEGORY: IP
| note | 2801286a-3190-4a08-b76b-1af4e61e9311 | ---------------------------------
| note | 8c64dc15-5d54-4316-bb5a-b3b848dcaf7f | RESPONSIBILITY: SE/PE/SPE
| note | a108de77-ba53-4489-88f1-885d5d661fcc | ---------------------------------
| note | 291ba244-e7fa-49c7-ac8c-e8ec1ea05548 | VERIFYING DOCUMENTS: Material certificate
| textbox | 8c3dda98-183c-4a2e-baa7-9bb9f0eeda7d | Date Completed:
| checkpoint |  | 2.4 Verify Adhesive
| note | ac934b4d-0c26-4d92-a8ee-cd4e30ab76bd | REFERENCE: Vic road Standard
| note | 5fa7a2c9-16fc-4e9a-b523-406979dacb95 | 721.A05
| note | 0d67df1a-b6e0-4af5-9630-f6c39a82bd6c | ---------------------------------
| note | d930d55f-8b48-4503-af69-fca317895b84 | ACCEPTANCE CRITERIA: Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
| note | ccd25c17-16fd-4dcc-8373-a9ed32ca7210 | Other types of adhesive materials shall only be used with the approval of the Superintendent
| note | 01836004-e8f1-4b33-be6d-68520092842d | ---------------------------------
| note | 914b2394-8f6d-4b9f-b323-dd744346df99 | METHOD: Document Review
| note | c462c45a-e4f1-448c-84e3-b22ac6c956f7 | ---------------------------------
| note | fa5204ce-0b38-42f0-8891-2753389b5e24 | FREQUENCY: Per Material
| note | 1e4f2705-436d-4eb9-b1af-f5885fb3dedb | ---------------------------------
| note | e8b9cd6f-8727-4423-819f-6369425f5cc0 | CATEGORY: IP
| note | e847877b-ad9f-49e3-a593-0d1d9e93e759 | ---------------------------------
| note | 19021242-338d-4ff7-860b-ce474be3c886 | RESPONSIBILITY: SE/PE/SPE
| note | 6d2708de-3a0e-4bc5-92ac-4d02826bbd68 | ---------------------------------
| note | 5737a801-d569-4a22-a364-1bf32d8312df | VERIFYING DOCUMENTS: Material certificate
| textbox | 845e4f0b-3383-4cb7-a288-bef849b6ec07 | Date Completed:
| checkpoint |  | 2.5 Verify Line marking and Road marking Paint
| note | 93c22aee-8c74-4b07-94e9-02b02267f8c5 | REFERENCE: Vic road Standard
| note | db1d1945-02f3-43ef-9b45-e25b16f72c3b | 721.A05
| note | b0e48bce-9f36-451e-abcf-868365e294d7 | ---------------------------------
| note | 9dcd4587-55a5-4448-b9e6-432395cb3b47 | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
| note | e11ff625-7bb7-48e4-b8e5-a20a9c0718b6 | ---------------------------------
| note | 8cec277e-58ee-4bda-ad29-9ec910f17b38 | METHOD: Document Review
| note | 6018ba96-49c0-419f-8f7f-d8fe98f88733 | ---------------------------------
| note | ebcb05f5-a21b-411f-b28b-838e6604ce30 | FREQUENCY: Per Material
| note | d383b690-6c7a-460c-bf45-8a788bd33abd | ---------------------------------
| note | 8a2ffaf0-a85e-43dc-8618-1d37b23dcb63 | CATEGORY: IP
| note | 608753b2-74dc-4c32-a848-c8f20351a85a | ---------------------------------
| note | 68dd7779-4544-4841-a200-78d26462262c | RESPONSIBILITY: SE/PE/SPE
| note | 2e071350-c7aa-4d4b-8ebc-3636c1d37083 | ---------------------------------
| note | 2c7ac42f-cf58-41bb-96af-97b86ab8b2b5 | VERIFYING DOCUMENTS: Material certificate
| textbox | e03368e6-d2ab-4399-a0b1-06d351ab914c | Date Completed:
| checkpoint |  | 2.6 Verify glass beads conform to spec. requirements
| note | 94e369e4-8fb5-4de1-99f6-228f48c73c30 | REFERENCE: Vic road Standard
| note | b9e7308c-e5e7-4741-a673-ab91543ca5a8 | 721.A05
| note | 85741397-3619-4734-b5c0-9ce77380bcbc | ---------------------------------
| note | b04c872f-f5de-42fa-be2b-abd37639c505 | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042 as listed in Section 175.
| note | 7f2fa8b5-04bf-48bc-ab3d-266e8f19f3d6 | (ii) Intermix glass beads for use in long life material applications shall conform to AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
| note | 84530fdc-29a1-43ea-9311-5fdab05a39bc | (iii) The amount of heavy metals in the beads shall not be greater than that specified in Specification 0042.
| note | 16a023b1-b558-4c07-a0fb-9724fd83927b | (iv) Pristine glass beads (Type B-HR)
| note | c17b9d03-a6ce-4a4b-9eba-6acf80c862e6 | Type B-HR glass beads shall comply with the properties of Type B (AS 2009:2006) drop-on glass beads, with an additional high performance retro reflectivity requirement, requiring the delivery of a minimum 450 mcd/lux.m², when tested in accordance with a modified Appendix M* of AS 2009:2006 (described below).
| note | a8465232-414f-483a-b0d6-ebb6786e1003 | Section M4 Apparatus clause a) Dry film thickness of paint will be 200-250 μm
| note | e64ddfdd-ee18-44ab-a4b5-a2b07301e662 | Section M5 Procedure clause b) Weigh 24 +/- 0.5 grams of glass beads
| note | a2818fa8-e792-47ea-81e0-04f310335312 | Section M5 Procedure clause e) Wet film thickness of paint will be 375 μm +/- 25 μm.
| note | af966dc8-0c19-439f-a568-fe15618bd814 | ---------------------------------
| note | d628dfc4-00f5-4c0c-a59f-fd702e6167de | METHOD: Document Review
| note | 6da0ada6-c8f4-425a-bf4b-54688da6e5a0 | ---------------------------------
| note | 34934e70-da09-4425-bb4d-cc28a2b9442e | FREQUENCY: Per Material
| note | 75a3ea7c-2b34-4ad0-abb9-b6b2f9698fce | ---------------------------------
| note | cb0fc9ce-0e6e-4678-bfcb-a579f38b6394 | CATEGORY: IP
| note | 5b11dbc2-5515-45d4-a4ad-f798dae45f48 | ---------------------------------
| note | 1af0cecb-05fd-471d-b977-087d73bfe29f | RESPONSIBILITY: SE/PE/SPE
| note | b7566e42-bdcd-4431-a17b-0b7781447190 | ---------------------------------
| note | 4f8a7959-c3a6-402e-901a-58e0778b365d | VERIFYING DOCUMENTS: Material certificate
| textbox | 6a69484d-2689-47ab-942f-49a8e66238ff | Date Completed:
| section |  | Application
| checkpoint |  | 3.1 Prepare the surface for marking
| note | 0c9269b1-f85b-44b5-acf3-2ed362bacbcf | REFERENCE: VicRoads Standard 721.A06
| note | b2a8219b-18dd-4a34-b443-496f8a658813 | VicRoads Standard 721.A09
| note | 947eeeed-e884-498d-bed3-bd16560f178d | ---------------------------------
| note | 9952eb1e-b990-4dda-b6e9-c038a692867a | ACCEPTANCE CRITERIA: The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
| note | b96777d9-d763-4896-9544-7ce985d55b08 | The area around making area is also clean to avoid tracking into the marking area
| note | 166c2442-58c6-4060-9212-7bafcc763032 | Removal of existing unsound, obsolete or redundant pavement markings
| note | 9dc1779d-fcb8-4888-9790-a1c163daf64c | Removal of any foreign materials and debris within reasonable limits.
| note | 997f8911-c0af-4fab-84e5-b892d600be4f | ---------------------------------
| note | 3bed6e06-3cfb-4984-903e-63b02e9fe361 | METHOD: Measure, Visual, Document Review
| note | 72851b19-c8d0-402e-9388-7a373393148b | ---------------------------------
| note | 01207f17-45e0-4de5-aff0-461ce816b23b | FREQUENCY: Per Lot
| note | 3f5066ed-c59d-4342-ac95-112e2bff3e52 | ---------------------------------
| note | 6e67a4d2-856c-4541-bde0-70db25cd010d | RESPONSIBILITY: SE/PE/SPE
| note | f95b0f81-d25a-4498-8686-bf6b3b3fa468 | ---------------------------------
| note | fd01487a-5c0e-4675-80d5-3f9c36c05d1b | VERIFYING DOCUMENTS: This ITP
| textbox | 2c73708b-02d0-4351-92f3-fdf84d353d38 | Date Completed:
| checkpoint |  | 3.2 Set out the works for installation of pavement markings / raised markers
| note | ad9ed574-9565-424a-ac1c-da38bda5e346 | REFERENCE: Prior to commencing line marking works
| note | d3fc509f-87f1-49e4-8e0f-f0c487afdc1c | VicRoads 721.B05
| note | 3ae9b9ab-896f-41a7-83f3-f78ea31bedb4 | ---------------------------------
| note | 173c8966-e32b-4fa2-b724-5c20c140f9cb | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
| note | a5c9a364-a1ed-4e84-b358-69a24ce9bfa4 | ---------------------------------
| note | 7dacb175-f8e2-48d2-8652-0683a71addf0 | METHOD: Survey Document Review
| note | c8a14f5d-6cb1-4724-afff-f29f7b65237b | ---------------------------------
| note | 5f122e93-3410-4c39-b449-ce919ae20829 | FREQUENCY: Per Lot
| note | 0428655d-f13c-460a-b9af-1cbd5b56e55d | ---------------------------------
| note | 8abfccee-9dc1-4c3e-9471-6632087158d1 | CATEGORY: HP
| note | 26bd21b8-76da-45b0-a40f-4434f9604ad9 | ---------------------------------
| note | 94378594-bdc5-410f-8f02-336b677ec1e7 | RESPONSIBILITY: Nominated Authority
| note | 05c267ff-3f2d-43f8-8b32-c52e3b73fac8 | ---------------------------------
| note | b233f7fd-7beb-4d17-9a4e-74fc331a8c47 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 6033eb9c-759e-40c8-95f6-d0a72b6aab0f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Remove redundant pavement / unsuitable marking markers
| note | d792a396-0a20-4f4f-bb9a-be5e4815e5ba | REFERENCE: Prior to commencing line marking works
| note | 504ecd30-d717-44f5-a295-ad88d43f9f5d | VicRoads 721.A12
| note | 01e2e32e-973e-4908-944d-6a922b571b4e | VicRoads 721.A06
| note | 3936de9a-0ed5-4509-be2a-faf679aeb16c | VicRoads 721.A08
| note | 3101d135-5774-4ae3-a6f2-01bb1e3b0cb3 | ---------------------------------
| note | f1b3bcf6-1e08-4147-b512-ecbe31425a64 | ACCEPTANCE CRITERIA: Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
| note | f79b1108-9ce3-463a-af4c-b7a38536122c | ---------------------------------
| note | 246320bc-acef-4ae3-bb0d-a8b16367b9b1 | METHOD: Visual /Site Inspection & Document Review
| note | 879994e7-9ffb-47ad-b396-3bee07ebcc2e | ---------------------------------
| note | bd95747b-907f-46aa-a147-015f1463466d | FREQUENCY: Per Lot
| note | 0f79c7db-d87d-4318-9857-eb6d66eed621 | ---------------------------------
| note | 02d5e901-6cc0-4342-93f1-494e4b1aba53 | CATEGORY: HP
| note | a41a5186-9be6-4907-92f3-c77b9dd1f16c | ---------------------------------
| note | 66051b71-bed3-44c7-8337-c247cb62adee | RESPONSIBILITY: Nominated Authority
| note | 5c2bee94-a1eb-4786-9609-c4d28727a768 | ---------------------------------
| note | ed5c6172-55ec-4f1c-a803-d924ca64a59c | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 6874359e-d4cb-4991-9d2f-2c0d01936b26 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Supervise the application of pavement marking / markers
| note | 0b53fa85-9d82-4ee3-b55c-fb8885d14864 | REFERENCE: VicRoads Standard 721
| note | 70f116ca-55c5-4ce1-af19-eda2acc6f2c4 | ---------------------------------
| note | 55161b09-5b69-4c93-bc9c-4294f762e6b6 | ACCEPTANCE CRITERIA: Check conditions for application of marking paint & materials.
| note | 7b37f5a1-b1a8-4aa9-8c69-c7495187773d | (i) Paints and markers installed as per manufacturer’s recommendations.
| note | 6881a116-6193-458f-9a8c-ba2ec6ece041 | (ii) The same materials used with those nominated in the certifications.
| note | f7dca741-b2ed-4475-aa12-1cd858048127 | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
| note | 6fc3cc2a-30b3-4615-92f1-fdfb4ca9c5b9 | (iv) Verify markings are straight or with smooth, even curves where intended.
| note | 3ce5568b-af1e-46bc-b009-43cb0295ab99 | (v) Edges are clean sharp cut off.
| note | e9e26f2f-4c36-4399-965e-ae10b9f20587 | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
| note | 2da454de-397a-44f2-ae74-73b67b3be9f0 | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
| note | 723f84b1-db40-4888-a847-f4a548a03ee4 | (viii) Markings are neat & free from traffic damage or other defects
| note | 1635c5c4-e360-4b30-9a63-34fd8b18c0de | (ix) Marking protected from traffic until hardened
| note | 6c22a5bd-2ac0-4e0b-ac15-3a4220c449c1 | ---------------------------------
| note | 0954da51-ef0a-46ad-b53b-f99ed4bd04bd | METHOD: Visual /Site Inspection & Document Review
| note | 40d9a586-e902-450e-a8a3-f8e7b0a1d985 | ---------------------------------
| note | e355126e-f773-4ae1-8d5c-2e761e483e6b | FREQUENCY: Per Lot
| note | 0ba992ce-4cf3-4946-b29b-5ea4b5a232c5 | ---------------------------------
| note | 01f6f48a-d569-4adf-905b-67ff9e62a40f | CATEGORY: IP
| note | 0d7bd3ed-7e65-417d-987b-61d801e9da0d | ---------------------------------
| note | 288ee435-3bf3-454c-861b-17196e7f9181 | RESPONSIBILITY: SE/PE/SPE
| note | 701ddf0a-24b5-42cb-8067-8e18a35c1653 | ---------------------------------
| note | a3548e96-4a5b-4884-bd03-546ecf3ab7d4 | VERIFYING DOCUMENTS: This ITP
| textbox | cf2cd8f6-a4e8-4036-bd7d-bf1934f23092 | Date Completed:
| checkpoint |  | 3.5 Tolerances for new marking/marker installations
| note | b803b105-efaf-4ca1-a7ba-1097fef57afb | REFERENCE: Vic roads 721.A10
| note | bb523b0e-f391-456d-9d89-cf82e392b012 | Table 721.A101
| note | fd2c78a4-324c-4b0c-abe6-e3210f7fe235 | ---------------------------------
| note | d7a53896-54eb-4bd0-b166-761876d0b537 | ACCEPTANCE CRITERIA: Pavement marking :
| note | e82ca4ed-2951-4100-87eb-21d15b300191 | Distance between the centreline of the marking and the centreline of the set out mark-<30 mm
| note | a7aa7c9c-c591-4d14-8b41-176db2890d61 | Distance between the centreline of the completed marking and the centreline of the previous marking-<15 mm
| note | b7f4f538-e114-458e-a18f-f29dc35fcdfa | Width of completed painted markings-±10 mm of the specified dimensions
| note | d74d572b-68d1-4a56-8e60-3c1d9dd26aa3 | Width of completed markings for long life materials0 mm to +10 mm
| note | b6545c71-5363-4fc1-b95b-ba8ef42554d3 | Length of completed stripes and blocks-0% to +10% of the specified length
| note | ff9e6275-aa7e-4634-9c48-1526285026ba | Gap between double lines--10 mm to +0 mm of the required 100 mm gap
| note | 308ff071-4b76-4f77-9111-92a8e2aef6d8 | Raised Pavement Markers:
| note | 6393f930-87f5-4e25-9b65-618ef644e7e6 | (i)Markers in line with broken segments
| note | 38278e74-bac5-4f19-b297-00b89efa7e13 | Transverse position-±25 mm of the centreline of segments
| note | dc02396e-6a05-4833-95cd-f1a9bab23a81 | Longitudinal position-±0.5 m of the specified position
| note | 7ab00428-8307-4059-999a-9582edc86abc | (ii) Markers in a longitudinal group
| note | 7563c529-20e9-427b-a55e-ed8f4bd98291 | Transverse position-±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
| note | 7ab866ac-3761-49a3-93cd-29089a65468e | Longitudinal position-±0.5 m
| note | dcbb89f3-3f22-459c-bb2e-f215d112433f | Spacing of markers within the group-50 mm of specified spacing
| note | 643eb35f-3040-4421-8e80-3fd6aa2da7e7 | (iii) Markers adjacent to an unbroken line
| note | 848b49d8-4b1d-48fe-b75a-4215dc114185 | Clearance to edge line-±5 mm of the specified dimensions
| note | 98063422-6508-4626-bce5-efeea25cfe5f | Longitudinal mismatch between markers in transverse pairs-<25 mm
| note | 1414e28b-c37d-4af3-9107-7be0f01cb8cc | Longitudinal position-Lesser of: 0.5 m or 10%
| note | 0f33fd80-bad5-4550-8b2d-e3914cf1e9a2 | (iv) Orientation of reflective markers-Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
| note | f221069b-a702-4ff6-8f75-26c270d4308e | Thermoplastic profiled lines
| note | 3b419878-bba7-4d45-a8cb-11f0c817d228 | (i) Tolerances on dimension
| note | 8d6d9ff7-5cd1-472c-a037-3a492b2f3104 | Line width-+20 mm, -5 mm
| note | 63e06065-af9f-4e87-a863-b7b472aef6c5 | Line height-+2 mm, -0 mm
| note | d99d3036-2084-4d37-9f43-62f969530a93 | Extrusion breadth-+10 mm, -0 mm
| note | 6696d20d-23cc-4017-af10-9c08024e3974 | Extrusion spacing-±15 mm
| note | fb5c951a-2c2f-47c1-8166-88272d50b7ad | Extrusion shape-±25 mm at any point from rectangular shape
| note | 02820957-6851-43e7-867e-83299c458d58 | (ii) Tolerances on position
| note | 45f60550-9674-486a-acbb-4fca48348be7 | Distance between the centreline of the marking and the centreline of the set out-<30 mm
| note | d7d66a82-df44-4d31-98f1-08ca8cc5a191 | Length of the completed lines--0% to +5% of the specified length
| note | 90da85cd-f4e0-46bd-be75-64cc9b839a56 | Longitudinal position of individual extrusions-±50 mm of any previously applied profiled lining
| note | 3baf27ac-b4f4-47dd-8e24-1c9203ae054a | ---------------------------------
| note | c0d01494-5a67-487d-bfd2-df7621e949b8 | METHOD: Visual /Site Inspection & Document Review
| note | 729341c8-75b7-45c8-bf1e-b6b922adfbef | ---------------------------------
| note | f4190524-2f91-4fd8-a4be-05ac16610cd2 | FREQUENCY: Per Lot
| note | 7bfbfbc6-9ea7-46d5-a1f0-d512c1f216cf | ---------------------------------
| note | 21d71f64-99bd-48e0-9172-800384798acc | CATEGORY: IP
| note | a99691f2-2517-4e3d-a7de-70c4a805280e | ---------------------------------
| note | 0e50c782-678e-4149-a094-caed19fceefe | RESPONSIBILITY: SE/PE/SPE
| note | 16f6e9ff-7857-41ca-b63d-cf5736c04d01 | ---------------------------------
| note | 50d41a50-93e2-480e-9f29-f73179922679 | VERIFYING DOCUMENTS: This ITP
| textbox | f1edc127-cfb3-4c8e-b7fe-0f6c488d1deb | Date Completed:
| checkpoint |  | 3.6 Field test of the paint performance if required
| note | 62c9e265-14a5-403a-8c4c-94d13876bf53 | REFERENCE: Vic roads 721.05
| note | eb02d351-4d7f-45c9-b02f-6b5ac34aab46 | Vic roads 721.A12
| note | e5d02ece-ef84-4ac3-b217-a3eeae13e113 | Vic roads 721.A13
| note | 23f2cba5-26e7-45d0-915b-cdcfe7d362d2 | Table 721.A131
| note | 5f0dffac-0290-4c85-8d60-6e378c2c287c | Vic roads 721.A14
| note | ec3dafac-284d-489e-8a27-bd458fe73b81 | ---------------------------------
| note | 5a9df661-6f95-4c5f-9be4-c80c9bca6a7a | ACCEPTANCE CRITERIA: Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
| note | f22ea2e0-79d0-491e-87c4-f0bac0fb323d | ---------------------------------
| note | d26024c6-d30f-473a-b137-1efe91aeac1a | METHOD: Field Testing
| note | 941c12d8-6f77-49ef-9848-d631878ddc56 | ---------------------------------
| note | bc685c9d-6527-4615-95dc-7772156f1c90 | FREQUENCY: Per lot
| note | 6494717f-a82f-48b8-9982-247de0f0b7ba | ---------------------------------
| note | ba664e35-5a15-45c0-9f38-5192d875b108 | CATEGORY: Testing
| note | fbf33c96-a95e-4e47-890e-c8e5d345af34 | ---------------------------------
| note | 62c89bc7-d48d-4a25-a325-6a4aad9f86dc | RESPONSIBILITY: SE/PE/SPE
| note | 6b5338cd-da4e-4ec7-856f-1f9623b2c1ab | ---------------------------------
| note | 764eb769-3bdf-44e4-a28b-5cc495fb0ef0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ec886f82-6fa6-47ac-8d9c-d6abdc61dd93 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.1 As-built Survey /Drawing
| note | 0cccf8c7-80da-4207-b69a-bc476e87a0ae | REFERENCE: IFC Drawings
| note | 26388d16-8c42-46a8-9ee7-39b3f549cf9c | Vic roads 160.A9
| note | 1359c73a-2785-4997-b8c8-fc688847f980 | ---------------------------------
| note | 5cf78a97-9fcf-4d52-8da8-26c915d40e13 | ACCEPTANCE CRITERIA: As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format
| note | 6555179c-76ff-4d85-a621-528f455f7f96 | Attach: Survey As-built / Survey Report
| note | aa8b8381-c504-4cd9-9d69-f40b82fc2a05 | ---------------------------------
| note | 5d856636-0e4c-4649-80a0-1ebaaa3c57cb | METHOD: Document Review
| note | 716a222d-27af-4bf8-a190-3f3e91607eb0 | ---------------------------------
| note | 900ffeec-db12-422a-9f08-27ba5c25f8e8 | FREQUENCY: Each element
| note | c0d48934-1ac0-48b7-b3ee-300cd2a9ad76 | ---------------------------------
| note | ba5bf92a-28f0-4377-b0bc-e3a2a3d492bb | CATEGORY: HP*
| note | b958460a-e106-4427-a6f9-6ba5c933826c | ---------------------------------
| note | 9995a80b-ffa0-42a5-b04c-d06760739ea3 | RESPONSIBILITY: Nominated Authority
| note | 4a4bbb5f-dc47-4637-92bb-4566f11c1a50 | ---------------------------------
| note | 5f96628b-11a3-4ff0-9636-720a8f2e42d2 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b60823b1-d8b2-4e2a-b7dd-17a03d009f2c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.2 Non-conformance Report (NCR) Closure
| note | f892aa5c-d4ed-41db-a244-220c3ee79235 | REFERENCE: MRPA Quality Management Plan
| note | 7fb2c686-e5f4-4736-861b-2752d0ac2038 | ---------------------------------
| note | cf8cac14-713c-448e-8a9b-038663b351d3 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 797b3dfc-6632-40a9-8bce-d81cd30ec0b2 | ---------------------------------
| note | c7818cde-5fa8-4c30-bfb9-aa511f817350 | METHOD: Document Review
| note | dcb5ddc4-38b7-492e-8b28-34c199652e95 | ---------------------------------
| note | 2557e5dd-ce10-4833-a471-c3cc08bf4dc2 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | e5da5e91-19ba-4dcb-a28d-a59465085192 | ---------------------------------
| note | 9b31f068-fd7f-42ee-9632-6d34311ea402 | CATEGORY: HP*
| note | 8cc70ee2-62bf-4df5-bcb4-cc5b3ceec893 | ---------------------------------
| note | c72beef8-48f4-4d88-9f48-f6d0c1827552 | RESPONSIBILITY: SE/PE/SPE
| note | 95d9863b-dafa-4ed7-b7a8-8de87d6c7106 | ---------------------------------
| note | 898d62c7-4937-494c-a51a-888b64450ef4 | VERIFYING DOCUMENTS: This ITP
| textbox | 68e9d711-c46e-44f6-8e28-e3f4b82b2681 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | bcd3642c-fbef-46bb-bba9-3e8291ede43e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 70bf3549-4ebe-49db-a2ac-00bdce4554ff | Name:
| textbox | 0183d5a0-998c-4637-9e41-89f16426d415 | Position:
| textbox | 85d6b8ed-ef4b-46a8-bda0-c5572ae82552 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-RAIL-Rubber Modular Units Install Rev 0 | itp | ITP-Rail-Rubber Modular Units Install | 54c1287d-a709-4916-b186-3db3c96fa847
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | a9825573-fcfc-4e8a-a6c1-8b5578331716 | ITP Description: Rubber Modular Units Install
| note | f14a3a01-3359-40ce-8316-6cb224971de6 | Itp Description: Rubber Modular Units Install
| note | 81913ebf-74e5-4953-a818-76a427760178 | Document Number (In Teambinder): Mrp-0000-Mrpa-Alt-Itp-00
| note | 9604b4b8-0224-4a99-ae97-16a8b09bbafd | Discipline (E.G. Civ/Str/Rail: Rail
| note | f5bb76eb-da21-40a8-85bd-dff1023cc53b | Revision Number: 0
| note | b4538bf3-bec3-4617-bd82-3c5af9c95205 | Revision Date: 25/03/2021
| note | fff2d7d2-ed03-463f-9910-b4aa1eefca5b | Itp Created By: Mathew Holm
| note | eefaad9b-e9a3-4068-b674-4fe97e9ddea0 | Itp Approved For Use By: Romualdo Magpantay
| note | c57f66c6-62c6-4a9d-a402-11e4dbbe40cb | Special Notes To Conqa Team : Itp For All Project
| note | c3978eba-36eb-46af-9571-3aceb44cb106 | 1.1 MTSP 030100-01
| note | c4d9a6f1-93bc-436e-9208-fb6804ac88d0 | 1.2 MTST 000002-01
| note | 5d33c18d-c21d-4cee-a009-22172fb059f0 | 1.3 VRIOGS 003.2-2006
| section |  | Preliminaries
| checkpoint |  | 2.1 Obtain and submit Material Certificate of Compliance for PedeStrail Rubber units
| note | f21be305-9164-4218-a4ab-cb624a44667e | REFERENCE: IFC Drawing
| note | 76943101-d65d-4b62-b07c-38ace5221318 | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
| note | 51c628bb-4e31-4775-9b68-4ed5a0f9e024 | Attach: Photo Rubber Sleeper
| note | 8a944d30-c7bc-4868-988e-81faabf5d54a | METHOD: Review Document
| note | 6191a913-0a4a-4322-9f48-729f4a3a66e3 | FREQUENCY: Once
| note | fcd615ec-2e3f-4912-8e49-f3bc94771b3a | CATEGORY: HP
| note | 961f8102-1e93-4ad0-bdaa-c2002cd42d8a | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
| note | 9e4b2eb4-24fc-48aa-aab0-3011f9e8ec06 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ce68c3db-738d-4591-bcbf-7b29921809d3 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Obtain and submit Material Certificate of Compliance for all metal components including fitting & appurtenances(Rodding and T-Beams)Stail & accosted jewellery, Equal Angle, etc. Surface treatment compliance report/certificate.
| note | 8d2f1e40-1625-4b09-9e51-165c36b01678 | REFERENCE: IFC Drawing
| note | 0d45e816-d62e-4a3d-a20a-b4702827bf1b | ACCEPTANCE CRITERIA: No damage or rust on components
| note | 94c8c0dc-798c-4c1a-b4cb-12f976966232 | Validate total number and type of components matches drawing.
| note | 5405d918-6371-4011-addb-3116fa459174 | Attach: Photo metral components
| note | cedd5a10-0784-441f-9107-f930d04d7c40 | METHOD: Review Document
| note | d0d7d2cc-d356-4218-9437-923e61568fac | FREQUENCY: Once
| note | aa007d3d-5a82-45cb-ab41-85ebfe330a49 | CATEGORY: HP
| note | 2d446ca9-92b1-439b-a166-788fa9026e3c | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
| note | 2e058433-cea9-4b62-b45a-e447bfa67f57 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 8590d96f-b01f-4a37-becb-4bd86054ef1d | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Inspect supplied items upon delivery(Visual/dimensional inspection)
| note | 6348133a-86a3-496c-a4ca-4a9d33cfe041 | REFERENCE: IFC Drawing
| note | 5ae94736-8784-4912-9154-73050933ed73 | ACCEPTANCE CRITERIA: No damage or rust on components
| note | eab41fbe-6823-448a-9ec2-8d49e3fbfc80 | Validate total number and type of components matches drawing
| note | 8682950d-04d9-4a0e-88b1-bd84cf4b7ec1 | Attach: Photo Rubber Sleeper, metal components
| note | f0e5deb8-0459-453a-b9de-aaf14b0d2213 | METHOD: Visual Measure
| note | 493bc0c7-c8c1-4cbd-8bcd-a04e2f6d65a2 | FREQUENCY: Per delivery
| note | 21746d69-c1f3-4495-8cb4-a2441bc4ea43 | CATEGORY: IP
| note | 0c092453-b1c7-42c8-87d2-f5e3a1df4376 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | e0cc24d2-264b-43fd-a463-b6552b1d3e64 | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | af59c5aa-15d9-4625-a54e-1c609fbfe10f | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.1 Inspection of Existing Track Condition
| note | 6ccb5cb0-7c46-421b-85ea-9e2958680954 | REFERENCE: MTM Product Type Approval Certificate
| note | 2b903f40-3b3d-4f68-b5a9-c5109610b770 | Approval Certificate
| note | 38191668-ad9c-4926-a2b8-97490141bb78 | MTSP 030100-01
| note | d3624593-cee4-42ef-8b96-addddccde7ca | Appendix 1 Table
| note | efb06b9f-a1e7-4c9a-b3ad-756d3e0ce435 | MTST 000002-01
| note | 943eaba7-6430-4586-93a8-a9e6c1610483 | ACCEPTANCE CRITERIA: Correct Rail Weight (60lkg/m)
| note | fb51ccd9-ae55-407c-82dd-8ea87df92349 | Rail Defect Free (Surface/Internal)
| note | e3938ebe-7694-48b2-8adf-9701347e8cc5 | Track Geometry Defect Free
| note | 50bac4b5-b670-41c0-942f-5d37f8acf22e | Wide gauge < 12mm from design
| note | 61d8e5eb-9fcc-4987-8a3f-222ccbfa4451 | Tight gauge <-8mm from design
| note | 4794b4f6-c83b-4543-b81d-d9a53a39608c | Cant <25mm from design
| note | 55e1f94c-ce86-4c10-9594-4f45171d3210 | Twist (3.5m) < 15mm from design
| note | 50651d20-8c6b-4090-b5d0-57e8388645e3 | Twist (10m) < 30mm from design
| note | 50ecf54c-0ba7-4993-a4c4-c0fb6f897651 | Top <20mm from design
| note | 20a94077-3681-45f6-91bd-699c2dec196d | Line <18mm from design
| note | 6d7e5f61-99d1-493f-9e04-d2003ddc2b39 | Sleeper Spacing @ 600mm c/c
| note | 37da0e95-e621-437f-b257-ae45cf96ba38 | Ballast shoulder 450mm wide 1:4 fall
| note | bd10e259-e844-48dc-bbe7-24d335bd4298 | Top of sleeper free from ballast
| note | c3e0b959-c030-4e96-ac93-356612d3570b | Attach: Track Measurement Sheet, photo site photo, photo sleeper spacing measurement, photo ballast shoulder measurement
| note | 17b4d4b4-2240-4f9b-a9a2-1a18eef46dce | METHOD: Visual Measure
| note | d7f6563e-08ba-428e-a8ea-12b86627194a | FREQUENCY: Per lot
| note | a0e39832-f034-4c66-ad8b-e9cb1e20c669 | CATEGORY: IP
| note | a4095dd5-56e9-4dfb-9a76-a7e99fd3cb77 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 0b19806a-07dd-4b06-b475-3c805aab9072 | VERIFYING DOCUMENTS: This ITP
| textbox | b7881a63-7df2-47cb-b1a3-cfe5143c9ac2 | Date Completed:
| checkpoint |  | 3.2 Layout of Rubber Panel Units
| note | 7b49e2cb-3e06-4baf-b9a3-cc571a331f52 | REFERENCE: Material Installation Instruction
| note | e7f046aa-aab8-4ffa-ae5a-ed0b606a74d3 | Material Standard Design Drawing
| note | cc3422ef-7359-4888-a153-4361e676a21e | ACCEPTANCE CRITERIA: Survey Check that panels are placed in correct location
| note | 6f19de27-c160-4657-97c3-86393b3f7dc8 | Validation that components are placed in correct position (I,e outer rail panels and inner rail panels
| note | ee266bcc-857f-429f-bf45-90c9643b9872 | METHOD: Visual Measure
| note | fdd86040-dcea-43d0-9b62-131ef1ea71e1 | FREQUENCY: Per lot
| note | fc77f0a0-622e-4277-9b45-b637922d06b2 | CATEGORY: IP
| note | 996636b1-47e3-4fb9-b9ed-0e8a6a73fed8 | RESPONSIBILITY: Track Supervisor Surveyor
| note | e0d71fc8-5066-415a-937e-03ea5f2d0e4b | VERIFYING DOCUMENTS: This ITP
| textbox | 0a171e4c-bcdb-4ade-a3ed-46b357f3754b | Date Completed:
| checkpoint |  | 3.3 Installation of metal rodding and T Beams
| note | 69b9f15f-08af-42da-b703-5809b2d1daba | REFERENCE: Material Installation Instruction
| note | 3dbe1cb3-4ba0-451f-a09a-b6e27dc6008b | Material Standard Design Drawing
| note | 77976b0c-4fff-4f48-b84e-755c318e6ec6 | ACCEPTANCE CRITERIA: Correct rodding components installed through rubber panels
| note | 2504ed43-5ccd-43ea-8bab-754d98700b46 | Rodding secured and tightened to rail foot manufacturer torque specs
| note | 03874f17-7912-4940-b782-d45c63bc78c8 | T-Beams placed on flat Ballast Surface under out Stail Panels
| note | 6f2578b9-4525-4e1f-a8a4-5713cf5c1547 | Attach: photo T Beam site layout, rodding rail fastener photo
| note | b3d4f917-5e13-46d7-b5d6-1c3782f66988 | METHOD: Measure Visual Test
| note | 74cad7fb-9779-4799-a1f3-c8d7d01b3cb1 | FREQUENCY: Per lot
| note | 7b2f6cc2-1c0f-428e-a9fc-85b3b636860f | CATEGORY: IP
| note | 15222a03-d2fa-4558-ac3a-de42c6eb716c | RESPONSIBILITY: Track Supervisor
| note | e871ae8a-8b41-4a17-85fe-c12df9765f80 | VERIFYING DOCUMENTS: This ITP
| textbox | 506eac86-8c48-4811-920a-42bc7c9a7635 | Date Completed:
| checkpoint |  | 3.4 Installation of Raised markers
| note | 9436fc76-0165-4bf1-9c38-37c9e9c2c5d3 | REFERENCE: Material Standard Design Drawing
| note | adc80993-8e68-4329-8f65-fc9aff47ebe8 | TGSI Installation Sheet
| note | 8aa1d822-8b75-4046-9a0d-8f87bb1cc205 | AS1428.4 Appendix D incorp
| note | 7fcff93c-2a0e-4cc3-968f-61dd535d40f4 | ACCEPTANCE CRITERIA: String Line between pedestrian crib openings either side of tracks for paved marker positioning
| note | b8e36d63-3146-4af2-ad4b-45c1c6d8c99a | Paved markers lines layed at 1800mm edge to edge clearance
| note | 2b27d221-5929-441b-b6a9-2e1569870036 | Clear of train wheel running point
| note | c458beb7-595d-43d9-9736-8b1c8ee0ab81 | Each tile secured with 2x SPAX screws 6 x60
| note | a8876cbb-e29d-4b34-bc4b-f0c76d0efc81 | Attach: Photo Paved marker site Layout
| note | 44be059f-bd34-49dc-bdd4-202fbc1260d1 | METHOD: Visual Measure
| note | 21ffa3a0-0e24-474e-8062-028ac54529ed | FREQUENCY: Once
| note | 5aeebe4f-ed57-4680-92cd-f61c8c64d874 | CATEGORY: IP
| note | 54261230-232a-4254-93b6-2ef06fec25ec | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | f51f23f8-7d96-43ad-9279-1b399a041c0e | VERIFYING DOCUMENTS: This ITP
| textbox | 3534e94b-0e0f-4063-bac7-8989a6a787b5 | Date Completed:
| checkpoint |  | 3.5 Wearing Course Installation( Geofab, Asphalt Base & wearing couse)If applicable
| note | ae784c43-f3d6-4224-8e9c-8718db36dd68 | REFERENCE: L1-CHE-SPE-178
| note | 9d0aa3c7-4833-4ddb-9a9a-178224d18fd6 | L1-CHE-STD-029
| note | a6318698-c2f8-4287-9a89-4628403a5e90 | VRIOGS 003.2-2006
| note | 4da31883-a551-4845-ba40-029aef4acf19 | ACCEPTANCE CRITERIA: Surface Smoothness
| note | b1f04ff2-f8ed-40d5-a69f-a704df7df4e1 | The path is to be durable and maintainable asphalt, concrete, rubber or equivalent. It shall be free of potholes with a non-slip surface with levels no greater than ±12mm from the design plane when constructed
| note | 6a47a50c-e991-4121-8354-419dfc60cfb5 | METHOD: Visual Measure
| note | d28ca8f6-bbce-4108-9ee0-fc2f430677d2 | FREQUENCY: Per lot
| note | 94c3b82e-a395-4d34-9c38-b52e6c1c4ab4 | CATEGORY: IP
| note | d43380f3-0f06-43d4-9a6e-56adc33dce31 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 65e82915-5d48-4c54-97ab-c9aef0445993 | VERIFYING DOCUMENTS: This ITP
| textbox | b0d07964-2e6f-4fe8-b5bd-1382ad2c19e9 | Date Completed:
| checkpoint |  | 3.6 Others Installation if Applicable(Access track, Gates, Bollards) If applicable
| note | 4534f8f4-cb94-41e4-a29b-3e0dd2ceb2ce | REFERENCE: Material Standard Design Drawing
| note | bda09dde-045d-4788-900e-71d5070eeded | TGSI Installation Sheet
| note | 2afd1182-282f-4d74-935b-2598cdd8601d | ACCEPTANCE CRITERIA: NDD foundation or equivalent Design requirement.
| note | 213d86c3-88e6-45b4-9e7e-24af702360c3 | METHOD: Visual Measure
| note | 17119fa6-bbba-4595-95b3-b233db7ee72f | FREQUENCY: Per lot
| note | fc6ebb61-6fb2-41b1-ab74-e34712922894 | CATEGORY: IP
| note | b9eb7283-29a8-4122-ba45-13a26d367aa2 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 0fa81651-e54b-48b0-98d8-76b3a028217e | VERIFYING DOCUMENTS: This ITP
| textbox | 929c4e4c-1708-4bfa-ae94-002ac4090716 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.1 As-built Survey
| note | e51a610b-18e1-4cfb-b72c-0053c051d314 | REFERENCE: As Built Drawings Asset Change form
| note | 6c82edc0-44e1-49df-a839-e78a946d14d6 | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction Attach: Survey Report, Engineering Asset From
| note | e6f60af1-9a39-4c61-b90b-9077db87d4d0 | METHOD: Survey Document Review
| note | d142b5bd-0d98-4b87-8968-78ca09b94a49 | FREQUENCY: Per lot
| note | e7cbb49b-75cb-4ca1-b383-50affd317866 | CATEGORY: IP
| note | e25faa9e-2322-43b1-8111-56b2eeb8f8c1 | RESPONSIBILITY: Surveyor Site/Project Engineer
| note | 4ad6a6ca-9e96-4f14-b821-8399efd38b2e | VERIFYING DOCUMENTS: This ITP
| textbox | 86869d59-9354-4027-aa06-5859775fa0c7 | Date Completed:
| checkpoint |  | 4.2 Track Certification
| note | 5d25addc-5a77-4f0b-acc3-776d33179d99 | REFERENCE: MTMF020000-1 – Track Form A T
| note | 36a5fe92-37e1-4353-99ae-d504a67f9a2d | MTMF020000-2 – Track Form B
| note | 7e5fc53e-8e68-48a0-8d97-b133e2a20932 | ACCEPTANCE CRITERIA: Attach : Track Geometry Conformance Certificate
| note | 5de741b1-4aa4-4abc-9954-ad3445df2ef7 | Attach: Track System and Component Conformance Certificate
| note | 49d2fa65-0902-44df-8be7-be0a890579f0 | Attach: Before/After Photo of worksite
| note | 7e411c26-7602-45ab-bd27-81672621d0a2 | METHOD: Visual Measure Document Review
| note | 7514d328-1578-489b-bf70-5fe671c05922 | FREQUENCY: Once when all occupation works complete
| note | 6eb6504b-7000-4e4d-bd2c-bd86342f6caa | CATEGORY: HP
| note | 73201a28-d4df-4bd1-a046-55e10216e2f6 | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
| note | 46f00a92-c6e3-4753-b017-58ed601a8e55 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 1fc3fd7c-5156-4773-8dbd-3e32673e51df | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 2f373078-5b64-4ea0-96c2-2ccdfd486b7f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 41783849-48d7-457e-a243-8715e425d886 | Name:
| textbox | 76cbea5e-11a9-4890-b29e-2076a822be18 | Position:
| textbox | e5c0c24f-7a05-4521-897c-f94da3f83f5f | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Temporary TL3 Barrier (Supply & Installation) Rev 0 | itp | ITP-CIV-Temporary TL3 Barrier (Supply & Installation) Rev 0 | 571eb8ca-35f8-4f36-ba2a-213a998a367b
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 74d089bc-35ac-4477-bb4b-ad763516daa4 | Document Title: ITP-CIV-Temporary TL3 Barrier (Supply & Installation)
| note | 6ea8e4e1-835f-440b-b9e2-068b612f32f8 | ITP Description: Temporary TL3 Barrier (Supply & Installation)
| note | 71e08336-65b5-463a-8142-ea83eaf840c5 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 66f15aca-919f-48d1-8520-48dc0997a65e | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 95a34853-b8a6-4a9d-b624-b7c18986083e | Revision Number: 0
| note | b3763420-8a01-401e-b6f1-85261f7e61c6 | Revision Date: 7/07/2020
| note | 658dab78-2042-48c2-a6b7-d3a2a85e168a | ITP created by: Demson Manafi
| note | 2e3aa0a1-3435-4e59-ac14-b9461938c598 | ITP approved for use by: Mike Freeman
| note | 12c6fdbf-7139-468f-9e77-25de0874890e | 1.1 VicRoads RDN 06-04 March 2020
| note | c75baff3-ae1d-4e61-8051-ec044a85c71c | 1.2 VicRoads Detail Sheet HighwayGuard Safety Barrier - Temporary April 2020
| note | 3e12db82-7269-45fd-9bb5-b032a33d9448 | 1.3 VicRoads Detail Sheet QUADGUARD-M10 Crash Cusion April 2020
| note | 18210929-e3e7-41ef-9c5d-b44e107f38a7 | 1.4 HighwayGuard LDS Australia & New Zealand Product Manual September 2019
| note | d2615551-7fba-4249-b395-5aebafb0b05f | 1.5 QUADQUARD-M10 Product Description Assembly Manual November 2019
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Barrier Component Approval
| note | a851d34e-bb86-4da4-8f6c-ec604e5f2a42 | REFERENCE: VicRoads RDN 06-04 March 2020
| note | 117f4c69-54ee-443c-bb9f-5cc99a8dc77b | ---------------------------------
| note | 2448180e-9f0d-4172-8fbb-3429b13b4fbf | ACCEPTANCE CRITERIA: Barrier components and end treatments are on the Accepted Safety Barrier Products list.
| note | 65d98602-2096-4597-9e0e-677c1892a72c | ---------------------------------
| note | 16677731-c2a4-4e1d-ad1a-36d2ffe84c05 | METHOD: Document Review
| note | fcb91a5f-96df-47ae-98a1-c59f81b03048 | ---------------------------------
| note | 3afe8b68-e777-49d0-bc86-b56fd39c7eab | FREQUENCY: Prior to starting Works
| note | d3bd860a-7402-402f-b32e-d77fcb919d73 | ---------------------------------
| note | 0e931a23-2c12-478a-98db-a65afceafe57 | CATEGORY: HP*
| note | 34086385-5abc-452d-bcc4-3dc8d2f2bc4a | ---------------------------------
| note | 0705cd2e-9fda-4b4a-ac65-e3f1ce4039c4 | RESPONSIBILITY: SE/PE/SPE
| note | 2cc0ac5e-995a-4a74-926d-b4fc48b701a4 | ---------------------------------
| note | d844caef-915e-4775-81c2-98a6f65865e3 | VERIFYING DOCUMENTS: This ITP
| textbox | 3ecf0bca-0e36-4332-a309-3ed3c24e33e2 | Date Completed:
| checkpoint |  | 2.2 Chem-set Epoxy Material Selection
| note | 4b10a171-ea64-4a7f-a885-253b7b457df7 | REFERENCE: Product TDS
| note | d50593b4-1c2c-4f94-98b5-249f8d61b57c | ---------------------------------
| note | ce1299ea-d5da-4571-9369-815e63c9673a | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | 8ecfa8a0-675f-4e6f-87d2-13e23d76c166 | i. able to be used to secure M20 & M24 threaded rod into asphalt and concrete
| note | 1cbd5be1-886b-4694-8485-b86e7c80feb6 | ii. able to be applied within the temperature ranges applicable to the site conditions
| note | 66821a5e-d5a8-4d64-9a0b-88f6c8a4e88a | iii. able to be cured within several hours to allow for testing
| note | dc4f38b1-9761-4244-9972-2abd174750b1 | Enter: Teambinder Material Approval number
| note | e7e5b3c0-2892-49b1-9edf-7807d02fca29 | ---------------------------------
| note | 6fdafbb8-65f3-4885-bc86-b350ac71a5fe | METHOD: Document Review
| note | 9d7fd951-c90f-4246-bf7b-d8fc782b5156 | ---------------------------------
| note | f97b74ea-493a-48c3-b5d8-6989bb965c5a | FREQUENCY: Prior to starting Works
| note | 8f2bb1dd-164e-4388-a6ad-bdecef969982 | ---------------------------------
| note | 546dd7b6-27a0-4a9b-91dc-a17ba72170b6 | CATEGORY: WP
| note | 4857258b-27c7-4939-8ef5-71963302afbc | ---------------------------------
| note | 4da6e3d6-f0f7-419f-9649-d1c3cda2b7ff | RESPONSIBILITY: Nominated Authority
| note | 3ddfab32-11a3-4fd6-91bb-374f2c1c60d0 | ---------------------------------
| note | 0074f687-a723-4497-b2e0-d54e1a058148 | VERIFYING DOCUMENTS: This ITP
| textbox | 2c1352cf-623c-456f-8267-5de790390014 | Date Completed:
| checkpoint |  | 2.3 Threaded Rod
| note | 0a32c8c4-5e15-4a52-bd86-f67e27cc43e0 | REFERENCE: HighwayGuard Installation Manual Page 17 of 23
| note | 64b61b41-013b-49bc-b2b5-342643707a3c | QUADGUARD Installation Manual Page 16 of 43
| note | 4c152882-b6cf-4975-a4a0-c8c51adccd24 | ---------------------------------
| note | 08c46512-b1a3-4609-92f7-0c0904e8a318 | ACCEPTANCE CRITERIA: Threaded rod must be 8.8 grade.
| note | 99e97f28-b830-4870-8a79-84fe1d821feb | ---------------------------------
| note | 159b3826-0c06-4e5c-9a7f-626713769aeb | METHOD: Document Review
| note | 4269e1c3-f5a6-4969-8e1c-da82d8fbb5dc | ---------------------------------
| note | 4c3c1fd3-fb11-4b9b-9a1d-e201f79440d3 | FREQUENCY: Prior to starting Works
| note | 57659a16-fec5-4c2e-9cfb-389e8558d322 | ---------------------------------
| note | 2771c70b-9e6c-4b7a-b72a-aa306e780efc | CATEGORY: HP*
| note | d8e3bb3b-94cd-4ec4-90ec-9c0062afb395 | ---------------------------------
| note | e3d428d1-3bf9-4929-ab77-df384618e64a | RESPONSIBILITY: SE/PE/SPE
| note | e271a38a-4f75-40d3-8247-c449ddfbd050 | ---------------------------------
| note | 7feb3cb0-5830-4cf0-9e32-a961a84ad488 | VERIFYING DOCUMENTS: This ITP
| textbox | 23e0eee4-5d0c-4e82-8aac-0cb24b88acec | Date Completed:
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 IFC Drawings
| note | 4bcf45bf-883e-481e-b428-761cd7272374 | REFERENCE: MRPA Quality Management Plan
| note | 9bef8eb6-1049-4042-b143-971ef658ed07 | ---------------------------------
| note | f610065a-84ed-4341-acdc-e4b5960de5ce | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current
| note | e22d9bd6-83b2-45ce-afff-3432e55721a1 | ---------------------------------
| note | df16f89e-d294-4ca9-8aa3-e6141788c396 | METHOD: Document Review
| note | 2d6e7c77-dde4-4903-b7dd-d7d5ff6e5d6b | ---------------------------------
| note | 1aa94d84-330e-423e-bb4e-271b51c82c3c | FREQUENCY: Prior to starting Works and at regular intervals
| note | 8dabb4ec-052c-4af5-ba06-773a1c6bb5e2 | ---------------------------------
| note | b3a9ebca-7650-4134-a0bc-c9738ef77219 | CATEGORY: HP*
| note | 1cb02543-617e-43a2-b704-d18c6ac07554 | ---------------------------------
| note | 01352bfe-9270-46c3-9d3b-52c8208780f1 | RESPONSIBILITY: All
| note | 45b2b497-0f15-43b2-b913-4eed05a798ed | ---------------------------------
| note | 1188137e-dd94-4a3c-b32f-d3c38f8610ca | VERIFYING DOCUMENTS: This ITP
| textbox | 442dd413-befc-42fb-b715-e1b61d0a6637 | Date Completed:
| checkpoint |  | 3.2 Survey Set-out
| note | 050ff5f2-9e0b-4336-8fc3-7614dc1b9ea9 | REFERENCE: TMP / Alignment Drawings
| note | 401a7018-da1a-47ca-b8f4-7d2f895d9bf4 | ---------------------------------
| note | 3e9c014a-c4d6-46a7-99ec-e36a6a483b60 | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location and alignment requirements as per IFC TMP drawings.
| note | ffabe19c-bbcb-4fd0-ab8b-37ab2f12b43d | ---------------------------------
| note | 14d600df-87f3-42a9-9607-8004d73834cb | METHOD: Measure Visual
| note | fab9a505-838b-4dcd-88de-295be7f80823 | ---------------------------------
| note | 9265b3c1-138c-4721-ba46-e78cf3b7c712 | FREQUENCY: Each element
| note | 361bebab-dbe3-4cd4-a1d9-531687986dce | ---------------------------------
| note | d8bc19b5-9425-4b0a-b941-7df73f081398 | CATEGORY: IP
| note | 1ed20bf2-c79b-495b-b20d-756f50f8489c | ---------------------------------
| note | a91e17a4-ab20-4e32-bebb-b48bff368017 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 1b117f9f-3cb4-4c34-8d7b-4fc16a04f715 | ---------------------------------
| note | e7fe25ea-7e92-4353-9c3a-1be0265d4fbf | VERIFYING DOCUMENTS: This ITP
| textbox | deaf865e-9544-4d63-a916-70c1935d8de2 | Date Completed:
| checkpoint |  | 3.3 Site & Substrate Conditions
| note | 37e24ff9-0125-45df-98cb-fe42669c0ecf | REFERENCE: HighwayGuard Installation Manual Page 10 of 23
| note | bae15fdf-eab9-49a0-bf8e-9133ab1cd3aa | QUADGUARD Installation Manual Page 15 of 43
| note | e59910bf-2d76-492c-b957-6f7d9220f91d | ---------------------------------
| note | 40ec09d8-f48e-4fc5-9c19-1edbe1206e58 | ACCEPTANCE CRITERIA: Barriers & end terminals shall be placed to the following requirements:
| note | dfba19ef-4376-48c1-b419-4fedfbd5b11c | i. Foundation = 150mm minimum asphaltic concrete over 150mm minumum subbase, or
| note | 725627b2-c3be-4edb-81c4-b379750b7361 | = 250mm minimum deep lift asphaltic concrete
| note | 2523f75a-98dc-4ad9-bdb2-8f3a74b8d5b3 | ii. Cross-fall = 8% maximum
| note | 3e3fa330-0fc3-4761-847f-61c43a8afb82 | iii Differential cross-fall = ±2% maximum along the length of the QUADGUARD system
| note | b6d40e66-6619-4db3-a3ff-bd0c45e0fec9 | iv. free from obstructions within the deflection zone
| note | aff165e1-3f84-4dc9-a612-91eb9bc04fb5 | v. have a minimum 60m length between end terminals per barrier run
| note | 1195adc3-2b63-4a30-ba4d-2d1ce7c46dbe | ---------------------------------
| note | 93ad0c42-de43-42fd-b21f-cfb57929a2ec | METHOD: Measure Visual
| note | 255a2b89-1982-444d-b957-e7218003af0b | ---------------------------------
| note | 146303d3-de51-4808-b393-01012b3465c4 | FREQUENCY: Prior to starting placement of elements
| note | d24237fd-f53f-454e-9e8f-64c818e26b36 | ---------------------------------
| note | 22482559-3b8b-4aa9-86e7-5e8b38b9fd47 | CATEGORY: IP
| note | c0a09766-efd4-4ab4-b2bf-819d2d705351 | ---------------------------------
| note | c20be202-3ee9-4dbc-a5e3-5ba020e13c7e | RESPONSIBILITY: Surveyor SE/PE/SPE Foreman
| note | 55e43d54-a633-41b5-82da-12df002365d5 | ---------------------------------
| note | b25b41b1-a636-433d-9e45-4cac193f6a8c | VERIFYING DOCUMENTS: This ITP
| textbox | bf3a2953-a919-437c-a83d-d31147261fb7 | Date Completed:
| checkpoint |  | 3.4 Materials Inspection Checklist
| note | 0b1789d6-23a9-4515-a405-485d30831e2d | REFERENCE: MRPA Quality Management Plan
| note | 3fcc36ae-a6ee-48e9-8acc-6c2265854b05 | ---------------------------------
| note | 2c871546-6f12-4b27-b1a3-d90202ecad13 | ACCEPTANCE CRITERIA: General inspection to ensure that all components match the requirements for the system, all parts have been received/deployed to site and are in a workable manner.
| note | 13091af6-67ab-4713-8acb-f97b3f1211cd | Complete: Materials Inspection Checklist in ConQA
| note | df5bb86e-768d-4e04-97d5-d9d9189ccf65 | ---------------------------------
| note | aa67ca07-92c5-4042-b5ec-6ccd97d4adfb | METHOD: Measure Visual
| note | ae233011-ead7-431f-b2a1-5d283f0e2a63 | ---------------------------------
| note | bba808a3-50e7-4ea8-8e6f-51674b03a4ff | FREQUENCY: Each element
| note | 21bc5515-8d8a-42c2-b70c-e0bc3e913007 | ---------------------------------
| note | 279f23e7-bf59-4a9e-9cf0-f3c6d1ade6a7 | CATEGORY: IP
| note | 31df8e26-f575-4150-a3bb-12c903d19146 | ---------------------------------
| note | e45cd6aa-659c-4c6c-87f4-0c180a8b3e00 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | e6b20f6b-815e-4ae3-bca0-e4a99745cff9 | ---------------------------------
| note | 8a437f57-41b8-4943-afab-972b38a5af45 | VERIFYING DOCUMENTS: This ITP
| textbox | 4d2644ea-8da3-4193-95cd-759b757c5add | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 4.1 Barrier & End Terminal Handling
| note | 84823770-86b5-4a5b-94ce-7c084bd63c0b | REFERENCE: HighwayGuard Installation Manual Pages 11 - 12 of 23
| note | 07b789aa-c15a-4154-a644-0b9503d56395 | ---------------------------------
| note | ae98fbff-347b-4cde-a711-7e0470f6e543 | ACCEPTANCE CRITERIA: Handle barrier components by nominated lifting points only using suitably sized chains or slings to prevent damage.
| note | 1fbed4e2-1584-433f-8741-0d71a01ce17e | ---------------------------------
| note | 0f86ecc9-192c-43d7-ae15-4eb82c9685b4 | METHOD: Visual
| note | 059b68b8-c77b-4618-8aee-2ce1a782d652 | ---------------------------------
| note | daa181a3-b194-44d3-9ac5-84718f5b4d62 | FREQUENCY: Each element
| note | e4375d7c-8e9b-4d5a-b0d2-5143ceca3817 | ---------------------------------
| note | 7fbe8efc-8ecd-41d0-9eb3-9a24c44f3dfd | CATEGORY: IP
| note | f4800877-a793-48b8-8cc7-e78d0e6537b8 | ---------------------------------
| note | a254089a-e395-4425-917c-5610e532b297 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | 7cac279d-73d8-45d5-bb2c-23b3d84bce65 | ---------------------------------
| note | 23bc8bf2-dd8d-4341-9765-c02dae6979b6 | VERIFYING DOCUMENTS: This ITP
| textbox | cb6e66ed-1382-4882-bd36-fecb4b33c1d0 | Date Completed:
| checkpoint |  | 4.2 Barrier & End Terminal Placement
| note | 48afbeee-2b81-41a3-b073-50c61e657ad4 | REFERENCE: TMP / Alignment Drawings
| note | 5820bd87-043b-4a0a-ac5b-27e3a8081439 | ---------------------------------
| note | 7e1cb111-4b73-4f39-b716-51dca6a33ff2 | ACCEPTANCE CRITERIA: Locate barriers as per survey set-out.
| note | 99c45c74-91c5-4e04-bc15-d1dd9cfa59e0 | Minimum 300mm offset from edge line of adjacent trafficked lane.
| note | 7a3dce29-e370-4259-8b82-e1b60d5297be | Selected barrier T-connector and/or angled barrier for required horizontal/vertical radii.
| note | 21463bcd-4a30-4d80-89e2-f5401e485462 | ---------------------------------
| note | ec832092-814e-42ec-b1d9-76118310a338 | METHOD: Measure Visual
| note | 91c8d2b9-fdb2-4343-891a-72e1fcbce184 | ---------------------------------
| note | ed1e1757-7efe-4798-9b58-60ebaba275c4 | FREQUENCY: Each element
| note | 7b336dc8-a2d2-484e-98e7-81d7a6b6e76a | ---------------------------------
| note | ebb6d8eb-5cce-4a0c-8223-2c5ff7095caa | CATEGORY: IP
| note | 727fb534-5732-4d7c-a80d-5332cebf078e | ---------------------------------
| note | 265910e8-3438-4b73-834f-7afe1759aff2 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | 80199790-e5e6-44c5-bea7-5dee1b094a25 | ---------------------------------
| note | 1a1f802d-6ff4-4bc0-ad05-493ce17c17d9 | VERIFYING DOCUMENTS: This ITP
| textbox | 390a0423-9f47-434d-890d-960e9f8c24e7 | Date Completed:
| checkpoint |  | 4.3 Barrier Connection
| note | 49f14ff4-0650-4be9-8149-43ba1dc47f11 | REFERENCE: HighwayGuard Installation Manual Page 13 & 23 of 23
| note | a31f0eab-15b7-4b77-a579-4e1f15c79516 | ---------------------------------
| note | 2d9943ed-0719-46fc-be8a-475d61bed83c | ACCEPTANCE CRITERIA: Secure the Quicklink security nuts to connect T-connector to barrier length to snug-tight condition.
| note | 2d96917b-8cc3-4711-a2b3-9b188ec2b094 | 10mm maximum mis-alignment to prevent snag-points.
| note | 00fb89ff-17b5-4fce-9fee-3abeb44bea63 | ---------------------------------
| note | 63ab7dee-df25-4199-9f89-e11afa3a444b | METHOD: Visual
| note | 52611153-275c-408f-8d3e-f7682c409ac6 | ---------------------------------
| note | 4e985033-27c6-4a43-8e7e-7da06bf620bc | FREQUENCY: Each element
| note | 37cbf905-f052-4ca7-89c8-c846272a2b38 | ---------------------------------
| note | 1cb57c96-098c-4cc8-adba-de8cd366841a | CATEGORY: IP
| note | 7a1d2037-a34f-408b-967a-d6b5b0863e73 | ---------------------------------
| note | 5498b10f-4fcf-4a13-8feb-3b6ad69f3219 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | 8f8f21a5-1897-49c5-84f6-1865713515ed | ---------------------------------
| note | 34de8c5b-ebb8-494a-babb-654eecb3cba2 | VERIFYING DOCUMENTS: This ITP
| textbox | c9eab3c8-3896-4e11-a469-6f8b44e1d8bd | Date Completed:
| checkpoint |  | 4.4 Installation of Anchors - Barriers
| note | c59aa8ab-4b9c-4e98-b8d3-c05fa3748017 | REFERENCE: HighwayGuard Installation Manual Pages 14 of 23
| note | c9bdb679-39ab-4cb6-b526-f22ce247b76e | VicRoads Detail Sheet HighwayGuard Safety Barrier - Temporary
| note | bf6461ec-abb0-4dd8-8ce2-b0cc779eb7fd | April 2020
| note | a46e4a0d-d235-40a8-9632-0640c03a74df | Epoxy Product TDS
| note | 96fc16f6-f5ac-441e-9165-1dcacb19bc72 | ---------------------------------
| note | e351e3d9-dbb5-4d44-af60-5c14679fa3f5 | ACCEPTANCE CRITERIA: Position 330mm long M24 8.8 grade threaded rods:
| note | c2092879-4af8-4e97-8570-67a922eb5c4d | i. 6 no. at the start and end of the barrier run (3 per side, per end))
| note | 200c54d5-ce53-48c0-ab48-7ce218c1c23c | ii. 2 no. at 12m maximum spacings, staggered across each T-connector (1 no. per side, per 12m)
| note | e574855f-e13b-4386-b3bd-6934e3e21ac7 | Using an 28Ø masonary bit, drill a 300mm minimum depth hole into the substrate.
| note | f2d730ba-7cc9-4270-822b-be657da51792 | Blow out the holes and inject/pour the epoxy into the hole.
| note | 2068e2b4-c5fe-492a-8160-488101c20eae | Wind a nut onto the threaded rod, making the end flush with the top of the nut and place a washer underneath the nut.
| note | 8644be85-6462-42e0-9683-1284e8f772af | Place the threaded rod into the hole, rotating as the rod enters to ensure full coverage of the thread until the washer has made contact with the barrier base-plate.
| note | cc8b0d4a-fa3c-4616-9836-ecfc97096814 | Note: Threaded rod lengths above are based on an asphalt substrate - see the installation manuals for required lengths into different substrates.
| note | 79d557b7-f329-4664-ab7e-dabf702b1fc9 | ---------------------------------
| note | 2f1aad99-6fcb-4a61-b64e-8d4500b14231 | METHOD: Measure Visual
| note | 97fee2dc-6fa5-48f2-b005-2459f3c82d8c | ---------------------------------
| note | f199ff4f-995b-4f86-8ab2-5461ad1a3d46 | FREQUENCY: Each lot
| note | 7f54b2a0-eb3d-4d9b-a21a-80e41e4092a6 | ---------------------------------
| note | 16ffd941-36ea-44a6-a871-50541edf219c | CATEGORY: IP
| note | 2b0018dd-e4e4-4ee7-ab3f-b082bc4f3174 | ---------------------------------
| note | 2f8d99b6-b145-4308-84eb-c66253bf2ad1 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | ef32e509-e0e7-4a3f-b158-208c22a315ea | ---------------------------------
| note | 5ddd03fb-64f6-474d-bd7a-60d6ae118d66 | VERIFYING DOCUMENTS: This ITP
| textbox | 00db3020-9016-4ff3-a51d-57acd386529f | Date Completed:
| checkpoint |  | 4.5 Erection of Gawk Screens
| note | 6ad3ca8f-6766-4bad-8d10-049d4d12a542 | REFERENCE: Product Drawings
| note | 9b885c87-045d-4c6d-9e77-8d6966500205 | TMP / Alignment Drawings
| note | 090f01af-e384-4e97-ab19-7e8a850da29c | ---------------------------------
| note | 3789e461-88b0-4191-ab53-e8c9a4a6bbe1 | ACCEPTANCE CRITERIA: Where applicable, erect the gawk screens as per the standard drawings.
| note | 63b4ec9f-bb05-4ce5-baef-dfcda9376031 | Securely fasten the bolts to snug-tight condition.
| note | caa96aea-ac9e-419f-a431-8e52170b55c8 | ---------------------------------
| note | 7aa90f0b-1a59-45a0-a566-cdcead54628d | METHOD: Visual
| note | 656280ee-cef3-443a-bbcd-29f70987b552 | ---------------------------------
| note | 09f3a39b-8b07-49d5-af12-39120877f107 | FREQUENCY: Where applicable, each lot
| note | c1e8efb8-386b-4766-91b4-8b61b451974b | ---------------------------------
| note | 562422f0-36eb-435d-aecd-d180a3b9a8d6 | CATEGORY: IP
| note | 2d35474d-1073-466c-847f-6d7240a2e70b | ---------------------------------
| note | 26690ba4-5b91-4684-bd3c-58862321a381 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | 470cadf3-1b54-41f6-8aed-89dc411ff06f | ---------------------------------
| note | 8b7b0a7e-cce4-41d0-878b-f9e70d358a72 | VERIFYING DOCUMENTS: This ITP
| textbox | 6743fe12-a8db-4739-bc3a-d3de6adffda8 | Date Completed:
| checkpoint |  | 4.6 Delineator Attachment
| note | c626cad7-4710-4d31-926f-a47348aee6ca | REFERENCE: Product Drawings
| note | 0036e7b0-2c51-4e45-8082-4cc66e9c7eb5 | TMP / Alignment Drawings
| note | 69bb7c25-1520-434e-8ceb-89225bd183e3 | ---------------------------------
| note | dd1ba250-9b36-426b-b4e9-6f43227970d5 | ACCEPTANCE CRITERIA: Where applicable, attach delineators so that the correct colour is shown in accordance to the traffic direction of travel and ensure that they are fastened to a snug-tight condition.
| note | 9419fbdd-d341-466b-8c68-e74d7ed52a45 | ---------------------------------
| note | 85ad9110-5bb6-4952-9e33-fef5808b773a | METHOD: Visual
| note | c7dbf7b5-1490-41ec-8a67-5b4c8d9af636 | ---------------------------------
| note | 1008794f-a6d2-4f9c-860f-c0c009175e3d | FREQUENCY: Where applicable, each lot
| note | 31c6349c-d956-4ff2-8baf-1c661bf13e45 | ---------------------------------
| note | cf63b40b-66d6-4e3f-82ce-f40921e5ccb2 | CATEGORY: IP
| note | 9d7e571f-ae50-46f9-b9df-43daf0accea5 | ---------------------------------
| note | 30a72f55-5678-4432-9be6-207af5015edc | RESPONSIBILITY: SE/PE/SPE Foreman
| note | 92d6596a-2522-4e0e-a0cb-0eb0350c4bdf | ---------------------------------
| note | 8f12072c-9f12-4912-adc0-dfac2575d852 | VERIFYING DOCUMENTS: This ITP
| textbox | b50e18bb-aac2-4b09-a282-c566144db65c | Date Completed:
| checkpoint |  | 4.7 Installation of Anchors - Test Anchor
| note | aca3b39d-67f2-480c-a2cd-9cb9cb5cc880 | REFERENCE: HighwayGuard Installation Manual Pages 17 of 23
| note | c6cb7af9-0d2b-44c8-aa02-4ba2fa47cd78 | Epoxy Product TDS
| note | f76149e3-b29d-49a9-a8b2-cc70de44667e | ---------------------------------
| note | 467abbae-6c52-4c52-8a37-2a362bb2f60e | ACCEPTANCE CRITERIA: Position 1 no. 330mm long M24 8.8 grade threaded rod into the pavement behind the barrier defelction zone.
| note | d569c4ab-516c-483a-941f-ba5e723a69c3 | Using an 28Ø masonary bit, drill a 300mm minimum depth hole into the substrate.
| note | edda8efc-0769-41fd-904d-a1a751c8c83a | Blow out the holes and inject/pour the epoxy into the hole.
| note | ec112ef2-212c-406b-abee-09f647921a6e | Wind a nut onto the threaded rod, making the end flush with the top of the nut and place a washer underneath the nut.
| note | 7cf857df-3285-4550-bb74-66d5aaa3bc85 | Place the threaded rod into the hole, rotating as the rod enters to ensure full coverage of the thread, leaving 30mm minimum projection to connect the pull-out jack.
| note | 7d14cf2b-17bb-4ee7-9c66-0632f46a315b | See 5.1
| note | e598b99b-a4ed-4a8b-94b5-14b4c8ee4d9a | ---------------------------------
| note | bdeda22a-0f54-4156-abdb-563ffc45c1a0 | METHOD: Measure Visual
| note | ce03b695-eaca-4dd8-9325-5988b941403a | ---------------------------------
| note | 4eea58c3-ec6e-4dab-bb08-d3638bc6ea12 | FREQUENCY: Each lot
| note | 915d761e-9e87-4008-b6df-63666d51866e | ---------------------------------
| note | 02bb6bcc-1ffb-4b6e-a29e-426f76c85fcc | CATEGORY: IP
| note | f47b5524-c1c9-4f4a-8a41-89712a348e28 | ---------------------------------
| note | d60fbe0d-3802-4ab5-8b2a-5ee159657a1f | RESPONSIBILITY: SE/PE/SPE Foreman
| note | c5555201-cba8-42cc-8e51-9a1383b3cead | ---------------------------------
| note | 61d4802c-fbb0-4bde-9b54-910867aa4b82 | VERIFYING DOCUMENTS: This ITP
| textbox | f45e49db-4abc-4524-be55-463be6045894 | Date Completed:
| checkpoint |  | 4.8 Installation of Anchors - End Terminals
| note | 54cbc5ac-4431-4b37-a409-083264573764 | REFERENCE: QUADGUARD Installation Manual Pages 16 - 19 of 43
| note | a67405dd-166c-453d-9b61-247ae161267d | VicRoads Detail Sheet QUADGUARD-M10 Crash Cusion
| note | 210da89d-e8ec-46bb-a475-f2849a0c7f4e | April 2020
| note | 738cb7e4-a811-428e-8e75-03fb67580902 | Epoxy Product TDS
| note | 2bcfcafd-d024-4769-a8a7-ba0c460bee80 | ---------------------------------
| note | 49c33fb9-d41f-4999-960a-2d6ebaf9e32c | ACCEPTANCE CRITERIA: Position a 460mm long M20 8.8 grade threaded rod in each monorail hole.
| note | 8d456ffa-0954-4b99-8637-77de0da3be16 | Using an 22Ø masonary bit, drill a 420mm minimum depth hole into the substrate.
| note | 19964340-d4c3-412b-8f20-80907a0a91c8 | Blow out the holes and inject/pour the epoxy into the hole.
| note | bdb1b99d-3317-4c1c-849d-fab3a99940f1 | Wind a nut onto the threaded rod, making the end flush with the top of the nut and place a washer underneath the nut.
| note | d0c85a6d-8482-4f10-a39f-4c09ccf5f68c | Place the threaded rod into the hole, rotating as the rod enters to ensure full coverage of the thread until the washer has made contact with the barrier base-plate.
| note | ec11f11e-7fd3-42a7-a444-bd42437f80bb | Note: Threaded rod lengths above are based on an asphalt substrate - see the installation manuals for required lengths into different substrates.
| note | cee6f9f4-de0a-4224-9d4d-4993fc12a477 | ---------------------------------
| note | 663378f4-cbfa-427b-a27d-e9e2b82fc4e5 | METHOD: Measure Visual
| note | 6cbc2dac-0fee-496c-84f9-4d5ceb47550d | ---------------------------------
| note | 48edddef-c835-4f1d-b1a1-a625bf2405dc | FREQUENCY: Where applicable, each lot
| note | 483e3fc7-d968-4a46-b279-d02e505eb514 | ---------------------------------
| note | f5da1ac9-9be4-4926-bc65-9390bf198b9d | CATEGORY: IP
| note | fba581bb-738b-457c-a4c1-c75931d29e8c | ---------------------------------
| note | b04fe2c6-698b-4417-ac1e-d1ff8dac45d9 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | 768adf52-03cf-48a5-aa7a-d251e102ef30 | ---------------------------------
| note | 0cf8ee01-453e-4ee5-b6f4-94d4bab292cb | VERIFYING DOCUMENTS: This ITP
| textbox | 07b0b262-cfc8-4e34-96e8-eb5821d16818 | Date Completed:
| checkpoint |  | 4.9 Torque Nuts - End Terminals
| note | 0968d4e9-dcbc-478b-b50f-b95b3ebdef7f | REFERENCE: QUADGUARD Installation Manual Pages 17 - 19 of 43
| note | 709eaf8f-935c-4b40-9f93-1b1ce9ac54e6 | Epoxy Product TDS
| note | 298a2b42-ab6e-4587-a9a2-ebf7670400c4 | ---------------------------------
| note | 0d2e522d-9a65-4c9a-aa96-7476d94b77fb | ACCEPTANCE CRITERIA: Once the epoxy has cured, torque the nuts to 15Nm.
| note | caa9f553-1079-4c62-bcb8-4bb3b9c2a9a3 | ---------------------------------
| note | 60449b05-17ed-41bf-9d34-4cabd4379263 | METHOD: Measure Visual
| note | a708a640-e375-4844-adf0-512b5bb38e85 | ---------------------------------
| note | 0d4bc98c-a79b-43a7-b99c-7a013cdafa0d | FREQUENCY: Where applicable, each lot
| note | 184696b7-41fe-403d-90c3-0e579754e387 | ---------------------------------
| note | 72ff5ac8-13b5-472a-a01f-6a6c97d30176 | CATEGORY: IP
| note | 2f214706-380a-4b7f-8df7-a8ef797a8101 | ---------------------------------
| note | 7edc8577-e187-4119-8230-7890ca2af340 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | 7848fd3e-22e1-4555-b607-e80bb3a95459 | ---------------------------------
| note | 8fcf828f-2258-4097-8659-97e23dbde78e | VERIFYING DOCUMENTS: This ITP
| textbox | 52881b95-aace-43bd-835c-05a7e955de26 | Date Completed:
| checkpoint |  | 4.10 End Terminal Assembly
| note | a2f2dcc6-b9bb-40ff-aa92-5f16fc689e00 | REFERENCE: QUADGUARD Installation Manual Pages 20 - 34 of 43
| note | 286ebedf-f7eb-4c1d-9c78-800dbf94d322 | VicRoads Detail Sheet QUADGUARD-M10 Crash Cusion
| note | 3670931c-8012-4fd6-b791-40995b24cca4 | April 2020
| note | c0f9106c-b973-4e28-ab28-04860d23bee2 | ---------------------------------
| note | 5e371a74-c510-4298-842b-358eacbe94cf | ACCEPTANCE CRITERIA: Complete installation as per the installation manual.
| note | cbc33b12-b8bb-46b3-ae85-df00c1f0d22d | Replace any parts that are worn or damaged.
| note | daa6a117-b057-4566-94af-111cd8300dde | ---------------------------------
| note | 97177030-b89c-40fc-a5ce-11c62b852f0e | METHOD: Measure Visual
| note | cc534fef-22b4-4faa-aff4-974f1a82d90d | ---------------------------------
| note | 68074bc7-2d38-4e00-9f4d-9c3ec545bdbe | FREQUENCY: Where applicable, each lot
| note | 4d33fd25-484d-4364-b846-ab2b153cb24c | ---------------------------------
| note | 38c0d5d5-2f5a-45d1-b5cb-906e03d90243 | CATEGORY: IP
| note | 682019bd-920a-4a29-8ba9-a2ae80474c5d | ---------------------------------
| note | d7b47e0a-2f9a-4ee9-978d-ba471d2110f8 | RESPONSIBILITY: SE/PE/SPE Foreman
| note | a7d17924-4742-47ba-8142-9e9068168fb2 | ---------------------------------
| note | 95514fa5-59f0-4e79-b5b3-a2effe3b3d50 | VERIFYING DOCUMENTS: This ITP
| textbox | 4d06ff70-0265-4045-abce-3cea5eb4969d | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 5.1 Anchor Pull-out Test Results
| note | b769060d-bf20-42ae-9c3f-207d95f9654b | REFERENCE: HighwayGuard Installation Manual Pages 17 of 23
| note | f9da5fd6-c602-4db4-9570-a431623a4f96 | Epoxy Product TDS
| note | b514ed37-7b32-4407-8218-02d0f7799e79 | ---------------------------------
| note | dac8d88f-2e81-483f-a63c-53dca30dadc9 | ACCEPTANCE CRITERIA: Conduct a pull out test on the test anchor to confirm ≥95kN strength has been achieved.
| note | c5f7f8e5-521a-49d6-8f11-794d617a496c | Attach/Photogragh: Anchor Pull-out Test Results
| note | 3a90a45a-bc91-4a4e-b27f-7d74364b2ddf | ---------------------------------
| note | cbee8db7-d3c8-45b8-b45f-da55e61b33ad | METHOD: Test
| note | f6d0d539-ee70-4efa-a3d8-682e5c97d34d | ---------------------------------
| note | 8b88bebe-629f-48af-99cc-6f8fc6f7badb | FREQUENCY: Each lot
| note | 48896ed5-8e12-4cb5-9b26-9e5f99891ba7 | ---------------------------------
| note | 2f341a95-d87a-41fe-9e5c-dda07fc911e2 | CATEGORY: HP*
| note | cbd99586-bfac-493a-8296-20d6539cee19 | ---------------------------------
| note | 70d42592-ae96-421b-a600-a2447de61a7a | RESPONSIBILITY: SE/PE/SPE
| note | 1d579162-0fc4-4073-8a27-c519c12c7c8e | ---------------------------------
| note | 45acd1f4-69a9-4e13-a762-5d9bb745f54c | VERIFYING DOCUMENTS: This ITP
| textbox | fc5fb8c9-b613-4593-a8d6-d05c2a5c3d59 | Date Completed:
| checkpoint |  | 5.2 Installation Certification
| note | 175c8c36-f36e-451b-91a8-31c51025f0cb | REFERENCE: Subcontract
| note | 340ef415-9595-4e13-abd9-8e2340bff7d9 | ---------------------------------
| note | 8294159c-3099-45f9-9ed3-691e2247f877 | ACCEPTANCE CRITERIA: Installation subcontractor to issue an Installation Certificate, confirming that the installation has been performed in accordance with the manufacturer's product manual(s).
| note | de2450c4-3606-47ab-8cfd-47324a43f1f1 | Attach: Installation Certificate
| note | 19f69166-ab73-44ce-87f8-d153cd1e3fcb | ---------------------------------
| note | 2e849961-b6f5-4337-8451-1a07a263ced6 | METHOD: Document Review
| note | d82e1742-53ca-4a41-84a3-eba45c7b1fd8 | ---------------------------------
| note | 3c13967f-0dc5-4039-89f2-046b54f73a78 | FREQUENCY: Each lot
| note | a17ef476-ec1e-4ce5-8040-8f2faffaa648 | ---------------------------------
| note | a26b0fd3-292b-47c3-98a9-10923dfc2323 | CATEGORY: HP*
| note | a894b2dc-00b8-4a60-b849-e1b66ca1454d | ---------------------------------
| note | 4b7aeb3b-315c-4943-9f0a-9d0f342b4c0c | RESPONSIBILITY: SE/PE/SPE
| note | bc216b13-9ca8-4455-9736-d76ff648d14c | ---------------------------------
| note | 607617c4-6baf-4038-8669-56374ac17649 | VERIFYING DOCUMENTS: This ITP
| textbox | 4883c7af-68b2-4533-91f2-9f11b743e888 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | b94ff300-e02b-4348-8455-c102cad5ec3c | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | d23868f8-a108-49a2-9341-4ebec97a5813 | Name:
| textbox | e4f50156-5cd9-417c-bcc6-5092585475b1 | Position:
| textbox | 2e61555c-320c-48ae-9803-a3a2d533f6a8 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-Track & Civil-Track Removal & Construction | itp | ITP-Track & Civil-Track Removal & Construction | 5b788a37-c97c-4cc9-b470-abc5681a00f1
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 30aab9c8-3f90-5a16-8255-ee79888ff157 | Document Title: ITP-Track & Civil-Track Removal & Construction
| note | 6a602767-2b7b-5bfd-99f1-fec85215b846 | ITP Description: Track Removal & Construction
| note | e9fc5571-9cce-5f34-8e53-bdfe5312ff81 | Document Number (in Teambinder): N/A
| note | 82bbea1e-e8d3-582d-a520-d6fe9ee2eb25 | Discipline (e.g. CIV/STR/RAIL: Track & Civil
| note | 4b51c408-5ed6-5ecc-9c23-c447d58726fe | Revision Number: 2
| note | 639c9280-a545-51f9-8bf7-279f37795a76 | Revision Date: 14/11/22
| note | a32d1c0c-741a-576c-9cc0-22e6e261f272 | ITP created by: Jake Argentaro
| note | 47c677a4-71e5-5522-b3ce-2152198bb757 | ITP approved for use by: Jihad Chahda
| note | 96d0670f-a16e-5c71-a4b3-9073c2c2ce08 | 1.01 Fitzgerald Road Track & Civil IFC Drawing Set
| note | bf55e900-edac-5d48-bb45-9bacb691c039 | MRP-DPK-057-00-CPW-0060
| note | 8c32ea90-171b-5fa7-aa3a-0e91912c82e5 | 1.02 NIST-2654 Ballast
| note | 13c12158-f591-51fd-8a0f-e89f7fd34d8d | 1.03 NIST-2651 Sleepers and Fastenings
| note | 9e1febb4-96f3-5cf3-b9a5-05167a161701 | 1.04 NIST-2650 Rail
| note | 60bd54d0-2fb4-5425-b679-2862e501ad51 | 1.05 NIST-2630 Track Construction
| note | ba9aab1f-2185-53d4-99eb-27c919d4de0d | 1.06 NIST-2706 Track Geometry
| note | 1550e771-9be9-5a34-bf46-6eb3bf943d80 | 1.07 NIST-2659 Earthworks and Drainage
| note | e0e1b043-0dbb-5ab3-9330-13cc268fc641 | 1.08 NIST-2618 Track Design
| note | afe3edb9-e6d4-5d6f-816e-b88325add1a5 | 1.09 NIFO-2650.5 Aluminothermic Weld Record
| note | a6078871-3a2c-55d8-a245-75b76c27cb04 | 1.10 NIFO-2690.3 Certificate of Track for Operation
| note | d9100c38-6a2b-58ca-b5dc-aec919a4c1d9 | 1.11 NIST-2703 Inspection and Assessment: Rail and Rail Joints (External)
| note | 58af19af-e10d-5ef3-b8da-8b6ff468976b | 1.12 NIST-2704 Inspection and Assessment: Rail (Internal)
| section |  | Preliminaries
| checkpoint |  | 2.01 - Obtain and submit Material Certificate of Compliance for Track Materials;
| note | 0c3ec7dd-ab62-57a6-bfcc-0d476bad1ddc | -Track Rail -Track Sleepers -Track Jewellery -Geofabric -Ballast Matting -Ballast 60mm Aggregate -Welding Kits - Weldingng Crucibles
| note | 12f028cd-57f5-5cd6-a134-94e8f16b839e | Reference Documents - IFC Drawing(s) Track Constrction Site Mudmap Bill of Materials
| note | 6f759b7a-a91d-5085-8083-da2679023ccf | Acceptance Criteria - Units to be free from damage, total and types of units for full set validated No signs of discoloration.
| note | eaa332f9-9914-5f2b-9a50-ab50e7ceae8c | Attach: Manufactuer Certificates of Compliance.
| note | b4c86214-22f6-52d2-9c47-8c15b613fc3a | Welding materials shall comply with specification NIST‐2650 Rev3 Section 9 and AS1085.20 "Railway Track Material: Welding of Steel Rail.
| note | f02a07e2-1dc8-564c-958f-dd47afe30307 | Inspection / Test Method - Review Document
| note | 79fa87bd-6874-5c58-b44f-cd93992c48c5 | Frequency - Once
| note | 84fb317a-d06b-5f10-b60d-29cd818dd788 | Category - HP
| note | eb2ca55c-3c87-51d3-b503-5cef579c8a55 | Responsibility - Site/Project Engineer
| note | d2f96d3b-6984-5945-8fa0-dcdc65084648 | Verifying Documents - ConQA Hold Point Release
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.02 - Submit Welding Procedure/welding qualification welders record.
| note | 321e9330-5ea1-576e-8c66-4f874e00133d | Reference Documents - NIST-2650 Rail AS 1085.20 Welding Rail Steels
| note | 534bd387-0659-57e7-9f55-5bfa8341bab7 | Acceptance Criteria - Qualified personnel & welding accordance with manufacturers specs.
| note | 79dbd809-cecf-5bda-ba57-d6ae51acb570 | Inspection / Test Method - Review Document
| note | 5722c9a8-c973-5e87-8804-50017cb2c1a3 | Frequency - Once
| note | d1fd1ff1-435d-5fee-b8b0-75885737ef44 | Category - HP
| note | a2f08ccf-152e-5da2-a2e8-c2792e6dc02a | Responsibility - Site/Project Engineer
| note | 9f6a97ac-e143-54fa-ac04-f2696b315bec | Verifying Documents - ConQA Hold Point Release
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 2.03 - Inspect supplied items upon delivery
| note | 3d33e0ec-3969-51c3-8f11-f5d21d278466 | Reference Documents - Bill of Materials
| note | 11b49516-6b83-596f-a578-4f5f5961130c | Acceptance Criteria - No damage or debris on components Validate total number and type of components matches drawing
| note | 51d56c9b-50cf-5ffc-80dd-ed0f83cd22fd | Attach: Photos on site; -Track Rail -Track Sleepers -Track Jewellery -Geofabric -Ballast Matting -Ballast 60mm Aggregate -Welding Kits -Welding Crucibles
| note | 3ec7c229-4a12-5119-a1e0-0b845c28bc55 | Inspection / Test Method - Visual Measure
| note | 4f4e3668-2371-565e-8c3e-e727385f2108 | Frequency - Per delivery
| note | 2d779a07-1048-5e10-825a-354be2c25c59 | Category - IP
| note | 1f98bd89-61ba-532b-9ee6-7b1355c94d42 | Responsibility - Site/Project Engineer
| note | ccced416-a3cb-58f1-b305-6013a696b8d3 | Verifying Documents - Material Inspection Report
| checkpoint |  | 2.04 - Confirm extent of track removal required for civil works
| note | 2a7df89d-105e-50a1-a67c-a8db1e713c91 | Reference Documents - IFC Drawing(s) Track Constrction Site Mudmap
| note | 8ae49b9e-fd80-5b82-a6d0-c2999e900905 | Acceptance Criteria - Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site Pre-removal survey of existing track alignment
| note | 027d793c-ce82-5d76-b6a0-8131a3d8de4b | Inspection / Test Method - Visual Measure
| note | 3f1e66d2-089d-507c-a725-baaa0aa64d21 | Frequency - Once
| note | 818e8932-028d-5206-85e6-d44ad2e5c6ac | Category - IP
| note | 260478a1-b469-579c-8ed5-5a3399ddba32 | Responsibility - Site/Project Engineer
| note | 2b7ee918-2c81-5006-b4f7-fec8003ffaeb | Verifying Documents - This ITP
| section |  | Construction / Installation Activities
| checkpoint |  | 3.01 - Deconstruct and remove track components, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
| note | 24cff3ac-b3cc-5f77-9f1a-348be2653e90 | Reference Documents - IFC Drawing(s) Track Constrction Site Mudmap
| note | ee53e12a-c52e-58db-90fe-32418e4ee15a | Acceptance Criteria - Track structure to be removed to the designated limits as identified. Visual confirmation of removal on site
| note | 05632349-41ee-5953-8409-f12b9e153b0a | Inspection / Test Method - Visual Measure
| note | 35445f5b-7964-57ae-a3ed-2fd1309d4200 | Frequency - Once
| note | a86408b8-465c-5111-b2b3-2ae7852cbe22 | Category - IP
| note | 0f335ab5-7574-5d50-be82-ae62a0609257 | Responsibility - Track Supervisor Site/Project Engineer
| note | 516f85ab-4146-5768-89a4-e52aa050d953 | Verifying Documents - This ITP
| checkpoint |  | 3.02 - Earthworks completed and site handed over from Civil Contractor
| note | 8da3ad3f-20f5-5351-b406-9c798a65dfdf | Reference Documents - NIST-2659 Earthworks and Drainage
| note | eb5959f9-d343-54bf-9b48-4ff0d78cb10e | Acceptance Criteria - Confirmation of completion of underlying ITP(s)
| textbox | b8927288-f820-5ad9-aeab-d209c75a3cbf | Underlying ITP reference:
| note | 0a0fd16c-7bcd-59e2-900f-6612b9559b48 | Inspection / Test Method - Visual, Measure
| note | bf19a027-62ef-5d53-bfde-834dae13332d | Frequency - Once
| note | a7702e46-f794-59ff-85cf-a298edc4b3b5 | Category - IP
| note | 5ae04a78-6f29-5160-b16c-3ab5ea65e2eb | Responsibility - Track Supervisor Site/Project Engineer
| note | 619754bd-28c9-5cc7-944a-544e63a26057 | Verifying Documents - This ITP
| checkpoint |  | 3.03 - Installation of Bottom Ballast
| note | e2f7af82-f33a-5f52-8bc1-5ef95d805586 | Reference Documents - NIST-2654 Ballast
| note | b44c93d3-8e77-585e-a00e-6b8596bed878 | Acceptance Criteria - Overall Minimum 300mm bottom ballast depth
| note | 713e8a26-5633-56a6-84b6-329a5d3d8bea | Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate
| note | b42ff9ba-a20b-5a7e-a0fb-51f7a631bdfd | Bottom Ballast to be left 20mm below final design level Tolerance: Under sleeper -0mm/+25mm.
| note | a516c9e4-1c82-50fe-be0f-954f76509e70 | Attach Site Photo: -Installed Bottom Ballast Layer
| note | 28bf9cf2-e9c9-5093-ae86-f0caca3b485c | Inspection / Test Method - Visual Measure
| note | 99ebea8f-7310-58bd-9414-d642451edc8a | Frequency - Once
| note | b0f8c9a5-bbe6-531b-93dd-89c7098f7e4f | Category - IP
| note | 9d55072a-3865-5c88-8125-7f08484651d9 | Responsibility - Track Surveyor Track Supervisor Site/Project Engineer
| note | 865d791e-282e-577e-8be4-388e5f2351e8 | Verifying Documents - This ITP
| checkpoint |  | 3.04 - Laying of Sleepers
| note | 7eaa0dc2-d109-5100-ae5c-e69e5e0a7732 | Reference Documents - NIST-2651 Sleepers and Fastenings
| note | 4eda8110-6378-55ee-b299-fc1cd77a2087 | Acceptance Criteria - Sleepers square at nominal 685mm +/-25mm for open track Sleepers square at nominal 600mm +/-25mm through level crossing
| note | 053b6a3e-e8a0-5367-a545-3f785847923a | Attach Site Photo: -Laid Sleepers -Sleeper Spacing Measurement
| note | f7de0c23-f079-52b1-95bd-86aaa005eefa | Inspection / Test Method - Visual Measure
| note | 44b5bfbe-76d6-580c-806f-817e9f19b179 | Frequency - Once
| note | 4ec3f833-dccb-5c61-b85b-cd7fa627e449 | Category - IP
| note | 17e5162c-f857-5c7a-b0b1-5fd4cfa25c34 | Responsibility - Track Supervisor Site/Project Engineer
| note | 92dabb81-2ee8-5891-8516-bdcf5aaa5954 | Verifying Documents - This ITP
| checkpoint |  | 3.05 - Rail & Fastening Installation
| note | f054421d-01e4-5fec-bb92-ca16603953d4 | Reference Documents - NIST-2650 Rail NIST-2651 Sleepers and Fastenings
| note | a01d73e9-b667-5441-ab11-9667640289d6 | Acceptance Criteria - All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
| note | 2f3ebfac-7a90-5b1b-a595-cd9413f07027 | Serviceable used rail shall be tested in accordance to NIST-2650 Rev 3 Section 6.3 and NIST-2704:
| note | 5340223c-ec08-5b79-86b7-36288a9f1613 | - Running rails in main lines shall be ultrasonically tested for internal defects, using rail flaw detection apparatus Attached to rail bound or hi-rail plant in accordance to NIST-2650 Section 6.1.1;
| note | f7eee397-c838-55cd-9c3b-3b697642ca1a | - Manual ultrasonic testing shall be carried out within 30 days of completion of all new alumina-thermic and flash-butt welds on passenger lines in accordance to NIST-2650 Section 6.1.2 and AS1085.20 Appendix F4.
| note | 3035791b-58eb-535d-bd06-2797df320933 | New Rail lengths installed to be as per approved Fitzgerald Road Rail Weld Plan
| note | 9c298580-ef13-5c62-bcd1-5c09b32fdc41 | Rails to be painted with Mirrortoned paint within areas of temporary roadway
| note | 01567028-7d37-56cb-a2e4-a76f262d558f | Gauge of track to be checked upon installation of fastenings Gauge +4mm/-3mm Gauge Variation over 2m 4mm
| note | 40426d84-e085-5e40-8387-be0dab8d9986 | Attach Site Photo: -Laid rail -Rail joint to exisiting weld measurement -Rail joint between sleeper bay measurements
| note | 30692903-c2e4-5cce-b2d5-cf5feac2653d | Inspection / Test Method - Visual Measure
| note | 5a1f6124-db20-56b3-9a7c-9a86235963b1 | Frequency - Once
| note | e83316fc-cbd1-5270-8652-ad32b055beae | Category - IP
| note | 9e8fffb1-aae7-59d7-9e48-eaa114e330f3 | Responsibility - Track Supervisor Site/Project Engineer
| note | 4944cbe3-04e6-5739-8a91-b7188f5d8fac | Verifying Documents - This ITP
| checkpoint |  | 3.06 - Track Tamping
| note | 89919a20-7f6e-5709-b5bc-f0e89dc981e4 | Reference Documents - NIST-2630 Track Construction NIST-2706 Track Geometry
| note | c4e8a730-fc8b-548a-808b-57e8c761f36c | Acceptance Criteria - Tamping Ensures Track Geometry Tolerances are not breached (dimensions are in mm); Line (10m Chord) +/-5mm Twist (3.5m Chord) +/-5mm Twist 10m (Chord) +/-10mm
| note | f6b465ee-1a7d-50fb-8a3a-952393fcf14e | Cant +/-5mm Top (10m Chord) +/-5mm Alignment +/-20mm Survey measurment of RL of top of rail head
| note | fc18032b-2963-5819-9454-f642701caf4d | A minimum horizontal clearance of 3.0m from track centreline to structure.
| note | 8b592773-8a90-5da1-b8dc-3aa13668a694 | Attach; -Tamping Geometry Recording -Survey RL measuring sheet
| note | b4208cad-bcfe-5991-ab00-e6455f7d79a7 | Attach Site Photos: -Tamping Activity -Structual Offset Measurement
| note | cfe47014-430a-56d3-890e-4ce1dd88082d | Inspection / Test Method - Visual Measure
| note | 3a361c39-1ff7-5df7-a117-6155fcb49714 | Frequency - Once
| note | cc29eb29-98cc-5035-8161-5548ea42d771 | Category - HP
| note | 6c4af9e4-60d1-54fa-8f52-f73487c50d18 | Responsibility - Track Surveyor Track Supervisor Site/Project Engineer
| note | fbe43478-0d1b-5f63-9d63-6cc5c012423a | Verifying Documents - This ITP
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 3.07 - Regualting and Ballast Profile
| note | 14b2b0e8-573b-516f-9d83-f5eb6194e819 | Reference Documents - NIST-2630 Track Construction NIST-2706 Track Geometry NIST-2654 Rev 2 Section 7
| note | af44154d-c561-5971-af23-bcf01c6715eb | Acceptance Criteria - Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter, to minimum depth of 300mm below underside of sleeper nominally. No Ballast to be on top surface of sleepers or aorund rail Fastenings
| note | 369c1cf6-3126-564d-84cd-cd9efec35057 | Attach Site Photos: -Ballast Shoulder Measurement -Rubber Panels free of ballast materials
| note | b7110794-f754-5207-95ff-265fe3eba402 | Inspection / Test Method - Visual Measure
| note | 217c3b47-9516-58be-acb8-6364969fb01c | Frequency - Once
| note | d5aedb3e-dd6c-5253-b1bb-7d0a5b13ffee | Category - IP
| note | 3e84158e-abd0-5280-9243-50c1b121d5b5 | Responsibility - Track Supervisor Site/Project Engineer
| note | c82b6519-0042-532b-9b89-36bd15ad61bc | Verifying Documents - This ITP
| checkpoint |  | 3.08 - Aluminothermic Welding
| note | 46f9c6ce-5c8f-5d54-9f1a-72461018164f | Reference Documents - NIST-2650 Rail NIFO-2650.5 Aluminothermic Weld Record NIST-2650 Rail Use, Laying and Adjustment
| note | dc77d6a5-21a0-58f7-a448-2aa7366efb8c | Acceptance Criteria - Welds to be lined and finished to alignment standard Tolerance: Gauge Face +1.0/-0.5mm Running Face +0.6/-0.0mm
| note | af37bd68-b620-51ea-aec1-5264e8f8a307 | Welds shall be: - A minimum of 65mm between rail end to be welded and edge of first bolt hole
| note | 2b783276-25bb-5565-9307-8f53680a2ea1 | - Welds must be located at least: ‐3m from a bridge abutment, ‐3m from a level crossing, clear (at least 5 sleepers) of change in track stiffness , ‐3m from any other weld, ‐3m from a rail end at a joint, ‐+/‐ 50mm from centre of bay between sleepers.
| note | 7e54661d-7ad2-52e4-8806-bc00c8054925 | - The weld identification number (Record Sheet No.) must be legibly marked with white paint on the rail web, near the weld. Free welds must be painted black on the web prior to applying the weld identification number; welder identification (initials), weld number, year shall be clearly marked.
| note | 1144477f-f1d2-5c0a-afe8-ff62476bbeca | Verify Aluminothermic welding carried out in accordance with AS1085.20
| note | 4cdbb2a3-e3cb-57c7-971a-08ea60d3a1b0 | Aluminothermic Weld Return Form to be completed
| note | 7f09be91-b38f-5227-b3a1-e07abfefc273 | Attach: - Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6).
| note | 95dd2e9e-0777-5429-9d71-f2c605976aad | Attach Site Photos: -Welding Aligning -Welding Process
| note | 905be471-50dd-59b5-941b-77329dee2aac | Inspection / Test Method - Visual Measure
| note | 6eb29686-7f24-505c-a977-58aefe52c960 | Frequency - Each Weld
| note | eb51d793-03de-5334-8966-f630a6ce2f09 | Category - IP
| note | a09db388-492b-5aeb-a6ec-cd44cf59e990 | Responsibility - Track Welder Track Supervisor Site/Project Engineer
| note | d9a48752-9f91-5be2-b351-f043cd8b064f | Verifying Documents - This ITP NIFO-2650.5 Aluminothermic Weld Record
| checkpoint |  | 3.09 - Track Stressing
| note | 22ef7c9d-242e-58c6-aec7-83c386144cfa | Reference Documents - NIST-2650 Rail NIFO-2650.5 Aluminothermic Weld Record NIST-2650 Rail Use, Laying and Adjustment
| note | 39f6e23f-c52b-56b2-96c2-9b26a31363c2 | Acceptance Criteria - Stressing Rail in line with V/Line Rail Welding Process Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
| note | d8fed00b-de00-5536-92d8-863bc30c09ef | Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
| note | 1f5a82f5-77be-5bd1-9692-6365faf7740b | Reference Marks recorded pre and post tensing of rail, creep monument recordings to be undertaken prior-to and following rail cutting in accordance to NIST‐2708 Rev2 Section 6 and Appendix A.
| note | ae03079a-1e75-501f-a4b7-41af40a7c334 | Aluminothermic Weld Return Form to be completed
| note | 9e59dffb-2be0-5a4b-9b56-6b96a452f901 | Attach - Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6).
| note | dd0fa84f-fb2d-59a3-96f3-c77a9f20829c | Attach Site Photos: -Stressing Activity -Before/After Reference Mark Measurments
| note | 572b699d-9aa4-5986-a223-ef838c86566f | Inspection / Test Method - Visual Measure
| note | 74bc4b3f-bd0c-5b5c-aab1-312803ac3649 | Frequency - Each Restress module
| note | 79f722ab-c6ee-56a5-9389-0cdff8eab648 | Category - IP
| note | 01a74782-1249-5ab1-b986-d08e71e37127 | Responsibility - Track Welder Track Supervisor Site/Project Engineer
| note | ec09ee66-c4e9-50b7-ae02-b58d3f005146 | Verifying Documents - This ITP NIFO-2650.5 Aluminothermic Weld Record
| checkpoint |  | 3.1 - Weld Ultrasonic Testing
| note | adb30681-fe3e-5e99-9068-7582be2da342 | Reference Documents - NIST-2650 Rail NIFO-2650.5 Aluminothermic Weld Record NIST-2703 Inspection and Assessment Rail and Rail Joints (External) NIST-2704 Inspection and Assessment Rail (Internal)
| note | d8fa3ee6-3d49-50a8-bd67-cf052a363ff6 | Acceptance Criteria - Ultrasonic testing to be carried out in accordance with NIST-2650 Rail Testing Procedure: Olympus Epoch 650 Ultrasonic Flaw Detector or approved equivalent.
| note | 39ed0473-ebcf-573d-86f9-f74399275ce8 | The cross section of the area of the head and web shall be completely scanned; • The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2. • Welds shall be scanned to both directions.
| note | ed245639-751f-569d-9077-906f20c14203 | No classified internal defects found
| note | 209f6d64-aa4e-5e44-886b-37f3029c0031 | Final weld geometry to be assessed Tolerance: Gauge Face +1.0/-0.5mm Running Face +0.6/-0.0mm
| note | 22bb775f-4f30-5524-8a38-04c16e191717 | Aluminothermic Weld Return Form to be completed Attach -Aluminothermic Weld Return Form - Aluminothermic Weld Test Report
| note | b8f86d74-a848-5de2-84a7-b63307799c4f | Attach Site Photos: -Welding Aligning -Welding Process
| note | ef352b30-9e79-5a6e-8ca8-7c7efb200080 | Inspection / Test Method - Visual Measure Test
| note | 895b1341-5686-52a9-9419-c9a8c05f50c0 | Frequency - Each Weld
| note | 68ce602e-193b-5262-bed6-e355bc69be1e | Category - HP
| note | ffe5df42-0f23-5e41-b593-adf8a804e8d4 | Responsibility - Weld Tester Track Supervisor Site/Project Engineer
| note | baf6b34d-7ee8-51c7-8fd0-0dc6e19cc578 | Verifying Documents - This ITP Ultrasonic Inspection Report
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 3.11 - Installation of Rubber Level Crossing Panel
| note | 596a7062-9d79-5607-89a0-58786fdd3b5e | Reference Documents - IFC Drawing(s) Manafactures Instructions
| note | 5e5dab48-24c8-5c5e-ba88-3b5492d9246b | Acceptance Criteria - Install rubber level crossing modules in temporary roadway Attach Site Photo: -Rubber level crossing modules installed
| note | 47f732fd-6833-55bc-92b2-b117580e36c0 | Inspection / Test Method - Visual Measure Test
| note | 790a5861-faaf-5d04-bb08-f90277921029 | Frequency - Once
| note | 51a9fb25-0b52-5a2f-8c82-3a8c938341b1 | Category - HP
| note | b9a194ec-b694-5d83-bea5-e0aa5a517152 | Responsibility - Track Supervisor Site/Project Engineer
| note | 02b95a96-6a69-5592-bc0c-fe2218d47245 | Verifying Documents - This ITP
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | 3.12 - Installation of Guard Rail & Guard Rail Nose
| note | b5bc01fb-8ff7-5c90-a371-8fbbfe38b2f2 | Reference Documents - IFC Drawing(s) NIST-2650 Rail
| note | 17b2e597-54c8-5992-b15c-7c946b011c7f | Acceptance Criteria - Install guard rail and guard rail nose as per IFC design Guardrail to be installed with alternating fastening pattern
| note | af995f73-e465-5a6b-ba8e-6d6542caabca | Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion
| note | 80527c39-9974-52e0-92b7-a06a837fc989 | Attach Site Photo: -Guard rail isntalled -Guard rail nose installed
| note | db72133d-6fe6-5e01-b720-fac02c2f9fe3 | Inspection / Test Method - Visual Measure Test
| note | da0574e6-08f7-5c0c-b36b-c30084a8be24 | Frequency - Once
| note | d2467918-2988-59c9-be9d-0f136b2f3430 | Category - HP
| note | 471cf5f9-8982-5f4a-b9c2-cfc5304648b5 | Responsibility - Track Supervisor Site/Project Engineer
| note | 17c35cb0-c6a8-52da-b78a-e67e332cd752 | Verifying Documents - This ITP
| signoff |  | AUTHORITY HOLDPOINT
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.01 - As-built Survey
| note | 629cc3d0-49c5-5b9d-a757-6194ea478263 | Reference Documents - IFC Drawing(s)
| note | 179a8bdb-cf85-5422-8598-8d0a0b17da96 | Acceptance Criteria - Survey activities undertaken to validate correct construction Attach: -Survey Report -Engineering Asset From
| note | c4998aff-e851-58b0-acec-742ce7ad45aa | Inspection / Test Method - Survey Document Review
| note | 022558b0-1333-55a8-9dc5-0b4012a7fc0d | Frequency - Once
| note | 91e9f940-7f50-54b7-a198-ae2279bd4647 | Category - IP
| note | 12c69c1a-31b9-56a6-8705-d384ea8d35a6 | Responsibility - Track Surveyor Site/Project Engineer
| note | d4f447e9-4106-595a-b9f5-b31ed61d8f6d | Verifying Documents - This ITP
| checkpoint |  | 4.02 - Track Certification
| note | 20e64fab-a004-5ed4-bd11-e6733d6ddbdf | Reference Documents - NIFO-2690.3 Certificate of Track for Operation
| note | ab5e2dec-b10a-54da-8710-1e4d4d21cbc4 | Acceptance Criteria - Attach : -Track Geometry Conformance Certificate -Track System and Component
| note | 09342f1d-39fa-5b93-993a-1bf6e773be52 | Attach Site Photos: -Before/After Photo of worksite
| note | 1bd72dac-07e0-5f4c-a504-1c5696c5f3f1 | Inspection / Test Method - Visual Measure Doument Reivew
| note | a73a6c89-7c2d-5366-8c7e-27d15d9904ed | Frequency - Once when all occupation works complete
| note | 6bc5230b-533d-5b39-9c9a-ea3022a50830 | Category - HP
| note | faf45c09-335b-5f05-bef0-926a881c52ef | Responsibility - Track Certifier Site/Project Engineer
| note | b2b29971-5d2f-5d83-b3c7-e8beaa7ab5c7 | Verifying Documents - ConQA Hold Point Release
| signoff |  | AUTHORITY HOLDPOINT
| checkpoint |  | Final Inspection
| note | 1b8f3c2f-7d73-52d5-9e5a-4b636cb35cbf | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 984b4971-29b1-56df-bfd0-f583869ce24b | Print Name:
| textbox | 7bbe77a2-99cd-5384-a42e-5751da5a429f | Position:
| textbox | a2a11f5f-0b10-5c0f-8c48-35081c3071df | Date Completed:
| signoff |  | Add Signature:
| checklist |  | ITP-STR Maintenance Walkway - Robinsons Rd (Supply & Installation) | itp | ITP-STR Maintenance Walkway - Robinsons Rd (Supply & Installation) | 5dfee9a7-2c21-4c86-903e-354456e0b8ac
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 4c90c063-0a22-584e-9e6d-c650089213ef | Document Title: ITP-STR Maintenance Walkway - Robinsons Rd (Supply & Installation)
| note | 3e314aa0-1e07-5003-abe3-6a87617cd087 | ITP Description:Maintenance Walkway - Robinsons Rd (Supply & Installation)
| note | 3bb509c2-6dbd-5cb0-9837-6e9d5d0ca87c | Discipline (e.g. CIV/STR/RAIL: STR
| note | 6b078e9c-a2ae-55ea-a159-4f39a902155e | Revision Number: 0
| note | 5098ad02-53b7-509a-8bd7-caa973a1e338 | Revision Date: 08/07/21
| note | 9d6743d0-cd76-5de8-a2f8-194ad614a290 | ITP created by: Thomas Hudson
| note | 65a8e38f-eabe-54e0-acc8-5e1a98892e07 | ITP approved for use by: Aldrin Guinchoma
| note | 5505eabe-6d2d-5ae8-88a7-953ff0243653 | 1.1 VicRoads Section 610 June 2019
| note | 670a647f-3b2b-50a5-ae19-5cfd210a1619 | 1.2 VicRoads Section 630 October 2013
| note | cd62435c-e58b-5f10-a702-c6da707076a4 | 1.3 VicRoads Section 631 February 2009
| note | fd902ba9-1cd2-5450-827c-44228fdfc596 | 1.4 AS4100-1998
| note | e5e1aaf3-b0f7-5f51-9d3c-997eef52dbe4 | 1.5 AS5131-2016
| note | a02bfd92-283f-5366-8bdd-bb69896aade8 | 1.6 AS4680-2006
| note | 7ce5296b-e97b-513e-9926-f4d8707e27e8 | 1.7 AS2312.1-2014
| note | 4011f73a-8b72-5555-897a-88cad988814f | 1.8 AS4506-2005
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 - Structural Steel Components
| note | 4d31622d-53dc-5af1-80f2-b318daf8c4e2 | Reference - IFC Drawings MRPA Quality Management Plan
| note | 7bb9bab8-9472-5a99-a93d-03ac31f44b2e | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. Typically this consists of but not limited to:
| note | 1b833ea1-e7ba-583b-bbb5-c1777d3c5435 | i. Certificate of Compliance
| note | d803ab2f-8193-5955-9145-20627708ece4 | ii. Completed ITP
| note | d2060207-6b1c-5757-b89a-0e6aaf10b8fc | iii. Weld Procedure Specifications
| note | 6d7dd3b7-c54b-5377-8768-052a23703b0f | iv. Weld Procedure Qualifications
| note | 043b5a86-37df-5986-89cd-237f4e857d6f | v. Welder Qualifications
| note | 52114c8b-d211-506d-a024-a568035c9a53 | vi. Material Certificates and traceability
| note | cd9a3d24-21b0-5cf2-a678-02ba1267a73f | vii. Quality Assurance check sheets
| note | ff57103a-3879-541b-a884-426d17e3031c | viii. Welding Consumable batch certificates
| note | 83e6d7c9-918f-53f9-a10c-c011b2e6826c | ix. Coating certificate(s)
| note | 3ab27532-4a00-534d-98ed-931ae3f41c0b | x. Non-destructive Testing (NDT) Reports
| note | bcbf3d32-3323-58f7-a3c7-973b8e529946 | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
| note | c8e13ca8-94c8-5c05-bfae-ab1fca9d313a | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | 0677980e-a148-5b1a-b7a8-609ff79789d9 | Method - Document Review
| note | f4e050d3-b00c-5c63-8487-10352e18f969 | Frequency - Each component
| note | 59b9a983-68fa-5ba1-8a11-985461b56e3d | Category - IP
| note | 34464aaa-aea4-51aa-958c-24ff9f791763 | Responsibility - PE/SE/SPE
| note | 73e34151-12e5-5da3-9516-a6ad18f6de81 | Verifying Documents - This ITP
| textbox | 451dd412-1e48-5985-8519-e30dd4263c28 | Date Completed:
| checkpoint |  | 2.2 - Structural Grout - 30mm PVC tube: Megapoxy 206 (Non- Shrink 32 (min) Grout) - HD Bolt Blockouts: 50MPa (min) Non Shrink Epoxy Grout - Base Plate: Megapoxy 206 50MPa (min) Non Shrink
| note | bd5fe537-21b5-5a41-a6b3-5b159c9c3c89 | Reference - IFC Drawings 610.33 MRPA-RFI-000825
| note | 265c282f-5f68-5d60-942a-23e9dc9ec50e | Acceptance Criteria - Product to be selected based on the following criteria:
| note | 64a64712-c4b1-5989-abcb-b0954a747d8e | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
| note | 61753092-4500-5958-942c-6dbdd5fe28e6 | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
| note | 8ab7cd45-12ff-5a38-8a83-9193dc90fa18 | iii. have a flowable consistency
| note | c5742333-f1a5-5c62-bd98-69773b8244b8 | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
| note | 8571be91-30a8-5420-b827-d710b399f81d | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
| note | 02a8d578-469e-577f-b84a-ed5fa31c02c3 | Details of the materials and the proportions of the grout mixture shall be submitted to the Superintendent for review.
| textbox | fce061e5-99d0-57a0-8908-cb71e47b6bba | Teambinder Material Approval number
| note | 692d679f-6430-5296-9da2-1e4757a36ce4 | Method - Document Review
| note | a37e04ce-4a1a-53a5-94f3-30454a4a179d | Frequency - Where applicable, once, for each product, prior to placement of product
| note | 31ec359a-43f2-53d2-b88e-8810a179bf0b | Category - IP
| note | 7a619873-0edf-53e9-acef-a0256694bf19 | Responsibility - Nominated Authority
| note | fd1e40b8-960f-5875-b083-e5f98f5646c8 | Verifying Documents - This ITP
| textbox | 4699c350-54d5-5c1a-be1f-015c0df4e376 | Date Completed:
| checkpoint |  | 2.3 - Curing Compound (if Required)
| note | 54cbd35f-f008-5162-a6fa-de2524efecbc | Reference - 610.23 (d)
| note | b80c7b8c-1202-54c2-8cf9-c43d7071dcfc | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Note: This may be the same product used for the concrete curing Enter: Teambinder Material Approval number [free text box]
| textbox | 609cc7eb-dd3e-52a2-a904-4445615be6b5 | Teambinder Material Approval number
| note | 7aca3ef5-5d02-5853-9fb7-1e4badc2d720 | Method - Document Review
| note | 763f7fb6-c3b2-5174-8bda-2414eafe09b0 | Frequency - Where applicable, once, for each product, prior to placement of product
| note | 2e293761-aa0d-53c9-8b5b-b586fb812912 | Category - IP
| note | f3ea0800-f01b-50b7-b244-dd7720e36dc0 | Responsibility - Nominated Authority
| note | 091f620e-c054-5f35-8027-e9fd121615f9 | Verifying Documents - This ITP
| textbox | 3a2fb109-50dd-50ae-baaa-f716bc8108c7 | Date Completed:
| checkpoint |  | 2.4 - Fasteners
| note | 39ac1932-59c3-51f6-855e-1bdad6bf992b | Reference - 630.20 IFC Drawing
| note | 4aff82b6-a237-5ae6-ade9-5548c66ef43d | Acceptance Criteria - Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
| note | 4dcf842c-444e-51ee-a93a-fc03b52e4e76 | Method - Document review
| note | 361deeff-9792-5321-9a26-052af502f75b | Frequency - Where applicable
| note | c70017df-ecf1-5ba5-b719-92556bbe9094 | Category - IP
| note | c8b69e3c-d0de-5da8-92cb-a94a03e1d2a9 | Responsibility - Nominated Authority
| note | df3b9b2e-ae6b-5f8c-b5b7-0e22f70c9184 | Verifying Documents - This ITP
| textbox | 6352bd95-1e03-5510-9fee-887f660bb644 | Date Completed:
| section |  | Preliminaries - Procedures
| checkpoint |  | 3.1 - Structural Grout Mixing, Placement (inc surface preparation) and Curing Methodology/Procedure
| note | 2d9b70e9-9d52-5d63-a7ba-cc4283a7883b | Reference - 610.18 610.23 (a)
| note | b35d9547-13b7-565e-87f1-f9efca97aaf0 | Acceptance Criteria - Grout placement & methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box]
| note | b6afee8d-ee73-5572-bcbf-838f7c5d5e59 | Method - Document Review
| note | e39f313e-dac2-592b-b0cb-ccd1e88f044e | Frequency - Where applicable, once, 4 weeks prior to placement of product
| note | 5ec8d9f2-871e-5026-bf6f-b14d518e3a56 | Category - HP
| note | 008ffc6a-fb6c-5d9e-82bf-fa108f67e534 | Responsibility - Nominated Authority
| note | 501fdf0f-96a2-5cac-a42e-56ba1563e99c | Verifying Documents - ConQA Hold Point Release
| textbox | da0ba4bb-b161-55d2-9e6a-db7157726d88 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
| note | 48fe14fa-0788-521d-b188-04ec297ffd75 | Reference - 630.20 (e ) (ii) AS4100 Clause 15.2.5.3 (a) AS5131 Clause 8.5.7 (a)
| note | 0dcef1a6-36d5-5169-bb86-4185d9108cb1 | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by: i. technical data sheet or information on the product ii. 3 no. min. correlation tests between a calibrated torque wrench and a resentative sample of each bolt diameter/length/grade combination to be used in the Works. iii. a valid calibration certificate of the torque wrench Note: Daily records of use and correlation between a calibrated torque wrench are required, see 6.3 in Post-installation. Enter: Teambinder Approval number [free text box]
| note | 541fe325-e6fa-5ba2-a8b1-913233042553 | Method - Document Review
| note | 453fd43f-c670-570b-8b1f-6e11a486b092 | Frequency - Where applicable, once, 14 days prior to use of devices
| note | 503a43c0-ecdb-513b-b2d0-d5c188afd361 | Category - HP
| note | e27fb13c-4bbd-5712-b8c6-66065fd87447 | Responsibility - Nominated Authority
| note | 68d1cfc7-75f4-5377-944a-02eb46c94eb5 | Verifying Documents - ConQA Hold Point Release
| textbox | 536502f7-fe18-5c00-905e-7214df7dcc72 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 - Installation Methodology & Works Method Statiment
| note | de0ed55f-ac31-55fc-a5bd-f5f5e799c2d8 | Reference - 630.20 AS5131 Clause 11.2.3
| note | dc94cdc0-454a-5db8-805e-1b11e02e9865 | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following: - Transported to site; - Handled on site; - Installation Procedure (subcontracor ITP's); - Patch Repair Procedure; Enter: Teambinder Material Approval number [free text box]
| note | c97a5f3c-25ca-5d68-9d52-309d70b08a7d | Method - Document Review
| note | 23379745-69ed-5e32-90c9-d050294fce0b | Frequency - Where applicable, once, 14 days prior to use of devices
| note | cc101804-0df9-5d24-90f3-1f243fb84300 | Category - HP
| note | de1e1a43-65ce-5284-a27e-d1cf296ad6f5 | Responsibility - Nominated Authority
| note | 0e5c831f-60ac-5b22-b568-5a8210e94fb8 | Verifying Documents - ConQA Hold Point Release
| textbox | a8a36b38-a909-5c50-b6b9-9ea40ad72f2b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 4.1 - IFC Drawings
| note | 30e533be-3fdf-5a81-a693-9728cfebec8a | Reference - MRPA Quality Management Plan
| note | 9f22d335-e0b4-5a3e-b78b-7e3abfb7a8f7 | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 3a443121-98a1-5e3c-b081-471d849c2b07 | Method - Document Review
| note | d810a887-95d3-5f4d-a39c-191aa25bff70 | Frequency - Prior to starting Works and at regular intervals
| note | d26637f5-8ce9-5d4a-946e-adef27751b81 | Category - HP*
| note | 1d0f38e8-5617-5c62-ac2c-f37b19be8c35 | Responsibility - All
| note | 9d4abcaa-8b73-5a1a-91e5-17b60c5000b7 | Verifying Documents - This ITP
| textbox | a7086814-fc5a-51e0-aba1-a5ee0a7721a3 | Date Completed:
| checkpoint |  | 4.2 - Materials Inspection Checklist
| note | 4ec59e02-4c48-5ea9-a58e-a62749776132 | Reference - IFC Drawings
| note | b221730c-1e7e-5854-b666-9ee993b6e427 | IFC Drawings
| note | 7497a26e-cecc-50df-94fd-a353e9ed7ac4 | 630.08
| note | b1bad7e7-1643-57dc-847a-aaa1f97c70e4 | 630.09
| note | b85b4725-2d1d-51ea-9e74-3612794e53c1 | 630.20 (a)
| note | 997cd3f0-c230-5db0-8b3c-685ae302a747 | 631.06
| note | ee09f165-2dae-56e6-8f93-a9372735835a | AS4860 Clause 7
| note | b507898a-61fa-595a-a104-cdeb949cbb8e | 631.11 (a)
| note | 8088ad2a-4dd7-515b-991f-d8d0e0a010d2 | AS2312 Clause 9.6.4 (i)
| note | ec3195c1-94fe-5a79-8e18-231e1fbf49f9 | AS4506 Clause 2.3
| note | 692b3981-f13b-5b5f-880f-2a4c326dba99 | MRPA Quality Management Plan
| note | 683d8602-d6ea-5f37-9ab2-7ce7904b6a25 | Acceptance Criteria - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion. Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Where bolted faces are sloping at 1:20 or greater, tapered washers must be used. Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects. Complete: Materials Inspection Checklist in ConQA
| note | 7b465537-686b-5fbe-a80b-fd1c8cb101ce | Method - Measure Visual
| note | 84fde37b-c3ac-569b-b975-460275da88a6 | Frequency - Each component
| note | 8fbaea3b-2344-5faf-83cf-f8f00352a02c | Category - IP
| note | 71a4b581-9326-50b5-ad93-ba589937b1cc | Responsibility - SE/PE/SPE
| note | 7a5e414f-e066-5710-9a4a-4e4ec1413a93 | Verifying Documents - This ITP
| textbox | 3b8704a1-cfc3-55a5-a516-51b8f71ea114 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Installation Activities
| checkpoint |  | 5.1 - Bearing / Mounting Surface Preparation
| note | c78a8d02-64b1-561f-baa8-013fc445ef0b | Reference - IFC Drawings Product TDS
| note | e7016e45-ef3c-560b-896e-6a295d34d02b | Acceptance Criteria - Prepare the bearing surface in accordance with the Grout/Mortar Product TDS & the IFC design drawings As a minimum, ensuring that it is clean and free from loose particles such as rust and laitance. Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
| note | 0b3ac027-e5ff-51c0-a6cb-e446501aeb6a | Method - Measure Visual
| note | 296dd687-b6e0-527f-a584-7da6adf8897e | Frequency - Where applicable, each installation location
| note | 189afb0f-b005-5d2f-b41b-16060efdda5b | Category - IP
| note | 9a030af4-af3a-503a-b2c4-a1807b9d23af | Responsibility - SE/PE/SPE
| note | 5a1b3e14-24fe-57d3-96ea-b0f3c89fda83 | Verifying Documents - This ITP
| textbox | 45c77f42-b24c-5df9-993f-6ee5ef97252a | Date Completed:
| checkpoint |  | 5.2 - Scabble back HD Bolt Anchorage Recess
| note | 7fec719e-1b0c-5ad9-a6b4-429af0d8f370 | Reference - IFC Drawings
| note | a2706800-9dea-53e5-a564-dfaedeebce06 | Acceptance Criteria - HD Bolt anchorage recess surface to be scabbled and bonding agent applied prior to casting in situ infill grout.
| note | 3ec9593c-4fd5-5806-8302-d03adc9e9a07 | Method - Visual
| note | 7cf56b9e-2dfe-56dc-81f8-ecb098b0ddc1 | Frequency - Where applicable
| note | 742231fe-1c07-5dc6-9d07-972c9ce66b62 | Category - HP*
| note | f4b44c56-45a0-57d5-89b3-1c6dc897f255 | Responsibility - SE
| note | a481eb1f-d6cc-5afd-ba2e-02959d7a08c2 | Verifying Documents - This ITP
| textbox | b0bb2b22-178c-53d1-8a83-50c2ab456490 | Date Completed:
| checkpoint |  | 5.3 - Structural Steel Handling
| note | a940649e-4769-5790-96b1-46875045c468 | Reference - 630.09 631.14 AS4100 Clause 15.2.2 & 3 AS5131 Clause 11.5.6
| note | 082101d1-e8ae-59d2-b68a-5062fccb733a | Acceptance Criteria - The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
| note | 121bbe49-19ba-55b5-ab69-a20977d6bcad | Method - Visual
| note | bd9cdd9e-67da-5132-b33a-0b605e99bdbd | Frequency - Each component
| note | ee4525e4-c117-56a1-b9b9-67067d2a261a | Category - IP
| note | b2b94874-694c-518b-97fe-8660df45c28f | Responsibility - SE/PE/SPE
| note | ee930528-f60f-5794-a6bf-2f54e76f0ff9 | Verifying Documents - This ITP
| textbox | ca4d7c10-ba0c-54fc-b5fc-969e5a7c4cac | Date Completed:
| checkpoint |  | 5.4 - Structural Steel Erection
| note | e7529a48-9c43-5b28-a847-6f33034f6db5 | Reference - AS4100 Clause 15.2.3 AS5131 Clause 11.5.7 630.12
| note | ca870283-9409-567a-bc6b-40bf5064ff9d | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely. Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
| note | 6da82a20-b91a-51cd-bd0b-0bae5b926644 | Method - Measure Visual
| note | f83f7c56-a752-5968-af9b-87f66e8e8eb1 | Frequency - Each component
| note | b79cd500-944d-54c8-9846-c78a9f69fdcb | Category - IP
| note | 405ab5e5-99ee-5187-bf89-79b0b7ce0099 | Responsibility - SE/PE/SPE
| note | 30c38113-a845-5265-80e4-d836199af6d0 | Verifying Documents - This ITP
| textbox | a5f779b9-3156-5813-a5a7-f90090f68421 | Date Completed:
| checkpoint |  | 5.5 - Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
| note | fc370e04-505d-5d40-9c22-fb457268fa27 | Reference - IFC Drawings 630.20 (a) & (c) AS4100 Clause 14.3.5.2 AS5131 Clause 6.7.4 AS4100 Clause 15.2.5.2 (a) AS5131 Clause 8.3
| note | c0423cad-e8dc-5770-a19b-76afcf9a0723 | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | 6c736080-6db4-529a-8767-4168aae74f73 | Method - Measure Visual
| note | ef1d46db-bcbd-52ff-a4a9-7b6e80c2a7b9 | Frequency - Where applicable, each bolted connection
| note | a87d47f6-6fb9-5da4-9346-85d2cb490533 | Category - IP
| note | 2feb2e8c-802b-5e8f-8aa1-21410e7fce27 | Responsibility - SE/PE/SPE
| note | 9cb54c65-e5bd-5998-9a3a-81cfc4096916 | Verifying Documents - This ITP
| textbox | 38c7411f-9fcd-5978-a38d-dde087a5160e | Date Completed:
| checkpoint |  | 5.6 - Fastener Tightening - Tensioning Condition (8.8/TB & 8.8TF)
| note | 89eb3f8b-3d12-566a-af4b-29a7013cbdb2 | Reference - IFC Drawings 630.20 (a) & (c ) AS4100 Clause 14.3.5.2 AS5131 Clause 6.7.4 AS4100 Clause 15.2.4 AS5131 Clause 8.5
| note | ef76ec50-be4f-5a87-b5f8-f1a4351141f6 | Acceptance Criteria - Nuts shall be either double faced or washer faced type. Place bolts, washers and nuts as detailed on the IFC Drawings with the high strength designation on the bolt and/or nut remaining visible at all times. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tensioned fasteners shall begin with the snug tight condition. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. Mark a datum point that crosses over the static part and the rotating part before tensioning via torque wrench, part turn method, stressing jack or direct tension indicators.
| note | 73a39ad4-5975-5337-a982-153ef2697aed | Method - Measure Visual
| note | f0e7cf90-ab36-55ad-80ed-01f7332fcc3a | Frequency - Where applicable, each bolted connection
| note | 64ac18ec-cf66-55b5-8cc9-e5b0d9ab6d6e | Category - IP
| note | b4b4c90c-cdc6-55d2-beac-19e40c00e993 | Responsibility - SE/PE/SPE
| note | a3c8797d-13a1-5f04-bc62-cc5302da7749 | Verifying Documents - This ITP
| textbox | d406c274-e52b-592b-954e-3892160bd355 | Date Completed:
| checkpoint |  | 5.7 - Base Plate Formwork Construction & Placement
| note | 90f95df5-bfe3-54bf-8d8c-1f8380c7d6bf | Reference - IFC Drawings
| note | 85a25bed-fc8a-5ba9-b8d2-ab620a2c347d | Acceptance Criteria - Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
| note | d20be9cf-2508-5e56-aa96-ef4213fde15d | Method - Measure Visual
| note | 21e2d832-b8fd-589d-ae00-ac3a6be343a2 | Frequency - Where applicable, each bearing /mounting location
| note | 90c9b496-3600-5add-8ab5-b1ece114ea84 | Category - IP
| note | 806018a1-32b8-5c0a-b0c3-ea4a95f75f21 | Responsibility - SE/PE/SPE
| note | 2ba305c6-5498-5560-87d6-9783c083fe88 | Verifying Documents - This ITP
| textbox | 5550aaec-aea5-59d6-b1d4-9a3d3c52c3ef | Date Completed:
| checkpoint |  | 5.8 - Pre-soaking Concrete Surface (if required in TDS)
| note | 0f9be76a-1a4a-5514-91b6-f8bf406ac546 | Reference - Product TDS
| note | 2dc75eb1-e3d4-52c1-a2c2-ff480dae1f05 | Acceptance Criteria - Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS. Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
| note | 04395809-b610-5fa4-bae7-b9ce9c50d976 | Method - Visual
| note | 5defe791-c675-54d6-97ea-1403fd9f5751 | Frequency - Where applicable, each bearing / mounting location
| note | 30b615b8-d20f-531c-9e5c-8e80b5e86067 | Category - IP
| note | ced6b6a5-b6cd-552c-a0b0-5d326f4cd603 | Responsibility - SE/PE/SPE
| note | fbc730ad-f6a6-5ce4-b55f-30f88893b11f | Verifying Documents - This ITP
| textbox | c1a91bb8-96e1-5c27-adc4-85ab92e29bb4 | Date Completed:
| checkpoint |  | 5.9 - Weather Conditions
| note | 59ed5487-cc2f-5b62-9072-a83f0f8149bc | Reference - 610.17 Table 610.171
| note | 40a9c4cc-e6e3-5c6c-bec0-3a8e5710d35a | Acceptance Criteria - Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected. The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Enter: Required information on the Grout Pour Record & Grout Pour Checklist.
| note | eebba523-55dc-5370-8500-661f6f0fbc23 | Method - Measure Visual
| note | 89a52f41-39c7-59f1-9fb4-cd7a9aec632a | Frequency - Where applicable, each lot
| note | aa09d9b2-8873-53a3-9b6c-ff186cd3deb2 | Category - IP
| note | 4a096eab-1f23-5212-b3d0-98fba474ce0d | Responsibility - Foreman SE/PE/SPE
| note | 7f9d223c-ec6e-5056-b53a-f06d2bad31b4 | Verifying Documents - This ITP
| textbox | d640e1d7-7b27-51d4-86b0-97a052a06a78 | Date Completed:
| checkpoint |  | 5.10 - Mixing Product
| note | a5c96675-e2e8-564a-8a1b-523608434267 | Reference - Product TDS 610.28
| note | 13f94f0d-c44d-5b4a-b3a0-72bf74cd99fa | Acceptance Criteria - Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. Enter: Required information on the Grout Pour Record & Grout Pour Checklist.
| note | 81932444-8102-5071-b663-29d0d8f8d74c | Method - Measure Visual
| note | 909737b5-f325-5fc5-b3c0-382c0e6bd3c2 | Frequency - Where applicable, each batch
| note | 77cde7da-b787-5f53-85fa-9f125c919302 | Category - IP
| note | b50f1224-39f2-5816-a9e4-d1106489091e | Responsibility - SE/PE/SPE
| note | abc5195d-2370-5f8d-b42a-e5a1854462b2 | Verifying Documents - This ITP
| textbox | b3c6b40c-4301-5a05-89d9-e5de661bb108 | Date Completed:
| checkpoint |  | 5.11 - Product Testing - Compressive Strength Cubes
| note | f8f0e852-5256-5033-ab95-1fcdf35cd3a5 | Reference - 610.28 610.33
| note | faa7a6e0-1274-567b-a3a6-2c12c687f560 | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) After consitant results, dispenstion for reduced frequency in testings to 1 test per days production Enter: Required information on the Grout Pour Record & Grout Pour Checklist.
| note | 8132fe59-a6cd-598d-9503-0c361558fa89 | Method - Test
| note | d99a6735-4390-50ec-8e3c-60c45d755a4e | Frequency - Where applicable, each lot
| note | a1fac4ec-e841-56c3-99c2-f7fdbad5326c | Category - IP
| note | d5a2fbab-3d21-5676-993d-1690d5bea840 | Responsibility - Tester SE/PE/SPE
| note | e46404cb-30e5-5b98-ba7e-afe7864be95c | Verifying Documents - This ITP
| textbox | a1509352-0d5d-5b6b-9f26-95cc8951e6fe | Date Completed:
| checkpoint |  | 5.12 - Placement & Compaction
| note | fc547e8e-24b0-5598-a8e3-1aa320abe953 | Reference - Product TDS
| note | e862f684-8d5d-5aad-b680-f13421633453 | Acceptance Criteria - All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. Enter: Required information on the Grout Pour Record & Grout Pour Checklist.
| note | 720f707d-f34b-5e9e-b9d0-93ef9401509f | Method - Visual
| note | d883bbb8-60b4-51aa-b5fa-219d62493b83 | Frequency - Where applicable, each bearing / mounting location
| note | ccb1cae7-d5c1-553e-bb50-183f2255c566 | Category - IP
| note | f377e561-2936-54fb-855b-76c945b299be | Responsibility - Foreman SE/PE/SPE
| note | 3d38e5f6-e51b-5bd5-9e9d-37d95572ca2d | Verifying Documents - This ITP
| textbox | 5bf2aec8-2f15-51c9-8679-d23fe2c768c6 | Date Completed:
| checkpoint |  | 5.13 - Surface Finishes & Protection of Works
| note | 2e44956c-9444-5447-882b-4ba24772bdb5 | Reference - IFC Drawings 610.17
| note | 7f713f9e-cb96-512a-adfd-ad6bf0565f5e | Acceptance Criteria - If shaping of the unformed surface is required, shape prior to the product fully hardening. All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | 95dc9fd5-dd8c-5140-9850-6fa8e5b10c62 | Method - Visual
| note | 9b971dbc-4b68-5bc0-8d3b-d3aa96a4aff5 | Frequency - Where applicable, each bearing / mounting location
| note | 07bb164f-17b0-5c8c-a78c-65aa465d9c45 | Category - IP
| note | debab149-ff73-566b-9ffb-02a85b56238d | Responsibility - Foreman SE/PE/SPE
| note | a79fe14a-7af6-59c6-93e0-4c029ed021c1 | Verifying Documents - This ITP
| textbox | 0c5e7a58-f8d7-51f8-b389-89a3bd9e6f0a | Date Completed:
| checkpoint |  | 5.14 - Curing
| note | aafa984b-61f9-5033-92f7-d35716128617 | Reference - Curing Methodology 610.23 Table 610.231
| note | 638a47fb-b968-54bc-a84b-b8992f7be7b7 | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | 07c77182-8224-5fd5-8572-210727d1249e | Method - Visual
| note | 3f3fc7ba-8ba5-5c6e-a12b-0356ab2f1a67 | Frequency - Where applicable, each bearing / mounting location
| note | 62d0192a-357f-57d6-9c82-f5d3b0752ec7 | Category - IP
| note | 8a38cca3-1f45-5493-963a-631703c4eba6 | Responsibility - Foreman SE/PE/SPE
| note | ad480dce-cbdf-55bf-ad44-de44ca8959dc | Verifying Documents - This ITP
| textbox | 6bf7d6c1-c700-5c9d-9f3d-fd68b85f6e83 | Date Completed:
| checkpoint |  | 5.15 - Installation of Electrical Isolation Materials
| note | cb7f726e-cf2c-5fb9-8560-f0fc39fe0b75 | Reference - IFC Drawings
| note | 32622af4-2f60-554b-ab8c-b3ac20fc56e5 | Acceptance Criteria - Installation of Electrical Isolation Material in locations specified on the IFC drawings - under baseplates
| note | afb05506-b1f5-508e-95f3-f86e1893ce8a | Method - Visual
| note | 2c51f354-a61d-5e08-9324-94e227736d6f | Frequency - Each component
| note | a07c5a06-4d17-566f-b335-618e58a37819 | Category - IP
| note | cd582495-b77b-5fff-8fed-85920bda8d70 | Responsibility - SE/PE/SPE
| note | 620b9cb8-5f68-5aa6-8ba6-69974f5984e8 | Verifying Documents - This ITP
| textbox | 6d798fe6-165e-5d36-9b32-0e2648b691d4 | Date Completed:
| checkpoint |  | 5,16 - Architectural Steel Erection
| note | a6bd3bc6-c35d-50bc-9ea5-c3c878cf620c | Reference - AS4100 Clause 15.2.3 AS5131 Clause 11.5.7 630.12
| note | d3870b72-5af1-50f9-a786-0b513784a7d3 | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely. Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
| note | 82a90e84-0bea-55aa-854e-cd922aabd85a | Method - Measure Visual
| note | 0423bbab-e2e0-5c62-a2a3-bf12f2fbf9e5 | Frequency - Each component
| note | f8c4481d-2d35-59c1-b0ef-48dad92b677f | Category - IP
| note | 883495ff-0ed6-57ce-bc31-9d36642a22d2 | Responsibility - SE/PE/SPE
| note | 13a8df95-216a-5317-aa4b-482000f2d50f | Verifying Documents - This ITP
| textbox | 826572eb-ed69-555d-b7dc-b0d849d3c50b | Date Completed:
| checkpoint |  | 5.17 - Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
| note | 1f8ca016-316e-5287-a462-1541b029f537 | Reference - IFC Drawings 630.20 (a) & (c) AS4100 Clause 14.3.5.2 AS5131 Clause 6.7.4 AS4100 Clause 15.2.5.2 (a) AS5131 Clause 8.3
| note | c7490988-c2d0-5a78-a32b-975fa0f6215a | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | 01d888cd-d206-5d9b-a867-be6d672ed7cc | Method - Measure Visual
| note | 70ef2a79-d9be-59b3-bd38-0102457be75e | Frequency - Where applicable, each bolted connection
| note | fd3719ce-df5b-5f52-b697-e1108c6d2c0b | Category - IP
| note | 909ac859-b312-5fc6-afec-dd554591d6eb | Responsibility - SE/PE/SPE
| note | c47c7826-833f-532a-b2b8-3e6d1a803b58 | Verifying Documents - This ITP
| textbox | c8893c31-5ea9-54b5-ace2-931bbd713fba | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 6.1 - Inspection of Coating
| note | 9e0b6cf3-2be5-5a9f-8978-829f99ca29b3 | Reference - IFC Drawings 631.15 AS4680 Clause 8.3 & 8.4 AS4506 Appendix E
| note | 9a85b70c-6805-587d-bf1d-61a5f7e1222c | Acceptance Criteria - After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure.
| note | 975389ec-487c-59f0-9cf4-2b567d5f7e62 | Method - Visual
| note | 1f1171c9-6265-5be8-96d7-b43d847c00f8 | Frequency - Each component
| note | a1026e5b-2bfb-5474-8d43-ca5f68c259a2 | Category - IP
| note | 3ea4f50f-0b9d-56f5-802e-39eb21ea2578 | Responsibility - SE/PE/SPE
| note | 5ba0fa3a-87f7-51ac-8174-fae0edb13035 | Verifying Documents - This ITP
| textbox | c4ba0baf-7888-5788-a35b-8acb6a2e8ee9 | Date Completed:
| checkpoint |  | 6.2 - Compressive Strength Test Results
| note | be24591c-38ce-5e21-a065-1ced54d61850 | Reference - IFC Drawings Product TDS 610.28 610.33
| note | b3330b2c-6d04-53f9-adc7-436ba253ef54 | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Complete: Grout Pour Checklist Complete: Grout Pour Record Complete Test Results
| note | 4a0a511c-dad0-5d44-bcfb-a56ff732a983 | Method - Document Review
| note | e44e8755-05a4-59b6-a5b5-edfcd254a8c6 | Frequency - Where applicable, each cube
| note | 995bc3cb-659f-5446-ad58-e6e854841c13 | Category - IP
| note | 435a9137-8a6f-5065-b688-b245f3efd559 | Responsibility - SE/PE/SPE
| note | 156e8673-0a48-559e-a4d2-a6765b154271 | Verifying Documents - This ITP
| textbox | b6f63ee3-53cb-5694-9e23-4a82ef4e9ed2 | Date Completed:
| checkpoint |  | 6.3 - Direct Tension Indicator Daily Records
| note | c1013889-2566-52cd-ae05-b26e80f141d9 | Reference - 630.20 (e ) (ii)
| note | 7b8b7d9e-3257-5a8b-bc38-87babf0152a7 | Acceptance Criteria - Provide correlation between a calibrated torque wrench and direct tension indicators (DTIs) per bolt diameter. Attach: Daily Record(s) of Correlation Between Torque Wrench & DTIs
| note | ccd1049e-0f11-581a-8588-d2426c6bd5e0 | Method - Document Review
| note | f89ea05f-d2ad-564a-8397-5db383b8d373 | Frequency - Where applicable, for each day that DTIs were used
| note | 998e3cae-d616-5ba1-a41d-fbbad8c01e59 | Category - IP
| note | 6ee45977-b950-56b4-9126-51a96f1a4f3a | Responsibility - SE/PE/SPE
| note | 398e0874-71eb-5d79-8581-1735fd163230 | Verifying Documents - This ITP
| textbox | e84cc5f4-0346-5438-af8d-3bd18cff45cb | Date Completed:
| checkpoint |  | 6.4 - As-built Survey
| note | 728ed746-25b1-5eba-b426-80497c7e4950 | Reference - IFC Drawings AS5131 Appendix F, Table F3
| note | e87d155c-d43b-534a-9c71-9d8614158c96 | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
| note | 681b88bb-53c3-507f-b594-af98455ef406 | Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, 5mm Location of beam = ±3mm Location of column = height/500, 10mm max.
| note | 56b907b8-bfb9-5610-94c8-e399f09a2d82 | Attach: Survey As-builts / Survey Report
| note | 9d325511-b87d-5ca7-9b90-e3c6d43c4cbb | Method - Document Review
| note | 375a4f99-fe0f-5556-aec1-764cbf71a482 | Frequency - Each element
| note | 87706035-ea67-51b0-a169-135cb90bde13 | Category - IP
| note | 3bb71e9c-7a42-5dc7-b688-89003f45fa73 | Responsibility - Surveyor SE/PE/SPE
| note | e208c4b5-b29b-52eb-ba0b-47a293597437 | Verifying Documents - This ITP
| textbox | 87b00341-62dd-5f69-9e61-ee4a4bcbafb8 | Date Completed:
| checkpoint |  | 6.5 - Non-conformance Report (NCR) Closure
| note | 4212f59e-acc5-5ab0-9945-9e8588239d2a | Reference - MRPA Quality Management Plan
| note | 55aedd70-daf0-5223-92af-c9b8d0e50fab | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 6077fa3b-40b9-5356-be9f-da4490daef7f | Method - Document Review
| note | 3ea27a2a-c0f5-56ff-ad14-1cea8dfec0bd | Frequency - Once, prior to closure of this lot / element / Work area
| note | e13e566e-1942-565e-ad50-a0491212f2ec | Category - HP*
| note | cc9e440e-78d7-5419-9a15-1417710b8da9 | Responsibility - SE/PE/SPE
| note | 185cdefc-1c6a-5249-9fed-387e72083be3 | Verifying Documents - This ITP
| textbox | ba851151-2527-5693-940f-ca9647773062 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 1a0b7915-6ef4-55ec-888f-aa224ca6eec3 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 908ee9e9-5ecf-502b-9dd2-990f3aaaf822 | Name:
| textbox | 6c8c6222-a371-564c-98f2-a894af0358d5 | Position:
| textbox | 0dfb1afd-3f26-596a-9a9c-3fd5b6913b1d | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Drainage Pipe Lining Rev 0 | itp | ITP-CIV-Drainage Pipe Lining Rev 0 | 5f6e3c53-392b-4620-bcc1-6db0bc3ec522
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | beff2d6e-ab75-565c-ae3a-08e03fd4b546 | Document Title:ITP-CIV-Subsurface Drainage Pipe Re-Lining
| note | 48043a4d-7fc6-522b-aa8f-599096f69570 | ITP Description:Subsurface Drainage Pipe Re-Lining
| note | 2b8d45c6-c553-51d5-a405-2907fc8ec50b | Discipline (e.g. CIV/STR/RAIL:CIV
| note | c3021083-2df3-5cc2-8b3e-477aa3b8e105 | Revision Number:0
| note | 000b1216-d7b9-5864-b065-9d5616d28150 | Revision Date:29/08/22
| note | f063beac-e76b-522f-a016-19c2a9225075 | ITP created by:Paolo Oliva
| checkpoint |  | 1.1 - Interflow Pipe Liner https://www.interflow.com.au/expanda-150-1200mm/
| section |  | Preliminaries - Material Conformance
| checkpoint |  | 2.1 - Pipe Liner
| note | b003f22b-d04f-5edb-84bb-cc870a37f9b5 | Reference - IFC Drawings
| note | 5a997cd6-48f8-5062-bbfb-39b67218db41 | Acceptance Criteria - Product - Expanda Rib-Loc Liner (Nom. 15mm Thick)
| note | 1fb73786-2a33-5010-b1f0-b9aae3d89931 | Method - Document Review
| note | b37237d4-bed4-5b24-9f67-fd5b1bf2092f | Frequency - Where applicable, once.
| note | 1051bb72-5bd3-5040-a218-f045bdf1572c | Category - N/A
| note | f2650662-ce08-5a5e-ba66-e73c87605c6c | Responsibility - Package Manager
| note | 0c638264-c482-5893-a54b-2d921592e546 | Verifying Documents - This ITP
| note | d6fff1ef-8727-56b2-8f98-5dea3957ee91 | Spool QA record
| textbox | edbdf10f-32c1-58fa-8912-d9011814b2aa | Date Completed:
| checkpoint |  | 2.2 - Epoxy Joint sealer for around Pipe Liner connections into pit.
| note | 670dae8b-7824-587d-9ef5-821a01847a81 | Acceptance Criteria - Product - Megapoxy PM & Megapoxy HT
| note | 4d8cf2ef-77b4-504f-ada0-ba130adf912e | Method - Document Review
| note | 713e4888-7036-5ca8-9d98-5e2468c74f96 | Frequency - Where applicable, once.
| note | c1ece79b-e741-51b2-b148-132703e7dbe3 | Category - N/A
| note | e05900cb-0477-59a2-923a-e2b7b53201ca | Responsibility - Package Manager
| note | 665faa67-ef0e-54fe-a5c7-48768a3d2fee | Verifying Documents - This ITP
| textbox | ed9b70a9-cb84-5891-a5fd-7bc73c07b067 | Date Completed:
| checkpoint |  | 2.3 - Pit patching material
| note | 055eaa79-405e-5c34-87c9-2bb8bab7cae0 | Acceptance Criteria - Product - Fosroc Renderoc HB50 / Hyperform
| note | c73270d8-71b9-5363-bd7a-dd8d1758a63e | Method - Document Review
| note | c0689507-79f6-55df-b822-41ba6265f0a3 | Frequency - Where applicable, once.
| note | 5db83346-24bf-5780-a4f7-28d7dabc7425 | Category - N/A
| note | 1320842c-1f4b-5b61-b1f0-20353d861509 | Responsibility - Package Manager
| note | e102066c-a90c-5f93-95f6-a7c69fba0992 | Verifying Documents - This ITP
| textbox | 8f86c34d-2f9b-5ede-ba15-000977ac1a57 | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 - Pipe Preparation
| note | cf3821a5-5f59-5922-bc5a-e8934173dcb3 | Acceptance Criteria - Pipes cleaned, all silt and debris removed and ready for lining as per SOP
| note | f4216d58-e6e0-5221-ab6e-84fb0da5518f | All contaminated waste removed off site and disposed of at Western Treatment Plant
| note | 8f288a23-6cd3-5c20-b6aa-aab0cfc2525d | Method - This ITP
| note | 61fad3c0-6690-56dd-9261-cc58e95002ed | Cleaning CCTV
| note | a6684207-44f7-5794-a8f8-002dc969dcaa | Frequency - Where applicable, once.
| note | 9909b50e-bf34-5409-8196-00721dcc8a78 | Category - WP
| note | 1cc1b5ba-f2cd-5a45-a862-793012f197a4 | Responsibility - Package Manager
| note | 37b16f4d-637a-5b16-8a58-61f82f525b49 | Verifying Documents - This ITP
| note | 313b4d8f-58d5-5aae-99b8-0d0770ae28ab | Cleaning CCTV
| textbox | b831f989-848c-5c6f-b2d8-fcafe111fa1d | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 - Pit Preparation
| note | 1a1209d7-9439-5378-9ab6-eeca95b62fc5 | Acceptance Criteria - Assess pit sizing to determine if linear winding equipment fits within the pit opening.
| note | dd35aef3-1916-5829-9d6f-f1c418aaca9b | If required Jack out pit wall as required.
| note | 8f03eb7a-93d0-5758-ab5f-b2739aa81cbd | Method - This ITP
| note | c87a43f6-b7db-53f1-a2d8-72a4d662ace7 | Frequency - Where applicable, once.
| note | ae5a52b8-a34f-54d6-a31f-0972e511dc03 | Category - WP
| note | 2641267f-e2c8-560a-8514-ba598cc102e0 | Responsibility - Package Manager
| note | 97c89862-dda8-596d-91cd-a564d8ef8ffd | Verifying Documents - This ITP
| textbox | 0126f5dc-617c-51bd-ae2b-59c61d917d49 | Date Completed:
| checkpoint |  | 4.2 - Lining
| note | 7105b16e-809d-5322-861a-b959e7f9e77e | Acceptance Criteria - Pipe lined with Expanda profile as per design
| note | af7ceebe-a247-57d2-82b2-5421b5e8d4b2 | No swarf present in line
| note | c24108f2-3fcd-5274-bea2-c19f30784633 | No defect in liner
| note | 1fdb0f66-2aad-5ce1-b16d-4a7f19f3b679 | Liner ends sealed/rendered
| note | c42fda9b-6d60-5f3d-9073-70437892c5bb | Method - This ITP
| note | f440c8e5-72ba-50b5-b2b1-21cee179b131 | Frequency - Where applicable, once.
| note | e79a8101-ba14-54f6-aa4a-b2ba97c650cb | Category - WP
| note | c1d89e16-23d7-586f-97e9-4ebf1ae6e7a5 | Responsibility - Package Manager
| note | c2effdcd-fe4e-55af-a875-43dd321d7ccf | Verifying Documents - Daily Site Record
| note | d87d7d33-7948-5758-a0f4-39a87fe97531 | Final CCTV
| note | af6b8b06-0bf9-5a8e-9de4-809b36c771be | Expanda design
| textbox | 935b1a97-7588-50ef-b7e5-3547c01a232f | Date Completed:
| checkpoint |  | 4.3 - Pit Wall reinstatement
| note | c71f3859-cacd-5002-aacf-e878982043ff | Acceptance Criteria - Re-instate pit walls to pre-existing condition.
| note | d5d1ea7e-0b1a-584a-ab49-d74b907477a9 | Method - This ITP
| note | b4d3920e-962e-557e-835b-5c082ff2ac1b | Frequency - Where applicable, once.
| note | 34167827-b271-517a-85f1-1453271bcf0c | Category - WP
| note | b7985a68-5ac5-58d6-8515-107ee9cc6858 | Responsibility - Package Manager
| note | 2860ec40-016e-50d0-b231-be8f32b7adce | Verifying Documents - This ITP
| textbox | 10fb8058-3bd5-512f-af3d-55ca5e63017c | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 - Final CCTV
| note | 81e73024-dd87-5a1b-9118-ca04866eeab5 | Acceptance Criteria - CCTV Drainage lines after all lining is completed.
| note | 900ee57c-8e3a-5dc9-9c1d-478fc63133d0 | Method - This ITP
| note | 8f875e1c-b297-56ff-a402-9cb32b63daf4 | CCTV
| note | 5da5049b-f1b4-5c2f-b2db-3b8acaab42d6 | Frequency - Where applicable, once.
| note | 0b0b2f67-a78b-5757-a4e3-bbbee610ef41 | Category - HP
| note | 15a35279-364d-5d11-9e42-f0a544f334d2 | Responsibility - Package Manager
| note | e4e56dc2-fc33-5aaa-b18f-1b609ad8d451 | Verifying Documents - This ITP
| note | 39fc259c-3d78-51ea-97e4-1002bf26ebcf | CCTV
| textbox | ab5420e4-bb0f-5c0a-af86-078645f8f01c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.2 - Non-conformance Report (NCR) Closure
| note | ae54ebdf-f813-5d1b-aab3-90b5a187d835 | Reference - MRPA Quality Management Plan
| note | 6cadc4ac-e951-5d01-aa32-a560dff26386 | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 9114adfd-1036-507e-abb9-14ba3b8e7de6 | Method - Document Review
| note | 29d9797c-9868-55e8-9f2b-36f5f3e8ec72 | Frequency - Once, prior to closure of this lot / element / Work area
| note | 0f9aff75-a2d0-51a1-b5fa-ed383a51e3c1 | Category - HP*
| note | 6c7bc489-4e64-5768-a456-fd8134b221fc | Responsibility - SE/PE/SPE
| note | 203a44e9-6d18-50cb-b596-652fd1ed3608 | Verifying Documents - This ITP
| textbox | 6ab9ccea-2365-52f7-8828-f8ddac43e723 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | c2f40b2d-67c3-54a0-9408-d50b989ba282 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | cc304184-125f-5244-be5c-4133f111d923 | Name:
| textbox | daa81638-d098-5655-860b-6b3ad38d6c8e | Position:
| textbox | 0ebe1df1-705e-5d16-8401-ac02587efd8c | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | itp | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | 5fc31eb2-adb3-45a0-bd0c-6ec00230c0c8
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | f6af434a-8332-4b85-877c-07bdf6f0b291 | Document Title: ITP-CIV Unbound Flexible Pavement (Supply and Install)
| note | 477246dd-ed61-468c-96ff-d4569a548d35 | ITP Description: Unbound Flexible Pavement (Supply and Install)
| note | 573dd141-32db-48b5-ac14-1dda7fa0ee07 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 3ecc38b1-6c6f-4dc0-b69e-b89bb5cf34ec | Revision Number: 2
| note | 3aef087b-c185-4271-9d32-e838b566a964 | Revision Date: 11/09/20
| note | 4cb0451b-67f4-43ea-8283-164731118f7a | ITP created by: Hiruni
| note | 4f5cfa59-eab7-4702-a7f9-d83ec555a19a | ITP approved for use by: Josie Pavlou
| note | 679f8998-3841-4151-b35e-2f143b3c936e | 1.1 Reference Documents
| note | 658c3540-a672-4f26-b8e3-8bbfeb536df4 | IFC Drawings
| note | 6ee099c3-aa68-40c8-8f72-137c3f4642b9 | VicRoads Section 173 (10/9/2008)
| note | e44f921a-ca9c-464b-8f15-a4476483251f | VicRoads Section
| note | 8af5baec-87c6-405e-b799-c7650edeb8fb | 304 (13/8/13)
| note | 3dc9ab7a-c649-4c3b-b87a-ef8d96aa4692 | VicRoads Section 801 (19/07/18)
| note | 391ead9e-50e7-4c6d-b576-3d23dae16f3b | VicRoads Section 812 (13/07/16)
| section |  | Preliminaries
| checkpoint |  | 2.1 Crushed Rock Mix Design
| note | 2cf03232-6f48-4527-9b66-b82ffab701c1 | REFERENCE: Section 304.03
| note | 18720d8b-1e39-4b9b-a72d-6be92159a6c8 | Section 304.05
| note | 58865eb3-fcd1-47dd-8c6a-2ba271bc7df2 | Section 801
| note | d3da801a-a827-47e2-998f-f9e75e40adb9 | Table 812.121
| note | ab4b23d9-e94e-4075-b125-f94f178a5791 | IFC Drawings
| note | e8da6340-41d5-4fe6-b202-2d93bad1de4a | ACCEPTANCE CRITERIA: All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
| note | 3fabc9bb-99de-4020-952c-bd2851924f5a | Material properties to be tested in accordance with Table 812.121
| note | 6f6ae93f-048a-46a6-9253-30a9dcddfa76 | METHOD: Document and Docket Review
| note | aefe6461-29d9-4159-8dd4-a4e063980c4c | FREQUENCY: Material conformance as per Table 812.121 Delivery Dockets to be checked each lot
| note | 875be2b5-2edf-4c6d-8ff0-78d30e43b982 | CATEGORY: HP
| note | e6904195-f877-4bf9-b432-0bf423d62756 | RESPONSIBILITY: PE & NA
| note | d9f6c6ac-94fd-4fb7-8b91-5d621d84c1e9 | VERIFYING DOCUMENTS: Attach: Manufacturers Compliance and Test Certificates, and Delivery Dockets
| textbox | 064b8174-66b8-48a0-9a50-f577b668f6c0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | 1e5ea9d7-720c-4f86-a3a7-1c3694d33a05 | REFERENCE: IFC Drawings
| note | 4e80114d-5393-4a6b-a4d5-132b97c3bb68 | Section 304.06
| note | 058846fc-ed19-45bb-ba8a-c1a3e57e1c73 | ACCEPTANCE CRITERIA: As per IFC drawings and within stated tolerances in 304.06
| note | 0a2fe2c2-ed7e-4e48-9cbf-d7e70ff4844d | METHOD: Visual and Measure
| note | eca43ea7-48a4-4fb2-99af-dd865a43ad90 | FREQUENCY: Prior to Commencement Each lot
| note | fbe62d96-35ee-4c2a-8f99-35b213cb102f | CATEGORY: IP
| note | 7fd5d1d8-cb71-48e8-9b6b-00fa26099514 | RESPONSIBILITY: Surveyor SE
| note | a2f69a1e-c5ae-4f97-8155-6fffc4d2b50d | VERIFYING DOCUMENTS: Sign ITP
| textbox | da77ac79-8cea-44ab-9279-971c5f3ceb8f | Date Completed:
| checkpoint |  | 3.2 Previous Layer Conformance
| note | a38632ef-b76a-4cfc-b143-dfc368500d29 | REFERENCE: IFC Drawings
| note | e6b9c503-39d5-4b2a-b60f-c9cbb39f60cc | ACCEPTANCE CRITERIA: Previous layer to conform with IFC drawing requirements and closed out prior to placing pavement.
| note | 8a9b98b7-8d4e-469d-9d54-2e674b66cb46 | METHOD: Review
| note | e3a1b411-4786-4935-967f-2fac9701db6c | FREQUENCY: Prior to Commencement Each lot
| note | 78166b3a-79e4-49fc-af72-0620d56ecc70 | CATEGORY: WP
| note | 47fc19bc-fa36-4615-ae08-980ddbd47e5d | RESPONSIBILITY: SE
| note | 65d0dd7d-be48-4475-a4ba-994c21c4efe3 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 9f70cfcf-52fb-4a41-ae54-d94b639d23ec | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Placement of Material
| note | d89438f4-4d2e-4525-a01b-ec3d0ee81919 | REFERENCE: Section 304.03
| note | 12ff3393-6550-46e9-8aaa-e79bb304b6c3 | Section 304.06
| note | b1f3bdfd-f11e-4b5b-97f1-9ac18e4bb42c | Section 304.08
| note | ad026c05-4e13-440f-bbe6-16d48ffb656f | ACCEPTANCE CRITERIA: Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas. Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
| note | 7a3e8236-8b62-49ff-bc6e-8fcffc7bcdc7 | Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
| note | 8b1821d6-850c-4340-8b32-12f4b6a8be0c | At no location shall water pond on the surface of any pavement layer.
| note | dfc9722c-0ae9-4680-951a-9f83279a354a | METHOD: Visual and Measure
| note | cae80f2c-5406-4197-ac86-4f4b3dc72555 | FREQUENCY: Each lot
| note | 1235db98-b8a8-488a-9b77-dd8ebb7515e0 | CATEGORY: IP
| note | feb13d6c-e444-4717-8a27-cd39918501cc | RESPONSIBILITY: SE/Site Supervisor
| note | 6798b249-0bc4-4e20-91de-9f71e97c0b99 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 4cc543fc-8bf0-4571-ae84-c1d18903b233 | Date Completed:
| checkpoint |  | 4.2 Placement of Material
| note | 565a1a54-1449-4680-92ce-4c3b842ebe8e | REFERENCE: Section 304.06
| note | 22a636ae-a4c7-4401-b0ad-d510d8004898 | ACCEPTANCE CRITERIA: Lot size shall be the lesser of 4000sqm or a days production
| note | 1b520292-a387-425c-bd39-47a988b3984c | METHOD: Measure
| note | a9711040-ec52-4148-8d2d-d9303e52af66 | FREQUENCY: Each lot
| note | 1d421392-77b2-43cc-bb47-1b27ee1464fc | CATEGORY: IP
| note | 768f48d7-c0c9-441f-9d8b-c4d58dd6b0be | RESPONSIBILITY: SE/Site Supervisor
| note | 03039b2d-8afc-4dc5-9266-b33aeb0ab090 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 2f72b4f5-d2e0-4981-b278-1e9418ab74d1 | Date Completed:
| checkpoint |  | 4.3 Construction - Jointing
| note | 26763a18-609b-47ec-a371-27ddb89be3a9 | REFERENCE: Section 304.07
| note | 029b44ee-1ec8-4167-90db-30bd441b6cb8 | ACCEPTANCE CRITERIA: Material shall be spread in a manner to minimise joints.
| note | 07137dd8-acd0-4846-94fe-b282642a1cde | Transverse Joints in adjoining pavement runs and in any underlying layers shall be offset not less than 2m.
| note | 4adf1a79-df46-49c5-bde0-47654184111d | Longitudinal Joints to be offset by not less than 150mm to any underlying pavement layers. To be located within 300mm of the traffic lanes or within 300mm of the centre of a traffic lane.
| note | fc77ca43-261b-43de-97ab-fcac88c1cfde | METHOD: Visual and Measure
| note | 0b1830b1-6f9c-460e-9ee9-466d2193c4ed | FREQUENCY: Each lot
| note | 3120cd5f-9375-4fde-a4f0-0f8ac58bc137 | CATEGORY: IP
| note | c5704a4d-b2ab-4056-8366-4862484c084b | RESPONSIBILITY: SE/Site Supervisor
| note | 22ed4cb0-64d9-4e46-bf33-e6061fc1820a | VERIFYING DOCUMENTS: Sign ITP
| textbox | dca413fa-5f1d-4a77-9202-4238288bfddb | Date Completed:
| checkpoint |  | 4.4 Compaction Testing
| note | e0c768e0-af8b-4323-8f01-3f9d88172a2b | REFERENCE: Section 173
| note | d3db8562-d54c-4741-a8d4-77f1f46d7cff | Section 304.08
| note | 2a26dd59-2a2b-4137-8293-f2092900e9d7 | Table 304.081
| note | 3a30365b-7c7f-41f5-8608-92bcbfb4d4a8 | ACCEPTANCE CRITERIA: During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
| note | 1936ebd8-c9a6-4163-9596-116cc86a1233 | Density Ratio to be based on tests performed with Modified Compactive Effort.
| note | d70e02a8-2445-4e61-9225-b08f922888b0 | Scale B:
| note | e9392092-25d4-4680-8362-9e5d6cc06dcd | Subbase Layer CDR ≥ 97%
| note | 3b494ade-6191-4dc0-a737-61d01c4c6ba8 | Base Layer CDR ≥ 98%
| note | 0ecea182-a3b8-4657-a2dc-08db2c2a3ede | 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
| note | 6fe449fd-f2f6-4690-9775-18ef75fa3c0a | METHOD: Review
| note | fce0589a-e85f-434a-804d-531aab185044 | FREQUENCY: If the lot is < 500sqm , test every lot. If the lot is > 500sqm, test the first 3 lots. If they all pass then can reduce testing frequency to every 2nd lot.
| note | e07555f9-0f92-4f76-9e49-5fe476d88731 | CATEGORY: IP
| note | ab1b9a93-3fb8-4f6b-a3e8-af19166a5b45 | RESPONSIBILITY: SE
| note | 75a743c9-c31a-47ab-a1ac-10e988fbe735 | VERIFYING DOCUMENTS: NATA Certificate
| textbox | 6787e45a-6020-4ecf-97b6-a05b373666fc | Date Completed:
| checkpoint |  | 4.5 Post Compaction Materials Testing
| note | 1dbc3fd3-7fd8-4987-bfe1-93f82cd468bf | REFERENCE: Section 304.10
| note | c7a7725b-b45d-4e75-a858-9c106554931e | Section 304.11
| note | 558f7e6e-0d38-4d60-8ef9-80c08fb32073 | RC 500.02
| note | 37e4e4d5-86de-4614-91a5-730cdc745f5d | ACCEPTANCE CRITERIA: Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
| note | a3a5b885-f0d6-4b4a-ba49-f51080d3cd1c | 20mm Class 4:
| note | bfac7a66-70ee-40e4-b033-ed72b5ce5f0d | Grading
| note | 504edff4-2e51-403e-9c3f-c13659718f99 | 26.5mm 100%
| note | 47a9e6f4-4ecd-4aab-931b-a8eb18eb0de6 | 4.75mm 42-76%
| note | e16211bd-a87f-4d59-ae92-15c8e6b62438 | 0.425mm 10-28%
| note | a9b2efc4-fef7-456a-9fc6-3e8f8d036ce1 | 0.075mm 2-14%
| note | 4e37ca75-dc65-46d2-9a8c-6796cc436e00 | PI between 0 to 20
| note | e12232a2-32a6-485d-bf02-0359372f6f1a | PI x % passing 0.425 mm sieve (max) 450
| note | c60b2b8d-d913-4bb2-b43e-eec880aeaadb | METHOD: Review
| note | adc256a4-70fd-454a-821b-ffde94056760 | FREQUENCY: Scale B: PI and Grading to be tested once post compaction
| note | c635272f-cb4f-44ea-afbf-ed624aa7e65a | CATEGORY: IP
| note | 39e53042-e258-4481-ae91-c8c5440e3622 | RESPONSIBILITY: SE
| note | 264415be-4bc5-49f7-8d4c-f0ee91d61af6 | VERIFYING DOCUMENTS: NATA Certificate
| textbox | 30a0385d-b8c1-469a-944a-ddcaceacc4b7 | Date Completed:
| checkpoint |  | 4.6 Proof Roll
| note | a4d3ca3e-bcda-47be-a8a9-394e3fc0d238 | REFERENCE: Section 304.08
| note | a46d01eb-dfb6-49a3-b6aa-909ef6700ea1 | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
| note | 532afde0-f7c0-46cb-b684-7325b090ff50 | METHOD: Visual
| note | 451a4da2-9323-45b4-954b-f0bb271d440b | FREQUENCY: Each lot
| note | 5aa44f13-e001-4a69-bb41-25bf105eed2b | CATEGORY: HP
| note | 9ae31788-ce18-4fdd-80bb-d9779cc0e54c | RESPONSIBILITY: SE/Site Supervisor, NA
| note | 0354d04d-a0f9-4374-8eb4-bc3ab6b074f3 | VERIFYING DOCUMENTS: Sign ITP
| textbox | c723ff3b-2f12-4c65-bb2b-fbd8bf5d4410 | Date Completed:
| checkpoint |  | 4.7 Protection of compacted layer
| note | a14123a9-c140-446b-bade-9700d73b076f | REFERENCE: Section 304.09
| note | 32e3e297-e606-4e83-9e7a-141c59863b02 | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
| note | 8b44ba5d-b916-4983-a18c-5019ff47a9e2 | METHOD: Visual
| note | 0d46ab4a-9196-43ab-ae0c-dc16f59fc167 | FREQUENCY: Each lot
| note | ea458e85-7fcf-46e3-994b-9df61c6f2e15 | CATEGORY: IP
| note | 91d6543c-b3a3-4e61-9c74-edebf0fc923e | RESPONSIBILITY: SE/Site Supervisor
| note | bb8275b6-dd61-417e-9a5e-7d478c9ce117 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 13c21682-0c86-4e9f-bf6a-7f00c1d0098c | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 Survey As-Built - Surface Level
| note | bccfb1cb-b18e-43d9-9c29-9ce064292b5c | REFERENCE: IFC Drawings
| note | 5e35ae51-578c-4407-ac7d-fbe4ad2c09f5 | Section 304.06
| note | d1d0ecff-78ec-496d-8967-32fe097c2b54 | Table 304.061
| note | 25700035-e6db-4ff8-abcb-4199343a47f2 | Table 304.062
| note | 8662b374-3c7d-4c09-a42c-f00e6c7c5e7e | ACCEPTANCE CRITERIA: No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
| note | 53147692-c640-440a-b4b5-28df02a54fe5 | Subbase course shall be not < the specified thickness by more than 15 mm.
| note | 8d80fc96-ffe9-46bf-a30d-78d6c4f1221c | Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
| note | 966f7d9e-bfe9-48bd-b3c7-636cb04d8f8d | The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
| note | a666b9bd-5a6c-45a5-bde2-a28269367493 | Scale B: A minimum of 40 measurements per lot
| note | 6ae78faf-7eb1-490f-8d6a-942810fff3ad | Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
| note | 3146e211-e484-4eae-a7de-c401005bfb60 | Base: mean range ±8mm, maximum Standard Deviation of 10mm
| note | 0056f45f-9404-4a1b-8cf4-e1b91a68db05 | METHOD: Document Review
| note | 97c22e16-648a-4027-991a-3befb7a1c37b | FREQUENCY: Each lot
| note | d7edf92e-f9d7-40eb-9c01-30d7c929e725 | RESPONSIBILITY: SE/PE
| note | 688a3f5d-ff86-4982-9882-a46ff48c889f | VERIFYING DOCUMENTS: Survey Conformance Report
| textbox | d4aaef73-25fa-437d-98f1-006d4d5df269 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 6ac9edfe-cbc5-48b6-af2a-ea758bca688b | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 965ca384-d428-4516-81ea-3ef390717bf0 | Name:
| textbox | c5d84abf-45d7-4d47-b63a-8f5ca63e448c | Position:
| textbox | f08dccd0-2413-43bb-a2a8-c08d7c6bb660 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Guard Rail (Supply and Install) Rev 0 | itp | ITP-STR-Guard Rail (Supply and Install) Rev 0 | 5fd6ed38-d52b-4c8f-aef6-ca18c4217391
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 0c8a6fe2-633e-5847-a70d-8d0211cec388 | Document Title: ITP-STR-Guard Rail (Supply and Install)
| note | cb68c118-4b4d-51a9-a327-ed360cfc8fab | ITP Description: Guard Rail (Supply and Install)
| note | 18eb5e95-449d-5b30-8851-b46a3c47f146 | Discipline (e.g. CIV/STR/RAIL): STR
| note | 4b8406d5-bf7f-57d1-9bfe-6c2a87f3c43c | Revision Number: 0
| note | 52c2ca91-0c92-5a1c-a916-db1847d2882a | Revision Date: 21/08/2021
| note | 00c7b025-65bc-5401-966b-482a34c9cc2a | ITP created by: Michael Daly
| note | cb75464c-260b-5ad2-a739-e8c5dd58ac49 | ITP approved for use by: Aldrin Guinchoma
| note | dfd4707b-9941-5e73-aa52-623448d5057d | 1.1 VicRoads Section 708 November 2018
| note | a6504fae-88c4-5e44-b226-572ac524739d | 1.2 VicRoads Section 703 April 2019
| section |  | Preliminary
| checkpoint |  | 2.1 Materials - Guard fence components
| note | 2b132c25-d44a-547e-bdcc-73839bbd72e6 | REFERENCE: 708.04
| note | 54739f7d-d638-5475-9cbc-e8a5b22fa398 | 708.05 (a),(b),(c ),(d)
| note | a6720c68-418d-504c-96ef-37db60f3dd9c | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
| note | bf09795f-3293-5074-93c7-68d117ad524a | The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
| note | ead833d8-0068-580f-944f-05578a4e817c | w-beam sections, both ends of posts and all plastic components of proprietary end treatments unotrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
| note | 47cfb3fb-7627-55a5-b905-4a359e789287 | W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
| note | df623704-9a8c-5091-ac57-f49ef00507bb | Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214
| note | 81d9c868-c634-5efc-bc4d-215cb50c8911 | Reference: Teambinder Approval number
| note | 5568b24d-a83e-571c-9308-ebe3f7d74551 | METHOD: Document Review
| note | aacbd3a6-c597-5251-ab39-db259d8b6b97 | FREQUENCY: Where applicable
| note | 77adf971-77e2-565d-9a65-6dc3befc7a74 | CATEGORY: HP
| note | c3e7bffc-a36c-5f87-a1e5-7b3a8c406ee8 | RESPONSIBILITY: Nominated Authority
| note | 538c7e0d-7a30-5d26-90e0-407f77697cc3 | VERIFYING DOCUMENTS: This ITP
| textbox | 6aed7922-8d0e-555e-8424-38d3f6465e59 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Concrete mix design
| note | a996dc53-7684-5752-bfe8-d5ad3d915f7f | REFERENCE: VicRoads Spec.
| note | b03c5dfc-680a-5ec4-9c82-41cb064b2ffb | Cl.703
| note | e551460b-b9a8-5373-acfe-7269ee607303 | Cl.708.05(g)
| note | 5823acc0-0ec1-5b9e-be11-ecc9aaf65cb2 | AS1379
| note | 23d01334-ca49-516a-a6da-4a1007d928a0 | ACCEPTANCE CRITERIA: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
| note | 83a55a38-ffb0-598c-8fdb-ff7ae0309d62 | (i) Portland cement-based concrete, N20 strength grade, or
| note | f61dfc91-ea77-5934-af27-3c0ea8ffdf3a | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
| note | fc2ae4fb-d0b7-5846-a8f6-ea5a7f9a29f3 | METHOD: Document Review
| note | 8d1c3158-3f0b-5df3-b8ad-fb644851bd0b | FREQUENCY: Prior to Commencing
| note | d44eeacb-c7f9-5564-96f5-5a030753781a | CATEGORY: HP*
| note | 117f7946-b72c-551d-a469-419f7e4d8fc2 | RESPONSIBILITY: SE/PE/SPE
| note | 7b1daa63-3e39-5ccb-89a5-9ea0e31ed382 | VERIFYING DOCUMENTS: This ITP
| textbox | 35d2d5a1-f2ed-5f9e-97ec-53db426878c6 | Date Completed:
| checkpoint |  | 2.3 Installing W-beams
| note | abd3eb93-a67b-5f64-b2d3-3e234629f210 | REFERENCE: 708.08 (b)
| note | d5ce8a3e-3856-5369-ace0-714b2f815fb4 | ACCEPTANCE CRITERIA: Prior to the installation of any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads prequalified consultant
| note | 33a5dc3b-edd7-55dc-b34b-1d410bd1221e | Reference: Teambinder approval number
| note | 276836fe-224b-5df9-8e08-32f1d7b60a60 | METHOD: Document Review
| note | e8273e34-8522-5185-af5f-d408718de76e | FREQUENCY: Where applicable
| note | 5e5db6e3-2b98-56fa-b5cc-764f2322966d | CATEGORY: HP
| note | f73d08a4-d7d8-5371-8187-7ef92b4aafad | RESPONSIBILITY: Nominated Authority
| note | 80a43fc9-7d50-5f56-9805-b1e0e7e51f52 | VERIFYING DOCUMENTS: This ITP
| textbox | 7ba8e112-7cd2-579d-a50c-f6114f225c06 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction Activities-Guard fence
| checkpoint |  | 3.1 Survey Set-out
| note | 720af448-91b2-5bbf-9deb-18be8a6be77f | REFERENCE: 708.08
| note | 610df685-edbe-59c3-9fa0-8ebb8b36ecfc | Project Spec.
| note | 8b5dfa8c-00c8-5e1c-ab52-bd40ca27da01 | Cl.1190.07
| note | c0285965-aa94-5661-86d5-755c3560251a | IFC Drawings
| note | 5abbb9d7-defd-5716-99a5-a7c1e39c30dc | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence.
| note | 9769698d-8254-5e42-8147-3a1acab9e33c | The guard fence shall be installed at the positions so confirmed and shall be constructed true to line and level.
| note | 5da65a1f-7ba4-562e-9f0e-c43c04b981a6 | METHOD: Measure , Visual
| note | ceb51338-19c3-5a87-8f9e-8650e2ab916b | FREQUENCY: Prior to Commencing Excavation
| note | 24d90180-4795-512d-9261-8360b67a452b | CATEGORY: HP
| note | f49ab05f-7036-549b-88c1-2f008397b33b | RESPONSIBILITY: Nominated Authority
| note | 91abaf16-4df4-54f5-af19-8780f4ca0920 | VERIFYING DOCUMENTS: This ITP
| textbox | 24169259-654c-5023-b534-9664386bbd61 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Installation-Posts
| note | 63ba5c90-da8e-5fde-9c95-082cac31b71e | REFERENCE: 708.08 (a),(d)
| note | e21abf77-4e37-512d-ad1c-92614858e2c4 | IFC Drawings
| note | 0b213b49-4b3b-5336-86c1-994277ed1386 | ACCEPTANCE CRITERIA: Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance:
| note | 9f09a5ab-6021-5043-8037-3de2759bffb6 | true plan position of posts ±20mm
| note | f5c3d385-1566-5fa0-a2c8-22f17f648bbb | posts from vertical ±15mm,
| note | 6de2cadf-f423-5460-80fa-0bb1fd007c67 | METHOD: Measure
| note | 1ec21ca2-546f-54f8-b7c4-31f648d71b4d | FREQUENCY: Each element
| note | a436bd8a-813e-5021-a95d-3f9e42c3db9c | CATEGORY: IP
| note | 79a5f597-fd87-587a-aa9e-fe679dfe4f70 | RESPONSIBILITY: SE/PE
| note | 653b7252-5511-5894-9701-5cc4935f02dd | VERIFYING DOCUMENTS: This ITP
| textbox | 77bc3de3-3703-5069-a009-69c10a0b5dfc | Date Completed:
| checkpoint |  | 3.3 Installation-Posts
| note | 8af39161-c1c0-595e-94de-9d1afca1fb4e | REFERENCE: 708.08 (a)
| note | 37542282-bbba-50cb-8c3a-50525fc7c727 | IFC Drawings
| note | 77207c25-d2bd-5ace-b428-5b261c5d434a | ACCEPTANCE CRITERIA: Where posts are located in areas to be paved with concrete or premixed bituminous material, the backfilling of the post holes shall be finished 50 mm below the underside of such paving and the remaining depth of the holes shall be filled and compacted with material similar to the surrounding material.
| note | f969e2db-ef2e-569c-8ee3-7d76573c3546 | METHOD: Measure Visual
| note | c5d799c4-ca4e-5014-a014-929a95584e3b | FREQUENCY: Each element
| note | 04af2909-515d-5a80-a390-7c8d87ed4525 | CATEGORY: IP
| note | c174519a-6a1f-5363-8f08-9edfb8031c6c | RESPONSIBILITY: SE/PE
| note | 4003936a-8448-520b-9a54-b19ce6d36b85 | VERIFYING DOCUMENTS: This ITP
| textbox | c7ee2765-876f-55c3-857e-ccffe8070831 | Date Completed:
| checkpoint |  | 3.4 Installation-Posts
| note | cd4c16ac-a1c2-5ac3-8348-a98226e71c85 | REFERENCE: 708.08 (b)
| note | 6cd98c7e-14be-5078-b9bc-e54c24ac685b | ACCEPTANCE CRITERIA: The foundation of any post shall be deemed complying when the displacement at ground level does not exceed 3 mm when a 1 kN force is applied 200 mm below the top of the post in any direction. For any posts failing the test, the Contractor shall take remedial measures and retest the rectified post plus one other similar post within 5 m
| note | dabf0638-b04d-5538-a091-974100da6446 | METHOD: Inspection / Test
| note | fe28d49a-ba08-5559-bb6e-6c41fe9cf5c3 | FREQUENCY: Where applicable
| note | e355b54b-3c1b-5dbd-822e-f6f6a2576939 | CATEGORY: IP
| note | 8c0ca3f0-180b-53b2-87da-ded2f46310b7 | RESPONSIBILITY: SE/PE
| note | d76ea359-2a74-500f-9117-e5b6187d8518 | VERIFYING DOCUMENTS: This ITP
| textbox | f161f629-5973-5c89-95d1-24978d93acb1 | Date Completed:
| checkpoint |  | 3.5 Installing W-beams
| note | fb3645a9-9e3e-5872-be1e-f3532404ff1a | REFERENCE: VicRoads Spec.
| note | 46f8d4a2-0aa4-552e-80a5-e9b013e9f100 | Cl.708 .07 (b)
| note | c9df838f-35fd-5bba-b017-20cbf4341262 | ACCEPTANCE CRITERIA: The w-beam sections shall be lapped so that the exposed ends face away from near side approaching traffic. The edges of the w-beam section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened.
| note | 349e3ca4-8bfb-5b24-b8b4-9ea5eddeb9ae | End treatments of the types specified shall be constructed in accordance with the details shown on the drawings.
| note | 10a2b442-80d0-5b5c-8a46-e62ec75f301e | Posts attached to bridges and culverts shall be bolted to supporting members and/or set on mortar pads as shown on the drawings.
| note | 1c3d4c4a-179d-529b-b5ae-2236eb06005b | All bolts used in guard fence construction, other than nuts on wire rope assemblies, shall be tightened to a snug-tight condition.
| note | 375f28d9-1506-5445-9b5e-d534b5820db0 | All bolts on the traffic side of w-beam installations shall be flush with the w-beam.
| note | f13e7e82-4408-5fbc-9173-d0a2353f1aeb | METHOD: Visual
| note | 939a730a-67d7-5f74-a6c7-139a7263314b | FREQUENCY: Each element
| note | d3f08720-d433-521f-ae53-21e27f0e978d | CATEGORY: IP
| note | f10a27e7-03a1-563b-8c02-71cbe04f8b68 | RESPONSIBILITY: SE/PE/SPE
| note | 90763e75-5585-5ed8-894b-af695328bbba | VERIFYING DOCUMENTS: This ITP
| textbox | faec2b8e-09e8-5715-a3d9-ea734e1bae17 | Date Completed:
| checkpoint |  | 3.6 Install posts, rails and terminations
| note | 91983bc8-e3f8-5ae4-af1c-fd65b98943ba | REFERENCE: IFC Drawings
| note | 90398892-e6c9-5f5f-8e9f-b459fa4052fe | VicRoads Spec.
| note | 1f23d52a-8794-5eb9-a9cb-3e05da02d1e2 | Cl.708 .08(a & d )
| note | c8d83b23-93f3-592f-a7f6-270c8e21fc5f | IFC Drawings
| note | b2744f8d-2573-530c-8ad8-235ceaf2239a | ACCEPTANCE CRITERIA: W-beams shall be installed to the following tolerances.
| note | 0574a07d-fd8e-56e7-becc-d828db839e75 | line of w-beams from vertical profile ±10mm,
| note | 8c88a885-bbd4-579b-94ce-0e852bd591a4 | w-beams from horizontal alignment ±20mm,
| note | 7503f145-576b-5fba-9c6a-78aba4cc494d | orientation of block and /or post to w-beam +0, -15mm,
| note | af6618f1-85ef-5731-8ba7-1c1f940e76f6 | dimension of holes +50, -0mm,
| note | 3727d1b7-2b7c-593f-9540-13f82e091c1e | top of bolt head relative to w-beam +5, -0mm,
| note | 9779ef28-bf61-599a-94f3-82e085ed9d25 | top of rail shall be within 25mm of level and 50mm of line.
| note | 7358c028-8737-5a70-bfab-f641de4109c8 | Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
| note | c1740a3f-b6f1-56c7-abaa-5a587d9b0073 | METHOD: Measure , Visual
| note | 45985c6e-757f-5663-bccf-5b20b8663a6c | FREQUENCY: Each element
| note | 46291f56-f409-55a0-aefd-57563375c2a8 | CATEGORY: IP
| note | 63851ae7-45c4-5303-a485-91dd1f159221 | RESPONSIBILITY: SE/PE/SPE
| note | bb2cabac-fed3-5c38-aaf4-4d7bcda1ad35 | VERIFYING DOCUMENTS: This ITP
| textbox | 36a1a3a3-eb98-5615-9bb6-c698af2832c9 | Date Completed:
| checkpoint |  | 3.7 Construct crushed rock base for maintenance strip
| note | 0d1b02e9-051f-5e0e-982e-45a30f34fffe | REFERENCE: VicRoads Spec.
| note | b179d5f9-72aa-55a1-8931-686bc836851a | Cl.708 .11
| note | 765c183c-81e9-5a97-bc97-290cbc060db6 | Cl.812
| note | 47185d17-96c8-586f-aca6-f4dc15f8a6d2 | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
| note | 3bf1252f-2eea-5c2c-8182-b4b755209d7b | METHOD: Measure , Visual
| note | feafec47-3d40-57d7-8bee-cd3af6a0136d | FREQUENCY: During construction.
| note | d07e6358-c56e-5f77-898b-9e31a5687a5d | CATEGORY: IP
| note | 2da65ad3-2574-5f8e-96db-766dc0648ab3 | RESPONSIBILITY: SE/PE/SPE
| note | 32c01a23-aa5c-5c78-8678-157545cb5355 | VERIFYING DOCUMENTS: This ITP
| textbox | c6633500-4d24-5057-beea-40fa648f17cb | Date Completed:
| checkpoint |  | 3.8 Construct concrete maintenance strip
| note | 3b445416-b54c-5fe2-94d5-7e8d26d9f1da | REFERENCE: VicRoads Spec.
| note | 713ff028-de37-5c53-a429-7a807161232f | Cl.708.12a
| note | 4437d8e1-7e3d-5e12-9244-a84c38faf192 | Cl.708.5g
| note | d99ca932-7c4f-5c2a-b521-7ba52d0557d8 | Cl.703.11
| note | 728570c0-20ea-587e-99a1-c59c2ac20638 | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
| note | 13fb63f2-cddd-5e5c-999f-53d47d9c7979 | METHOD: Measure , Visual
| note | 547a6aba-531c-5baa-b63f-4ab12cb342e1 | FREQUENCY: During construction.
| note | 519f654d-3d28-50f4-b252-1543d7393d5b | CATEGORY: IP
| note | 7bdc2dd5-6583-54ab-b825-c541f7a4b1c6 | RESPONSIBILITY: SE/PE/SPE
| note | ea820d8d-d324-5603-94c8-608a282e56dc | VERIFYING DOCUMENTS: This ITP
| textbox | 91ac061e-3391-5947-b540-0d6801aa75ce | Date Completed:
| checkpoint |  | 3.9 Curing of concrete maintenance strip
| note | 6eb23ef4-00fa-58dc-89cf-b181f3f35d82 | REFERENCE: VicRoads Spec.
| note | 5dad9f65-1974-50a7-8267-5c6e8a46e01d | Cl.708.16
| note | 3c1bd315-b1a2-5047-8af1-0e207eb6397d | Cl.703
| note | 08805035-0a5a-560e-aa17-70a8b1220742 | ACCEPTANCE CRITERIA: Concrete shall be cured either by water curing,wet hessian,polyethlyene sheeting adequately sealed against moisture losses, curing compound or combination thereof.
| note | bd136ec0-37e9-5bce-8c80-76ef6fb2bf55 | Curing compounds to be in accordance with AS3799.
| note | b914b3fa-ac9c-546e-8a86-e54bbe9953f9 | METHOD: Measure , Visual
| note | 2c735626-ec07-5609-a054-3bc3dcf10014 | FREQUENCY: no less than 7 days after concrete placement
| note | 08810f53-870c-5c65-8a90-cec305cc9edf | CATEGORY: IP
| note | acac5735-f5c6-56fb-a624-104b3bd077dd | RESPONSIBILITY: SE/PE/SPE
| note | ebd975e5-dfe4-5c58-ba20-514f7bc05d38 | VERIFYING DOCUMENTS: This ITP
| textbox | baf00488-5f85-5a98-871a-043270f8dfd4 | Date Completed:
| checkpoint |  | 3.10 Delineators
| note | 5b68a962-4d93-5a01-b9c7-92720de20e5a | REFERENCE: VicRoads Spec.
| note | d936fcbd-5ae7-5de5-bd80-1d9bc4a6e4cc | Cl.708.10
| note | 41a2b0d5-d168-5c56-b6dd-76a065a955b5 | ACCEPTANCE CRITERIA: The Contractor shall supply and fasten delineators to the top of the w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2. Delineators shall be installed at 15 m spacing and shall not be placed on flared sections.
| note | eb646571-0452-53b8-94a8-c17ff10c83d9 | The Contractor shall arrange delineators so that vehicles approaching from either direction at night will only see:
| note | c5323857-4784-5f30-9add-cdbb182407c3 | • red delineators on the left side of one-way and two-way roadways;
| note | d05f25c3-cc68-50fa-9c42-e3f66b178d44 | • white delineators on the right side of two-way roadways; and
| note | a59f6c7c-66fe-5e50-8e51-35feaf528168 | • yellow delineators on the right side of one-way roadways.
| note | 4b10427c-0587-576a-91cc-422a6e645d25 | Delineators shall not be installed on guard fence when the barrier offset is greater than 4 m from the traffic lane. White guide posts with delineators shall be installed in accordance with VicRoads Traffic Engineering Manual Volume 2.
| note | 366c1e25-3ce4-5c50-8150-646116ab9056 | Where guard fence delineators are required to be installed as part of the Works, they shall be installed in accordance with VicRoads Traffic Engineering Manual Volume 2.
| note | 70bb9f9d-dfed-5a23-a3b1-a6e526ef2b8c | METHOD: Visual , Document Review
| note | cc038447-1b67-5b9b-80a4-4eec78aa7011 | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
| note | e0b67c53-d299-55ee-b521-f466429b7600 | CATEGORY: IP
| note | d6af9439-51e3-5dd0-b74c-82253e09b468 | RESPONSIBILITY: SE/PE/SPE
| note | d737164b-e197-5e4b-b924-e4e400c49097 | VERIFYING DOCUMENTS: This ITP
| textbox | 0fb47eb0-1cf5-5d03-82fa-9b123e13ce59 | Date Completed:
| checkpoint |  | 3.11 Compliance Audit of Safety Barrier System Installation
| note | d0fe84d6-1318-576d-a2b7-0d227faba5df | REFERENCE: VicRoads Spec.
| note | f796e1cc-0e20-5e6c-a5fb-27202d550c06 | Cl.708.09
| note | e769def4-9ecd-561b-9b4e-3c256625d92b | ACCEPTANCE CRITERIA: Prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract. The audit shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance (CoC), signed by the Contractor’s Representative and the Licensed Supplier, shall be provided certifying that the products have been installed in accordance with the manufacturer’s Installation Manual and this specification. A CoC shall be provided for each end treatment installed.
| note | b78d5616-5f2c-5e79-be0e-445b5817ee74 | In addition, the Contractor shall complete and submit to the Superintendent a signed copy of the Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual.
| note | 646644c3-9571-5c21-9466-989b50380e06 | METHOD: Visual, Document Review
| note | d4b7ad37-006c-5deb-b489-6d5dc9a2fe4c | FREQUENCY: Each bridge beam
| note | 83f5f5b4-1f88-533b-8c03-45b7dc74578a | CATEGORY: HP
| note | 2e845082-eec2-51ff-9fab-9e1a4d6d3cc8 | RESPONSIBILITY: Nominated Authority
| note | dcdcf101-34c0-5aa4-9a21-f90ac0653f74 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 6531cd9e-17b4-5150-8f20-8f5857d3e287 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction Activities-Maintenance Strip
| checkpoint |  | 4.1 Maintenance Strip for Guard Fence
| note | eff0b674-424c-5a87-b059-5888f5b89b3a | REFERENCE: VicRoads Spec.
| note | 644938c1-824d-594b-8021-a0b5f14396bf | Cl.708.11
| note | ed8a3e47-68e3-5496-9fe0-aa2653c28f55 | ACCEPTANCE CRITERIA: The Contractor shall provide a concrete maintenance strip beneath the guard fence and terminals in unpaved areas of median or outer verge applications as shown on the drawings.
| note | cef4be52-a651-55aa-a525-6d09ac73f023 | The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff.
| note | 4ace29d1-9f8b-5d2a-b74d-44fd944e49c0 | The concrete maintenance strip shall be placed between and around the posts to not affect the performance of the guard fence.
| note | 1008a815-e225-57a0-8962-af0bbc0c787f | All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock or Section 820 for Class 3 Crushed Concrete.
| note | f825bc9d-a1f4-5dea-91d0-b6df915551a0 | The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of Clause 708.04(g), on 75 mm of compacted Class 3 crushed rock.
| note | 0b77efb8-b00f-5117-b0b8-033ac8d981e1 | The edges of the infill area shall be boarded up prior to placing concrete to ensure smooth edges are produced. The edge board shall be placed parallel with the steel beam guard fence. The surface of the maintenance strip shall be finished with a wooden float to produce a lightly textured surface.
| note | 098546c5-7ed5-5eb6-a01a-78db03a09689 | Where the maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
| note | a890513e-7f91-51cf-a611-3112f3a1feac | The Contractor shall topsoil and grass all disturbed areas as necessary to ensure that the concrete maintenance strip is flush with the adjacent ground surface level.
| note | b7826f7c-83e9-5b60-9395-9041511464a6 | METHOD: Visual
| note | 3f4b2cf1-dca3-5ad0-9724-6f09fa69280e | FREQUENCY: Each lot
| note | b3e7cd2e-da13-556b-baab-eea106b5d28d | CATEGORY: IP
| note | f583f59b-45b0-5e17-aea0-f7d7f9494c31 | RESPONSIBILITY: SE/PE/SPE
| note | f6fbf119-f168-590f-8ab7-8fe32399ec5f | VERIFYING DOCUMENTS: This ITP
| textbox | a381481b-35cd-5dfb-be52-379fac73f46f | Date Completed:
| checkpoint |  | 4.2 Interaction of guard fence with existing assets
| note | 81a52b97-65cf-5be8-8595-7ed1cf18d690 | REFERENCE: VicRoads Spec.
| note | 0e796dbd-b0af-5c54-80ac-67ef4669c37b | Cl.708.12
| note | 83e8e0a9-4ffd-539d-8185-2d6f60e8668e | ACCEPTANCE CRITERIA: The Contractor shall install the guard fence to provide for its dynamic deflection that does not interfere with any existing roadside furniture.
| note | f2569688-f685-57a6-87a3-621a485112b1 | The Contractor shall remove any existing guard fence located between existing assets, such as gantry legs, variable speed signs and bridge piers. The Contractor shall allow for the interaction between all roadside furniture, including slip base light poles, and the guard fence by providing for the dynamic deflection zone or providing reduced post spacing as per the Drawings.
| note | a3142712-0e6d-5900-9768-0d6d24cbb85f | The Contractor shall integrate the guard fence with any existing lengths of safety barriers protecting ends of bridge parapets as shown on the drawings and in accordance with Clause 708.13.
| note | 206eb622-0264-5fe0-9173-07cf044d5198 | The Contractor shall remove and dispose of existing guide posts that conflict with a new guard fence, including any in front of a new guard fence located within a 4 m offset from the traffic lane and any behind a new guard fence greater than 4 m offset from the traffic lane, as well as bollards or other roadside furniture affected by the Works or where shown on the drawings or instructed by the Superintendent.
| note | bac213c8-b89b-5a2e-8c96-6a1323580871 | METHOD: Visual
| note | cf61f799-b6ac-52ef-a0a9-192aa34ee5f7 | FREQUENCY: Each lot
| note | 61c8d574-1b79-53fe-b98d-dffdbf6c8b9f | CATEGORY: IP
| note | 61e29c86-097d-521d-9bb9-476e70397e99 | RESPONSIBILITY: SE/PE/SPE
| note | c59ee4e6-dd5a-5b81-9df3-f4b991ebac08 | VERIFYING DOCUMENTS: This ITP
| textbox | d1fce7a6-3c30-5d2e-8b8d-9d7cb724a9e5 | Date Completed:
| checkpoint |  | 4.3 Existing Sign & markings Reinstatement
| note | 44cc8bc9-21f6-5374-89a3-394a10c65e75 | REFERENCE: VicRoads Spec.
| note | 14fde323-0550-5582-9d9d-1999685bcfb5 | Cl.708.17
| note | 8e0ecf58-8d98-5cd6-a912-9bb8c465b090 | IFC Drawings
| note | 7bff152e-a56b-594f-a435-bd735eb0e987 | ACCEPTANCE CRITERIA: The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
| note | cfbe2fa1-77a8-5776-b907-3bfeb171517d | METHOD: Document Review
| note | a8103c1c-e234-54d6-9b0a-f14e9d1aa8a2 | FREQUENCY: Each element
| note | d8f648be-591b-5408-96d0-900cad84d86e | CATEGORY: HP*
| note | 25a9662c-7309-511b-b4d7-8373661c33c2 | RESPONSIBILITY: Nominated Authority
| note | 5863e700-0359-5eb7-8519-a0068fcd28f1 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | bbf182c1-7086-587c-8841-5d28ddfe572b | Date Completed:
| checkpoint |  | 4.4 Placing, compacting and finishing concrete
| note | 30796fa4-92e9-59e4-b538-186cbc31959d | REFERENCE: Placing, compacting and finishing concrete
| note | 3fa375b0-ac08-5443-aa77-e7f99db3d4c1 | ACCEPTANCE CRITERIA: Concrete shall be transported, handled and placed so as to prevent segregation, loss or leakage of materials. Fresh concrete shall not be placed against concrete, which has taken its initial set, except at properly formed construction joints. Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and anchorages and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
| note | e73b09f8-9824-571b-9c68-f09c1fc51807 | Unformed surfaces shall be hand tamped to ensure a smooth surface and screeded to achieve the specified level, dimensions, falls and tolerances. Surfaces shall be finished uniform in appearance with a Class 3 surface finish in accordance with AS 3610.1.
| note | 757c15b8-5125-5840-a2ca-ad2445bc793a | Any concrete repairs shall be carried out using a method and materials approved by the Superintendent.
| note | b738b1e4-52be-506a-9584-7defbc1ddfb7 | METHOD: Visual
| note | d69c6985-55a4-53c6-905f-6c537c3e4a6f | FREQUENCY: Each lot
| note | a4df3994-f508-5e15-b376-a684f0c3a5e0 | CATEGORY: IP
| note | b150d57d-2389-551a-8e95-ca785be433c7 | RESPONSIBILITY: SE/PE/SPE
| note | 87981460-438e-551e-a4bb-e82022bd819a | VERIFYING DOCUMENTS: This ITP
| textbox | 5abcb879-cb98-5ecc-8f63-8991680ad6e5 | Date Completed:
| checkpoint |  | 4.5 Curing of Concrete
| note | a26dd47d-4a99-5a27-a5bd-cac02c0b4a9e | REFERENCE: VicRoads Spec.
| note | 96318c59-2a5c-58c1-95ae-6bf10f4f41d3 | Cl.708.17
| note | d169da2f-1531-5d2a-8e8d-8f3760f2ab4c | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete.
| note | deb4d8a1-55f8-599c-a786-60ce832a69e3 | Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed against evaporative moisture losses, curing compound or a combination of these. Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
| note | 95871698-c624-5418-a98b-09bb23287340 | When used, curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance. The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application.
| note | 5f4ccc4b-d15b-5a21-9d95-8d61369c6328 | Where used, geopolymer concrete shall be cured in accordance with the requirements of Section 703.
| note | 3a9f04ca-08bb-5a35-9dbf-f40a4579c794 | METHOD: Visual
| note | 5ac8b1dd-a0d9-5a2c-be61-d45a23b7ef57 | FREQUENCY: Each lot
| note | 7574feee-e0bd-5c38-b293-7b2728ca49fd | CATEGORY: IP
| note | 2fd9581e-0e1f-540c-8a5a-7d20fee800a9 | RESPONSIBILITY: SE/PE/SPE
| note | 296c391f-faa4-51c0-b2af-b120b0029c82 | VERIFYING DOCUMENTS: This ITP
| textbox | 1cb40656-1825-59a5-b4df-8a3c497c9d22 | Date Completed:
| checkpoint |  | 4.6 CONFORMANCE TESTING FOR CONCRETE STRENGTH AND CONSISTENCY
| note | 6b180576-fbaf-5e2f-994e-5caa18789996 | REFERENCE: VicRoads Spec.
| note | 30a60f27-4fcd-5d95-846a-4039a7c716c4 | Cl.708.18
| note | e0c0cfaa-d106-53aa-bb21-6544b469a95c | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379. The frequency of sampling and testing shall provide at least one sample to be tested for each 50 m3 or part thereof of concrete placed on anyone day, at the point of discharge. Where less than 50 m3 is provided for any one-day then one sample shall be tested.
| note | fe8b47cd-6aaf-5eb1-bc02-78d82344873c | The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3.1 and Clause 5.2 of AS 1379. The concrete represented by the samples shall be deemed to comply with the nominated concrete slump if the measured slump is within the limits given in Table 5.1 of Clause 5.2.3 of AS 1379.
| note | ffb9417c-71b6-5a76-bb08-e695ec0c25e2 | METHOD: Visual, Document recording
| note | cd50fb29-0c6a-5e67-8676-c991af9a9462 | FREQUENCY: Each lot
| note | 9df67f01-cf53-587f-9f97-1f2fac218d5c | CATEGORY: IP
| note | cdbae880-cc25-580f-8c76-ab6abff7abd1 | RESPONSIBILITY: SE/PE/SPE
| note | 0a720f28-f038-559f-a638-9cd69dc36798 | VERIFYING DOCUMENTS: This ITP
| textbox | 3b00d6cd-b623-5911-86aa-c40f2db8a41b | Date Completed:
| section |  | Completion
| checkpoint |  | 5.1 Survey data captured for as-built purposes
| note | 5abc4e51-a701-5982-b114-227fef502844 | REFERENCE: IFC Drawings
| note | 43779aeb-c7c1-57a7-89c4-b12675ffaae6 | VicRoads Spec.
| note | dd6eaec8-4ab0-5907-9d94-dfa964b0727d | Cl.708
| note | 0327853b-535e-5694-840b-a68322ee2a19 | ACCEPTANCE CRITERIA: As-built Drawings
| note | d3d00572-4d65-550b-8596-0a9ef3a87424 | Tolerances as per VicRoads Specifications, Clause 708.
| note | 9dc62067-e7c4-5072-bb1a-0fbdb531a818 | METHOD: Visual , Document Review
| note | dbcd6055-4430-56b2-acea-224cbae1c163 | FREQUENCY: Where applicable
| note | 43174a49-a368-5720-960c-e624421c9239 | CATEGORY: IP
| note | 3205136b-2958-57c5-9f12-6fc6f3d9db94 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | c3b89b4d-ae2d-5fd4-b163-f6c732b51b36 | VERIFYING DOCUMENTS: This ITP
| textbox | 526a18f7-57b3-52f4-847c-b33299d79393 | Date Completed:
| checkpoint |  | 5.2 Non-conformance Report (NCR) Closure
| note | e454cd5e-6529-54da-9ced-fdd6b1d91a08 | REFERENCE: MRPA Quality Management Plan
| note | 588cc2ff-f9e4-52a3-97a9-6dacc1c4aafc | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 8a2d49ef-c2b0-5ef1-bca0-d5b3b2dfbe1e | METHOD: Document Review
| note | 1ada76c0-a36f-5813-9689-eb6b5a105ccd | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | a4f80930-569c-57a9-b743-5441a50ee67b | CATEGORY: HP*
| note | d5b2da3a-7444-502b-bbd3-1e125da58029 | RESPONSIBILITY: Nominated Authority
| note | e301af52-81a4-50a9-81e3-00223d77c38c | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ed61e2d0-ca7f-5d9f-abcd-5e8e8c28e40f | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 829a9ce0-18eb-5a3e-8a9a-0ca9f5b2ff79 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 7d82e76c-4f95-5eeb-a00b-d578d60ff7ca | Name:
| textbox | d4ee8a38-d398-59b5-917d-223037a89e33 | Position:
| textbox | cc0915e1-8339-5fc0-9a71-51f454016a21 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Soil Nails Rev 1 | itp | ITP-STR-Soil Nails | 613f7709-8c75-4936-9f45-67bd76112139
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 97654610-d792-5de1-aec8-f9d438fc6942 | ITP Description: Soil Nails
| note | 1c44161a-52bd-54dd-a910-86b30bbde5da | Discipline (e.g. CIV/STR/RAIL): STR
| note | aa0d20da-58d4-5cd5-810e-dea5ca5b7006 | Revision Number: 1
| note | e8569779-7b18-5248-808b-77cea36f2bad | Revision Date: 3/08/2021
| note | ab8a393f-b2db-59f5-ad9c-c4bb9dcebb03 | ITP created by: Mike Freeman
| note | aabea483-0754-57b9-93cc-a5c3810562c5 | ITP approved for use by: Mike Freeman
| note | 8c11bf17-edef-50f5-a6ed-a355bba1123d | 1.1 Non Dependent
| note | 4684f616-d948-5e9c-9bb6-c90f1e85b198 | REFERENCE: VicRoads Section 610 June 2019
| note | 9f3b8dee-d674-5555-9cf9-490fe69e4dc7 | 1.1 Non Dependent
| note | e67a41e8-1cb1-5efb-a2fb-172d3226d823 | REFERENCE: VicRoads Section 611 November 2018
| note | c947e0db-4f2e-5d31-acec-a8ad2fee7664 | 1.1 Non Dependent
| note | 45732f9c-5d3e-572e-a48e-4e45a84ea68f | REFERENCE: VicRoads Section 683 April 2019
| section |  | 2 - Preliminaries
| checkpoint |  | 2.1 Design
| note | 201e9fa6-08d4-5441-93db-a727202698a4 | REFERENCE: 683.04
| note | 0f4e435f-8e67-5a16-8654-b83dae527ee1 | 683.04 (d) (i - xi)
| textbox | 06e119ed-2bbb-568c-bc5b-e01e4b2ea45e | ---------------------------------
| note | 1261dc62-3d9f-5c54-9834-98df1e194e45 | ACCEPTANCE CRITERIA: The Contractor shall submit construction drawings for review by the Superintendent prior to soil nail installation.
| note | 33a641fe-f8a5-5361-932c-aa89fb494657 | See: MRP-DPK-072-00-CSW-0021 (Robinsons Road)
| textbox | 1e3b5655-d159-5914-8ca8-e92fb45a34ab | ---------------------------------
| note | 3946893a-578e-50f0-99d2-ac653fc104a1 | METHOD: Document Review
| textbox | f49053f2-45b4-5933-a03b-aa03e8e6653a | ---------------------------------
| note | 00fdad2e-f0ae-55e5-a7cb-1e11425ad6bf | FREQUENCY: Once, 4 weeks prior to installation of soil nails
| textbox | 96c356be-204e-596d-8cde-b3b536a6c17b | ---------------------------------
| note | ce3e22e4-f326-5f70-9b49-cfdf9dad0502 | CATEGORY: HP
| textbox | 8e31c751-ce32-521c-85ec-f7d75a6b39b8 | ---------------------------------
| note | 6aff7bfe-cd27-5454-9200-a5fc541f1898 | RESPONSIBILITY: Nominated Authority
| textbox | 02c649e1-5443-5db5-add4-01a04880eb67 | ---------------------------------
| note | 24028187-b8da-5dff-8e2f-7f7fecd01f56 | VERIFYING DOCUMENTS: ConQA Hold Point Release (note this hold point is already released)
| textbox | 438932c1-4262-522a-88b7-7ec53ebd5c92 | Date Completed:
| checkpoint |  | 2.2 Nail Certification - Steel
| note | 72e3a99d-2814-57fe-a85e-01a4481b7753 | REFERENCE: 683.06 (a)
| note | c75bb124-59f1-584f-b096-739d02730f76 | 683.07 (b)
| textbox | ab79491c-3a25-5607-ba66-32a09c5534e5 | ---------------------------------
| note | 58c8233c-e0cb-57a8-a9f2-b21bda0d36f6 | ACCEPTANCE CRITERIA: Current ACRS certification for Grade 500N materials including couplers (where applicable).
| textbox | 7881144f-e46e-52f6-bd60-9d6340e71273 | Enter: Teambinder Material Approval number
| textbox | 169b6cc7-6b4a-5aa5-9f49-9fc4041d5110 | ---------------------------------
| note | 6ce4c3c2-f4fc-5591-9ecb-00f8289257b6 | METHOD: Document Review
| textbox | 2ef77526-07c3-5f0d-bcc0-637853aa1a0e | ---------------------------------
| note | 62ce0d4a-25d5-5b6d-9ef6-6589404cfb24 | FREQUENCY: Where applicable, once for each supplier, prior to installation of soil nails
| textbox | 1221724d-722b-52e0-a51f-1f919c1d87fa | ---------------------------------
| note | 67838d45-7720-5d19-867c-b998bf87407e | CATEGORY: WP
| textbox | 6d62d029-6ce4-5ccb-b907-c0d81c06f0fc | ---------------------------------
| note | 456ba2ca-9f6d-5f21-8a43-0e8787170fb6 | RESPONSIBILITY: Nominated Authority
| textbox | fa37a5e4-e7db-55ce-bb31-7e98d5ca720d | ---------------------------------
| note | 25b96e28-b2de-56d8-9e12-626422aaea45 | VERIFYING DOCUMENTS: This ITP
| textbox | 31ae6244-70ed-5d1c-98f5-d3d2b67c930f | Date Completed:
| checkpoint |  | 2.3 Nail Certification - Carbon or Fibre Reinforced Polymer (FRP)
| note | f9e5c5d7-33e6-549d-9ced-c84f528f02fb | REFERENCE: 683.06 (b)
| textbox | 16787a1a-73e4-5fce-8dde-0b209366a0cf | ---------------------------------
| note | a8d816ac-1adf-543f-9276-75dded50e9a9 | ACCEPTANCE CRITERIA: Carbon or FRP nails shall not be installed until the material certificates for all batches of nails have been reviewed and approval granted by the Superintendent.
| textbox | 27e0b0e8-174b-5b44-82a4-9c74b64be299 | Enter: Teambinder Material Approval number
| textbox | 89069695-0655-5d0d-ad63-72e4596ba879 | Enter: Teambinder Approval Number
| textbox | 9cc8cd99-cade-5355-a754-0fd9f1a6d537 | ---------------------------------
| note | cdec1bdc-7924-52df-bf9d-41e470cadc2c | METHOD: Document Review
| textbox | 46ca70c8-44e2-517b-af7e-a01277aa68c4 | ---------------------------------
| note | ed970251-86cd-5bf4-a52b-50bb3ae8367f | FREQUENCY: Where applicable, once for each supplier, prior to installation of soil nails
| textbox | 0a76aa00-d0a0-5479-9bc3-500a7516e855 | ---------------------------------
| note | 8833afc3-48ba-548d-b33f-1e61f34d0abc | CATEGORY: HP
| textbox | 7979b85b-bc08-5184-97f7-1ada1a9c8508 | ---------------------------------
| note | d7972bf0-472b-5ac2-9acd-fff25e1e8e63 | RESPONSIBILITY: Nominated Authority
| textbox | ab62e584-3cfb-5fe5-bb66-3c33f0e7d23d | ---------------------------------
| note | b60bd1c8-a955-5f58-b4b4-5ba95eebdbf7 | VERIFYING DOCUMENTS: This ITP
| textbox | 5d582ab2-879d-5a57-b0fe-a2d1b71cd9c0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.4 Corrosion Protection (for All Steel Componentry)
| note | bbbd1132-f4f8-586b-a9a1-326c29aeeee8 | REFERENCE: 683.07 (b)
| textbox | f6082641-4cf6-59cb-a51e-c5946f881d17 | ---------------------------------
| note | 58f74a16-9ac5-5386-95d1-9269a275852f | ACCEPTANCE CRITERIA: Coatings for corrosion protection on all steel materials shall be either:
| note | d35982dc-a3c5-531c-9577-7f7f8288cbad | i. Galvanised to thickness as per AS/NZS 4680
| note | 6bf8234a-51c4-5b3d-a78c-b6caa6d7146d | ii. Thermo-diffusion coated to Coating Class 80 or ≥80µm
| note | ae214d9f-ba59-5f2c-9701-83a3ee466f91 | iii. ≥80% zinc-rich product with ≥100µm DFT
| note | 81fa6289-adb2-5958-92a0-6384938219c4 | Attach: Coating Certificate of Compliance
| note | 447b648f-3411-5976-a223-ea303d004309 | Or alternatively, include in the nail certification in the Teambinder Material Approval.
| textbox | 0b8cbade-b94c-5fee-8e18-4564e6cbd049 | Enter: Teambinder Material Approval Number
| textbox | f989d3a0-159f-5ba5-b5e8-3fd65b90d31b | ---------------------------------
| note | 28664967-7c95-5bd0-905e-c2172ab6e1fd | METHOD: Document Review
| textbox | 20b2529e-6d0f-55cf-b4dc-f1a7fcfc9136 | ---------------------------------
| note | aed6014a-60f8-5358-b5f6-a32800ae2906 | FREQUENCY: Once for each batch of materials, prior to installation of soil nails
| textbox | 551b52ab-6dba-5fdb-a8be-6f0cbf76d851 | ---------------------------------
| note | 17cf0d11-fe65-5886-a4e9-3428eeac8cee | CATEGORY: WP
| textbox | 50fcfc90-1e16-5482-b132-e2638f69a1e9 | ---------------------------------
| note | 8b540cb4-5d3e-5823-a18d-e836075e09d2 | RESPONSIBILITY: Nominated Authority
| textbox | 1937bbea-1c80-505d-94ee-6416d278f6da | ---------------------------------
| note | bf34542a-e41f-5403-a946-04d9b97af21d | VERIFYING DOCUMENTS: This ITP
| textbox | baad5743-9756-58c0-bd22-8127f3ca3d18 | Date Completed:
| checkpoint |  | 2.5 Grout Mix Design
| note | ee6c257d-2f9d-5d39-a62a-6dbf5370e3e8 | REFERENCE: 683.11 (a) (i - iii)
| note | 0fac651c-01be-58c1-b483-833fbc86b276 | IFC Drawings
| textbox | caf709f7-88aa-5cf9-a1c0-5a8586c7a336 | ---------------------------------
| note | 2ee5f18e-98f9-5cce-931a-2929c5abd046 | ACCEPTANCE CRITERIA: The proposed low shrinkage grout mix design with supporting test results to be submitted for review to the Nominated Authority.
| note | b1c520b8-ff7b-5567-bffe-36437938e287 | The following test results and information shall be provided:
| note | 40804c02-0adf-51d5-9ee3-c47243c95ad1 | i. Water cement ratio between 0.38 - 0.45
| note | 3ffdc7f2-3c4a-54a6-8e8a-b3b2c7a241f7 | ii. The chemical admixture
| note | 5f1cc24a-e246-51a7-96ae-08b9b108e336 | iii. 7 day compressive strength test results ≥32MPa
| note | 29c4d113-fb59-5e19-845a-e8864e8d4c23 | iv. 28 day compressive strength results ≥40MPa (Robinson's Road)
| note | 4a7e734e-0281-518f-a2de-9566883cc33f | v. Flow cone test result between 10-30 seconds
| note | 11ea3b7a-0b2a-5551-924d-8e31d4dd32a2 | vi. Bleed test result ≤2% 3 hours after mixing, ≤4% at any time and separated water absorbed within 24 hours
| note | 8615232e-8cb7-596f-a488-d7d44b736c3b | vii. Chloride-ion content ≤0.07%
| note | d34d5e70-bdb8-5205-85f4-e4d664ee2864 | viii. Sulphate content ≤5%
| note | 2c5dc15a-0643-528b-804e-aed032e75bdf | The grout shall be made strictly in accordance with the approved grout mix design and in the event of changes, re-submitted for review and approval to the Nominated Authority.
| textbox | a5452465-c434-5196-82c5-1cf34bb113ab | Enter: Teambinder Approval number
| textbox | 5026b411-e430-5c0d-93b9-f4250eabdacb | ---------------------------------
| note | 607818d4-a79e-51cb-8fda-e24524b6dc20 | METHOD: Document Review
| note | 86b35b0c-5afe-5fca-a629-3fb8ead20aee | FREQUENCY: 2 weeks prior to installation of design verification testing
| textbox | 9c3750dd-0a1e-524b-b007-f9803d597878 | ---------------------------------
| note | 77d5c598-fd51-5615-9fd8-3f95e5f4cb9c | CATEGORY: WP
| textbox | c85929e2-61a9-5219-bbb4-7934195738d4 | ---------------------------------
| note | 9575cb28-aea5-554b-9162-7f6db5c444bf | RESPONSIBILITY: Nominated Authority
| textbox | 458d71a1-25bf-562f-b988-e65298ebbe94 | ---------------------------------
| note | cadb3f0e-60e8-50d8-996a-ac6dfec9f91d | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | bb8893d1-cd7e-53a6-8f65-26c136156922 | Date Completed:
| checkpoint |  | 2.6 Soil Nail Installation, Grouting & Testing Work Procedure
| note | 8fd53e57-18dd-578f-b43e-dcdeb3a55f2c | REFERENCE: 683.12 (b)
| note | cb7636f2-3fa0-5883-a37f-391e55164ee7 | 683.11 (b)
| textbox | a98d647e-dc15-5e93-b700-a9d883287852 | ---------------------------------
| note | dc588c40-0643-502e-bf2e-515d829b4a48 | ACCEPTANCE CRITERIA: Soil nail installation WP, fully detailing the proposed drilling, grouting & testing equipment, methodologies and reporting, to be submitted for review to the Nominated Authority.
| textbox | 8e1c37b3-d723-5874-b21e-cfae2b90492f | Enter: Teambinder Approval number
| textbox | 4c476490-af3f-5f92-ad28-ad08bef4a6d6 | ---------------------------------
| note | 60d524ee-84f2-5d59-8207-8aa9325e033b | METHOD: Document Review
| note | c16d099c-3585-59f9-80b7-8f9c965095f8 | FREQUENCY: 2 weeks prior to installation of design verification testing
| textbox | 4e37b77a-1628-51a4-bac9-c5ca0fe80d1d | ---------------------------------
| note | d7f9d2c0-9f1a-5835-b1c4-9c3c624e3613 | CATEGORY: HP
| textbox | 6ca6dfa0-4723-54ac-a18e-41d129ca4e81 | ---------------------------------
| note | c88571f6-d437-5569-b0fb-bcc7599be2b7 | RESPONSIBILITY: Nominated Authority
| textbox | f5b49b05-603d-5bab-b50d-b5a9428cb453 | ---------------------------------
| note | b64e1614-dd3c-523b-9ab6-a49a57c5d4f0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | a7837535-9e0b-5d3a-b10d-5c81c1a7c72d | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.7 Soil Nail Testing - Type I / Design Verification
| note | 60b200ab-253a-537b-8037-bc0a97720639 | REFERENCE: IFC Drawings
| note | f3b4d510-268c-568d-b851-7748d10c8c9e | 683.12 (a, c - d)
| note | 48e28db2-2f2b-5ae7-8968-ad28feb3de12 | 683.13 (a - b)
| note | 1fac2777-c654-5f12-ab57-c8de8f271e75 | Table 683.161
| textbox | 52287a01-3ef2-597a-b8d0-35f4590f9046 | ---------------------------------
| note | c3a2da89-af2d-5b8e-99eb-804e17b46e7b | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
| note | 3aa1adff-add2-5419-932e-e6c4ac07f642 | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
| note | a99760f2-3718-5e1b-8dfb-d9f4fac1d569 | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
| textbox | 6a3e652a-3137-5219-a288-6521b0b5ef32 | Enter: Teambinder Approval number
| textbox | ac1fb734-b0e4-5160-96b0-75e5a60eba33 | ---------------------------------
| note | 11ef4be8-6137-5c7e-8c3b-160164ceda58 | METHOD: Document Review
| textbox | 57a09666-3607-5181-bee2-3a7f79ba9fc0 | ---------------------------------
| note | 803c7779-ec02-564b-963c-88e368eb85ff | FREQUENCY: Once, 3 no. tests per soil/rock type
| textbox | 4ae33ff9-86da-5595-9a04-2ce6d656104f | ---------------------------------
| note | 11603087-7cb7-5b67-a7c2-3dac9a05bee1 | CATEGORY: WP
| textbox | 909fcaab-9c3a-537e-8938-e21a1e96404d | ---------------------------------
| note | e210df3f-4eae-543b-a01f-bffbd90afdd5 | RESPONSIBILITY: Nominated Authority
| textbox | 2545549e-2d4d-5461-984b-460307b4bf1d | ---------------------------------
| note | 10b95497-4c24-5460-9865-6aebc69634c9 | VERIFYING DOCUMENTS: This ITP
| textbox | 233e7335-a233-507c-a03f-49a26df3c500 | Date Completed:
| checkpoint |  | 2.8 Testing - Type I / Design Verification Test Failure
| note | 8f011211-44e4-5bd5-a571-f59302a13f17 | REFERENCE: IFC Drawings
| note | 7daf4487-027e-5c12-b608-08c0d35a29b2 | 683.13 (b)
| textbox | 795e0b92-5dcb-5352-b51a-7462cd11cf3b | ---------------------------------
| note | 37b2f275-3b81-5fe8-9e9e-48e06f3c9a5d | ACCEPTANCE CRITERIA: Where applicable, if any Type I / Designer Verification Test results fail, Type II / Sacrificial Testing & Exhumation Testing shall not proceed.
| note | 3133254b-a359-561d-8d8b-9715574941d2 | Where this occurs, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
| textbox | b6b72171-858a-50f1-ba0d-eac327120175 | Enter: Teambinder Approval number
| textbox | d7d8ce4b-0639-56bf-aabc-e3a064d3fd4c | ---------------------------------
| note | 66c1b89b-19a6-52be-b317-ffeffd923054 | METHOD: Document Review
| textbox | dde484b9-084b-57cf-933a-290467533dc5 | ---------------------------------
| note | 049e77f5-0b82-5fc0-a65b-a2a8cfbd028f | FREQUENCY: Where applicable, per failed test result per soil/rock type
| textbox | 554beeb9-5aab-5ff6-bdea-149869a6c7f7 | ---------------------------------
| note | a24285f4-bfb7-5c2f-8f18-71327561700b | CATEGORY: HP
| textbox | 87b602d7-9df6-5b0e-8196-cee94b3ff612 | ---------------------------------
| note | 9b72baa8-4e9e-53ef-b71d-3d3679066a7d | RESPONSIBILITY: Nominated Authority
| textbox | 57410ca5-17fa-55d8-b31a-01d7c5433b1d | ---------------------------------
| note | f61dfe0b-326a-5602-8293-4f2e6a3484f0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 848d21ed-4a3e-5ceb-955a-11fda91a6ca7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.9 Testing - Type II / Sacrificial Testing & Exhumation
| note | d222c1f9-b2e6-51e2-a3e6-404bc6fa22ea | REFERENCE: IFC Drawings
| note | 769802d2-f152-5349-a89e-41866fe7c8c2 | 683.12 (a, c - d)
| note | 9f83e127-cbea-5131-bcf5-677831ac24e2 | 683.14 (a - c)
| note | 15933a5e-3d05-5203-bc75-e96bd02f983f | Table 683.161
| textbox | 534c1d42-c288-5005-bb4e-b76d50309ae0 | ---------------------------------
| note | 667491b4-fc8a-5fba-8051-1d86dcfc1cdd | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
| note | cd517285-4320-56a0-ab8e-d29a311a810a | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
| note | 99d4f216-b4b2-556f-8110-1680c7596550 | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
| note | b1cf3aa0-22a6-5710-8c42-c911696adf55 | Exhumation of the sacrificial nails shall be conducted in a manner to avoid damaging the grout column and cut into 500mm lengths with ends photographed to prove grout cover of the nail.
| note | ea77599a-0507-5adf-abde-e9495f45678b | Note: Dispensation from Type II testing in rock can be requested if:
| note | 85ecaa19-c48e-5b48-8449-2e428cfaae02 | i. All Type I test results pass in that material
| note | f7c62384-ecbb-5ed1-8d3e-c6d969627c99 | ii. The material is not weathered more than slightly weathered and/or less hard than a Rock Quality Designator (RQD) of 50
| note | 579ba860-b933-5176-af7f-9b3197738c24 | iii. Encapsulation sheaths are used for steel nails
| textbox | 162f943d-e32b-5792-8157-818f5e0cbc82 | Enter: Teambinder Approval number
| textbox | 92471bfe-6114-531e-835c-548dd864f282 | ---------------------------------
| note | b51ce695-6cb2-51c3-b372-4f144abc5c74 | METHOD: Document Review
| textbox | d27a14ed-8882-5bc9-b57b-df5ae98c913a | ---------------------------------
| note | 1547ee96-6b20-5bdf-8ace-bc907458e2d8 | FREQUENCY: Once, 3 no. tests per soil/rock type
| textbox | e8af9ef6-df8f-5ae6-9c3e-49b78c071215 | ---------------------------------
| note | be5e5c85-8d1a-5c70-83e4-c24260aca286 | CATEGORY: WP
| textbox | 9cd1d961-e7af-5ac5-8a15-cb0520801650 | ---------------------------------
| note | de22735a-7ce7-5464-966d-98902b2d91a6 | RESPONSIBILITY: Nominated Authority
| textbox | 33b87f49-6dd2-5654-965c-1e362eb971ba | ---------------------------------
| note | 5f802263-0370-5b60-9918-ed8360b01f95 | VERIFYING DOCUMENTS: This ITP
| textbox | eaf5e6ab-188e-5b83-8eb1-d0c3f5923387 | Date Completed:
| checkpoint |  | 2.10 Acceptance of Test Results
| note | b8a4b109-1545-53ad-8f02-e44c2b8ae380 | REFERENCE: 683.10
| note | 5da4cb18-c334-5e26-ab61-64359bedab0f | 683.15
| textbox | 3ebdf783-c661-5aee-9d53-066d8411bc90 | ---------------------------------
| note | 9c340c67-24ca-5e3e-84e6-43c292326d8a | ACCEPTANCE CRITERIA: Installation of production nails shall not commence until the Type I & Type II test results have passed the design requirements (inclusive of any re-design assumptions).
| textbox | 82a1b61c-e10b-55bf-a0e3-3f5d2200e625 | Enter: Teambinder Approval number
| textbox | 535dfa05-7010-51cf-96e4-6ac0dd1de65f | ---------------------------------
| note | 1decb756-c2f5-5821-89a9-e4d4c47680ec | METHOD: Document Review
| textbox | 5ed65322-ed21-5fb7-ab76-fa22946ab564 | ---------------------------------
| note | 1b85ce4e-719c-580d-ad47-0100c5e79970 | FREQUENCY: Once, 7 days prior to commencing production nails
| textbox | 4df6eeb0-df3c-5290-ae9b-23a0d39cd019 | ---------------------------------
| note | 3ce7a06c-ed67-57e3-80a0-225a3ea6101c | CATEGORY: HP
| textbox | 25f93f0b-d466-5d12-9deb-a42f3cd66734 | ---------------------------------
| note | 1e791755-9c51-5ad8-ac21-d7fa4420d67d | RESPONSIBILITY: Nominated Authority
| textbox | 17073e51-f668-5e5f-a28d-f4469276d41e | ---------------------------------
| note | b658adf9-2e98-5927-95df-2be3b0309e1e | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ed9bc0ac-d509-5173-a5f9-f1df3b503546 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | 3 - Pre-construction Activities
| checkpoint |  | 3.1 IFC Drawings
| note | 8b37bceb-f850-5049-8e37-f6ecf75ea5a2 | REFERENCE: MRPA Quality Management Plan
| textbox | d320526b-465a-5380-aaad-b4241d814e2c | ---------------------------------
| note | 4202c127-d178-517d-9515-e6d64e142a4e | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| textbox | 880c6a7a-8004-548f-b68a-b8fd5d60677a | ---------------------------------
| note | 87f1f6d9-0a4d-5dbe-bb6e-6bd0da61974d | METHOD: Document Review
| textbox | a7424a3e-3613-5f95-8df5-596406bc331a | ---------------------------------
| note | 47917390-2935-5036-8d5d-c7ef75b18ed8 | FREQUENCY: Prior to starting Works and at regular intervals
| textbox | 426afd9b-d143-5e8a-87e4-ef9af6369aa3 | ---------------------------------
| note | 907d40aa-7305-5f5e-97b5-16abebfebc59 | CATEGORY: HP*
| textbox | c4bf677b-5c0a-5bc9-bbc7-1aafd741e3ec | ---------------------------------
| note | 2c61632b-84a6-514e-bdbb-967f7101a2ce | RESPONSIBILITY: All
| textbox | 3937a70c-100e-511e-95d4-cd03faf4179c | ---------------------------------
| note | b53f4dc4-e73d-59cd-8b5d-6015c3438a59 | VERIFYING DOCUMENTS: This ITP
| textbox | 5c93c897-fb8c-549f-8b83-ed61a129c4c2 | Date Completed:
| section |  | 4 - Construction Activities
| checkpoint |  | 4.1 Excavation - Change of Soil/Rock Profile from Design
| note | 8ca2ff12-1064-55be-a25b-cb366a6c1676 | REFERENCE: IFC Drawings
| note | 9979d33b-34d9-59ce-834d-43a0f1d3d35c | 683.05
| textbox | 448071c3-3941-5363-9c08-ca157f129170 | ---------------------------------
| note | 5b6357b7-fbad-5a48-a2de-8f1af2df5457 | ACCEPTANCE CRITERIA: Excavate in layers shown on the drawings.
| note | db53aef6-1aaa-55d6-92a8-f5e9101aa9e0 | Where applicable, if the Geotechnical Engineer's representative determines from an on-site inspection that the soil/rock profile does not match the design assumptions, no nails shall be installed until the design is verified or amended to the satisfaction of the Superintendent.
| textbox | 6cae916f-517c-54db-aadc-4b78af4ffad7 | Enter: Teambinder Approval Number
| textbox | 00007321-27cc-5321-bd0c-5739dd40ddc4 | ---------------------------------
| note | 8997fa20-5725-53a4-bc77-9157a86bc5b3 | METHOD: Visual , Document Review
| textbox | 51fc8814-9089-535b-bbb8-e6a32253eca9 | ---------------------------------
| note | 2271c8b0-877a-5fb9-8f49-76a6a939fd95 | FREQUENCY: Where applicable
| textbox | 843a25dc-4304-5c13-852e-acdbded21185 | ---------------------------------
| note | 445d1e76-af79-5744-8110-cecfffb28a36 | CATEGORY: HP
| textbox | 9b40fa6b-63f2-58af-8978-7b42ba063096 | ---------------------------------
| note | b7e8f920-ba30-5cd1-97ee-8913c16b8d94 | RESPONSIBILITY: Nominated Authority
| textbox | c7eeeba2-d663-5784-b5c7-ef8be8b67664 | ---------------------------------
| note | d1307d90-cd60-533f-935d-0d5ac8103f77 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | f968cb25-ead6-5922-9aba-d313595668c7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.2 Drilling
| note | cb50fcc1-f8ba-5633-acec-9fe4bdd52ce0 | REFERENCE: IFC Drawings
| note | 94d3d461-0b79-5983-ba95-812aef8068eb | Soil Nail Work Procedure
| note | dcdd78dc-ab01-57ae-b9ce-e32d954f0c3a | 683.08
| note | a47dd736-be71-5664-a16c-b9f785b6701b | 683.10 (b)
| textbox | a0c48dfb-b508-5fe9-a281-34cbbebf8e68 | ---------------------------------
| note | 9de54406-67b9-539d-a668-c8e27ca05ebc | ACCEPTANCE CRITERIA: Drill holes shall be the depths, diameters and angles shown on the IFC drawings using the equipment stated in the Work Procedure.
| note | a96e6c0c-09c0-5e1c-83fb-7847afed077a | Where casings are used or sheathing is omitted, the hole diameter shall ensure that the cover to the nail is 40mm min.
| note | d6426b53-82d3-525d-88ff-cda82ed83b75 | Drilling records shall be kept including any observations or difficulties encountered.
| note | 9e14d5cf-f90c-5cf7-a8bb-d3016d7baca8 | Only air flushing is permitted, no drilling fluid or water shall be used.
| note | 77a135e3-7e18-55c6-9cad-17428e458276 | Placement tolerances to comply with the following:
| note | 4743c1a6-b34b-5dd3-abc4-0d5f000ebae9 | i. Horizontally = ±50mm
| note | 8a69fbd5-385f-51e1-98b3-c497a5958250 | ii. Vertically = ±50mm
| note | 765feb50-1a91-551d-ae5d-db6a4b95c532 | iii. Alignment = 1:20
| note | 0bb2b771-4ea6-512a-99e1-6128d3020f21 | iv. Straightness = 20mm in 3m
| note | a1c5720d-5867-5cad-aabd-cf4b07f0f324 | v. Inclination = +0° to -3°
| note | 1151f443-227d-5e9e-8c64-254548a647b1 | Attach: Drilling Records
| textbox | a44c1a62-a968-5736-b939-b7c6c045e8f8 | ---------------------------------
| note | a638dd4f-9b27-526f-87dd-0871421fe036 | METHOD: Measure , Visual
| textbox | 6d0a814e-0ad1-5f1c-bb5f-435820eb9a8f | ---------------------------------
| note | 65ad43af-1b0a-520d-861b-639595601c5f | FREQUENCY: Each drill hole
| textbox | 30f2011d-7288-52b6-a5e2-6c0465b7c6d3 | ---------------------------------
| note | 3034cecb-870a-5dde-9ab5-f33d4d598527 | CATEGORY: IP
| textbox | b79da07f-82c9-5bd4-89cf-2739265046fc | ---------------------------------
| note | 18ab4154-b13a-5eae-84a9-22b2310a8769 | RESPONSIBILITY: Foreman , SE/PE/SPE , Surveyor
| textbox | 48abfeb2-cb2a-53a6-9c7d-13fb6202f291 | ---------------------------------
| note | c13426b5-7c26-540d-919e-c5729494fbfe | VERIFYING DOCUMENTS: This ITP
| textbox | 7455d910-e334-546d-be13-a518feab50f7 | Date Completed:
| checkpoint |  | 4.3 Hole Inspection
| note | 034e8400-ad11-5c99-9f80-8f06acdfc6fb | REFERENCE: 683.10 (c)
| textbox | fea516f1-db03-58c7-b7c6-f7c6238ffa8e | ---------------------------------
| note | 952a90b9-77ad-5342-bf41-1457c142e8b2 | ACCEPTANCE CRITERIA: All drill holes shall be inspected following air flushing and prior to insertion of the nails.
| note | a78810f5-50eb-5013-8e5e-d0f8fc80b807 | Drill records shall be made available for review.
| textbox | 9b6bd351-b53c-5e99-b1d5-14dc7fecf568 | ---------------------------------
| note | 49c22d0c-0eb8-590f-adc8-0b3771cd4a4a | METHOD: Measure , Visual , Document Review
| textbox | 0948ca6b-ba3d-5596-b502-53540b529821 | ---------------------------------
| note | a8d6a0aa-3f61-59d7-9aa1-75f872154d04 | FREQUENCY: Each drill hole
| textbox | 2653f0be-4d9b-5d7a-b3c4-0dad2214897c | ---------------------------------
| note | a2c0bbd9-f651-59f1-bf8a-cd60a3589afb | CATEGORY: HP
| textbox | 26c25ee5-9b75-52a4-9df9-c31b1fe94c35 | ---------------------------------
| note | 37198fb5-73a2-51bf-8111-34e3a06acf69 | RESPONSIBILITY: Nominated Authority
| textbox | 9b5db251-86aa-55e2-8cb9-77c1ba220620 | ---------------------------------
| note | b2ee366e-c008-59ec-98e8-7e666963a659 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 2e9da4ac-faec-5e6e-891f-367797b8b48f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.4 Nail System Installation
| note | 48830854-e936-5cd7-8f44-d638f0b0d428 | REFERENCE: IFC Drawings
| note | 09d32fcc-49e5-502f-bda8-b80e0c80eae0 | 683.07 (c - f)
| note | e13b2d3f-401c-5b18-b971-1427f29f5f82 | 683.09
| note | ac15887c-133d-5be7-9859-5e2f21c0e4e0 | 683.10 (c)
| textbox | ff72fdea-5d09-5950-85d8-4e5b7ada5fd9 | ---------------------------------
| note | 0c1dcc67-6863-5a30-a5e8-947aac6fe008 | ACCEPTANCE CRITERIA: Each nail shall be made from the correct material, be the diameter and length as shown on the IFC drawings and be free from defects or damage.
| note | 4c437968-1135-5c22-a9a3-ac57325f4016 | Centralisers shall be spaced at 1.0m max., ensuring that 40mm min. cover is maintained all around.
| note | ebd2bcf0-1e89-53cb-b4f0-e354cdc9eb92 | Steel nails shall be encapsulated by a corrugated sheath unless previously approved during the Type I & II testing.
| note | 39a463a7-cd07-5b28-8cd0-ed03b0b0260c | Steel nails shall be isolated 300mm min. where they are to be in contact with the shotcrete facing using tapes or other approved methods.
| note | 304b10f6-dd3a-50b1-a751-f93058a1d022 | Grout tube shall be positioned at the base of the hole to displace any moisture present in the hole and to prevent entrapping air.
| note | 5759e0a0-23a0-5526-84f9-60a610fbd774 | The resulting set up shall achieve the minimum bonding length, projection and be able to resist the forces expected during the grouting operations.
| textbox | 928f65e8-1dd1-5755-88ac-6e006ab748d0 | ---------------------------------
| note | 83c28525-fca5-5fc5-b8d4-021bf6ce69db | METHOD: Measure , Visual
| textbox | 440cced3-fac2-57f3-867d-43f30d7b7bcb | ---------------------------------
| note | 1ee03b6c-9e0b-5173-ad2e-96ba82b6faaa | FREQUENCY: Each drill hole
| textbox | 049bd4e4-0ee1-5b58-baf8-4cf3ce6ce05f | ---------------------------------
| note | d3511938-fcbf-58de-a999-7d90979035a2 | CATEGORY: IP
| textbox | 7b476d68-5594-59fa-9108-bff89b229dc1 | ---------------------------------
| note | 7752dc2d-66c3-528e-88d8-f942a21f06bf | RESPONSIBILITY: Foreman , SE/PE/SPE , Surveyor
| textbox | 5c05afd6-0cc8-5564-87b8-b6e791d4264e | ---------------------------------
| note | 65a22f31-8ce7-56e1-8c85-c27476313a5d | VERIFYING DOCUMENTS: This ITP
| textbox | 0f7cd4ea-195b-5bc1-9c78-ad87565b6088 | Date Completed:
| checkpoint |  | 4.5 Grout Mixing
| note | ff17a4db-9ab2-548a-a2a9-30526ffcfba3 | REFERENCE: Soil Nail Installation Work Procedure
| note | 6f9ae91a-207a-5f1d-8723-398680010529 | 683.11 (b - c)
| textbox | 8eadb511-2e86-5594-90d0-1f17937ff011 | ---------------------------------
| note | 2bc7a16c-a00e-53ec-a32b-c32dc175bd46 | ACCEPTANCE CRITERIA: Grouting shall not take place when the air temperature is below 5°C and above 35°C.
| note | 50d571e9-4e07-50fd-a261-8fea8eca5893 | Mixing shall continue for at least 2 minutes and until a uniform consistency is observed using the same equipment nominated in the Soil Nail Installation Work Procedure.
| note | 6424f0c2-efc8-57fb-94eb-60b0569d330f | Grout shall be discharged/pumped within 90 minutes from the addition of cement.
| note | f133aa06-d4b1-511a-a9a2-764bb8235e37 | Record: Required information on the Grout Pour Record
| textbox | 54b7392b-6d7a-5241-97b9-64b8ee77d22b | ---------------------------------
| note | 2808a7e6-edad-51c0-b735-3a425387a840 | METHOD: Visual , Measure
| textbox | 74c6e687-92b6-5eac-b04f-fb1b379a1991 | ---------------------------------
| note | 2470b907-4e6c-58f4-ac61-0963ebae8b76 | FREQUENCY: Each batch
| textbox | 57c6ff5d-21b4-539c-ab56-926d61d34f58 | ---------------------------------
| note | 91ac0a69-0d4c-56d6-9392-a241bf1ba521 | CATEGORY: IP
| textbox | 1806f4d9-a949-50ce-975d-bb038f83110c | ---------------------------------
| note | 1d4d71a7-3578-574d-9811-d7d91537c8e7 | RESPONSIBILITY: Foreman , SE/PE/SPE
| textbox | a10ac021-335d-5188-a4a8-b9eac883f1bd | ---------------------------------
| note | 403d1a25-d8e6-5042-b337-dd001d469413 | VERIFYING DOCUMENTS: This ITP
| textbox | 9426d6f7-c5e6-521f-b7c3-0078e3a6ef96 | Date Completed:
| checkpoint |  | 4.6 Grout Testing
| note | 76470448-47fb-518b-bd2d-8acee0c172d1 | REFERENCE: IFC Drawings
| note | ccbf0459-262a-5304-aeef-fbb618a2dbee | Soil Nail Installation Work Procedure
| note | 461bbf64-ed0e-5c94-9134-5d5834ab0a42 | 683.11 (a) (iii)
| textbox | 9e8bb86e-0ca5-53c0-949c-4c63bd028f77 | ---------------------------------
| note | 28c15df1-6eec-5015-9936-0efcad223f78 | ACCEPTANCE CRITERIA: Each test shall consist of:
| note | 59d4d63a-dfc7-5611-860a-85b34ebda014 | i. 3 no. compressive strength cubes = 2 no. 7 day strength, 1 no. 28 day strength.
| note | f391f7b4-ee45-5da2-b6ec-cc75008b12a4 | ii. 1 no. flow cone test = result between 10-30 seconds
| note | 88507eb5-04dd-53d2-abcd-30408466ee18 | vi. 1 no. bleed test = result ≤2% 3 hours after and shall not exceed 4% at any time with all separated water gone after 24 hours
| note | bf6760bc-1ee0-511b-a4c2-3346c64ba8e3 | Record: Required information on the Grout Pour Record.
| textbox | caf55ba9-ff8d-5d6f-978b-bd3397c5e5bd | ---------------------------------
| note | 0bedebea-990d-5de2-bbfa-7576faae79d2 | METHOD: Visual , Measure
| textbox | 3f2d10ee-5cdd-51c4-9b37-93971e70dee8 | ---------------------------------
| note | d25a73af-48eb-5449-bda1-0a56fd3f4e51 | FREQUENCY: Each 5m³ or part thereof batched per lot
| textbox | 8e5c17bf-f217-59a2-807c-9664e5eb5329 | ---------------------------------
| note | f07d81fb-cac5-5a8e-9fc8-a9d2a8f69b1d | CATEGORY: IP
| textbox | b32f4fa7-93d6-5d04-8e9c-94499f0158ab | ---------------------------------
| note | 4658d647-8d30-5ba3-a051-43f0aa307f62 | RESPONSIBILITY: Foreman , SE/PE/SPE
| textbox | a60ba54f-a128-57e9-81e4-3b8eccfde3b5 | ---------------------------------
| note | d72c6ca4-15de-5dfa-a028-9da99f58fb2b | VERIFYING DOCUMENTS: This ITP
| textbox | 32012b33-093f-5d7b-aaf0-3d4b1172e68e | Date Completed:
| checkpoint |  | 4.7 Grout Pumping
| note | 69ae5d1f-92dc-5e03-bdb9-0bed319f22bc | REFERENCE: Soil Nail Installation Work Procedure
| note | 3ac42710-3b73-5452-86a9-bc802aecc410 | 683.08
| note | 472e9d1f-2be9-5386-a31e-35bc73342ca3 | 683.11 (b - c)
| textbox | d8fde818-c752-55d9-8dcc-0fd689e43d38 | ---------------------------------
| note | fe7320da-3f10-5212-b951-dae7b9345472 | ACCEPTANCE CRITERIA: Grout shall be pumped in a continuous operation and monitored with flow and pressure gauges so that the flow rate is between 0.3m to 0.6m per second. Where temporary casings are used, these shall be extracted progressively once 0.5m of the hole has been filled.
| note | 69bde867-51be-5035-aa1c-6a65d185d99f | The volume of the grout used per hole is to be recorded and checked against the theoretical volume.
| note | 4b841cdc-d916-55db-b50d-e52b56aecddb | If grout seepage has occurred, the grout shall be topped up to the required level.
| note | ac960c96-e125-503c-b8fe-c2130c6093a5 | Where applicable, if the actual volume is 10 times higher than the theoretical volume, pumping operations shall cease at the completion of that hole and be reported to the Superintendent - no further grout shall be pumped until the conditions are reviewed and approval to proceed has been provided.
| note | 8ba14717-f106-5250-bc4e-6ea6b0ff86a8 | Record: Required information on the Grout Pour Record
| textbox | 06094381-c1ec-5df6-9b37-c022489ff393 | ---------------------------------
| note | 311c87c8-4cef-5c8d-a048-15bec1d286da | METHOD: Visual , Measure
| textbox | 9f4b1d00-5826-562b-ada0-57341078ff7b | ---------------------------------
| note | 9fe65439-5e04-5197-9468-47f8dac77931 | FREQUENCY: Each batch
| textbox | f4f2534b-8f92-5080-81d6-bb5456c7f5d8 | ---------------------------------
| note | d1a1eb84-378e-5f51-949d-12bdb4a43baa | CATEGORY: IP
| textbox | fec37e55-cb11-5b11-a493-52b545320c7e | ---------------------------------
| note | 09c211e2-c1cd-518b-9347-906c40195ac0 | RESPONSIBILITY: Foreman , SE/PE/SPE
| textbox | e6586461-9906-5a89-9377-1db8d5ab2c40 | ---------------------------------
| note | ea5374d5-6dfe-5f75-b164-3395337b5fee | VERIFYING DOCUMENTS: This ITP
| textbox | 8946a889-7ea5-545e-9e13-4fe21eacdd44 | Date Completed:
| section |  | 5 - Post-construction Activities
| checkpoint |  | 5.1 Grout Compressive Strength Results
| note | cfd248d0-7633-5436-b681-be31f15c82a6 | REFERENCE: IFC Drawings
| note | 0c5613bf-9718-5882-9790-4b0ac5f94e4e | Soil Nail Installation Work Procedure
| note | 4b27d359-8b56-5e7d-90d6-cfdee75e2bb8 | 683.11 (a) (iii)
| textbox | 4c153eb7-5e19-5400-b2df-4b12b57068e1 | ---------------------------------
| note | 6ba8bde0-5957-53e9-8de3-aa7e94c811cf | ACCEPTANCE CRITERIA: 7 day compressive strengths to achieve 32MPa min.
| note | 366c9123-a228-5264-8199-a35c6bc8f779 | 28 day compressive strengths to achieve 40MPa min. (Robinsons Road)
| note | ea3e5886-1ac6-5e7b-8518-a332c75eb32f | Attach: Compressive Strength Test Results
| textbox | 47c2a2df-b416-506c-bb79-33a06d44cb8d | ---------------------------------
| note | 7c2a8448-be87-56e6-a157-9b8337a71f89 | METHOD: Document Review
| textbox | 1c95279f-a9be-5ed6-ad83-8e479bf83ba6 | ---------------------------------
| note | 729de32c-7b7a-5d15-8042-4ee5aad766bb | FREQUENCY: Each cube
| textbox | 15ecd5fe-3911-5ce4-beeb-51abf309f9dc | ---------------------------------
| note | 8d347c11-86bb-562e-af61-9eb65110ba51 | CATEGORY: IP
| textbox | a97429e5-e538-5f68-96d8-fcba48dd4cec | ---------------------------------
| note | 4ffd6482-0f66-5e25-99f2-4287188a3a8a | RESPONSIBILITY: SE/PE/SPE
| textbox | b2bfec5f-b85e-5ab2-8616-ba34e0912a5a | ---------------------------------
| note | 15021bc9-5237-5566-a1d3-3686e86925f1 | VERIFYING DOCUMENTS: This ITP
| textbox | f2c94929-48fc-58a4-809e-c4de928d8a35 | Date Completed:
| checkpoint |  | 5.2 As-built Survey
| note | afd0177e-ed10-5379-83ba-38079dfd5509 | REFERENCE: IFC Drawings
| note | a95d9919-b89d-5a17-b924-72b2cbc6938f | 683.10 (b)
| textbox | a66cbcf2-c3e2-5f92-905b-0d3a9f7e3827 | ---------------------------------
| note | 53b9bcc4-d51d-571a-8c87-04d4665be947 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate nails comply with the following placement tolerances:
| note | a9aa4cb0-1b64-57f6-8549-e6ef32196c74 | i. Horizontally = ±50mm
| note | f068525e-b97b-5997-bd39-bbb644831390 | ii. Vertically = ±50mm
| note | 68186ab5-2658-58e4-ab8a-86975776ab88 | Attach: Survey As-builts / Survey Report
| textbox | 9ad3b089-e4c6-57a0-9e8f-ba1ac7620bf5 | ---------------------------------
| note | 14ac2b89-a51b-53e5-9ac2-65accda76661 | METHOD: Measure , Document Review
| textbox | 909e2ff3-4ab8-5b1f-9ba6-c7e8c8b15080 | ---------------------------------
| note | 59164c13-8558-51be-a39c-42ae15d2ab3a | FREQUENCY: Each nail
| textbox | 489a0871-f11e-5cf3-90e5-247d54a8b040 | ---------------------------------
| note | 782f2fc8-f299-5d55-84ce-88c37a354d08 | CATEGORY: IP
| textbox | c7d62d3c-240c-5681-ada1-03eff66c45bd | ---------------------------------
| note | 7f93ea03-8e3f-50da-b5f6-02d9306d48a2 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| textbox | 5bcd1d04-0c63-5507-b267-81dec67a3600 | ---------------------------------
| note | 8527e93e-490e-58c5-ad96-d264c0ce3672 | VERIFYING DOCUMENTS: This ITP
| textbox | 9c859ad5-3163-502f-a839-8ef254a60b60 | Date Completed:
| checkpoint |  | 5.3 Testing - Type III / Production Testing
| note | 9e43963a-ac96-5402-9651-5406c796a465 | REFERENCE: IFC Drawings
| note | 65feb292-4a6a-51d7-9cca-b024840e6169 | 683.12 (a, c - d)
| note | 92dfe28e-8772-55d4-a5e5-b9e3cf775cfb | 683.15 (a - c)
| note | 449fbafe-a9de-5187-a81f-d5bd50f1735b | Table 683.162
| note | 89381391-b6d7-5d0c-b5f7-52dacde08cfc | Table 683.163
| textbox | 62c5af8e-e9b8-5b92-a51b-755f06047613 | ---------------------------------
| note | 993e20c0-85c2-5595-978c-f8b620408365 | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
| note | 3a28ec3e-6c1c-59b5-9499-fc8ac26153d1 | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.162.
| note | 838b3e94-69af-53df-abbe-472c46f04f66 | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
| textbox | 8910e8f2-90f2-5ff7-b539-fbcf1b5d32d5 | Enter: Teambinder Approval number
| textbox | 5281420e-b14f-5b38-a6d0-c39b972580f4 | ---------------------------------
| note | a8efab48-4943-5aab-827b-4af9d53f48b5 | METHOD: Document Review
| textbox | f79239eb-5bdf-58de-8450-47f05b813af5 | ---------------------------------
| note | af40724d-acb8-52da-bd8b-17fde71cb4f4 | FREQUENCY: The greatest value from, 5% of all nails, 2 no. soil nails, 2 no. soil nails per type of soil, 2 no. nails per installation method
| textbox | 900a6fa6-e0ba-5e2e-b89a-cdcf86652e2c | ---------------------------------
| note | ee06ef5f-ac90-521c-b64d-3b675a689235 | CATEGORY: WP
| textbox | 06751be6-cd78-52a8-9bf2-2249c382a0d3 | ---------------------------------
| note | 84527f8c-6623-5318-9ea5-efe63ed459eb | RESPONSIBILITY: Nominated Authority
| textbox | 1a7495a0-877b-5541-96de-7228c1459d53 | ---------------------------------
| note | a3035fbe-e7b5-5a71-9f3c-875cf4928835 | VERIFYING DOCUMENTS: This ITP
| textbox | e9bf14ca-2632-554c-b078-e1e4daf2f728 | Date Completed:
| checkpoint |  | 5.4 Testing - Type III / Production Test Failure
| note | f33a5977-b051-5770-a445-9a008ef50383 | REFERENCE: IFC Drawings
| note | bc04cb46-2fbb-56dc-88d7-00f6965bf01d | 683.15 (c)
| note | e7e0fec0-2601-50d2-a5b0-e1c541135028 | 683.16 (b) (i - iii)
| note | 4982e5f7-b071-54c1-8fce-efc8172aeaae | Table 683.163
| textbox | 009796b4-0717-5b6b-9d1e-307732a58626 | ---------------------------------
| note | c07ee735-4f4c-5b0e-8998-442e3b5348f7 | ACCEPTANCE CRITERIA: Where applicable, if any Type III / Production Test results fail, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
| note | e48b3741-163a-5152-88d4-3195654f2ab0 | An additional 2 no. nails are to be installed using updated installation procedures, either side of the failed nail and shall pass the load test - note that the loads may require updating.
| textbox | ba123508-1ccd-5b72-b293-c21deb3fe7cd | Enter: Teambinder Approval number
| textbox | 2db1895a-8b06-57e8-b414-4a1c6bbe7f2b | ---------------------------------
| note | d915c5fa-8e87-5501-8e48-7c45410de967 | METHOD: Document Review
| textbox | d627e9e6-9d42-5152-8e31-25d67720b495 | ---------------------------------
| note | ca1805e3-b5c5-5f65-87a2-b8dc4dd05480 | FREQUENCY: Where applicable, per failed test result per soil/rock type
| textbox | c8bafc0b-aeb5-554a-b601-6761921fab46 | ---------------------------------
| note | dbe51ed1-ca9e-5a09-af42-d564946cb277 | CATEGORY: HP
| textbox | 018f39dc-5f5b-5cc8-bdc8-eb4097c5dc39 | ---------------------------------
| note | 732791a4-7f78-59bf-909d-1fd0da333ad9 | RESPONSIBILITY: Nominated Authority
| textbox | 96bb82d4-c3fd-5740-a7b4-dfdc8d60280d | ---------------------------------
| note | c9639499-7f3f-5a07-82d8-4fa43c0795cd | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 07ae6293-dd8c-564f-bf3e-f95b28db7089 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.5 Non-conformance Report (NCR) Closure
| note | 7ef08b61-5f26-5639-a6d3-2a69258314f1 | REFERENCE: MRPA Quality Management Plan
| textbox | e493a311-c314-5256-aa07-b8b30e49401d | ---------------------------------
| note | de654f9a-66e0-55b5-8108-cc7f98bd69aa | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
| textbox | d9fe339f-e451-5e1e-9fc2-4b9b10b84e3f | ---------------------------------
| note | 8029a7e4-91d0-57fa-aaf9-f63b4e503786 | METHOD: Document Review
| textbox | 380d728b-20b7-5196-92c5-c9045e0fa05f | ---------------------------------
| note | 40242b01-63d2-5539-9931-9fe9e0da6e1a | FREQUENCY: Once, prior to closure of this lot / element / Work area
| textbox | 68f9d591-f693-5f72-a1b0-26b6ac43daf5 | ---------------------------------
| note | e42e894f-d275-5ca7-b3a8-a50414a2ff7e | CATEGORY: HP*
| textbox | 9812781f-2c35-5cab-aa47-ccd862a96d27 | ---------------------------------
| note | 92187574-2c34-5c82-9bc9-354e23b95cac | RESPONSIBILITY: SE/PE/SPE
| textbox | a58927cd-3a17-52aa-aa35-ccb6085a22a9 | ---------------------------------
| note | 23616532-5507-59ee-a9ae-ee358d4711ad | VERIFYING DOCUMENTS: This ITP
| textbox | e833127c-f6c2-5e36-8d82-000191f2a554 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | c3d29d3d-6e5a-5b27-8d69-cbb23634e72e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 8750fb25-7ee3-5a80-86af-d0810062bb20 | Name:
| textbox | 9f1fd7c7-513b-5c2f-8919-e1db60df15c1 | Position:
| textbox | 4b640f70-6a55-566e-b3b7-b63f0f5d3ee6 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Waterproofing Pits Rev 0 | itp | ITP-CIV-Waterproofing Pits Rev 0 | 63b7254e-d861-4976-ba61-130471b998ce
| section |  | Referenced Documentation
| checkpoint |  | 1.1 - Normnet Waterproofing https://www.normet.com/process/waterproofing/#3adc133a
| section |  | Preliminaries - Material Conformance
| checkpoint |  | 2.1 - Waterproofing Membrane to Pit and pit-to-pipe connection.
| note | f27a16ad-8860-5365-bc73-7a3e3f91aa42 | Reference - IFC drawings
| note | 7a114cb1-a7d3-5b51-8e7b-df72e9519d28 | Normnet
| note | c81797d5-135b-5bf1-949b-c694a0aa181a | Acceptance Criteria - Product: TamSeal 10GM
| note | 9fde83d8-1c58-5ce4-aeb4-4057062ea5a2 | Method - Document Review
| note | f3992df6-6db8-5b34-8224-1e60f35f82ca | Frequency - Where applicable, once.
| note | 7e602c6d-d1b5-5ce6-8588-eb72bd47d5d8 | Category - N/A
| note | 7033f89d-0f04-5354-b5bf-2caf2c93e1f4 | Responsibility - Package Manager
| note | fa5838dd-921b-5672-b5a3-19928eae8fe9 | Verifying Documents - This ITP
| textbox | 18feee8c-69e4-5617-bc53-5786b3207d15 | Date Completed:
| checkpoint |  | 2.2 - Waterproofing installation - GeoTextile
| note | 6741c909-f885-5e66-a2c6-9c66f4fd8a05 | Reference - Normnet
| note | d1b0b409-125e-508c-a204-02d122cf44cf | Acceptance Criteria - Product: Geotextile cushion layer >500GSM or Minimum; Bidim A49, single layer
| note | cbafa84b-2def-5787-99a6-251c73fca33c | Method - Document Review
| note | 2d501364-425e-5861-b401-d07ca25d31b8 | Frequency - Where applicable, once.
| note | 971120c4-37be-5f91-b8d2-2df7a0b987ed | Category - N/A
| note | 93a97567-53a7-5a9b-b78a-cbf7eabb3ae2 | Responsibility - Package Manager
| note | 00cbd345-d835-5861-881d-4f9554851e5a | Verifying Documents - This ITP
| textbox | 8e9c6f6f-bc72-5cb5-9b01-d610b6c32ff3 | Date Completed:
| checkpoint |  | 2.3 - Waterproofing Pit-to-Pipe - Hydropfillic Strip
| note | 2ed49504-66a8-5faf-b131-6feb9c786d5d | Acceptance Criteria - Product: Tamseal BR
| note | 067a6464-7756-5271-a767-8cd5b68090e2 | Method - Document Review
| note | ae17d87d-322a-548b-ad23-795e32b9b52b | Frequency - Where applicable, once.
| note | 25b8aa39-a176-51e4-9e80-5c235711ad9f | Category - N/A
| note | 5fb71d95-c752-5218-9f55-621e2e512157 | Responsibility - Package Manager
| note | 6e991687-ab3c-5844-a18a-9bbf44557871 | Verifying Documents - This ITP
| textbox | 513e5b6e-1689-5779-a04a-eaaabd9a2e8c | Date Completed:
| checkpoint |  | 2.4 - Waterproofing Pit-to-Pipe - Dry pack grout
| note | eba24309-7802-517e-8e97-2033c5db9e7e | Acceptance Criteria - Product: Dry pack grout Minimum; 50MPa
| note | 394acd38-8588-50bd-8a51-c4cbcffc7633 | Method - Document Review
| note | a8e28230-8154-54a4-a88f-1df48bb97651 | Frequency - Where applicable, once.
| note | f4c65dbf-e94e-583d-9c2d-9fdb86d8f436 | Category - N/A
| note | 88317fd8-0133-58c3-b992-32a3d821245a | Responsibility - Package Manager
| note | 1162a193-0cf0-5b98-b8d1-958afbbb419e | Verifying Documents - This ITP
| textbox | 2732f640-d320-58d9-ad0c-cfad756e951d | Date Completed:
| checkpoint |  | 2.5 - Waterproofing Pit-to-Pipe - Calking Sealant
| note | eeebc2d4-505c-5a30-b927-09f4b0676748 | Acceptance Criteria - Product: Polyurethane or Modified Polyurethane:
| note | 5449151c-a81a-5604-baa1-8d8138ddd46c | Chemical resistant and Minimum; Shore A >40
| note | 58d4e6c3-e97e-5874-8ba9-36628a56956f | Method - Document Review
| note | 19ed7f51-557a-542f-b5ae-21ed47c28ae0 | Frequency - Where applicable, once.
| note | b41f8e71-d87f-5a83-b477-09b3854ab2ac | Category - N/A
| note | ad920ddd-7dde-52a6-b4f5-58b50ddd12eb | Responsibility - Package Manager
| note | 2e65bfd2-4746-5049-a511-3843626d5a51 | Verifying Documents - This ITP
| textbox | 1a3f0fa1-202a-5eff-8f17-97fc088c6281 | Date Completed:
| checkpoint |  | 2.6 - Pit Penetrations
| note | b13c63a8-fdea-517e-9a9b-cd584abcb409 | Acceptance Criteria - Confirm Pit Penetrations have been cast in right locations or have coring schedule to complete core holes after Pits surfaces have waterproofing membrane applied.
| note | fb58a58d-70dc-553b-8d72-f35e24739297 | Method - Visual, Document review
| note | 807cebc7-32e9-5599-9ea6-91671af3a93c | Frequency - Where applicable, once.
| note | cecde187-701e-538a-aed0-eaed326bee3c | Category - N/A
| note | 1d8308e1-a416-5051-b40b-1f5d09f487ba | Responsibility - Package Manager
| note | 57ab721f-4a61-5c13-a23e-67d18fc6c1de | Verifying Documents - This ITP
| textbox | 49adbdfe-657f-5dad-aade-3701e4271838 | Date Completed:
| section |  | 3 - Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 - Inspection of substrate
| note | 34731f04-caa3-53e8-a1e8-3049828f307b | Reference - Normnet
| note | 1426b82c-be62-58f8-b919-63058c431cc7 | Acceptance Criteria - Normnet Representative signs of on Normnet Quality Control Inspection Checklist "1.Substrate HP TS10GM" and uploaded to this ITP.
| note | b5b4b574-8c0e-59cf-aea5-805b45486535 | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | 1b8b343a-dd21-5d54-a91a-740ea944dc54 | a) Concrete substrate is clean, dry and free of dust and other deleterious material. Min 25MPa Comp./ 0.5MPa Tensile
| note | ad67e1c4-ca78-5a40-b896-e1198f90d0e0 | b) Substrate has no active water ingress
| note | 6f2918af-3842-55b0-bbf1-528adc962e57 | c) Any mechanical fixings, starter bars, are clean and free of visible rust and oils that can inhibit bond. SA-2. Interface is level with main substrate.
| note | a68d866c-30a8-5eb0-ab8f-ad2753f1cd99 | d) Surface profile is suitable for optimal consumption rates.
| note | cd09e5eb-d737-51a8-b245-e4af5caefe68 | e) Damages, voids, holes greater than 10mm are filled with appropriate mortar.
| note | ae7f0ff7-372a-5878-b8f2-42443f676df1 | f) Any temporary fixings are removed and repaired, or cut back flush without projection.
| note | a68b2dd0-0d7d-5e68-a3c0-e298a539b658 | g) Active water is controlled with drainage sheet and cementitious overlay, if applicable.
| note | 6d0f2668-ac76-5a47-a4c7-00383868b5d5 | h) Ground Anchors are appropriately protected, if permanent, strands are neat and treated.
| note | b34e6e7c-c2af-52e9-addd-f84c8000c5de | Method - Visual
| note | fa833bdd-4db2-5d5d-a62c-a2e44938b988 | Frequency - Each element
| note | 6abc338f-e8e8-5a0a-bb16-b462a6055bae | Category - HP
| note | 6047d381-9dfc-5030-908f-1bec2b211690 | Responsibility - Package Manager
| note | b7db78b1-bcf9-56d0-a917-72baca28893a | Normnet representative
| note | 9a7c8bb6-6bf7-595f-9d77-ad298a670969 | Verifying Documents - Normnet ITP
| textbox | 2d16e810-fa35-5d1f-9f3a-54704ed4ab35 | Date Completed:
| signoff |  | HOLDPOINT
| checkpoint |  | 3.2 - Install 2 coats System of TamSeal 10GM for 2.5mm DFT to Pit outer concrete surface (min 48 hours cure prior to lifting into place.)
| note | 4c45ed94-639b-5641-8781-96e44cf4f911 | Reference - Normnet
| note | 28d5bb3b-4327-5c43-b502-fbac34210614 | IFC Drawings
| note | f085c0e0-a4af-5af7-8859-c490d38e5834 | Acceptance Criteria - Normnet Representative signs of on Normnet Quality Control Inspection "membrane instal/HP TS10GSM" and uploaded to this ITP.
| note | 3667a144-01dd-5c9d-a09d-061db2e1cfef | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | f9ee53ef-8019-5fa8-904d-ad9cbc3fcd7e | a) Wet Spray machine is appropriate and calibrated for task.
| note | a9b38622-cad5-5993-9a67-730e6d39402d | b) Lead applicator is trained and approved to spray material.
| note | b33450a3-5383-5a58-aba9-9df7db9fb301 | c) Surrounding sensitive surfaces and areas are protected to mitigate overspray.
| note | dc0b1c79-7bfd-554f-883b-a117ae6706c4 | d) Wet film gauges and QA recording sheet ready. 10 tests per 100m2
| note | a6fa529e-30bc-5946-acc4-80f122ee7deb | e) Wind protection is used when airflow >5m per second.
| note | c36e76ea-53db-543d-93b0-c680181e7773 | f) Consumption markings are in place and checked against target consumption
| note | e37163cc-3366-500d-99ab-b6b0c3aae85d | g) All active water ingress is controlled and or in sublayers.
| note | ffa01ff1-a6c5-5e15-9f59-986a0ebd29d5 | h) Areas to be sprayed are protected from sun, to reduce outgassing effects. Do flash coat/prime at end of day if likely to operate in direct sun conditions.
| note | 1b4dedd8-69af-5083-bfd8-747b2d848393 | i) Trial area established for nozzle and feed system dose rates check.
| note | 8be81fb9-de95-5f8f-8a3a-724040387783 | j) Applied membrane is homogenous without holidays, gaps or runs. Overlap zones are minimum 200mm.
| note | 6af0b5b2-fd4e-5a2a-b2da-2cd3307851f6 | Method - Visual
| note | 6e073418-f595-5f56-8900-358c9c85615b | IP
| note | e3ab7ab9-bd12-5a7c-ae6d-2d849a48cfb9 | Frequency - Each element
| note | 612b78fd-be2a-5141-8d18-cbf575105cbc | Category - HP
| note | 7e7e1bae-3677-5a76-989e-dc2f258bb927 | Responsibility - Package Manager
| note | 9afe9a4c-53a2-5bef-9ffa-2e411869a1bc | Normnet representative
| note | 7eb5e3a4-d022-5be4-a45c-45e771654463 | Verifying Documents - This ITP
| textbox | d3e14747-cb30-5d8c-b730-488d293b4c4b | Date Completed:
| signoff |  | HOLDPOINT
| section |  | 4 - Construction / Installation Activities - Pits
| checkpoint |  | 4.1 - Secondary Waterproofing measure
| note | a61bb01a-0709-5966-afe5-ca4f4d658e46 | Reference - Normnet
| note | 86c3c648-91e9-5049-b073-0b383b28bb14 | Acceptance Criteria - Install Waterproofed Precast Pit into preplaced Geotextile cushion layer >500GSM & PE Slip Sheet.
| note | 4e93712d-30a4-5d8c-be26-cb480349a789 | PE Slip Sheet to completely wrap the entire pit substrate.
| note | 9323ce43-e446-586d-adbf-ff00bd8ad5b0 | GeoTextile to completely wrap the entire pit substrate.
| note | 8112b5bb-c776-5f54-85b7-1537ff9d59e7 | Note, geotextile to be installed after PE Slip Sheet
| note | 6f65ae19-4acf-57b5-85b6-be4526b86f06 | Method - Visual
| note | 8c1b1014-906c-5e76-ab2b-c67491179439 | IP
| note | 263e0200-8cd3-520d-9612-9d44b5a2de8d | Frequency - Each Element
| note | c805adbb-3ee2-5e74-ba0d-9664343cf93d | Category - WP
| note | c6cb744a-7652-56b5-82d9-7556a33021b7 | Responsibility - Package Manager
| note | 62e66a0f-0f50-5178-9cb6-e2a4424d6b35 | Verifying Documents - This ITP
| textbox | fc4bbf3d-633e-5e78-beea-6a7047de4806 | Date Completed:
| checkpoint |  | 4.2 - PE Sheet & Geotextile Securement
| note | 9d2844a0-d372-50b4-93c6-ad01e772b41b | Reference - Normnet
| note | ebf5af61-1642-5fd4-9335-66c03b930964 | Acceptance Criteria - Wrap PE Sheet and Geotextile Cushion layer up and secure with speed tape. Tape applied should be enough to hold the Geofabric in place for the purposes of finalising construction activities.
| note | 2156a78b-cb39-5964-b4c1-c09b40087f24 | Method - Visual, IP
| note | 89357036-5303-581a-8135-1853790e9331 | Frequency - Each Element
| note | 9c5c936d-3efa-55e9-89c5-6141fd31d86b | Category - WP
| note | a5a5959b-44f8-5b88-83a8-76443e16dba6 | Responsibility - Package Manager
| note | a303cc56-94cf-5ad3-bac4-463f3743424f | Verifying Documents - This ITP
| textbox | bf3b4694-f60b-50e1-9546-6c1945264904 | Date Completed:
| section |  | 5 - Construction / Installation Activities - Pit to Pipe Connection
| checkpoint |  | 5.1 - Pipe-to-pit Preparation
| note | 57ce3789-1bae-5c31-aebe-522b5b371382 | Reference - Normnet
| note | 42110495-e154-51a0-b233-61e2522669ff | Acceptance Criteria - 1. At each Pit Penetration, Cut/slice a Cross at pipe penetration and peel Geofabric and PE sheet Back.
| note | 8e5521dd-7a9f-5660-a03f-79068c0ba773 | 2. Inspect roughness/cohesion of penetration. Brush off any loose material. Where required, apply a contact adhesive around penetration to incease stickiness to temporarily secure hydrophilic strip.
| note | 50a2472a-620e-5bb7-8633-58b144ecde4e | 3. Apply First Seal around the penetration of Tamseal BR (hydophilic strip) with at least 3cm over lap.
| note | b53de24d-785b-575a-8238-77abef1476ac | Method - Visual
| note | df8f00f7-6ebe-5a33-8ee9-8579027ff6f1 | IP
| note | 5597877d-ca72-5f4c-a35e-d5910d7a9a43 | Frequency - Each Element
| note | 928e78d8-ede5-5b5d-ba1f-1fa721590e83 | Category - WP
| note | 130fc190-cd20-5e74-b130-a181a794848c | Responsibility - Package Manager
| note | 9993c9d7-a1eb-5cf8-865b-ec6b71e3beaf | Verifying Documents - This ITP
| textbox | 810dbfc7-900f-513f-8b80-4637d69f3d86 | Date Completed:
| checkpoint |  | 5.2 - Pipe-to-pit Installation
| note | 68ed4c5a-ea02-53b6-ba09-9a08b68faf0c | Reference - Normnet
| note | a11c4508-2328-53c8-b905-100623852d4d | Acceptance Criteria - 1. Inspect roughness/cohesion of pipe outer surface for pipe length that resides;
| note | cdfcb0ca-a42b-59a2-b550-0c406a4c3f75 | a) inside of pit
| note | 74665e1f-25d9-5190-a8e9-e7c97021cda4 | b) last 100mm (minimum) from the outer edge pit.
| note | 100e5708-4505-51fd-ab21-2d5bdc547809 | Where roughness is not achieved cup grind pipe to scuff and ensure bond occurs.
| note | 2617887f-d974-5b4f-8b56-4e3d6855313a | 2. Clean any loose debris from pipe and apply Second Seal around pipe of Tamseal BR (hydrophilic Strip) with at least 3cm overlap. Then install Pipe into Pit.
| note | e8974721-d6be-547a-acbb-01d4bb5e773e | 3.Dry pack grout >50MPa Grout.
| note | 6c03770e-ce82-5c00-85a3-9cda42800e94 | Pack uniformly from one side against firmly secured backing board, ensuring full tamping for homogenous consolidation
| note | 471f807d-9b9f-5786-bc05-9d1e73f62574 | Method - Visual
| note | 1d5bd564-5b3b-5c3f-a518-5997fc3e08e8 | IP
| note | 3109d861-1741-5095-9ef6-534e6a110680 | Frequency - Each Element
| note | db1d697a-d0ac-5a5a-b4c2-52bf9308c11b | Category - WP
| note | 6fe53c54-e891-5b58-b458-0689ce5ddc26 | Responsibility - Package Manager
| note | 0429aa2a-b243-5c2c-ae51-6cedc92d6149 | Verifying Documents - This ITP
| textbox | d26bf268-5490-57fb-97e2-1a6d33a13a89 | Date Completed:
| checkpoint |  | 5.3 - Pit-to-pipe Waterproofing
| note | e873388a-541f-5599-9c48-858b767b70f2 | Reference - Normnet
| note | df31f498-610f-5672-98d6-d5ebce1db82b | Acceptance Criteria - 1. Clean Existing membrane of any loose debris and if required scuff pit waterproofing membrane for adhesion.
| note | ec6c782a-0883-5a56-8cfc-b29a0df5da14 | 2. Caulking Sealant applied at join to create bevelled edge between pipe to pit around circumference.
| note | 7463f013-62b9-5533-95c3-6d771e2bd63b | 3.Apply Tamseal 10GM, with minimum 100mm overlap on pipe and pit.
| note | c4ed1c4a-4897-59e5-836c-2bdb80cdc2d0 | Method - Visual
| note | 810bd2aa-cb06-56af-ac9d-74681bc7008d | IP
| note | b6de31ca-1c49-5243-9bea-5fb96c8ec23a | Frequency - Each Element
| note | d47f60b3-b977-5817-92df-ec20231e40ef | Category - HP
| note | 22eb724d-8cec-5753-8fe1-2f8e6eec05b0 | Responsibility - Package Manager
| note | 9dd309b7-c44b-5287-8ceb-729585e24b5d | Normnet representative
| note | 6e902019-7b5a-5955-a72c-f0c48f6d52cb | Verifying Documents - This ITP
| textbox | 58c14c86-a307-5716-8b58-fe81fc514a10 | Date Completed:
| signoff |  | HOLDPOINT
| section |  | 6 - Construction / Installation Activities - Riser
| checkpoint |  | 6.1 - Riser Installation(if required)
| note | be5c723c-f3d0-5f18-adac-fe21d758a1b6 | Reference - IFC drawings/Auspits certificate of specification
| note | 80661e2f-b85e-5c91-ad28-961f119b2d0d | Acceptance Criteria - 1. Drill 16mm holes for N12 150mm embedment into shft wall and grout with approved high strgth epoxy. Maximum N12 spacing 200mm; follow Auspits reinforcement design.
| note | 14fd9847-fc48-5660-b282-d72ccc7f16ab | 2. Form wall 150mm thick at final level.
| note | 0f5de028-14ea-5f7f-b5af-d0a700dc758a | 3. Apply Tamseal BR (hydrophilc strip).
| note | a468ba65-b0c8-52a9-9370-91e2d4c140b9 | 4. Pour 50Mpa Concrete
| note | 362c1fc9-88e3-5f75-881d-0db05d07fa65 | Method - Visual
| note | aa469e15-2ae3-5d25-a808-d9ee7a572e05 | Frequency - Each element
| note | af452bc2-9ec8-5664-b4a4-9737766802e0 | Category - HP
| note | 043d0140-9b16-597c-94df-a2266c1fedc3 | Responsibility - Package Manager
| note | e65960fa-a5a5-5b07-90b3-56ce5cbdde08 | Nominated Authority
| note | ec91860b-adab-5dde-9952-61fd3681b01e | Verifying Documents - Normnet ITP
| textbox | d58355e6-5e5b-5278-bf2f-a4b55d50a6ad | Date Completed:
| signoff |  | HOLDPOINT
| checkpoint |  | - Riser Installation - Inspection of substrate (if required)
| note | 3c4b1720-7e21-5601-a6be-6768c684f797 | Reference - IFC drawings/Auspits certificate of specification
| note | 1317e33f-3b69-58dd-ad1f-6435105a0ae6 | Acceptance Criteria - Normnet Representative signs of on Normnet Quality Control Inspection Checklist "1.Substrate HP TS10GM" and uploaded to this ITP.
| note | 6151efc5-e30a-5e6a-884d-c9f30f787886 | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | 274a4f31-4e2b-5bf7-a9de-90307841ebbd | a) Concrete substrate is clean, dry and free of dust and other deleterious material. Min 25MPa Comp./ 0.5MPa Tensile
| note | 19991064-1b8e-5bd1-ae00-26fc9f707977 | b) Substrate has no active water ingress
| note | 4f9523c2-450e-5db6-bf76-1c84b3071c6c | c) Any mechanical fixings, starter bars, are clean and free of visible rust and oils that can inhibit bond. SA-2. Interface is level with main substrate.
| note | b08329e1-abf5-58e9-bca7-826717af670c | d) Surface profile is suitable for optimal consumption rates.
| note | 4d0ec9e9-0f3c-58f1-af31-33e5ea150ed6 | e) Damages, voids, holes greater than 10mm are filled with appropriate mortar.
| note | 7ffcb6e4-bab5-5e42-8c13-ae316701984c | f) Any temporary fixings are removed and repaired, or cut back flush without projection.
| note | 5357200c-703a-58a6-b577-c235c9069eba | g) Active water is controlled with drainage sheet and cementitious overlay, if applicable.
| note | ddf4ca2a-1c9c-5a01-b553-0f56907c14d3 | h) Ground Anchors are appropriately protected, if permanent, strands are neat and treated.
| note | e363b93a-31b1-5540-a183-7f66b8d4e461 | Method - Visual
| note | d9bbd1b7-670c-59ed-981e-17ac54ab5ef7 | Frequency - Each element
| note | 79daea2c-57c2-53a5-af85-d0f378be679d | Category - WP
| note | bfb0ca47-594f-5e89-9c3d-70393647e24e | Responsibility - Package Manager
| note | 3284f433-ab1d-5d00-af3e-2ec02ac9f350 | Normnet representative
| note | 6a8be22c-c4b1-5f55-a48f-9b7fe89bcadf | Verifying Documents - Normnet ITP
| textbox | 58b97d1d-970e-5f61-84bd-982e94729fae | Date Completed:
| checkpoint |  | - Install 2 coats System of TamSeal 10GM for 2.5mm DFT to Pit outer concrete surface.
| note | f7ade13f-1f83-5598-a62e-2227c39de678 | Acceptance Criteria - Normnet Representative signs of on Normnet Quality Control Inspection "membrane instal/HP TS10GSM" and uploaded to this ITP.
| note | 85e601aa-0405-532d-9891-2a4ec1f6fa1e | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | abbd3e13-4006-55ae-ad17-b7fa7a7ab3e7 | a) Wet Spray machine is appropriate and calibrated for task.
| note | c54e13c6-9465-5f6f-86ee-99f4c17a5426 | b) Lead applicator is trained and approved to spray material.
| note | f4ce426d-a931-5bab-9e69-fef033cd6e98 | c) Surrounding sensitive surfaces and areas are protected to mitigate overspray.
| note | 5ec1194b-732d-54f3-a582-dba78674d50d | d) Wet film gauges and QA recording sheet ready. 10 tests per 100m2
| note | b903c745-fd30-5d73-b7b4-72a383298282 | e) Wind protection is used when airflow >5m per second.
| note | 0b943c79-4e6e-5ea1-b63a-67bb63c4a819 | f) Consumption markings are in place and checked against target consumption
| note | e01c5930-246a-5a12-a7c3-5d6c43d724a1 | g) All active water ingress is controlled and or in sublayers.
| note | 5e1b94ad-334e-5110-851b-3babca4c6059 | h) Areas to be sprayed are protected from sun, to reduce outgassing effects. Do flash coat/prime at end of day if likely to operate in direct sun conditions.
| note | 95b96809-481e-5da4-a8a8-2fc6f5031818 | i) Trial area established for nozzle and feed system dose rates check.
| note | ddca0740-f51f-532e-9d5c-30ce175a8dc7 | j) Applied membrane is homogenous without holidays, gaps or runs. Overlap zones are minimum 200mm.
| note | 491a6679-f3f8-5c8b-a70f-9d5592e5de37 | Method - Visual
| note | 3e57bdcb-3088-5576-97aa-391fb8261e90 | IP
| note | 0d493c7b-be87-561c-bd2b-62f53e99acd9 | Frequency - Each element
| note | 3330a6b2-c5d0-55d5-82e3-20586489b241 | Category - WP
| note | bc967ddb-25c7-5631-8cd0-e555cf930a9b | Responsibility - Package Manager
| note | 0b996f49-d59e-5fb3-910a-8ffb9242c0f7 | Normnet representative
| note | 9310087f-f8ab-5349-8174-86a137f3d019 | Verifying Documents - This ITP
| textbox | 5bb45386-4b03-58c3-975d-5c69d7412939 | Date Completed:
| section |  | 7 - Construction / Installation Activities - Backfill
| checkpoint |  | 7.1 - Backfill
| note | fc98468d-8558-5198-9c2e-129db13bd17c | Reference - Normnet
| note | 95d12182-d80b-55b5-9c1d-0d387e6d0d6f | Acceptance Criteria - Apply backing board against pit wall
| note | d676b2db-344e-5877-af70-df202ccebfe7 | Method - Visual
| note | 2b706b22-f335-570b-82f6-a0ae1150d51b | IP
| note | 7c0d05bf-8ad3-50c7-aa73-a6c74a39d158 | Frequency - Each element
| note | 775fa447-bffd-5dde-a3b8-519ca77476cc | Category - WP
| note | 187b521e-6199-526f-9fee-13d2220a4c4c | Responsibility - Package Manager
| note | 4af703bf-25e2-538d-ae89-fcc25eba4507 | Verifying Documents - this ITP
| textbox | 6d772b54-593e-56a8-bf14-25665ba50d6a | Date Completed:
| checkpoint |  | 7.1.1 - Backfill
| note | a8145fb5-7cc9-58d3-925a-c410bc4f8f12 | Reference - IFC drawings
| note | 51475bca-7a52-5db2-a7db-ea3834e403f1 | Acceptance Criteria - Backfill to underside of Tanking Slab Blinding with 3% stabilised sand
| note | 2641614b-4d65-55e2-8541-8fa417deb7f2 | Method - Visual
| note | c036cc7b-b4e1-5929-a494-5eff5f03fa96 | IP
| note | ac9c3204-f2a9-555f-aff1-bcaa3e50015e | Frequency - Each element
| note | fc4a0069-b089-5da0-b679-585fa86bcc20 | Category - WP
| note | 51d6857c-46d8-5295-8803-a1156f69f9bd | Responsibility - Package Manager
| note | e40b06f6-e064-530c-a100-fffd4f911d79 | Verifying Documents - this ITP
| textbox | 9756a4e3-1bf9-5be2-9ed1-f50ae2177d10 | Date Completed:
| checkpoint |  | 8.1 - As-built Survey
| note | b9ef051a-bd74-5a17-90b9-ab9a433f4a54 | Reference - IFC Drawings
| note | 08527173-62c3-5add-8263-6a18bd4923cd | 610.46
| note | a31db7e3-9a6f-5b64-a5fa-3d2e2b33dd95 | Table 610.462
| note | 97a0916c-de09-5609-a3bf-e529151d3d1e | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
| note | 73440e18-51f2-5cbb-80fd-0f210bebec52 | Attach: Survey As-builts / Survey Report
| note | 0b1dae99-0946-5c79-a0b8-39b00aa8fb60 | Method - Document Review
| note | 881dcab0-e62b-5106-9aef-9b23e8623bcb | Frequency - Each element
| note | 05539f03-fe34-560e-9000-a542e76b827f | Category - IP
| note | 17af5f8d-9322-5d89-9e1d-3854d9c28a3b | Responsibility - Surveyor
| note | 7868055e-fa04-5ff8-a795-eb9d17eb455f | SE/PE/SPE
| note | f10fb826-403c-5890-8c58-9eb25e258d60 | Verifying Documents - This ITP
| textbox | 1a6f6efd-630a-5faa-ac8d-71b3817762f7 | Date Completed:
| checkpoint |  | 8.2 - Non-conformance Report (NCR) Closure
| note | 1df51623-5a8e-50a5-aaa5-e812d436c354 | Reference - MRPA Quality Management Plan
| note | 673b23c1-1261-5cdd-9a14-d03e13de0b06 | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 57487395-42df-5c3e-a396-a15ad2d70ce4 | Method - Document Review
| note | b0702f20-b6f4-5e2b-b13e-dbed44f2b3f6 | Frequency - Once, prior to closure of this lot / element / Work area
| note | 9df62269-4178-5e0a-9aec-8d6ab12d2945 | Category - HP*
| note | 9d35380b-2dda-516c-925e-f03c1a59618f | Responsibility - SE/PE/SPE
| note | 06117eec-7349-5b42-953b-5e21215eb2b7 | Verifying Documents - This ITP
| textbox | 4dce2839-9221-55f9-b61d-cf34ac3d2b87 | Date Completed:
| checkpoint |  | Final Inspection
| note | a12ebb7a-7be6-5aea-898a-3246dfdf1ccb | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 389c64b8-da0c-542b-ba1b-c26248e17a6f | Print Name:
| textbox | 222feef3-2613-55a7-88df-d5497124a6db | Position:
| textbox | dabd53e5-19e0-5e64-a75d-80213070580a | Signature:
| textbox | 4dba2a06-0d55-573a-a94f-9ba4e45bd765 | Date:
| checklist |  | ITP-STR-Precast Crosshead & Fenderwall (Supply, Installation & Stressing) Rev 0 | itp | ITP-STR-Precast Crosshead & Fenderwall (Supply, Installation & Stressing) Rev 0 | 63db9936-795d-462f-b0a9-077b80d704f3
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | ab442cfb-43e9-5a6a-bb95-77835ef4906c | Document Title: ITP-STR-Precast Crosshead & Fenderwall (Supply, Installation & Stressing)
| note | 54f25152-1605-522d-b58d-b231509d3226 | ITP Description: Precast Crosshead & Fenderwall (Supply, Installation & Stressing)
| note | d6a68cd7-deac-5dba-a1ce-f898ff7eea0e | Discipline (e.g. CIV/STR/RAIL): STR
| note | b8f54d35-5292-580a-be57-c4af9836ae8e | Revision Number: 0
| note | eabe7e3a-7b9f-5790-8cf3-ac61ffdc5a13 | Revision Date: 08/07/21
| note | 27d56c6c-f180-51fc-a0f3-20a20926cedf | ITP created by: Thomas Hudson
| note | b3c4918c-bc55-5d37-b57b-88a69c9ce65f | ITP approved for use by: Aldrin Guinchoma
| note | eb14aa1f-8db3-546e-a2c7-3cc1d81090c4 | 1.1 VicRoads Section 610 June 2019
| note | 4fbd3093-8b92-5cb4-86d6-8f7b5f26c1d3 | 1.2 VicRoads Section 612 November 2018
| note | 088e1b28-f53b-586a-acbc-6ccb627d192f | 1.3 VicRoads Section 613 June 2017
| note | 071acbd1-2b9f-5bb5-9ce8-01206649de7b | 1.4 VicRoads Section 614 June 2017
| note | 59b4cbaf-614d-527a-8aac-d77cf6d2fb66 | 1.5 VicRoads Section 620 May 2009
| note | f6efca1c-acf5-559d-8676-236f9a5bd595 | 1.6 VicRoads Section622 November 2018
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Grout Product Selection - Cementitious (Non- Shrink 32 (min) Grout)
| note | f23b0df1-77fc-51dc-885c-ca402029ce47 | REFERENCE: 612.18
| note | dbb2681d-1b4c-5863-b3c0-f07319033f5b | AS 3972
| note | af78c861-b404-5dc5-99ca-8bd9e5e70de1 | IFC Drawings
| note | 4e6a5117-c466-55cf-a3eb-482b3609ba5e | ACCEPTANCE CRITERIA: Cementitious Grout
| note | 1cf8744d-a689-5091-b2a4-12b4d5d71477 | Details of the materials and the proportions of the grout mixture shall be submitted to the Superintendent for review.
| textbox | dbf53173-b140-56c1-9a97-2390468ce042 | Enter: Teambinder Material Approval number
| note | 2ec6085c-e0f1-516f-b091-5b8f1f3589df | METHOD: Document review
| note | 3500c01f-eefb-5233-be84-484826711b7c | FREQUENCY: Once, for each product, prior to placement of product
| note | 1a0f7117-540a-5013-8637-f9c06e499f0f | CATEGORY: HP
| note | 781f7fe8-12e7-5766-acec-981f7e5c9d90 | RESPONSIBILITY: Nominated Authority
| note | 5d904cca-21de-595f-9b36-6716c42d28fb | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | a14b0544-56d1-5580-91df-ef95e49be65c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Grout Product Selection - Epoxy (60MPa (min) Epoxy Putty or Megaepoxy PM)
| note | 7a2c6cad-2b46-5001-9440-3943aa984bc4 | REFERENCE: IFC Drawings
| note | f72fd8b7-50e7-53f1-a66f-bdc152e05c3c | ACCEPTANCE CRITERIA: Epoxy Grout
| note | e1639c5e-599f-56b3-99a7-fd35bff6d43b | Details of the materials and the proportions of the grout mixture shall be submitted to the Superintendent for review.
| textbox | 32ae7293-8332-5b4c-8f16-dd900a56c106 | Enter: Teambinder Material Approval number
| note | e259251a-cc78-53d6-a4c3-6c9218d54629 | METHOD: Document review
| note | 1160c9dd-a374-5f5e-aee8-cb8ef4af8ba4 | FREQUENCY: Once, for each product, prior to placement of product
| note | 442ea591-a578-5c5d-be65-1cba13c88bff | CATEGORY: HP
| note | 2935a52b-9bbe-5f7c-9395-ef11a392d227 | RESPONSIBILITY: Nominated Authority
| note | 52807115-6e6b-5e09-8b9c-599776666bf0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 50091c08-1a0a-556f-89f4-d365ad47ed4f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Supply of Anchorage -Manufacturer's certificate of compliance
| note | d57a49e6-73bf-5801-b016-819c3b1b98a3 | REFERENCE: 612.04
| note | ea5db592-9c46-53c0-8f48-456bdb6e00c0 | IFC Drawings
| note | eabb475c-a4d9-564c-bbf6-7076a670dc5f | ACCEPTANCE CRITERIA: Anchorages shall be tested for compliance with the requirements of AS/NZS 1314 - Prestressing Anchorages and the test certificates shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for the testing laboratory
| textbox | 88952c58-4e9e-5516-88d2-25ae40f3cd7f | Enter: Teambinder Approval number
| note | d5183ecb-55e5-53d9-a193-0193ec38b96c | METHOD: Document Review
| note | 82a1472b-b058-54b2-9dbe-1ff5d6ea5b1d | FREQUENCY: Where applicable, once, install
| note | 0a98580c-15eb-5a5d-a506-2de661278422 | CATEGORY: HP*
| note | 98f7b9f2-c9ca-5002-8068-c9f30027e0c8 | RESPONSIBILITY: Nominated Authority
| note | 1177cb33-094b-5542-84ca-81113276a8ef | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | f66cc1bd-9715-5718-992f-2e39aafb4ef7 | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Precast Elements - Crossheads & Fenderwall
| note | 0aa08532-beee-5f8d-90f7-9a65125fd935 | REFERENCE: IFC Drawings
| note | da85ba15-2352-5d2e-a561-5ca62ba3decd | 610.47
| note | 69970c4e-bf40-5aac-980f-9cff5e96d63b | Table 610.472
| note | b1d115f8-458b-55f4-ab96-a94c06206e2e | ACCEPTANCE CRITERIA: Pre-cast onsite element QA documentation has been reviewed for completeness and compliance.
| note | c360d478-1826-5991-83b0-db43b42fc9d9 | i.Completed ITP-STR-Structural Concrete
| note | 81f2b399-74ec-5239-ba4a-0e26ea5e9f2f | ii. Compressive strength test results (6.7- Early age compressive strength)
| note | fc29622d-2b8f-5d90-ae91-21331c39accc | iii. Covermeter check record
| note | 5da3eb03-9a3a-51e7-a0d4-18fef28c4edf | iv. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (ITP-STR-Structural Concrete-6.9) (±15mm for stress ducts from crosshead to pile)
| note | 23754626-8813-5567-8b45-ced8c0956ab0 | v. Precast Lifting Design
| note | ce5f32aa-f457-55e0-92a1-de6927530f56 | Note: Different revisions of 610 have different clause numbers
| note | dc55ba42-7068-5c8f-b60c-9320f2ee7245 | METHOD: Document Review
| note | e81c5c87-8ae4-5db5-89f9-e7a3222d26a6 | FREQUENCY: Each element
| note | 72bf0fda-371c-5438-8c10-ce6bac2a3c3c | CATEGORY: IP
| note | cff68290-80e3-51e5-877c-9cb119148bad | RESPONSIBILITY: PE/SE/SPE
| note | dea3e98e-207f-59a2-b931-dfc617aaa718 | VERIFYING DOCUMENTS: This ITP
| textbox | 7e341a9d-b33e-5187-a543-cad77ed5578b | Date Completed:
| checkpoint |  | 3.2 Temporary Works Designs
| note | 9fc59427-1e62-572b-9b84-ee94bb5e8f29 | REFERENCE: 610.27
| note | 9c3454fb-0ec3-5761-8632-2a89f0f2408e | 613.04
| note | 87792370-3cce-5abb-b56f-ef4263bfadc1 | 613.05
| note | 637ff422-d998-5069-a42f-057ecc8f479e | 613.16
| note | 7f936e2d-1b91-5cf5-84bc-16afe9058e89 | ACCEPTANCE CRITERIA: All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design.
| note | f781cc29-e963-5d0c-84be-578c900de043 | Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority.
| note | 743de6ed-fff1-531f-b673-2b6b4898ec0d | Attach: Temporary Works Design
| note | d64b30f2-5716-5f13-9606-dccb3d58b061 | Attach: Attachment A
| note | 0dbd2f78-ef80-5725-9ccc-7c77f107fe7e | METHOD: Document Review
| note | 3d9b569f-7181-5d85-b5c3-bd6dc761afa8 | FREQUENCY: Where applicable, once, 5 days prior to installation
| note | 722de837-650e-52d8-9e63-4887505b808a | CATEGORY: HP
| note | 7d21577c-3aa2-5b6c-aa7b-10bcf88b74da | RESPONSIBILITY: Nominated Authority
| note | 043f1a86-5c96-5ce4-8fd1-b4f68424b749 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ea98df8c-e267-5ae4-9369-eb4ba894c7c5 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Post Tensioning System
| note | 0f56ddde-a671-5780-aea8-0d60f620e793 | REFERENCE: 612.02
| note | bcc29039-1107-5f77-83e3-e01b255a1cf7 | 612.18
| note | 75660c55-1d4e-5704-8088-4cead47f47fb | ACCEPTANCE CRITERIA: Contractor shall submit full details of the proposed Post-Tensioning system to the Superintendent for review. These details shall include (when applicable):
| note | 4671a725-2102-5f32-b463-ff1cceb5cd19 | (a) drawings and calculations that demonstrate the suitability of the proposed prestressing system for the structure.
| note | 887a6534-d5cd-5f26-a4e8-141fae578592 | (b) source of the tendon;
| note | e5f28716-3c43-5970-b6e2-3340f613f66b | (c) minimum breaking load of the tendon;
| note | f6f79951-3d34-5535-a0f6-10c7470f286b | (d) maximum permitted relaxation of the tendon;
| note | 9f5446fb-75b9-5ffa-b981-45f569c9a16b | (e) modulus of elasticity of the proposed tendon material;
| note | 99011fdb-529a-5db6-a4bf-cbffeed608a9 | (f) maximum values of the friction, curvature and wobble coefficients as defined in AS 5100;
| note | f032620b-1615-568e-94aa-6c2c770606c4 | (g) predicted extension for each tendon;
| note | c72d1182-c704-59e1-a7a3-1ecf4184abe3 | (h) predicted draw in at anchorages;
| note | 093d6d3a-1072-546a-a1dd-03a4f40065e9 | (i) anchorage details including any additional reinforcement at the anchorage zone;
| note | 797d4a94-2b68-5d1f-95e6-a1a09348931d | (j) type of duct and duct material;
| note | 91836cc8-cb23-54a1-b4d4-e58bf46784b7 | (k) internal and external diameter of duct plus the type of coating;
| note | c1774d3c-2df2-54e5-90b0-16b027fa2f3e | (l) method(s) of restraining and joining the duct;
| note | 2a785bf0-b23e-5f85-af13-3defaffcb3ec | (m) proposed tensioning system.
| textbox | bdf106f6-eb22-5d44-ac1f-a4e5026fdd36 | Enter: Teambinder HP Approval number
| note | 78db6a55-7b87-5efd-a732-d1e87631b7db | METHOD: Document Review
| note | cdfb775a-610c-551a-bd8d-14de1701ba3c | FREQUENCY: 14 days prior to installation
| note | 29909527-7559-566b-b7c6-66851f97a892 | CATEGORY: HP
| note | 5fecfbba-3b1f-5cd4-bc2a-e0477e219faa | RESPONSIBILITY: Nominated Authority
| note | 3faef152-793c-5582-bcd1-e25d94ea96c1 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 01e0b880-f3eb-55d8-ae22-c187c6e51cd9 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Installation of Stress Bar & Stressing Methodology: Post Tensioning Equipment; Basis of Measurement of Tensioning Forces; Tensioning Forces Required; Tensioning Procedure; Grout placement methodology; Mixing & pumping equipment
| note | 7f49f721-2636-5a4a-bc48-0750e7d9dbd9 | REFERENCE: 612.13
| note | c915d6c4-3786-5995-9813-aab9680e9bf4 | 612.14
| note | d212a260-6952-5097-86ac-b2322cfec3fc | 6.2.15
| note | bd89e1d5-2fc1-5323-bdc5-65a3a974a821 | 612.16
| note | f17cd626-6a59-5c48-9e51-c6c12eb7382d | ACCEPTANCE CRITERIA: At least 7 days prior toPost-Tensioning Contractor shall submit following documents to the Superintendent for review. (When applicable)
| note | 669ca88f-759b-554b-89e6-b961ebb5b2d3 | 1- calibration certificate
| note | 28ad2615-dc10-5781-aa73-8ecce9a05353 | 2- calculations for extensions corresponding to the upper and lower limits of the tendon force diagram shown on the drawings
| note | 37be603e-51f2-52bb-b9d4-f5ceca2cb3c5 | 3- Where the coefficients for the adopted prestressing system vary from the values shown on the drawings, the specified tensioning forces shall be revised by the Contractor and submitted to the Superintendent for approval.
| note | 2313dbf9-a1a5-571b-a263-b7a043d6f4a8 | 4- All stressing operations shall take place in the presence of the Superintendent.
| note | 50703b35-1d22-54de-af12-7336ac6912a8 | 5- Details of the materials and the proportions of the grout mixture shall be submitted to the Superintendent for review.
| note | f77ace32-bf14-56a3-ab32-72c3c250f742 | 6- The Contractor shall give the Superintendent not less than seven days notice of any grouting operation.
| note | af437a4e-eb5c-5f14-a20c-6d8590bfc887 | 7-All grouting operations shall take place in the presence of the Superintendent
| textbox | 3fc43936-c578-5b72-bac8-d45eb0c128f6 | Enter: Teambinder HP Approval number
| note | 8514b904-c2db-5d68-a633-7b993577daa1 | METHOD: Document Review
| note | 69be082e-a38d-5e60-9a52-1a766f2a43da | FREQUENCY: 7 days prior to installation
| note | 15cc86e7-8c31-5232-8a82-ed8ac7648ef4 | CATEGORY: HP
| note | 50ce3fd0-e3f9-52c6-82a3-965ac780f570 | RESPONSIBILITY: Nominated Authority
| note | abfefd0c-de39-5f7f-b072-e20cca14ef06 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 1679deb2-d847-516b-90fa-0dd66fa70b00 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 4.1 Survey Set-out of Precast Elements
| note | 7b3625e5-c57d-534f-9e01-5e06809b7659 | REFERENCE: IFC Drawings
| note | b3557b83-ccce-5609-a20c-ffc99fd73f9e | 610.47 (a)
| note | d8c48e30-709c-5ebb-9746-4dc53e1fb9ac | Table 610.472
| note | 314b1b9f-a72a-56bd-a068-1d671edb78c8 | (March/June 2019)
| note | 5e3fa4a6-bac0-5af4-897f-49b67cab469a | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.473 (March/June 2019) as applicable to the element.
| note | 16b9e108-40cc-5ec4-8116-e93051efaf11 | METHOD: Measure , Visual
| note | b9fa6667-5ce6-551f-83a1-816bed576369 | FREQUENCY: Each element
| note | 125788ef-3504-5b54-acc5-ba3367022434 | CATEGORY: IP
| note | 1284f235-8ca0-5cc0-966f-6251e5777496 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | d91617fe-6f06-55a8-80ce-34eab3db6296 | VERIFYING DOCUMENTS: This ITP
| textbox | 6e2d76b2-e5d1-5f25-8e3f-678f6863c6a1 | Date Completed:
| checkpoint |  | 4.2 Install Packers & Compressible foam seals Placement (for integrally cast Precast Concrete): Pile to crosshead connection
| note | a0749dff-db5b-5730-abcd-6693fb8ff03a | REFERENCE: IFC Drawings
| note | 149f55d1-2f9c-5b2b-91a0-85f8e5a25a26 | ACCEPTANCE CRITERIA: Place the bearing packers to the survey marks around each pile/stressing location.
| note | c531c1bf-9aaa-54b7-ae32-a15a815113d4 | The packers are to the be precisely levelled to ensure verticality of the crosshead segment (nominal spacing is 20mm for crosshead & 25mm for fender wall)
| note | 66f3e567-a7ef-52a7-bbe9-2a930eaf7e0e | Foam seals are to be placed around piles and fixed into position
| note | 1ec20a00-766c-5afd-8b77-e85d6d3e2dbb | METHOD: Measure Visual
| note | 97c2c3fa-b4e1-55d2-8e58-45d40ae7389e | FREQUENCY: Where applicable, 8 No. around the perimeter of the pile
| note | cbe8ebf4-aa85-59f7-8d68-3e854a4f165a | CATEGORY: HP*
| note | 04fae2ed-41bf-59c7-b274-2504df7149ea | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | d5177d07-99ad-56e7-992e-7060c2339a86 | VERIFYING DOCUMENTS: This ITP
| textbox | d9cc7f68-2a0f-5e79-aec6-23cf84807156 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 5.1 Precast Handling
| note | be320a49-e4cd-59aa-86b5-c56a096933b2 | REFERENCE: 620.07
| note | df58d526-83b8-54d5-863c-fec030300d12 | Crane Lift Study
| note | d7da154b-6834-581b-a624-ea6381aa67b2 | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
| note | 32c66552-6478-59b5-9fb2-3eb70f9f6137 | METHOD: Visual
| note | 4f525eb2-efa2-5acf-83dc-29bf06fca6f3 | FREQUENCY: Each element
| note | 526a5aab-802f-5ed3-97c6-4a214a3462c1 | CATEGORY: IP
| note | dacfc458-2643-5e8b-8d85-3078c20d7868 | RESPONSIBILITY: SE/PE/SPE
| note | 78bbe5c7-27b2-5eb6-a4e4-4960aa36cbbf | VERIFYING DOCUMENTS: This ITP
| textbox | e86384ab-9c20-5f72-8d6d-6f0d48d25847 | Date Completed:
| checkpoint |  | 5.2 Precast Placement
| note | 4e4b3141-9bc6-53de-96e8-3388b27892ee | REFERENCE: IFC Drawings
| note | ee83f217-520b-51eb-90fb-f1daebdd2ae9 | 610.27
| note | 7d2b0244-f6c3-5127-b8c1-10df0123f0e9 | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
| note | 929f706f-d9cc-5acd-9a2e-1c68e2df2e09 | The nominal gap between elements is as per the IFC Drawings:
| note | 40eec447-e787-5eef-a913-7e08abfccf54 | Piles to Crosshead: 20mm
| note | 2398d1ed-e9f4-5619-a103-9bf3dd54e76f | Fenderwall to Crosshead: 25mm
| note | 1a8933d8-6597-5784-8983-5f33069a19af | Crosshead to Planks: 25mm
| note | 1dedc70a-17df-54c7-be1f-936c55354a47 | Fenderwall to Planks: 50mm
| note | 4b342cc2-6fa7-5a0a-96f6-4e0fde2f8de5 | METHOD: Measure , Visual
| note | fc060f90-b120-58c1-9510-efe8180769b7 | FREQUENCY: Each element
| note | 8b42719b-153c-5d6d-ae03-a56bc97e040c | CATEGORY: HP*
| note | 68efc968-9779-58a5-8a11-dbdcd621c71f | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 4300528c-9630-5cab-9962-c23d77766190 | VERIFYING DOCUMENTS: This ITP
| textbox | 0b870b7a-7146-5515-918e-956ee00c4a69 | Date Completed:
| checkpoint |  | 5.3 Flowable Epoxy Grout Placement: Pile to crosshead connection
| note | 4407851b-1e95-59a2-92b2-b0fb0a736f2a | REFERENCE: IFC Drawings
| note | 49c03af3-7d50-52a3-ad39-e922a570d5e1 | 612.18
| note | 609ddd15-6891-572a-bc8d-f8f0dba4cc06 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 60 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 887f25b4-9417-56b4-b703-523ebab521da | Complete: Grout Pour Checklist
| note | ac50f180-9a42-5a16-95c9-9550a49d85ca | Complete: Grout Pour Record
| note | 3171ce64-b78b-5e1a-be25-89c017708ed2 | Complete Test Results
| note | d47677ee-5a12-54c2-8ea8-5c2d2b2cdddc | METHOD: Visual
| note | 5c7fdbd7-5653-5fa6-bf90-c6bed01b2397 | FREQUENCY: Where applicable
| note | 4f782e7e-9ebc-5c1a-aeaa-9ec5682078e5 | CATEGORY: HP*
| note | 3edbff72-efbf-51a1-89ae-0a9efa57e4de | RESPONSIBILITY: SE
| note | 9309d241-1f74-54e6-b97c-a41b212e087b | VERIFYING DOCUMENTS: This ITP
| textbox | 5b51a348-0daf-5d82-a6ae-f23699b3e52e | Date Completed:
| checkpoint |  | 5.4 Flowable Epoxy Grout Placement: Western fender wall soffit (grout bed)
| note | 59f54a10-b1ef-5bd1-9574-ceaf69ce218d | REFERENCE: IFC Drawings
| note | 85b61dd0-ee74-5dd7-bac5-02944a685a29 | 612.18
| note | a1532698-937f-53c0-ab37-1c788da6532f | MRPA-RFI-000803
| note | be56c546-a5d0-5292-85f2-d3feeac14487 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 32 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 7cbc8287-4527-5eca-92da-02fcf9c9e350 | Complete: Grout Pour Checklist
| note | b81a135f-45c2-5a18-a89c-0267d8b5b2d9 | Complete: Grout Pour Record
| note | ebb42ecd-ba28-5bfa-8cbc-119c9cbc2f67 | Complete Test Results
| note | cd786cb6-56e4-548c-a3ba-667851c7301f | METHOD: Visual
| note | 6519ac54-bed2-5cfc-b79e-3092980dc4f2 | FREQUENCY: Where applicable
| note | e3ae6540-5c62-5afe-90af-a332197226ad | CATEGORY: HP*
| note | 71de7796-9e75-5b25-9d5a-55bdcc903816 | RESPONSIBILITY: SE
| note | 92f05f2a-ee95-5599-b2b9-952b70b2f2f7 | VERIFYING DOCUMENTS: This ITP
| textbox | 379a24da-8cab-52c3-aaac-e6ddbf55d00f | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 6.1 Falsework Certification
| note | f4929930-7f37-55e2-a86b-3d46bc2864b8 | REFERENCE: 613.12
| note | d5d6fb61-1e28-5d8e-9894-addb9c30c7c7 | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above)
| note | 7af06eb9-4e30-5b7f-bd2e-3e8aecc90173 | Attach: Attachment B
| note | a7ad94c0-7b96-5c07-941e-067b11a6813c | METHOD: Visual , Document Review
| note | f14f7bed-9103-5dbb-a3be-84c5c794ed07 | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
| note | 14df4ea0-8d8d-5e57-a6f0-7b4879c64f26 | CATEGORY: HP
| note | f4a6bde5-b664-59e6-9a00-e1f6a14219f3 | RESPONSIBILITY: Nominated Authority
| note | fff18b24-c111-5bf6-8354-714a72e3dcfc | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 51b889a4-0110-567c-8ad8-ca3eba0b6683 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.2 Required strength & age of concrete for stressing
| note | f2a53e5d-4e78-5fd0-a414-230f8ea9c384 | REFERENCE: 612.11
| note | 4d5fe1bb-bc09-521b-93f4-890fa28696ab | IFC Drawings
| note | 15cee9eb-20dd-5da1-a07e-e159a69db423 | ACCEPTANCE CRITERIA: The post tensioning force shall not be applied to a member until it has attained the compressive strength of 40MPa
| note | 409b0fd4-a278-5031-8915-f07cc24b9128 | Upload Concrete Test Results
| note | d3527a54-9dc4-5a3a-95ce-e3d425f6f4a8 | METHOD: Document review Test results
| note | 72208c54-fc1b-5608-89d5-c422beeb79b9 | FREQUENCY: Before Stressing
| note | 9f050680-810a-531f-84a6-d83fd97748b6 | CATEGORY: HP
| note | 234c51d7-650f-5b96-81e5-db04b3d01e95 | RESPONSIBILITY: Nominated Authority
| note | 8b34dd26-a2a9-53a8-a2fd-d9ca1deb8edd | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b5b6d76f-396b-581b-973b-adc8ca22be5a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.3 Required strength for Epoxy Grout for stressing
| note | 6021a0bd-b33e-5a9e-9b9b-693c68727032 | REFERENCE: IFC Drawings
| note | eea39ef2-04bc-5a04-8471-b7da50cc6d4d | Compressive Strength Results
| note | 9f4fdc1f-176b-5246-9571-905b8c4d2e1b | ACCEPTANCE CRITERIA: The post tensioning force shall not be applied to a member (crosshead) until the grout (cementeous/epoxy) has attained the compressive strength of:
| note | 7274fc1e-907b-5270-a809-cfcc14d01d04 | Stage 1 Stressing: 15mPa
| note | a6ccea1f-5328-5332-b1e0-0d5bbae3c8b4 | Stage 2 Stressing: 26mPa prior (outside piles) & 18mPa prior to stressing for central piles.
| note | fd1d45fd-bc08-53ea-8f63-68063d55a85d | Upload Concrete Test Results
| note | 386a1cf2-91ee-5373-88ca-c52cc0d366f5 | METHOD: Document review Test results
| note | d1f0fc52-ecab-5aed-b36e-5eb750a46098 | FREQUENCY: Where Applicable
| note | 2657e1dd-45ca-51bf-afb1-18329a453bc9 | CATEGORY: HP*
| note | 9c34bbea-1488-5699-81f8-be31a9880d7a | RESPONSIBILITY: SE
| note | 465e3e8d-22d7-5154-a4f0-3ff4a15eedc6 | VERIFYING DOCUMENTS: This ITP
| textbox | f1e00987-bd94-55b7-9360-22d041f2ca94 | Date Completed:
| checkpoint |  | 6.4 Post tensioning
| note | a6ba244a-f799-5838-a824-3b5e20212b5d | REFERENCE: 612.16
| note | 2e39fdd5-f263-53c4-844e-5aabbeda390a | ACCEPTANCE CRITERIA: All stressing operations shall take place in the presence of the Superintendent
| note | 9dae8ad8-2da8-58b3-af5a-871a6fdb7645 | The following data shall be recorded where applicable:
| note | e143310f-ce68-59a0-9734-006de8a2fc4f | identification number of each dynamometer/gauge, pump and jack
| note | 3f33bc9e-4bcc-5d88-920a-9a57d472f590 | identification particulars of tendons
| note | 72ed0a59-9ce1-5207-ab37-e7101e2541fc | initial forces (or pressures) when tendons are marked for measurement of elongation
| note | 739b5013-6bce-567d-b53d-e834faa94a48 | forces (or pressures) together with corresponding elongations obtained at 20%, 40%, 60%, 80% and 100% of the required force
| note | 05632480-a698-5a99-90b6-c914a8d257a4 | final forces (or pressures) and elongations obtained on completion of tensioning
| note | 80b434e9-7a0a-5dd0-a528-431bc0f0e0d7 | residual elongations after release of jacks
| note | aaea91c7-3962-5045-a551-8a6ee8413fa6 | measurement of hog at completion of stressing operation
| note | bd1bcdc1-af95-5555-88e2-ab626efb2106 | the nature of any unexpected occurrences and the corrective measures taken.
| note | caaf7af1-05bb-5f0b-97d9-bb609bce1a7f | Completed records shall be submitted to the Superintendent on completion of stressing.
| note | 9350e24a-f088-5e27-9397-95571a6fec6a | Attach: Subcontractor post tensioning ITP/check list/tensioning record
| note | 08c0c754-3d1e-511d-bfe5-9af028e5ffd8 | METHOD: Document review Test results Tensioning Record
| note | 09770b68-fbf9-54f0-bae6-8bd9f5c1496e | FREQUENCY: Where Applicable
| note | f52ab938-75f0-5ad9-ae36-e1f32af8af70 | CATEGORY: HP
| note | 3500620d-7825-5104-a9a9-9e39b4a6ac02 | RESPONSIBILITY: SE
| note | 49008dbc-6478-5818-9048-0dcfb99f08df | VERIFYING DOCUMENTS: This ITP
| textbox | 7bce4176-229f-56ec-8b25-1f057a4522e4 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.5 Scabble back stress bar recess
| note | 4f97f2c3-4332-5fc7-9bd8-78d85c4dc755 | REFERENCE: IFC Drawings
| note | 1567d321-34e6-5521-b63d-d924f8f1255c | 612.18
| note | 790a2eed-1a32-54b6-a585-035c8404584f | ACCEPTANCE CRITERIA: Stressbar anchorage recess surface to be scabbled and bonding agent applied prior to casting in situ infill grout.
| note | 3d0b5659-792c-5e3c-83e9-c159f1d8e8a9 | METHOD: Visual
| note | 61c4a5e3-069d-587e-bb3c-6fa476e86b62 | FREQUENCY: Where applicable
| note | 39b3121b-79ef-5d8a-b9fb-a8c19e4232b9 | CATEGORY: HP*
| note | 34e63f54-c304-52ec-9056-181b325a10c3 | RESPONSIBILITY: SE
| note | 99490d7e-7ae5-529e-a6f9-2b9c7461bb1e | VERIFYING DOCUMENTS: This ITP
| textbox | 83c79e9e-3ea1-5875-96ba-3b934c843988 | Date Completed:
| checkpoint |  | 6.6 Flowable Cementitious Grout Pour - Crosshead stress bar ducts
| note | 89cda083-21b7-5a27-a13c-3d227f2d123b | REFERENCE: IFC Drawings
| note | e64efbec-91e2-57fc-9a45-79ee260f3a65 | 612.18
| note | 6948fc0b-366c-5ca2-9aad-7c820e1489da | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 32 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 1a889787-475e-5f15-b38b-9cd0ebeb488f | Complete: Grout Pour Checklist
| note | 0997c103-dd07-5b55-be47-999898a225a5 | Complete: Grout Pour Record
| note | 62f2bc45-bee8-58a8-be28-72c7b3be5f51 | Complete Test Results
| note | 0618be6a-490a-5d7c-a4ad-08e301b1654b | METHOD: Visual , Document Review
| note | d344b886-826e-5e5d-9987-c38bc9ba9a65 | FREQUENCY: Where applicable
| note | ee360b64-a3f0-5c3c-9523-27445c0d71d4 | CATEGORY: HP
| note | aae2168f-cd93-5ed6-9269-f1fc6e9c6bd6 | RESPONSIBILITY: Nominated Authority
| note | f81ba75d-8778-550e-ae2c-8e22b214733a | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 5bbc42e4-48ec-540c-8b8c-8ffa2562fe30 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.7 Flowable Cementitious Grout Pour - Crosshead stressbar anchorage recess
| note | a226b016-0398-5d8d-ab0f-577ea474931d | REFERENCE: IFC Drawings
| note | afeca2d3-b325-5a94-8692-f7ec2f724a28 | 612.18
| note | 95cc34f7-3d87-5e5b-93e0-1872423cd209 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 32 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | 22ea626c-1385-53ae-80a9-7199f2d0455f | Complete: Grout Pour Checklist
| note | 9e00137f-b369-5a21-b596-5237ec418de1 | Complete: Grout Pour Record
| note | 149820ce-f450-53a7-8e30-02e3216dca8c | Complete Test Results
| note | fc195818-0ce5-5a29-8451-33e3e8ae8407 | METHOD: Visual , Document Review
| note | bfd15689-baca-5aa7-9f3e-aedf048986e4 | FREQUENCY: Where applicable
| note | 8898101c-90fb-5f49-82c4-38de355300cd | CATEGORY: HP
| note | 75920f4d-8730-52a4-b905-aeffc9f5ee8e | RESPONSIBILITY: Nominated Authority
| note | db5afdee-f11d-53e6-9fd3-1f6c780ec06e | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c5dee44d-9e6e-52b8-84b7-c394e976e073 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.8 Flowable Cementitious Grout Pour - Western fender wall HD bolts
| note | 2990d0ab-25e4-5f4a-9e90-84da3b1d13bc | REFERENCE: IFC Drawings
| note | 63d88072-7275-5afa-a99c-6065b0d0ab1b | 612.18
| note | 76ed0cfc-e995-533b-996c-47ef26b49b55 | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 32 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | adb0cf00-cb95-5576-b259-88325bebae7a | Complete: Grout Pour Checklist
| note | deff01bb-87bb-53a0-8fca-3406a4ca38cd | Complete: Grout Pour Record
| note | 4ff6481a-1216-52cf-894e-3a3486ec5ec7 | Complete Test Results
| note | aaf8b4c8-6772-5326-bd31-de2b553313f3 | METHOD: Visual , Document Review
| note | 3e1b776e-0436-5d53-84f0-a1572580d472 | FREQUENCY: Where applicable
| note | 18053f51-801e-5544-87a6-3da4db442dcb | CATEGORY: HP
| note | e89dd4a2-1620-570d-b1d9-e74e47519715 | RESPONSIBILITY: Nominated Authority
| note | a6b65b01-6a97-516b-9692-4c375b76f25f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 341eadae-3d80-5c08-975f-83e29257cadf | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.9 Flowable Megapoxy 206 Grout Pour - Plank/ western fender wall interfaces
| note | 469561d3-c122-5840-9e64-45b1681ee9e3 | REFERENCE: IFC Drawings
| note | 11dae04c-17fd-557a-8229-bbf6e4d9cd35 | 612.18
| note | 7ebbac2b-ee10-5d90-9985-38ae4187e2fc | ACCEPTANCE CRITERIA: Fill plank soffit (25mm) and plank to fender wall interface (50mm) with Flowable Megapoxy 206 Grout
| note | ff822271-7b59-5233-82d1-069fe8d58f5b | Finish top of Megapoxy 206 Grout with a JointFlex 50x15mm blockout.
| note | 6ea27da8-a933-5d04-a246-7ab806abf1f5 | The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2 shall be 32 MPa at 28 days. At least one pair of cubes shall be taken from each 5 cubic metres or part thereof of grout.
| note | d2c81cd0-b9bf-5b49-8e10-d69b3fc214c2 | Vertical gap: no strength requirement. Horizontal Gap (Soffit of planks): min compressive strength of 25 MPa prior to loading planks with Rail & Ballast
| note | e5d19721-aba6-5073-b2bb-37377dab7ae7 | Complete: Grout Pour Checklist
| note | 54e0daf0-0789-50c7-83ed-825311335823 | Complete: Grout Pour Record
| note | 07b42ed1-0a8a-5f3a-8b4c-20db2230d854 | Complete Test Results
| note | 13b02f69-17a5-55fb-869e-338edb8bc004 | METHOD: Visual , Document Review
| note | 0d7bc045-4cf5-5bea-9bd8-bcf88a555413 | FREQUENCY: Where applicable
| note | fc97069f-90cb-5432-83fa-1bd85a6b90ba | CATEGORY: HP
| note | 6febeae7-3a21-5ad8-88af-1aeafaea3f65 | RESPONSIBILITY: Nominated Authority
| note | 9da2b555-7a48-59f7-b5c4-f37d5f01c04f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 90aa77a1-3b49-5de7-80ed-d4ebb2dc7fcd | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.10 Sealant - Plank/western fender wall interfaces
| note | eaf37b77-bc8e-5be8-a5a7-8d58111837de | REFERENCE: IFC Drawings
| note | 381ed56f-cbeb-56ba-a29e-ef2da51f2188 | 612.18
| note | 9a1f1a8d-c474-5f54-9ef8-879a1b5c9ad6 | ACCEPTANCE CRITERIA: Remove JointFlex 50x15mm blockout once Megapoxy 206 Grout has set and cork joint with 50x15mm polyurethane sealant (Sika Flex fillet or approved equivalent).
| textbox | 0fbd9149-8336-5b24-bcdf-49a5f42fbc1b | Enter: Teambinder Material Approval number
| note | ca460ead-c806-5424-be90-4aacb067882d | Install debonding tape (Bitumen Tape) in accordance with manufacturers recommendations.
| textbox | ee5136e2-cbf1-5578-b988-4e59e2af23be | Enter: Teambinder Material Approval number
| note | eb773ec9-7d49-5894-b279-89f19a8590e1 | METHOD: Visual , Document Review
| note | 65aa98c1-cb2e-5143-8e12-c020973fa95f | FREQUENCY: Where applicable
| note | 087ebc22-2523-5061-99f3-fbd6a8c5e775 | CATEGORY: HP*
| note | 68c02081-06cb-54a1-954a-763b417140ff | RESPONSIBILITY: SE/PE/SPE
| note | 245f5906-f85c-5bb9-ac57-ef5c780b840f | VERIFYING DOCUMENTS: This ITP
| textbox | fe41f681-8f61-5937-866e-87032a004ce0 | Date Completed:
| checkpoint |  | 6.11 As-built Survey
| note | ba3eef8a-36b4-5dfb-865e-61376b8f2981 | REFERENCE: IFC Drawings
| note | 6a0342a6-ed94-511d-872b-e7da1b128f0a | 610.46 (a),
| note | d5884bce-c458-5fe8-9582-6649dccba63e | Table 610.462 (November 2018)
| note | 3b6d96eb-70b8-5bbb-aa8d-3d301ca578a3 | 610.47 (a)
| note | 8d77be19-683c-5e4e-aa9d-724518f68d88 | Table 610.472 (March/June 2019)
| note | 406a0d86-b301-5fc8-89c7-6f8a9b38e5a5 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
| note | f9aa9725-f8f6-5c37-b788-6266dec54f9d | Attach: Survey As-builts / Survey Report
| note | 342807c2-e28e-5799-8f1b-0aaf87ed77c7 | METHOD: Document Review
| note | acade12a-ce6a-542a-b18c-710bb7428f0a | FREQUENCY: Each element
| note | d1631afc-934b-58f1-b72b-7c96f2876426 | CATEGORY: IP
| note | 1f30c920-bab1-5aa9-a844-64667df4bb85 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 98468936-f630-57f3-95f8-16a149736a9d | VERIFYING DOCUMENTS: This ITP
| textbox | 2e9e9d3a-ece0-5654-887a-ab849795da36 | Date Completed:
| checkpoint |  | 6.12 Patching works
| note | 2d27d1ed-b9bc-5bf6-8e80-d7421feca379 | REFERENCE: Temporary Works Design
| note | 6893ed3f-48d1-5fb4-8890-38a731004c4a | 613.16
| note | d7c7b591-1095-5fc5-ac07-f8d2dd666872 | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
| note | ba0fdba6-00cb-5123-8c67-0b9a4ef09073 | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for any repair.
| note | b563ecf3-591b-5391-88bc-cb6d17c4b4b0 | METHOD: Visual , Document Review
| note | a5661533-db49-566c-bb98-39538199c2ac | FREQUENCY: Where applicable, each element
| note | 4825690a-3a97-5ca2-83d1-0bd1ad7d9c2d | CATEGORY: IP
| note | 1e80c1e3-261a-5b05-b424-76cbdc55875f | RESPONSIBILITY: SE/PE/SPE
| note | 992246dc-820a-52da-a703-77fdacb25e8f | VERIFYING DOCUMENTS: This ITP
| textbox | b6694afb-bd81-58d8-b9bf-836eb551c5fd | Date Completed:
| checkpoint |  | 6.13 Non-conformance Report (NCR) Closure
| note | 2abfece6-0139-5dff-8ef0-a06abd13d754 | REFERENCE: MRPA Quality Management Plan
| note | baa603ef-45ec-5a9b-9063-b60b4fe02881 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 472bab0f-449f-529e-8433-6490062d65ef | METHOD: Document Review
| note | ec5fc94a-b043-5ccb-96b8-be075837b89f | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | c8793f00-9702-597b-a622-1709559d35c2 | CATEGORY: HP*
| note | 23a9c978-702d-5a8b-bcd2-febcdeb80303 | RESPONSIBILITY: SE/PE/SPE
| note | 49c0c0e2-9a21-50e1-8d6e-50cbba75713b | VERIFYING DOCUMENTS: This ITP
| textbox | 0a3489fb-0fc4-58fc-aea1-1d209facf3ed | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 56a9b54e-2726-5de4-b374-d99d237fac5f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 983439f7-5484-512f-910f-7f8c6b002806 | Name:
| textbox | 9ad66507-ce88-5eb3-88e2-5ac72997501d | Position:
| textbox | 66d04286-e182-54cd-bf5d-2f93aee7ad64 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-ACO Pit installation |  | ITP-CIV-ACO Pit installation | 64b5fe32-62ec-4968-8db2-8890fa6ddf33
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 73bc26f6-5623-5c3f-bc54-9d0b550e4707 | Document Title: - ITP-CIV-ACO Pit installation
| note | 70f3d6a1-51b9-5ec6-b721-a8c063f81fa9 | ITP Description: - ACO Pit installation
| note | f6e754b4-bb77-5f64-8aba-219127a002bc | Discipline (e.g. CIV/STR/RAIL: - CIV
| note | b97fa481-45f9-5374-a39c-40c01889af8c | Revision Number: - 0
| note | 561939b3-6545-516d-a9c3-0fe6b7f3126e | Revision Date: - 44481
| note | 0b016a7c-3043-5e3c-bb1c-9dee2bf13c3a | ITP created by: - Michael Daly
| note | 4b5f86a5-fed0-53df-8a05-8a503086b596 | ITP approved for use by: - Aldrin Guinchoma
| note | ae09240c-d2e5-55b1-b92b-9118b6fdc1d6 | 1.1 VicRoads Section 701
| note | fd35eb28-2ba5-5eaa-ab23-b066d4648674 | 1.2 VicRoads Section 705
| note | 491431a4-17f7-5040-8645-f61d8a123488 | 1.3 ACO Installation Guide XDPG-BC
| section |  | Preliminaries-Materials
| checkpoint |  | 2.1 - Pit Details
| note | 2eb2aca5-7724-531b-abae-9107d33a3883 | Reference -VR 705.05, VR 705.09
| note | c657b61d-34d2-528c-92f9-0197eccf0cb4 | Acceptance Criteria - Pit Supplier: ACO Pit Lid Type: Grille/Welded Bar Grate Pit Type: ACO: XDPG-BC Enter: PIt ID, Line Number from IFC Drawings
| note | 0fd00d9b-4d5b-561e-b97b-af5ff48f0af3 | Method - Document Review
| note | 0ec1ce2c-e431-5c3e-bf2c-6e62f6fc909f | Frequency - Each Element
| note | 498b621b-98c2-5d36-b331-dbe773fe7459 | Category - IP
| note | d81e122f-6d83-5a1a-b6ba-9669feb9cc68 | Responsibility - SE
| note | 0f6b4215-afc1-5d15-8088-60ec6e717dca | Verifying Documents -This ITP
| textbox | 228d4233-6bcc-5a74-bc7f-018a6e111e0b | Date Completed
| checkpoint |  | 2.2 - Embedment material
| note | 512d5a55-f8a5-59cd-b0ce-0fb97db45da4 | Reference -VicRoads Section 701.09 (d)
| note | 0f270046-e187-5301-8b63-d6fd0e01d859 | Acceptance Criteria - Materials used for bedding shall be free from perishable matter and lumps and shall conform with the following requirements; 100% passing 19mm sieve 5-40% passing 0.075mm sieve PI (Max) 20
| textbox | b1a15007-368b-4ce4-97e2-8efb16ed778e | Team Binder Material Approval number
| note | 267e3be1-357b-557c-806a-2339d6b76e82 | Method - Document Review
| note | 4157656e-88f3-521a-9b98-c03d8c660354 | Frequency - Once for each Lot
| note | 4aee7a6f-e02d-5cce-b1e0-865e3d486dda | Category - IP
| note | aaec5301-945f-5011-a5b1-7a8dfb686601 | Responsibility - SE
| note | 802b538b-0587-5654-a6b3-c0422f515baf | Verifying Documents -Material Approval Number Attach Delivery Dockets
| textbox | ffa96723-856a-5aee-9dfa-ccedcd03f64f | Date Completed
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 - Survey Set-out/Conformity with drawings
| note | fe3eeddc-1c5c-5bbe-9137-125ff78adfad | Reference -VicRoads Section 705.09
| note | ceb27c03-6a68-5a15-b8b1-80193eb175c4 | Acceptance Criteria - drainage pits shall be installed at the locations and to the dimensions shown on the drawings.
| note | 0aa4daed-c66f-56a5-8fa7-400279ecb1e9 | Method - Measure
| note | 81f9abb0-3bc8-55ff-bfc0-b18a810d213f | Frequency - Each element
| note | 31328035-7879-54c7-8a5e-4f6cd34ca068 | Category - IP
| note | 58b2f425-ddb5-5163-94e3-9903721b5585 | Responsibility - Surveyor SE
| note | 6d5a68e6-02d3-5a12-bbd0-b7d888ef4536 | Verifying Documents -This ITP
| textbox | e227cb1b-0dde-5908-8a33-2836faaeaee4 | Date Completed
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 - Excavation
| note | 5e992015-fb99-57ef-8b5f-2a4bc3da1819 | Reference -VR 705.05
| note | 9b15657a-a3ac-548f-8500-b5099dc9c201 | Acceptance Criteria - Excavation to design depth. Foundation is satisfactory. For precast pits clearance provided to each face of excavation is not less than 400mm
| note | b180b629-61a6-5d9a-af2c-c4b091298b58 | Method - Measure
| note | 2529d24c-4ad8-57ab-91ab-50e4275cdd5c | Frequency - Each element
| note | c4e2c1d3-b75f-5b25-8712-0723c79e39b7 | Category - IP
| note | 63af94d3-d290-5a65-abda-dd8750fc6c31 | Responsibility - SE
| note | fdac4ccb-2639-5ff3-8eb5-f4021f5ad2d7 | Verifying Documents -This ITP
| textbox | 16abdae8-ff4a-5f7f-bd82-f71e60ce6801 | Date Completed
| checkpoint |  | 4.2 - Bedding
| note | f8ee16cc-c34e-5130-8d5b-ee30cc6e415f | Reference -VR 705.05 VR 701.09
| note | 800755ea-8c84-5e0a-8614-b22e0dc58d75 | Acceptance Criteria - Bedding for precast pits meet requirements of 701 and compacted to refusal. 80mm for clay and 150mm for rock foundation.
| note | 4456509b-b862-5da4-a0e9-4efd5374b2fd | Method - Visual
| note | 27f9b71e-27ee-5cf7-89a8-d95d30e19546 | Frequency - Each element
| note | c571ba24-cfea-5c70-a69d-7854b69f7093 | Category - IP
| note | e0c4d1d0-ccff-5219-b317-b4fa0b1594ea | Responsibility - SE
| note | e1ec6476-084c-51bf-942e-62ec49652c39 | Verifying Documents -This ITP
| textbox | 6b51cfde-4f3c-58d8-9845-95256e5c40dc | Date Completed
| checkpoint |  | 4.3 - Placing of Regulation Concrete Layer
| note | 9b0529c6-685c-5134-9b95-93bfbce8aecf | Reference -Manufacturer Installation Guide XDPG-BC
| note | 2143bc48-1b74-5069-9efb-c74439649e7d | Acceptance Criteria - Place concrete regulation layer of minimum 25Mpa with minimum thickness of 100mm
| note | 19866065-d24a-5710-831c-c0630ae92861 | Method - Visual
| note | 15eb75b3-06c5-5792-8fb4-a5504e48e042 | Frequency - Each element
| note | 46d171a0-be69-5fcd-b863-234533647561 | Category - IP
| note | a95e401a-2fe9-5ccc-8ca2-01e672c6a8db | Responsibility - SE
| note | 41bdadfd-2596-5318-b904-ef2a2715bb9e | Verifying Documents -This ITP
| textbox | 8411dd53-398b-5d8a-9138-c8c3421efdd5 | Date Completed
| checkpoint |  | 4.4 - Placement of Pit
| note | aba5872e-af81-54e1-84bd-79c422bfef92 | Reference -VR 701.09 IFC Drawings
| note | 1d8e5710-4142-5a19-8211-664018f3a96f | Acceptance Criteria - Survey pick-up to verify - Offset pits to kerb +/- 20mm - Plan location pits not adjacent to kerb +/- 100mm
| note | 1174caf7-b25d-58a0-ad8b-9f5ebc3e4a0c | Method - Measure
| note | bfedc615-6653-5cc0-9bc9-9ec9cb0f8c57 | Frequency - Each Element
| note | 64fd2c13-955b-5635-af59-df374c31a60d | Category - IP
| note | caa75b5f-b13d-557c-bd9a-8edcf1ced496 | Responsibility - SE
| note | b0424cd9-df2d-5876-b324-0449b3950174 | Verifying Documents -This ITP
| textbox | ff1a23ed-ac6d-5df0-9102-c64960d08589 | Date Completed
| checkpoint |  | 4.5 - Pipe drainage connections and jointing
| note | bf6609c8-e239-51c3-8680-9616f45bf4c5 | Reference -VR 705.1
| note | 9be10b2e-49d0-5e4a-ab22-9e89c4487bbd | Acceptance Criteria - All stormwater connections to be neatly made. Where necessary, trim ends of drains and finish with cementitious mortar openings to be neatly saw cut to required size, not to exceed pipe diameter by 50mm Reinforcement exposed by the cutting of holes shall be coated with epoxy.
| note | c8228c5d-11d7-5654-b5a0-fc6aa9819b1a | Method - Visual
| note | 8adf2c49-fdd4-5f2a-a4e9-23f3d24806c6 | Frequency - Each Element
| note | cbbbf7fe-007e-5ed2-bcaa-d0e281f73d69 | Category - IP
| note | 33f40f04-a2db-5e4c-8268-73389de7d73a | Responsibility - SE
| note | a3849982-1fda-5268-bd0a-89aec7dddb89 | Verifying Documents -This ITP
| textbox | 02e6de41-3f94-555f-b88f-4572b966fe4a | Date Completed
| checkpoint |  | 4.6 - Shape pit floor
| note | 68dde6dd-9c8e-56f5-9912-0b30d103d722 | Reference -VR 705.12
| note | b7e752a8-59ec-59c9-8e78-72a0edcf9d47 | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
| note | 2c40c85a-bae8-5c11-a187-8bd8aaa2a1b8 | Method - Visual
| note | a0f8138f-4aeb-5332-8442-fa799f54fc4e | Frequency - Each Element
| note | 14232bf5-5de0-5c14-9720-2b01704d2f82 | Category - IP
| note | 7ec2c9af-33b9-5c8f-8817-2e5bc41c8bd0 | Responsibility - SE
| note | def556fc-5d4a-513b-91ae-35ce1343a43d | Verifying Documents -This ITP
| textbox | 1a11e2d5-244e-5f05-99bd-7022372009a0 | Date Completed
| checkpoint |  | 4.7 - Fitting of covers
| note | dcec8ef9-cdb2-5a66-9619-7fdac78dea47 | Reference -Manufacturer Installation Guide XDPG-BC
| note | c35a540e-bf29-556f-a9eb-aabf59a308b7 | Acceptance Criteria - Grille/Welded Bar Grate installed with ACO product with bars running perpendicular to direction of cyclists
| note | 83b6fe4d-e788-5958-829b-2542e7e9a61a | Method - Visual
| note | 04a8933c-3134-5b57-adb5-3beaecc4d7ce | Frequency - Each Element
| note | 0773499e-582b-5029-a7f5-921b8aaacecd | Category - IP
| note | ccdd2e29-32dd-5aae-aae2-8aa7e7b9cbd8 | Responsibility - SE
| note | b69c259d-4946-5710-ad6d-1296a9bc5e82 | Verifying Documents -This ITP
| textbox | fe11f197-96a2-5969-b18f-bf17fc499d63 | Date Completed
| checkpoint |  | 4.8 - Backfilling around drainage pits with compacted sand
| note | 948aba5e-b5ed-5c28-aa07-c8114380d622 | Reference -Manufacturer Installation Guide XDPG-BC
| note | 89aecdf6-a00d-5540-8a04-bf78fb822526 | Acceptance Criteria - Backfilling around ACO pits using stabilised sand as per drawing requirements
| note | e1c71b37-cbcc-506e-96aa-be04f9a96f5f | Method - Visual Measure
| note | bf495bfb-1c13-5c04-b670-15e0c09030f4 | Frequency - Each Element
| note | 2b30298d-60d1-511e-87a9-f061ff71cd42 | Category - IP
| note | 11c1dcb9-3a72-517c-a776-c4e2b2ef0f2c | Responsibility - SE
| note | 48e19374-03a8-5781-b8bf-acfe38df30fc | Verifying Documents -This ITP
| textbox | d78da6c5-4f1d-532e-97ec-2f9273e228c1 | Date Completed
| checkpoint |  | 4.9 - Backfilling concrete surround filling
| note | d50a8817-5a83-52e6-970e-90ec163562e4 | Reference -Manufacturer Installation Guide XDPG-BC
| note | c7c61695-e8cf-5834-a61d-d0bdc11c9401 | Acceptance Criteria - Backfill top 150mm layer with concrete of a minimum 25Mpa
| note | c53b64a4-823e-510e-9442-761427286714 | Method - Measure
| note | 4a38e5f5-3d53-5dea-b3d7-7c0bad6ea00a | Frequency - Each Element
| note | 3d75afb1-3528-5a2f-9e17-c786ef1578a5 | Category - IP
| note | 563bdbd1-0bd3-589b-b1dc-cc2e115cea21 | Responsibility - SE
| note | e30d5419-8c66-50d0-abaf-5d041599237e | Verifying Documents -This ITP
| textbox | 7c28f5d3-6742-5a00-8f38-805d49f81a82 | Date Completed
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 - As-built Survey
| note | 41465233-496a-5107-9251-cfdf5039974e | Reference -IFC Drawings VR 701.10
| note | c71c46af-489b-51fa-99e3-b0a0738d6c7f | Acceptance Criteria - The location of each element shall be recorded progressively on the Contractor’s as constructed drawings.
| note | e081e388-ea38-5997-a300-fe29e567f798 | Method - Document Review
| note | 380f9cdb-c8d4-57f3-a9d8-052eadb6cf21 | Frequency - Each element
| note | 60ad5255-4479-5d15-b4b5-f1ce014b4be1 | Category - IP
| note | b5cab600-f273-5f85-9dd1-ad85262aa6c1 | Responsibility - Surveyor SE
| note | 4b01459b-42b9-5a82-96c9-a1447585280c | Verifying Documents -Attach As-Builts Document
| textbox | 13b23574-0935-5616-9085-3d79e8ca5b2a | Date Completed
| checkpoint |  | 5.2 - Non-conformance Report (NCR) Closure
| note | 0519d3d1-950e-5956-9305-1487b22b2c9c | Reference -MRPA Quality Management Plan
| note | 92722b82-ed03-55f4-9d61-f28e326173f9 | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 0246c4f9-cd1a-5a6f-b884-d55f2392674c | Method - Document Review
| note | 5bee413a-8242-53d0-9fee-674c94607e31 | Frequency - Once, prior to closure of this lot / element / Work area
| note | 4866cdb5-6b5f-5726-976e-c6ac9dd7343b | Category - HP*
| note | 8c0c1363-7134-5ebd-b206-08f6c88b2126 | Responsibility - SE/PE/SPE
| note | e49eb777-c760-5b8b-9c9d-d836aaa91aeb | Verifying Documents -This ITP
| textbox | 7989472d-c8c8-5446-a587-0f77f7d67b1c | Date Completed
| checkpoint |  | Final Inspection
| note | 3ba298cd-cff4-5d68-8516-812c2ccf3cf0 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 0924d2c3-e5e8-597d-ba99-bf7f46d33e6e | Print Name:
| textbox | 082d4b15-b484-5ee7-bede-f23650ca8304 | Position:
| textbox | 001c05f2-7d85-56a6-ae96-c4882c8b23ba | Signature:
| textbox | 9fba6e1d-002a-53c4-8f8d-295793520238 | Date:
| checklist |  | ITP-CIV-Installation of ACO Drainage Rev 0 | itp | ITP-CIV-Installation of ACO Drainage Rev 0 | 68163b7d-3c46-41f2-aaf9-47f81336a121
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 2d400b24-3aa0-46ed-944e-9b35f37ed012 | ITP Description: Installation of ACO Drainage
| note | 46a07b2f-5256-4564-b641-55f8b9a5084e | Discipline (e.g. CIV/STR/RAIL): CIV
| note | be0daa29-b742-43bc-a18b-c8d9c0264375 | Revision Number: 0
| note | 90b96165-fdb5-4a6f-9529-e1e5a2778205 | Revision Date: 30/08/2021
| note | aaa79b38-8d76-44d1-8e44-3bea0397e375 | ITP created by: Thomas Hudson
| note | db354628-9ef0-481d-a129-47de52029da5 | ITP approved for use by: Aldrin Guinchoma
| note | 3ba16529-352a-47f8-b1b9-154a252fcb6f | 1.1 NIST-2659
| note | b2545049-9995-47e8-bc77-37f85f8f4cc3 | 1.2 VicRoads Section 610
| note | bef96df0-881c-47e8-b5cf-da8649a5e29c | 1.3 VicRoads Section 611
| note | 40f23eac-8546-43b3-ae0f-17184fa988c1 | 1.4 VicRoads Section 612
| note | 128e403d-9528-4ca5-8de0-20ca86610842 | 1.5 NIST-012.2.1
| note | 155dc097-4514-4a5f-9ddf-f313776814db | 1.6 VicRoads Section 702
| note | b5d08c41-42e8-40d2-83de-24cad17820ec | 1.7 AS 1289
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Concrete Mix (Min 32MPa) - No testing Req.
| note | 5750459f-9909-4ad4-b8fd-429b87c76aef | REFERENCE: IFC Drawings
| note | bd088020-7995-459e-9a2a-86522b0d7f97 | 610.07
| note | 04050053-174d-4395-a330-71e20341b762 | Table 610.071
| note | 4e8854dc-125b-40c7-861e-b3877dd0dc2a | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
| note | 2f1c3f46-5c1a-442d-814c-b12fd5088cb4 | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
| note | e2edbfa9-2a84-43ef-8bec-b42c401fa412 | Enter: Teambinder Material Approval number
| note | 53f02de7-7cf0-42b7-a0c2-3da7cfa8e3bc | METHOD: Document Review
| note | 738fd423-aa05-4795-8f4f-bf01d549906f | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
| note | fa70789c-f9de-494c-b7a8-b4d0a40f6d42 | CATEGORY: HP*
| note | e563110c-2708-4fb0-93c4-1e8cf72c7676 | RESPONSIBILITY: Nominated Authority
| note | d15dbc53-edbe-4755-ba89-ea73b55abca0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | f91fdb22-dd36-442b-b4c4-b95db19c3dfc | Date Completed:
| checkpoint |  | 2.2 ACRS Certification (for Reinforcement)
| note | e5107c7c-08a4-4ded-9841-fbd3964a4118 | REFERENCE: 611.05 (a)
| note | ab5a13a1-a154-4882-aca7-96a52c68b499 | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
| note | 8205910a-09ae-43fe-891a-9dd4f5645dd7 | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| note | 89b1a83d-9214-467a-8eb0-fd617013ef3f | Enter: Teambinder Material Approval number
| note | 967f5ae6-5f8e-4822-a7bb-2eee2ae5c070 | METHOD: Document Review
| note | ed12b06e-3545-4c4c-8d99-126ae046057a | FREQUENCY: Once for each supplier, 14 days of award of contract
| note | ff9cb27c-c3e1-48ce-9a68-c22088d30a34 | CATEGORY: HP*
| note | 690ebec1-de8e-4da2-a177-da4d8aef9c3b | RESPONSIBILITY: Nominated Authority
| note | ad674cb4-b5ab-4cdd-aee8-6b77e39f6e19 | VERIFYING DOCUMENTS: This ITP
| textbox | 73f60056-a41d-4892-8a34-7c0de6269387 | Date Completed:
| checkpoint |  | 2.3 Bar Chairs/Aspros Certification
| note | e108c540-daaa-4ac3-afe4-728cbe45daee | REFERENCE: 610.26 (a)
| note | 21107f11-0453-4446-bb38-331173c6fd9b | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
| note | 00e67820-580e-4ca9-a115-813c5df59e80 | Concrete aspros require annual compressive strength and soluble salt testing is required.
| note | 09b7552b-f81c-49d2-94fa-b41360cba025 | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
| note | cef9e5a1-a3cb-4dab-922a-148a2b29aa5e | Enter: Teambinder Material Approval number
| note | f892e754-0ec6-4e7e-b097-ac650100b98d | METHOD: Document Review
| note | 08d005e3-ac4c-4687-ae10-17f837df5a23 | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
| note | c7ed1513-f80a-4aa6-b91f-6cac0e4f8f24 | CATEGORY: WP
| note | 93024ca1-255f-40c2-88e3-b43b2f45afd9 | RESPONSIBILITY: Nominated Authority
| note | 2b856ea3-c3ea-4f39-9ca1-f34124e154c8 | VERIFYING DOCUMENTS: This ITP
| textbox | c8b34085-8642-46c0-9551-4d6ff4d347a9 | Date Completed:
| checkpoint |  | 2.4 ACO Drain and Lid Supply
| note | 786f3b5a-8bb7-4115-875a-33c956b0b3ae | REFERENCE: IFC Drawings
| note | 557e577b-5861-49ce-a0c5-ebe05ae492fd | ACCEPTANCE CRITERIA: Aco Drain Type: KlassiDrain K300
| note | a316727c-e663-4d5f-b5f4-3545e363a262 | Linear/Nutral Grade Drain
| note | f2df7c1f-0408-49ba-ab28-7257cc572795 | Depth 300mm (300x325mm)
| note | 41c65077-6ba6-484e-8534-80dfa3493646 | Lid Type: Galvanised Steek Grated
| note | 5e48ffca-9814-4e82-93c9-6ccd597e4def | Lid Loading Class:
| note | 23508377-7701-44d4-8376-c35a886a9b56 | Class B for non trafficable areas
| note | 1b89ae82-2765-47dd-bf89-b138c925c3f8 | Class D for trafficable Areas
| note | ab06b720-3714-4c7f-bdfd-eb53979270ec | Enter: Teambinder Material Approval number
| note | 8e318c2b-bb6c-4900-819b-31be8c682e04 | METHOD: Document review
| note | 34dc1d5a-8ba1-40ba-b560-bbda55e6be49 | FREQUENCY: Once, for each product, prior to placement of product
| note | 69883b0b-d0f0-4030-a64a-ff9b3edfacd7 | CATEGORY: HP*
| note | 40526244-f350-4547-a7cf-030e42771e4c | RESPONSIBILITY: Nominated Authority
| note | d9313dc7-b1ed-410e-b1df-69f2014b2a58 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 070ee91d-3ea1-4dee-a08b-23042d2469a2 | Date Completed:
| checkpoint |  | 2.5 Pits and Pit Lids (Class D area's only)
| note | 99ae166f-6f6d-429d-b3d3-57f71db560ec | REFERENCE: IFC Drawings
| note | 9589afe9-af75-4ced-997f-c47020e5e526 | VicRoads SD1121
| note | 45b95a98-479a-473a-90e6-14561d1ce0fc | NIST-2659
| note | c7202ad9-4162-4def-b874-765f3e23a7cc | NIST
| note | 3e017b9b-439b-412c-8aa8-7201a0eb9aa8 | 012.2.1 Section
| note | da7a4885-300a-4bcc-9936-578eea476783 | 6.15-16
| note | 9bd5136d-a2b5-4a7c-b60a-e80ce152724d | NIST 012.2.1 Section 6.9
| note | 19d6cf7d-6b71-486c-bbbd-59a959c7ede2 | NIST 012.2.1 Cl. 6.7 (c)
| note | 7c916596-f834-4777-8c28-74ce139e9d03 | ACCEPTANCE CRITERIA: Pits: located within 1.5m of nearest rail, pit to be 300LA Railway loading
| note | ac6708e1-0bcf-43c2-9e71-42322f140caf | Pits 900x900mm or greater, multipart pits lids to be used.
| note | 616a16f5-be79-432a-b039-71f09374ee3d | Concrete Pits to be made as per AS 3600
| note | 3b4dce43-0ded-48fd-8768-952e554eb6fc | Pit lids: Covers shall comply with AS3996-2006
| note | c22dde1e-89cb-40e4-8244-c2b210e874b4 | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class B
| note | 8900e3c7-d543-4bd1-bf6c-737d85da04f1 | Enter: Teambinder Material Approval number
| note | 3c3dbc4e-726f-4433-b9af-06b19ee24577 | METHOD: Document Review
| note | 5ec8fd74-ade5-4591-89c5-aa62c8a9ac91 | FREQUENCY: Where applicable, once, install
| note | ba184858-8fe0-45f0-ad7f-d9e4c9302ad1 | CATEGORY: HP*
| note | 7095f14d-745c-4366-ab52-c0efcec37947 | RESPONSIBILITY: Nominated Authority
| note | 93c3bfc4-e4b4-43a3-873e-dc9486169097 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 4ec9b3ed-d4a5-4473-9ba2-25e623a4516d | Date Completed:
| checkpoint |  | 2.6 Bedding & Backfill Material
| note | e185e560-c911-4475-991d-20af641067db | REFERENCE: IFC Drawings
| note | 6fbcb86c-85ce-4545-a8d2-ce33da9bdc48 | NIST-2659 cl6.4.2 & cl6.4.3
| note | 8c2a2de4-3520-4253-929e-b19b2b139881 | VicRoads Spec
| note | 663b83af-395a-43a5-9313-d81b132510d4 | Cl.701.10
| note | 52770730-4bf0-44e8-ba50-06bcb6d470c5 | VicRoads Spec
| note | 71701b23-ec75-4d0f-be5d-d7b22bb59c26 | Cl.701.05(b)
| note | d8738253-3dd4-4b73-93b0-f4c23722085d | AS 1289.5 Cl1.1
| note | 49cecdd2-a87d-4435-81b8-7d6e3f46543c | AS 1289.5 Cl3.1
| note | b23c4701-2388-437f-b199-b6a8cd806866 | AS 1289.5 Cl4.1
| note | 1afcbade-d3b4-4b51-831a-4850ac438e16 | AS 1289.5 Cl5.1
| note | a4531986-232f-416a-b5b8-a3d11cbcdeb1 | AS 1289.5 Cl6.1
| note | 3f3051d7-a4a0-48d1-a87d-6b2eebaf7ace | ACCEPTANCE CRITERIA: Bedding & backfill material free of rocks that will not pass a 75mm sieve. The material shall be free or organic matter or anything that could damage the conduits.
| note | 22fc12a5-deae-489f-b408-a1acd40c0ad2 | Nominal agg size 20mm
| note | 8f3f1388-a672-4224-b4a5-d1877910b097 | Swell => 2.5%
| note | b1ab617e-b231-4654-8b48-9260fd980248 | 98% compaction
| note | 2c5f40db-4b8e-4be0-89f1-8390cfd385ec | METHOD: Document Review
| note | b8f2d895-234a-4ccd-883d-83fdce0fd3dc | FREQUENCY: Each Material Type, Each Delivery
| note | aafeac3f-21b2-4aa0-9a36-f839e9c52bcf | CATEGORY: IP
| note | eec5991c-93da-4549-9f25-89c01459e42d | RESPONSIBILITY: SE/PE
| note | b417e3be-d404-40b6-8353-a2cce7ef6a90 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | cc75c18b-0506-4e4c-ac2e-04a68ebf6ffe | Date Completed:
| checkpoint |  | 2.7 Geotextile
| note | b3ed3491-c1ab-4b51-bdc4-b2a9efec0a3d | REFERENCE: IFC Drawings
| note | c3d29fdf-c8ac-46dd-8ec4-15c6f6fd047d | NIST-2659 cl7.4.2 Table 12
| note | 54cab4ce-945c-47cb-b998-84c6ddacb994 | ACCEPTANCE CRITERIA: For separation of subgrade and aggregate base a Class 2 geotextile is preferred. Either
| note | b668f458-03d9-47c1-809b-0efd546b7eec | medium weight non-woven or a 155gsm woven. Minimum permittivity of 0.02 s
| note | cc5016da-4bba-49bc-b00c-c50c5d6578ae | 1 and maximum EOS of 600 µm.
| note | e2ccb6ab-0b4a-4d09-8af2-57212793a4df | METHOD: Document Review
| note | 27fd92ff-42f7-46ee-b025-7280ea0f5fb7 | FREQUENCY: Each Material Type, Each Delivery
| note | 1a02f50d-94e2-43be-96a3-a28cd0d87346 | CATEGORY: IP
| note | 09540339-5216-4738-983d-10c5a5ba7f15 | RESPONSIBILITY: SE/PE
| note | b166c544-d6ae-49be-bbb7-936b016cac10 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | 3ebbd840-6d04-4ae9-a02d-077be5316c62 | Date Completed:
| checkpoint |  | 2.8 Joint Sealant
| note | 87cf0f2b-3a05-4a8d-9137-cbe3c5c5bd2d | REFERENCE: IFC Drawings
| note | 412e77c6-57e2-401c-8c05-73069412fefa | 612.18
| note | 4047abde-0805-4b6b-8787-92a250b412cc | ASTM 0262
| note | c7d9c04a-2731-4317-9a27-905c95e58ebb | ACCEPTANCE CRITERIA: 10x10mm Joint Sealant (eg Neoprene Compression Seal)
| note | f46b783f-853a-45bb-9193-caf2bcc1d660 | Enter: Teambinder Material Approval number
| note | ccee6959-6eca-43ab-80d7-bdc1f63f8712 | METHOD: Document Review
| note | f27cc47e-a9ac-43c6-a0e4-f399f11d8684 | FREQUENCY: Each Material Type, Each Delivery
| note | 8bb328c7-a011-4e06-b373-eb97fd5c0790 | CATEGORY: IP
| note | 6417d5d2-2f70-432a-8b15-ae7697d6330d | RESPONSIBILITY: SE/PE
| note | 378e1dea-056c-4e7b-b6bd-48930bfe30c7 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | 0af0e7f2-6044-4114-aa2c-10d267a8da0f | Date Completed:
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 IFC Drawings
| note | 5186aab6-1443-409e-bd2f-6dc9d008e17c | REFERENCE: MRPA Quality Management Plan
| note | 70721148-fe7d-4de3-8ec4-99ffb37319a0 | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | b9adfc3d-2acf-4322-b30a-d95fdb320c38 | METHOD: Document Review
| note | 42d695b6-b61e-4821-aa22-ee28fb99550e | FREQUENCY: Prior to starting Works and at regular intervals
| note | a9a79e2d-afa7-42b8-85a7-a043e6c5a79a | CATEGORY: HP*
| note | 003344ec-a23a-4ecb-9219-7d0fd5bedcd8 | RESPONSIBILITY: All
| note | e4aec0e9-d68e-4396-934e-86aaa2d9b6a1 | VERIFYING DOCUMENTS: This ITP
| textbox | 050d83f5-e15c-4e61-b24c-195f116e68ba | Date Completed:
| checkpoint |  | 3.2 Survey Set-out
| note | 5c3cbda1-024c-4e07-8825-5e81b6cd5e45 | REFERENCE: IFC Drawings
| note | 23db838a-26bf-4af2-a895-ea9b9e207bd5 | NIST-2659 cl6.4.1
| note | 4ec84ea0-84a7-41f7-bd76-80290f7621f0 | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.473 (March/June 2019) as applicable to the element.
| note | 7eb22593-06e6-4fc7-9e7c-b8a58b0c4a20 | METHOD: Measure , Visual
| note | 8a5ca19e-275e-4ca6-b98e-afac35dc9fef | FREQUENCY: Prior to Commencing
| note | 4c42ee0a-6cdd-4f45-92ed-a141778dbf72 | CATEGORY: IP
| note | adf73e7b-81d2-40ef-8c35-ecb1baa5cf4e | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | e7d2d3db-8607-4387-9711-44f439e7e95d | VERIFYING DOCUMENTS: This ITP
| textbox | 825cf572-7277-4c6d-96a1-23fdf234d0ff | Date Completed:
| checkpoint |  | 3.3 Temporary Drainage Provisions
| note | 19967a17-e320-4d10-8700-f12e7dca918f | REFERENCE: VicRoads Spec.
| note | 796c34fd-225e-43b7-9262-8a49c73185ad | Cl.703.18
| note | 8c60fac8-733a-47d6-809a-25fb80b32620 | ACCEPTANCE CRITERIA: Temporary diversion of drainage to be in place where required.
| note | 796fb7d5-e41c-4155-a0ed-adbaa976c985 | Written approval of from V/Line (SAP) to be provided where diversions are to be installed.
| note | 87b5b193-a0cc-4909-9e1e-d78f3a4de446 | METHOD: Site Inspection
| note | 0da01c2f-51a0-465b-8d80-04cff83e1c4f | FREQUENCY: Where applicable, Prior to Commencing
| note | e0f75bf1-90d0-4d40-9d10-da3b51c5eca5 | CATEGORY: IP
| note | 54e8754f-6d78-471e-8f42-a194ab658a1f | RESPONSIBILITY: SE
| note | c11f54f4-ba17-4731-8d2d-a7ec5826ede1 | VERIFYING DOCUMENTS: This ITP
| textbox | d052a6d4-7bb2-4ba7-9dea-ca606077b063 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Trench Excavation
| note | ba800012-213c-4bc5-9b31-0e9709bb6bdb | REFERENCE: NIST-2659 cl6.4.2
| note | 610385d3-23cc-434a-a353-0d852bee95d6 | IFC Drawings
| note | 337881b1-a746-4595-b911-3ce108ba8ce9 | Section 702.08
| note | 4c73d413-78f1-4fd2-93b7-ac78cbcca64b | ACCEPTANCE CRITERIA: Trench shall be excavated to allow for a min of 150mm between each side of the ACO drain
| note | 11cd4875-7fb6-47dc-be41-01e6507d7533 | The depth of the excavation shall be a min of 225mm below the base of the ACO drain in clay areas and 350mm in rock areas
| note | aa807762-bf54-4904-b921-abe2468e7376 | The bottom of the trench shall be compacted
| note | b7c56a62-51a8-4934-82a5-0a39b37f27e3 | There shall be no departures from the grade of the base of the trench that would allow ponding of water.
| note | cf6ac56b-6385-4747-a836-b5bce589ed8f | Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
| note | 89c3f349-5122-4e56-a96f-667844e66e79 | METHOD: Visual
| note | 97eabadb-f809-4ec7-8a7e-2ff16e9624fa | FREQUENCY: Each Lot
| note | 98773fb6-b536-4296-9d5e-4c03b4f9c0d5 | CATEGORY: HP
| note | 565e369a-2abd-49aa-9ee2-4e9b0906ef67 | RESPONSIBILITY: SE, NA (Nominated Authority)
| note | 40d01fa9-1596-4905-b196-e1ed6a157920 | VERIFYING DOCUMENTS: This ITP
| textbox | 7530356f-84ac-462a-8d4b-e5a31ec01631 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.2 Placement of bedding
| note | 780816df-89bc-4155-9b5d-ef3873d57cc3 | REFERENCE: 702.09 c)
| note | c3352996-fc9f-4da0-bee8-8d29aa47aac9 | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 75 mm and 200mm placed across bottom of trench and screeded & compacted to level
| note | 150a88a2-65cb-4f46-818b-b2836c951b1a | Place 150mm of bedding under pits
| note | cc98a0ff-8d97-468b-81f5-780591fdaf17 | METHOD: Visual inspection
| note | 1432b200-85a6-4348-b5b0-b85976baef36 | FREQUENCY: Each lot
| note | d7c27513-0a36-4f18-9f60-8ea9500eaaf7 | CATEGORY: IP
| note | ce4a3f98-45d3-4a19-990a-ca7e5482adfe | RESPONSIBILITY: SE/Site Supervisor
| note | a582ef0d-0bb4-4fcb-8620-06624893d18a | VERIFYING DOCUMENTS: This ITP
| textbox | 74be15ea-4b1d-4f04-ad38-894fc47c7154 | Date Completed:
| checkpoint |  | 4.3 Placement of SL81 Mesh (75mm cover) - Trafficable areas only
| note | 9f608603-b837-4505-9343-5a176958a468 | REFERENCE: IFC Drawings
| note | 3e075c9e-71e9-43e4-8ae7-082edc57662f | 611.06
| note | 306cf503-5ce1-46f2-8f04-3e66e8bedafb | 611.09
| note | 748e311f-ca95-4e72-a084-d2506f9884c6 | 611.1
| note | 6d0a6d95-c139-499c-9aaa-9b9b1c6af989 | 611.11
| note | 9d04fa02-ae2a-49df-b055-83a067808375 | 611.12
| note | cde875d9-04b9-48d8-a029-ef862e660298 | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
| note | 6ec3605e-cb7c-46ab-8070-0c9d8ce83344 | Splice lengths achieve the minimum length and are in contact for this length.
| note | da67e969-8919-4c62-9da2-930bdf0ca892 | The reinforcement surface condition is free from dirt, debris and damage.
| note | e056c8ac-703d-46ff-8c40-ad23195724ca | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
| note | 29b66fda-a25a-4681-9057-3d67605d1db9 | METHOD: Measure , Visual
| note | fc5e0807-bfe5-470e-bb91-ee8677738265 | FREQUENCY: Each Lot
| note | 2f3d65b5-735d-44e1-960e-7aa9d24077ca | CATEGORY: IP
| note | 40843639-2f0c-4ae8-abdd-9230eac22414 | RESPONSIBILITY: SE/Site Supervisor
| note | 320f57ff-02a5-4d5f-b2be-5d2a2021e58e | VERIFYING DOCUMENTS: This ITP
| textbox | c6e15247-6e2e-412e-a4f5-010a6a4d27d2 | Date Completed:
| checkpoint |  | 4.4 Formwork Design and Construction
| note | cac64d0f-8b01-48f0-8512-f6cea551c1ae | REFERENCE: IFC Drawings
| note | bbeaaed2-8b7d-403b-afc4-0e5dd022d51d | 614.04
| note | fa757d63-ff08-4920-832c-2892e0584906 | 614.05
| note | 6fd67e3e-5d3e-4b96-8ca1-0bce71c52ab9 | 614.06
| note | f2dae86b-7de3-4f6a-963e-6a9a0fb8f2e6 | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
| note | 67b8581d-4492-419e-9c9e-b66776c204a8 | Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
| note | ad1c186c-a733-4f45-b58a-922d296c1a08 | Formwork shall not be placed where steel & fixtures cannot be inspected.
| note | f1b4bc8f-1d86-4555-886c-d458adb2d30c | METHOD: Document Review , Visual , Measure
| note | 1d5cfec4-54bc-405c-a50e-f3cd5c7a9e4f | FREQUENCY: Each element
| note | 501003eb-cb93-4191-9e6e-3a839fee74e3 | CATEGORY: IP
| note | 42e0bde5-5520-480d-a495-4edb2f2a2dbd | RESPONSIBILITY: Temporary Works Designer , Proof Engineer , SE/PE/SPE
| note | 28cc3a6d-450e-4262-979f-f7c355d64eee | VERIFYING DOCUMENTS: This ITP
| textbox | 017160b9-68f8-4dc6-97a3-7e245f504af2 | Date Completed:
| checkpoint |  | 4.5 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
| note | f5402a90-4b20-4e6f-81f6-3b872da09d50 | REFERENCE: 614.08
| note | 93a6ceef-2a55-4809-b61a-633e5d4fda6e | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
| note | 65df2f24-f6d2-486d-a97d-01a75d0f8e57 | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
| note | 6815c690-aac7-43ba-88dd-e9d9595e2d37 | Attach: Attachment C
| note | a186df0c-61d8-47f9-9fef-9f2b7c1c7239 | METHOD: Document Review , Visual , Measure
| note | 596409af-2177-481c-b2eb-398d64922e4d | FREQUENCY: Each element (where 2m or less)
| note | ddd49168-9619-4103-b6ad-336c6e8a2506 | CATEGORY: HP
| note | 36e25c54-bf9c-48c3-aa8d-191b29f4ec17 | RESPONSIBILITY: PE/SPE
| note | 3857553d-7dfd-4fc7-9d27-f89ede9a94fa | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 635fcd02-b62c-4511-964f-029b0cdf563a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.6 Installation of Contraction Joints
| note | b166c1eb-20e7-40f7-912e-26fa870cdd53 | REFERENCE: IFC Drawings
| note | 42654469-e466-4193-9a30-756ee6482e5f | ACCEPTANCE CRITERIA: Contraction joints shall be placed at a maximum spacing of 12m and shall comprise of the following:
| note | c390f017-fc34-483f-bcf8-fd8e7c1c6292 | 10x10 Blockout to be filled with approved joint sealant
| note | 7b5ce392-60d1-4a1b-a9a8-d81168fd328f | R10 x 500mn long gal dowels
| note | 50f1b109-bec8-4d81-a6ee-fe88d5446990 | METHOD: Visual , Measure
| note | 036aabcc-baa7-4bdc-9c00-8ea8f59eff84 | FREQUENCY: Each element
| note | 56c4647f-b489-432b-8a25-0be5c1354245 | CATEGORY: IP
| note | d21817ef-a31e-45f5-ac17-fa5673c3e813 | RESPONSIBILITY: SE
| note | 4c86f27c-13ba-488c-8389-86f1fa53266a | VERIFYING DOCUMENTS: This ITP
| textbox | 493b73ea-699f-4a96-8448-c5a792b52437 | Date Completed:
| checkpoint |  | 4.7 Pre-concrete check
| note | 5ca0a81c-3973-44d6-87fb-caf0e9765030 | REFERENCE: VicRoads Spec
| note | b0a72fbf-394c-4975-ac1b-c44072581e2e | Cl.703.09
| note | f60fd6dd-aa65-4b01-8e2d-04c300171066 | Cl.610.17 (a)(b)
| note | 11810e67-5c21-4d41-ae2a-ff2c55176c50 | (c)(d)
| note | b02a1aad-1470-42d0-80a3-5ee7465d17ee | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature measured at the point of placement is >35 C or < 5 C.
| note | d977185a-d619-4397-8cab-dc0c055a5cac | Temperature of concrete, measured immediately prior to placing, shall not be less than 10 C or greater than 32 C.
| note | 34fa3be5-247a-4776-bdff-bf6d12b92512 | Unless otherwise specified concrete shall be N32 standard strength.
| note | 35ab0128-71c4-41dc-b792-7dee58bff6ba | METHOD: Site Inspection Temp Verification
| note | 59ba9a47-56a8-4406-b76a-c05910c8a894 | FREQUENCY: Each Lot
| note | f3d19787-09a3-4068-8742-255401d96c97 | CATEGORY: IP
| note | 9dd66723-7935-44e2-8366-5de45a5dad61 | RESPONSIBILITY: SE
| note | e95b66d5-4400-4305-9f61-fc6bc0823fbd | VERIFYING DOCUMENTS: This ITP
| textbox | 1f56c182-d1cd-48d7-b27f-4ef4671ef88b | Date Completed:
| checkpoint |  | 4.8 Concrete Placement
| note | e28db0ee-3006-46be-b421-4a8a748fa80a | REFERENCE: IFC Drawings
| note | 078ced64-8281-4862-b8c9-19db6b10f82e | VicRoads Spec.
| note | c8ea45fe-4989-4f9f-ad99-7ddc6746e803 | Cl.610.13(f)
| note | ce77038c-b901-4a8d-b5b1-d0de51ed8702 | ACCEPTANCE CRITERIA: Concrete Strength to be 32MPA as nominated on Drawings; Concrete placed within 60-90 minutes of the commencement of mixing;
| note | 3a00ead0-b81d-4a54-89fa-d4cd54f5bdae | METHOD: Site Inspection
| note | ef826f6f-929d-480f-a882-54ddc40b6872 | FREQUENCY: Each Lot
| note | ea4f2d1c-5d66-47f1-876e-8f50c571d49e | CATEGORY: IP
| note | a47748a2-fe09-42b8-9f42-a8017e98b652 | RESPONSIBILITY: SE
| note | c9b3107a-59e0-4d4e-9117-921532f1bc41 | VERIFYING DOCUMENTS: This ITP
| textbox | 995f69c4-9ff5-4c97-ad23-85eeb09f0632 | Date Completed:
| checkpoint |  | 4.9 Concrete Finish
| note | acba62f8-edfe-4c95-b4c2-59a2fc897e56 | REFERENCE: VicRoads Spec.
| note | 5e0e2233-eed3-4ab4-babc-ee650cde735e | Cl 703.25
| note | 83027cb1-d26c-4139-b3e5-4363bc7c5bf9 | ACCEPTANCE CRITERIA: Edgings: Rendering shall be applied within 30 minutes of placing or extruding concrete. endered to a thickness not exceeding 3mm and steel trowel finished. Footpaths and Surfacing: Use a wooden float for a lightly textured non-skid finish. Concrete to have a neat appearance and uniform colour
| note | 36169def-6276-4446-8ef6-f8175599cdf9 | METHOD: Site Inspection
| note | e8d7beb0-1fbe-457d-9d3c-0041b5f273cd | FREQUENCY: Each Lot
| note | 0596221b-cbd1-4dac-a700-6113542f77c0 | CATEGORY: IP
| note | 8d9a384d-0361-4cf0-89b4-dee872d3b4b9 | RESPONSIBILITY: SE
| note | 2209b739-61a2-465c-b00e-4819ab2b5365 | VERIFYING DOCUMENTS: This ITP
| textbox | 652ddfe9-dfde-412f-80bf-7ac5c9456097 | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 5.1 Backfilling
| note | df43c89e-72d3-4373-889e-1ba35c83815e | REFERENCE: VicRoads Spec.
| note | b20f852b-3c8c-4641-937e-54d13c22a84b | Cl 703.29
| note | e1be1c9c-f418-4aa7-aa2c-4f39ebfa65a4 | ACCEPTANCE CRITERIA: As soon as the concrete has cured sufficiently, but not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging, unless otherwise specified.
| note | 826b984c-eec9-46e9-960c-a551ee7a938d | METHOD: Site Inspection
| note | 004776d4-d3b6-438c-94cc-5c65e12c0ccb | FREQUENCY: Each Lot
| note | 6674c5ee-c548-43a8-b19f-5df6e501963c | CATEGORY: HP*
| note | a43af298-b131-4b60-aa46-e2f445534bd6 | RESPONSIBILITY: PE/SPE
| note | 79b46f35-d453-452c-957f-9897a533826b | VERIFYING DOCUMENTS: This ITP
| textbox | 1c37f60f-3868-456f-a589-8711f7a8557c | Date Completed:
| checkpoint |  | 5.2 Place ACO Drain
| note | c736ad81-9015-4cbf-a343-7047a73b3867 | REFERENCE: IFC Drawings
| note | 228dadf3-42a7-4cec-881f-ac4887e41c08 | ACCEPTANCE CRITERIA: Place ACO as per IFC drawing in center of trench and fix in place at 1:300 grade
| note | 8423286d-d1f5-42e0-ba74-ff057608891a | ACO units to be placed flush with adjacent units with slope facing correctly as nominated on drawings.
| note | 3996d8b6-de22-455d-a00e-47a2cc830d67 | Joints between pits and ACO units to be grouted and watertight.
| note | dc602ceb-1f92-4515-a7d2-99c3d52c783b | METHOD: Site Inspection
| note | c576329e-332f-46b5-a575-a662092bd23b | FREQUENCY: Each Lot
| note | 88f282fb-74aa-469d-bff3-0d13019baf5a | CATEGORY: IP
| note | 693090f8-605e-46fc-ab8e-1d6403bfe85a | RESPONSIBILITY: SE
| note | ee73d041-60f7-44e3-a0e6-96a6b12f350f | VERIFYING DOCUMENTS: This ITP
| textbox | 18e1125f-288e-4ae5-845c-aa6f482b6c5b | Date Completed:
| checkpoint |  | 5.3 Sealant
| note | 66e4e06b-843c-4830-bf8f-4bc11f516028 | REFERENCE: IFC Drawings
| note | 19835787-8a10-467b-8157-da38d62a9497 | ACCEPTANCE CRITERIA: Remove 10x10mm blockout seal joint with 10x10mm or approved Sealant
| note | 368ef767-ec6a-4b56-bb7f-6a9d62c3fbf4 | METHOD: Visual
| note | 3ffefb70-f3a5-4091-863b-78e07448115c | FREQUENCY: Each element
| note | 0e438ada-2a6a-4c0f-9a9d-404554741559 | CATEGORY: IP
| note | 564aa3a5-eda9-41cd-892a-394656e8c964 | RESPONSIBILITY: SE
| note | ce551591-7f7b-43a3-bdad-704e4617cff3 | VERIFYING DOCUMENTS: This ITP
| textbox | 5a23ae6c-df66-417f-8f64-0304aa7207dd | Date Completed:
| checkpoint |  | 5.4 Connection to Pits and Pit Cover Installation
| note | d8fa7e9a-79ab-420c-8642-8574d9322393 | REFERENCE: IFC Drawings
| note | 3894167d-7c8e-4971-b562-8b6c13ac4a5f | NIST-2659
| note | 6f113491-6eed-4b4a-8179-747692e5bdc7 | ACCEPTANCE CRITERIA: Gap between reinstated pit walls and Aco drain units shall be 20mm with nominated water stop seal as per drawings.
| note | 161acd7b-34a9-4cb5-a302-51be1310c4e0 | METHOD: Site Inspection
| note | 6e325a81-a835-4cce-b3d1-1e3d659cb1cf | FREQUENCY: Each Lot
| note | af049784-9089-4859-8d7b-1622d196ce44 | CATEGORY: IP
| note | 3c46bbe1-84d5-4fc3-9feb-50c6ae68311d | RESPONSIBILITY: SE
| note | 13d1473b-d726-4276-8eb7-cb44abe6c2f3 | VERIFYING DOCUMENTS: This ITP
| textbox | d26096de-ca70-40d9-a1c1-1d93a56b8039 | Date Completed:
| checkpoint |  | 5.5 As-built Survey
| note | f9b18eb5-a59b-4391-bc26-e83a94308d33 | REFERENCE: IFC Drawings
| note | 1d42a8d0-2bf5-4825-b3b8-6eb269ff206c | 610.32
| note | 95b956b0-7516-45de-9aeb-dcd15ae3c4d5 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate Vertical and horizontal alignment between adjacent segments shall not exceed 5mm
| note | 5394fae9-0c09-4289-a6ed-2c9248c5350e | Attach: Survey As-builts / Survey Report
| note | 112c2ef5-9af3-4032-ba68-f1ec2462f556 | METHOD: Document Review
| note | 230fa9aa-4fef-4b59-ba9d-270d0a4d13d2 | FREQUENCY: Each element
| note | 4e118b4b-a0bc-4322-98ae-4e6140e1840e | CATEGORY: IP
| note | 2e285b21-adef-4d69-a113-81cc19365ca5 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 0557e3c0-4539-4439-9627-1a396d9bd8a3 | VERIFYING DOCUMENTS: This ITP
| textbox | 73ac78eb-1845-4f5b-b119-38b4ee01e967 | Date Completed:
| checkpoint |  | 5.6 Non-conformance Report (NCR) Closure
| note | 042aa78c-a3a3-4254-a610-bd80d5c3e616 | REFERENCE: MRPA Quality Management Plan
| note | 2fe2fc37-02f3-4e75-a188-bd2735da9306 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 79d28a85-30b8-4fb3-bb7f-24ea0661433c | METHOD: Document Review
| note | 169418b9-e59d-4ea4-a435-01caf071a964 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | e9738518-3a3f-400f-9696-835a554d89e7 | CATEGORY: HP*
| note | f6f577fc-f7a8-4a7b-951a-c35404df7528 | RESPONSIBILITY: SE/PE/SPE
| note | d774ed64-3822-4d7d-9790-e3d9b5a56bb1 | VERIFYING DOCUMENTS: This ITP
| textbox | ead52ae2-8a00-41dd-a223-00892aa39396 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | ce2e3016-b888-4982-8fcb-eefda50e911a | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 521988e4-1726-4daf-bdb7-ecb432e9cd34 | Name:
| textbox | 065e43a8-7daa-4a18-a64e-217a4b8373b8 | Position:
| textbox | e10fa1e9-d382-4501-864d-e7ec1371e948 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-CFA Piling Rev 4 | itp | ITP-STR-CFA Piling | 68436303-d850-446c-be76-7b83d1fbe4a2
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 7c502f61-6960-409b-b367-45a0a605aa08 | Document Title: ITP-STR-CFA Piling
| note | 51515e20-e404-4bb1-9f07-612d5e73deed | ITP Description: CFA Piling
| note | 9a3ff12c-6d9a-4b11-80c2-ab16ecf25013 | Discipline (e.g. CIV/STR/RAIL): STR
| note | d1beac71-1782-4e4c-a383-b4a79d78628e | Revision Number: 4
| note | ede0e416-52e7-4d4c-835f-7c039b17b127 | Revision Date: 12/05/2021
| note | a69ae8cb-c10f-4b66-b78f-d0393c5df921 | ITP created by: Mike Freeman
| note | 4f5d4fdd-da0d-483d-8700-4dc3502660aa | VicRoads Section 607 March 2015
| note | 4b87a692-51cf-4dce-99fc-a44b069decc1 | 1.2 VicRoads Section 610 June 2019
| note | 5e1b1dca-1e93-4b65-9454-2d4337efac9a | 1.3 VicRoads Section 611 November 2018
| note | 26d0cfb3-b5c2-45a0-8b2c-5c7877f37ef5 | 1.4 AS2159-2009
| note | 1576c0e7-167d-4134-b351-15a0e5119f1e | 1.5 AS3810.1-2015
| note | 7086552f-aa0c-4b0f-8558-555253bf50cd | 1.6 AS5100.3-2017
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Concrete Mix
| note | 504f2a39-482d-42cf-9299-4c5777b78694 | REFERENCE: 610.07 Table 610.071
| note | 4479763f-cae0-4f3c-a819-b444485c33a4 | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
| note | bbb6b4e4-2aed-46f1-926e-b42d6953bfbb | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
| textbox | 2a5dfc4f-01e0-49a9-9319-4aa4f3b43277 | Enter: Teambinder Material Approval number
| note | 47f4280f-934f-42f7-beef-da050e91232b | METHOD: Document Review
| note | bc1bc3c4-cd0b-4792-b025-c473b65797b7 | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
| note | d8a5d15e-f0b2-4ec3-a06a-6cd7c503a214 | CATEGORY: HP
| note | 0433dbca-540c-4b77-9eed-7ae6b37f6049 | RESPONSIBILITY: Nominated Authority
| note | b8568095-cbfb-495e-b96c-fd3bab733bda | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 6f731be0-99f4-4c2f-8919-d0586a489945 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 ACRS Certification (for Reinforcement)
| note | dd1e611a-ccd2-4f12-a16e-a861bfd03b65 | REFERENCE: 611.05 (a)
| note | d6bddd42-6277-4205-a999-6958cd6a1e2d | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
| note | e8aceada-1f57-43c2-8217-77266ccad5e8 | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | 4cfb4b7f-2a8e-4aac-ac11-2a3cd731e800 | Enter: Teambinder Material Approval number
| note | 6e68f5d7-9ead-4523-85bd-e19a387dd947 | METHOD: Document Review
| note | 2295c051-b836-450d-9a77-a72a3edcc8a6 | FREQUENCY: Once for each supplier, 14 days of award of contract
| note | 4bb8b189-f2a0-4d15-9844-7331573dcb73 | CATEGORY: WP
| note | 515c5752-5f79-4df7-a4c0-a1d4915c089b | RESPONSIBILITY: Nominated Authority
| note | d80a7a79-bbb4-474f-baa2-9583c7a4a1f8 | VERIFYING DOCUMENTS: This ITP
| textbox | 9c575896-e727-4988-98ce-c13178eba51b | Date Completed:
| checkpoint |  | 2.3 Bar Chairs/Aspros Certification
| note | 4123a839-a375-456b-9a1d-db6895732fce | REFERENCE: 610.26 (a)
| note | 2ef6012a-06a1-43da-932e-2869e71b8bd8 | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
| note | 7ada480f-6425-4f71-afdf-ca9a1a692bc2 | Concrete aspros require annual compressive strength and soluble salt testing is required.
| note | 0e33a8e5-aeba-4a8b-95ab-a1c947b1e8d2 | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
| textbox | 5ae8643a-e3c2-47cf-8163-4b8ce13a5b82 | Enter: Teambinder Material Approval number
| note | 7daa33a6-1003-42d3-a717-6da023f06d6a | METHOD: Document Review
| note | c513a700-d7b3-4968-a4b6-724c8e5a5080 | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
| note | 8e16f5a7-a857-4b35-86dc-5833f7b04719 | CATEGORY: WP
| note | 85f4a5ea-cf60-42e8-9714-c7efa8727957 | RESPONSIBILITY: Nominated Authority
| note | a1c2ba5d-10a5-46f2-93a1-3101427c03ce | VERIFYING DOCUMENTS: This ITP
| textbox | a18d2b01-a723-4b35-87ea-e24ad4ccf378 | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Piling Operations Work Procedure
| note | b810f559-2499-45b6-81fb-5d4e8aef144a | REFERENCE: 607.01
| note | 02ef7ec0-1dda-4178-88bb-a3c67798dce4 | ACCEPTANCE CRITERIA: Where concrete CFA piles are proposed for bridge foundations and other structures on or over roads, the following documentation shall be submitted for approval to the Nominated Authority:
| note | 26fbbe20-0624-4008-b824-8ed23be3409b | i. plant & equipment for the Works
| note | 3f532cb2-0d3d-4cf1-a81d-4fc6be23ea81 | ii. method statement for pile installation
| note | 000b988f-e215-4b4b-a478-3e9eb62f01d6 | ii. ITPs for installation & testing
| note | 90bad35e-b389-4573-91fc-2fc3689e931e | iv. training & experience of piling crew
| note | 38ecdb60-c615-4e26-bffe-b06e6916f711 | v. training & qualifications of on-site & off-site engineering & geotechnical supervisory personnel
| note | a8fb4184-d06b-4219-9900-75da0089ce9c | vi. the method for achieving verticality & pile position
| note | 34ef7d82-00b1-459a-be57-df9190828de2 | vii. the method of measuring penetration rate & torque during augering
| note | 9a781e49-0a0f-47d4-92ba-06e4d9ad6d55 | viii. the pile design and founding level (if this differs from the design)
| note | f53e8755-b420-481d-a1d2-4507013a4e22 | ix. the procedure for checking that the pile toe has reached the anticipated founding stratum
| note | 4865c917-f30c-4c5f-8188-1a37d6fdf66e | x. the procedure for reviewing the design of the pile if ground conditions vary from the anticipated conditions
| note | 2e037fad-1c9d-4f91-933f-e52e7ece7a69 | xi. the method of extraction rate of the auger
| note | 5bfeed41-bd67-413f-89e3-313837ee37bd | xii. the method of measuring & monitoring concrete line pressure
| note | 436293b5-03f4-4c13-bc59-2cb51dbc43ea | xiii. the method of recording concrete flow
| note | bcf5d08a-682c-4de0-9681-52ad4bf4a3f3 | xiv. actions to be taken if the concrete supply pressure &/or flow is not maintained
| note | b89763b5-f779-4e44-a85b-83ef0ef7f086 | xv. the method of installing the reinforcement cage & ensuring the correct cover
| note | 39938194-de86-4396-b223-1beae5493b9c | xvi. the method of spoil disposal
| note | 0cad3357-c969-4eee-ae0c-f5defa44955d | xvii. the methodology of determining the pile capacity below the ultimate retention height of the test pile (for earth retention piles only)
| textbox | c2516975-2a37-400c-ac56-d3f97e21ec4d | Enter: Teambinder Approval number
| note | 0c31673e-b858-4d01-aa4e-ab4369efa6fe | METHOD: Document Review
| note | 75aa26a3-0f0a-4d50-abc0-d9e464e3a8a9 | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
| note | 32b2b7c1-41e5-4f00-b87a-480c63dd9091 | CATEGORY: HP
| note | 7c396c69-3c91-4eb5-897a-ec645bce2a31 | RESPONSIBILITY: Nominated Authority
| note | f99fb8e1-141f-4b1f-ada9-39cb99694182 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 54933c3b-f8ef-41cc-8c9b-d0b584a9e03b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Preliminaries - Procedures & Documentation (Continued)
| checkpoint |  | 3.2 Casting Under Water Procedure
| note | d756141c-3cf9-4a61-a7b1-f46bd844f3db | REFERENCE: 607.04
| note | 5da64d93-e99e-4398-96cd-ea1187cc64a5 | ACCEPTANCE CRITERIA: Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
| note | 80632f63-de7a-4900-8b51-8edfc5233a93 | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
| textbox | afaf408f-0d5d-4ae6-b0a3-84586ebe12c4 | Enter: Teambinder Approval number
| note | 593efef4-e237-4f0e-9555-d8d31db841ee | METHOD: Document Review
| note | 98459456-570e-4937-832a-4fbe1fe12c09 | FREQUENCY: Where applicable, once, prior to placement of concrete
| note | 235b2e8f-9890-4d63-8895-5d5942574bb2 | CATEGORY: WP
| note | 00a4998b-c61a-4625-84cc-bc094b275dcb | RESPONSIBILITY: Nominated Authority
| note | 4c2ba663-4b81-4d29-91a4-ff04252e71e4 | VERIFYING DOCUMENTS: This ITP
| textbox | 1a243704-abd8-458a-b515-9c6a22b617b7 | Date Completed:
| checkpoint |  | 3.3 Dynamic Pile Testing Procedure
| note | ba65f9be-56d8-4df3-8779-c0426072c84f | REFERENCE: 607.01
| note | fdf4b543-940f-4afd-abae-39348e8e935b | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
| note | da41c607-bb2e-43ca-a317-e5ca1bcd526b | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
| textbox | f20d83cb-3ffb-47af-b9ad-c584b370d267 | Enter: Teambinder Approval number
| note | 8fb50ba1-9457-4289-92a9-2034abc0b243 | METHOD: Document Review
| note | 4c95d366-d2d5-4347-91e7-dc4c473b859c | FREQUENCY: Once, prior to testing
| note | df313dca-75e3-4ff3-bf6c-dcb2b7a3f69c | CATEGORY: HP
| note | 5d5686fa-21b1-4382-939e-5311c6d33a29 | RESPONSIBILITY: Nominated Authority
| note | ca07c943-bca9-4082-b5fa-cf840359ffaa | VERIFYING DOCUMENTS: This ITP
| textbox | b113ce09-4884-49a2-b4fd-ed3230d79433 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Pre-qualified Pile Testing Consultant
| note | 81e6c0f4-640a-44c3-9872-527539840136 | REFERENCE: 607.07
| note | 55c21469-6b94-4307-ad1e-06bbdfdb940b | ACCEPTANCE CRITERIA: All testing shall be undertaken by a pre-qualified consultant who is independent of the piling contractor.
| note | e6f5dfbe-dfa2-4af2-9678-75c0c555c9fa | Details of the consultant to be submitted for review to the Nominated Authority.
| textbox | 42d27642-cca9-4c0a-ac70-8a20f988db17 | Enter: Teambinder Approval number
| note | 776f1799-d67b-4490-9f3a-43115601b2e9 | METHOD: Document Review
| note | 80b698f2-2774-4e6c-a12d-815e6df06389 | FREQUENCY: Once, 2 weeks prior to testing
| note | 424d5a93-1b6b-458a-b537-dd1504c3d56d | CATEGORY: HP
| note | 6f79e528-0b72-4d3f-a47f-bd4de8c14501 | RESPONSIBILITY: Nominated Authority
| note | 49c6b26e-9fd8-4709-b13e-eaa3a28f6212 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c5e106fa-5c72-4df3-9b42-e67d28e0f961 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.5 Reinforcement Welding Specifications & Qualifications
| note | ded184f0-b9f4-4c94-a999-1fdbe79b3939 | REFERENCE: 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
| note | c8d9e2d4-aa6a-40d9-a564-85ad6caf69d6 | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
| note | b63671e3-a3e6-4975-8ce1-d425ade0387b | Note: Tack welding requires the same documentation but is a Witness Point
| textbox | aa9125b5-ad57-4708-9074-c5cfcd8e76fb | Enter: Teambinder Approval number
| note | cc8b1a08-c3c0-42e3-b6e2-ded47b08e732 | METHOD: Document Review
| note | 6aa30d74-f5d6-4d99-baed-5ce3962a0af6 | FREQUENCY: Where applicable, once, prior to welding
| note | 33f01d23-c70c-41d3-b6cc-635c3decde0d | CATEGORY: HP
| note | 299ac877-7061-4fd1-96a7-5be23375763a | RESPONSIBILITY: Nominated Authority
| note | 43b5de44-ef85-4de9-8d10-91c22c75e24f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b3a3a8ad-3c70-4f4e-9f4d-687db2acaf7e | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 IFC Drawings
| note | 9e6b4fd8-87f0-42f9-a84f-c58398a6dc69 | REFERENCE: MRPA Quality Management Plan
| note | bdfc995b-3150-4ee4-bdcd-4eddbc4e34be | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 33a94218-0543-4358-8fd2-bf2d816b5a31 | METHOD: Document Review
| note | eb4bc90c-cf5f-4be3-bbbb-64dad7bc3aed | FREQUENCY: Prior to starting Works and at regular intervals
| note | 98df4285-0ff5-4a19-b033-5fe3c6311e43 | RESPONSIBILITY: All
| note | d7e3786e-aa8e-4126-8586-9d92419c4bdc | VERIFYING DOCUMENTS: This ITP
| textbox | 41e840d7-6105-49fd-99af-9dc5a75dd9f7 | Date Completed:
| checkpoint |  | 4.2 Survey Set-out
| note | 160a52e9-c4ce-4fc0-b1eb-b08a999fce8b | REFERENCE: IFC Drawings 607.06 (a )
| note | b403c33f-565a-494b-994e-dec8f63e4a0b | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
| note | dc9c3e3f-1bde-4ed6-879c-e2aad1a5c2ff | METHOD: Measure Visual
| note | 4914c351-6dae-4cd5-ad03-512588a7f848 | FREQUENCY: Each pile
| note | 93ff964e-1c38-4b75-8d8d-13e8f29cc407 | CATEGORY: IP
| note | f1679229-416d-4ba4-8a37-70b843b407b1 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 772ea2cf-01a6-40ab-8160-21bda2cbe268 | VERIFYING DOCUMENTS: This ITP
| textbox | 34b735bc-368a-46f9-bdcc-5a1a814f9307 | Date Completed:
| checkpoint |  | 4.3 Protection of Adjacent Piles
| note | 920630a1-571e-4141-ac2e-1cfd1192f6a8 | REFERENCE: 607.05
| note | 24681f43-2ed4-4092-bda7-7f00a444a998 | ACCEPTANCE CRITERIA: Pile construction shall not: i. result in damage to adjacent newly cast piles due to ground vibration. ii. commence within the lowest dimension of either 2m or 3 x diameter, from newly cast piles if that pile concrete strength <15MPa
| note | 5b0d725f-bc9b-433d-a22f-f77097627ff0 | METHOD: Measure Visual
| note | 52783a7b-557c-4679-8f94-9b17e1b2776b | FREQUENCY: Each pile
| note | 4576035f-1c9e-4b1b-9cf6-df07a8fd34b4 | CATEGORY: IP
| note | 60182ad4-17dd-4735-8583-fc45881cc0fa | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 18a7d582-d4fb-424f-8ae6-8e920f96b135 | VERIFYING DOCUMENTS: This ITP
| textbox | ecc5c138-21c1-46ee-947d-47444a4a8b73 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 5.1 Reinforcement - Inspection
| note | 8bb588ea-66fc-4da8-a6b5-bc07ee4d9065 | REFERENCE: IFC Drawings 611.06 611.09 611.10 611.11 611.12
| note | 43a4bfc0-ba3d-4446-9b47-c33bd974d5fc | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
| note | 0a117d9d-a91c-47f4-a180-a18f0d63bb0c | Projecting reinforcement is the correct length and location.
| note | 32987395-c066-437a-9813-13eda56fac92 | Splice lengths achieve the minimum length and are in contact for this length.
| note | 508f23b6-16a9-4b1a-9101-83e31fd0641c | The reinforcement surface condition is free from dirt, debris and damage.
| note | 87c3245f-0f6c-4be9-ad64-3699e9833baa | Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
| note | dc05f709-88f5-4334-9c9f-f359563eb998 | The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
| note | 575c8ff9-8bf8-4224-b648-2e8aa62f64b6 | METHOD: Measure Visual
| note | a11842ae-81cd-4a57-81fe-0d37666dcf1b | FREQUENCY: Each pile
| note | 6cbcb408-9962-4230-9088-c63d69569214 | CATEGORY: IP
| note | 11fa1816-e086-4806-a31c-be0dd772d336 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 72eb6df2-a91c-4670-be3e-78067e71b9f0 | VERIFYING DOCUMENTS: This ITP
| textbox | 747ecf14-065a-47e7-8e25-1845c266d3ff | Date Completed:
| checkpoint |  | 5.2 Reinforcement - Electrical Continuity
| note | b8596cbc-f2a8-4d52-89b0-f6c3f675b50c | REFERENCE: IFC Drawings 610.29 (d) 610.43
| note | 026b3a64-b5a5-4e83-bb8b-2ea276463684 | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by: i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable) ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar) iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required. Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
| note | 16e39217-8f10-4309-bdbc-72b07b81b940 | METHOD: Measure Visual
| note | 5c9d8b0b-4d6f-473a-b3f1-43ea06b09efd | FREQUENCY: Where applicable, each pile
| note | 151813cc-c01d-437e-bb0b-68f13e8ae3de | CATEGORY: IP
| note | a1de6b89-9805-4fe2-a144-a2fa67db8592 | RESPONSIBILITY: Earthing Engineer SE/PE/SPE
| note | bca38cf5-86ba-4ca4-a5ce-b46ab10d4d3b | VERIFYING DOCUMENTS: This ITP
| textbox | 56bb294f-9afe-4283-a245-6c71ba6e61dd | Date Completed:
| checkpoint |  | 5.3 Augering Operations
| note | f10a5f43-8e10-4996-b6cb-08ed651e2d97 | REFERENCE: IFC Drawings 607.04
| note | 254a7b6c-48e5-401c-979a-905c9975e769 | ACCEPTANCE CRITERIA: Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer. The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process. Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
| note | a6759da7-e0ee-4b75-939d-7e78ccbb9620 | METHOD: Measure Visual
| note | 9cbfc20f-dc70-4b25-add7-34fac037be39 | FREQUENCY: Each pile
| note | 3805b5c2-23d8-405a-a2bf-600109d53e14 | CATEGORY: IP
| note | b8adc346-1f9a-47a4-8ea2-8b168df2d592 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 532f96dc-c4b0-4139-850b-88c5f6e08641 | VERIFYING DOCUMENTS: This ITP
| textbox | 770b2a4c-517a-41a8-bfe0-200e3ed77996 | Date Completed:
| checkpoint |  | 5.4 Inspection of Excavated Material
| note | 24445bb5-aa0a-4537-ae2c-17335d2766d5 | REFERENCE: 607.04
| note | 49c779ed-ee51-4099-b165-843e5c3c68d5 | ACCEPTANCE CRITERIA: Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions. Attach: Geotechnical Field Sheet or Report
| note | 40305560-6775-469a-87a8-c2e835456dea | METHOD: Measure Visual
| note | ff45cdb2-a598-4733-844e-29f70c0997b1 | FREQUENCY: Each pile
| note | 2189b339-7031-4921-949c-a0476482c52f | CATEGORY: HP
| note | a157e622-36ee-4855-81ee-660b696bc30e | RESPONSIBILITY: Geotechnical Engineer or Nominated Authority
| note | 8eeafbee-488e-4c8d-835b-6a47f7fec545 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 6836f690-f81f-4858-9617-e976fbd0170b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.5 Increase in Depth Beyond Design
| note | 9be04b29-fbfa-47de-b844-f7f96b9a1b38 | REFERENCE: 607.04 (a - d) Piling Operations Work Procedure
| note | 4a8ff52e-2b56-4d94-82a5-c11547713c8e | ACCEPTANCE CRITERIA: Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity. A full account of the changes shall be submitted for approval to the Nominated Authority: Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
| note | 2932ebfe-2481-4310-b71b-fd45aa6f9a75 | METHOD: Measure Document Review
| note | 709ba39d-c790-4992-aa34-2a055400357a | FREQUENCY: Where applicable
| note | 9ac5e348-d3d8-45c3-84be-3c77fd8e269e | CATEGORY: HP*
| note | d2a59c18-7a70-4c5d-8b08-4ec809e0e0cb | RESPONSIBILITY: Nominated Authority
| note | f717514a-5a42-4fe9-b49c-89eea9c888d4 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 79a6dfe7-3eb3-4063-a70f-7b64517727ff | Date Completed:
| checkpoint |  | 5.6 Weather Conditions & Evaporation Limits
| note | c559cfcf-b175-4a76-b5a9-d3a645e96b63 | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
| note | 82ace5f6-12a0-47a5-9b29-2c8d23592c48 | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
| note | 43ac973c-ffaf-4e73-8ab4-5c6ed55b091d | METHOD: Measure Visual
| note | 8edbf7e3-634f-4618-8e46-485adc06e941 | FREQUENCY: Each pile
| note | 1d1fc509-8815-42bb-90de-ad5c989d0047 | CATEGORY: IP
| note | 76d4e641-86a5-4cac-bd4c-da8b8ec39a31 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 5b716fe5-b449-4b41-aac0-151ae9cdf074 | VERIFYING DOCUMENTS: This ITP
| textbox | d1c2c472-548e-42e5-a30b-225ec951a466 | Date Completed:
| checkpoint |  | 5.7 Concrete Testing - Sampling Frequency
| note | ba257862-7ea6-4ce8-9e34-660f36d9a1c4 | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
| note | b3c8a5e0-32ad-4185-89a7-d163981f2a95 | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
| note | 71f30fe2-8316-4f62-bea0-a35ea2f06e2a | 0m³ to 10m³ = 1 sample
| note | 85ccc3d9-d6fe-44b2-ad04-d81059741d6e | 10m³ to 25m³ = 2 samples
| note | 52613b42-39f5-4ca5-b52b-ef28114b871f | 25m³ to 50m³ = 3 samples
| note | 79ba3800-5b27-40bc-ab43-0fc22871c3d9 | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
| note | a0dfa371-6b0a-4e2b-ac2b-8d6fa9217c1d | For each additional 50m³ and additional sample shall be taken.
| note | 6eabf55d-9b33-4c30-87da-9ac70c5cd2bc | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
| note | 29193b2f-74d3-46b0-8ea6-5faba66ab8c5 | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
| note | 95cde35e-207a-4af7-bf91-e7d3f58a400c | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
| note | b85c0954-6b1e-4cc2-ba64-d5c50d8234b0 | Record: Required information on the Concrete Pour Record.
| note | 3a7ef252-71f4-433b-b255-4478e554e621 | METHOD: Test
| note | 27d59ea9-f2e7-4e4d-a848-f7fa2eb68f51 | FREQUENCY: Each pile
| note | b676f242-82bb-4cae-841f-4e4a47c75971 | CATEGORY: IP
| note | 8bbc1ec5-6ee1-4e0c-8dde-e38b0df8067f | RESPONSIBILITY: Concrete Tester Foreman SE/PE/SPE
| note | d73de53d-73e7-44dd-9160-f1f0d3facb03 | VERIFYING DOCUMENTS: This ITP
| textbox | ca3419b4-1c2c-4c52-b166-264d0a3fca7b | Date Completed:
| checkpoint |  | 5.8 Concrete Testing - Spread, Passability & Viscosity
| note | 80f689e3-52cf-4520-93c9-1038657c5d3c | REFERENCE: 610.13 (b)
| note | 104848f5-2bcf-461c-998f-54f4a686faad | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
| note | e5817bd7-4610-48c7-be74-cc1a9252a91b | METHOD: Test
| note | 148af6be-1284-49da-bf58-4a6c30359f5e | FREQUENCY: Each sample of Self-compacting Concrete
| note | 7a91a63c-7d34-4abc-a60b-61790bcd12e7 | CATEGORY: IP
| note | c8867586-7fbb-42a0-83f7-9aa4290ba0df | RESPONSIBILITY: Concrete Tester
| note | 17940862-086d-459b-b866-1a2abfc467c8 | VERIFYING DOCUMENTS: This ITP
| textbox | 142151f2-6df1-4614-b354-f92610c01ba6 | Date Completed:
| checkpoint |  | 5.9 Concrete Testing - Compressive Strength Cylinders
| note | da1d6a40-cc0c-4ee2-9547-50f4d6f86b78 | REFERENCE: Site Sampling & Testing Procedure
| note | f0405ab8-a09a-447b-b3d4-e0ceab6ab7be | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
| note | 8a5ffd68-b4f7-4cfd-95ef-11d3480ef01c | METHOD: Test
| note | 49576c67-899c-49ad-aabc-f4e6a654b96b | FREQUENCY: Each sample
| note | 6491256e-3fc0-4d36-8e6d-aab1261bfdd3 | CATEGORY: IP
| note | a9d6e9c5-7606-491f-9b21-4edd2f34a110 | RESPONSIBILITY: Concrete Tester
| note | dce9e481-6126-4994-a3f0-59d0ed9f3d9a | VERIFYING DOCUMENTS: This ITP
| textbox | 213e9053-bd2f-4557-bc38-3a86250a9a82 | Date Completed:
| checkpoint |  | 5.10 Concrete Placement & Compaction
| note | 0d2bdcac-199e-489a-9f27-ae1bf00cf989 | REFERENCE: Piling Operations Work Procedure 610.18 (a) & (b) 610.18 (d) (i) 607.04
| note | 48fcf562-41c6-4e2c-8145-d477559a1de9 | ACCEPTANCE CRITERIA: All concrete batches are traceable.
| note | 4977ce35-fce1-42f8-b6c2-70605c26dbda | The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
| note | 26d7dde4-2f1b-4620-8dfe-9880efb1d5d6 | The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
| note | 5ace2156-6a80-46e2-8582-4b2c705a130f | Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
| note | 15d69b23-c9d3-403d-88a0-d1097da87451 | Record: Required information on the Concrete Pour Record.
| note | f1864540-9589-4cf8-a8c2-fe7da24d8c9e | Attach: Concrete Pour Record
| note | cd59dfab-0d90-447e-92bf-2af7258531d1 | Attach: Concrete Dockets
| note | de762eaa-91d9-4dde-8cf1-e8882e8cf26a | METHOD: Visual
| note | f04c69bf-f354-4ac8-9783-b3c40746fa21 | FREQUENCY: Each load
| note | 60feedb2-6fd0-487b-a297-dd487556e72e | CATEGORY: SP
| note | 317046d0-daf7-4185-bcb0-8f1ef7f3a229 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | c1bebf1b-e155-4ac0-b8d6-4ba9630330f6 | VERIFYING DOCUMENTS: This ITP
| textbox | 66200a10-f3df-4de1-b06c-676c2b13a384 | Date Completed:
| checkpoint |  | 5.11 Reinforcement - Placement
| note | d276c6ea-30bc-48cf-acdd-80f73f8e9a21 | REFERENCE: IFC Drawings 607.04
| note | 47f70296-8e6f-46f6-a1b7-e2223a2623bf | ACCEPTANCE CRITERIA: The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
| note | 8d6d429f-76d9-44e0-ae95-b7a8d8bce711 | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
| note | e5cbff6d-4a5a-4905-8c5f-71844ee80daa | If the cage cannot be positioned into its final level, the pile shall be rejected.
| note | 964fc6d0-ae43-4b97-a807-54caf1060dd6 | METHOD: Measure Visual
| note | 8ac6c828-1b45-4076-aa74-58a37c675fdd | FREQUENCY: Each pile
| note | fe89da09-9eb2-4020-9d73-c7128a307e76 | CATEGORY: IP
| note | e3e04bc1-9154-4c60-a411-7ad1b4df9352 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | a73c6090-43d0-45e8-a332-647085e3a525 | VERIFYING DOCUMENTS: This ITP
| textbox | a7182de8-c38e-4b53-ba46-c61b5f460878 | Date Completed:
| checkpoint |  | 5.12 Cast-in Items
| note | 6d4810c8-4bcc-44e8-a2bc-6b9f7fb94b60 | REFERENCE: IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) AS3810.1 Table 3.3.6.2
| note | 2663f0bd-f13e-4288-ada7-ee0eca50d75b | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement..
| note | 465b39f1-1980-45b3-80b2-c213efd18ff1 | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
| note | 9417feef-0bbc-4912-a478-517c6bb00a9a | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
| note | 53689637-45f6-4e12-bb42-3addbbe3edaf | Grout tubes shall be fastened at regular intervals to prevent kinking.
| note | e1b724ac-d6bf-48b4-ae82-64f88723bee3 | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
| note | e92d4d49-5d9b-4ce0-910f-fa18bd4cde2f | i. Bolts, ferrules, projecting bars & couplers = ±3mm
| note | 1d13d31a-bbf8-4a6d-94ee-bac39459fd07 | ii. Running dimensions of a group of the above = ±6mm
| note | f093e277-178c-4506-a2ba-e8ba60c13656 | iii. Ducts and conduit location = ±12mm
| note | 3b700263-03e8-46ba-84ff-ee6429d59a96 | iv. Diameter of ducts and conduits = ±3mm
| note | 597d476f-8d2f-4834-8aa1-72bb6ad3490e | METHOD: Measure Visual
| note | d48cd681-e331-4b41-9907-62cbb252f035 | FREQUENCY: Where applicable, each pile
| note | c6533834-38ff-4ec8-b540-41371095392e | CATEGORY: IP
| note | 9fa89456-4f8b-42fe-93d1-8e8a1121d8ac | RESPONSIBILITY: Foreman SE/PE/SPE
| note | bff0322a-0416-4e7c-803c-b9138a0b0267 | VERIFYING DOCUMENTS: This ITP
| textbox | 752cb5af-5754-42b7-92b1-f5ba4f2f3c6b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.13 Surface Finishes
| note | 071f57ea-adce-4400-81ac-bb9ffcac533e | REFERENCE: IFC Drawings 610.31 610.20
| note | cc0cdacd-8008-4373-8f32-00940092c372 | ACCEPTANCE CRITERIA: Where applicable, surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
| note | 99e3ad6e-80ec-4dba-859b-6daef947f4d2 | METHOD: Visual
| note | 0ab8773a-77ee-43c7-9b3e-7733da5a60ca | FREQUENCY: Where applicable, each pile
| note | 06f88740-6c2e-4b5a-a109-b8d55774a0f9 | CATEGORY: IP
| note | c98ca9ab-49bb-4418-ab4e-545e091d732d | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 48e4e900-7962-4bfd-8e3a-c49987ebf49a | VERIFYING DOCUMENTS: This ITP
| textbox | 861b4043-ba86-4e4d-9dc9-c43b31a5baf9 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Pile Trimming
| note | e988110f-695f-43d8-9fbb-cacf0f60a306 | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 607.04
| note | 7bf1a0e9-17ca-4f02-bc47-f39b6effe113 | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
| note | 1dcd4bcc-c0da-408b-88c8-f74318124457 | Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
| note | 082ea061-0c7d-498f-bf0f-424a4590bd73 | Any weak or damaged concrete shall be removed back to sound concrete.
| note | 50a7df07-5b43-4f9f-a65e-f46ac5a73a5d | METHOD: Measure Visual
| note | 4c228f45-8055-493d-95d0-de2aa89d14d6 | FREQUENCY: Where applicable, each pile
| note | c6833185-7fa4-47c2-b3ed-f384eb5ee99c | CATEGORY: IP
| note | ce0d395d-3f16-4f5d-a4de-fbb0a89b2143 | RESPONSIBILITY: SE/PE/SPE
| note | fcf56337-2860-4250-b156-880ec4c1b818 | VERIFYING DOCUMENTS: This ITP
| textbox | 6816759b-10c1-44a3-8147-0233e40086ba | Date Completed:
| checkpoint |  | 6.2 Compressive Strength Test Results
| note | 2482939f-a076-419d-b1a1-fa0f5b18d3e6 | REFERENCE: IFC Drawings Table 610.05.051 610.16 (g)
| note | f32a43f6-c303-4646-ac26-29ffcfaa861b | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
| note | 4ed7c948-4515-4df2-81fc-ee3ef5862c67 | METHOD: Document Review
| note | de1cf5bf-4ee8-43de-9355-95f440bcceb0 | FREQUENCY: Each cylinder
| note | bd5deac9-3ad1-4691-9221-1c3b4e8cc89d | CATEGORY: IP
| note | c9e0a994-6fab-4fbd-8711-4634af151418 | RESPONSIBILITY: SE/PE/SPE
| note | e8389bad-ee38-443a-ac46-c5d185bf9774 | VERIFYING DOCUMENTS: This ITP
| textbox | 0e5d95e7-3288-4dd7-b537-13873d0bae79 | Date Completed:
| checkpoint |  | 6.3 Pile Integrity Testing
| note | 14ca632a-b47f-4e16-9855-8325307816a8 | REFERENCE: 607.04 AS2159 Clause 8.8
| note | 71ea829a-d9a2-4e98-ae0c-39da7534ca0d | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting. Cross-sectional area = ≥90% Attach: Pile Integrity Test Report
| note | 66654f52-8c3c-407c-a913-562ab65941c8 | METHOD: Document Review
| note | 8397c5f8-13ed-4404-8e02-8683f551f86e | FREQUENCY: Each pile
| note | 4a6a45a7-8c57-471f-9f53-dcdbfb9ee949 | CATEGORY: IP
| note | bf436a9d-dc52-4ab1-9e75-deb040c1312f | RESPONSIBILITY: Testing Consultant SE/PE/SPE
| note | 09ec89af-f83d-40ef-bcba-524e0e92fb6c | VERIFYING DOCUMENTS: This ITP
| textbox | a77dc1c4-03de-47f7-a649-01b05d664178 | Date Completed:
| checkpoint |  | 6.5 Dynamic Pile Testing
| note | 3466b639-b5c7-4756-8b5b-ea4ac5281481 | REFERENCE: 607.07 (b) AS2159 Clause 8.7
| note | 5c378945-e442-435d-9806-650317db39de | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength. Measured Ultimate capacity = ≥ values on IFC drawings Attach: Dynamic Pile Test Report
| note | ee022af4-3e37-441f-82db-2a9890242765 | METHOD: Document Review
| note | 9e6fb2cb-48c1-4161-891a-aaca8d8c1799 | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
| note | 8fc3423a-17c3-416d-83dd-9a9ff8f485f4 | CATEGORY: IP
| note | 8b90e697-e022-4c3e-a243-fa767e3decb2 | RESPONSIBILITY: Testing Consultant SE/PE/SPE
| note | afc61460-a84b-498d-879b-4af9cd0ebdb1 | VERIFYING DOCUMENTS: This ITP
| textbox | 99fd25ae-b4ae-49a8-adb9-7c3c5b1fd37b | Date Completed:
| checkpoint |  | 6.6 As-built Survey
| note | fa8b8673-f174-458d-9072-8866d44f2591 | REFERENCE: IFC Drawings 607.06 (a & b) AS2159 Clause 7.2.2
| note | 4265a958-32b3-4f42-bc1a-f3644c535a64 | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
| note | 8b35250d-a094-41bd-b504-c47ef9545b3f | i. Centre of pile head plan location = ±75mm
| note | 1d4ce3cc-d56d-445f-96e4-af813b975e46 | ii. Variance from vertical or rake = 1:50
| note | 03bc0101-4819-4bb0-ad93-f21b05d6e600 | iii. Irregularities in straightness = 1:100
| note | a7860a5a-d96e-4afc-b235-1db5f63fb1da | iv. RL = ±25mm
| note | ee496361-b319-40ae-8c01-18a0ea46617e | Attach: Survey As-builts / Survey Report
| note | 9e05655b-fdb3-4ee2-aa81-13f2ba41e499 | METHOD: Document Review
| note | 4f87fb5b-728d-4146-9bd3-827f2d327efa | FREQUENCY: Each pile
| note | 23b0b8cb-f099-4043-a017-2d027701ab49 | CATEGORY: IP
| note | c6b4bc34-4596-40b6-bd76-d6ac72b20476 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | db7dd9ca-a781-4e97-8086-9ef5e036fe4c | VERIFYING DOCUMENTS: This ITP
| textbox | c32927c7-2bb6-46e5-b8dd-95cbf6d9d286 | Date Completed:
| checkpoint |  | 6.7 Non-conformance Report (NCR) Closure
| note | 39f69717-806e-4cbf-8741-952c09d1a4af | REFERENCE: MRPA Quality Management Plan
| note | b5ee7182-264e-4a50-afb2-ed3907b7113b | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 558bd43c-4bd9-4927-850f-fbdf4a762f1f | METHOD: Document Review
| note | 124cdd04-a472-40c8-9f45-4d129799598b | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 693d76ca-3488-4e20-abb5-a2b4eaf88d32 | CATEGORY: HP*
| note | 0ade223b-1147-496c-9c69-17bc06397518 | RESPONSIBILITY: SE/PE/SPE
| note | 775cf99e-8ab6-4f31-afef-4c10ee550afc | VERIFYING DOCUMENTS: This ITP
| textbox | 84b9a5f1-0fbd-4797-8146-f8a9507d4493 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | b46b68f2-23c7-4834-b9bb-6f23653ba14b | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 7ce6fde8-f979-47da-844f-44c09486951e | Name:
| textbox | 04c56a2f-9e79-4836-bacd-424cd5c7095b | Position:
| textbox | c9145090-0fe8-4a69-9991-5768f19cfdae | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Structural Concrete Rev 3 | itp | ITP-STR-Structural Concrete Rev 3 | 6b657685-3c1f-4258-87c9-96612b78272e
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | a97551af-246b-531e-823c-c8dcdae78d9e | Document Title: ITP-STR-Structural Concrete
| note | 51e33dc4-63e1-5930-9dba-d1fcbec51f25 | ITP Description: Structural Concrete
| note | e263d61f-eb57-5d49-9993-6d16ce8c3b9b | Discipline (e.g. CIV/STR/RAIL): STR
| note | 7172c690-a39a-598a-bbdd-be21f23f8881 | Revision Number: 3
| note | 5b4cf925-1704-58c8-adae-6c533efcb016 | Revision Date: 12/05/2021
| note | 8c6d92d8-5ee1-5729-ae5a-7c824eabceb3 | ITP created by: Mike Freeman
| note | 53ffbe9f-34d9-551c-ad2b-8d318c79b029 | ITP approved for use by: Mike Freeman
| note | e4bcbefe-6e85-57cc-8cf3-f04cccb319ce | 1.1 VicRoads Section 602 October 2007
| note | f7b48ea9-64d4-5389-b602-dc55240cd259 | 1.2 VicRoads Section 610 June 2019
| note | 65361b6d-d3ce-5d06-ab9b-69c0545fd2ad | 1.3 VicRoads Section 611 November 2018
| note | 428c8458-f13f-5a7c-9b6e-684e4af022fa | 1.4 VicRoads Section 614 June 2017
| note | 1849c6aa-3610-56ec-a34b-12b6a9d30109 | 1.5 AS3810.1 2018
| checkpoint |  | 2.1 Concrete Mix
| note | 8698801f-ce7c-5292-879c-ff60909e5188 | REFERENCE: 610.07
| note | 02bada9a-9dd3-50b3-8b9a-185e4ab105b1 | Table 610.071
| note | 7c2e280a-485e-54ba-bf50-50c57323151e | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
| textbox | a00d1248-4e46-5156-9a5e-04ccbbd62595 | Enter: Teambinder Material Approval number
| note | e0ff5bf7-2816-5219-bcfb-04e47850fe66 | METHOD: Document Review
| note | 9316ca91-d0fa-5e68-8f5c-36a9aaddee34 | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
| note | 7cd7b0f8-8f57-5392-b890-54d5d81acb83 | CATEGORY: HP
| note | 479e33a4-7321-598c-86bf-4fc4d887ff28 | RESPONSIBILITY: Nominated Authority
| note | 6b942077-743f-5f46-9ead-c8a7994be726 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 2d3f74c5-7f6a-5c46-a522-d032a1837530 | Date Completed:
| checkpoint |  | 2.2 ACRS Certification (for Reinforcement)
| note | 69ae1d11-b68d-5905-9531-c3d1e5623bd4 | REFERENCE: 611.05 (a)
| note | 9f7193d8-f927-5cc5-9894-6f3fd0258ed6 | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing
| note | ba3cd733-46a9-56ed-b2d8-033665b3e1cd | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | caea1ed3-46c0-59a9-9340-013152d9c360 | Enter: Teambinder Material Approval number
| note | f6ec7599-c150-5224-976e-920e348fdef0 | METHOD: Document Review
| note | 7a90f6ff-9ef4-5531-bc06-2a8633351c41 | FREQUENCY: Once for each supplier, 14 days of award of contract
| note | 9b4d1289-2392-55db-a7b5-e2862d9f7494 | CATEGORY: WP
| note | 1d04a40c-477c-5ca9-9773-f7ca226c4e9e | RESPONSIBILITY: Nominated Authority
| note | 31805df8-618a-5634-a7a4-985d19625e6f | VERIFYING DOCUMENTS: This ITP
| textbox | 92206434-6065-5c39-8a72-b110d5df3dee | Date Completed:
| checkpoint |  | 2.3 Bar Chairs/Aspros Certification
| note | f302dfbe-05c5-57fb-83ee-97e37468c7e9 | REFERENCE: 610.26 (a)
| note | c5b0d796-ba8e-5edb-b50a-db53cac7ecdc | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
| note | cf28e848-9beb-5cf1-8f3b-5145ff050f63 | Concrete aspros require annual compressive strength and soluble salt testing is required.
| note | f40464dd-f0b7-5e42-ab08-475f156591c2 | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
| textbox | 86e3b9c4-e475-56d2-9a22-ad4f8e358bc7 | Enter: Teambinder Material Approval number
| note | eb3375ed-b2ca-53f9-aac7-5e730fea9e34 | METHOD: Document Review
| note | 525be135-0dfb-5c1b-913a-f9db8bd96103 | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
| note | ca4934dc-9e11-5f37-b34d-317adf1bdd43 | CATEGORY: WP
| note | 8d998068-43c3-5b4c-8cbe-73ba0b49275b | RESPONSIBILITY: Nominated Authority
| note | c53dcbfa-53f1-5b44-9615-26b73ab0df5f | VERIFYING DOCUMENTS: This ITP
| textbox | 739eaa1b-b973-5a35-aa3d-7d2815ed5f6b | Date Completed:
| checkpoint |  | 2.4 Evaporative Retardant
| note | 905299f5-cbc7-5bcf-b1e0-bc4e400cb305 | REFERENCE: 610.17 (f)
| note | aebe19c6-e71f-5404-ac2c-e9c34cccf79f | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority
| textbox | 161543ae-f4b3-51c3-a738-7c5dd0446789 | Enter: Teambinder Material Approval number
| note | 59b1113c-fd7f-5702-8053-4df5cb688586 | METHOD: Document Review
| note | 53b7d05a-3109-528d-b0be-afe94a9dabca | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
| note | 72ea244e-58b3-5f64-be36-a367ffb42c5a | CATEGORY: WP
| note | 622e1594-4bf2-5b8c-aedb-10b6a8f54a2e | RESPONSIBILITY: Nominated Authority
| note | 8d7524f7-81c2-518d-b0ac-fa3bf2c027ec | VERIFYING DOCUMENTS: This ITP
| textbox | 40a5aae7-624a-51e7-a8a4-a2f9fe10d129 | Date Completed:
| checkpoint |  | 2.5 Curing Compound
| note | c7d02a25-10ea-5c14-9057-671d4363451d | REFERENCE: 610.23 (d)
| note | 7952b45b-936c-555c-bb71-1c279a06defe | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| textbox | 20f99057-1961-5752-9f17-874a2463341f | Enter: Teambinder Material Approval number
| note | 688269bf-f66c-5d8c-8ea3-ba8ce879df00 | METHOD: Document Review
| note | 3554e020-0769-5f40-9559-97a2f1cd5576 | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
| note | 218ec411-2f19-5488-ba99-257f1891ce8c | CATEGORY: WP
| note | 657128b0-4f3f-5c8a-9f87-81bfa94599aa | RESPONSIBILITY: Nominated Authority
| note | 4bf03dfc-7909-5790-a805-5711dae19774 | VERIFYING DOCUMENTS: This ITP
| textbox | ad99c461-e6ff-5c37-91c7-dd6b2cfa7624 | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Concrete Placement and Compaction Work Method Statements
| note | 9c44602d-bfd2-5137-a7ee-6721c8007520 | REFERENCE: 610.18 (a) (i)
| note | f431e020-841f-5d89-9e87-978004583f94 | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
| textbox | d332400a-c9f6-5a41-9de1-13f2c469080e | Enter: Teambinder Approval number
| note | db639a3e-7185-5db5-a4c9-3d9a981ca08c | METHOD: Document Review
| note | 130938f8-025e-5605-aaa1-2c208ce24600 | FREQUENCY: Once, 4 weeks prior to placement of concrete
| note | 403c7190-67f7-59e0-95be-f0cec254639b | CATEGORY: HP
| note | 62f2a3dd-3a71-5953-8a0c-71de055b32f8 | RESPONSIBILITY: Nominated Authority
| note | dd03b114-be7d-5f44-9a15-6080bdf63779 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 48d7770a-65b5-5b10-89fa-f1e5e8a62879 | Date Completed:
| checkpoint |  | 3.2 Concrete Sampling and Testing Procedure
| note | 6d43ade9-e384-552b-8802-9b5dc499a5db | REFERENCE: 610.18 (a) (v)
| note | 442d36e6-6cad-5ab1-b141-af2745769629 | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
| textbox | 5aa5b33b-82d7-5ad3-81c7-f5b51a96ec1a | Enter: Teambinder Material Approval number
| note | 87ccca23-df4f-511e-99d9-ae3a03f9e0cf | METHOD: Document Review
| note | 6d5da1ec-e5a6-59ae-9531-f67f8cdfcae3 | FREQUENCY: Once, 4 weeks prior to placement of concrete
| note | 87ccb3cb-d959-5ef4-b0d5-81586547b870 | CATEGORY: HP
| note | 20bc30c3-fcd5-5c12-8877-6c201fae5364 | RESPONSIBILITY: Nominated Authority
| note | 10bacfc7-50a2-5da0-b9c6-8b30f3083b6f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | d6c032c0-ea95-54d3-a56f-44d9b5552c79 | Date Completed:
| checkpoint |  | 3.3 Concrete Placement and Compaction Toolbox Meeting
| note | 3857bf62-0fdb-57f0-9d94-f2d017c76960 | REFERENCE: 610.18 (a) (iv)
| note | 91c3c61f-241d-58b6-af93-aff37f68cd0f | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
| note | dd39b3d0-939b-58ff-b7bf-07b756c0b33c | Minutes of this meeting to be submitted to the Nominated Authority.
| textbox | 32196e34-d8cc-52d2-a365-3d66a47f16c3 | Enter: Teambinder Material Approval number
| note | ff520d0f-8f41-5fd8-a056-47c3f60a0f0a | METHOD: Document Review
| note | 36aeff07-3c77-5f28-812a-9b849cd93ae9 | FREQUENCY: Once, 4 weeks prior to placement of concrete
| note | c4de079f-d503-5d8a-aa65-0c61df31acf8 | CATEGORY: HP
| note | 754b29bf-b131-5a6b-a460-b076608f20c8 | RESPONSIBILITY: Nominated Authority
| note | 3b39db89-f823-5867-b7e3-3ef148a5f6df | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 82bb5f0d-f79e-550c-8fcd-02ef05c70469 | Date Completed:
| checkpoint |  | 3.4 Hot and/or Cold Weather Concreting Procedure
| note | 5f37b3c0-c198-566b-bd03-40aa0503a4be | REFERENCE: 610.17 (a)
| note | e244a8c1-da80-51fa-857d-4ef502a25ab5 | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
| textbox | 14be1544-b88c-5c27-a8a5-ce5a202c6989 | Enter: Teambinder Material Approval number
| note | 49a80c2b-a9d8-5129-a08d-07abe8d53714 | METHOD: Document Review
| note | 4d1fdc0a-6048-515b-a81d-12bef45f23fb | FREQUENCY: Once, 4 weeks prior to placement of concrete
| note | 9b613af8-c0b9-59e3-a79b-4a5f68e4978f | CATEGORY: HP
| note | 631de9f7-cc98-5b54-b2f4-5998589bda17 | RESPONSIBILITY: Nominated Authority
| note | 4c0637a0-e98c-5d5d-8d63-3aee43a4ddaf | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c7860018-b2d7-5d30-8c26-af599197ccb3 | Date Completed:
| checkpoint |  | 3.6 Early Loading and Trafficking of Decks and Approach Slab Procedure
| note | dea787ee-803a-5608-8e65-a9cfcbcf645a | REFERENCE: 610.36
| note | 07ce7625-3ba8-58d8-bb3c-06115b899fa3 | ACCEPTANCE CRITERIA: Early loading shall not proceed until:
| note | 1bd81d5d-9f10-5665-b9ab-2f90ae8ee553 | the early loading and trafficking quality procedures and ITPs have been reviewed by the Nominated Authority; and
| note | dcbc7dcd-c904-5f80-b472-7d21b09ba4e6 | evidence of the minimum curing periods, compressive strength results and temperature monitoring have been provided.
| textbox | 7734cc37-854d-58c2-a687-28fcda279c4c | Enter: Teambinder Material Approval number
| note | 8520e42f-d2f0-54b9-be90-c186d5e1a61a | METHOD: Document Review
| note | 1a457512-21bb-5c3e-9733-9efa774ac7ca | FREQUENCY: Where applicable, once, prior to application of load
| note | 5687ea9f-08a2-5314-b0cc-66a6431759d7 | CATEGORY: HP
| note | b61255e3-4bd5-5075-ba26-eb54a386ba83 | RESPONSIBILITY: Nominated Authority
| note | b88c1a1b-0bb5-578e-be9d-70219bb91801 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 5063f9de-78e6-533e-9d17-376c443b355d | Date Completed:
| checkpoint |  | 3.7 Concrete Drilling Procedure
| note | d901e42d-b112-5f3a-8256-53d1e7311ce5 | REFERENCE: 610.46
| note | aefad9f7-35af-5aaf-bcc1-82d9ac267e27 | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
| note | f998b361-5ea7-5af1-8ee7-a4a6f03d5f6e | The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
| textbox | 3a790745-62c3-5caf-9704-e91ca72d0280 | Enter: Teambinder Material Approval number
| note | d45d7670-a215-584b-ab26-3d1335d037b6 | METHOD: Document Review
| note | fef0677a-c4bf-5e05-a73e-cad36a58b166 | FREQUENCY: Where applicable, once, 2 days prior to drilling
| note | 2864cc67-5d11-52bc-909f-e8b869840587 | CATEGORY: HP
| note | 69b60fa9-edab-5f96-854b-443d4444a42e | RESPONSIBILITY: Nominated Authority
| note | 2a7dbef8-95f9-551f-bcd7-d2c47e9bb638 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c9e5dbfb-c4ac-5c63-a45b-e9188e1c3552 | Date Completed:
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 IFC Drawings
| note | a1598e41-9470-55ef-864a-4cd947331d4a | REFERENCE: MRPA Quality Management Plan
| note | 479e75fa-dfb6-552f-a8db-329656e6a175 | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| textbox | 1275eaee-7449-504c-85d3-7cfc85ead278 | Enter: Teambinder Material Approval number
| note | 969ee766-8391-5d73-b704-f9bdee033c80 | METHOD: Document Review
| note | 55ebe0a6-672e-5862-be15-6699b515e859 | FREQUENCY: Prior to starting Works and at regular intervals
| note | 99b59b1f-ceba-5062-b5ad-b7ff2db0f33c | CATEGORY: HP*
| note | 2172d2cc-dfaa-5322-b0a0-d1cb97eb9801 | RESPONSIBILITY: All
| note | 0b2520da-4982-5a36-ab71-ddce1ad39a24 | VERIFYING DOCUMENTS: This ITP
| textbox | a413f3c6-318b-5ec7-a08f-03fc0b504c23 | Date Completed:
| checkpoint |  | 4.2 Survey Set-out
| note | f04c90d2-90f1-5081-8e65-661be26066bd | REFERENCE: IFC Drawings, 610.47 (a), Table 610.472
| note | b9af0e36-0893-5c28-9255-1e84d42706d0 | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
| note | c8b395d4-ce5d-507a-aa51-462dd8a0b36f | METHOD: Measure, Visual
| note | 821c450a-c5f2-518b-96bc-08fb3e972fb5 | FREQUENCY: Each element
| note | b550a5cd-682d-5fa4-8005-987ce10f0932 | CATEGORY: IP
| note | 28c0c74f-f9d2-5ad4-8686-edf2598e6561 | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | 5802d3ae-807c-52b0-85ab-ac3266e6876d | VERIFYING DOCUMENTS: This ITP
| textbox | 20d1d337-3c0d-5b15-aea4-18abbe95c18b | Date Completed:
| checkpoint |  | 4.3 Excavation Drawings
| note | a779e083-402d-5bfa-b175-37270f93ea30 | REFERENCE: 602.02
| note | a8ea0931-cc01-5c14-8b5d-81712a1da615 | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
| textbox | 639bed5e-5d1b-5070-9cdd-506f3e101eb7 | Enter: Teambinder Approval number
| note | f2dde708-9a40-5685-8d28-a93a78c0e299 | METHOD: Document Review
| note | ae55ca9f-ea0a-502d-813f-c65e7beb1b12 | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
| note | bd6fa580-664f-56ae-9826-cd9d128104ca | CATEGORY: WP
| note | 95f60467-f2df-562b-a504-efdea65d4865 | RESPONSIBILITY: SE/PE/SPE
| note | 6e9e41c4-b5c9-5921-afb7-421765ff8bbe | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 52b236c9-bded-5dd1-94e0-b3f620b762b7 | Date Completed:
| checkpoint |  | 4.4 Excavation Inspection
| note | c826fd17-1bf9-56d8-b6f3-c2b11b39bdc1 | REFERENCE: 602.03
| note | 511a3024-1ecf-5fda-9304-86e12d13c4d4 | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
| note | 2709c9d6-96a0-544e-89ca-f9df7285cdb3 | METHOD: Visual
| note | 4985d820-5620-5476-8006-b389ab0d4184 | FREQUENCY: Where applicable, prior to placing blinding concrete
| note | 66422e9a-83d8-5b1a-b553-0bc1b235cb05 | CATEGORY: HP
| note | b55c50ee-8a7e-5374-be83-d4e64be7e640 | RESPONSIBILITY: SE/PE/SPE
| note | c9844646-a916-5608-aeee-dd8b56f28c4c | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 2df2f842-e992-59ef-8296-57e7bf4c5245 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction Activities
| checkpoint |  | 5.1 Formwork Design and Construction
| note | 9a23f521-021b-5911-88ca-93afd868bec3 | REFERENCE: IFC Drawings, 614.04, 614.05, 614.06
| note | d19aedbb-be0f-534c-a80d-55e6093cac9a | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
| note | 96eccdcf-6fcd-5889-b709-521b384908c0 | Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
| note | 918dce0f-6ee3-5d01-943b-9a6c2ae79a2b | Formwork shall not be placed where steel & fixtures cannot be inspected.
| note | 8bf3355f-89c5-5280-a2fd-18f6d326c214 | METHOD: Document Review, Visual, Measure
| note | da3ca8e1-385f-5099-9bd2-f3965d72f59b | FREQUENCY: Each type of element
| note | 42138e6d-82b1-5ac9-9846-b46ed9398c6f | CATEGORY: IP
| note | f62fc1d4-decc-5e27-93b5-fcf595858bd5 | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
| note | b1e49d10-f72c-5c17-af63-10fea11186f6 | VERIFYING DOCUMENTS: This ITP
| textbox | 2a94157f-cd0b-51f2-b525-31e4903c4fa7 | Date Completed:
| checkpoint |  | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
| note | d2ca25e4-6391-57cd-9666-c88cbe852cb8 | REFERENCE: 614.08
| note | ee0e7767-802b-5483-8480-4397ad3dc1b3 | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
| note | fce4cc5a-a2d8-5d71-8bfb-0547bfa22f8c | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres
| note | 5314e331-702c-524a-863f-eac45deace96 | All other concrete members
| note | 078b632c-9b0b-5207-8938-c1ed2f1e4b3f | Any member for which self-compacting concrete is proposed.
| note | bd87daa7-fa1c-5912-8b2b-c601f4afd8b4 | Attach: Attachment A
| note | 9e56ef48-dd01-5e3b-b96b-b8d0a37d27b4 | Attach: Attachment B
| note | 9e42cc5c-71ce-594b-929f-35c432546524 | METHOD: Document Review, Visual, Measure
| note | de459b5f-1618-5e52-9e45-e5d4dc70c8fe | FREQUENCY: Each element (where greater than 2m)
| note | 2a03c0b5-7410-568c-81fb-9868fcd5276d | CATEGORY: HP
| note | ea6d2707-3331-5703-898c-18bc8be0fc06 | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
| note | d4a9a3a0-6a6a-575f-b5c1-94bf81798a7b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 18130d1c-b874-58e2-b598-efa6289507eb | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
| note | ded0d797-4804-5edb-875b-b4ee74bde37d | REFERENCE: 614.08
| note | 121560c9-e000-5e0c-882f-6b41624c78b3 | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
| note | 6d41e56e-681e-59bb-bbfb-ef51e65d4adc | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
| note | acc1a199-f43b-51c8-a854-cfb1bb1bff3e | Attach: Attachment C
| note | b3331828-4416-5b11-a543-41b42c970a2b | METHOD: Document Review, Visual, Measure
| note | 19f9b1d0-0747-5d3f-b16c-aa912e6edc2d | FREQUENCY: Each element (where 2m or less)
| note | a0988c05-0879-5f52-937c-29816e002851 | CATEGORY: HP
| note | 3ec1eee6-78f5-59bf-8e77-6543f544b328 | RESPONSIBILITY: PE/SPE
| note | b38ddcbc-0db1-5002-bc00-7c4ab47ec5a5 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | d48ee42a-8a63-5066-ace0-c51bd9afff81 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4 Pre-pour Survey
| note | afce64f5-868a-55d1-9b79-b7f8dd4444ae | REFERENCE: 610.47 (a), Table 610.472
| note | 74905cd6-3aad-53ec-9155-60bec61a4e6a | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
| note | e786be97-2795-5d7e-931f-ca7dc47cf1c1 | METHOD: Measure, Visual
| note | 20dabba4-eb3a-5187-8331-39c67bf024f7 | FREQUENCY: Each element
| note | 71dd6ce1-1d87-587d-bc3f-4d951a414c52 | CATEGORY: IP
| note | 98926faf-9c0a-501e-8d47-c4a52ea86299 | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | e972f242-4fbc-588c-9eaa-de3491119c8f | VERIFYING DOCUMENTS: This ITP
| textbox | ea5462cd-f621-552e-a588-fa265d06a21a | Date Completed:
| checkpoint |  | 5.5 Reinforcement Placement
| note | 6adf5e32-d7c5-51d7-8871-397990c0d443 | REFERENCE: IFC Drawings, 611.06, 611.09, 611.10, 611.11, 611.12
| note | e2df325f-ab3c-5941-b4b7-9be193f0883c | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
| note | 6fc11ebe-ed84-5f4c-9f32-8456a28db44d | Projecting reinforcement is the correct length and location.
| note | 9a9ed214-790e-5c0e-8b36-4db4102e889e | Splice lengths achieve the minimum length and are in contact for this length.
| note | d976746b-87b6-55f1-80de-30df5f23f3e0 | The reinforcement surface condition is free from dirt, debris and damage.
| note | 6bf9f6d1-1895-595f-b483-ad5dbb7cf452 | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
| note | 3568a405-a6f1-51f0-931e-bd22ef6367d6 | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
| note | 302efedd-4053-5b39-8ca5-6ce97b78871c | METHOD: Measure, Visual
| note | c55eb57d-076c-5648-931f-320db376c093 | FREQUENCY: Each element
| note | a1932b86-b0a5-566b-8cc4-6af44007ed35 | CATEGORY: IP
| note | a3b09e0f-0ea7-5129-bc61-d555432c0712 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 9fc4705a-a379-57b0-8ae2-3d3a93303096 | VERIFYING DOCUMENTS: This ITP
| textbox | 09a14c6f-67d8-5234-9b7d-4fc9658f9ecd | Date Completed:
| checkpoint |  | 5.6 Reinforcement - Electrical Continuity
| note | e3570d05-3812-5a5c-ab0b-1920b3e9ff0f | REFERENCE: IFC Drawings, 610.29 (d), 610.43
| note | 8220c961-e01f-50d2-a294-f0311c0ba8bf | ACCEPTANCE CRITERIA: Element reinforcement cage to be made electrically continuous by:
| note | 78c490d3-8af7-5ddd-a2f7-695e05bf6a79 | i. tack welding 4 no. min. selected main / longitudinal bars to all intersections of every ligature / lateral bar at 1.5m centres
| note | b36572cf-e326-5784-bab8-763f1b6212cb | ii. tack welding the selected main / longitudinal bars at all splices (2 tacks minimum per bar)
| note | b54f3cc5-1ed8-50bd-8615-f40e75946bfe | iii. tack welding or fastening the grounding clamps to the main reinforcement
| note | 7dc1e0bc-b45c-5af1-aede-4c498fd54cfd | Evidence that the resistance across the cage has a maximum value of 0.01� / 10,000�� is required.
| note | 032b36c7-0295-57da-912c-d7542cbb0f32 | Photograph or attach: Ohmmeter reading from end to end or corner to corner of the reinforcement cage
| note | 7d06cb4f-6453-5abb-b5c5-f9464036dce4 | METHOD: Measure, Visual
| note | 1ce93031-45d5-5799-8936-411c1e7367dd | FREQUENCY: Where applicable, each element
| note | c3ea8399-6b2b-573a-be4c-850bdb31bf3e | CATEGORY: IP
| note | 527d26ae-6f29-5020-8b6e-a6150286f8f3 | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
| note | 36feb8ce-b043-5f9c-8e50-2930c9fdd6f2 | VERIFYING DOCUMENTS: This ITP
| textbox | 3823f81e-d5d8-52bc-a382-f91c3725d41f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.7 Cast-in Items
| note | a3573f3b-3903-542f-afe5-698aa60ee413 | REFERENCE: IFC Drawings, 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
| note | 3c90d2e6-b6a4-58ea-a50c-56ec5c33ce19 | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
| note | b9d95a1c-e00b-5138-9d82-2572af1bb283 | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
| note | 34253a31-56bf-5b05-9a38-f6de69d51b20 | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
| note | fb519ad5-f894-5f55-9ddf-c86ee94f9a62 | Grout tubes shall be fastened at regular intervals to prevent kinking.
| note | 02127fe7-81ea-5ad1-ba59-8884c2924393 | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
| note | c470172e-e323-5486-86bb-d1cf519b7e46 | i. Bolts, ferrules, projecting bars & couplers = ±3mm
| note | 965ac793-ebd5-55fa-a56c-4c55602c1789 | ii. Running dimensions of a group of the above = ±6mm
| note | a6a1d764-4d16-55c6-80bb-7dcffd9827f4 | iii. Ducts and conduit location = ±12mm
| note | b2588c59-2bd4-5809-aba5-1a588183d017 | iv. Diameter of ducts and conduits = ±3mm
| note | acb60aff-a7f7-573e-8a63-403718a05241 | METHOD: Measure, Visual
| note | b2635f7d-1f1d-5433-a3a4-e17c28e63fa2 | FREQUENCY: Where applicable, each element
| note | 7c34a8eb-8418-5afb-918f-325d0b6424be | CATEGORY: IP
| note | 5d4e500c-0b03-5496-a041-2f3cbb6513a1 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 53f88de5-f899-58cd-a602-a24d6d5a90c4 | VERIFYING DOCUMENTS: This ITP
| textbox | a0970411-3b1e-502b-a1cd-8a6e154d0393 | Date Completed:
| checkpoint |  | 5.8 Thermal Differential Monitoring
| note | e9939065-a6fe-5cdb-88e5-32d813cf0e9b | REFERENCE: 610.22
| note | 48f03dca-5d1c-54bf-8da1-d2f7f655ce80 | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
| note | 7fdf83a4-eb7f-5d21-ae1b-a17b8672cf45 | Only applicable if the element has:
| note | d0ede7f7-5186-564c-8fec-4b86b00011da | i. the smallest sectional dimension exceeding 500mm
| note | ae17e2c6-4635-57f2-aa2a-d0a73a3bf836 | ii. one or more faces being restrained by previously hardened concrete or other external constraints
| note | 9911cc62-226f-5689-b5b7-9caa1fc8e206 | METHOD: Measure
| note | 26acb5a0-8826-56f9-8bf0-e26b370a484f | FREQUENCY: Where applicable, each element
| note | c2dec2b8-9abf-5da3-838f-bacdcd8c7c2c | CATEGORY: IP
| note | d989de34-f955-545e-af34-3a9db6c44b60 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 18189fbe-2ca9-529c-a13e-4eb183e9262f | VERIFYING DOCUMENTS: This ITP
| textbox | 9f0abe11-82f8-5009-a930-353f9bbfdc81 | Date Completed:
| checkpoint |  | 5.9 Pre-pour Inspection
| note | 567a261a-109a-524b-bcd4-ebb78350bf11 | REFERENCE: IFC Drawings, 610.18 (a) (ii) & (iii)
| note | 9f44c230-3f39-5282-92ae-f13eaf490854 | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority. All foreign material has been completely removed from the forms.
| note | a89dd1ae-ff4b-51b2-92d5-9e19c2d60bae | METHOD: Measure, Visual
| note | 3347c57f-d182-5fa4-bfa4-2c8993bcd732 | FREQUENCY: Each element
| note | 0b0b0cea-c781-5ca4-84ba-686a872e1e28 | CATEGORY: HP
| note | 8f6b2445-2c98-552d-9f84-746a77006bc2 | RESPONSIBILITY: Nominated Authority
| note | 857a5456-2104-5cc9-9e8c-28f492fa0394 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 3087fdde-b0c1-58a0-90f5-545a7283faca | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.10 Weather Conditions & Evaporation Limits
| note | e52c382e-3fe8-55a8-9990-92ba9e41dca6 | REFERENCE: Hot and/or Cold Weather Concreting Procedure, 610.17, 610.17 (a) & (e), Table 610.171
| note | 9583b5ce-e6fa-56db-a841-d7cea45dc7bf | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | 9fd79ca8-b645-5a94-a5a1-943662b7e9ab | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | c95ba554-1f08-56d1-8b44-1f353fa8c466 | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
| note | bbe54aba-4a58-5e17-8fb9-9c5151044ff6 | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
| note | ca421dec-60f1-537c-8030-95fd33b8a392 | Record: Required information on the Concrete Pour Record.
| note | 356b3bac-a7a1-5a19-b2a2-4945ae34de07 | METHOD: Measure, Visual
| note | 294441f5-8dcf-5017-9150-a87d4e09a342 | FREQUENCY: Each element
| note | 6b426494-c966-53ff-8ded-771f19a66917 | CATEGORY: IP
| note | 81fc1b10-b1cb-5fc1-b096-7a730ff6a159 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 22a8c5d7-1afe-52db-a6f3-4c4c30ea32a7 | VERIFYING DOCUMENTS: This ITP
| textbox | bb253476-3174-565a-9342-42f69ef08bff | Date Completed:
| checkpoint |  | 5.11 Concrete Testing - Sampling Frequency
| note | 5dd9dcb7-ff4e-53e2-ad64-47e3da5e19fd | REFERENCE: Site Sampling & Testing Procedure, 610.16 (b)
| note | 50d9c7ee-c65d-5127-9f9e-deddaf4040f2 | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
| note | 92d9ed22-c608-5d09-abd3-473e6d3c9156 | 0m³ to 10m³ = 1 sample
| note | 33055125-b3c2-5264-b550-686b7d687e35 | 10m³ to 25m³ = 2 samples
| note | 0f3cb237-61a3-5140-8b24-31ddcecf3a2b | 25m³ to 50m³ = 3 samples
| note | 36638a0e-1b25-5d3c-80b2-d796b8e7e652 | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
| note | 6ada4062-3b2b-5096-b9f8-41d5a0e7ace3 | For each additional 50m³ and additional sample shall be taken.
| note | 5cc2a359-8919-5ab6-bba4-bef4eea247f0 | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
| note | abab45c4-20bd-5cba-b645-773e564ef900 | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
| note | adc7a43d-0bc5-5085-89ca-31c5eca66d68 | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
| note | 82169a08-4c02-5079-a66c-606236f99c96 | Record: Required information on the Concrete Pour Record.
| note | 894f00ee-2bc9-5e3e-aafb-a25ddbb05e6f | METHOD: Test
| note | 63f171c9-4628-5fd9-abb8-8b41db2520c3 | FREQUENCY: Each element
| note | e835c03c-4cdc-52f8-b332-dd02a405d876 | CATEGORY: IP
| note | aceee362-01c9-5421-861c-b7e899e42c8b | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
| note | cb4ddb8f-858f-5ed4-acf3-c62e63680006 | VERIFYING DOCUMENTS: This ITP
| textbox | b06fea77-bfd7-522b-a33a-3c8fbee4ac52 | Date Completed:
| checkpoint |  | 5.12 Concrete Testing - Slump
| note | c3b8d4ce-4ff7-5b65-803c-d2d3c4f2332e | REFERENCE: 610.16 (c)
| note | f62efb4d-ddd6-5528-827c-b5dc893d61c0 | ACCEPTANCE CRITERIA: Slump testing tolerances = <60mm = ±10mm
| note | 6b7ea989-2fce-5099-a33d-3a80922e0bae | ≥60mm to ≤80mm = ±15mm
| note | 33e87f2c-a646-5735-bce8-0034076e98f4 | >80mm to ≤110mm = ±20mm
| note | eeffb729-9419-5a3c-bb1e-faeccc7aae8f | >110mm to ≤150mm = ±30mm
| note | 18364d0d-bd95-55b5-b4fc-c092394cb3df | >150mm = ±40mm
| note | aa3a3158-2f13-5c1f-8cf6-9f5113fc6947 | Record: Required information on the Concrete Pour Record.
| note | a8310a5c-394c-5b72-bcb2-f113380b3f34 | METHOD: Test
| note | fe4fe253-141d-5955-b709-4936741c165e | FREQUENCY: Each sample of Standard or Superplasticised Concrete
| note | e8013985-da01-5e43-9bea-cc0d9f5f456e | CATEGORY: IP
| note | 716fc965-de76-5b38-afff-a119ae106d52 | RESPONSIBILITY: Concrete Tester
| note | ac258b4b-4a57-55b3-895e-0e530a4b6c44 | VERIFYING DOCUMENTS: This ITP
| textbox | d90e1498-423a-5d42-ae9a-02bec1d20e8f | Date Completed:
| checkpoint |  | 5.13 Concrete Testing - Spread, Passability & Viscosity
| note | 0e209274-a42a-594c-9dbc-097b50a13e55 | REFERENCE: 610.13 (b)
| note | 0f324b11-f3db-5edb-ae8c-ad8b15f02a6b | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
| note | 48d0eec4-f1af-59f6-b1f5-ebc0a14f4680 | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
| note | 1c3f76f4-00d8-5432-969e-a9020982c2da | Passability = d10mm (aggregate height differential)
| note | 9ce65bc9-7a11-550c-9185-57fa5cb22258 | Record: Required information on the Concrete Pour Record.
| note | 6db0ec2d-a259-5f1b-b258-7834a2fe5ffc | METHOD: Test
| note | af927c48-d48c-5ea8-88ab-42456495d94b | FREQUENCY: Each sample of Self-compacting Concrete
| note | 61369700-59b0-5542-ab6a-a1467256a32e | CATEGORY: IP
| note | 474d296c-7a17-5f7c-b99d-3f4e81db3c8d | RESPONSIBILITY: Concrete Tester
| note | 51f1604e-7456-59d4-9376-3d0a4d6baae1 | VERIFYING DOCUMENTS: This ITP
| textbox | a83a82a4-138c-5600-84f3-6ce6dd98b905 | Date Completed:
| checkpoint |  | 5.14 Concrete Testing - Compressive Strength Cylinders
| note | 83c23a3a-cdeb-5210-8fcd-5b01700bd6e3 | REFERENCE: Site Sampling & Testing Procedure
| note | da8016c1-537f-5a2d-a1a5-875e604896f1 | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
| note | a6427173-2b07-5d02-943e-dda9409afe8f | METHOD: Test
| note | d06208af-daad-53be-b3b3-9095552a3cc1 | FREQUENCY: Each sample
| note | ca432a50-3897-5c91-9801-bc57599df91d | CATEGORY: IP
| note | caf32316-8192-597c-b284-7338722e52e6 | RESPONSIBILITY: Concrete Tester
| note | 58914674-7536-53b9-b185-3e3ac1cdea77 | VERIFYING DOCUMENTS: This ITP
| textbox | b65cc4ec-3ace-52ec-a03e-e8755f8a8dd7 | Date Completed:
| checkpoint |  | 5.15 Supply & Discharge Rates
| note | eae180da-2e3c-5291-908a-e7da0138cd17 | REFERENCE: 610.13 (a) & (f)
| note | b9496a50-500e-566a-a917-e6842d66d00b | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
| note | 70103e6f-7762-55c4-980b-281a4f7fc2a8 | No water is to be added once discharge commences.
| note | 073ad2ce-5541-578a-9cc5-7117b505a6a4 | Maximum time between batching trucks is 25 minutes.
| note | 71acc7d5-4a0c-5f33-ab34-dddbdaed7127 | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
| note | c7b369fa-20fc-54f1-82c1-9d137d331dc3 | Concrete that stiffens or is showing signs of stiffening shall not be used.
| note | ad2173e2-94ac-5bb1-be26-0d7aff885cb0 | Record: Required information on the Concrete Pour Record.
| note | 68ea08ce-5be0-5edc-adfd-4b17916ca805 | METHOD: Measure, Visual
| note | cd2d6080-d991-58a1-9e5b-62e4c9af3d9e | FREQUENCY: Each load
| note | a9986e47-5434-5957-bb9f-af1fc42d5b44 | CATEGORY: IP
| note | 22fc7447-ba44-58c9-984b-2a9bcec7eaeb | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 84ff7875-8f20-59d1-9cdd-6bab9065a5fb | VERIFYING DOCUMENTS: This ITP
| textbox | e78e0edb-0622-5e0b-9751-b3f85c5c28b1 | Date Completed:
| checkpoint |  | 5.16 Placement & Compaction
| note | 6d7f247f-3f6b-5009-b039-d442c513d96b | REFERENCE: Placement & Compaction Work Procedure, 610.18 (a) & (b), 610.18 (d) (i)
| note | 191453e5-d324-5b7d-a4ae-0b1af83c67ee | ACCEPTANCE CRITERIA: All concrete batches are traceable.
| note | dd6cf09d-c99b-5aaa-9972-39aac22174f9 | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
| note | 36152fe0-2781-50ea-b33b-bccee6d534c8 | Concrete is not dropped freely from a height exceeding 2m.
| note | 701bb17f-9862-5c91-8e40-4c9a96550419 | Concrete is not moved horizontally by use of vibrators.
| note | f8477a9f-5285-51a4-9162-0c04e982d1a4 | Adequate compaction is ensured
| note | 1270cd50-5b2c-5417-9cb9-1df3e0652064 | Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
| note | 919281a2-bfbc-5a48-b6fb-9726d3f25ac0 | Concrete layers are not more than 350mm
| note | 27c5df7f-682f-5547-a511-6df5d06d6681 | Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
| note | 172d88d9-d7df-5a27-b662-9f20a57a7065 | Vibration continued at each point until air bubbles cease to emerge from the concrete.
| note | 74525bd0-5c9b-548b-8f46-0e2436945919 | Record: Required information on the Concrete Pour Record.
| note | 571774a3-60dd-53bc-bbd6-da6c12533a66 | Attach: Concrete Pour Record
| note | 01848f16-1c8f-5c15-a6aa-58e1ed77994b | Attach: Concrete Dockets
| note | b0d7eb18-5960-53d5-a621-5db06989187e | METHOD: Visual
| note | 3cfbde8b-e621-5fbf-951c-c4ba1ebf1a77 | FREQUENCY: Each load
| note | 0224202e-5b07-5fce-b3ee-013dd1942647 | CATEGORY: SP
| note | 2b76c4c4-b681-5335-aadd-d394fdf93a37 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 50e9ec22-f508-5043-8c08-e4a4eef94a64 | VERIFYING DOCUMENTS: This ITP
| textbox | 673923a6-923a-5a6f-b6dc-bad08c0766da | Date Completed:
| checkpoint |  | 5.17 Surface Finishes
| note | 24a60cfa-c364-54d6-a759-9ad827b20e94 | REFERENCE: IFC Drawings, 610.31, 610.20
| note | 480cb9ee-89d6-5ce0-8971-ed35a0129086 | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
| note | 4080561b-3138-59a9-9572-af1a6316c004 | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
| note | 95830b48-18ab-5a74-adbd-9a7f50e20096 | METHOD: Visual
| note | e824c501-c684-5b72-9a87-a9efdb4b80cf | FREQUENCY: Each element
| note | d6661d00-60e9-5976-8132-0316df0ad50d | CATEGORY: IP
| note | 634aca69-6e9a-57e4-b887-61a7eaf90d2b | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 4fb98b99-d25c-54e0-9ae6-a1262cf678d8 | VERIFYING DOCUMENTS: This ITP
| textbox | f1847edc-084a-50a6-a357-92c4ca3dc8a3 | Date Completed:
| checkpoint |  | 5.18 Curing
| note | 3ab421ac-ccc7-5511-a65f-db9118537f3e | REFERENCE: Curing Methodology, 610.23, Table 610.231
| note | cee89d35-d188-5520-9186-921af58fa2fc | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | 6f0ec38a-1bd2-5121-b9a5-85abbaf54cb9 | METHOD: Visual
| note | 93037677-aeab-5367-974f-e119c8c93711 | FREQUENCY: Each element
| note | 7e27490d-cf2f-5b08-9c1f-243a6fc3d5b2 | CATEGORY: SP
| note | 42e9c3ed-76f7-5c9d-b0be-0f28ec73fcaa | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | feeca18c-dd92-59d3-a428-856fe941e65f | VERIFYING DOCUMENTS: This ITP
| textbox | 416e28a5-9eb0-5a12-8694-4e37b82a050d | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Thermal Differential Monitoring
| note | 989c7c48-ee80-5ace-b72e-5ddc545dd00e | REFERENCE: 610.22
| note | 8d71874e-ba29-577a-961b-f4521f33dcb6 | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20�C.
| note | d558525e-f5b1-5d6d-a313-5bd267015fde | Only applicable if the element has:
| note | 421e2c00-f307-5458-bc87-2d76fe7b90a1 | i. the smallest sectional dimension exceeding 500mm
| note | 9220be94-290a-5155-8471-42412beb653d | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
| note | c9ed6813-abfe-5741-ba73-9b9a0276d9de | Attach: Thermal Monitoring Report
| note | 35aa3f41-9177-5291-a77e-f81a069a2a92 | METHOD: Document Review
| note | f20105f6-6ae3-57f3-93f1-56fd89cd3bdc | FREQUENCY: Where applicable, each element
| note | 69ba4aad-4b7e-586b-89df-25a76aefdd28 | CATEGORY: IP
| note | 2a767854-67ca-5da9-9289-eaec9c129077 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 633a882a-5a40-5507-a35d-7a72db0440e2 | VERIFYING DOCUMENTS: This ITP
| textbox | 303f17c9-912f-563e-805d-bce50944e131 | Date Completed:
| checkpoint |  | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
| note | 9166fd51-2afa-5479-8a8b-fec2c2856e5e | REFERENCE: IFC Drawings, Table 610.251
| note | d3876480-6daf-5434-bf33-0fcef41967d3 | ACCEPTANCE CRITERIA: Where IFC drawings do not nominate minimum strength development for removal of formwork, refer to table 610.251. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
| note | 5f4652ac-df70-556d-8c05-f01eda0dfe2f | Only applicable if the element has:
| note | 58490e52-7d2b-5083-b4b2-34c81465c9d8 | i. the smallest sectional dimension exceeding 500mm
| note | 61aeeed5-203b-5276-9c15-2a804c4b2854 | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
| note | eb3205e7-7a8b-5c8b-b152-1054d273e97e | Attach: Thermal Monitoring Report
| note | 14b654ae-5a0c-51c5-809c-3aa98798ef6b | METHOD: Document Review
| note | 4537df01-1977-55c3-91f8-c93ddeda4451 | FREQUENCY: Where applicable, each element
| note | 25a3869c-1dc6-53e6-b205-36f78e89a662 | CATEGORY: IP
| note | 65c42148-8d18-5c4a-ab1a-751f360e03ee | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | c38d6e72-73b0-515f-b59b-8e7ed5a1dc2f | VERIFYING DOCUMENTS: This ITP
| textbox | 6087176f-a41f-5f7f-b660-05f9b36de381 | Date Completed:
| checkpoint |  | 6.3 Surface Inspection - Cracks
| note | 61668ca5-f3d7-5db5-9cdc-30d88f828efd | REFERENCE: 610.24
| note | f75f1ab1-42ff-5db5-bd18-a6581d3accd0 | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1). If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
| note | 71ccff73-4b9c-548d-aaf2-e40d064097aa | Only applicable if the element has:
| note | 0f813708-4f3f-5124-9d44-9957a9aafe4f | i. the smallest sectional dimension exceeding 500mm
| note | d1544ccf-93a1-5314-97c1-a809da2e73fc | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
| note | e2037724-967a-5ad5-82d1-63bb28d8e8bc | Attach: Thermal Monitoring Report
| note | c5880c9c-129e-502a-b92a-6469ae150167 | METHOD: Visual, Measure
| note | c19914ff-4495-59dd-a8d4-cb717e566f3e | FREQUENCY: Each element
| note | 78e8b984-4516-57c6-879a-08a5befdd822 | CATEGORY: IP
| note | 421e6a27-5329-5822-80e1-637471e463ed | RESPONSIBILITY: SE/PE/SPE
| note | 0aa51f90-a2d1-53f0-ba44-bedd31328dcd | VERIFYING DOCUMENTS: This ITP
| textbox | 5fdb6057-5356-5aa6-b5df-aad0c8798df7 | Date Completed:
| checkpoint |  | 6.4 Surface Inspection - Surface Finish
| note | 102aac8b-b2ce-513b-8d44-f409927425bc | REFERENCE: IFC Drawings, 610.31 (a) - (n), 610.32
| note | d8a6bb47-294c-5289-b857-b58a1cd5c1e6 | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
| note | 22f0cfff-77c8-5849-b56d-752736540fb4 | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
| note | 38026483-c5e1-5dd7-8962-245d7d9307f6 | METHOD: Visual
| note | 5c271ca1-8876-5dc1-9b32-9c2954b062f5 | FREQUENCY: Each element
| note | a9f4e186-9634-5f89-95ef-d090d03e4a49 | CATEGORY: IP
| note | d151cc4d-4067-57f3-a045-68ed3d12a62e | RESPONSIBILITY: SE/PE/SPE
| note | 3a793a23-44e9-54eb-b11b-26265eec66ca | VERIFYING DOCUMENTS: This ITP
| textbox | 89381728-375e-53bd-9010-511eeadd1734 | Date Completed:
| checkpoint |  | 6.5 Measurement of Concrete Cover
| note | 54c2379c-5ef8-5301-8395-1d1baa9e8a0a | REFERENCE: 610.34
| note | a8893124-17ad-5085-abd0-d9af2e2f00fe | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
| note | 717e22de-c1c5-58af-b42c-3a31fd36bfb2 | Minimum 10 no. measurements recorded in each area.
| note | 99fbda9b-5bb5-5c71-8711-b261abb196b0 | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
| note | 883af887-c789-53d1-a79f-0febcdcb422b | Attach: Covermeter Check Record
| note | 4ac7b100-0e8c-5687-9575-eeaaf01d2acf | METHOD: Measure
| note | 4e91c4a5-6c8e-558f-a2af-de2eb6b848b0 | FREQUENCY: Each element
| note | 2ee5009e-69e3-513f-92a0-2b35ee99df33 | CATEGORY: IP
| note | 3296eb25-c672-52ce-a3e7-9d962a6a1908 | RESPONSIBILITY: SE/PE/SPE
| note | ef6febc3-5243-502d-a1a4-ca20e682a731 | VERIFYING DOCUMENTS: This ITP
| textbox | 37a0a671-a709-5e18-b3dd-02518facfa29 | Date Completed:
| checkpoint |  | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
| note | 2849aa3e-e78b-54cf-87f2-44333e39f066 | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure, 610.35
| note | bc52587b-6914-5adc-8160-a728e7e02b7f | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
| note | 56d96c5d-10ac-5ad3-bd24-816c9bd334fe | Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
| note | c7d8a2b1-f517-5e9a-8d4e-2e3e48bada99 | Attach: Concrete Test Results or Maturity Test Results
| note | 4b5dad0d-a75e-5088-87f5-4c6d90275c74 | METHOD: Document Review
| note | 3415a757-b91f-586e-aea7-2ece1ee7c308 | FREQUENCY: Where applicable, each substructure element
| note | 03ce317b-d0d4-5880-9890-55919a13fdb6 | CATEGORY: SP
| note | 52a61b11-f8f6-5a35-829d-75d2b3bcd6ca | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | abd6c29c-c24a-5610-a598-58601ee3f824 | VERIFYING DOCUMENTS: This ITP
| textbox | 0ebd1570-7b9e-5270-ab74-299ff4bcabf7 | Date Completed:
| checkpoint |  | 6.7 Early Age Compressive Strength Results - Early Loading and Trafficking of Decks and Approach Slabs
| note | 2b03442f-3ec6-5ab8-8178-540d5cb3f460 | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure, 610.36
| note | 8cdc218c-c2e8-5a6b-b54d-7e586d88dfb6 | ACCEPTANCE CRITERIA: Minimum compressive strength requirement of 32MPa.
| note | 02a4c84d-609d-59c0-9523-4ca0e0cc9fcc | Minimum duration before plant and equipment may access = 3 1/2 days.
| note | 7631c18e-aead-5dcf-a34a-db3576d62b60 | Minimum duration before traffic open or element loaded = 4 days.
| note | 595d396d-c9f0-566d-9b53-16c703b806c1 | Attach: Concrete Test Results or Maturity Test Results
| note | a0a4ee62-3af6-59a6-a36d-654069828881 | METHOD: Document Review, Visual
| note | 07ffd956-75b8-5977-8da1-51d66d150ab6 | FREQUENCY: Where applicable, each superstructure element
| note | d0e53ee5-541a-5c33-8da0-4538f0096f15 | CATEGORY: HP
| note | 7efee2ec-f168-5962-9529-da8b6c7c0f8c | RESPONSIBILITY: Nominated Authority
| note | 28ab6997-d1f7-5ff5-9792-3c151d57e3f8 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 881ee687-c797-560f-8c8a-dbd00c278540 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.8 Compressive Strength Test Results
| note | ef78adb0-40b5-5777-8d4b-f374732f1289 | REFERENCE: IFC Drawings, Table 610.05.051, 610.16 (g)
| note | 1e801315-d911-5a8c-88c6-310d3032ec03 | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
| note | d147f6d0-bfc3-5d21-848c-291b5f8d16be | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
| note | 3f7091bd-beb1-51a9-96dd-db497c4eafc1 | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
| note | 86dc321c-1266-582d-b4e5-54f07d483d1d | Attach: Compressive Strength Test Results
| note | b384b51f-57c9-51f4-b54e-829929f5c3ec | METHOD: Document Review
| note | e8e3fd20-5870-5a7d-a031-9d02b7fa22a6 | FREQUENCY: Each cylinder
| note | f1db15cb-b19c-5ab1-a84c-4887ba0ddff6 | CATEGORY: IP
| note | 76136e02-6ab1-57bf-82cb-465f29b45cdb | RESPONSIBILITY: SE/PE/SPE
| note | 4fe9d1bc-5370-50d2-bd14-5af4a618fe70 | VERIFYING DOCUMENTS: This ITP
| textbox | fa1bb77f-6645-5b75-a81b-64843a31d207 | Date Completed:
| checkpoint |  | 6.9 As-built Survey
| note | e4ad722f-2d6a-5192-bbbf-844599bf9955 | REFERENCE: IFC Drawings, 610.47, Table 610.472
| note | 401f53da-7a11-5a39-bf26-bb874dc08938 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
| note | 4c427359-d841-5c7b-84fc-a81eb1003585 | Attach: Survey As-builts / Survey Report
| note | ea3f7491-98e5-5257-bb55-445ab1e327bd | METHOD: Document Review
| note | bb21eb56-b9e3-570e-a99c-f4255715ffa9 | FREQUENCY: Each element
| note | eedfb6da-caa5-586f-9096-c51dc0ff7737 | CATEGORY: IP
| note | dd43c740-7a05-5bb4-b58d-781905e074e6 | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | be88abf9-34d7-5c9c-adc6-a17bf610879f | VERIFYING DOCUMENTS: This ITP
| textbox | 1189029f-43e4-50ff-a31a-a3d818a7814d | Date Completed:
| checkpoint |  | 6.10 Non-conformance Report (NCR) Closure
| note | 518b46e8-8653-53c9-805d-197e5602c859 | REFERENCE: MRPA Quality Management Plan
| note | 10bad0ba-1d14-5a26-ae3d-06ad38d36b3d | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 9a3dc134-04da-5d0b-872d-6eac0d61916e | METHOD: Document Review
| note | df5c05e9-1552-517d-9af4-7ec3b7f62304 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 09d4b7f4-e5d1-549d-9c8b-c4764463ece1 | CATEGORY: HP*
| note | 02c964a2-1e9a-5ae1-866d-be48f78a20ff | RESPONSIBILITY: SE/PE/SPE
| note | 19fb8275-f8f8-5195-a413-3a6176dafb46 | VERIFYING DOCUMENTS: This ITP
| textbox | 80583f97-4b84-56a2-b72f-e9428455659b | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | dabc7d55-447e-5fda-9330-12c72bcc9d1e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 84be6865-dbd1-58b2-bcf8-e9a76fa70f46 | Name:
| textbox | 2aece164-b5d3-55a5-83be-2a20c72e429a | Position:
| textbox | 25335f4b-a02f-5124-ad2c-80632627e3f6 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Waterproofing Tanking Slab Rev1 |  | ITP-STR-Waterproofing Tanking Slab Rev1 | 6bd51015-1e7c-4827-b269-fa355aa76d67
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 4f06625e-628a-56eb-b2bc-2d932801c968 | Document Title: ITP-STR-Waterproofing Tanking Slab
| note | 4f91fe4c-9a0a-5487-8880-d7a1f1c57e41 | ITP Description: Waterproofing Tanking Slab
| note | fec70608-aae6-5241-862e-5d05a32567f7 | Discipline (e.g. CIV/STR/RAIL: STR
| note | e7af9c10-fc85-5cfd-be2e-4de3de7c9044 | Revision Number: 1
| note | bdb9c541-b6d4-5834-85c1-89f05d50d857 | Revision Date: 26/05/2022
| note | 225d5e94-64af-5d7e-b2f0-fa1441ac5b0b | ITP created by: Furqon Edwars
| note | 27bb0b04-7590-59cd-9824-6288ac51a1e7 | ITP approved for use by: Pradeep Talasila
| note | 26b3ad1b-f063-5426-893f-6ddbeb295eec | 1.1 - Reference - VR 691 Nov 2018
| note | d870ee68-3546-551a-a5d5-0683f050491d | 1.2 - Reference - IFC Drawings, MRP-DPK-016-00-CSW-0017-0
| section |  | Preliminaries
| checkpoint |  | 2.1 - Materials Waterproofing systems shall be used in accordance with the manufacturer’s recommendations and materials safety data sheets.
| note | 6c20ecdd-6886-5991-995d-bcedd3835cb1 | Reference - Normnet
| note | cf1980ae-06c6-53bb-a5fd-af6d309c5362 | Acceptance Criteria - Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent.
| note | 8ae0ecf1-2627-5f8e-bf4e-d141b14e0241 | Method - Document Review
| note | 8a5519c5-b992-5ac5-b21e-08c8b74c74df | Frequency - Once prior of commencement of work
| note | 319bcbd3-f3cc-577d-a132-02424d323023 | Category - HP
| note | 77684105-ca5d-5799-8706-049579e87e21 | Responsibility - SE/PE
| note | 5c3a011e-d788-527d-953f-1fc25fbf4e85 | Nominated Authority
| note | bdd23183-d632-5fdb-b3fa-aa65550901b3 | Verifying Documents - Material and Surface Procedures
| note | c2171cb5-d285-5472-aba7-e888a44952dd | ConQA Hold Point Release
| textbox | 1f519493-a93e-52c6-9d7f-100350973ca8 | Date Completed:
| signoff |  | HOLDPOINT
| checkpoint |  | 2.2 - Work Method Statement and Inspection Test Plans
| note | 8d306f41-789c-51d6-9549-17a414664d43 | Reference - IFC Drawings
| note | 1217d4ba-5300-54d6-8097-21d37a1d078b | MRP-DPK-016-00-CSW-0017-0
| note | 5f188daf-8e2b-5508-b70f-7b688ebc632e | Acceptance Criteria - The Contractor shall not proceed with the trial system application or the permanent waterproofing membrane system installation works until the WMS and ITPs have been reviewed and approved by the Superintendent.
| note | 68aa063c-01ab-5ccb-aec2-9d9d856409f5 | Method - Document Review
| note | 915f39ff-188c-5872-bfae-68350124265d | Frequency - Once prior of commencement of work
| note | 5c4ce931-cb04-5512-b10e-740c230197b2 | Category - HP
| note | a556d43f-bdcd-532d-9223-b86e84a3ef34 | Responsibility - SE/PE
| note | 08e88a3c-a3d0-5df2-b723-d3b521d130aa | Nominated Authority
| note | 3e98db6d-8e90-50c6-a846-126c6cfd49cf | Verifying Documents - WMS
| note | ed3e3b43-4caf-56f6-b6d7-fbf762d35a0a | Subcontractor ITP
| textbox | 9671f31f-8a51-5e17-89d4-d187247dee5e | Date Completed:
| signoff |  | HOLDPOINT
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 - IFC Drawings
| note | 22eb7f94-191d-5cf3-a068-84f6d10ce105 | Reference - MRPA Quality Management Plan
| note | 4dc9d7d6-0c7b-521b-bf08-4f3eee6d9640 | Acceptance Criteria - Check the revision of the IFC Drawing are current as per the drawing register (on Teambinder)
| note | 61d0b5ac-d621-5c15-99ef-f49f01cf9552 | Method - Document Review
| note | 00a0de3e-5be8-5992-a071-c634adb12510 | Frequency - Prior to starting work
| note | cfdbc70e-32d7-5c9b-9375-17b787f123d1 | Category - HP*
| note | 5b135bd1-b23c-5819-b6db-672df3188037 | Responsibility - All
| note | 69066a6e-f223-5b85-a046-bcc4d5a2e6f7 | Verifying Documents - This ITP
| textbox | 885f7daa-c323-5c75-bd9f-03ca77e7fe54 | Date Completed:
| checkpoint |  | 3.2 - Survey Set out
| note | 82e3b335-b324-573f-a053-d10cf61fc528 | Reference - Work Method Statement
| note | 358ae84a-54c5-5c3f-9e13-b1abb8f6bb89 | Acceptance Criteria - Survey set out and mark out area for waterproofing prior to commencement of works
| note | 2b83281e-4cb9-5127-bd4d-04248cc7592c | Method - Visual Survey
| note | 92dfc9f0-f235-5b46-bb6e-d053111b90bd | Frequency - Once Per Lot
| note | 7d3ce45e-450f-5d1c-8df9-9fda10dbc4ee | Category - WP
| note | 8c1bebcd-32a2-5159-b57f-995f9be295d7 | Responsibility - SE/PE
| note | 5ea7df64-e329-5973-a9e7-78e05b68ed20 | Survey
| note | 9b63c549-a217-5123-a8b1-bdd96bfbf498 | Verifying Documents - This ITP
| textbox | 85f3d4d7-2234-5616-b27d-18a1a117152e | Date Completed:
| checkpoint |  | 3.3 - Surface Preparation
| note | a4dab500-9136-55c6-9a97-863d132a8b67 | Reference - Normnet
| note | d03eb57b-ae64-5d35-b728-595aa8a00236 | Acceptance Criteria - Concrete Surface Preparation
| note | 3ab14e55-f639-5b74-b089-0bc637ba761f | Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles.
| note | aff8099c-11c8-5ba1-9d1e-f435f75488e5 | Method - Inspection
| note | c7b62991-71f8-5000-a6a3-792ea1b76ac0 | Frequency - Once Per Lot
| note | 637b2a70-4670-5d07-b55a-19f841276dbb | Category - HP
| note | 3b5ebfad-59e9-5741-a852-548936ac819d | Responsibility - SE/PE
| note | 121f0fde-d24d-5148-b4d3-267977ecb7fc | Normnet representative
| note | 88ca8423-03c8-5e3e-9a96-1e4908adf77a | Verifying Documents - Subcontractor/ EPTEC ITP
| textbox | 8cb0e622-6df4-599a-afdd-bdcec7fac61c | Date Completed:
| signoff |  | HOLDPOINT
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 - Waterproofing Application
| note | b99444b6-f8a7-54eb-9e2a-6826497e5bc7 | Reference - Normnet
| note | 447b49bd-77e7-5b78-99e7-ae2435ff3f56 | Acceptance Criteria - All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application. Sufficient drying time shall be allowed after wet preparation.
| note | 22f215f6-220f-5855-a7b5-b6542f30692f | Air shall not be allowed to be trapped at the concrete/primer/membrane interfaces.
| note | 21366c72-d79b-5ca8-bb65-9d5f8b70a814 | Method - Inspection
| note | c74b63b6-2076-5c1c-bc58-00896209137d | Frequency - Once Per Lot
| note | b670766e-0483-5c29-8d76-98b86e4ac94a | Category - WP
| note | f131d9a1-1578-5c1b-98ac-80ae128e893d | Responsibility - SE/PE
| note | bdb86c31-1641-5823-bcf0-21f86dafbb8c | Verifying Documents - Subcontractor/ EPTEC ITP
| textbox | 4d158a6a-7b6c-5e7a-8582-6917bd9ed367 | Date Completed:
| checkpoint |  | 4.2 - Final Inspection of installed membrane system including all accessories
| note | 2d2c3f73-f439-5e70-80a0-946c6a01e112 | Reference - Work Method Statement
| note | 17833873-7be1-5d0b-af49-5fe272864fed | Acceptance Criteria - No visual damage to the installed membrane system
| note | 5eea334f-cfaa-5bf7-b13b-2a0f7b2d0ee7 | Method - Inspection
| note | d430c6d3-28c2-554f-9215-4b2dffe4a18c | Frequency - Once per Lot
| note | 139cb9fa-80fe-51e2-832a-418b9a8791a3 | Category - WP
| note | 82d0a103-8977-53a4-acea-25f605bffa2a | Responsibility - SE/PE Nominated Authority
| note | c0c04589-d97c-574c-a82d-9b3e4146a8f9 | Verifying Documents - This ITP
| textbox | 2df64149-4b02-5539-ae8d-7b4737363b44 | Date Completed:
| checkpoint |  | 4.3 - Patch Repair for membrane (if required)
| note | ca7829ca-fff7-5108-adb4-298c36dd25e4 | Reference - Work Method Statement
| note | 3b4b9b84-03e2-5858-846a-3d07f7ec73ca | Acceptance Criteria - Round out hole
| note | 6a0b69d2-c9ab-5868-9d64-589714243c42 | Cut a sufficient sized "patch" from membrane ensuring size for overlapping the edges of the damage by 100mm
| note | f12278f3-4ced-5a57-b33a-df009890133f | Method - Inspection
| note | 86a63528-30f0-5e7c-aebe-467247045c90 | Frequency - Where needed
| note | f647b867-394f-5c9b-889a-cbcfbb4fe0d1 | Category - WP
| note | 76cb7f36-9865-5d7f-a59b-a7d215b0ab5d | Responsibility - SE/PE
| note | 93725ef7-0128-5a06-a941-7bb56eaf49b0 | Nominated Authority
| note | d38a256e-8ac4-568f-940d-80938029e497 | Verifying Documents - This ITP
| textbox | e4394095-17fd-5674-8649-8bd91d0aa9f5 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 - Copy of Subcontractor ITP/Checklist
| note | 24b411c0-0753-54a2-9cd2-61997b620110 | Reference - Subcontractor ITP
| note | 09976637-ed75-585c-8c01-403228ff0a9e | Acceptance Criteria - Attachment of Subcontractor ITP/Checklist
| note | 0626a33c-e16e-50c6-9bca-9222c7273a85 | Method - Document Review
| note | e426ffc2-0461-5e56-9921-9499f8fba0ec | Frequency - Once per Lot
| note | 75746440-d9ac-56b5-b984-18513ffe3d07 | Category - WP
| note | 02727a71-4abf-5fbe-a294-5f0c114cf4f1 | Responsibility - SE/PE
| note | 22e5eae5-6449-5eac-bf44-0062e77c9e48 | Verifying Documents - Contractor's ITP/Checklist
| textbox | ae9465e4-f7a9-5a02-8460-9a4e26dd1741 | Date Completed:
| checkpoint |  | 5.2 - Subcontractor Product warranties obtained
| note | 68f9c5a7-3ef8-5b6a-afe8-76fc1704ce68 | Reference - Work Method Statement
| note | e30ee9b4-59c1-5068-aebd-97c1eb816ebc | IFC Drawings
| note | 302bc14a-2104-5ec5-b582-1e2642faa5ed | Acceptance Criteria - Product warranties obtained and are compliant with the what is specified in IFC Drawings
| note | bf0a4756-978f-58e5-b78b-d34c1b07d2d6 | Method - Inspection
| note | 65f0f626-5dde-5c66-999f-7067eac6c7a0 | Document Review
| note | 28aeed05-7752-52f6-b861-3040e85a15a5 | Frequency - Once per Lot
| note | bede0c6f-18ba-5309-879a-302c743c9cea | Category - WP
| note | 3fb25b6a-e33b-5e9b-bb8c-343aaf861aa3 | Responsibility - SE/PE
| note | 989ae52d-fcbc-5edc-a941-2daef4b50396 | Verifying Documents - Copies of product warranties
| textbox | 4c6db770-46ab-50cf-b5e8-727c6d062058 | Date Completed:
| checkpoint |  | 5.3 - Relevant RFI's
| note | 0a1adf71-b7bf-52da-bdcb-bc8535637170 | Reference - MRPA Quality Management Plan
| note | b6358d30-8352-5b1a-b2d0-bd17721a9245 | Acceptance Criteria - Design/Construction Queries or clarifications relating to this ITP
| note | c40e8fc6-e4d0-5803-b134-06dff42d8aa9 | Method - RFIs closed out and linked NCRs where applicable
| note | a230c3ae-956b-57e2-8a8a-f17237dc6aee | Frequency - Once per Lot
| note | b9c9a52f-adeb-5fc2-8398-4086dc6d111c | Category - WP
| note | 7ddc6053-bdc6-50a4-9ff3-7781b10c5b32 | Responsibility - SE/PE
| note | 59b55308-7926-55ec-a36f-f65a839462d2 | Verifying Documents - RFI's and NCRS linked to this ITP
| textbox | ec0f0ace-a5b5-5a44-aac4-4e8cf985d213 | Date Completed:
| checkpoint |  | 5.4 - Close Out NCR(s)
| note | 13d2c7d8-070d-568d-a855-bce9428c0bd9 | Reference - MRPA Quality Management Plan
| note | b0f9dae5-c842-5994-87a5-d6e183b0808c | Acceptance Criteria - All out of tolerances notified via NCRs reporting system.
| note | a3d9b5f6-1ee0-5a79-8122-a2facf2da8cf | Method - Prior to closing and signing ITP
| note | 551aaef3-6ac1-54be-a114-cc7ccb888837 | Frequency - Once Per Lot
| note | 479c0aa1-cf79-54c4-aee3-99d98f41a6b1 | Category - HP*
| note | d8efe73f-558e-5faf-a1be-9541e904bf37 | Responsibility - PE
| note | 83bdf4fc-8831-5200-96e5-d28a6d222ebb | Verifying Documents - NCR(s) relevant to ITP
| textbox | 27da1d07-e0b4-54b8-b367-8fb4f4ee8dcd | Date Completed:
| checkpoint |  | Final Inspection
| note | 8e039097-ca9a-5a50-b551-07ce81bcd149 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| note | 45beb03b-65aa-500a-88fb-3c09354553cd | Print Name:
| note | 1df79d9e-8044-528f-9246-c595c18fed83 | Position:
| note | eb4332da-f744-5438-a1a3-1577f1a009c2 | Date Completed:
| checklist |  | ITP-CIV-Ground Improvement (Supply and Install) Rev 4 | itp | ITP-CIV-Ground Improvement (Supply and Install) Rev 4 | 6dfea71b-645d-45c1-b0c2-081332448c16
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 62df7d77-0656-4d7d-a86f-fb46aeab20f7 | Document Title: ITP-CIV-Ground Improvement (Supply and Install)
| note | 05ac05e2-a432-46f4-bcaf-98c4ec8d4fd5 | ITP Description: Ground Improvement (Supply and Install)
| note | cbb7dd07-876a-486c-9c07-5894709ac744 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | f9820d50-fc7d-40e4-a33c-59a2428ba948 | Revision Number: 4
| note | 98410496-1085-49b9-88e9-426c9ece3b41 | Revision Date: 16/06/21
| note | baa84ef9-136e-4bcf-8041-6b4de5753937 | ITP created by: Matthew Dib
| note | 9af2e30a-7f66-4454-991f-c1dd97269816 | ITP approved for use by: Aldrin Guinchoma
| note | b862eed6-5eff-4ab1-9b55-963461b25f98 | 1.1 VicRoads Section 204 (Dec 2015)
| note | 50142254-7303-4639-88a7-7c2181f0ed29 | 1.2 IFC Report and Drawings
| section |  | Preliminaries
| checkpoint |  | 2.1 Material Approval
| note | 60835a58-0086-4b60-a1b2-15f4742ccf18 | REFERENCE: Section 204.04
| note | fca68985-5159-4784-b214-260a6b7ec966 | Table 204.141
| note | 1160d355-d74a-461e-b667-6adbc076f864 | IFC drawings
| note | 5747dca2-ace1-4551-b786-932ebb06618f | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
| note | 93199a19-1891-456f-bc1a-7d5a7b1f419a | Scale B
| note | 51a8df68-51ce-4945-8eb5-15b5e68f68a9 | CBR ≥ 6%
| note | ff07f4d9-9a76-4c53-a3f5-6809367c0023 | Swell ≤ 1.5%
| note | 3547b024-fec1-413d-aaa4-2fb75e522301 | Permeability > 10-7m/s to allow consolidation (where <10-7 m/s, drainage layer or geonet to be provided)
| note | fc075937-45d1-451a-828b-2c95507a53c9 | PI (LL) = 6 - 25
| note | e5498a10-4170-4c49-9194-5ccb0e99f33a | Effective Friction Angle = 34*
| note | 6424ac11-8fb3-4ac3-b3dc-72c5293e2984 | Effective Cohesion = 2kPa
| note | cd89d6d8-eeeb-43a1-960a-d4248d027202 | Unit weight =24kN/m3
| note | bf60533d-4fd1-4ccf-ad3e-07ad72c0909c | Undrained Cohesion = 75kPa
| note | ec2c2bc1-e310-4633-8987-657c26496273 | Grading:
| note | bd3a7668-d7c5-40b8-a311-c6009be12943 | % passing 75.0mm sieve = 100
| note | e6a86929-0386-4edf-882d-c1127bcda77b | % passing 4.75mm sieve = 40 - 80
| note | a6dee150-1b50-42b5-9a3f-4f85f08ca032 | % passing 0.075mm = 10 - 40
| textbox | 9f5e52a2-327e-49f5-8f75-c487d61e7645 | Enter: Teambinder Material Approval number
| note | 187635d4-279a-4270-87b9-15a0b22c5429 | METHOD: Review and Verify
| note | 740571f9-e448-4a1f-8223-777b5f0d3d58 | FREQUENCY: Once per material type prior to commence of works
| note | 17aece82-fc2f-4f2f-ae9f-0946973c6605 | CATEGORY: HP
| note | 897ec0ce-bb96-4bd9-a42a-59eaaddc40e0 | RESPONSIBILITY: Nominated Authority
| note | eaebb05e-670f-41a4-9fd0-ac892608366a | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b262d5c1-1865-489f-9f83-11c5e47fa261 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | 1f227b1f-66a5-4bb7-9956-bc3eadddb106 | REFERENCE: Section 204.03
| note | a91d73c2-8923-4b94-9ccc-9e5b8fb3e104 | IFC drawings
| note | 9bd82d66-1eec-4f93-9e7d-3c52ae67f8a1 | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
| note | 55ff23c3-7f2b-428c-a63c-e21c3e4a16b1 | METHOD: Measure , Visual
| note | 06987840-26f7-4748-aa0e-afcac223a8ed | FREQUENCY: Each element
| note | 3d08347e-599a-4012-adbe-5f102e931cfc | CATEGORY: IP
| note | c605fb79-76c2-4b30-8892-0377a6413aa2 | RESPONSIBILITY: SE/Site Supervisor
| note | 7b33ecb9-7e4c-4754-b47f-ef1b69f2d770 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 8a081141-b8e5-4aff-af02-3e5bb5bf1436 | Date Completed:
| section |  | Cut Activities
| checkpoint |  | 4.1 Subgrade Level
| note | 58b6f943-e1a2-49d3-8b04-f06b450d16c6 | REFERENCE: Section 204.03 (g)
| note | 130926e0-23fc-4100-afe2-fe29fb5e200f | Section 204.03 (h)
| note | ca07b53e-a8f9-4b73-ae00-18879cd52106 | IFC drawings
| note | 22f997d0-e05e-438c-8326-2e5b11ba8053 | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the relevant Ground Improvement drawings within the following limits:
| note | 6a99ca42-fd36-4eff-972a-3f07a9c8713e | Mean value range: +5 to -25mm and a standard deviation of 15mm over a minimum 40 measurements per lot
| note | fda4bc66-1c3f-4738-aea2-21e8eed75367 | METHOD: Measure
| note | 0d67baa0-af24-47fb-904b-c2f13505eb09 | FREQUENCY: Each lot
| note | cb5363a5-0b35-4f8f-8d5f-21c33a3e9282 | CATEGORY: IP
| note | a7524157-7866-4f7f-a65c-1af420649820 | RESPONSIBILITY: Surveyor/SE/Site Supervisor
| note | de1825d3-84d1-4542-a44e-75e077892236 | VERIFYING DOCUMENTS: Sign ITP , Survey Pick Up Report
| textbox | 53f3a29d-e97d-45f2-9793-0cbc63331ad2 | Date Completed:
| checkpoint |  | 4.2 Founding Material Inspection
| note | c9baa15c-529c-4bdd-a9c3-db5a4cec39bd | REFERENCE: IFC Report and Drawings
| note | ada68aa4-71ad-4405-a07c-8132501a55c3 | ACCEPTANCE CRITERIA: Geotechnical Engineer shall inspect founding material.
| note | f86777b3-6efc-4778-826b-7dfb83cd5620 | Any areas beneath footing footprint where foundation soil is not stiff clay or better will require ground improvement
| note | 05abe49b-8a13-4d7d-ae9d-68b1c1c164f5 | Attach: Geotechnical Field Sheet or Report
| note | 7e520455-6600-4326-a4a6-f8c696106bc2 | METHOD: Verify , Document
| note | 82fb4891-ffa9-4a6b-b3b1-6943190f57f5 | FREQUENCY: Each lot
| note | d402d174-1510-4223-8c81-51051c3c63fa | CATEGORY: HP
| note | e12e7a61-7f5e-44bf-b37a-736fc82b0b9c | RESPONSIBILITY: Geotech Engineer/SE/Site Supervisor
| note | 563ca114-f5b3-4676-a21b-81d22a54ac66 | VERIFYING DOCUMENTS: ConQA Hold Point Release , Geotech Report
| textbox | 795f6c5b-8392-4b33-9d7c-b409fbdfa738 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.3 Proof Roll
| note | 04f3b12d-5445-4f95-8e2a-9cf43f921139 | REFERENCE: Section 204.10 (b)
| note | bbb93817-e6df-45d0-ad74-5700c9fefcb5 | Section 204.12
| note | 9444abde-809e-4d9f-870a-0cecc31f646c | IFC drawings
| note | e95ab269-4965-40ed-8a3a-304b47d6d4d5 | ACCEPTANCE CRITERIA: Excavated subgrade to be compacted and proof rolled before any construction.
| note | 9d7d8d2e-cd27-45e5-9f61-f02f67a8c240 | Withstands Test rolling without visible deformation or springing.
| note | 81f6e5ee-8279-452b-a1be-6eee2e938ca5 | No fill to be placed until the area has been reviewed and approved.
| note | f3af8457-6542-4e43-8f2e-5506ebf86eed | METHOD: Visual
| note | ab0a9a84-60f3-4f97-b39d-535167fb873f | FREQUENCY: Each lot
| note | 0f4d0a6b-701c-4f74-9604-6193fbe91e7b | CATEGORY: HP
| note | e6abf245-a6dd-4b6a-ba2e-fa5e9d3cc2e5 | RESPONSIBILITY: Nominated Authority
| note | 5497c472-479c-4275-9bac-7c696b2c12dd | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 4c4ba11a-3b7a-4e25-83eb-4459456ec367 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Fill Activities
| checkpoint |  | 5.1 Structural Fill Placement
| note | 6eed8572-9543-4409-933d-817bc9b3ee4c | REFERENCE: Section 204.10 (d) (ii)
| note | 46f27121-b579-46ee-92f8-e4701cdc3c35 | IFC Report and Drawings
| note | 876f8ef8-b949-46c8-90d3-a5bc0d10da33 | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness.
| note | ed77aac0-7793-4be5-98e3-9de1dc5efbc4 | Extent of fill placement to be as per IFC Report and Drawings
| note | cad1bb39-0467-46c3-97cb-9038365313b0 | METHOD: Visual
| note | 0861f518-fdde-412a-b931-d092ce5cfbf8 | FREQUENCY: Each lot
| note | ad6c273c-f1ff-40a9-b409-dfd7e46f4536 | CATEGORY: IP
| note | 4945a187-304c-4476-8526-99a2ba5958e2 | RESPONSIBILITY: SE/Site Supervisor
| note | 90238b6a-6925-4d6d-9496-da3cd1b65a0a | VERIFYING DOCUMENTS: Sign ITP
| textbox | 525a112b-9216-42fd-9ba3-f962a457765b | Date Completed:
| checkpoint |  | 5.2 Keying of Layers
| note | 558d9d0a-8f19-461d-8edf-ed064d55d9a4 | REFERENCE: Section 204.10(d)(i)
| note | 0c90afb0-d31f-40fa-99d3-8a8c421f71ae | ACCEPTANCE CRITERIA: Each layer of fill shall be keyed into the layer above by creation of a textured surface.
| note | 2859601f-02dc-401d-8a8b-241a65d2e069 | METHOD: Visual
| note | c4e52069-5e37-47e3-91ce-8d418a9f0269 | FREQUENCY: Each lot
| note | 161aeaf2-7f86-4809-86c6-76bc6b5c3da2 | CATEGORY: IP
| note | b885d0ec-80d7-4bfc-a2c8-dc59c7c70040 | RESPONSIBILITY: SE/Site Supervisor
| note | bca99555-8254-49e9-9d57-32202056a3e3 | VERIFYING DOCUMENTS: Sign ITP
| textbox | a9e3afcc-c8a1-4042-a713-4b0ebabc22c3 | Date Completed:
| checkpoint |  | 5.3 Proof Roll
| note | c1899754-0ad8-4961-bffd-1ef171ed6828 | REFERENCE: Section 204.13 (b) (i)
| note | 293e7f08-4157-45e8-a78f-483f0fa59b85 | Section 204.12
| note | 69a118e5-8fcf-4478-8c60-1a2a1ef819cc | ACCEPTANCE CRITERIA: Withstands Test rolling without visible deformation or springing.
| note | 402283ce-5936-4111-bb60-ef441cf473c3 | No fill to be placed until the area has been reviewed and approved.
| note | d385e6cb-7440-4a48-9d9e-d5a94a37c3e2 | METHOD: Visual
| note | 9723e4bb-7aaa-44ab-91d8-955ee24873a9 | FREQUENCY: Each lot
| note | ccbbb1bb-ae7c-473d-85f2-b1d9462f7ad0 | CATEGORY: HP
| note | e81e68f9-f456-4f43-9e72-4d1b42caea78 | RESPONSIBILITY: Nominated Authority
| note | 27e01ed9-784c-4ecf-946a-bde1d2f19c97 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | d6bc4fb8-8689-4a5e-b927-cc0d8b239957 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4 Compaction Testing
| note | 0a2e0343-0e96-440d-8ff8-8c5d14a9d4ff | REFERENCE: Table 204.131
| note | 97dc4e19-cea0-4458-9d63-8b43f51aef05 | Section 204.13, 204.14
| note | 67181712-d9d6-4782-91b5-27afba789b18 | ACCEPTANCE CRITERIA: Frequency = 6 tests per lot
| note | b2b249d2-a435-429d-9b5b-7ae349bb9e44 | Lot = One day's production or 5,000m2, whichever is the lesser
| note | 7df4d9ac-c320-466f-81f7-f9a88d7478b6 | Characteristic Density Ratio = 98% minimum
| note | c62a1124-4fe4-40f7-b5f1-fd8c25888648 | METHOD: Document Review
| note | 82de2977-f386-4ec8-960c-8e49c97c7f04 | FREQUENCY: Initially test every lot until three consecutive achieve passing results. , Min. every 2nd lot of like material and work
| note | 4f20e559-2f7c-4160-9f0b-48954e5f7757 | CATEGORY: IP
| note | 221c3013-ef23-4b14-84e5-7ba2d5ae7df8 | RESPONSIBILITY: SE
| note | 542112a6-df01-4b14-89d7-e5dcb587ba19 | VERIFYING DOCUMENTS: Sign ITP , Compaction Test Report
| textbox | 9cb9a86d-7a8e-4424-924c-f4b8cfbc1f72 | Date Completed:
| checkpoint |  | 5.5 Material Property Testing
| note | 8994099e-1cfd-42de-940c-7936dbdce9d2 | REFERENCE: Table 204.041
| note | 91bf85ba-c9c3-432f-9482-0ac8d95c370c | RC 500.2
| note | ad798fdc-0748-408c-b29b-f70d6f408a1d | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
| note | cdf587ad-a3d7-430f-9b98-747a33168b7e | Scale B
| note | b8ce4891-cb24-405c-b701-57d35de0b65a | CBR ≥ 6%
| note | deecac0f-c591-4871-b90a-4c287730e53a | Swell ≤ 1.5%
| note | a05c8b61-bc9a-49e1-9ce2-07f3d540eb43 | Permeability > 10-7m/s to allow consolidation (where <10-7 m/s, drainage layer or geonet to be provided)
| note | 7a129266-30a2-4caf-9c4e-cc446beb0413 | PI (LL) = 6 - 25
| note | 256756a8-ad84-4701-b43c-5a14894ed9ce | Effective Friction Angle = 34*
| note | d9890467-c4e0-427b-b8d8-2a35ef5f7456 | Effective Cohesion = 2kPa
| note | cf795b6e-27a8-47d7-8399-19a4bbfddee2 | Unit weight =24kN/m3
| note | 459272b3-b149-40f9-a314-8343dc907fc4 | Undrained Cohesion = 75kPa
| note | abd56bf8-6557-463a-a91e-977b76d5a288 | Grading:
| note | 76dca418-65d7-4810-827d-09a66b149fe3 | % passing 75.0mm sieve = 100
| note | 5faa317d-e4dc-4011-923d-f1c8d4ee8641 | % passing 4.75mm sieve = 40 - 80
| note | 44db2297-3958-42f2-a404-ff5b4ea80f90 | % passing 0.075mm = 10 - 40
| note | 88e67313-04f0-430f-ad24-6366ff0a28c1 | METHOD: Document Review
| note | 39f3b9b1-168a-4389-a489-71c9c17cc4e7 | FREQUENCY: The first lot
| note | 88de91c1-55c7-4a95-b902-9e9c448a2a30 | CATEGORY: IP
| note | d0c5bdf9-c986-423b-bf4c-af5965d2255f | RESPONSIBILITY: SE
| note | 401d8385-c002-4729-8ce8-b986acb49894 | VERIFYING DOCUMENTS: Sign ITP , Material Test Report
| textbox | 72012c74-53df-4446-9afe-87c8d0aaf04a | Date Completed:
| checkpoint |  | 5.6 Preparation of final surface
| note | d4dd3e6f-0847-41e1-9efe-bfc1085ba929 | REFERENCE: Section 204.15
| note | 8278bf2e-2828-498f-a865-4adc5093fa3e | ACCEPTANCE CRITERIA: The top of the subgrade surface shall be prepared to level and shape to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
| note | 2c228e57-f91c-4740-b856-888c7a3dcbac | METHOD: Visual
| note | b3894cea-b917-4465-835e-7164c9195498 | FREQUENCY: Top layer
| note | ea04f2c9-f498-42ee-944f-9f7d33c3b381 | CATEGORY: IP
| note | e75317e5-ca03-4902-9ebc-38b683ae52f0 | RESPONSIBILITY: SE/Site Supervisor
| note | 7c961c1e-41aa-42c1-82bd-5b1fdcb10c58 | VERIFYING DOCUMENTS: Sign ITP
| textbox | ceee12b5-14fe-4ae5-bb2f-d6895517f823 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 6.1 As-built Survey
| note | e4a89a5d-6aae-4760-8bfa-da73ec43dac3 | REFERENCE: Section 204.03 (h), 204.16
| note | 9703d25e-2dcb-408a-90dc-48d0b85190f0 | ACCEPTANCE CRITERIA: Scale B:
| note | fc746776-59fb-47c7-b0ad-90973f9645db | Min. No. of Measurements Per Lot: 40
| note | a413e77d-56e4-42d5-bd96-901a6409ffea | Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
| note | 2abf0c92-f29f-45c2-ac94-1631c1ffe183 | METHOD: Document Review
| note | a90fa0b8-4170-40d7-b85b-e149ae25cde4 | FREQUENCY: Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
| note | 1c4045e0-50ce-4954-8bed-0d4223e542d2 | CATEGORY: IP
| note | 34d27cca-3d66-40b1-b69c-de1f5fb2066c | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 35f376f7-0a24-4d50-ba50-37d0a876618b | VERIFYING DOCUMENTS: This ITP , Survey Conformance Report
| textbox | 1bc3945a-cfa0-4785-9616-47c44fe2f752 | Date Completed:
| checkpoint |  | 6.2 Non-conformance Report (NCR) Closure
| note | a7a078f4-d46a-4f95-b7b7-28f8bec5b6a4 | REFERENCE: MRPA Quality Management Plan
| note | 89d85832-2429-4595-870e-e58a7840e90d | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | cd4944f1-6352-44ae-8aab-4d38372266b0 | METHOD: Document Review
| note | 7f9585d1-45a9-4682-8473-357dcc152653 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 85551760-8804-4c79-82e2-6074905ac0eb | CATEGORY: HP*
| note | ff80fc59-358d-4bf5-8e25-b9a32d0bebad | RESPONSIBILITY: SE/PE/SPE
| note | 9b0a5a61-138a-467f-8e97-a4c1c4d0ddae | VERIFYING DOCUMENTS: This ITP
| textbox | 9e5fa6c4-92cd-4f2d-b570-3069f3998f86 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | e07d6551-3871-41ac-82f3-2b46f6ab3a09 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 2f9030f8-0409-4ac0-b2f2-cc89cd32bb21 | Name:
| textbox | 73fa1035-c7aa-4b9a-bc85-ee2880a7ca57 | Position:
| textbox | 3717ef43-c758-42a0-99ba-00864671e268 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | itp | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | 76631fbf-1351-4fe8-a3bb-e5bf108425f3
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | adae9d4d-b67e-4c8c-aaaa-ca344a1cd214 | Document Title: ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3
| note | 1d36f9ac-c9e7-4e17-aaeb-017851de1a0b | ITP Description: Structural Steel Barrier Rail (Supply & Installation)
| note | 792bf003-8c59-4d58-9178-795580743704 | Discipline (e.g. CIV/STR/RAIL): STR
| note | 5c6256de-ad4f-49d2-8146-fb0565543594 | Revision Number: 3
| note | 4d780a5f-9ea4-4460-b3ca-6b6a9768570b | Revision Date: 4/05/21
| note | 65f36246-429d-45a5-ac16-f2cbef85a2db | ITP created by: Mike Freeman
| note | ad9a9a91-dc9f-4891-b621-cb6fc84ef27b | 1.1 VicRoads Section 610 November 2018
| note | 0a57e4bc-0928-44d3-b036-66fad85d22d8 | 1.2 VicRoads Section 610 March 2019
| note | 793e5c6e-9454-405e-90bd-1c89f1cfc756 | 1.3 VicRoads Section 610 June 2019
| note | b47fa068-1e1d-47bd-9539-332bc982f002 | 1.4 VicRoads Section 630 October 2013
| note | 894e378f-d39b-45b1-b9d0-8adc79b0929e | 1.5 VicRoads Section 631 February 2009
| note | 35352c9e-4d3e-460e-9e06-b32e1e3e3d35 | 1.6 VicRoads Section 671 October 2013
| note | 0e0e1850-379e-4faf-ba67-4b5af4125e13 | 1.7 AS5131-2016
| note | e3deb57d-08e9-4b83-adf3-a9cbdc230d8b | 1.8 AS4680-2006
| note | f40c4561-1199-4964-9817-c758f7ce7d51 | 1.9 AS2312.1-2014
| note | 45a9e833-3a9f-4d31-a5be-f375892c1c5a | 1.10 AS4506-2005
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Structural Steel Components
| note | 24ba9873-986a-43b0-aebd-66aa8b6eb822 | REFERENCE: IFC Drawings
| note | 8ba2419d-0b76-419d-9889-bfdea3e350cc | MRPA Quality Management Plan
| note | b0a2ac9f-a8d8-4c49-9fb9-96783a34faf8 | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
| note | 2ae71416-f8ef-4432-a408-ec83d4b18a73 | Typically this consists of but not limited to:
| note | a2f9837b-9e96-4511-a404-e61bf5295532 | i. Certificate of Compliance
| note | ed1b38b3-5435-46a7-84f0-fce5a02994bf | ii. Completed ITP
| note | 22a5d432-acef-44cf-bddb-8ea601fccb84 | iii. Weld Procedure Specifications
| note | bae44cca-3c88-47bd-895e-3f0dafd8dc4a | iv. Weld Procedure Qualifications
| note | e507cd92-82f5-446c-90d1-5684a8406b73 | v. Welder Qualifications
| note | 675423c6-468f-431e-ae36-daee189c87d5 | vi. Material Certificates and traceability
| note | 8cc03af0-098c-47e9-86e7-f544929d8f11 | vii. Quality Assurance check sheets
| note | b4620a60-120c-4f60-bdfb-f99cff3a1b1d | viii. Welding Consumable batch certificates
| note | ce8b8200-9d6a-42c6-bec2-de110e7b5c11 | ix. Coating certificate(s)
| note | 47eb347b-4c8a-461b-8f5e-f59fb88217c3 | x. Non-destructive Testing (NDT) Reports
| note | ccfd3af2-4f85-403b-ba3e-a5e0cce102fa | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
| note | b5e9c16d-2956-4563-84c3-c4664686b5dd | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | e2cc4b4b-469e-4234-9617-2c5c06f0a781 | METHOD: Document Review
| note | 7ef3e7e9-f596-4baa-88f6-10d30556176f | FREQUENCY: Each component
| note | 1cf1b100-e5c1-4da4-b1c4-fe6a58c7001b | CATEGORY: IP
| note | 44939e93-ab3b-4801-ac4e-f471ed49f1da | RESPONSIBILITY: PE/SE/SPE
| note | be6db382-36bb-4886-9b97-f7e8ac6dca64 | VERIFYING DOCUMENTS: This ITP
| textbox | 338e1872-e604-47ff-949b-ca0a82af5e7f | Date Completed:
| checkpoint |  | 2.2 Base Plate Structural Grout or Mortar
| note | 65824a36-7567-4d6b-bd1e-1fa3ee29cb72 | REFERENCE: IFC Drawings
| note | 7116611b-467f-43af-ab67-33bb9724afe5 | 671.04
| note | 0d7a902d-718c-48ce-a64f-fbd6a8b5c7c1 | 610.33
| note | cebe679f-ed7c-483e-b269-9948b18544f3 | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | 29944583-3750-4d34-88ff-e8bc1515a4ed | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
| note | 9888b049-32a9-48df-82dd-3a4fd1be21e7 | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
| note | 88b793b5-64a7-4898-a1a8-9c654573ca2b | iii. have a flowable consistency
| note | e2c5158c-dfef-44d9-a446-fdeab7c1a6b7 | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
| note | f4caa0b0-dc8e-4a27-99f2-e034e8b6b9de | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
| note | edfd52bc-fc37-4373-a36c-f366e3d8ddaf | Enter: Teambinder Material Approval number
| note | 2a962a0e-f026-49a5-ba2a-b14365fcdcf2 | METHOD: Document Review
| note | 186aa31e-7efd-48a7-a04c-33ad8d746167 | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | d2ecd355-d8cc-4cc7-8ce9-3e2a1013b650 | CATEGORY: IP
| note | fc8086bc-1325-417d-bd7b-972ba9ffdabc | RESPONSIBILITY: Nominated Authority
| note | 9e5cb82d-16f2-4610-afc9-3a192c6bbe74 | VERIFYING DOCUMENTS: This ITP
| textbox | 9288a082-f3b9-497d-ad5d-1698bc6f99ab | Date Completed:
| checkpoint |  | 2.3 Curing Compound
| note | f397e5b5-d1cc-43c5-8820-486924d0ef27 | REFERENCE: 610.23 (d)
| note | acc70afb-f477-4742-b58f-eb0a3f0196ff | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| note | 1aadd829-bb9d-41d0-bc5b-5d23a1d1e37c | Note: This may be the same product used for the concrete curing
| note | f715a5cb-917a-47ac-ab17-d8b8c3d3bce5 | Enter: Teambinder Material Approval number
| note | fc27712b-b114-4925-9cb6-1be2100d2bdf | METHOD: Document Review
| note | 28c57106-de44-4019-adc3-4751326396e3 | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | 338b68b6-4f77-4cf3-8773-4f62cacdfc35 | CATEGORY: IP
| note | a5908c82-5e52-49b0-9f61-41008a791fdd | RESPONSIBILITY: Nominated Authority
| note | 589f62e8-a15a-4725-84b2-281d15ba0d62 | VERIFYING DOCUMENTS: This ITP
| textbox | 2708e1e8-41ac-4384-b0dc-5dea0b5884e5 | Date Completed:
| section |  | Preliminaries - Procedures
| checkpoint |  | 3.1 Curing Methodology (for Grout and Mortar)
| note | 875562d7-cf5b-44ef-b984-1a9a89ad1857 | REFERENCE: 610.23 (a)
| note | 9de6b0a4-657a-4b36-9ef6-f3870500e030 | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
| note | 16fbf39b-38de-4c45-9579-37504d435ca3 | Note: This may be the same document used for the concrete curing.
| note | 857647c4-ce33-4ad6-8a59-816bc48c377a | Enter: Teambinder Approval number
| note | 5685c014-f7bd-4675-8a4a-2bcca30b89b3 | METHOD: Document Review
| note | c4756361-759b-4322-bd29-dc8e4641eebc | FREQUENCY: Once, 4 weeks prior to placement of product
| note | 5a1d76af-9235-4766-8b12-3ae103e9e915 | CATEGORY: HP
| note | 2a8e3c44-94ba-49c5-a05c-733abc27e4e0 | RESPONSIBILITY: Nominated Authority
| note | 2037a5c7-67d3-4bf1-b408-cdf83e575bf6 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 1ac4ee65-76e1-4910-b8fb-8071dfca6091 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 4.1 IFC Drawings
| note | 97ed0588-be40-4a21-9caf-918ee83815f0 | REFERENCE: MRPA Quality Management Plan
| note | 89566f2a-79ec-4a28-a359-defd4f9a224c | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | b0c36f0d-68c4-403b-af54-1eaf01f98423 | METHOD: Document Review
| note | 49122914-9b98-4f71-aa7d-913d898dbdb1 | FREQUENCY: Prior to starting Works and at regular intervals
| note | df60dee1-ce17-446d-b5ca-d1e47b2c246f | CATEGORY: HP*
| note | 9a21a790-9e27-4477-bb0f-96f6727e69c3 | RESPONSIBILITY: All
| note | 7ac017c5-882a-4b26-8789-8ca42e517b4e | VERIFYING DOCUMENTS: This ITP
| textbox | 1adc9dc0-393f-4c9e-95c3-3e80b7d58ab7 | Date Completed:
| checkpoint |  | 4.2 Materials Inspection Checklist
| note | 1cf5630f-1230-4b4b-8daf-987804c1b3d4 | REFERENCE: IFC Drawings
| note | 59a0543f-60ac-47ab-bca5-74e5e9ba0d79 | 630.08
| note | fb657cbf-8ccd-4140-a143-e5178064c86f | 630.09
| note | 2a328178-fb1a-48f3-b49e-9e4798c6d365 | 630.20 (a)
| note | 141e21ec-e84c-4731-91b9-cf75a3b2b587 | 631.06
| note | b5d9a857-6cb8-4e8b-a098-4f5a40cb0d4f | AS4860 Clause 7
| note | 276eaa04-056b-4656-9daa-eb5c0dafa100 | 631.11 (a)
| note | e58e3859-1fef-4f07-9ed2-15403201efaa | AS2312 Clause 9.6.4 (i)
| note | 4ef2e693-b97a-495a-b14e-e842389a055d | AS4506 Clause 2.3
| note | 17ab2c08-2c14-410e-9334-8734e2e4b28e | MRPA Quality Management Plan
| note | 06c9fd94-1f36-49c7-8a8c-e8d6622accea | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
| note | e37b0f04-c69a-490b-817e-d10772720fe9 | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
| note | f4f265d3-5472-4da6-ac27-12e326be5d16 | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
| note | 96e914ce-886d-4f8c-bcad-31ad9c638a6f | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
| note | 1129b51b-7334-4cac-8d23-175a8217c628 | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
| note | 8a33a754-efa3-492d-875d-196c481a939f | Complete: Materials Inspection Checklist in ConQA
| note | 489b6819-8178-4da9-84a1-038359e65079 | METHOD: Measure , Visual
| note | 66fef421-af83-4432-bc30-4d3a08ef178e | FREQUENCY: Each component
| note | 5c3c3df8-5621-4ede-9387-1d0159be7d5b | CATEGORY: IP
| note | bc1a3b08-cfbc-4ac3-867f-c4cbedcf6f46 | RESPONSIBILITY: SE/PE/SPE
| note | 393ee02a-37a4-4a34-8640-6a99143a4087 | VERIFYING DOCUMENTS: This ITP
| textbox | d411b96d-dbda-4bb1-ad46-aed53ad127fa | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 5.1 Bearing / Mounting Surface Preparation
| note | a8979a74-ff16-4eea-ba26-7317c934bb90 | REFERENCE: IFC Drawings
| note | 2c15f710-8366-4526-abf3-f6f44992378b | Product TDS
| note | 206fc1d8-3811-4a79-a2bd-077d5706af66 | ACCEPTANCE CRITERIA: Prepare the surface in accordance with the Product TDS.
| note | c6873c17-7a74-442a-9d6e-d45803caba3d | As a minimum, ensuring that it is clean and free from laitance.
| note | eefd6b77-2659-434e-975f-1aabace684de | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
| note | 8523ccff-4dbe-4831-91a4-fba87c5f6cc6 | METHOD: Measure , Visual
| note | aed6f142-6089-41ae-a8c3-89adb4f7772f | FREQUENCY: Where applicable, each post location
| note | e39ae37e-b065-4c0b-8adc-ae0b6bc18bab | CATEGORY: IP
| note | 51046109-2670-4d69-880c-52d7e9a48171 | RESPONSIBILITY: SE/PE/SPE
| note | 0cdd815c-bace-4560-82d3-6feb55cd05e0 | VERIFYING DOCUMENTS: This ITP
| textbox | 2368695a-90ae-4a46-8ff8-993d3589eac0 | Date Completed:
| checkpoint |  | 5.2 Structural Steel Handling
| note | 023aa73b-c30e-41ba-a333-efec6f1bb697 | REFERENCE: 630.09
| note | c5f2670a-bc64-4680-8029-a65df01c04f6 | 631.14
| note | a72b0939-f202-4486-a4bf-ce496a0c114b | AS4100 Clause 15.2.2 & 3
| note | ce7a3207-0e28-4836-8887-8a5fa0d8c97c | AS5131 Clause 11.5.6
| note | d2493af3-9a12-4387-b663-a335ecf81be1 | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
| note | 0d948f38-5989-466e-9369-cfdc17f6ad3a | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
| note | 7e55525d-2211-46e2-99d8-5d17e2ef6c95 | METHOD: Visual
| note | 20ef1ef2-40f5-4c36-8944-f84b7fd8bbd4 | FREQUENCY: Each component
| note | edc1eb4d-cb65-4711-94c7-314c7f5075aa | CATEGORY: IP
| note | a8234679-0256-49d8-a3ca-693648bf65ff | RESPONSIBILITY: SE/PE/SPE
| note | 9a14190e-51d0-42cb-b9d7-174a9c7885eb | VERIFYING DOCUMENTS: This ITP
| textbox | 0ea1d0f7-01c0-4cec-b63a-542603443b9d | Date Completed:
| checkpoint |  | 5.3 Structural Steel Erection
| note | 2a801d1f-9bd7-4b85-9f6a-741a03a82262 | REFERENCE: AS4100 Clause 15.2.3
| note | 4395999b-416f-4e96-8b82-8ee4b595a663 | AS5131 Clause 11.5.7
| note | 1ec78c75-2854-4ce6-aed8-0f2b6a86847d | 630.12
| note | 58359ad3-8bc5-42b1-81fb-9749d4dd4183 | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
| note | ba91d928-b985-47c7-a345-bfb3ce5837f4 | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
| note | 5c988e39-a283-4d9a-88d0-9dda9eff8424 | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
| note | c50898e0-732b-4dd4-8dec-7ffdb8f825ce | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
| note | 96571110-58c0-47ec-b24e-dc1ed3de9dc5 | Holes shall not exceed the greater of:
| note | 2c2a3685-2cbc-4203-b05f-077ffe43914d | 1.25 x bolt dia. OR bolt dia. + 8mm
| note | 31a129ad-e8c2-46b2-8122-023d587b4025 | Slots shall not exceed the greater of:
| note | 20a282cf-7e19-4d9a-a023-885c68dd4c36 | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
| note | 078d055c-3a8e-4a98-a92a-e201aa795131 | METHOD: Measure , Visual
| note | c6a02271-dfe7-4817-ae19-324a0d770007 | FREQUENCY: Each component
| note | 09cb488b-ffe1-47f4-9e43-1a1484c72cb9 | CATEGORY: IP
| note | a8823ece-c9a1-4ec3-8b99-d4c4fa33caad | RESPONSIBILITY: SE/PE/SPE
| note | 9ec10c4b-6da0-4a17-bff5-0344165f8a11 | VERIFYING DOCUMENTS: This ITP
| textbox | d4ba7532-1a8d-47b8-b3b8-2b01fe6a6930 | Date Completed:
| checkpoint |  | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
| note | bc34da90-b9e0-4ab4-95c7-c50038a2fad7 | REFERENCE: IFC Drawings
| note | d2ec75a0-e0e1-45e0-9b8b-295ed2a9ddff | 630.20 (a) & (c)
| note | fda4fa86-81c1-4040-93e7-8c5e7626edc4 | AS4100 Clause 14.3.5.2
| note | fd3a7455-8e65-40ab-951e-754ac258c7e6 | AS5131 Clause 6.7.4
| note | 770780e0-3143-43a8-a71b-10a4cb87c994 | AS4100 Clause 15.2.5.2 (a)
| note | f9ed3133-bad3-4494-87a4-39b67344e28a | AS5131 Clause 8.3
| note | 9a49125d-ec7d-4097-9699-c99892b4db09 | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
| note | 6db9d23e-70cf-4664-81d7-0591aa177073 | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
| note | 17cbcd94-fcb6-4540-b3b2-0b680d40c073 | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
| note | b845b681-a234-4f90-b7b3-3150d6cdb266 | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podgier spanner.
| note | b4dbe196-1fb2-4902-bddd-fccee394d272 | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | 9deade1a-63f5-4701-bdc2-021172775b94 | METHOD: Measure , Visual
| note | 148a2e8d-e241-4886-825d-a9061e857670 | FREQUENCY: Each bolted connection
| note | 15026e97-81eb-4b80-8b94-7bc71125b8b0 | CATEGORY: IP
| note | bfc87069-62fa-4821-aab2-092cfc102538 | RESPONSIBILITY: SE/PE/SPE
| note | c5516ecd-3b78-402e-9926-c67eb62646be | VERIFYING DOCUMENTS: This ITP
| textbox | 1b284228-e681-4a56-8146-4f5ad4e3887e | Date Completed:
| checkpoint |  | 5.5 Survey Conformance
| note | 83ae5c26-8740-4c86-8d60-bde5dc3d1b26 | REFERENCE: IFC Drawings
| note | 1866abde-26a1-46bc-9f1a-413ce8eabc52 | 671.06
| note | 52c2e729-f399-40a6-85f1-44530f5cbbe6 | AS4100 Clause 15.3.1 - 7
| note | d996070c-84c5-444e-b0c9-dac3331d4d5d | AS5131 Appendix F, Table F3*
| note | 5dbf100d-a253-4845-be6f-582f342dbf6d | ACCEPTANCE CRITERIA: Railing posts shall not be grouted until verification that the Works meet level and location requirements within the tolerances below:
| note | 2c1c6756-9e02-4a8a-8952-6752395d28c7 | Departure from RL = ±10mm*
| note | 9b3cee75-90c5-451e-b6db-8b2d19ef35f2 | Departure from plan position = ±25mm
| note | 6e72b565-d14e-4dc8-831c-ac9be196877e | Departure from alignment = ±5mm
| note | 31b6a611-676c-433d-997d-679b07a227dd | Irregularities in alignment = 3mm in 3m
| note | 9b8e385b-d372-4f1b-899c-8aa3eae29688 | Variation in joint gap width = ±3mm
| note | 17c4710c-eaaa-416c-9175-4f1be5b1c42d | Projection of bolt = +25mm, 5mm
| note | be539dff-513d-477f-bb4c-0a79eb5fefb2 | Attach: Survey Report
| note | c6b68eca-dd20-49d5-9d6c-ebe71cf3975f | METHOD: Measure , Visual
| note | 923e4b58-16aa-48c9-887e-d61aff74c7b0 | FREQUENCY: Each post location
| note | b9c591d0-f182-4f7b-8d86-961459d76c01 | CATEGORY: HP
| note | d691a511-f7d0-4873-a157-c8707740a66b | RESPONSIBILITY: Nominated Authority
| note | 8ca25511-2a96-44af-b16d-496a0c6e82e6 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 73f82146-01f0-4f19-8027-ea8120884931 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.6 Base Plate Formwork Construction & Placement
| note | 9ff622d8-ff24-46af-9ccd-f415969a1754 | REFERENCE: IFC Drawings
| note | 5f4f80d6-bd60-4d79-a509-d32e8209eef6 | ACCEPTANCE CRITERIA: Dimensions as per drawings (typically flush with base-plate sides and underside).
| note | ddffbf4e-b81d-43d8-94ed-ad45f6373607 | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
| note | 4433e25a-4eb6-4909-b5a3-40c12c29228d | METHOD: Measure , Visual
| note | 95244109-caec-424a-a40e-f2b6f805aa4c | FREQUENCY: Each post location
| note | 4b0c7391-4b91-4d1f-9315-bdcb839a07b0 | CATEGORY: IP
| note | 59759c1a-51b2-4cd3-b2fe-fd2268044a63 | RESPONSIBILITY: SE/PE/SPE
| note | 493c896f-06b6-4522-9956-88352074473b | VERIFYING DOCUMENTS: This ITP
| textbox | e23648d8-cfcc-43f8-9c63-5243c9b2d3e7 | Date Completed:
| checkpoint |  | 5.7 Pre-soaking Concrete Surface
| note | 68bafdeb-10a1-440d-b091-b45f0aa7dd15 | REFERENCE: Product TDS
| note | 27bce66a-0c40-47d2-b397-0bb50cd2222f | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
| note | e36a7c5f-422b-48b3-aa06-222e2399d13b | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
| note | 0af2f6a7-dc1d-4928-97e8-f1686ebd078e | METHOD: Visual
| note | b315d835-2983-42e3-86ff-28932cbf0f8d | FREQUENCY: Where applicable, each post location
| note | e8ae89f8-6a41-4041-b266-a3aa444bbf4e | CATEGORY: IP
| note | 1e07cfce-9e7d-43cc-aead-aab159abe444 | RESPONSIBILITY: SE/PE/SPE
| note | 4f52e84f-f981-4614-8aec-7c9d66a251a9 | VERIFYING DOCUMENTS: This ITP
| textbox | d074d7fe-dc26-42fe-a7a4-555da426a8d2 | Date Completed:
| checkpoint |  | 5.8 Weather Conditions
| note | 1c99cd6f-048e-4a3d-bfa7-795e3e48aaa4 | REFERENCE: 610.17
| note | 5892b3cf-9551-4b08-a266-91aae9d18c4e | Table 610.171
| note | 67239f9c-c2ea-46df-9e40-058e30b04f46 | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
| note | 8420ce35-f614-4164-9d61-ef74b6a796d3 | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | 73a43a26-ff86-4842-b858-65975704725b | Record: Required information on the Grout Pour Record.
| note | 16539809-ade1-4884-a09c-e9186db136fb | METHOD: Measure , Visual
| note | d9e5dc6a-4d78-4ece-8157-e29e713eb967 | FREQUENCY: Each lot
| note | bf44f8ee-5dbe-482f-8edf-a02f52cc47fd | CATEGORY: IP
| note | 4599fbab-5d65-491c-9cc8-01ccfd66854d | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 789a01a6-4bde-443b-ae51-4886374e309b | VERIFYING DOCUMENTS: This ITP
| textbox | 2482e769-6792-49ff-9f91-1caa4e8733b8 | Date Completed:
| checkpoint |  | 5.9 Mixing Product
| note | c8281654-1654-44ee-a762-42abb3e078fc | REFERENCE: Product TDS
| note | ab723bf7-25c7-4aa7-8eab-1fcdb1e17bf0 | 610.28
| note | b6aa5e1d-9f8e-4dd2-b5ca-1c156c1b0241 | ACCEPTANCE CRITERIA: Size of mixer should match the application.
| note | 50e89f1a-1a75-45b9-a619-3ffdc46f7c21 | Only whole bags to be mixed with potable water.
| note | fa0ec530-fe15-4f57-9b19-867842b2ef7c | Volume of water matches the required amount for flowable consistency and accurately measured.
| note | 5884cd4e-57eb-41bb-99b2-689c989d9df4 | Product poured into the mixer slowly.
| note | 25f18c00-269c-4199-b411-4ba881f6cb3a | Mixing time as per TDS so that a smooth, even consistency is obtained.
| note | c734638b-c38e-4165-b384-8e752c845bcb | Enter: Required information on the Grout Pour Record.
| note | b0448c43-08f8-4b1f-8e4c-fa0006315cab | METHOD: Measure , Visual
| note | a808b417-be61-495e-9dc8-d5130d01da93 | FREQUENCY: Each batch
| note | 211ee0d3-10a5-4355-b4e2-52ededdfb695 | CATEGORY: IP
| note | 1b27dbf0-f6ca-4118-8b4d-be6e86253309 | RESPONSIBILITY: SE/PE/SPE
| note | 58f1f11d-ed80-48aa-b069-7de13e885c7d | VERIFYING DOCUMENTS: This ITP
| textbox | 21d910d4-8d2f-4f89-93a7-4028be6ba927 | Date Completed:
| checkpoint |  | 5.10 Product Testing - Compressive Strength Cubes
| note | 42ba2d43-d3ae-4032-8957-14210aa0203a | REFERENCE: 610.28
| note | b68ffb99-bc47-4ca9-a306-1255fbbe91ad | 610.33
| note | af9ef3d6-e74a-4aeb-9293-25b6cda1bd02 | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
| note | 31996608-fde6-4acb-966d-41d1d7438333 | Testing is be in accordance with the following frequencies:
| note | 64b095bb-6b41-453a-8761-be7a152735d4 | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| note | 853d8362-6d83-4548-95b0-51df3509c9e1 | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| note | e361237f-83bd-41a0-8eb3-50a84673690a | Enter: Required information on the Grout Pour Record.
| note | 50308706-ee6f-45dc-9b40-efe0181f8d23 | METHOD: Test
| note | 6dc91826-d0d4-4bbe-bb88-6b63dc583b38 | FREQUENCY: Each lot
| note | 41931124-c56c-4e4b-badd-1d681a5a87c1 | CATEGORY: IP
| note | 751a5a0c-d77b-4eb9-9813-79ad6e14e74c | RESPONSIBILITY: Tester , SE/PE/SPE
| note | aac092ba-e9dc-4c89-846f-1db9523a7b91 | VERIFYING DOCUMENTS: This ITP
| textbox | 94cb63e0-3ee0-46ab-b53c-e8ce72790bba | Date Completed:
| checkpoint |  | 5.11 Placement & Compaction
| note | f088ebed-3592-4123-b778-2f4339758e6d | REFERENCE: Product TDS
| note | 32a8ba10-88ef-4e04-aeb4-773155b8ae53 | ACCEPTANCE CRITERIA: All batches are traceable.
| note | e307c596-bdf3-4b81-922d-61177e910df2 | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
| note | 6dc7bf3d-1f07-4779-bf45-7ead629ae744 | Product should flow to all areas and self consolidate.
| note | f6ed13cf-37a8-4f3e-8dbf-4b7a0f29cfd3 | Product that stiffens or is showing signs of stiffening shall not be used.
| note | d5f40cf5-7a4f-4ae7-8258-04d6ec50c6af | Enter: Required information on the Grout Pour Record
| note | 9f921ce9-3908-4a45-a912-e815caa65802 | METHOD: Visual
| note | 0cca327e-9a83-4402-b536-45cf328717c4 | FREQUENCY: Each post location
| note | 2e55a8f2-3d38-4ad6-9f07-036ae57ee547 | CATEGORY: IP
| note | dd266388-858b-4627-884a-cf6cc7d6ea2e | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 48b23b17-2c5a-4c8a-9ccc-b0391c5330e7 | VERIFYING DOCUMENTS: This ITP
| textbox | d214f6ac-ddbe-4d31-9486-278e908a312b | Date Completed:
| checkpoint |  | 5.12 Surface Finishes & Protection of Works
| note | ace981c0-07f1-4357-ac1a-1f810793a9d8 | REFERENCE: IFC Drawings
| note | 246f5d7e-4fbd-48ee-9fff-9c1995b18414 | 610.17
| note | 0721160e-7900-49d2-b369-d8754776e541 | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
| note | 4baa4a75-421c-43f1-bee3-a6ad0787420c | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | fd39a96a-85d5-4e1f-8ea3-126018406586 | METHOD: Visual
| note | c670e816-5998-40a3-88c0-d135ad1cf990 | FREQUENCY: Each post location
| note | b8da96f8-61e8-4044-a583-7fbf70518957 | CATEGORY: IP
| note | 5dac41dd-90cb-47b9-9e63-eef4e12f022f | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 3dbb4239-3f39-44e9-92ed-a2b2803e20f5 | VERIFYING DOCUMENTS: This ITP
| textbox | 36ebf752-32bf-4a01-87ca-478cd3c8c735 | Date Completed:
| checkpoint |  | 5.13 Curing
| note | 543bc34f-8995-4266-a5d1-f2561747c121 | REFERENCE: Curing Methodology
| note | 4602c0ff-f3fa-4683-859a-1b5285619890 | 610.23
| note | eb6881bf-0770-4be3-be48-1cc8b2da4f65 | Table 610.231
| note | 3ac877eb-d0c4-48c6-a824-4a8f22991b0d | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
| note | fdc579c2-f455-46eb-9465-908c0984118f | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | e8fe8da4-e5a2-4507-bd5b-a4383d96e274 | METHOD: Visual
| note | 433253a6-d757-42d3-9683-77a8fd31b7b1 | FREQUENCY: Each post location
| note | f9fb252d-d4cf-45b1-b0f9-b357ee6b6f85 | CATEGORY: IP
| note | c05f1761-92ae-4f2d-a2c8-2a94acfa3b80 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 6173bb2b-7cca-412d-940e-6498f3afcc38 | VERIFYING DOCUMENTS: This ITP
| textbox | fcc969ec-16d8-43c6-9a3f-3f34be053f1d | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 6.1 Inspection of Coating
| note | 0a1f3085-4550-4e42-8797-9974bcaed756 | REFERENCE: IFC Drawings
| note | 712bc534-7327-466b-af20-6f4ba9620d01 | 631.15
| note | d9429056-7e61-478a-9812-fa876c8f42a1 | AS4680 Clause 8.3 & 8.4
| note | a12326fd-5862-40f3-ad73-a4677169e5e7 | AS4506 Appendix E
| note | d9f77c06-a6e9-48ee-8e69-0b2298e00003 | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings .
| note | 7069ac07-8f96-4831-8aae-43c2de4629ff | Where damage exists, it shall be repaired using an approved repair procedure.
| note | f6c8743f-baf7-4add-9ac9-c6f3ebc0e5c7 | METHOD: Visual
| note | 93956f1b-4a0b-4695-9628-a13eea5b3bac | FREQUENCY: Each component
| note | b47be97c-71d6-40ec-8818-5ef2593a0bfa | CATEGORY: IP
| note | 39d80471-79c9-45e1-bf39-665695d2055a | RESPONSIBILITY: SE/PE/SPE
| note | 8e10dcc6-f5c5-488e-a6a7-41fd888ea76c | VERIFYING DOCUMENTS: This ITP
| textbox | 3e52737e-5713-4f68-bae9-485a050aa00a | Date Completed:
| checkpoint |  | 6.2 Compressive Strength Test Results
| note | b7347ea4-383d-4d30-979a-eaa90dec6f81 | REFERENCE: IFC Drawings
| note | 0ed92d9c-26a8-4848-88a7-1f0fa3b9e6b8 | Product TDS
| note | d7d4688b-c8fb-4bba-87b9-f926f591cc82 | 610.28
| note | fceeca48-001c-4c33-9b55-9d63d208e177 | 610.33
| note | 7eea0992-1749-476e-b72e-92fdc1f6ff90 | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
| note | 28ebbd6c-5bb7-49b7-8584-263901aad96f | 28 day compressive strength per sample comply with the design strength.
| note | 76188b2a-219e-4728-a861-d897ae4adf78 | Attach: Compressive Strength Test Results
| note | 7c7123a5-8db1-440b-a091-7a625f6e3808 | METHOD: Document Review
| note | 4fd0907f-3b38-4a58-8199-e204aa3fb353 | FREQUENCY: Each cube
| note | 0c158708-7996-423f-a5e4-a6ff65a55045 | CATEGORY: IP
| note | 574382e9-8f84-42c0-8363-66dbc1f49580 | RESPONSIBILITY: SE/PE/SPE
| note | dd98eef6-bfd9-4386-a9cb-db7bf277318e | VERIFYING DOCUMENTS: This ITP
| textbox | 6ac54f55-2784-4a37-8fb7-974fa13f19ba | Date Completed:
| checkpoint |  | 6.3 As-built Survey
| note | 5059e770-687f-4211-b884-b7bbec704616 | REFERENCE: IFC Drawings
| note | 606114f0-1f95-4e33-a5c6-b11fbb55e1f5 | 671.06
| note | 9baf6b69-5a44-4cbd-988c-e58254687485 | AS4100 Clause 15.3.1 - 7
| note | a514014c-6ab5-4b08-9c2f-e7f87d21b63d | AS5131 Appendix F, Table F3*
| note | 516e7563-152c-4774-b38c-2dfa7a4cce29 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
| note | 7c07e500-5502-4c90-99f3-f71c84db5c01 | Departure from RL = ±10mm*
| note | e5c23d32-179c-4bce-a5e8-b40eb1d7b7b2 | Departure from plan position = ±25mm
| note | ed2aff12-7f2e-4b03-9a91-6b970443feed | Departure from alignment = ±5mm
| note | bd7eadf6-72be-4982-92c7-3b749529b4cb | Irregularities in alignment = 3mm in 3m
| note | 78d670b2-e8a6-4331-ae4b-b60f9806dc6d | Variation in joint gap width = ±3mm
| note | 88886655-a112-465a-955f-0a2d101b3499 | Projection of bolt = +25mm, 5mm
| note | 3e733762-e86f-467e-894c-f4f91fe008d2 | Attach: Survey As-builts / Survey Report
| note | 3ea5bb83-505c-40db-96f2-45d9f1ebecd8 | METHOD: Document Review
| note | a281d4c8-fe33-41ae-b257-8ea894a58b5c | FREQUENCY: Each post location
| note | 90f70d61-ea87-4266-838e-bba064d6badc | CATEGORY: IP
| note | a373a05e-5efa-4b4c-a491-fbf5aab92190 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 252e35f0-9c17-41c1-bdd0-1ad38e1070af | VERIFYING DOCUMENTS: This ITP
| textbox | fddf4fbd-5aed-402e-9aa4-4e239874c64a | Date Completed:
| checkpoint |  | 6.4 Non-conformance Report (NCR) Closure
| note | 87e9b031-15c3-4aa7-8b59-b80bdd347a89 | REFERENCE: MRPA Quality Management Plan
| note | 86e3ad6b-bea2-4858-916d-a8fb91570e7a | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | aa14db83-f6e2-4641-ae89-4f4f8a29a0b1 | METHOD: Document Review
| note | 8988be7e-5a6d-4c5a-a144-4e215efeeba4 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 3406899d-5b87-4d62-8859-487e24e556f2 | CATEGORY: HP*
| note | 23ac5cdf-5f1c-4cc6-8fdb-c4ec6b55b367 | RESPONSIBILITY: SE/PE/SPE
| note | 1b8119c7-bec1-47cc-942e-a9e48e094a43 | VERIFYING DOCUMENTS: This ITP
| textbox | 23b28d35-c858-4c58-9fc5-5b22bd250857 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 6ad4a7d4-ddfe-4d26-8cef-b362e7ef1e66 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 39e74f11-9794-4284-8e50-a948fccefc9f | Name:
| textbox | 5c2170dd-7a7d-4a8c-8d2c-68082e6cb0c8 | Position:
| textbox | 57649ec3-a8e6-40f5-9c95-cf56ba425236 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Bored Piling (OHW Foundation) Rev 3 | itp | ITP-STR-Bored Piling (OHW Foundation) Rev 3 | 7a17843a-7148-481f-ab03-b8a0c69413a2
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 0b65cac3-f08a-4d50-9b81-34b3a50870e3 | Document Title: ITP-STR-Bored Piling (OHW Foundation)
| note | c91a4619-12d0-46be-b45c-5203903dc330 | ITP Description: Bored Piling (OHW Foundation)
| note | 5174790e-db12-4bd4-83c7-a70f0641395a | Discipline (e.g. CIV/STR/RAIL): STR
| note | 285e2a4e-8cf4-457a-acf9-d905499198a9 | Revision Number: 3
| note | 3a7d540f-c9b9-4d9a-8d66-4c7c37af71b6 | Revision Date: 12/05/2021
| note | 100d2f36-924b-492e-a717-9fa9716dcb55 | ITP created by: Mike Freeman
| note | b1267f0c-a58b-4824-9695-c7b9904c6324 | 1.1 VicRoads Section 606 July 2017
| note | b90a169a-e1bd-4a03-bcb4-9018917a9154 | 1.2 VicRoads Section 610 June 2019
| note | 716276e7-ca45-4d58-b5d5-94dad9349f6e | 1.3 VicRoads Section 611 November 2018
| note | 2db96844-0066-4b50-b0f7-f59e0de3f0a3 | 1.4 AS2159-2009
| note | bb794393-0c01-44c9-8019-4f35b655849a | 1.5 AS3810.1-2015
| note | fc519285-8f60-4157-aa32-78d1554defb7 | 1.6 MTM L1-CHE-STD-058 Rev 2 July 2019
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Concrete Mix
| note | 39ad28ac-ef08-46a6-8a3c-fe0923c59b7c | REFERENCE: 610.07
| note | ac62ad81-1eff-4f07-ad22-8b63fbb89737 | Table 610.071
| note | 227c7e23-e106-4669-a3f4-1189f1641dea | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
| note | b8c52abe-a945-4e9d-8251-a38cb9437086 | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
| textbox | 4deb1a95-7e05-4e09-b987-af390bb0c5e4 | Enter: Teambinder Material Approval number
| note | 7d25a205-8081-4a2b-980b-fa6aa32f2db8 | METHOD: Document Review
| note | be47b89c-77d9-4400-a54e-e3040936d4f5 | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
| note | 8a2895b6-a923-4f40-8424-40fd16f75250 | CATEGORY: HP
| note | a1256ede-99e1-4329-bc25-d85b8db632cc | RESPONSIBILITY: Nominated Authority
| note | be24635c-827a-4c81-80a4-1376d086aac6 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 14ab146d-6632-47f9-80dd-6c6e5e9bdf59 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 ACRS Certification (for Reinforcement)
| note | f2b22504-cfea-436e-91ec-485ea45cbdcc | REFERENCE: 611.05 (a)
| note | 86817971-cd71-487c-b3f4-e41507cc7cf5 | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
| note | 6540f7d7-b78b-4005-a329-522402e358aa | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | 60e0d5c4-31a2-4048-86d2-875ffdf606b8 | Enter: Teambinder Material Approval number
| note | 9234d1e1-ce2f-48e1-94a1-9d97ddca6b6a | METHOD: Document Review
| note | 0a4bff65-7b51-4a3e-85fc-36630fd8013e | FREQUENCY: Once for each supplier, 14 days of award of contract
| note | b6c2fc72-4b2d-43c7-9f3b-1ed84be601d1 | CATEGORY: WP
| note | 9cb20c15-a0af-4fe5-a076-86ea2742a815 | RESPONSIBILITY: Nominated Authority
| note | a58fbf22-c449-4984-a544-5e52cab27009 | VERIFYING DOCUMENTS: This ITP
| textbox | 0a2d125a-a383-403a-bf1b-c3d1a8df4a52 | Date Completed:
| checkpoint |  | 2.3 Bar Chairs/Aspros Certification
| note | 331c982d-ab60-40b9-b225-93c1dd1af8c4 | REFERENCE: 610.26 (a)
| note | 889938f1-72db-41af-8014-1fbdf13b29a6 | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
| note | 51800c77-2e75-4992-a78e-309f896fda51 | Concrete aspros require annual compressive strength and soluble salt testing is required.
| note | adf6c928-1a39-4c80-9f6d-57dcabdb57e8 | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
| textbox | ff7ee489-d6b3-40cf-9917-4bc17ba3a22d | Enter: Teambinder Material Approval number
| note | effda2b2-691b-4f57-b882-11769a4c129a | METHOD: Document Review
| note | e1b969d2-af34-4536-a270-eb700ab85858 | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
| note | 6a9f0295-0621-4d66-bd96-4dc1dba72b80 | CATEGORY: WP
| note | a0c4c821-be6c-40fd-a2aa-fac86c09b6e3 | RESPONSIBILITY: Nominated Authority
| note | b4e8be78-4d02-4643-9992-d2251db5b8a2 | VERIFYING DOCUMENTS: This ITP
| textbox | bef20946-d7ed-4645-9a90-0e68ba3dc799 | Date Completed:
| checkpoint |  | 2.4 Curing Compound
| note | e25e24d9-e817-420b-af2f-59ba7f231013 | REFERENCE: 610.23 (d)
| note | ba0b5135-f6bf-47bb-9c8e-280f97e90177 | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| textbox | a595a363-8c34-462c-824f-21747b5a27b0 | Enter: Teambinder Material Approval number
| note | 34166df4-6dc1-414c-a70a-a13024118a47 | METHOD: Document Review
| note | 78b715d0-9dee-4670-9e7c-4b338dc2c1ac | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
| note | b4c8f92b-0c00-4dfc-9d14-5017bb839d8f | CATEGORY: WP
| note | 67600c9d-af18-43ee-b2c8-8f1df07f0413 | RESPONSIBILITY: Nominated Authority
| note | af1bdfb6-5e5c-4360-ba1c-1a94c27f81ca | VERIFYING DOCUMENTS: This ITP
| textbox | cfa46a6a-4dd9-47c2-b440-a980c09f0ef7 | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Piling Operations Work Procedure
| note | bedf03f9-4b4b-4bb6-864c-247c3fa5dd6a | REFERENCE: 606.03 (a)
| note | 2da76e35-89ae-484e-b99e-678e5f9a08a0 | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
| textbox | 0af7d1d3-dd79-45ea-ab96-e5dff13632f3 | Enter: Teambinder Approval number
| note | dc061630-faf0-4333-8b10-21a005fad5ea | METHOD: Document Review
| note | 82212346-834e-4707-92da-bf178e311cee | FREQUENCY: Once, 4 weeks prior to the commencement of piling
| note | 79259ec6-36a9-432b-8059-b2002891449b | CATEGORY: HP
| note | bdfd5303-b650-44c3-884f-b65eda6e2d72 | RESPONSIBILITY: Nominated Authority
| note | 3e29aa82-cff2-49af-a079-d3f49a7e039b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 680eee8e-1bbc-4e28-a468-f3d3edc6859b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Temporary Steel Casings
| note | 3a26be1a-65d1-4c01-a690-1612f9fc9a8b | REFERENCE: 606.03 (b)
| note | 769e934d-e0f7-4fe6-8796-a2b44f12b007 | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
| note | 5367aa75-643f-4ce4-a292-6d44403e5709 | Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
| note | e00fadfe-6ba8-4db6-930e-908605d0e1ea | The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
| textbox | 92acd849-1b86-4177-8998-ab8224da3284 | Enter: Teambinder Approval number
| note | 1e87c8c7-7866-4dd8-b7eb-600a9cad4d70 | METHOD: Document Review
| note | e0a2df34-43bd-4f71-a0d6-50ae0a874086 | FREQUENCY: Where applicable, once, prior to use
| note | 1f281268-f1df-46af-9dca-f8f602f6387b | CATEGORY: WP
| note | 132d3025-c8c3-4f42-8ccf-1cbeaf82d57d | RESPONSIBILITY: Nominated Authority
| note | e6b458d5-97bf-44c6-85d3-598a85399682 | VERIFYING DOCUMENTS: This ITP
| textbox | 7f9f95af-a39d-4d59-8e35-f3072ccddb6b | Date Completed:
| checkpoint |  | 3.3 Casting Under Water Procedure
| note | ebd3b4f3-78bf-410e-a0bd-1e97f07e7819 | REFERENCE: 606.06 (a)
| note | 8d42dc8c-1d4f-4ab7-9ff6-6a662134d07c | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
| textbox | 9e9b0031-0c63-4dec-9251-4b9e905ff749 | Enter: Teambinder Approval number
| note | d20b1360-8a8e-4db7-9ae8-5c16c4e2756f | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number.
| note | 703c00f3-ffb5-447b-be4c-e17d12cadf5d | METHOD: Document Review
| note | 02b1c675-f094-413d-a4e1-462f519078c9 | FREQUENCY: Where applicable, once, prior to placement of concrete
| note | a314aadd-5505-41e7-8aee-1a8bd59bd6f3 | CATEGORY: WP
| note | 1388009b-3e15-40a7-bf46-ba2c8ad5c3c4 | RESPONSIBILITY: Nominated Authority
| note | 247c04b3-f08b-47eb-a7ac-419baec2dd43 | VERIFYING DOCUMENTS: This ITP
| textbox | 22d12a56-a554-45d3-8906-49bd80c5f4af | Date Completed:
| checkpoint |  | 3.4 Boring With Bentonite or Polymer Fluids
| note | f0809921-354f-43f4-bb69-d7c56edecd8c | REFERENCE: 606.06 (c)
| note | 9289a257-f245-487d-8f8d-daebd187ac4f | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
| textbox | 023c2ac0-c7ec-4a1b-a114-9e923804db88 | Enter: Teambinder Approval number
| note | c1d492ca-dcb1-424d-a6ef-1949ce742410 | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number.
| note | 4736cf17-468a-4aae-9790-d65430c75a74 | METHOD: Document Review
| note | 0d64564b-aa3b-42b9-83b6-6e7eb16c7a3f | FREQUENCY: Where applicable, once, prior to commencement of boring
| note | b8a8e238-9720-4cef-ba1b-1f3909b363fa | CATEGORY: WP
| note | 587f6a3c-ab31-4161-acea-2da5c8be4bf5 | RESPONSIBILITY: Nominated Authority
| note | 43e51645-7c7a-49a2-a4d9-8020f1fa2766 | VERIFYING DOCUMENTS: This ITP
| textbox | c09c95f4-1a5c-425e-8798-fb5342bc1212 | Date Completed:
| checkpoint |  | 3.5 Pre-qualified Pile Testing Consultant
| note | 0d43fa2e-5f28-48ba-b548-0db92534ca20 | REFERENCE: 606.07
| note | 81dd5f62-a956-4c50-827a-25bc475c10b9 | ACCEPTANCE CRITERIA: All testing shall be undertaken by a pre-qualified consultant who is independent of the piling contractor.
| note | 0890bb22-4f18-413f-90d4-87a122ffed15 | Details of the consultant to be submitted for review to the Nominated Authority.
| textbox | 227f626b-940f-4d4c-aa36-0c0942ec87d5 | Enter: Teambinder Approval number
| note | 4c47def2-30a5-4a71-b458-057aa0fd2878 | METHOD: Document Review
| note | ad46b37f-141e-480a-932f-7164956ce773 | FREQUENCY: Once, 2 weeks prior to testing.
| note | bb0b2718-bc6d-4999-9101-e1e59f54a547 | CATEGORY: HP
| note | b243003a-4bf2-419e-ba91-9a8cebcafffd | RESPONSIBILITY: Nominated Authority
| note | 49f78c7b-f45e-4ece-b523-602431269cdf | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | f5bd4621-d797-4753-8e9a-4c22078b498b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.6 Reinforcement Welding Specifications & Qualifications
| note | 5955aded-aa2c-4fd7-a16e-38d4b5c718c2 | REFERENCE: 611.13 (a)
| note | 31c8963d-b6e9-4dc0-bf56-2ea9a24a2132 | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
| note | da14b0ce-c2ef-4033-b2d1-e9cc0a3f3460 | 611.14 (b)
| note | d33b5f73-af4b-4895-9f53-059724cde021 | ACCEPTANCE CRITERIA: Welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
| textbox | bf8f9374-7902-4d6d-a596-38838adbcfa5 | Enter: Teambinder Approval number
| note | 0b1fcc3b-cac9-434f-9649-f5959fb2588d | Note: Tack welding requires the same documentation but is a Witness Point
| note | 34aeb02c-2839-433f-b067-c31413631832 | METHOD: Document Review
| note | 35d42990-7e8e-4241-88cb-016e2b840309 | FREQUENCY: Where applicable, once, prior to welding
| note | 6a39ae15-d3ad-4b45-bdf6-d92a2df9ce98 | CATEGORY: HP
| note | 3c5653f9-246c-4e41-8820-b74ad903fc21 | RESPONSIBILITY: Nominated Authority
| note | 9fea66d4-5ed7-4ee9-81dc-cf8ae9364d08 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 5c45b3f1-1ec7-49cc-ba76-fa18bb97cf47 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 IFC Drawings
| note | 9c36389e-1352-4066-9101-22e96c367653 | REFERENCE: MRPA Quality Management Plan
| note | 3ae1f1de-1289-4618-816d-0c50cf4b041e | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 9050de2e-976b-464a-952e-2fa15db9f077 | METHOD: Document Review
| note | 556eaaa3-2554-48fb-8c34-564b5f8f728e | FREQUENCY: Prior to starting Works and at regular intervals
| note | 8cd6fb0b-15a0-43d1-9bd2-cacb8be033f5 | CATEGORY: HP*
| note | 4b90e828-a7f5-4d07-ac00-2390efbc28d7 | RESPONSIBILITY: All
| note | 23700c95-d513-47fa-ac2c-ca0c33b15a55 | VERIFYING DOCUMENTS: This ITP
| textbox | 62ededde-084d-49c7-9a3d-bcec615ae80d | Date Completed:
| checkpoint |  | 4.2 Survey Set-out
| note | 26079e65-ebe4-46b2-9fd9-e4cd86890eef | REFERENCE: IFC Drawings
| note | 4917935a-7501-4deb-a5ac-4f7e55f653e6 | 606.08 (a - c)
| note | 767be317-6c1f-4439-b611-8b8db198134a | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
| note | 2e14f5f2-2efa-482f-bbdc-3493780895b3 | METHOD: Measure , Visual
| note | bf470ca6-a23f-4bf5-962d-cc358982661e | FREQUENCY: Each pile
| note | 7117abf6-b4e0-4e6d-a7ca-bd360e115821 | CATEGORY: IP
| note | e6b406be-ee0d-42b4-9f2e-e95d8cf9e816 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 0862efe0-1c58-48cf-bd58-80a20d348e0f | VERIFYING DOCUMENTS: This ITP
| textbox | bef9f503-6a13-42b3-9374-e5f08006861c | Date Completed:
| checkpoint |  | 4.3 Protection of Adjacent Piles
| note | 540d5c32-1d18-4dde-8489-3a73a1aa88af | REFERENCE: 606.04
| note | 2b034707-73e0-4366-9c7c-4641e3e6acb5 | ACCEPTANCE CRITERIA: Pile construction shall not:
| note | 94955b57-2bdd-4729-81fc-1ecae2be4237 | i. result in damage to adjacent newly cast piles due to ground vibration.
| note | 187e614e-811b-4eb3-8ead-65da18755250 | ii. commence within 2.5m from newly cast piles if that pile concrete strength <15MPa
| note | 0f8134ca-bfcf-484b-ae77-ad368a8f88d0 | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
| note | 5df84afb-1de8-45fb-96ea-5659d3012f60 | METHOD: Measure , Visual
| note | 9ecb4d55-e167-4095-9f5b-507c9f9e3e46 | FREQUENCY: Each pile
| note | 42c87503-b030-4f24-871d-cabc29fa5bda | CATEGORY: IP
| note | c66bf1fa-90eb-4a7f-b145-2f163d7fbaa7 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | c733a77b-76ba-4b61-b0c1-3a34b195b867 | VERIFYING DOCUMENTS: This ITP
| textbox | e33a60c7-bc89-4ec5-993e-9c97b937635f | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 5.1 Boring Operations
| note | d355debd-6d06-43b1-a445-d83edd0a6f6f | REFERENCE: IFC Drawings
| note | 462f8294-2907-4871-a4c8-dfe81ad756f7 | 606.03 (a)
| note | 42fb0309-dd66-4caa-a4e6-ce363244e8f3 | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
| note | ce3ea90f-9af7-4ec8-9242-1b3c149b1039 | Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
| note | b374faff-8fe6-4d0e-904d-55c450d70440 | Excavation clean and de-watered (where applicable) for inspection.
| note | 36ac9151-cc28-4da1-89d3-148a6fcbf6bb | Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
| note | ad5528b7-3a0d-4b8e-9cca-c156e253ae49 | Excavated material to be disposed of as appropriate to maintain a clean site.
| note | 493a6684-5db6-48f8-8aea-c67f10fc3591 | METHOD: Measure , Visual
| note | 9fae375a-04ee-4a4b-b461-c34fc7d6670f | FREQUENCY: Each pile
| note | 14c0356b-e89e-4007-bfa1-be97d122fc4b | CATEGORY: IP
| note | d7bb9d4b-1de5-4032-82e3-38a0da61ddd9 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 8ce85fa4-b57c-4272-97d6-1f709ca9cd73 | VERIFYING DOCUMENTS: This ITP
| textbox | a813f270-c714-4d3e-b3fa-f486f77a065b | Date Completed:
| checkpoint |  | 5.2 Formwork Extension
| note | 346b2d6f-e935-4328-be5e-c18ba177110f | REFERENCE: IFC Drawings
| note | 2259b2c5-b075-4fa5-b2ba-bf6d7ae11683 | ACCEPTANCE CRITERIA: Formwork / formatube shall be used to ensure the top of the pile is at the required RL.
| note | 07292885-bdde-4645-b9a2-c7342f9fa9a6 | METHOD: Measure , Visual
| note | 6a5d3a0a-4159-4f2a-a2c0-129daeb6121a | FREQUENCY: Where applicable, each pile
| note | abbbf0af-31a4-40c3-8ae8-3ec32a531371 | CATEGORY: IP
| note | d41f65e5-bf92-4270-957a-05a314e3d94b | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 02417a19-46ea-4d94-8e62-11880a0ff293 | VERIFYING DOCUMENTS: This ITP
| textbox | 1254a4e5-cb48-45fb-aa92-39e70b5fb3a4 | Date Completed:
| checkpoint |  | 5.3 Inspection of Pile Excavation
| note | cc75cfb7-6105-4ac4-af1e-e464729b6ebf | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
| note | 45473256-8ade-45c3-8099-ea2049785b44 | Attach: Geotechnical Field Sheet or Report
| note | 47ed4f2f-bc39-49e0-ab35-349834091101 | METHOD: Measure , Visual
| note | 618d7677-6895-428a-b231-23fbcae9f0ca | FREQUENCY: Each pile
| note | 52004d83-73da-428d-91ce-5d3114dbfadd | CATEGORY: HP
| note | 89e1d14e-8620-43c0-a57a-2a5f6771cd93 | RESPONSIBILITY: Geotechnical Engineer or Nominated Authority
| note | d54901fe-c35b-421d-874c-526e49e228d2 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 2746232b-8e4b-45de-a526-881b94d0d5ed | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4 Reinforcement Placement
| note | 71b14e95-40bd-4f97-996f-34ceeb9154f7 | REFERENCE: IFC Drawings
| note | 25f0c5f0-b576-44ea-a56b-f90b54eae64d | 611.06
| note | 78bad2c7-5649-4117-9cc2-da102b7a9565 | 611.09
| note | e021bca3-9a32-453f-858e-d175ef34357e | 611.1
| note | f4c9cecd-2e15-40d7-a23d-2b05da8120f2 | 611.11
| note | 1281ad5f-8a3a-466c-a7d6-45143c357da8 | 611.12
| note | 08776ec9-c63b-40a1-bd50-aca47c1d6298 | 606.06 (a)
| note | 2b8e3320-3221-4c30-aa8c-7e50bbc99a80 | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
| note | f3204cd4-d014-4218-8370-6914dd8916ae | Projecting reinforcement is the correct length and location.
| note | dd74d11a-b683-426a-8640-f0d9d6f4318d | Splice lengths achieve the minimum length and are in contact for this length.
| note | b2f82f66-19ea-4b99-95b4-f22f5bf1cf46 | The reinforcement surface condition is free from dirt, debris and damage.
| note | 1c2d8767-fc4c-499d-82c8-09996f9e0129 | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
| note | 0cd7763d-20cd-43b7-b3bf-49bc43e68892 | Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
| note | b362b690-23ef-4419-9350-1a2aa90e391b | METHOD: Measure , Visual
| note | a845bc51-fb5c-4e9e-b3a9-daccb53f0421 | FREQUENCY: Each pile
| note | 57f50ae8-5919-428f-b63c-fc49bcadfcaf | CATEGORY: IP
| note | 80ff74ba-5f2b-42e2-9d6a-cc05968e299e | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | a0be2fcc-b44d-4022-8551-145520c5dc5a | VERIFYING DOCUMENTS: This ITP
| textbox | 1ab9da27-6224-4c0e-882e-ae333e6f3324 | Date Completed:
| checkpoint |  | 5.5 Reinforcement - Electrical Continuity
| note | ccc1f00f-4fa2-4e89-aad0-c2bf9eefc567 | REFERENCE: IFC Drawings
| note | 1aaf8e9f-76b6-455a-9125-0b72fdce1919 | 610.29 (d)
| note | 6ae4c33b-8c3a-487d-aaf2-e2a7d575c04e | 610.43
| note | d2460355-73b7-4cdc-8529-512314e53e7f | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
| note | cf1a6bb9-22fa-4e38-9232-5bb6bcdce55f | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
| note | 010eb0f9-c529-4eab-985d-9a22dcd196e3 | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
| note | 93a07656-4a9d-4cd8-b291-142966bf7e58 | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
| note | 13db87a0-3f1f-40ab-8336-686c7c2015c2 | Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
| note | bd267533-0cd3-4c30-a24c-0e7a6a7a7909 | Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
| note | 8e1e4131-d5bb-4421-ab5b-79cd8f661580 | METHOD: Measure , Visual
| note | f5a99a1c-f6c6-4152-9ab0-0c39b5571c6c | FREQUENCY: Where applicable, each pile
| note | 96fa33d0-e1d3-41e5-872d-f7872799f576 | CATEGORY: IP
| note | ea88852b-4cbd-4822-b913-73598201458d | RESPONSIBILITY: Earthing Engineer , SE/PE/SPE
| note | b1c5c6d6-95dc-40c0-8567-359b8800e5a1 | VERIFYING DOCUMENTS: This ITP
| textbox | 92e2dd65-a779-443a-8ea2-4a0a608feb22 | Date Completed:
| checkpoint |  | 5.6 Cast-in Items
| note | ed8bc6c0-1f48-4dda-ada0-4eb40455c921 | REFERENCE: IFC Drawings
| note | ffea49de-4f88-47f4-be99-e8fdfdd9a891 | 610.46 (a),
| note | 31add246-549c-485a-a715-4f3206d10f8b | Table 610.462
| note | 0fa7adcd-426d-4dbc-8a1f-ae41e790511a | (November 2018)
| note | 3db702bb-db95-4d2d-b0fe-b6301bdfd30e | 610.47 (a)
| note | 85e1b5ec-0da6-499e-bb38-6b05efb7a862 | Table 610.472
| note | 2de9b2d7-fe0a-47b5-82d3-2a000c5cba50 | (March/June 2019)
| note | 95c03829-41c5-48f3-8959-27d764b4bf81 | AS3810.1 Table 3.3.6.2
| note | 1830946f-cbd9-4174-8f0b-fd213d4e9254 | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
| note | 8422249c-e56b-4c91-bd9e-49939f053080 | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
| note | a41cf4f7-700f-4ebc-b88e-7b84bfd39d1f | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
| note | f9ee1f70-7f63-439f-9a70-6b0a8bda1846 | Grout tubes shall be fastened at regular intervals to prevent kinking.
| note | 04c0c6c2-8f04-4d2e-944b-f5f54a067250 | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
| note | 1516bccb-b802-48ea-b231-50c36c7f05a6 | i. Bolts, ferrules, projecting bars & couplers = ±3mm
| note | 46c9141a-870c-45d7-9083-9b4292f946b3 | ii. Running dimensions of a group of the above = ±6mm
| note | 00b53d27-ee59-46ce-abc1-34a2388969e4 | iii. Ducts and conduit location = ±12mm
| note | 0e3bdcef-6e49-4c88-9586-aca508f5c85e | iv. Diameter of ducts and conduits = ±3mm
| note | 26db0fa5-2c6a-4913-a84e-92d14b4c5134 | METHOD: Measure , Visual
| note | 9de118d4-a9b5-4050-9fb3-36982779c706 | FREQUENCY: Where applicable, each pile
| note | f223a692-a801-407e-851b-d761fc1eb784 | CATEGORY: IP
| note | ca006fb2-9e51-4931-88d8-855979e42b24 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 1945d34c-cc80-4264-902b-24e46bc15957 | VERIFYING DOCUMENTS: This ITP
| textbox | a9fa28db-ee26-4fd1-b536-a068f34bd391 | Date Completed:
| checkpoint |  | 5.7 Pre-pour Inspection
| note | 86e6927f-6e97-4cb7-99b8-70c700b8f1c6 | REFERENCE: IFC Drawings
| note | 77b4797f-d0e4-4117-a752-8c3c9933ed46 | 610.18 (a) (ii) & (iii)
| note | e8512bf5-6628-457c-b893-ce8dccff2752 | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
| note | 073951d4-5685-4f4e-a11c-04e4d9d37a98 | All foreign material has been completely removed from the excavation.
| note | 9b743ca5-e8f3-4778-9f61-9f4e072e9fdc | METHOD: Measure , Visual
| note | 4c159898-7d35-460c-b533-12257f9c7cde | FREQUENCY: Each pile
| note | ae37dbe8-5de2-4712-b522-17c1b256753f | CATEGORY: HP
| note | f847d69e-0f05-4e64-885c-5798f3d1df51 | RESPONSIBILITY: Nominated Authority
| note | 5c8e2deb-97e3-4711-a5e9-cf5d4e933cf9 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | e8dd306e-bcd9-4c61-a166-7095d8a221e7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.8 Weather Conditions & Evaporation Limits
| note | 9fcbec9f-87e2-4d62-a634-d762d020dff9 | REFERENCE: Hot and/or Cold Weather Concreting Procedure
| note | 7e669203-0f8d-4144-b20c-2b3992c8d781 | 610.17
| note | 827b6c16-f8b9-4c0a-a495-e077e8469988 | 610.17 (a) & (e)
| note | e5418854-7263-4e37-b541-ca0f4056053f | Table 610.171
| note | e51a2295-6c92-407b-a220-c4cf98b60360 | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | 3b03f0f6-a25f-4830-850c-c1076e93c01b | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | 2aa68aa5-f20f-4c03-afcc-28fa95483836 | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
| note | 7bc5f9f9-f200-4770-8b7d-6e8ea66b5a1a | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
| note | 8687896c-dfe0-4b1e-9953-5bc3eae29a99 | Record: Required information on the Concrete Pour Record.
| note | 9a4e47fc-4043-46b0-b6d3-aa3d860bdf17 | METHOD: Measure , Visual
| note | 544bd278-7e07-420e-81ec-71374c3c972b | FREQUENCY: Each pile
| note | 6d793d04-4083-462f-8e8d-ebd418cb1ec9 | CATEGORY: IP
| note | 97770a42-5505-464d-ac6b-81e921dafe01 | RESPONSIBILITY: Foreman SE/PE/SPE
| note | 3d80672a-4d6a-44f7-9155-838d7c8f4b01 | VERIFYING DOCUMENTS: This ITP
| textbox | 8b0d8df3-d974-4f7a-8c1f-a424fad0a2d2 | Date Completed:
| checkpoint |  | 5.9 Concrete Testing - Sampling Frequency
| note | aed4fd7e-a2a5-42d9-b3fe-5ce32cdfb777 | REFERENCE: Site Sampling & Testing Procedure
| note | 37c021f0-91da-4de1-af51-74fe146285e8 | 610.16 (b)
| note | 9bb88dc9-3888-464f-8e6b-7efe22de2750 | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
| note | 534d9d70-fde3-4d0c-9ee9-ad4a384c9178 | 0m³ to 10m³ = 1 sample
| note | 3517b1ad-d0eb-4b94-b593-a96de732a53c | 10m³ to 25m³ = 2 samples
| note | 84a54d06-1e6a-40fe-8f7a-1aa6fb4500dd | 25m³ to 50m³ = 3 samples
| note | 2f02e9f2-af75-44c2-abd4-986cfa2a7298 | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
| note | 716f626d-dc21-420e-bcdd-e9a03dba4406 | For each additional 50m³ and additional sample shall be taken.
| note | 1df2c792-46f9-477a-9817-c8a50030798d | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
| note | 8ced28d7-f659-41a4-906e-2813c6a87773 | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
| note | 2e3b8962-b87c-4307-9d80-64c3567cff5a | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
| note | 6e0fc8df-22a0-418a-8378-3399690ce5da | Record: Required information on the Concrete Pour Record.
| note | af28b409-6ad8-47d5-af88-620037d90e6a | METHOD: Test
| note | d128a844-b3b8-4d08-9ab6-2d2c909613ef | FREQUENCY: Each pile
| note | 2c6dfc07-3656-4ff0-8885-08e5802b721c | CATEGORY: IP
| note | a2729b5f-e521-456d-8fbe-f9c18a215ab7 | RESPONSIBILITY: Concrete Tester , Foreman , SE/PE/SPE
| note | 7d55990d-d7c1-4f7e-a6f5-d238eb6e06f4 | VERIFYING DOCUMENTS: This ITP
| textbox | 8771d094-3029-48bb-99e4-0e8ee70ff06f | Date Completed:
| checkpoint |  | 5.10 Concrete Testing - Spread, Passability & Viscosity
| note | 8242c765-47f0-4c1b-a935-60071aa79df1 | REFERENCE: 610.13 (b)
| note | b40f879b-6c47-45bf-ad6e-311c03b949a1 | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
| note | 18667b6a-3085-42e4-84b2-99adb3f2f6e7 | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
| note | 4e88553c-b40a-4ec2-8b26-e9e8fa301726 | Passability = ≤10mm (aggregate height differential)
| note | a5149ff7-fcc9-4a2d-bcd2-5e0dd556b1e4 | Record: Required information on the Concrete Pour Record.
| note | 8b7be3f1-a470-48ab-a74c-a188363d316b | METHOD: Test
| note | a4d6a3dc-e7e2-4fef-9833-47275b6fabf9 | FREQUENCY: Each sample of Self-compacting Concrete
| note | ee93777a-de0b-40a1-bef3-7cd76bdd610c | CATEGORY: IP
| note | 05910495-e279-4eeb-9497-ac7e11ee3bcc | RESPONSIBILITY: Concrete Tester
| note | 0248413b-639f-4e50-801a-205fe9106f32 | VERIFYING DOCUMENTS: This ITP
| textbox | 9c3b31e9-f995-4592-8cbe-c60276e172a2 | Date Completed:
| checkpoint |  | 5.11 Concrete Testing - Compressive Strength Cylinders
| note | 18bcafb3-bc6e-48a9-9e5a-8f734ee055ef | REFERENCE: Site Sampling & Testing Procedure
| note | 50c78106-f907-44a1-8e3d-231550facf1f | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
| note | 3b53502b-c81d-4874-bcb8-7575f503793a | Record: Required information on the Concrete Pour Record.
| note | b436c4fb-b2c4-478c-837f-fd1815fd9809 | METHOD: Test
| note | 4bda72bd-5a29-4c4a-81ad-e5a9bde7d8b9 | FREQUENCY: Each sample
| note | ad174912-54c4-4e71-b7b4-8cc8e06b3305 | CATEGORY: IP
| note | 1feeaa91-9d79-46f5-8a0a-32b2943d086b | RESPONSIBILITY: Concrete Tester
| note | 8a48747a-4d4d-4d7f-a690-ff0672e0d3fd | VERIFYING DOCUMENTS: This ITP
| textbox | 29f003bb-187c-42ab-b971-cbc8f23d47dd | Date Completed:
| checkpoint |  | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
| note | d0a19141-78a1-40a9-9dd5-75f5257ca9e9 | REFERENCE: Piling Quality Procedure
| note | 2f8d7ac1-7e14-4d16-9a25-83fa04d3e7bb | 610.18 (a) & (b)
| note | fa4e0bf3-a5b7-4910-9be0-6631d71bfec5 | 610.18 (d) (i)
| note | 02282a33-74ba-4e6a-9bb4-ffe214334ecd | 606.06 (a & b)
| note | ba133e4c-d383-4b82-8c8b-31e5dea00f8a | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
| note | d356ea67-58c3-4533-a38d-9a40e6b4e242 | All concrete batches are traceable.
| note | 07ffcd86-4d4b-4a54-bb4a-9a0e86a26bed | Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
| note | 5192554b-1c6a-4f37-b457-1fd8f216051a | The initial discharge is pumped to waste until a consistent workable mix is discharged.
| note | edb073d1-c4e3-4922-9db7-06538e82d079 | When placing under water, the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
| note | cc59c8ed-8c0f-4be2-a67a-79084305aa72 | Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
| note | 4e509859-7ff6-493b-be70-e58d3733eb09 | Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
| note | a6ce56b7-3cfa-4235-8dfd-14190cbe64dc | Record: Required information on the Concrete Pour Record.
| note | 9bd6a195-da5e-4e59-a682-ee494c9f7d0b | Attach: Concrete Pour Record
| note | 316cba6e-5f22-4517-9bf4-cc9d30adf330 | Attach: Concrete Dockets
| note | 4e413dd8-c85b-4ae9-906b-02eff82bfab5 | METHOD: Visual
| note | c0554a7b-9ffd-4a99-8301-421129c30391 | FREQUENCY: Each load
| note | 3232964e-1b08-46ad-a00e-78c79a59e8ea | CATEGORY: SP
| note | 323f57de-9114-4238-afd1-eea2d9d04a1d | RESPONSIBILITY: Foreman SE/PE/SPE
| textbox | 8be32d35-6720-4d37-8e12-5fe2a8b570e1 | Date Completed:
| checkpoint |  | 5.13 Surface Finishes
| note | 0c9d1af0-9e84-40a2-bd15-1766973cc26e | REFERENCE: IFC Drawings
| note | f2e9d32d-6bf1-4fca-b156-72de75c340d7 | 610.31
| note | a9989a81-3a32-49ee-a2a2-82840c1e7dcc | 610.2
| note | 2edb9aa1-14ac-4e8c-8be7-88b8a8fa4261 | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
| note | 8d90467d-6307-483a-a10f-984b7ce8f869 | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
| note | b1a247d6-e862-4ce4-afd9-a2721e658bb6 | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
| note | c25dbaeb-de9b-4c31-9b78-c5fc9902f9f1 | METHOD: Visual
| note | 0df24f97-2068-423e-84b5-2500a43c20fc | FREQUENCY: Each pile
| note | 11378023-0504-4c19-9db4-68b811eca820 | CATEGORY: IP
| note | bdfe9b2f-e87b-407d-9dfa-ccfffdbf45a4 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | f5c28fa5-9746-4d4c-80b2-7dab9d967bcb | VERIFYING DOCUMENTS: This ITP
| textbox | 498876a6-c2f3-4e2c-b546-6d458ea7930b | Date Completed:
| checkpoint |  | 5.14 Curing
| note | 369a8af6-070f-447f-b1e7-dd2894a690db | REFERENCE: Curing Methodology
| note | 2efa23b1-b9be-469b-95e7-a49317cc0c2e | 610.23
| note | 44452c3e-359a-4381-bfee-b499a9a768b4 | Table 610.231
| note | 2590d6ec-820c-4584-81a0-fe9a028eadda | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
| note | ef077aa7-109f-43d1-bf79-dce12e42b35a | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | 53b0ec4b-b84e-474c-a010-0ed8aff9bc38 | METHOD: Visual
| note | 70652a10-83ec-4ea5-9710-2e40990060a2 | FREQUENCY: Each pile
| note | f87f6fce-f0bb-4969-98df-018ad44e343c | CATEGORY: SP
| note | 262df353-bdb4-482b-81ee-7adf0673804c | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | f3f2846e-4053-4df8-83b9-b464cf491023 | VERIFYING DOCUMENTS: This ITP
| textbox | 55e29f98-4a4f-4f87-944d-a2675153d962 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Compressive Strength Test Results
| note | bdc74fa5-4df7-49db-803e-879973fc6c64 | REFERENCE: IFC Drawings
| note | 38e4c2f6-5a7c-4cc1-8884-a91dd91068d7 | Table 610.05.051
| note | 0fdc5da2-a1c7-4745-8e52-901acc86da63 | 610.16 (g)
| note | 0cfecad9-872e-4e2b-996e-8db0f08ee2be | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
| note | 2aabfac3-a632-4310-b2a0-ce6454ee9156 | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
| note | b49aab90-4cab-46b8-9c74-af4dba7514a1 | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
| note | a354e858-ba26-4864-9fbe-2ec6b1bb8791 | Attach: Compressive Strength Test Results
| note | 1226c65d-0b03-404f-b3ca-429514a4ad53 | METHOD: Document Review
| note | 79319f69-7419-4ebf-9234-5126dca37cb0 | FREQUENCY: Each cylinder
| note | f82a0289-8fc2-4dae-bb01-8154e12d44fb | CATEGORY: IP
| note | 7fed2ff9-c04d-468e-b5fe-625043cae85a | RESPONSIBILITY: SE/PE/SPE
| note | f0bebb9d-5fef-41de-97a2-7a92282ac887 | VERIFYING DOCUMENTS: This ITP
| textbox | 095ecf42-2b25-4bd7-bf37-d38ec6672451 | Date Completed:
| checkpoint |  | 6.2 Pile Integrity Testing
| note | e061f2ae-9969-4915-af5c-9b0ef9266ead | REFERENCE: 606.07 (a, d & e)
| note | 91111c25-5238-495f-a279-e261ef3b0644 | AS2159 Clause 8.8
| note | 1fbe3b1d-2951-4ac4-b5a4-fa461420731c | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
| note | bf8319c3-e5e3-43ac-bcd0-c5451fc057fc | Cross-sectional area = ≥95%
| note | d7297512-286f-46ed-9cfd-d4a81adba560 | If any test fails, all piles shall be tested.
| note | 779ee0d5-00c8-4987-92c3-928fa1a70d9a | Attach: Pile Integrity Test Report
| note | 1e27c7c9-b9cf-46e6-be52-90d601cc9c5c | METHOD: Document Review
| note | 8f1e35db-827d-4107-a76f-1b2390a88991 | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
| note | c4cc91ec-01be-4f36-b44e-a4fc5e230af5 | CATEGORY: IP
| note | 50b3ba0e-aa6f-4602-8033-658217f5decc | RESPONSIBILITY: Testing Consultant , SE/PE/SPE
| note | 2a208de5-8643-4d79-9657-b2bf87f26723 | VERIFYING DOCUMENTS: This ITP
| textbox | 07e0b182-9439-4303-81bf-192bb036e8c8 | Date Completed:
| checkpoint |  | 6.3 As-built Survey
| note | a5053fe3-c7d8-4701-bab1-f04274b108a2 | REFERENCE: IFC Drawings
| note | b86fef4a-276f-4843-be09-85c05145cd1b | 606.08 (a - c)
| note | 1f2c27bd-9f49-4253-ae7a-34bcf9070a0b | AS2159 Clause 7.2.2
| note | 50936434-812c-4d7d-89f3-37103fa69fae | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
| note | 88c6a7cd-d4f0-47bd-9a6a-d11ca9b8dd05 | i. Pile head plan location = ±75mm
| note | f102db9f-6da5-4b4a-aaaf-4c39d5fa52ba | ii. Variance from vertical or rake = 1:100
| note | a6342a05-6327-4dcf-a046-a5d412110462 | iii. Irregularities in straightness = 1:100
| note | d74ca588-e983-4350-a92f-d082e33982db | iv. RL = ±25mm
| note | 7269a9ee-c935-4dec-8863-00ca139c62b8 | Attach: Survey As-builts / Survey Report
| note | b040062b-37f4-45e3-b5a0-986009997430 | METHOD: Document Review
| note | 714eae9a-59b5-4dff-80f6-9065a6645542 | FREQUENCY: Each pile
| note | f784de7e-b8fc-4288-b3a4-c868507b82da | CATEGORY: IP
| note | 79e4833e-21f1-4b3a-86a9-3f63e708ca1b | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 671cb36a-0d65-4aab-ace1-0b52681a7379 | VERIFYING DOCUMENTS: This ITP
| textbox | 7fa558f1-61fa-41a7-bd4a-1a0ad365caaa | Date Completed:
| checkpoint |  | 6.4 Non-conformance Report (NCR) Closure
| note | 2ecd26ec-6417-4d03-8806-4c28f6051ffb | REFERENCE: MRPA Quality Management Plan
| note | 1a585a2c-d3ff-4a3a-9bf7-d6bcdd0f8d8a | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 5dffc051-9954-4ed7-9d0d-69f978869cc0 | METHOD: Document Review
| note | cab74a96-c952-4a6e-8b26-c2c58c711739 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | fb2ef58e-d9a6-4e43-be8f-348ac077010e | CATEGORY: HP*
| note | 866bb310-b692-4a46-a7db-ac52d4baea26 | RESPONSIBILITY: SE/PE/SPE
| note | aec83d30-0d6a-4935-8c38-d8c5897da9cd | VERIFYING DOCUMENTS: This ITP
| textbox | 53d1602b-bf63-4a23-bb42-0eaab6306222 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 42d40b0c-b834-4d2e-9cde-dd78aa2fa60b | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | a4c197e7-151e-4533-8407-74a36e6b91da | Name:
| textbox | 37a8f2da-1f69-4302-a2e1-350b989b0d48 | Position:
| textbox | f1020d27-6b7c-4f6e-8797-f1043a9ff2cf | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Drainage Pit Waterproofing Rev 0 | itp | ITP-CIV-Drainage Pit Waterproofing Rev 0 | 7afce2d9-5dff-4341-b4a7-cb005b2b571c
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 1c91d19f-09a1-53be-a71b-f4eea88744f6 | Document Title: ITP-CIV-Drainage Pit Waterproofing
| note | 4ce200b9-c2d3-5319-aa9d-3a4b328bda59 | ITP Description: Drainage Pit Waterproofing
| note | a2a2a786-4ece-599c-b991-b282613375da | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 2e7902a8-85d0-5539-84d1-7ce108a63d5b | Revision Number: 0
| note | 6a5c09eb-5fee-5c67-89a5-956d405b14ad | Revision Date: 7/04/20
| note | 137b0bf8-b0ef-5759-b821-4e587d03c616 | ITP created by: Brigette Rizzato
| note | 1be017e3-0ea1-5710-b909-e3efdfa20d40 | ITP approved for use by: Romualdo Magpantay
| note | 8401a32b-4634-5bd4-9e13-69d10330a07d | 1.1 IFC Drawing MRP 072 C AUR DRG 32 DPK CBR 0082
| section |  | Preliminaries - Material Conformance
| checkpoint |  | 2.1 Materials, Waterproofing systems shall be used in accordance with the manufacturer’s recommendations and materials Technical data data sheets( . Hydropfillic Strip,Dry pack grout ,- Calking Sealant, membrane)
| note | 2157e50e-0600-55b1-b135-2f957ec576a1 | REFERENCE: IFC drawings
| note | 7f445920-03bb-590f-b206-52e692b7800e | ACCEPTANCE CRITERIA: Normnet Product: Tamseal B
| note | 0a894163-c5fa-5880-a45e-442f6a4e2103 | METHOD: Document Review
| note | a6d50609-58bb-5f94-9c26-a069ffe00d78 | FREQUENCY: Once prior of commencement of work
| note | 8b38700d-12b7-5815-8c25-f19233440008 | CATEGORY: HP*
| note | 13179cbd-a30d-5fec-884f-7fcaf2cbd6cc | RESPONSIBILITY: SE/PE, Nominated Authority
| note | b172b14c-e395-5a58-8dd1-73f4d1c0a687 | VERIFYING DOCUMENTS: Material and Surface Procedures, ConQA Hold Point Release
| textbox | 25d0f50b-1291-5fca-ba86-db968dfdefd8 | Date Completed:
| checkpoint |  | 2.6 Inspection of delivered waterproofing materials on site
| note | 21628641-b25d-5fc9-9515-0816eb242969 | REFERENCE: IFC Drawings
| note | 72c25fed-e011-5535-884a-9b47d1457b40 | ACCEPTANCE CRITERIA: Materials not damaged during transport or handling and meets specifications
| note | 99e3ad08-00fd-520f-abce-a2ca653aac22 | METHOD: Visual Inspection
| note | 70a25a60-3c37-5f67-b2f9-1804bc88cf72 | FREQUENCY: Once, prior to commencement of works per delivery to site
| note | fe00958b-fe66-5c96-ab86-c9975b5a650d | CATEGORY: IP
| note | c9680b36-03b5-5bbf-b1d3-33a9e1ad1c81 | RESPONSIBILITY: SE/PE
| note | dd822539-6060-5eb4-8803-5f844ca6a085 | VERIFYING DOCUMENTS: This ITP Checklist
| textbox | 26cb59ff-6234-5c21-891d-57b9fb4a568b | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Inspection of substrate
| note | 31d43402-c7fb-55e1-9a6d-5508ccf90e01 | REFERENCE: Product recommendation requirements
| note | 04f76e75-0313-52fa-8db6-31b529969d0d | IFC Drawing
| note | 73fe2454-8362-5501-a372-6787f9c0b853 | ACCEPTANCE CRITERIA: Normnet Representative signs of on Normnet Quality Control Inspection Checklist "1.Substrate HP TS10GM" and uploaded to this ITP.
| note | 29d66917-bef9-54c4-8609-e4f6fc3c4cf0 | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | 97d43e92-51de-5c04-a48d-27c8e4861c16 | a) Concrete substrate is clean, dry and free of dust and other deleterious material. Min 25MPa Comp./ 0.5MPa Tensile
| note | 6a74bfdc-b16b-5c66-b92c-e33ce96d6af2 | b) Substrate has no active water ingress
| note | c1d0826b-70e8-5444-9d80-ebe0051f57c5 | c) Any mechanical fixings, starter bars, are clean and free of visible rust and oils that can inhibit bond. SA-2. Interface is level with main substrate.
| note | 2e8d24eb-250d-541a-893e-d847a623626d | d) Surface profile is suitable for optimal consumption rates.
| note | bf3288be-a94b-5edf-9ad2-11f4d853c50e | e) Damages, voids, holes greater than 10mm are filled with appropriate mortar.
| note | 4516d25a-283d-5bad-8d9b-5127dbd774d0 | f) Any temporary fixings are removed and repaired, or cut back flush without projection.
| note | f38c7db4-59a3-5e61-96c0-2bd172db0594 | g) Active water is controlled with drainage sheet and cementitious overlay, if applicable.
| note | 58c30119-d36c-5d9d-bca5-27f6ce36caac | h) Ground Anchors are appropriately protected, if permanent, strands are neat and treated.
| note | f53cad83-d416-56ec-92e7-f80d145d964b | METHOD: Visual
| note | 5d62ff68-a739-5823-b292-08eb66ba9fd3 | FREQUENCY: Each element
| note | 83861ca1-ea6b-5a13-b7bb-7647631e4526 | CATEGORY: HP
| note | a09ab69c-b7e2-58de-bb92-439dbb0568ad | RESPONSIBILITY: Package Manager SE/PE
| note | a9ca827e-f95a-5ee7-b5f7-4b1151033d7b | VERIFYING DOCUMENTS: This ITP Checklist
| textbox | cfd5d703-faa3-5a56-b304-879af5fc6f9f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Install 2 coats System of TamSeal 10GM for 2.5mm DFT to Pit outer concrete surface (min 48 hours cure prior to lifting into place.)
| note | 0b6d9bf6-53cd-53fc-b765-427847740a27 | REFERENCE: IFC Drawings
| note | 40a0d31a-82ed-551a-ae0d-2c6369a6215a | ACCEPTANCE CRITERIA: Normnet Representative signs of on Normnet Quality Control Inspection "membrane instal/HP TS10GSM" and uploaded to this ITP.
| note | 2bd1ff80-0a21-5acf-8599-53780487652d | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | 544f924b-c408-500c-b7d4-6ce3f308e0ee | a) Wet Spray machine is appropriate and calibrated for task.
| note | 34e87902-7185-5049-9a78-d0e7e0ba4659 | b) Lead applicator is trained and approved to spray material.
| note | 648ab5a2-2967-5fd0-85f6-fe87e86bcbc5 | c) Surrounding sensitive surfaces and areas are protected to mitigate overspray.
| note | 2adb501f-99c3-5237-8f7e-34cbe0937f34 | d) Wet film gauges and QA recording sheet ready. 10 tests per 100m2
| note | f13f812a-5cbd-5a5a-9dac-1ea09703fd94 | e) Wind protection is used when airflow >5m per second.
| note | 6646daad-4588-577e-ad1c-c5911f04159b | f) Consumption markings are in place and checked against target consumption
| note | f014f66d-7d57-59d2-ab9c-6bdf68c5c108 | g) All active water ingress is controlled and or in sublayers.
| note | b500be8f-d3fd-5258-b680-f575a5c4d597 | h) Areas to be sprayed are protected from sun, to reduce outgassing effects. Do flash coat/prime at end of day if likely to operate in direct sun conditions.
| note | 5f31f87f-a53c-564f-a38e-b981987b69ad | i) Trial area established for nozzle and feed system dose rates check.
| note | 991fe242-4b7b-5fea-a1a4-543d59921b54 | j) Applied membrane is homogenous without holidays, gaps or runs. Overlap zones are minimum 200mm.
| note | 47286161-73ca-5847-89d6-970b2b3a2c80 | METHOD: Visual, IP
| note | e248bba2-75b4-5e97-bfc8-76c8d9e8f710 | FREQUENCY: Each element
| note | 70d4e254-7f33-5aa3-8887-d8160ac4ccbf | CATEGORY: HP
| note | 7121700d-7b28-5496-9984-74918b17cfe8 | RESPONSIBILITY: Package Manager SE/PE
| note | 8489094e-653d-53e1-b8e5-b80b53c554ef | VERIFYING DOCUMENTS: This ITP
| textbox | 881d2160-a0ac-580e-b2c6-81f0ef6e2ef6 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction / Installation Activities - Pits
| checkpoint |  | 4.1 Secondary Waterproofing measure
| note | db276d20-103d-5efc-af46-e1e192c18d1e | REFERENCE: Product recommendation requirements
| note | f543e104-b04c-5886-aea4-d3a5fc2db0af | IFC Drawing
| note | 6bc16cd4-4225-5110-94e9-f27c86232956 | ACCEPTANCE CRITERIA: Install Waterproofed Precast Pit into preplaced Geotextile cushion layer >500GSM & PE Slip Sheet .
| note | 9f29aa33-4ead-5bfa-8679-98219b0a793c | PE Slip Sheet to completely wrap the entire pit substrate.
| note | c6fefa23-2e87-5792-a987-c4ca0c0f6b92 | GeoTextile to completely wrap the entire pit substrate.
| note | 2dc1cfea-16c1-5b5b-bad3-a2887dad8322 | Note, geotextile to be installed after PE Slip Sheet
| note | 093c14d2-1ee6-5e51-85d5-0a6dc62a157c | METHOD: Visual, IP
| note | 6758b8bf-9598-52e9-896d-c74671b598cd | FREQUENCY: Each Element
| note | 35c95836-b417-5b99-a465-f3e01e8cdff4 | CATEGORY: WP
| note | 3a4b632a-2e0f-53dd-a7d5-fbf66d32ae14 | RESPONSIBILITY: Package Manager SE/PE
| note | 3b6b6ac2-0fe2-53e3-a2d2-f37fd4fa885b | VERIFYING DOCUMENTS: This ITP
| textbox | 5ab137e4-d796-5cfa-a6d4-c3212f3e3b55 | Date Completed:
| checkpoint |  | 4.1 Secondary Waterproofing measure
| note | 90d6a42e-b2d6-5611-b7ab-92081c46e46a | REFERENCE: Product recommendation requirements
| note | f7449766-97ee-5d41-8b0a-f9b1060802a2 | IFC Drawing
| note | fd58a266-c3f2-59c2-8c30-9b8b0c57297c | ACCEPTANCE CRITERIA: Wrap PE Sheet and Geotextile Cushion layer up and secure with speed tape.
| note | 4c88e46f-4917-54ff-b919-a8f9a8a8d3ab | Tape applied should be enough to hold the Geofabric in place for the purposes of finalising construction activities.
| note | 9c68762c-d4ea-5a59-b846-d07adb1b47f7 | METHOD: Visual, IP
| note | 74c239ee-e10d-5757-9764-f17c630c1f36 | FREQUENCY: Each Element
| note | 4ea3aec0-806a-59b1-9fe9-d9675f74f874 | CATEGORY: WP
| note | 569731b0-bb44-5170-acce-9a66835dc44f | RESPONSIBILITY: Package Manager SE/PE
| note | db8fa13b-1529-54d7-84a8-9817a2ca6dd1 | VERIFYING DOCUMENTS: This ITP
| textbox | 6856faee-ade0-524a-b312-45f4dbfacd34 | Date Completed:
| section |  | Construction / Installation Activities - Pit to Pipe Connection
| checkpoint |  | 5.1 Pipe-to-pit Preparation
| note | 545843bd-079d-50a6-b0f2-bff60e6a8d23 | REFERENCE: Product recommendation requirements
| note | 3c45d16b-e1bf-5b01-ab57-7ad5f7554beb | IFC Drawing
| note | 90cc493e-d8b7-5c0b-a5a4-9b1084982e4c | ACCEPTANCE CRITERIA: 1. At each Pit Penetration, Cut/slice a Cross at pipe penetration and peel Geofabric and PE sheet Back.
| note | ea290efc-91d2-5444-9cd9-d430ce96c3f5 | 2. Inspect roughness/cohesion of penetration. Brush off any loose material. Where required, apply a contact adhesive around penetration to incease stickiness to temporarily secure hydrophilic strip.
| note | 94db3f29-8efb-5844-b146-78a449d2376b | 3. Apply First Seal around the penetration of Tamseal BR (hydophilic strip) with at least 3cm over lap.
| note | b4752867-3918-52c9-bc6a-a42a01b84d19 | METHOD: Visual, IP
| note | 5b18d2a0-df01-5414-9326-a528c64947a1 | FREQUENCY: Each Element
| note | f883b73b-5745-583a-a762-e8132c2ce202 | CATEGORY: WP
| note | 7239de00-62ae-56fc-9e4e-514c2a2fe82f | RESPONSIBILITY: Package Manager SE/PE
| note | 8aa7c4ce-8dcd-5440-a82f-98def653abdb | VERIFYING DOCUMENTS: This ITP
| textbox | 738e45a2-6c23-5cc8-bd6c-2a8929f401fc | Date Completed:
| checkpoint |  | 5.2 Pipe-to-pit Installation
| note | 7fdfcd9b-367c-505b-a73e-f091093f1782 | REFERENCE: Product recommendation requirements
| note | b2d7b7ec-7019-5dec-b979-dd965d962bcf | IFC Drawing
| note | cfcec81d-a96b-506e-ae0b-442a3ce4a66a | ACCEPTANCE CRITERIA: 1. Inspect roughness/cohesion of pipe outer surface for pipe length that resides;
| note | 7aaaa4b1-6f05-597a-93ad-93178ddc928a | a) inside of pit
| note | 03838367-fdca-51b4-9663-d5b1fe8d14d3 | b) last 100mm (minimum) from the outer edge pit. Where roughness is not achieved cup grind pipe to scuff and ensure bond occurs.
| note | 80010c90-d06f-5a72-9995-977c40f469e6 | 2. Clean any loose debris from pipe and apply Second Seal around pipe of Tamseal BR (hydrophilic Strip) with at least 3cm overlap. Then install Pipe into Pit.
| note | a3c82c87-d847-5435-ae3b-9d0289c8c867 | 3.Dry pack grout >50MPa Grout.
| note | 43c29d01-96a4-5402-a244-8590c57562e9 | Pack uniformly from one side against firmly secured backing board, ensuring full tamping for homogenous consolidation
| note | 72bbf8a5-1d7f-5d36-909e-0e60a91e1eaa | METHOD: Visual, IP
| note | cb10ae4f-7ef5-5840-911f-a8281a905473 | FREQUENCY: Each Element
| note | baca4d7c-0b45-59bb-bf0c-8062d33b7140 | CATEGORY: WP
| note | 01f73622-153c-50e7-8f05-6c63a6bbd6f9 | RESPONSIBILITY: Package Manager SE/PE
| note | 2d0b00eb-3109-5751-95a6-a40de83bc5ba | VERIFYING DOCUMENTS: This ITP
| textbox | 18a4c870-a1de-550c-92ac-eb305bf83ee8 | Date Completed:
| checkpoint |  | 5.3 Pit-to-pipe Waterproofing
| note | ac7fce1f-e6ab-54cf-b53c-183dd4fecf59 | REFERENCE: IFC Drawings
| note | d3193ff9-da79-5f23-8d43-5e75b3e8e3b2 | ACCEPTANCE CRITERIA: 1. Clean Existing membrane of any loose debris and if required scuff pit waterproofing membrane for adhesion.
| note | 7c08ba8e-7c86-5a87-a03a-94e1a4a9c3ba | 2. Caulking Sealant applied at join to create bevelled edge between pipe to pit around circumference.
| note | 7cfc5eeb-f20b-59ec-8839-57b78bf54985 | 3.Apply Tamseal 10GM, with minimum 100mm overlap on pipe and pit.
| note | d3a8b61e-cf76-51d8-a31d-97da3afbc231 | METHOD: Visual, IP
| note | 6b9b322a-4048-53a6-9182-e92e417a2e46 | FREQUENCY: Each Element
| note | b8d3372f-598f-50f8-9802-25af81442b3b | CATEGORY: HP
| note | 11c5cd72-3c27-573a-b74d-e422a773c6f6 | RESPONSIBILITY: Package Manager, . Normnet representative
| note | bb31bcc6-f70c-5375-9967-b15f7e769c69 | VERIFYING DOCUMENTS: This ITP
| textbox | 46f16907-79cc-50fa-89c1-7040a9206fe8 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction / Installation Activities - Riser
| checkpoint |  | 6.1 Riser Installation(if required)
| note | 5d30ea4b-3626-5898-b945-265b4964278e | REFERENCE: Product recommendation requirements
| note | b86b3510-5cb8-5c7c-bdda-9e0dcf195f5d | IFC Drawing
| note | 60c0c138-76bf-56b4-8b53-07c182c98cad | ACCEPTANCE CRITERIA: 1. Drill 16mm holes for N12 150mm embedment into shft wall and grout with approved high strgth epoxy. Maximum N12 spacing 200mm; follow Auspits reinforcement design.
| note | ec2be409-5088-59fa-9af4-0d0a0504b676 | 2. Form wall 150mm thick at final level.
| note | e1e6a99a-f680-5a1b-9bda-ceaf06513040 | 3. Apply Tamseal BR (hydrophilc strip).
| note | c60e05de-a27c-5f02-8b58-063d49a63d05 | 4. Pour 50Mpa Concrete
| note | d3d63179-39d5-5e33-9b0a-f10dec571414 | METHOD: Visual
| note | f53d67cb-3b19-5bed-ae01-60a182ac975f | FREQUENCY: Each element
| note | d972854c-b8ea-52be-8f39-49db6ef20141 | CATEGORY: WP
| note | cd1c22e3-d832-5926-a848-9183bff6d251 | RESPONSIBILITY: SE/PE
| note | 20f16382-29c4-54b7-ac8d-e4271fdbb1cf | VERIFYING DOCUMENTS: This ITP
| textbox | 45f9cc71-207d-5c04-a06e-140ab4189cfd | Date Completed:
| checkpoint |  | Riser Installation - Inspection of substrate (if required)
| note | 23f975ba-f117-59d3-9673-ae027ef8f313 | REFERENCE: Product recommendation requirements
| note | fdbd0413-6437-546e-99fa-a8006174fb50 | IFC Drawing
| note | 6f16ada9-8273-5e94-91c7-895debec641f | ACCEPTANCE CRITERIA: Normnet Representative signs of on Normnet Quality Control Inspection Checklist "1.Substrate HP TS10GM" and uploaded to this ITP.
| note | 107f80bc-0d1f-50bf-a38c-ca7323365c7e | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | 69fbff17-a378-5d77-bee8-fea3505b3853 | a) Concrete substrate is clean, dry and free of dust and other deleterious material. Min 25MPa Comp./ 0.5MPa Tensile
| note | 85073b4d-d523-5d66-9eb4-c9b554086cd2 | b) Substrate has no active water ingress
| note | b3720b69-8962-52df-8132-a2b32090b625 | c) Any mechanical fixings, starter bars, are clean and free of visible rust and oils that can inhibit bond. SA-2. Interface is level with main substrate.
| note | b275d10a-2a88-5303-8d73-ec20383b3fa7 | d) Surface profile is suitable for optimal consumption rates.
| note | 8d30493a-aa5e-51ec-b21e-22c40510f5cf | e) Damages, voids, holes greater than 10mm are filled with appropriate mortar.
| note | 2a8d66c2-aab2-5042-b326-c62b28f60420 | f) Any temporary fixings are removed and repaired, or cut back flush without projection.
| note | f31dce46-6545-540f-8c21-d025e8f431c6 | g) Active water is controlled with drainage sheet and cementitious overlay, if applicable.
| note | f2aabeb0-aff5-511f-926d-cc5f4aeec0a7 | h) Ground Anchors are appropriately protected, if permanent, strands are neat and treated.
| note | 108c2934-38f0-51d5-8444-004be8d7c94b | METHOD: Visual
| note | 4fea5666-d4f5-58e7-9d5c-bfa8305eb989 | FREQUENCY: Each element
| note | e33ad9f1-5932-51f1-9187-280599df43cc | CATEGORY: WP
| note | f340b8a5-bbb6-51e7-84b2-2a04f9d7bb49 | RESPONSIBILITY: SE/PE
| note | f08b3e8d-3aff-59eb-88fa-09ddd3891bc3 | VERIFYING DOCUMENTS: This ITP
| textbox | 173a438e-dcb7-561e-aead-e3517f9746bc | Date Completed:
| checkpoint |  | Install 2 coats System of TamSeal 10GM for 2.5mm DFT to Pit outer concrete surface.
| note | 600032dd-ce0b-58e8-8196-03018efbf9a4 | REFERENCE: IFC Drawings
| note | 66624ecc-75c9-5c12-93fa-01dd82e4f7df | ACCEPTANCE CRITERIA: Normnet Representative signs of on Normnet Quality Control Inspection "membrane instal/HP TS10GSM" and uploaded to this ITP.
| note | e32e4a20-4642-50fb-a483-a842b699e55e | Normnet Quality Control Inspection Checklist acceptance addresses:
| note | 0cae1e52-7ebb-5b81-8d87-a39f995bcac2 | a) Wet Spray machine is appropriate and calibrated for task.
| note | 5e5c5790-62e2-5fb1-9ae8-3134975d77a7 | b) Lead applicator is trained and approved to spray material.
| note | a28be096-4523-5a6f-8411-3563e374bee7 | c) Surrounding sensitive surfaces and areas are protected to mitigate overspray.
| note | 2b85054a-d29e-5308-9ad2-15954cb3f6fe | d) Wet film gauges and QA recording sheet ready. 10 tests per 100m2
| note | 86cd45ca-9e07-5f27-8ccb-47051760b26b | e) Wind protection is used when airflow >5m per second.
| note | 3ff8b7e2-14c9-5aa4-a431-21789b38fb6a | f) Consumption markings are in place and checked against target consumption
| note | d9bc38ca-2f5d-560c-9bad-a872967306bd | g) All active water ingress is controlled and or in sublayers.
| note | 630f5660-7e58-5554-b851-d929af464320 | h) Areas to be sprayed are protected from sun, to reduce outgassing effects. Do flash coat/prime at end of day if likely to operate in direct sun conditions.
| note | c6c99f57-254f-5320-869c-2f6f8b007b6c | i) Trial area established for nozzle and feed system dose rates check.
| note | 69a5b86c-703e-56e8-86a4-92f7c0ad3257 | j) Applied membrane is homogenous without holidays, gaps or runs. Overlap zones are minimum 200mm.
| note | 60fc3baf-3dbd-5630-b061-95becbe725bf | METHOD: Visual, IP
| note | 959b0843-4a6b-5943-a67e-566024e398ba | FREQUENCY: Each element
| note | fc2a5e22-fbfb-585d-9a4b-09d4c24b1554 | CATEGORY: WP
| note | 08b24178-c0bf-5262-8d67-23dbcf4c481a | RESPONSIBILITY: Package Manager SE/PE
| note | 5ca2ccc8-0e0d-59dc-be69-39312aea1b70 | VERIFYING DOCUMENTS: This ITP
| textbox | 89524614-5319-5612-afc9-80fd48db3988 | Date Completed:
| section |  | Construction / Installation Activities - Backing Board/Backfill
| checkpoint |  | 7.1 Installation of Backing board
| note | 5516e7e7-4c47-5fad-9bd6-b984d874a056 | REFERENCE: Product recommendation requirements
| note | 54d09029-2dc0-5684-8f92-0ff4f0abf288 | IFC Drawing
| note | 2161fb33-59ee-58f8-a050-a571a93d27ec | ACCEPTANCE CRITERIA: Demonstrate smooth & flatness against pit wall
| note | 8c4ea3f6-f0bc-507e-a361-c25164e31b90 | METHOD: Visual, IP
| note | a2cce9d6-e39d-5ebd-9355-17047cd3ef54 | FREQUENCY: Each element
| note | e09010fe-49d9-5a81-91f7-75b7efd11496 | CATEGORY: WP
| note | 26171bd7-68ff-55e0-a511-8cf3323d28f1 | RESPONSIBILITY: SE/PE
| note | 8be4552b-89d6-51cd-a94b-cc8d1fd95e0a | VERIFYING DOCUMENTS: This ITP
| textbox | 5149fe50-2bee-5042-8304-6e8291d96d85 | Date Completed:
| checkpoint |  | Backfill
| note | b150a3db-f9a3-5999-b0ae-0fb3da1a361c | REFERENCE: Product recommendation requirements
| note | 47f7f52d-74b1-51fb-b31e-5f39077428e8 | IFC Drawing
| note | c56f7b3c-1717-5d8c-a142-f809feaa9acf | ACCEPTANCE CRITERIA: Backfill to underside of Tanking Slab Blinding with 3% stabilised sand
| note | b30ee9ed-5472-5e33-84d8-052fae7e0516 | METHOD: Visual, IP
| note | 6cc350a4-5fc1-5f0e-b8e9-c572fb9455c7 | FREQUENCY: Each element
| note | 91d6778a-e134-58a8-85ae-db8e54b4abeb | CATEGORY: WP
| note | 1f87d3f6-8df5-5492-b3ce-92b06f5b8e7d | RESPONSIBILITY: SE/PE
| note | 107972ec-fcb4-5640-8485-f44d41bd63fa | VERIFYING DOCUMENTS: This ITP
| textbox | 5e069b2d-26cd-5d67-b3bf-ba0cfb103495 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 8.1 As-built Survey
| note | 15a687c6-0bf3-5840-a058-82f6e3cc205b | REFERENCE: IFC Drawings
| note | b874b9b7-e060-5e3d-865f-494fdc9dc254 | 610.46
| note | 3f1b74e6-19cb-5957-b145-4c26588dd0cc | Table 610.462
| note | de36145f-838e-5645-912c-c3c6de6dfe20 | ACCEPTANCE CRITERIA: Backfill to underside of Tanking Slab Blinding with 3% stabilised sand
| note | 0ca44cc5-aebd-54cb-8722-d74e5e3d8e8a | METHOD: Document Review
| note | 1b1ac55e-97cc-5307-baf3-3e4b602c96b2 | FREQUENCY: Each element
| note | fb323a7c-a0c4-5edd-8070-34b05897d77c | CATEGORY: IP
| note | 91ef16ff-842e-5ebe-b3c4-4e57e8b2aeb2 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 85287ecc-b9f5-507e-82e4-b0b8037644de | VERIFYING DOCUMENTS: This ITP
| textbox | b769945f-c022-59ac-9480-faecd50ba0d8 | Date Completed:
| checkpoint |  | 8.2 Non-conformance Report (NCR) Closure
| note | f6d8823a-44cc-5132-8e9b-a9f5421a2586 | REFERENCE: MRPA Quality Management Plan
| note | 0f10c966-d3de-5469-a46d-ac8b4fe79510 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area
| note | 52bd3d92-9b95-5b35-b843-dad7a6e3aa0c | METHOD: Document Review
| note | 15ed2729-88bf-5717-8964-b92214abb434 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 4fbe94bc-71af-5f21-af2c-8e1f072e4092 | CATEGORY: HP*
| note | 01288ea2-6ccc-50c0-8166-9fe5442c1a2c | RESPONSIBILITY: SE/PE/SPE
| note | 102a32ba-c87d-5105-b466-65e24b257a0e | VERIFYING DOCUMENTS: This ITP
| textbox | d7402c41-cb0c-52d0-898a-71c6ca7a476b | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 4e3c49b9-e7f5-59e5-9f03-da917aedd0dd | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | ff7a1006-5e72-5d48-ae0d-86b5ea6cb8b2 | Name:
| textbox | 890d8ccf-9813-5f43-b744-218a90d4fa87 | Position:
| textbox | effef53d-5206-5a77-b0f9-7200ad39dab8 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Elastomeric Bearings (Supply & Installation) Rev 0 | itp | ITP-STR-Elastomeric Bearings (Supply & Installation) Rev 0 | 7c2feef4-a16d-4766-b62a-840461b2d47c
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 59008c4a-f7c7-4e18-b379-ee428699e157 | Document Title: ITP-STR-Elastomeric Bearings (Supply & Installation)
| note | 924f58c8-6f9d-44e0-b004-db60dcc1340b | ITP Description: Elastomeric Bearings (Supply & Installation)
| note | 26d47787-c2ba-401d-bb60-8a8d3fe1fc6b | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 175e233b-0e46-49f7-92cc-8387b67d62d3 | Discipline (e.g. CIV/STR/RAIL: STR
| note | 17011fa6-564b-406e-be96-14efeabb5ab7 | Revision Number: 0
| note | d618756e-0809-4ed9-bc04-a3486fe00451 | Revision Date: 15/04/20
| note | b37fe88e-7323-45f5-8202-bc2a5aabcee9 | ITP created by: Mike Freeman
| note | 0e0c68ac-f120-43fd-a9a6-5ea30d009e66 | ITP approved for use by: Mike Freeman
| note | ff5faeb1-81de-40db-904d-0ce3251c1b84 | 1.1 Reference VicRoads Section 610 November 2018
| note | 58cf305b-7e41-4e48-8f12-3713258c345d | 1.2 Reference VicRoads Section 610 June 2019
| note | de532c4b-af53-4c95-b2f6-800c2400bfab | 1.3 Reference VicRoads Section 620 May 2009
| note | 0a82f41b-7837-4062-a367-3f0d6cef4cca | 1.4 Reference VicRoads Section 622 November 2018
| note | 89ddd0de-ac64-4588-8bb9-a1a37558d7c0 | 1.5 Reference VicRoads Section 652 June 2010
| note | 1989bd02-5f56-497e-8900-867845430b97 | 1.6 Reference VicRoads Section 656 June 2010
| section |  | Preliminaries
| checkpoint |  | 2.1 Galvanised Bearing Plates
| note | 127b2a63-03dd-49dd-9202-0627f6fc4a19 | REFERENCE: IFC Drawings
| note | 1b2892a1-5bd1-4c31-b2af-ffe899c6262f | 620.05
| note | 6813f18f-7ec0-48f9-b367-4aabdbfc5fec | AS5100.4
| note | 269e3859-df1b-481c-b9c0-8dfc9d948398 | AS/NZS4680
| note | 5f2e677a-a194-4d28-9ee3-b49a336f55a8 | ---------------------------------
| note | 2dd8d213-c767-47f7-a338-5c66f0d293fa | ACCEPTANCE CRITERIA: Steel bearing plates (top, bottom and tapered attachment plate) are to be manufactured to the requrements of the IFC Drawings and AS5100.4 and galvanised to AS/NZS4680:
| note | 441f3496-c5c3-4987-819f-030e120f6656 | Tolerances:
| note | cb07e706-2094-4d6e-a8e8-6b3ba69f4b8e | Length/width = +2mm, -1mm Or;
| note | a689ed71-5cdc-4ca1-a5c0-728b4be405cd | Diameter = +2mm, -1mm
| note | 48f6dfeb-157b-431e-928d-ddd98ab413c9 | Twist = the lesser of 1% or 1.5mm
| note | 6c6f0687-254d-48b0-92b9-4325198aed21 | Galvanised coating thickness for material >6mm:
| note | 97a9c121-cbfd-41f3-9d04-167eacbccaff | Average = 600gm/m² or 85µm
| note | d0b8e89d-37c5-405b-9d4f-e79f4e527b3f | Localised minimum = 500gm/m² or 70µm
| note | fcaea127-79a7-4369-ae30-60bc62621c23 | Attach: Dimensional Records
| note | b4af9b02-89e1-45f7-8523-acb82ae5416b | Attach: Galvaniser's Certificate of Compliance
| note | b9bed28f-9278-4a25-ab64-44dd2842158a | ---------------------------------
| note | d7f69e85-4fbb-4a18-a1a3-10c64725f2d6 | METHOD: Document Review
| note | f30fc6df-799a-4d27-b548-b4bc54b499db | ---------------------------------
| note | 83253240-d155-44f6-ac42-9da7f1d5cf87 | FREQUENCY: Where applicable, once, for each component
| note | 8ee8cb67-2c97-42a6-98ec-37fa9451ea0b | ---------------------------------
| note | dfa423ff-f198-44b1-ba6f-b25024fd396a | CATEGORY: IP
| note | 53d13a88-1fe6-43b5-816d-4da1022d329e | ---------------------------------
| note | ca300428-d508-4a2b-85ad-9bc280a098ec | RESPONSIBILITY: SE/PE/SPE
| note | 342d4073-ca4e-4b78-96da-3038f4e1637f | ---------------------------------
| note | 15491499-21f3-4266-80f9-d56d76d5e820 | VERIFYING DOCUMENTS: This ITP
| textbox | 7ebb3dcf-8cbc-4960-9567-24c776eaeece | Date Completed:
| checkpoint |  | 2.2 Epoxy Bedding Mortar Product Selection
| note | e924f9c2-a099-44c2-b49d-444334fa148a | REFERENCE: IFC Drawings
| note | e619d7b3-4ed1-45b1-ba95-d7bf30c76d9a | Product TDS
| note | 456fb15a-489f-47f4-bedc-3a40a797e7d6 | ---------------------------------
| note | 346b85eb-ae5b-4d00-83da-d172d69fb64a | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | 99e28909-9ce6-41c7-b3b4-40bcf7370c07 | i. dual component, thixotropic epoxy resin or adhesive
| note | be0e6ef0-ef96-4e49-a086-0213f993e152 | ii. Have a minimum compressive strength equal to or greater than substrate
| note | b8bc2365-f53d-4278-8087-e522f1663667 | Iii. have no minimum thickness requirement
| textbox | 5903d67b-6f33-4734-b353-5b3c84643099 | Enter: Teambinder Material Approval number
| note | e4c5cff5-8116-4541-9d61-8a5d9c29ed75 | ---------------------------------
| note | 31d767f0-18a7-4305-81de-4b8ce89064c0 | METHOD: Document Review
| note | cc8e7f6d-1e48-47b5-ab11-ff700392e9a5 | ---------------------------------
| note | 92238f47-d14b-4df9-b9c9-67633de3c63a | FREQUENCY: Where applicable, once, for each product, prior to use
| note | 40b55b1e-2b54-478b-ae15-921ed8e7f5fc | ---------------------------------
| note | 9d71a8c5-170d-422d-9437-3765113578ae | CATEGORY: IP
| note | 45ffe70f-eec9-407c-b51f-00d880e1ee22 | ---------------------------------
| note | 38cfc1ad-152c-4b3c-9cd5-eff70ddf6a76 | RESPONSIBILITY: SE/PE/SPE
| note | beda265a-18ac-4fb2-ba76-ca796cc9501f | ---------------------------------
| note | a06c0288-bed9-4cba-af71-776116830db7 | VERIFYING DOCUMENTS: This ITP
| textbox | 423b46b3-bd01-4efa-b4ec-a4b3d977a973 | Date Completed:
| checkpoint |  | 2.3 Elastomeric Bearings
| note | 3cc8ee98-2859-4aae-9c1a-e064de1755a1 | REFERENCE: IFC Drawings
| note | c0fd4067-1877-46f1-b3e3-4cd1f66a17e7 | 652.02
| note | 4f96c0a7-2ae9-4ac2-bd2c-b7e76adc1c3b | 652.03
| note | 9eab4ad8-de98-4c6f-8d92-9ddfbc50e75e | 652.04
| note | ca7406c3-031c-4708-b042-974736e3a643 | AS5100.4
| note | 5c41863e-4bda-47a7-8ed8-f42bccc17b68 | ---------------------------------
| note | 5c3eea1f-b585-4e3f-ba4a-3fb5df570c9f | ACCEPTANCE CRITERIA: Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
| note | 72b52c77-25cd-48a4-9f67-2b8be9ef8b8c | Tolerances:
| note | 72980c54-9f84-4506-a56d-a463295367a0 | Dimensions in plan = +4mm, -2mm
| note | c5c67d64-cf5b-4313-a4fe-3bc3d4ef200e | Thickness =
| note | 05c694de-ff6b-47a8-9470-3a73e6bb81b6 | ≤100mm = ±2mm
| note | 9e3094d6-196d-4571-bdac-003c399a8e1c | >100mm ≤ 150mm = ±3mm
| note | 9a80be62-c661-4da4-99cf-d3fb6b43d9e9 | > 150mm = ±4mm
| note | f55bc5e1-c2c1-4aaf-bd7a-09a9b6c50c68 | Testing:
| note | 6b929043-a26b-4fa8-9a11-01ff9c704e57 | Each bearing tested under compression
| note | 3987dd0b-03f8-42db-8ec1-7e4c5a3330ca | Batch tested for shear stiffness
| note | 3d4fea6e-fd2f-49df-b847-95c48c5bee5c | Attach: Elastomeric Bearing Test Reports
| note | 1e8d30a2-740a-4c60-9add-4d8658c8ad3f | Attach: Elastomeric Dimensional Records
| note | 1eb77bda-428d-4f13-a2e8-ee8faaf82dbe | ---------------------------------
| note | 664247be-7b26-4794-a138-255d5404d571 | METHOD: Document Review
| note | c16f7bd5-3994-429e-8a3f-dfaad2a41847 | ---------------------------------
| note | 318d6a5f-e7a2-47c7-a2cf-ed430178aa59 | FREQUENCY: Where applicable, once, for each component
| note | 4415cfe7-90b6-45cf-a9fb-1cf968646b4c | ---------------------------------
| note | 4a2356d2-aeca-4187-9f03-3c92d4247ecb | CATEGORY: HP
| note | ab063c39-25d3-433e-a94e-a9dfe01abb0e | ---------------------------------
| note | 632e2e21-aa34-4dfa-9166-c17c8b7d0365 | RESPONSIBILITY: Nominated Authority
| note | 478341cd-f7b8-4802-94ed-a0c3b19aedc7 | ---------------------------------
| note | e26a3b8d-4b6c-4e6e-8476-f7ba8ef0b9ae | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 298086f1-9b15-4711-bf20-f730cc789f99 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 Crosshead / Pedestal Tolerances
| note | 1b576d89-9883-4277-aa6b-aa5f8505a9e2 | REFERENCE: Survey As-builts / Survey Report
| note | 690d3b50-0f8f-4a76-8a89-21d13f61d964 | ---------------------------------
| note | 49278be0-63fb-406f-95eb-59b2e8275268 | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
| note | c0d528b4-8f0b-4fb1-a35a-28cc3b1414a3 | Reduced level ±2.5mm
| note | 2e752141-ffde-4c0f-91be-7791d130d42a | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
| note | f7e448e5-60bc-49ea-844f-7bd4e51e48d3 | Deviation from flat surface ±1mm
| note | 6ee3b78a-bbf0-41eb-b7d4-c45ff401fb99 | ---------------------------------
| note | d7bc29b6-7388-4c14-a95c-70a464df6cc8 | METHOD: Document Review
| note | 94fecb61-f407-4935-b5e2-6ec2163b1270 | ---------------------------------
| note | 1ed867e2-deff-4709-bea2-4ad338ecc888 | FREQUENCY: Each element
| note | 3e01878f-e2d6-4812-ab9c-796352460156 | ---------------------------------
| note | 0a66fa41-f902-42b7-99a6-6f4f751556c0 | CATEGORY: IP
| note | e230a966-7228-4323-97ed-e4ce438d749a | ---------------------------------
| note | a9b65756-9443-4160-b2e8-1bd310307493 | RESPONSIBILITY: PE/SE/SPE
| note | 6011bb2e-a0e5-4243-a882-3f5ffafb22dd | ---------------------------------
| note | db577336-9a6e-4468-a27a-fe00bdeaaf0f | VERIFYING DOCUMENTS: This ITP
| textbox | 8e905d99-b5aa-4bb6-a0eb-ab13f8b101d3 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 4.1 Bottom Bearing Plate Installation
| note | 6695adb9-b048-4bba-8fc2-32f8a0222933 | REFERENCE: IFC Drawings
| note | 343b3dc7-821b-44ad-bce7-8a06d8145fbe | ---------------------------------
| note | e0025809-eac2-449d-9b29-e86edd048dd4 | ACCEPTANCE CRITERIA: Bottom bearing plate to be dry-fit into the correct location and orientation as shown on the IFC Drawings.
| note | 01144a6e-9262-4402-97b2-9a0ba26ce32a | Mix the epoxy bedding mortar as per the manufacturer's TDS and apply a 1mm thick layer (approximate) evenly to the full extent of the plate.
| note | f8e9ae6a-64c9-4061-a817-fd34bbda9266 | Bolt the plate to the pedestal to a torque setting of approximately 175Nm.
| note | 77130ad1-ee02-40ec-abea-6f7714bce04b | Record: The bearing plate ID onto the Red-line Drawings or Survey Report
| note | e7244285-50e5-4b9a-bfd8-60885f7aabaf | ---------------------------------
| note | b083d71b-85cb-4663-bc88-962136397ac2 | METHOD: Measure, Visual
| note | 24416c14-5943-4805-bae8-df3ca940f0d5 | ---------------------------------
| note | a7343121-9d55-46b9-9a97-bcf542462394 | FREQUENCY: Where applicable, each bearing plate 4 days prior to loading
| note | 8c4b6858-3bd1-4aaf-b3d8-be62894fd24f | ---------------------------------
| note | 55722217-9c75-4ad6-9624-30ce293214e1 | CATEGORY: IP
| note | 0024e0d2-c929-4cdf-be3a-d3a7d73a661c | ---------------------------------
| note | 70a77d79-6492-4712-ad6c-8e4efe3e8a11 | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | 3a11ed39-6525-4610-b9a6-30cbfa0fdb14 | ---------------------------------
| note | 4751da7a-147d-41de-b278-c1b68a723e40 | VERIFYING DOCUMENTS: This ITP
| textbox | 0f139417-a051-4fef-8d9d-050eb37391ce | Date Completed:
| checkpoint |  | 4.2 Elastomeric Bearing Placement
| note | c514a182-58ca-45ec-863e-b7e7b25784a2 | REFERENCE: IFC Drawings
| note | fb7cd916-8663-4516-a96f-8a4936f2935a | ---------------------------------
| note | dd1fbf4d-c8c0-4be1-a78b-146397ef34f8 | ACCEPTANCE CRITERIA: Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
| note | 4458a147-02ea-4e2e-b073-ac5656d519ad | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
| note | 48070236-09e1-4bdf-8348-3a91d6cab0c2 | ---------------------------------
| note | b602878c-1c15-4e96-a117-7c62a03f2bf0 | METHOD: Measure, Visual
| note | a80a7cdf-78d7-4828-b34f-a2ffccc521f0 | ---------------------------------
| note | a219ba3c-5c65-4524-83c8-84e48c6defcf | FREQUENCY: Where applicable, each bearing location
| note | c59afd3a-8a08-460c-9ebc-cf4fc3d05e08 | ---------------------------------
| note | 159f59f1-616d-4540-a959-57b96b2bb288 | CATEGORY: IP
| note | dac84c59-ad36-4194-8d53-2aa7a2389833 | ---------------------------------
| note | 372c8333-61de-4d59-a4d4-a6765741aefd | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | dfe76e49-a0bf-4db3-90ad-981a99766aea | ---------------------------------
| note | 5e2ab4c5-e1db-4a57-94b8-8e5af0022a7f | VERIFYING DOCUMENTS: This ITP
| textbox | d866fa24-d06f-4582-99f8-a945a044df4a | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 5.1 As-built Survey
| note | b2b124b9-68da-447d-872a-8a6c1de46bd5 | REFERENCE: IFC Drawings
| note | 5a1fa171-b1bd-48a0-a68e-1ecdd71ad49f | 610.46 (a),
| note | d7313879-24fb-42f6-9502-d2607808c375 | Table 610.462
| note | a7c5dc49-0152-44ef-ad63-507ae1902a7c | (November 2018)
| note | 9818cdac-6db1-452c-b2a2-d7512067575c | 610.47 (a)
| note | 649ac770-8ade-480b-b8e8-07474ae0ea0d | Table 610.472
| note | 338fdde5-e225-458d-8da5-b2e3bb807941 | (March/June 2019)
| note | fd747b2d-c572-4121-896f-72d9478c0d83 | ---------------------------------
| note | 3d7f60b5-fc8a-47ad-a4c5-202853f39c35 | ACCEPTANCE CRITERIA: (March/June 2019)
| note | 7d70c487-d041-41bf-85d0-0f211897c5ac | Attach: Survey As-builts / Survey Report
| note | 1c1fd7db-9e1c-4464-8b75-e443f2bb721f | ---------------------------------
| note | 2639b90d-cf07-476f-91e6-5434da2aae5a | METHOD: Measure, Visual
| note | 62b27a27-1348-47f7-b09c-092b1b22877b | ---------------------------------
| note | 50784edb-663d-4881-b85d-d818ad8e853c | FREQUENCY: Where applicable, each bearing location
| note | 29e9e421-2ccc-4e2f-aa2e-9f458ac9300b | ---------------------------------
| note | 87c24a83-0685-4caf-bb8e-9d30c7650dda | CATEGORY: IP
| note | a322f0d9-5fdd-4c3d-b8a5-8153daffdb47 | ---------------------------------
| note | 5f28b67a-a907-4d17-85c1-a8cd965eecc3 | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | 3062564c-cd34-4fff-bfe7-6f47c49fb530 | ---------------------------------
| note | d526174c-58e2-4bed-ac5f-933c2eae575b | VERIFYING DOCUMENTS: This ITP
| textbox | f886cc60-032f-4e45-8a3a-c5aeb32b483f | Date Completed:
| checkpoint |  | 5.2 Non-conformance Report (NCR) Closure
| note | a46fdc35-bd42-41d7-a55c-30756a41745c | REFERENCE: MRPA Quality Management Plan
| note | 031e2efb-7436-4710-be2f-5152df035ea9 | ---------------------------------
| note | 1e7b9776-691e-41ae-92e1-984a616fc789 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | bd5ff4ae-723a-42cf-b9da-b0c13f71e12b | ---------------------------------
| note | 7496a464-6d8d-42de-9345-3514efd299a2 | METHOD: Document Review
| note | 42131a6b-f638-444f-ad7b-af56d8bce328 | ---------------------------------
| note | 06b4bfab-34c6-42c3-9389-5d8e36c885a6 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 88cbc5b4-9309-4b14-bc08-cb4d92a15d00 | ---------------------------------
| note | 1cf2f0bd-7e4c-486b-acd8-d678d086b55c | CATEGORY: HP*
| note | 2b9e17cf-ae27-4ce9-8fa8-5b2027cdce7b | ---------------------------------
| note | 638ff192-8e81-49eb-b7bb-7b0d2c398dfc | RESPONSIBILITY: SE/PE/SPE
| note | 533dfda9-cebf-4ca6-8b45-8398e8f4f790 | ---------------------------------
| note | 754eacdd-0d09-43f0-965f-8144bb6d1c65 | VERIFYING DOCUMENTS: This ITP
| textbox | fba40602-adf4-48f6-911e-781168a12582 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 3b7593e9-a831-4abd-a23f-d417b0fddcb3 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 18a389cd-3aa4-4002-8080-d5fcc3b31deb | Name:
| textbox | 3304468e-26d9-4736-b35b-6961a306f7d3 | Position:
| textbox | f65a6f28-d5e1-47dd-bc80-23a33ed4d962 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | itp | ITP-CIV Hot Mix Asphalt (Supply and Install) Rev 2 | 7dbb02a7-058f-4407-87e4-b1c64e53904b
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 0d7c104e-8b4d-459c-80dc-55aed29ff47a | Document Title: ITP-CIV-Hot Mix Asphalt (Supply and Install)
| note | 5b033122-d809-43fd-9379-a13e36524889 | ITP Description: CIV
| note | 63e551e8-9989-4845-9aef-c67baff314ca | Revision Number: 2
| note | 6dbfa83b-9c65-40b0-9d58-76de3d41094c | Revision Date: 15/01/21
| note | 7b579819-2ec0-4836-9821-c80382ef1d88 | ITP created by: Matt Velcek
| note | 4d87f4c9-4754-4432-af38-238eeb3b743a | ITP approved for use by: Josie Pavlou
| note | ee73905a-8cc4-4773-89e3-924794f255b4 | Reference: IFC Drawings, VicRoads 407, VicRoads 408
| section |  | Preliminary Works
| checkpoint |  | 2.1 Submission of Asphalt Mix Design
| note | e9185806-ef44-4bac-bc32-640d3de3cacf | REFERENCE: Section 407.06
| note | 56c990d8-8fc3-4005-9681-2936f3ae8add | RC500.01
| note | 8815fa17-cb9e-4e02-a9be-a6bdd1754c3c | ACCEPTANCE CRITERIA: Ensure this mix design has been Vic Roads registered and is approved by the Nominated Authority prior to laying mix.
| note | ee01d03f-bdac-4a76-992a-1c8bb6e2e87e | METHOD: Document Review
| note | b0ef29cd-6af9-4e44-a01c-90ececa5a9de | FREQUENCY: Prior to commencing works
| note | 28f373e9-2853-485e-9b02-d42bffd31f7b | CATEGORY: HP
| note | 42b0c382-f31e-4cdb-a0d4-857401348dd8 | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Nominated Authority
| note | aeeec1ac-29c3-4e89-bdf0-c8fd5ea0deb1 | VERIFYING DOCUMENTS: VR registration and Conformance Certificates Team Binder Approval Number
| textbox | adf61a43-ae35-44f5-99ea-fb4bed300547 | Team Binder Approval Number
| textbox | 64ad8973-78db-438b-aba4-ad44b736f023 | Date Completed:
| checkpoint |  | 2.2 Asphalt Placement and Lot Plan
| note | 79c919cf-b2d1-468a-99f1-fcdc8c4f60bc | REFERENCE: Section 407.17
| note | 62745217-0c4d-4e03-a229-87ab662ffbf6 | ACCEPTANCE CRITERIA: Asphalt placement and Lot plan to be created prior to commencement of works.
| note | 3fd1b7b6-17f2-4c38-89e7-53d67a1987c2 | The location of all joints shall be planned before work commences to achieve the specified offsets between layers and the final position of joints in the wearing course
| note | f966e34a-3856-43db-9b1b-abece1c87bba | Plan to specify start/end chainage, offset/lane and layer.
| note | 4b461c4d-57dc-4a44-8061-34d6750794bc | METHOD: Verify
| note | 7e73cda7-b696-4308-ab3f-e8b23563c93c | FREQUENCY: Each lot
| note | f3917ccb-9d84-4e99-8a1f-6ee2f4921beb | CATEGORY: IP
| note | b9fa11bf-ffa9-496d-8a17-8a1045a4f05e | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| note | 883b208c-43c7-4937-9d65-c6ade8473c01 | VERIFYING DOCUMENTS: Daily Lot Record
| textbox | 2fd521ad-8b91-4b92-be9a-b561f3738259 | Date Completed:
| checkpoint |  | 2.3 Site Inspection and Base Condition
| note | fc3d3d15-9141-4291-a333-b47ae7da3a62 | REFERENCE: Section 407.13
| note | e0ee6606-e72d-4557-8a77-f949e5f41d74 | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
| note | 7989715e-a8e5-486c-988c-84c667f4743c | METHOD: Visual Inspection
| note | d9dff0eb-3527-461c-9de5-91b4f62d5693 | FREQUENCY: Prior to commencing paving
| note | 46ac559c-3cdb-4686-854f-045ba3c6abac | CATEGORY: IP
| note | b00e4b09-3af2-4c2e-b9a1-ca3de3fdfbe0 | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| note | 87a481cb-b851-4b1c-ae59-3a608b9b643a | VERIFYING DOCUMENTS: This ITP
| textbox | bede4a8c-3eb9-447e-84a8-4ee03c69faaa | Date Completed:
| checkpoint |  | 2.4 Submission of Primer Material Documents (if applicable)
| note | 1c9d4b84-dbb9-4328-ac8d-9863c9ec264e | REFERENCE: Section 408.08 c, e
| note | 5d05c682-e7d7-4ec8-9b05-e79a847bd55b | ACCEPTANCE CRITERIA: The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.
| note | 9bfdf18a-839c-4923-951e-39349aa2eb09 | METHOD: Document Review
| note | 1f96c1b5-922e-425a-a9a2-ec0813e6220c | FREQUENCY: Prior to commencing works
| note | 752d8af0-7c42-4873-b625-fc59a66455dd | CATEGORY: HP*
| note | 60171ea9-00fc-4cd5-a1b1-46a3e71a0649 | RESPONSIBILITY: Site Engineer/Project Engineer
| note | ed88e47c-dec5-4b34-b0e4-7f1cb548d4a0 | VERIFYING DOCUMENTS: Conformance Certificate uploaded to TeamBinder
| textbox | 3983058c-5448-41e7-ae0e-b3013ebed747 | Team Binder Approval Number
| textbox | 376d69cd-a9a2-4972-a7e2-e4ad90d87336 | Date Completed:
| checkpoint |  | 2.5 Application Rates for Primer (if applicable)
| note | eab3bbff-8918-443a-ad42-c1af74d5e3ff | REFERENCE: Section 408.13 a
| note | 9f340c37-4128-4abc-b758-cc5bfea33a08 | ACCEPTANCE CRITERIA: At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent
| note | e23d9bf5-c210-49fb-bf44-a2b6ca715787 | METHOD: Document Review
| note | fb649bbe-4eeb-494b-b649-3cf65037277a | FREQUENCY: Prior to commencing works
| note | 563a89ae-37a3-4eb7-b5e3-835e8b5fbb82 | CATEGORY: HP
| note | 9d08db1e-0458-4353-9965-b5ee4626587a | RESPONSIBILITY: Site Engineer, NA
| note | eeea8c7e-2366-4205-95cd-289a1372c898 | VERIFYING DOCUMENTS: Application Rates uploaded to TeamBinder
| textbox | 6b775d94-1412-44cc-bf77-60bceb399485 | Team Binder Approval Number
| textbox | b5f37a9d-e63f-46bc-91ed-5176fc24b97a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Ambient Conditions
| note | 8c1908d3-1aa3-42b1-bcc6-2857a57290c1 | REFERENCE: Section 407.13
| note | ddd32566-ddb9-43d4-8582-a3c4775a37e0 | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
| note | 79433f47-3a90-4361-93e1-37b5db1b1c23 | Base & Intermediate Courses: < 5°C for conventional binders or < 10°C for PMBs & Class 600
| note | 6ee21ef8-d022-4608-a927-2f07e781ed25 | Wearing Courses: 10°C for conventional binders or 15°C for PMBs
| note | dbb34e8f-62cf-4e99-adfa-0675afce6218 | METHOD: Verify
| note | 8ff8294a-4838-4827-b8d4-64c6a65f4622 | FREQUENCY: Prior to commencing paving
| note | 5473b149-2257-41aa-86c8-1a0af8723f34 | CATEGORY: IP
| note | 5a86bffb-68e5-4155-bda7-daeefafb259a | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | ff31d5b0-4342-451b-9fa2-3e3e4317b622 | VERIFYING DOCUMENTS: Thermometer Reading Check
| textbox | 18062d41-57ed-4f26-9f30-7f5abc24af65 | Date Completed:
| checkpoint |  | 3.2 Planning of Joints
| note | b1bc87f8-bd49-41dc-a58d-007373e5aee5 | REFERENCE: Section 407.17 (b) & (c)
| note | ffd2cf64-925c-40b8-814b-33ed64ed9765 | Pavement Drawings
| note | 86f83b60-07f3-433d-ba8a-5e7bdfe38a9c | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
| note | 681fd1f9-799e-4b76-bd6a-02a689580b46 | Transverse Joints Offset from layer to layer by at least 2m.
| note | b12caf12-dbe2-4f79-a4b0-a6cee709320e | Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
| note | cff63ee1-9376-49d6-8fff-82e35f8aae86 | METHOD: Measure and mark out runs by tape measure or survey
| note | 632d2a5b-a755-4f29-a2b1-2a1cdc6ba514 | FREQUENCY: Prior to commencing paving
| note | 21d22af4-60a2-4f6f-b7a5-65fb590647fd | CATEGORY: WP
| note | 6cc92fc5-bb4f-4972-9b16-3d0065b8f70a | RESPONSIBILITY: PE/ Asphalt Supervisor
| note | 2c6a2d47-5aa1-4ee3-8603-244b38ffea92 | VERIFYING DOCUMENTS: Attach Paving Plan
| textbox | 62d9ace5-97db-4308-bcec-76ee07971dbc | Date Completed:
| checkpoint |  | 3.3 Longitudinal Joints with existing Pavement
| note | a0f043b4-4fc0-4f68-9551-54bd22fc0cce | REFERENCE: Section 407.16 (c)
| note | bf838d61-c8e6-495e-8563-c842900ed444 | Pavement Drawings
| note | 512ca2f8-533a-44b1-b996-4710e7f05232 | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
| note | 51dff7ce-8a38-4fee-8f95-32be2464ebd7 | Depth of step to be cut to the full depth of each individual layer.
| note | bbe797ca-323f-4632-8a14-d2cd21b68787 | METHOD: Visual Inspection
| note | 4dd30c75-cc9d-4369-b1b1-95b1a22138f6 | FREQUENCY: Prior to commencing paving
| note | bbbf374c-0d13-435a-aba4-ec2dcf9f7bd5 | CATEGORY: WP
| note | b986d20f-9814-42e7-bc93-480dcfd4c6a7 | RESPONSIBILITY: PE/ Asphalt Supervisor
| note | 2a108a79-52c0-403c-9abf-0df2388d8e57 | VERIFYING DOCUMENTS: This ITP
| textbox | a471c0ff-f5d3-4a7f-a2ab-881e9d32e7f1 | Date Completed:
| section |  | Construction / Asphalt placement
| checkpoint |  | 4.1 Tack Coat
| note | ad0d56f3-9e07-408f-b6c0-59ac2f286b95 | REFERENCE: Section 407.15, 407.17 a)
| note | d68cf894-2baa-40e9-b82a-6145035c35f0 | AS2150 11
| note | 1cc560c1-ab75-4970-a661-7d9a6c5942d9 | ACCEPTANCE CRITERIA: A tack coat shall be applied to the cleaned asphalt or sealed surface on which asphalt is to be placed unless the unsealed surface has been primed.
| note | 5d3307af-7da8-4486-ba46-480f49300073 | All cold joints and abutting concrete edges shall be heavily tack coated.
| note | f0a48815-81a0-48c6-b464-784b542b6c8e | Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
| note | 78f36138-fbd0-47c1-ba27-8d2e2c919b67 | Tack coat must be allowed to turn from brown to black before paving.
| note | b6dce9af-814c-46f9-a3d9-25b27e8ee4f3 | METHOD: Visual Inspection
| note | f77e4d36-9ed6-4ba9-94ad-401a304b4e0d | FREQUENCY: Prior to commencing paving
| note | b3f62b0c-84ad-4b42-bd39-2c14253d57f5 | CATEGORY: WP
| note | 43406619-e033-49f1-9dcb-b2f07687562e | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | 5eddd275-bf7a-41a2-857a-b87551fa6764 | VERIFYING DOCUMENTS: This ITP
| textbox | 007c2b67-6abc-4335-a47f-9325f78a57ce | Date Completed:
| checkpoint |  | 4.2 Commencement Primer Placement (if applicable)
| note | a5c28c9d-44d8-4038-a5b3-f09a7c83e431 | REFERENCE: Section 408.04 b
| note | 508b5cca-4990-4b69-88d5-0d40ce55d17f | ACCEPTANCE CRITERIA: Work shall not commence until the Contractor and the Nominated Authority have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 hours prior to the works occurring.
| note | 926cb8fa-383a-4707-bea6-742fdefb02fa | METHOD: Visual Inspection
| note | 4a124f6f-c060-4258-82e9-6628e485cb79 | FREQUENCY: Prior to commencing paving
| note | 8a690b9a-f799-4d70-a72e-c83628b7e3d2 | CATEGORY: HP
| note | 76df2272-19ce-4f38-a94a-21b6bcf737cb | RESPONSIBILITY: SE/ Asphalt Supervisor / Nominated Authority
| note | 959c7bd1-076a-4009-91d6-11a8874fec2c | VERIFYING DOCUMENTS: This ITP
| textbox | 6fab13ad-dae8-46bb-9005-e489ce171fca | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.3 Commencement of Placing Asphalt
| note | 5b11f1bf-09b3-4a77-a38e-038d10d2efdf | REFERENCE: Section 407.18
| note | e032dfcf-5af7-4469-a63f-323e33c663dc | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Nominated Authority
| note | dda9fab3-877c-405f-9519-286d894f798e | METHOD: Visual Inspection
| note | 1fdbac30-d5ab-4710-bf43-2af7784c0f6e | FREQUENCY: Prior to commencing Paving
| note | be68bb86-6372-4504-9d61-0a562efcc224 | CATEGORY: HP
| note | 5d84bb23-f2de-459e-9bce-da2da839aac2 | RESPONSIBILITY: SE/ Asphalt Supervisor / Nominated Authority
| note | 5d404bca-ab89-4b1d-8016-c24e233a1bc6 | VERIFYING DOCUMENTS: This ITP
| textbox | 268811d4-ee0e-42a8-9ba8-302cd2dc653d | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.4 Mix Design Confirmation
| note | 92c28298-7d95-40d7-88c2-ad2ff5ca0e82 | REFERENCE: Section 407.06
| note | ee4eb534-21f8-4102-8636-b8fe5640cc48 | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
| note | 32459a27-ff09-4da0-8461-aebc4dcc54f6 | METHOD: Document Review
| note | 110aff5d-7d4f-4828-8b7b-cd887b6c87a2 | FREQUENCY: Each lot
| note | 6f0cfa6d-7c8f-46e4-8c91-0ba2691b1d6c | CATEGORY: HP*
| note | 4b654206-86b9-41cb-a6a6-cf3c6bdb7e6c | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | 63acbcaf-8ff0-466f-b20f-b668b65cf040 | VERIFYING DOCUMENTS: Attach Delivery Dockets
| textbox | c9fa1910-123f-4a37-b296-9c44e9cb953e | Date Completed:
| checkpoint |  | 4.5 Asphalt Delivery
| note | c5fc10cc-46b8-48e5-8cf8-a6d9c07904f1 | REFERENCE: Section 407.16
| note | 8a8d190f-7f7e-4e8b-b46b-34a424b0a9da | Table 407.081
| note | a0df6876-a9f3-468f-91bb-dd45307f283e | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
| note | 16e8a5f5-0983-441e-8415-8fe1dcd6d115 | METHOD: Visual Inspection
| note | 9d105a5d-06c2-43a7-bd75-e1949c8dfec7 | FREQUENCY: Each load
| note | 8189f412-28ff-4649-94ce-89d4d3c1a9cb | CATEGORY: WP
| note | 9d2b31c5-c706-42a8-b473-0a5448a4e175 | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | a092f1e6-6ffb-4dad-9af2-54c1e3dae6c5 | VERIFYING DOCUMENTS: Attach Delivery Dockets Thermometer Check
| textbox | a8c92335-2e92-4c04-95bf-78221ae79bed | Date Completed:
| checkpoint |  | 4.6 Layer Thickness and Level Control
| note | 33891438-fd8a-4641-8e0b-b5bce7929f62 | REFERENCE: Section 407.20 (a) & (b)
| note | 6623dddf-b733-4a69-91d4-1e14ea13e381 | Refer to IFC drawings
| note | 9c1d6e24-5d7a-4374-8ccb-ed8ed9828b31 | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications.
| note | ffea584f-9c21-49f1-a928-5c25fe9b3357 | METHOD: Verify
| note | 0d376ec5-911f-455f-9321-d873fffa06c4 | FREQUENCY: Regularly during paving
| note | ed5c5feb-b1a5-4234-83f5-21d045bbcdf5 | CATEGORY: WP
| note | d4a28e5a-945f-4753-9e78-10dc22a25a1d | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | c80dc0aa-96f2-4567-af86-e3c92fd79459 | VERIFYING DOCUMENTS: Dips using ruler or dip stick This ITP
| textbox | d1f875b8-dc06-43a0-9ac5-f899d6bed07e | Date Completed:
| checkpoint |  | 4.7 Spreading and Stoppages
| note | f4a9e4f7-f032-48fd-b8fb-4d5b9fb1f267 | REFERENCE: 407.20 (c)
| note | d9a8c3bc-5d4f-48c7-9784-d97149b8ce34 | ACCEPTANCE CRITERIA: All asphalt shall be spread with a aving machine to form a uniformly smooth asphalt mat without segregation, tearing or gouging. Paver not required for small areas where use of a paver is not practicable.
| note | 4446186d-0931-4448-9b97-c19d14ffabb1 | Conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised.
| note | 90cbba92-102b-4e1e-a150-cd59e693c7ba | A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
| note | 52651134-36b2-4bbc-bbce-4dfb4bdc2360 | METHOD: Verify
| note | 1540dca2-3dff-4751-9efe-358d83d3015b | FREQUENCY: If paver stops
| note | 7450322a-f42a-4aa0-8b6a-abbf6d4102af | CATEGORY: WP
| note | ae816286-3df5-4b4c-9455-3992c0896e22 | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | 2c36884b-117d-451e-8f7b-53cdc66a6f2e | VERIFYING DOCUMENTS: Thermometer Check
| textbox | 6e8f2391-ef4f-4c00-a6a3-fa7826f4f8b9 | Date Completed:
| checkpoint |  | 4.8 Surface Finish of Wearing Course
| note | 9f65327f-b648-4038-b50a-1ea499191160 | REFERENCE: Section 407.23 (a)(I)
| note | 550368fb-e601-478f-bd40-0e9df0bcf51e | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
| note | 2b4f699c-923c-420b-8182-75541f0211f2 | METHOD: Visual Inspection
| note | dae8a782-839a-4b72-891c-fe385d2c97ba | FREQUENCY: During paving and after final roll
| note | 16379b2a-e028-4480-9a27-f067cea61427 | CATEGORY: WP
| note | 42883967-87cd-4495-9085-bb7276cb8ce1 | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | 4a734d56-46c5-4fec-be40-936afcf0808a | VERIFYING DOCUMENTS: This ITP
| textbox | a23c1859-3ada-453f-b3eb-28fdb6516f85 | Date Completed:
| checkpoint |  | 4.9 Kerb and Channel
| note | 60ed9b1b-de57-4532-85ce-45386cfd554d | REFERENCE: Section 407.23 (a)(ii)
| note | 12ddcfab-ac6c-4827-b9e4-fc9682b6ac27 | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified.
| note | d19d606e-47c9-460e-8127-cf28da4ca14c | METHOD: Visual Inspection, Document Review
| note | 770c2cf7-f46e-4be3-ae90-0a889c5c24ad | FREQUENCY: During paving and at completion of work
| note | 54466f07-70d3-424e-828b-38f9f64781ad | CATEGORY: WP
| note | 11bda3fb-c828-4806-a721-d78a53fa8415 | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | 47859f3b-8c7d-42cc-b06d-0c63c1f2d79d | VERIFYING DOCUMENTS: This ITP
| textbox | b45e7652-5213-4c69-b4e3-29ade3d64ab0 | Date Completed:
| checkpoint |  | 4.10 Alignment (Asphalt not placed against conc. Edging)
| note | fa384a1f-033a-4323-831e-b75f94b9a72e | REFERENCE: Section 407.23 (a)(iv)
| note | e1056164-2d0f-418c-9454-f480670ce817 | IFC Drawings
| note | 4fc99355-8bb2-41f9-a66c-e0987748653f | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
| note | 2c148b82-a92f-4bd3-836f-b4e5b2f87630 | The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
| note | 1a9e2a0e-5403-4af9-8b84-0309ce666646 | METHOD: Visual Inspection, Document Review
| note | b946bcb9-0a6f-4674-bd05-811230190914 | FREQUENCY: During paving and at completion of work
| note | 5b02cc1f-05bb-4edf-95a5-c899e227eb72 | CATEGORY: IP
| note | 7284dc24-6243-481d-af80-91b407650f9d | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | 8891474b-4396-45ce-86f3-eae7756512ae | VERIFYING DOCUMENTS: ITP Signed and Survey Conformance
| textbox | 08f4478f-ba9b-46e1-99da-0fb6c11e3132 | Date Completed:
| checkpoint |  | 4.11 Width (Asphalt not placed against conc. Edging)
| note | aab0079a-ad29-4e96-b80c-9e7bcc4a70b3 | REFERENCE: Section 407.23 (a)(v)
| note | 78b1bd1f-2446-4a15-89e1-a6429596fe90 | IFC Drawings
| note | a174690c-471e-42ab-a9f6-2cba5f98ed55 | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
| note | a0d1c207-2d8e-40d7-85dc-a76b976eb023 | The average width over any 300m shall not be less than the design or specified width.
| note | e4119082-b5c4-409e-86bd-9a3a35ea4cc1 | METHOD: Visual Inspection, Document Review
| note | 48ebce3e-e957-4896-8c7e-8309768e6183 | FREQUENCY: During paving and at completion of work
| note | f1e33c63-9a1e-46e9-94b2-5195c38bd2ae | CATEGORY: IP
| note | 7e10de79-2cfe-4526-9e48-072922fb95fb | RESPONSIBILITY: SE/ Asphalt Supervisor
| note | 1e5f9e60-1687-4621-b9fa-fce836856515 | VERIFYING DOCUMENTS: ITP Signed and Survey Conformance
| textbox | 2dd1ca15-dac1-4f5f-abef-b737b326330d | Date Completed:
| section |  | Post-construction / Testing
| checkpoint |  | 5.1 Compaction and Assigned Density Ratio
| note | 411248b9-e77d-48d8-ad34-fba5e1f82df8 | REFERENCE: Section 407.22 b)
| note | 2d4dff48-11d7-43f6-8a88-f373f824b302 | Table 407.221
| note | 7de6742d-791c-4453-8d76-c62867aa478b | ACCEPTANCE CRITERIA: For layers <50mm, characteristic density ratio to be ≥ 95%
| note | cf5dc106-e94b-4033-b32e-cd4c0b1b0817 | For layers ≥50mm, if characteristic thickness to be ≥ 96.0%
| note | e8f1a357-840b-4116-af6e-c562306d1ffa | The assigned maximum density of the asphalt shall be calculated. Should a single maximum density of the production mix vary by more than ±0.5% of its rolling average then a check design or redesign should be initiated.
| note | fca12a33-e8b7-41e6-9fcd-2b053145e0e5 | METHOD: Document Review
| note | 3735cefa-5d72-421f-aa9c-e835fc21cf2e | FREQUENCY: Per Lot
| note | c9e20316-d674-4a17-97f9-0f0a5d97d2ef | CATEGORY: IP
| note | c6657f79-2079-478c-b34c-56e5936a4381 | RESPONSIBILITY: SE/ FH Lab Technician
| note | 9252aa49-0bdb-4f2a-802e-3d628494dd49 | VERIFYING DOCUMENTS: Attach Test Report
| textbox | a06a5ae8-7520-4910-b9c0-72bfd26fb054 | Date Completed:
| checkpoint |  | 5.2 Level Conformance
| note | 8391d61d-3dc0-45ad-af40-12422790cfe7 | REFERENCE: Table 407.232
| note | 2857ad51-5aa1-4baf-9fa5-afee98eb7ae3 | Section 173
| note | da5dd72b-c4dc-4aac-9415-3ecbdf8baae6 | ACCEPTANCE CRITERIA: Scale A (Princes Hwy):
| note | dae0a139-cadd-4c14-89a9-a005d92b273c | Individual departures from design not to exceed ±5mm with a standard deviation of not > than 8mm. 80no. Measurements per lot.
| note | 46eecbde-f3f4-456d-b43d-cd605bd3fb28 | Scale B (SGH):
| note | 8a9be03e-5447-4c85-81a8-ad9cf7c662cd | Individual departures from design not to exceed ±8mm with a standard deviation of not > 10mm. 40no. Measurements per lot.
| note | 965b16da-5fe9-4e8a-ba74-6f68a3c289e5 | Scale C (Beaconsfield Car Park):
| note | a60b48fc-2208-4b61-8452-8e7ab2ef5bb2 | The level of the top of each asphalt course shall not differ from the specified level by more than 15mm for intermediate and base courses and 10mm for wearing courses
| note | 2d8ad49a-a2e2-4b2b-92aa-e47f47015f81 | METHOD: Document Review
| note | ee52d244-ec82-408f-8043-b614cc336c5f | FREQUENCY: Per 4,000m2 at completion of work
| note | 7942ea3b-b76d-40e1-a233-71ce4a02a59c | CATEGORY: IP
| note | a9d5e2a2-80a7-4402-a140-5592c9c44efb | RESPONSIBILITY: Site Engineer/ Surveyor
| note | fd5e940b-5d2c-4999-bcab-3b5f487a4c3a | VERIFYING DOCUMENTS: Attach Survey Conformance
| textbox | dc00edec-16c1-42ef-b190-f7b9aaff0275 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 5774cd11-d47e-42c5-bf1d-067a8e2b30d3 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 9bfa8995-46a3-4a13-a82e-ecf01f9284b1 | Name:
| textbox | b91d2e70-7f40-4fd0-ad5e-f252fcc4f1dd | Position:
| textbox | 85b2c223-1861-4fd8-bed3-a470c2adf79f | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Precast Bridge Beams (Supply & Installation) Rev 2 | itp | ITP-STR-Precast Bridge Beams (Supply & Installation) Rev 2 | 7e4a2d28-62a2-4338-8c79-57a67c61f7fb
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | fb7a3c4f-e206-4842-abf0-20a6a886fcd7 | Document Title: ITP-STR-Precast Bridge Beams (Supply & Installation)
| note | 2e9ae496-2cb8-489d-9554-df9f9993f8df | ITP Description: Precast Bridge Beams (Supply & Installation)
| note | 077d119a-ba01-466f-ab40-12f168af2566 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 23c012cc-e70d-4294-a29f-f00a2d8c7b3f | Discipline (e.g. CIV/STR/RAIL): STR
| note | 9428cb3a-c30c-46b4-a4ab-11831131fe45 | Revision Number: 2
| note | 79262150-b092-4923-8402-6474c9d7f60f | Revision Date: 44244
| note | c9f3d4c9-f026-4bf2-b283-edc6dd7f34a8 | ITP created by: Romualdo Magpantay
| note | 14a22628-5750-4e74-965a-8f498b0b253d | ITP approved for use by: Mike Freeman
| note | 04461f15-0f3b-4534-895c-e7719ff88049 | 1.1 VicRoads Section 169 July 1993
| note | cf477b9e-2688-4b83-86de-5a92de6b9db9 | 1.2 VicRoads Section 610 November 2018
| note | 02b15237-e83e-44f1-9ea6-f960e1d7ae27 | 1.3 VicRoads Section 610 June 2019
| note | 441749ab-d6a6-479c-a6e0-d221e1a8e7cb | 1.4 VicRoads Section 613 June 2017
| note | 22eb6cc7-0605-4e20-ab4e-17669bc96709 | 1.5 VicRoads Section 620 May 2009
| note | fd9d105a-2d61-40cc-81ea-295e520bd547 | 1.6 VicRoads Section 622 November 2018
| section |  | Preliminaries
| checkpoint |  | 2.1 Precast Elements
| note | 0690fbe5-5d61-4220-8035-80decbbc3343 | REFERENCE: IFC Drawings
| note | 873d190a-47a4-4608-9a2a-ba658079fde8 | 610.46 (a), Table 610.463 (November 2018)
| note | da11b6bf-d1ac-4b64-93c1-7f2aaf37d3cf | 610.47 (a), Table 610.473 (March/June 2019)
| note | c4f4aa51-54d6-4169-9dcd-2d7f0716c596 | 620.03
| note | e755a467-1d1a-48b4-b52b-2fb3611ad04b | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
| note | 6ca43b2b-19ea-4d2f-9e87-0f946baa2d2c | i. Certificate of Compliance / Birth Certificate
| note | d3ba4b4d-defb-4e6a-a8a0-0dfc0926f62d | ii. Compressive strength test results
| note | 33a82343-38c9-4d83-bec8-c3941665de66 | iii. Precast Lifting Design
| note | 58cb39af-8f69-4542-b0dc-d8a1e424eddd | iv. Pre-pour check sheet / ITP
| note | ffb6d55c-e3b3-4b47-a377-32bf646ae721 | v. Pre-stressing check sheet / ITP
| note | 6e4efd84-b4b4-4697-abe3-340e3c697e17 | vi. Post-pour check sheet / ITP
| note | 31b797ca-c546-4f63-9dcf-b28adac23210 | vii. Covermeter check record
| note | 86894450-c129-4983-8a20-b6da39734967 | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
| note | 20ba444a-f9c2-4f8f-9ec8-a7f100ce1ce4 | Note: Different revisions of 610 have different clause numbers
| note | 742b3c59-9a4f-4894-8814-1dd67f924596 | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | ad77f7e4-af3f-469e-82f8-ea07dc59c224 | METHOD: Document Review
| note | 6f63c467-aca4-4ed3-8116-dd8392ac0021 | FREQUENCY: Each element
| note | f294d6ce-221c-4148-a469-519a29f5fd1d | CATEGORY: IP
| note | 01abf318-aa6a-4c58-8947-937a941b7306 | RESPONSIBILITY: PE/SE/SPE
| note | bf104b48-e4aa-4f83-8805-7c93360611a1 | VERIFYING DOCUMENTS: This ITP
| textbox | 2c00f3f0-346f-49c9-98fe-d800c9ce9fcb | Date Completed:
| checkpoint |  | 2.2 Temporary Works Designs
| note | c191bfd8-0136-4327-a8b4-6b79d370216a | REFERENCE: 610.27
| note | 58670df7-d947-4fe3-8d90-ce61e306dc0c | 613.04
| note | f53d00a9-4345-4eee-9958-862a26081c3a | 613.05
| note | 7c733b8b-69ee-4b01-8a3d-76a80451fc4d | 613.16
| note | 9ef3c2bf-19ed-4632-bb9f-2b95102eae49 | ACCEPTANCE CRITERIA: All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design.
| note | a348212f-1b65-494e-a7ff-a35141150601 | Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority.
| note | e6bfa5eb-36c2-40f8-82c8-6cb19b5259c6 | Attach: Temporary Works Design
| note | 71961802-9dd2-4ad1-9ddc-f75e2482e3b2 | Attach: Attachment A
| note | d26771de-86a9-4e13-9082-94290c6d1433 | Attach: Attachment B
| note | 1c9b870b-b389-44d2-a98b-7833a93d2225 | METHOD: Document Review
| note | 0f6254d2-09ca-438b-b5d3-78c6ec14f773 | FREQUENCY: Where applicable, once, 5 days prior to installation
| note | ed96884d-96a1-448c-bb2b-d8c75bc91228 | CATEGORY: HP
| note | 57eab7c7-79e5-49be-b43d-5e2a6612245c | RESPONSIBILITY: Nominated Authority
| note | 85c7f73b-7d52-4f0d-81d8-ac7a73b1e1c7 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | add6ec26-501f-4542-908b-2733c6723dae | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Crosshead / Pedestal Tolerances
| note | e1d08ba9-cad9-475f-b481-13131ac3b0d2 | REFERENCE: Structural Concrete ITP
| note | 19a761d7-8043-497d-8860-6c0148fa6ddb | Or,
| note | b3ec6128-bcfe-4771-9ca2-764134c6691b | Grout Pedestals & Bearings ITP
| note | 76f2d18f-9111-4d49-8719-0bc365cdcb7f | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
| note | ece11aa7-c753-4ae2-9337-87f866d2187f | Reduced level ±2.5mm
| note | 35eed8a0-ae6d-4c6a-b591-b44ee42300fc | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
| note | 7ad695f8-3202-4d15-b1ec-902bc945f589 | Deviation from flat surface ±1mm
| note | 86321399-5e21-4257-ac95-cb2de52a55c3 | METHOD: Document Review
| note | c40d833f-75eb-4331-918f-3fdfd461c94a | FREQUENCY: Each element
| note | 80a87ceb-c85e-415a-a161-a996f494e534 | CATEGORY: IP
| note | 461747e5-57bc-4e75-a510-3fd83e2019da | RESPONSIBILITY: PE/SE/SPE
| note | b8be1276-7213-4bd3-8629-91ae1d3ccde6 | VERIFYING DOCUMENTS: This ITP
| textbox | 0c609174-9d8c-43b7-ae78-fe538da0b5ae | Date Completed:
| checkpoint |  | 2.4 Crosshead / Pedestal Compressive Strength
| note | a6ded94f-5fa3-4d55-a3ab-fa9c01c336dd | REFERENCE: IFC Drawings
| note | 8712adfa-0984-4312-8357-808a9d6fd670 | Compressive Strength Results
| note | 27afb778-bf41-4413-bcca-0b2f9a0ce990 | ACCEPTANCE CRITERIA: Re-check that the minimum required compressive strength as shown on the IFC Drawings has been achieved.
| note | ac7b9f84-fa9f-42e9-93fe-b21c89f6e953 | METHOD: Document Review
| note | 81b77395-3c48-4b31-a2b1-17a113e873ca | FREQUENCY: Each element
| note | 3bdd0d1a-e57b-4894-8b51-88a778b6f0b7 | CATEGORY: IP
| note | d52280ca-e245-4e18-91ac-4044e3762fb3 | RESPONSIBILITY: SE/PE/SPE
| note | 8b158097-ba04-4404-8f6b-3b68788934e9 | VERIFYING DOCUMENTS: This ITP
| textbox | bf360648-e289-4068-993d-b17d51f253f8 | Date Completed:
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out of Precast Elements
| note | de221efc-2c85-4495-ae90-8a2e27ec4a47 | REFERENCE: IFC Drawings
| note | c470ef7c-be8b-4734-8f6b-550ce4149534 | 610.46 (a), Table 610.462 (November 2018)
| note | 880a04c5-b702-4b1e-8c76-5a497779744e | 610.47 (a), Table 610.472 (March/June 2019)
| note | 96c1a189-6783-4c2d-8fdd-1b6dcba64ffc | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element.
| note | 5973ff34-52ee-4e23-ad8c-b87c6db19bd5 | METHOD: Measure , Visual
| note | e3b7fa8f-f86d-4486-b1f3-e1c0fe0c3971 | FREQUENCY: Each element
| note | 6d127219-7e9f-4f5f-9dca-26dacd7e4e4a | CATEGORY: IP
| note | 72d4a4ba-a0b0-4c01-af0c-c0511af528c1 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 46d763ee-ca22-4ba2-a0b7-d2323bc73f68 | VERIFYING DOCUMENTS: This ITP
| textbox | bd34d406-07de-44b6-88ba-25f907b9c680 | Date Completed:
| checkpoint |  | 3.2 Elastomeric Bearings
| note | 025cde20-220a-4d39-9fc6-0a334361ed1b | REFERENCE: IFC Drawings
| note | bbeaeae9-b707-4f87-8e4e-b81b40023f27 | ACCEPTANCE CRITERIA: Where applicable.
| note | 4da22861-e707-4fb7-8e2e-cbea62ce6720 | Complete: Elastomeric Bearings (Supply & Installation) ITP before proceeding with this ITP.
| note | 03b1c24d-93c6-461c-9b0a-6a502f6c683b | METHOD: Document Review , Visual
| note | 68de23d0-f6df-4bd9-87d0-1b0591c6f07d | FREQUENCY: Where applicable
| note | 7ef4804f-ec86-4f63-b890-13a8e78f8ad4 | CATEGORY: IP
| note | e2b613c0-105b-431e-a9a3-2b305445966b | RESPONSIBILITY: SE/PE/SPE
| note | 79e1de3b-9819-425e-9949-0a5264cbcc8d | VERIFYING DOCUMENTS: Elastomeric Bearings (Supply & Installation) ITP
| textbox | ded5fe12-94d5-4e23-8a02-c092bc1b498a | Date Completed:
| checkpoint |  | 3.3 HDPE Bearing Shim Placement (for integrally cast beams)
| note | 23ad20bb-e4ac-4d41-9f66-6176c523b2d4 | REFERENCE: IFC Drawings
| note | 21b5f2c6-5e71-4aad-9290-634694ac720c | ACCEPTANCE CRITERIA: Place the bearing shims (or variety of shims) to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
| note | 6f4b7b74-769b-42e3-b9eb-6e7cf43847f9 | Note: The minimum and maximum thicknesses of the HDPE bearing shims as this will determine the product for the grouting activities.
| note | 2728dee1-49e5-4cf3-b2b7-5be3bc03f39b | METHOD: Measure , Visual
| note | 40f0e85c-6357-4ac2-9520-b8eaf9bff437 | FREQUENCY: Where applicable, each bearing location
| note | 850881b7-490b-407c-ba34-409705b8a673 | CATEGORY: IP
| note | a6b1bc7b-dd41-4867-a27f-1eb833cc4f9a | RESPONSIBILITY: SE/PE/SPE
| note | 4f9f4520-e9ce-41c9-b339-867c0698a8e7 | VERIFYING DOCUMENTS: This ITP
| textbox | fd599a0d-b35c-49dd-8c48-b6f9ba1e51dc | Date Completed:
| checkpoint |  | 3.4 Materials Inspection Checklist
| note | 43c7261c-85d4-4d84-b3b3-c3801e215bae | REFERENCE: 620.06
| note | cb64694c-f0ce-4b9b-b8a5-c88cc646b5ad | 620.07
| note | 37dfeb30-2d1d-42f9-8890-859aa0e35b30 | MRPA Quality Management Plan
| note | f2f3f9d0-2806-4930-a631-63fddef723d0 | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
| note | 2f93b649-5d96-4250-b350-f87938dea11c | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
| note | 9a190ca5-1b6e-4277-9d03-422190a51f38 | Elements shall have unique identification and orientation marked (if applicable).
| note | 9549e316-dfa7-4527-ad45-87bdd09c99cb | Complete: Materials Inspection Checklist in ConQA
| note | 9026b716-40e8-4d8b-bca8-8e8552e1f75e | METHOD: Measure , Visual
| note | f99325ed-54d6-40d5-922e-4ee7d713b223 | FREQUENCY: Each element
| note | a90e341b-20f4-4a87-8f54-ce404b197dcb | CATEGORY: IP
| note | becf0cc1-cc47-432e-9d4a-a5ece4f4fda4 | RESPONSIBILITY: SE/PE/SPE
| note | 4dd5d68c-bac8-4fe6-8f36-8332b43ece30 | VERIFYING DOCUMENTS: This ITP
| textbox | 78764009-af49-4193-a913-d8077dbfefa9 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 4.1 Precast Handling
| note | eaa68679-78a6-48b0-8442-6e37483708c0 | REFERENCE: 620.07
| note | 72d60a2b-8869-4090-9358-478f159540f5 | Crane Lift Study
| note | e4547776-c3ba-4db5-9409-0e65a2aa77b0 | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
| note | ad835295-dfc6-4565-939c-b5e5aa5268a8 | METHOD: Visual
| note | bb2e0b5c-5487-48d4-ac60-ced1fa310482 | FREQUENCY: Each element
| note | e39f22d0-b00b-4b1c-85d9-a14d853fd457 | CATEGORY: IP
| note | 4007f828-b653-45d5-b9a5-a2d83b66c285 | RESPONSIBILITY: SE/PE/SPE
| note | e1164f40-bb4b-43b7-a36f-b54c5e3cd830 | VERIFYING DOCUMENTS: This ITP
| textbox | 65a4a42a-3aa6-40d2-983f-51551f342868 | Date Completed:
| checkpoint |  | 4.2 Precast Placement
| note | 26ba6f06-adc1-4ecc-8fe0-9bc8c073f533 | REFERENCE: IFC Drawings
| note | 3105ffa8-266b-4501-81fa-8c72c90765bc | 610.27
| note | 7179c230-7c25-4cd9-84dc-c9b4ca5e61d0 | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
| note | 30312c33-c456-4405-95f7-841790461430 | The nominal gap between elements is as per the IFC Drawings.
| note | 49d0b55b-d63d-4cdc-8de8-32563ba88fc3 | METHOD: Measure , Visual
| note | 449f8975-c6cf-4476-85dd-7b8bdccc41ba | FREQUENCY: Each element
| note | 36c2f882-2487-4827-a21d-f7437d9e6ec8 | CATEGORY: IP
| note | 2375616b-b924-4bd2-a6b2-aa5d77c79ff2 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 086f1177-56f5-4e70-b8c5-455b97cb5db5 | VERIFYING DOCUMENTS: This ITP
| textbox | 8961e475-85c3-4c66-984e-b43ecb9bd52d | Date Completed:
| checkpoint |  | 4.3 Precast Traceability
| note | e1b669b8-7162-4299-832f-37259491f8a1 | REFERENCE: 620.09
| note | b7afe35a-fd26-4dad-8042-61a94bb49b46 | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
| note | 6deacd36-6640-448a-85ac-b05523fc161a | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
| note | 03186e31-68c5-47d4-8643-489037e89dd8 | METHOD: Visual
| note | 9f64a834-d80e-470a-ada8-2fae139bc839 | FREQUENCY: Each element
| note | 98ed5ddf-7c25-4036-a7e5-9fcd5cafbe81 | CATEGORY: IP
| note | 37c1ec60-e85c-4827-8020-f78611765c0b | RESPONSIBILITY: SE/PE/SPE
| note | 871a7e5a-8383-4444-a3d6-672692052868 | VERIFYING DOCUMENTS: This ITP
| textbox | 17593fe5-b306-425b-b330-29ae8d2a7aca | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 5.1 Falsework Certification
| note | 18a152fd-5d1e-41b3-be8f-80bc07bd4206 | REFERENCE: 613.12
| note | cc1b37f2-038b-4af6-8aa8-80d532ff9143 | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above)
| note | 965a5cb1-b539-443a-bcc4-11a27a2982ed | Attach: Attachment B
| note | e60e9ed5-16ee-4702-824a-a47c9034b53a | METHOD: Visual , Document Review
| note | f9524752-6857-4311-b2ac-ebd3be0d10e2 | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
| note | 56e480b5-1a99-4460-bd9c-78980af8e5af | CATEGORY: HP
| note | b480a6a4-296d-4219-8758-35e1c0810ec3 | RESPONSIBILITY: Nominated Authority
| note | 62126907-0a94-407b-bbfe-ff609aab4fb6 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | d3a6ef65-3fa3-42f9-821b-930d908548c2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.2 Flowable Grout Pour (for integrally cast beams)
| note | 0be38ee5-ca35-45fb-ab74-9bf54439c8a3 | REFERENCE: IFC Drawings
| note | 3f57fccd-469d-4bca-9cf0-54371cf8f8da | ACCEPTANCE CRITERIA: Where applicable, the gap between the bottom of the precast element's soffit and top of the crosshead should be grouted.
| note | 4a4a6439-a339-4eb2-8fd1-f4a639a99457 | Complete: Grout Pedestals & Bearings ITP
| note | 5d19deaf-19dd-4172-920c-ab8718e0dda4 | METHOD: Visual , Document Review
| note | 889ab6cb-975b-4bf7-beb5-6efab7d8ca5b | FREQUENCY: Where applicable
| note | a997ed24-fee1-496e-8423-61e19159c325 | CATEGORY: IP
| note | 34208f90-6723-48b0-a834-afa7812cb8ef | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | bb3d12b4-7d20-44cc-9099-71eadf694ae9 | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
| textbox | 671c3ebb-11fb-4fb7-9ead-e1840d5da778 | Date Completed:
| checkpoint |  | 5.3 As-built Survey
| note | 4f0725e8-226b-45f8-9e60-251943b35427 | REFERENCE: IFC Drawings
| note | 9ba6a7a3-8ce3-4c2c-a439-0c0f8c620534 | 610.46 (a), Table 610.462 (November 2018)
| note | cab98ceb-8286-472f-9183-41ce8c7d0a83 | 610.47 (a), Table 610.472 (March/June 2019)
| note | 22db37f1-e198-4de1-aa76-2feaad3af13a | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
| note | 5ca6dac8-3e1a-4c89-a387-92811508a707 | Attach: Survey As-builts / Survey Report
| note | 05393345-0a85-49d0-9c30-0f98efdfa87d | METHOD: Document Review
| note | f0203647-794a-4fde-bb30-bd681094bd3b | FREQUENCY: Each element
| note | fd99b60e-deda-4d53-ac93-c35c7960337c | CATEGORY: IP
| note | f7e6e74a-7e05-4342-8e06-efc24be8417c | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | e34dd50a-1420-4c25-939f-3759f60dcb17 | VERIFYING DOCUMENTS: This ITP
| textbox | a1022ca8-7d89-48ab-a72e-bd677fd2f5e3 | Date Completed:
| checkpoint |  | 5.4 Removal of Falsework
| note | bd4720e9-8917-491d-b44a-2ef12481fe2c | REFERENCE: Temporary Works Design
| note | 3dabd6dc-399c-43f1-8f7d-9a3ac5196a99 | 613.16
| note | e446a8b0-0077-4be3-a94e-66f5f91cc024 | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
| note | 770f1211-0736-42c3-bddb-22efd7b8975b | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for and repair.
| note | ea46a2cd-c2af-4ea6-9c09-c6ee28cda833 | METHOD: Visual , Document Review
| note | 5a4fa5b9-1655-4ac9-b68b-3101b0815cef | FREQUENCY: Where applicable, each element
| note | d5a8cc48-dce0-4c18-974b-19815c93febc | CATEGORY: IP
| note | e8a8dbe0-1584-43a8-805d-59142f052618 | RESPONSIBILITY: SE/PE/SPE
| note | 7331bb7b-49e2-4511-b2e6-ae02ee2ace0c | VERIFYING DOCUMENTS: This ITP
| textbox | 68022e7a-afb4-4d21-9ff4-96c0a6732471 | Date Completed:
| checkpoint |  | 5.5 Non-conformance Report (NCR) Closure
| note | d33bc824-cf4f-43e9-963c-ebdccc0b5f1e | REFERENCE: MRPA Quality Management Plan
| note | d6aa81c7-7827-4dbb-b737-35226cf5d9b6 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 806bae95-217e-43ac-b0cc-e1821ce1abb0 | METHOD: Document Review
| note | 7f2a20e8-8533-4b5a-947a-5f6b5fb02a3f | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | b5448290-0311-4e5c-9c81-db3e81ba3f64 | CATEGORY: HP*
| note | a812d4db-cc67-4220-99f6-4efa08bba8ff | RESPONSIBILITY: SE/PE/SPE
| note | 75420ca8-8131-4eee-a6bd-ed58d02ad9ce | VERIFYING DOCUMENTS: This ITP
| textbox | ab84cc35-0c3a-4b3f-b131-a0c4a6c80fc6 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 156a6223-8d95-4070-b5a2-0c0761bcb4c3 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | d7a6f9c5-923a-46d4-803a-c8e32d14d785 | Name:
| textbox | f99a4a54-7e09-4a65-97f1-66135bb2102f | Position:
| textbox | 074a2b5a-04ea-4081-b563-65f29659d805 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Supply & Installation (Recycled HDPE&PPE) Drainage Rev 0 | itp | ITP-CIV-Supply & Installation (Recycled HDPE&PPE) Drainage Rev 0 | 7f2495ea-8639-4704-809d-2eb89a678d9c
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | ec73e393-f8b5-4491-b732-31e1d9f2053a | Document Title: ITP-CIV-Supply & Installation (Recycled HDPE&PPE) Drainage
| note | ef827317-e35d-477d-ba3a-a19566c0f96f | ITP Description: ITP-Supply & Installation (Recycled HDPE/PPE) Drainage
| note | 071d6cac-b097-4d16-912a-8630c752df01 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 24418253-505d-4790-938c-6b4413447158 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | c8440e7c-e4a5-4827-9f0d-652281a1bae7 | Revision Number: 0
| note | b1be87fa-321f-4b7e-a79f-0c101833cc3f | Revision Date: 10/06/2021
| note | 37fbcbcc-bd51-4675-99ad-0bb2299317ba | ITP created by: Romualdo Magpantay
| note | 21350dfd-6212-42f2-b79f-c957dd7bac60 | ITP approved for use by: Romualdo Magpantay
| note | b7fe91f7-0f67-48c4-9d60-01b228c2d6c2 | 1.1 AS 2566
| note | 35583b04-e034-42f9-b460-45a0d52a803d | 1.2 Vic road 701
| section |  | Preliminaries
| checkpoint |  | 2.1 Submission of Cert of Compliance for Supply of Recycle HDPE/PPE Pipe
| note | 970d7e68-5b4a-44cf-9255-8f047ca825cc | REFERENCE: AS 2566
| note | 210ee1bb-f1fa-40a6-8bd4-7c61ae93c1f1 | IFC Drawing
| note | b90a250d-48e4-4974-9985-4605d1313dac | ACCEPTANCE CRITERIA: Prior to incorporating into the Project Works and Temporary Works plastic flexible pipes and fittings, obtain a signed Certificate, verifying that the materials and components comply with the requirements of this Specification.
| note | d589fd49-97f8-4bd8-b67e-a00581ec36f1 | METHOD: Review, Document
| note | b90bd91b-e2d2-4dbf-a37c-d8802a827873 | FREQUENCY: Once
| note | 12a1357e-774e-4386-b11a-fc6b0265dd96 | CATEGORY: HP
| note | db87446b-f2d6-4d55-b8b4-b5b9e8186d6e | RESPONSIBILITY: Nominated Authority
| note | 5d6bd7e5-05e7-4b03-9a63-234cc1fc8a49 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 9f25f2a9-77dd-4720-968f-d1ddfe768b3f | Date Completed:
| textbox | 16f9c8fa-715f-448d-970f-a8847925403c | Team binder:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Submission of conformity records to verify compliance of Embedment materials
| note | 14b42e84-4928-4ab3-9bc6-59fabc5501f2 | REFERENCE: AS 2566
| note | 06fdce51-464d-4d9e-9498-259dd8d3b16e | IFC Drawing
| note | 26f2d6c4-e7de-4593-8a53-cc97e7615ddd | ACCEPTANCE CRITERIA: The conformity records includes verification of:
| note | c9bb0c88-a11d-4772-9041-dee3e0267c80 | Embedment Materials(e.g. bedding, backfill ,etc.)
| note | f49647b5-c365-44bf-bc69-826403b01f55 | METHOD: Review, Document
| note | bba2245f-795d-4a5c-bc1d-54947105ef2f | FREQUENCY: Per delivery
| note | 1735159c-f7e0-46fb-9d95-41f1f771de46 | CATEGORY: HP
| note | 7af4c333-9515-4001-b0f7-a8c37cf2104e | RESPONSIBILITY: Nominated Authority
| note | 1f341f99-32fd-4d8a-82c7-9e12555197a2 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 3ef33bf1-060f-40ad-905c-e39c5d8525b2 | Date Completed:
| textbox | c49fed14-19d5-4d33-9945-2ee06833ee82 | Team binder:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Check the type, size and class of pipes and other drainage structures to be laid
| note | 511118f1-a784-44b1-b624-bf1af209ef3a | REFERENCE: AS 2566
| note | 41f81253-8dd7-4d0d-b7b2-03b88db12139 | IFC Drawing
| note | 3eaa73be-6c6e-4828-b42a-84108d834c40 | ACCEPTANCE CRITERIA: Supplied items are:
| note | c655ce66-8c6d-4e4b-93aa-1ae93154ef37 | To correct spec, type, size and quantity
| note | 795cc078-445e-459a-8396-ebc7fcdfb33e | Defect free, safely stored & prevented from UV Exposure
| note | cd21ec31-a704-46f2-adf6-f1daf9b816a9 | Markings have been made as required
| note | 0d6e8eec-6b6c-430b-a75c-92f2b11e9968 | METHOD: Visual, Review, Document
| note | 681f6a43-6f1b-47e3-ad2b-eb065df5190b | FREQUENCY: Once
| note | 5b5fd3ef-b190-483c-b75d-9d0b95d9a7f0 | CATEGORY: IP
| note | 54e6dc50-421f-400b-8153-4b42807c6891 | RESPONSIBILITY: Supervisor SE/PE/SPE
| note | db1657fc-1c8a-43a9-9ae1-da9fb4a6f530 | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | 792eb427-9533-46da-98bb-96a835f66150 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.1 Set out the works for each drainage system
| note | e32d6d0a-b616-415d-b512-ab896dde835d | REFERENCE: AS 2566
| note | 314d7631-393d-45be-bfba-2bc3ef61b906 | IFC Drawing
| note | 58bc7c28-fe59-4357-9fed-21ce38643b24 | ACCEPTANCE CRITERIA: Establish Pegs (or equivalent)survey marks to identify location, length, and levels as per design drawings and schedules and check if:
| note | b50b6074-1798-4c9a-9554-8c09ca7bbd2e | Inlet/outlet heights fit in with natural surface (i.e. not too high or low)
| note | 7751c053-a147-462a-ab91-87116d7da0ca | Inlet/outlet location suitable for water-course (e.g. no drainage problems)
| note | 37feabc2-e0ef-4829-a2a5-26eda6d6bfdf | Pits relocated (through RFI’s) in order to avoid cutting of pipes
| note | f87e5010-d989-4bf6-9597-747357be9a88 | METHOD: Inspection Survey
| note | 660613ab-098d-4185-b473-a8b3f0db0178 | FREQUENCY: Once
| note | c10735b7-4ab7-43d0-91d2-7a0f082d66a4 | CATEGORY: IP
| note | 6c53ac10-873d-45a3-a313-5e83891cd509 | RESPONSIBILITY: Supervisor SE/PE/SPE
| note | 64f74975-72ed-4b6e-a5b3-7d8691cdbc4b | VERIFYING DOCUMENTS: This ITP
| textbox | 899e2b22-5d8d-4022-b949-0348557b1831 | Date Completed:
| checkpoint |  | 3.2 Confirm position of all Drainage line/culverts
| note | 313ed3c1-bdc6-45bd-aa42-ceaef741c295 | REFERENCE: VicRoads 701.09
| note | 79bdc775-3a4d-4e1b-94af-b765b936697d | IFC Drawing
| note | c6e20dd7-01e7-45ce-806c-9f8d4b115e96 | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the Drainage the contractor shall confirm the position of all drainage line with the Superintendent.
| note | 7c3a8e6a-7e75-4e2b-ba1e-808d38a55e64 | METHOD: Establish Pegs (or equivalent)survey marks to identify location, length, and levels as per design drawings and schedules and check if:
| note | ac30702a-ce41-46c9-92e8-336031319a2b | Inlet/outlet heights fit in with natural surface (i.e. not too high or low)
| note | dd64abbd-c6eb-4efe-a5b2-cb47585f0dd2 | Inlet/outlet location suitable for water-course (e.g. no drainage problems)
| note | 0067b822-166e-46e4-8e9f-a9559aea3e91 | Pits relocated (through RFI’s) in order to avoid cutting of pipes
| note | 4ba0470d-83f9-46cb-9e7c-83dbe6b9faa5 | FREQUENCY: Once
| note | bf9b8d95-08db-4ddc-965e-fc288d38e3ee | CATEGORY: HP
| note | 254f1958-3770-4801-986a-45d094a67c0e | RESPONSIBILITY: Supervisor, SE/PE/SPE
| note | 718cac0e-8e45-4361-a43f-a5a076e1a676 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 5afe327d-09a7-4534-859a-09d7f8ac67e0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Excavate trench to the underside of bedding to correct width
| note | e1f99e6e-628a-4f10-ac11-e664b94d2b64 | REFERENCE: AS 2566
| note | 6b15f884-4989-4791-a068-ff2316d6d4ca | IFC Drawing
| note | 7a7777a7-03e3-4017-b20b-eb60f5b390f0 | ACCEPTANCE CRITERIA: Width and depth of pipe trench as per AS 2566.1. Refer to right table
| note | ea5396e3-801b-4bb7-8b11-1a408afafb30 | For other structures, the clear width between structure wall & face of excavation is ≥ 300mm or 1/3 height of excavation face, whichever is greater
| note | b522f504-17aa-4055-af4a-8a9155d0ede1 | Trenches > 1.5m deep are either shored or benched
| note | aa90ff0b-bd13-47d0-a93e-a5a981bbc5c1 | The excavation is ≤ 50mm beyond the specified width and depths of the trench
| note | 723c7d74-12e7-47ca-ba06-6ebb0c16ec31 | For pipes under embankments:
| note | 01ded3bf-bddf-4016-bf81-507e59431edf | the first embankment is constructed to a height ≥ 0.7 times the external dia of the pipe above the top of the bed zone, and for a min lateral distance past the boundary of the trench of 2.5 times the external dia of the pipe. Trenches done after the construct of the embankment to the level of the underside of the Selected Material Layer
| note | e147e374-364c-460e-9e33-3d9158aab821 | No welding/ anchor block systems etc. required. This system is just a simple lubrication of the end of pipe.
| note | 9ee36546-8302-400e-bc8a-da5fb2f90d87 | METHOD: Inspection
| note | 75c6e8e1-30c4-400e-b0e9-279d7d9903a5 | FREQUENCY: Once
| note | 5c53dcda-34a9-4986-b76d-b24ea5dae398 | CATEGORY: IP
| note | 7cec564c-dec6-4819-8530-684f0482ce67 | RESPONSIBILITY: Supervisor SE/PE/SPE
| note | f0ce14b3-ab32-48dd-83a4-d47bbfcc64b1 | VERIFYING DOCUMENTS: This ITP
| textbox | 4c756e49-b8a0-48b8-8ed1-a39f5020aaef | Date Completed:
| checkpoint |  | 3.4 Install pipes in accordance to manufacturer’s instructions and design documentations
| note | 2c3f0e1e-fa36-4104-a8f1-14bfb17e4697 | REFERENCE: IFC drawing cable running plan
| note | 0fa51632-d1f4-4039-8b2a-5840d41fdfd0 | ACCEPTANCE CRITERIA: Pipe laid from inlet to outlet
| note | 2b7d74a1-8239-40f0-8343-35391fc33d86 | Pipe support conforming to AS2566
| note | 98e1d005-9700-480f-9a4e-fd3bac73a39b | Polypropylene Pipes (Blackmax or StormPro)
| note | 3f03b958-0c06-419e-9fd9-0999e63da269 | Correct size and class of pipes are laid with socket end placed upstream
| note | e2d8f305-51bb-46d7-ba25-dde6dae40b81 | Pipe ends cleaned and rubber rings / bands installed as per manufacture’s recommendations
| note | 0aef4b8d-2797-473d-9939-fcc7b58a9142 | Inlet/outlet heights fit in with natural surface (not too high or low)
| note | eed9f24c-7955-422c-a20b-7c6f7a9d6afe | HDPE
| note | b39ee4f1-d4d9-4a47-b244-e39f8c16ce97 | Pipes to be cleaned, beaded and jointed by suitably qualified personnel.
| note | 54694fa7-149e-40c2-8dad-cdf03efd4503 | Electrofusion Welding or Butt Welding of pipes permissible.
| note | 765a4f95-1147-41f0-bbfa-a7b0e3469eec | Joints allowed to cool prior to lifting or shifting into position.
| note | 87ef509d-352f-44ba-8b12-3facaf8b76e5 | Anchor blocks provided at 3m spacing max., at bends, junctions and where shown on drawings
| note | 0292d09d-0376-4599-ac88-c7ba430875f9 | Subsurface drainage installed at the discharge end of pipes
| note | b2fa4945-30c6-490b-9fa8-703829b90f06 | Add check lengths as per the minimum required
| note | a6cf353b-3cc6-4421-95dd-35da7f37e304 | Width to edge of trench, 150mm
| note | 1d9d6854-df5c-41fb-b3b3-d8d3c9ead2f3 | 300mm above pipe with selected backfill material.
| note | 731ecd67-6804-4923-903b-719296b6f68c | METHOD: Inspection
| note | c185a133-49ad-4ee7-b0d5-181c58cdf408 | FREQUENCY: Once
| note | e35fdf51-d23b-4ac7-9474-320bd42ae92b | CATEGORY: IP
| note | 0974cb9e-b5da-405d-be68-67beb518b291 | RESPONSIBILITY: Supervisor, SE/PE/SPE
| note | 913172bb-3d0f-4579-9d48-467c88d7fd0d | VERIFYING DOCUMENTS: This ITP
| textbox | 9394a415-d336-4ca6-b53a-4c5fc284dd96 | Date Completed:
| checkpoint |  | 3.5 Verify that completed pipeline against survey marks design level and alignments
| note | 5aa097e6-11a5-4602-a4d0-743231f82acb | REFERENCE: AS 2566
| note | fa97f2d3-2bbf-4f69-bb8a-735d62e42a7a | IFC Drawing
| note | 623724f3-4d53-4027-bafd-3a05977c8a74 | ACCEPTANCE CRITERIA: Completed pipeline is inline and within ±200mm of location (plan)
| note | b5611861-fb27-4765-b172-a60f25544aec | Invert level are within 20mm of the design level at any point
| note | f1b238dd-979f-41e8-a197-f46f02e984b9 | To be checked at each pit and headwall
| note | 302ad8b0-bf52-4f5d-aa55-6a4dba48dff6 | Horizontal Position for Pits in Kerb to be
| note | c36d6d15-88ba-4617-8757-da30472608c6 | +-200mm longitudinally
| note | de6ea872-1956-454e-9d20-6be88a7eb2cc | +-20mm perpendicular to kerb alignment
| note | 25e09c95-235b-4875-bb4c-0702258a2a00 | METHOD: Inspection
| note | 7b335692-898b-4d55-88f0-c7749cafa557 | FREQUENCY: Once
| note | aabc43d4-c92f-4d2a-841a-d9e7e80458ac | CATEGORY: IP
| note | fd45f9db-2249-4f7e-b721-138d7d99c859 | RESPONSIBILITY: Supervisor, SE/PE/SPE
| note | 1984ea58-ab20-43c5-b95c-25fe428cac3f | VERIFYING DOCUMENTS: This ITP
| textbox | 4ef91834-a358-448a-a4ee-7b32d2e29bf5 | Date Completed:
| checkpoint |  | 3.6 Place and spread haunch, side zone, overlay and backfill embedment, replacement and backfill material,, compact and test to specified densities
| note | 02a06767-9a4c-4642-98b0-b671b58f8bf8 | REFERENCE: VicRoads Spec. Cl. 701.26
| note | 4565140c-3989-40d3-b8ad-f8a1cc596b86 | ACCEPTANCE CRITERIA: Placed in 150mm layers and compact to 95% std compaction
| note | fbc6c499-156b-49c8-b98e-bf2d8553e343 | If stabilised sand used, the materials been vibrated to obtain complete placement & compaction of material under & around
| note | 0ec85626-5295-4313-a105-4fbb3c4def9b | pipe and the placed stabilised materials are firm a day after placement
| note | 5ab63b00-047e-46e0-9ba2-c06d101896b4 | If 10/14mm aggregates used, the materials been vibrated to obtain complete placement & compaction of material under & around pipes
| note | a5b30e1a-629c-4ae4-ae22-03af03802c45 | METHOD: Inspection
| note | 4d69f088-8ca6-4fb1-b10b-b3a07d8104fe | FREQUENCY: Once
| note | c460bb3e-e7f7-4eb3-9a57-87eb38fa957c | CATEGORY: IP
| note | 2aae5a66-ff58-47ad-9306-fec4007a6026 | RESPONSIBILITY: Supervisor, SE/PE/SPE
| note | 13a41431-515a-492d-8590-fbf83b970186 | VERIFYING DOCUMENTS: This ITP
| textbox | cae64879-09cb-4884-8659-48ce5faa0f6b | Date Completed:
| checkpoint |  | 3.7 Inlet/Outlet Structures
| note | 905120b7-094e-4f3d-b849-a71bc41c4471 | REFERENCE: VicRoads Spec. 701.23
| note | e9ca7fd2-3248-4a44-a1d5-e535b40b4b37 | ACCEPTANCE CRITERIA: Refer to Pit supply & installation ITP
| note | ae0ea5c2-7f23-40b9-9fe3-15e9a639f637 | METHOD: Inspection
| note | 2d305b50-3394-4e89-bf12-b6047337e044 | FREQUENCY: Once
| note | 9f872b3c-3dac-4bab-b1d7-7edef3ce06dc | CATEGORY: IP
| note | 39be4a7e-3bad-47f9-8689-80dbe74a9e4d | RESPONSIBILITY: Supervisor, SE/PE/SPE
| note | 13fca8f3-b1dd-43b4-8549-648075b2390f | VERIFYING DOCUMENTS: This ITP
| textbox | b636545e-c11a-457a-b2f6-b1622173cfef | Date Completed:
| checkpoint |  | 3.8 Flushing System
| note | 171fc209-e59c-450a-bbc9-182479618f99 | REFERENCE: VicRoads Spec. Cl. 701.26
| note | a681dcb2-2ca3-4166-8c43-fa25ad8ee20c | ACCEPTANCE CRITERIA: Each Drainage/Culvert line is to be flushed clean from end to end on completion. and maintained in proper working order.
| note | 1d634a92-7b43-4e38-b3b3-07f8276b7788 | METHOD: Inspection
| note | dbcc1ba4-90d0-47b3-b2a1-d323499692a0 | FREQUENCY: per lot
| note | 7b636c43-2231-4f86-b701-ec74ba1fe0f2 | CATEGORY: HP
| note | 69697803-5547-4190-967e-d747c29a1757 | RESPONSIBILITY: Nominated Authority
| note | 2f86cd0c-056c-42a3-8305-6bd7a4f8714d | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 3c4fd8e3-7f3b-462a-9fc7-f574a849ae26 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.9 Engage pipe inspection video subcontractor to take footage of all completed new pipes.
| note | fe049b2f-2f47-470f-8294-95ac2fa3f457 | REFERENCE: VicRoads Spec 701.28
| note | 43a583b8-9bae-47c7-8ba7-9afbcd6e5743 | ACCEPTANCE CRITERIA: All Drainage line constructed shall be inspected after completion of earthworks to subgrade level and prior to construction of pavement layers, by independent Testing Organization using closed circuit television(CCTV). The report shall be provided to the Nominated Authority
| note | 486539a2-7ec8-404f-accb-b9accdf60d12 | METHOD: Inspection
| note | 67f65df3-fbc6-4628-b098-f27844cbf067 | FREQUENCY: per lot
| note | 3b337953-f68e-43f9-8a4e-f2c5e083df51 | CATEGORY: HP
| note | 8a6543de-f612-42af-a49b-9330278ef799 | RESPONSIBILITY: Nominated Authority
| note | bb12f44c-f47d-45ef-94da-437d9d4b9746 | VERIFYING DOCUMENTS: ConQA Hold Point Release, CCTV Report
| textbox | eaaef8fc-8d8d-4986-9d86-33ee0e24fbff | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.1 As-built Survey (if required)
| note | aa602475-af14-422a-963c-b859b06c2151 | REFERENCE: As Built Drawings
| note | f05ae7d4-be39-42b5-8805-afde102f0309 | Asset Change form
| note | 122ad4b1-7eb0-4a82-8e30-694dcf3c1a16 | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
| note | 7ddba25f-70d2-4518-8439-4f31dce95945 | Attach: Survey Report, Engineering Asset From
| note | 0da0bc90-e995-4858-9f83-df284ed9b727 | METHOD: Survey Document Review
| note | b60e2b3f-6eac-4bd0-9c67-9999cf6ec967 | FREQUENCY: Per lot
| note | 2e2a56e9-0482-43b5-88fb-c9acf8eb8297 | CATEGORY: IP
| note | 3ba830ee-a409-4c13-b866-2d5d5cd2ca34 | RESPONSIBILITY: Supervisor SE/PE/SPE
| note | e4234917-5963-46ed-9fde-9ca852adf6f0 | VERIFYING DOCUMENTS: This ITP
| textbox | 6a7a6171-bb3a-4099-b7af-aec0d4491099 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | a719f301-3975-4e24-8d77-de0341a850fd | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 0d638011-2d22-40c1-9365-049104a86fc3 | Name:
| textbox | 46a0871e-c2ee-4247-b7c5-2fbede8db41a | Position:
| textbox | a73417bd-f969-4b2f-b6fb-eae1ac93df72 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Delineation Fencing Rev 1 | itp | ITP-CIV-Delineation Fencing Rev 1 | 7f920090-68d6-4ba2-90da-3bf9e106e32a
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 1a79dcff-d728-5641-b39a-8af26a0da034 | Document Title: ITP-CIV Delineation Fencing
| note | 52b0cc87-f177-5f64-9db0-9f4de0bc3011 | ITP Description: Delineation Fencing
| note | 50805fc9-0cd1-5e88-a6aa-efefbddf8ea0 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | aa578996-70a3-5f2d-8a89-9f45e78b7d32 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 64bcd25e-a497-5e83-9ba2-18eb4c94102d | Revision Number: 1
| note | 79e765a7-4fc3-5c4a-aac3-1806f86c52ca | Revision Date: 19/08/2022
| note | 39dcad73-894a-5c01-bfee-1b29755b7ee9 | ITP created by: Ethan CARUANA-SMITH
| note | 8da5f60b-0e5a-5eee-a703-292fa1c549b4 | ITP approved for use by: Pradeep TALASILA
| note | c7abe76b-35eb-55df-a7d3-faa433d803b2 | 1.1 - Non Dependent - IFC Drawings
| note | 7ea46ef6-4f57-5bf2-9acc-1e6188b2df38 | 1.2 - Non Dependent - AS1657
| section |  | Materials
| checkpoint |  | 2.1 Concrete
| note | 0b404621-ad3c-5b9b-845c-2277d56e58d5 | REFERENCE: IFC Drawings
| note | 3888f0f8-277b-5b4b-8cba-cc697095968c | ---------------------------------
| note | c0913719-e7b6-5206-a656-57679f1a4bf5 | ACCEPTANCE CRITERIA: 25 MPa concrete to be used as per IFC drawings.
| note | add2f606-fe22-553e-8ea1-dbf259559f3d | ---------------------------------
| note | 77d3d638-2863-549a-adb6-c4cfd96cc50b | METHOD: Document Review
| note | 62803d03-693e-5b4d-b0ef-325358bc3919 | ---------------------------------
| note | c038994c-d272-5160-b1ee-158f622e89c5 | FREQUENCY: Each Mix
| note | 6d64092d-67af-5b96-88bf-9bbd9278c7b8 | ---------------------------------
| note | c6580e24-54aa-5c08-923c-d914a988f6f6 | CATEGORY: HP
| note | da8f6a33-21f7-56be-a66a-8de711f5f6c5 | ---------------------------------
| note | 2b0fb75c-c88f-5a7b-b66e-cb742a5e4f29 | RESPONSIBILITY: SE/Site Supervisor
| note | a83a93fd-1d20-5cc8-8b30-a899f10b3eb9 | ---------------------------------
| note | 0b77f49c-8d9c-58c0-b3c3-b74f805e0b8e | VERIFYING DOCUMENTS:
| textbox | 0e2739c4-87af-5c30-9cae-d92bb31de5d2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Steel components including posts, mesh and fittings
| note | 27a7a19f-bf14-5a6b-b2a9-3cfd1ab3ae42 | REFERENCE:
| note | 7e65f88a-5760-5b0f-8771-c7e727dcd9c5 | IFC Drawings
| note | 7cd7ddf0-9a39-55c6-9451-337a5db41a38 | AS1657
| note | 9400f075-6ecd-599d-9d09-da140bcb39d0 | ---------------------------------
| note | 8276e2c0-7e94-5093-98ac-72ac693412c1 | ACCEPTANCE CRITERIA:
| note | e69a41ab-1596-5335-a6e6-80d50df2d95c | All Steel must comply with Australian Standards.
| note | 9c525750-dde8-5aca-8a5b-dbb648ebcddb | Steel section sizes must be checked on site.
| note | b719a92d-9a9c-5dd5-ba4a-043708943356 | Steel posts to be CHS with a grade of C250
| note | e18fc848-54f5-5553-bb95-237a7d2d3cd1 | Black PVC finish
| note | c069b6af-2bce-5e4f-a1c4-c5917daf49f8 | ---------------------------------
| note | e6e8b677-971e-563f-a71b-93d9cd1a3fcf | METHOD:
| note | dcebf419-acd5-52fa-92b2-39057d19e9e6 | Document review
| note | 3ce4d142-f27a-5270-9371-fd395534cd67 | Visual and Measure
| note | 05f37412-b762-5771-83d1-0d78b980147a | ---------------------------------
| note | a7745a34-15df-5403-9bd8-db0ae955dec0 | FREQUENCY: All elements
| note | 9bfff49c-77dc-59af-b850-e1a6bd66f03a | ---------------------------------
| note | bd649cfe-6a3d-5f02-8ed4-c9b25fe7b946 | CATEGORY: IP
| note | f59a9843-8e5a-54d8-8be4-53d6f87bbdb8 | ---------------------------------
| note | 5ad22207-37f0-5dfc-a2a3-d5a7f6df0626 | RESPONSIBILITY: SE/Site Supervisor
| note | 818e2148-6bb4-5696-ad44-123effae9918 | ---------------------------------
| note | 1720830a-dcae-534e-9db5-6c7eb493949c | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
| textbox | 3a5b3f47-e47d-5cd9-bda8-d92727503e9d | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | 662c9e1c-9502-555a-b8ea-56ffa4feab6f | REFERENCE: IFC Drawings
| note | 2d9a9216-b0ec-5d5f-ad96-91c7f3772b82 | ---------------------------------
| note | ad3ee608-5236-5560-afa1-1df67d5c3f17 | ACCEPTANCE CRITERIA:
| note | bc26ab96-84dc-5b33-8e19-e71bacdd86c3 | Survey to set out the following but not limited to: existing services, and fence start and end points.
| note | 859a7802-2f0e-5c42-94b8-ef5e19e09d9f | Offset checked against the running edge prior to installation of posts.
| note | 89619afb-3c8b-5a78-be0a-0314e0813976 | ---------------------------------
| note | 0e6c6199-bad0-559a-82fc-28d9126f8ca8 | METHOD: Visual and Measure
| note | b02de00d-6903-5d1c-bfe0-a863a85632cf | ---------------------------------
| note | 61f23b42-f192-5481-9331-8a04c9761f1a | FREQUENCY: Each element
| note | a084e981-7683-5b39-acff-3e283a915c62 | ---------------------------------
| note | 0bd693ec-9b6a-50e3-b19f-88505c64c2ff | CATEGORY: IP
| note | ac84f0d2-76f1-5906-84bd-0363942b21ea | ---------------------------------
| note | 50132f93-a90b-59f3-9eaf-eb5e70d99587 | RESPONSIBILITY: Surveyor, SE/PE
| note | d1a64698-65b4-5db7-8c5e-38fe78c6c794 | ---------------------------------
| note | 4d0b4a2a-df7e-53a7-86d0-4862f1a1a66e | VERIFYING DOCUMENTS: This ITP
| textbox | a3f73400-5d00-54ee-97f9-0dd9d033727d | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Excavation works
| note | 593c7b3d-8956-524f-bafd-87e64c3c82ac | REFERENCE: IFC Drawings
| note | c8a21acb-52fe-5107-aefa-b99f6c241fd5 | ---------------------------------
| note | 54d7dd87-756d-541c-b1ca-728b44abc204 | ACCEPTANCE CRITERIA:
| note | 8756518a-0b6d-5417-a495-6d7d32bd301a | Excavation completed by auger outside of service working limits.
| note | a0f070a7-8362-5e89-9f30-da65b2877ef2 | Follow asset owners guidelines for work around their service.
| note | dce14061-e5d1-583e-91d6-bc736d557ee6 | ---------------------------------
| note | 110ebfa8-f6cf-5112-8a9a-315d3208d197 | METHOD: Visual
| note | 46d7552e-7d50-57a7-833f-2b9cfcd9b17c | ---------------------------------
| note | 6e6d777a-46b9-5ca7-8a57-03f97c432f3d | FREQUENCY: Each fence footing
| note | fae67ce1-0e07-5792-8643-05e6e54818d0 | ---------------------------------
| note | 2592b737-c82e-541b-bba4-33325f15fc79 | CATEGORY: IP
| note | 063a519f-e976-5c78-b61a-8f44ac598098 | ---------------------------------
| note | 2984ef70-8ada-5c3d-b085-fcbfb1735479 | RESPONSIBILITY: SE/Site Supervisor
| note | bcc846fd-f63d-5e9b-a30a-560ee18961c7 | ---------------------------------
| note | 367392f4-ae8a-5907-83b4-7a784cb114c3 | VERIFYING DOCUMENTS: This ITP
| textbox | 773d0705-1bb9-5e56-849c-d7197b4c2f9b | Date Completed:
| checkpoint |  | 4.2 Ground Conditions
| note | 5bfd5f1f-72cc-5f54-a738-40fa6788a6d5 | REFERENCE: IFC Drawings
| note | 633ddde1-fa3a-567a-9cd6-73d0671c0cb1 | ---------------------------------
| note | 8cd0406a-77ed-525c-a71d-4186b9da4e7a | ACCEPTANCE CRITERIA:
| note | 99364610-eb15-585d-845b-4f41dbde6147 | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
| note | a108da20-20d7-5653-86df-22199f93b297 | If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
| note | 2cd2986e-0982-58e1-a343-3ead7f96c76a | ---------------------------------
| note | aec0704e-0b22-5b02-aa5b-27cdd084eeb5 | METHOD: Visual
| note | d734b1a0-d2f4-5f2a-a014-591648b9185e | ---------------------------------
| note | 3c0411ca-b913-54c8-b38f-0013f32538ad | FREQUENCY: Each post
| note | 6225f059-5cd2-5501-9f9e-dd457b91ecc9 | ---------------------------------
| note | 5a7ad6a7-c625-5d32-8212-93c170e92fd9 | CATEGORY: IP
| note | 15a821c0-2fde-508f-a839-67078d5b677b | ---------------------------------
| note | 21f336a0-5f20-5930-a6e4-f6150f27d354 | RESPONSIBILITY: SE/Site Supervisor
| note | 078921a0-793f-5e14-81dd-6b16a73347ca | ---------------------------------
| note | 0c667b20-b1ef-5ef8-95f7-033fed423639 | VERIFYING DOCUMENTS: This ITP
| textbox | fa937035-19b3-5a42-b43f-6e9023c2a9f3 | Date Completed:
| checkpoint |  | 4.3 Fence Footing
| note | 3726e863-5521-537a-95fd-7642e9844160 | REFERENCE: IFC Drawings
| note | 06856277-336e-5204-aaa0-315927c1d465 | ---------------------------------
| note | 44949912-325c-5af7-8f8c-08e750001cc2 | ACCEPTANCE CRITERIA:
| note | e14b7a1a-629b-52f0-a321-5c0c0da3627d | Footing dimensions 600mm deep x 300mm diameter. Every second footing to have dimensions 1200mm deep x 300mm diameter.
| note | ee6da5b1-2006-5d4d-bf61-b5b18d50f61f | 25 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per VicRoads Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample.
| note | 5a4b1bf5-77a1-54c4-bde8-4879b565cf22 | ---------------------------------
| note | ff1f905a-c821-551a-849d-aa597e9a2bac | METHOD: Measure
| note | 93ea2197-359a-5e81-b9c7-add5d54a5fc2 | ---------------------------------
| note | d57c5c5d-8fa6-5868-993a-36e97620d79e | FREQUENCY: Each footing
| note | 4c3966a2-25b3-556b-8b5c-71ff79bbc27f | ---------------------------------
| note | 08d06f31-2673-5854-b2d9-7804d1dfea20 | CATEGORY: IP
| note | 24b540a1-f998-58e1-b529-d81ec2a8210b | ---------------------------------
| note | d3649d5b-bcc7-5ab7-a71a-b8283af44c53 | RESPONSIBILITY: SE/Site Supervisor
| note | a210bcf0-4c83-5059-85e4-8e49b499d363 | ---------------------------------
| note | 585d6de3-2ac6-5338-8ff7-607bd2908c33 | VERIFYING DOCUMENTS: This ITP, Concrete Dockets
| textbox | 007527dc-7e86-57df-ac40-3b963b7acec2 | Date Completed:
| checkpoint |  | 4.4 Fence Post Installation - Non-sleeved
| note | 0634aa19-79ec-5da3-bbde-79636f8e225f | REFERENCE: IFC Drawings
| note | b9ba164f-aecb-5369-a8eb-edabe6644266 | ---------------------------------
| note | e9edd99d-045d-54e0-9960-4650a8cffa80 | ACCEPTANCE CRITERIA: DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover.
| note | 7a63a7f1-a121-5e8e-9c13-257111611cea | ---------------------------------
| note | 7adb5361-d075-5972-b6af-915b6e210fb1 | METHOD: Measure
| note | 9dcd9c91-724b-5874-9d0d-2d10d6904f9f | ---------------------------------
| note | a21b1240-da18-53fe-8291-776bc68fca6f | FREQUENCY: Each post
| note | 07423a80-5cf6-593e-8c20-26945835940a | ---------------------------------
| note | d440fc5d-2891-5eaa-b09e-980abd175049 | CATEGORY: IP
| note | c84400a5-8c5f-5dbb-84a1-347bcf259bf4 | ---------------------------------
| note | 024d8803-0694-55ee-a387-580317a6ee1e | RESPONSIBILITY: SE/Site Supervisor
| note | 993cc141-855d-5420-9011-c26b065a4bcd | ---------------------------------
| note | 0db1ed10-d1bc-53e0-b11e-fa10fad07fd7 | VERIFYING DOCUMENTS: This ITP
| textbox | b42c5745-9cdc-515a-9636-1488679a2f89 | Date Completed:
| checkpoint |  | 4.5 Chain Wire Mesh Installation
| note | b8fcbe90-7f9c-54b8-8f69-c330ed6998ec | REFERENCE: IFC Drawings
| note | d8ea2091-68f2-5e91-89d2-2731b58f95d6 | ---------------------------------
| note | 1f671248-e710-5df5-8a73-cd9ecff77330 | ACCEPTANCE CRITERIA:
| note | e01341e0-8d70-55c6-aadb-23fc698200e8 | Chain-wire mesh 1200x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications.
| note | e5b4c147-798a-5799-90e5-5579e08bc19d | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
| note | ace310af-868b-5847-9a86-20d2365c89bb | ---------------------------------
| note | 543ba911-d902-5621-9fe4-815ec5962079 | METHOD: Visual
| note | 78299cfa-72cf-5ed1-bae6-7bffdb528074 | ---------------------------------
| note | 61d26862-7331-520a-8931-f5ec34ab6444 | FREQUENCY: Each element
| note | 8c201077-cc8e-5f31-9501-930091628e59 | ---------------------------------
| note | 3ca77bc3-1b1d-54fe-8275-99f040c10f48 | CATEGORY: IP
| note | 73348a18-520a-59c5-98d3-fb30d5d6c8c9 | ---------------------------------
| note | 5b34605e-ffaf-5ce3-8887-1521235fac94 | RESPONSIBILITY: SE/Site Supervisor
| note | aa10b5f6-1921-588c-9f48-31a2c500aec0 | ---------------------------------
| note | 90df4d74-6445-5848-ae8d-07336a7f401b | VERIFYING DOCUMENTS: This ITP
| textbox | 0e81ef8b-7948-5f08-b225-74fa183182e3 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 As-Built Survey
| note | f1b92a81-1971-5026-b33a-a5d0bcea5147 | REFERENCE: IFC Drawings
| note | d989ff2b-9796-5f53-8ee6-1128f9b25591 | ---------------------------------
| note | 9252fa4f-d8b0-5b12-b8a0-3a117631735e | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure spacings do not exceed standards.
| note | c5d7f289-d1c7-5b8a-a3d0-d23e67e4bdc6 | ---------------------------------
| note | 651b8d4a-d797-544d-93d7-1329defffee1 | METHOD: Measure
| note | 97c6f21c-9cca-56ec-a461-99448cf5b839 | ---------------------------------
| note | 7af8f343-2019-5c73-8888-1b16606eb12b | FREQUENCY: Each lot
| note | 42a40041-d1dc-5e52-8464-ead5f5de75c9 | ---------------------------------
| note | 650384b2-33d7-5852-a6b7-c4c63a301d1c | CATEGORY: IP
| note | af507b87-1649-5d6e-98ef-51bbeac7f69f | ---------------------------------
| note | 2a482dbf-b995-5f0e-a679-2757be54842b | RESPONSIBILITY: SE/Site Supervisor
| note | db10d699-12d9-50e2-b688-4fd2c972fb8f | ---------------------------------
| note | f887bdab-7e66-5079-83e1-a171383d8e82 | VERIFYING DOCUMENTS: This ITP
| textbox | 7e1705e3-ce08-5116-ad03-796289ffb26f | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | fd4a38a5-d83e-5f57-938d-5ddc1854c5c1 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 71cfc3fd-64c1-52ff-bbc1-d37dbdc2f847 | Name:
| textbox | ff733f43-bf67-54bf-845d-f68898ce6dfb | Position:
| textbox | 4dd05f61-28e2-5638-a25d-a0333d511bac | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Horizontal Directional Drilling (V-Line) Rev 0 |  | ITP-CIV-Horizontal Directional Drilling (V-Line) Rev 0 | 80bd45bf-9889-476b-860f-832902cd2d48
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 2b3a785d-40a5-42f8-91cd-56e337823d1c | Document Title: HDD - VicTrack and CSR
| note | 5c2286ea-a659-4bb8-b3d6-a9b6cb883bb3 | ITP Description: Horizontal Directional Drilling (V/Line)
| note | 21909910-0906-4885-9e84-e6bf3bbcf7f5 | Discipline (e.g. CIV/STR/RAIL: CIV
| note | 1854f343-0480-4784-9c26-d20711aa2a22 | Revision Number: 0
| note | 6799c731-fc25-4e5a-a49c-e61a2579fb12 | Revision Date: 22/02/21
| note | b66da7e0-7496-4113-a44e-c2c7f0684d36 | ITP created by: Tom Hudson
| note | db3db34a-077e-4660-a575-c511e6b25a2e | ITP approved for use by: Josie Pavlou
| note | 2498eefa-e215-44c9-bd53-7e24c1fcd867 | 1.1 AS 4799-2009 Installation of underground utility services ad pipelines within railway boundaries
| note | bd13dc7a-1f62-461d-b558-e6abfc393ad6 | 1.2 NIST 2076 Inspection and Assessement - Track Geometry - V/Line
| note | 464b21b3-552c-40b5-aea3-429da9597854 | 1.3 D/17/62901 Design Requirements & Guidelines - Civil Works on, under or over VicTrack Land
| note | d6221f2c-370f-4be5-abdf-4ab4d9b6bc82 | 1.4 NIST 012.2 - Specification for Signalling Supply, Construciton and Installation (V/Line)
| note | bf84eac0-20ef-44c5-ae91-5dcfd5df34bc | 1.5 NIST 012.2.1 - Standard for Construction of Cable Route and Signalling Civil Works (V/Line)
| note | ddc602b7-a09d-4794-a418-b41c88960431 | 1.6 NIST-2706 - Inspeciton and Assessment Track Geometry (V/Line)
| section |  | Preliminaries
| checkpoint |  | 2.1 Pipe Sleeve
| note | 4fd03472-338c-43cf-b2a9-5c6c8188e4f8 | REFERENCE: IFC Drawings
| note | bb4e520f-1ec2-4b59-af0d-7c4bfd8f1258 | ACCEPTANCE CRITERIA: Confirm that sleeve pipe matches the material specified on the IFC drawings.
| note | ce4a56c3-7eeb-4852-b379-f134c1dce64c | Obtain approval from VicTrack for sleeve material prior to construction.
| note | f78d524f-e572-4bc6-b975-dff05aa9d165 | METHOD: Document Review
| note | dde68321-6046-4074-83eb-a6601dc567eb | FREQUENCY: Prior to Commencement
| note | b4b5588c-a3e4-47a5-935f-7827b48440a3 | CATEGORY: HP
| note | 599aae7b-34a3-44de-9865-60b07e6895d4 | RESPONSIBILITY: SE
| note | 4ed1f3b0-2dde-4fac-9dc9-666e68e92a15 | VERIFYING DOCUMENTS: Material Compliance Certificate
| textbox | 5d8d0f45-f7c2-44f7-87af-07e70cfbbc51 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Materials - Draw ropes
| note | e37ab93a-5e0c-42ed-b2d5-1ca18dc1408d | REFERENCE: IFC Drawings
| note | 37b413bb-ee2e-45f2-913b-639f6d3e08b7 | ACCEPTANCE CRITERIA: All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
| note | 63c0f4cc-bcf9-43cb-9cf0-e536ea1373a4 | METHOD: Document review/ Visual
| note | d128f98a-0540-461b-991c-cd14d707df67 | FREQUENCY: Prior to commencement
| note | bb03385e-007c-430c-b4a2-50d3e7af66fd | CATEGORY: HP
| note | da708877-c35a-4444-ba7f-fc45849d92a0 | RESPONSIBILITY: PE/SE
| note | 6d814b0d-bd78-4851-920e-5e867ec8b2db | VERIFYING DOCUMENTS: Material compliance certificate
| textbox | 8e4e7982-1aee-4592-b610-fabd3b99bc34 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Materials - Communication conduits (victrack), Signalling Conduits
| note | c930bbc3-11f1-4d16-bfb8-faa0adbcc0a2 | REFERENCE: IFC Drawings/ TS-SP-013
| note | 72e1c0bc-ccd3-4077-a382-4c72d028eeb7 | ACCEPTANCE CRITERIA: Victrack conduits must be min internal dia 100mm.
| note | 9feb4b14-087a-4c52-af85-91c34ff26607 | Outside of the conduits must be marked with Communications or Victrack communications.
| note | fd86687c-acb4-4134-8ffe-41c42df76646 | Bored conduits must be Class 9 HDPE.
| note | 9822b7dc-42cc-47a9-9d3a-18e1b7445d73 | Signalling conduits must be min 100mm internal dia. heavy duty rigid UPVC conduits to AS 3000
| note | 7776acfc-ca8a-47ab-9ab0-bc30ce5c27a8 | METHOD: Document review/ Visual
| note | 65014103-7ca0-44a3-86a6-4941fd18f512 | FREQUENCY: Prior to commencement
| note | 6bc8d6b4-a7e0-42c0-bbb0-c67376287c08 | CATEGORY: HP
| note | 05ba20dd-58bd-4ef0-a45b-b1bc2f6ac633 | RESPONSIBILITY: SE/PE/SPE
| note | eb245c4c-b6c9-47d3-ae72-3ab9809427ba | VERIFYING DOCUMENTS: This ITP/ Material compliance certificate.
| textbox | 7610fa5c-d731-4837-8231-d91e3f0028b2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.4 Materials - Grout (if applicable)
| note | 2c87fa92-9dc8-4aea-924a-f467d5cbaadb | REFERENCE: IFC Drawings
| note | ecf90f5e-24ab-4cb7-8b0b-b7187d6d9880 | ACCEPTANCE CRITERIA: Grout strength to be 40MPa
| note | 45efe914-daa6-49d3-80cc-2c8c39be2a93 | Grout shall be a high flow, cementitious material.
| note | dc38e1fc-ea22-437d-a252-82187fa84307 | METHOD: Document Review
| note | 9d2575b9-c643-4d11-965c-936e7fbe460c | FREQUENCY: Prior to Commencement
| note | 7264d4f8-2394-4b11-ae61-780079c978aa | CATEGORY: HP*
| note | bfbf11e7-65be-47ef-a4cb-98fb577cd5a7 | RESPONSIBILITY: SE
| note | 6be859b6-91e0-4998-96fc-3b7f61735993 | VERIFYING DOCUMENTS: Material Compliance Certificate and TDS
| textbox | d618a85f-a016-4109-8d02-486c05f3a626 | Date Completed:
| checkpoint |  | 2.5 Drilling Fluids
| note | c5812a86-89f7-4a63-bf9a-bede56d55936 | REFERENCE: IFC Drawings
| note | cce9d10a-e5c8-48bd-bc33-438e84d09a9a | ACCEPTANCE CRITERIA: Drilling fluids must be of the polymer variety, Bentonite shall onot be used as a drilling fluid.
| note | 8272a40d-e6b9-40e8-8c9b-74b369a5801b | METHOD: Document Review
| note | aaafcd0e-f8f6-422d-be48-15902e452b0e | FREQUENCY: Prior to Commencement
| note | 0d92b33f-050f-4eb3-a2ff-a10220b2952a | CATEGORY: WP
| note | 3a1f1ec4-a410-47e5-ab07-65650c5f8198 | RESPONSIBILITY: SE
| note | d1953116-81de-445f-ad78-9f3c7696a246 | VERIFYING DOCUMENTS: Material Compliance Certificate
| textbox | 282af31b-4cb3-4d2d-8fd7-3c3765b7e1de | Date Completed:
| checkpoint |  | 2.6 Marker Post and Marker Plate (if applicable)
| note | 69328eae-187b-4db1-852f-7323d316651d | REFERENCE: IFC Drawings
| note | a51cfb1c-7292-48b4-8a34-e5fd51ab2384 | AS4799-2000
| note | 9782a501-4203-4466-bdbb-710c3ed1af47 | ACCEPTANCE CRITERIA: Be of non-combustible material for the marker plates and of at least fire-resistant material for the pole.
| note | 3c5201f4-fc1c-4c38-b216-d62e12efd405 | METHOD: Document Review
| note | ec826b89-d1b8-4a11-abbb-c0ebfdec4e76 | FREQUENCY: Prior to Commencement
| note | 672f5452-d8aa-40d2-84d1-83360a600794 | CATEGORY: WP
| note | 6c2a108e-3ec4-402e-b2c1-11f1e73e0dc2 | RESPONSIBILITY: SE
| note | d64d4f3b-4bc8-48fc-910a-1f04e74f6ff9 | VERIFYING DOCUMENTS: Material Compliance Certificate
| textbox | e5a97f41-21a6-457d-8930-c20bc2bdc3d3 | Date Completed:
| checkpoint |  | 2.7 Poly Welding Qualification (if applicable)
| note | c354a048-1c6d-4706-a436-5d6dc1ee346e | REFERENCE: IFC Drawings
| note | 9d252a4c-02fc-4f9b-8a99-7982eef42be2 | ACCEPTANCE CRITERIA: HDPE welder qualifications to be supplied
| note | 2196f460-535a-4707-ab28-46d2b754125b | METHOD: Document Review
| note | b467f649-76c3-4884-83cb-e20d4159a73e | FREQUENCY: Prior to Commencement
| note | f3e69d07-ba44-4673-967e-0734901d4ef6 | CATEGORY: WP
| note | 31060c68-a43e-4474-adab-554412d337c6 | RESPONSIBILITY: SE
| note | 9a5812fc-a437-4345-93cc-bf69eafe26c9 | VERIFYING DOCUMENTS: Welding Certificate
| textbox | d84e74e0-0bd3-4866-a8ae-cab28e76e656 | Date Completed:
| section |  | Pre-construction Activities
| checkpoint |  | 3.1 Survey Set-out
| note | 2341c582-194a-4cbc-9da2-bc78020ddcb5 | REFERENCE: IFC Drawings
| note | 0cc21995-0865-49c5-9b2b-5fcd2c619868 | D/17/62901
| note | 71341cdd-87ed-4b07-ab8f-f162ad43ef98 | ACCEPTANCE CRITERIA: Set out line and level of drilling works.
| note | 121d95cc-64fb-43b6-8339-b7ea93df5729 | Survey to mark out existing services.
| note | 678ae509-2d3f-425b-a630-d4f5b925bb77 | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
| note | 4b6f48c4-3298-49cd-8aea-6db7d8e9f67b | Sleeve must achieve a min. 2000mm verticle clearance to tracks. Check FSL of track after lowering works
| note | 7a74a8fa-d98e-476a-882d-11828fdfd92a | METHOD: Measure and Visual
| note | 8fb28c85-c304-4b03-8f74-afce474cd3c5 | FREQUENCY: Each element
| note | fd728bc8-3357-4e8c-94f2-6fda04ce6546 | CATEGORY: IP
| note | aec0c1e1-b0ca-4a6a-a181-a33cb8d64976 | RESPONSIBILITY: Surveyor and SE/PE/SPE
| note | f584968e-7964-4979-a23b-42f8bbf84b00 | VERIFYING DOCUMENTS: This ITP
| textbox | bfb71014-fc96-4507-92f0-1a19b6f65231 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 4.1 Drill rig setout
| note | db0166e2-41a2-413e-b9ee-75e7a02a47d4 | REFERENCE: N/A
| note | a65056ce-b1bf-4aad-94ec-1e86bf774c40 | ACCEPTANCE CRITERIA: Location as per current Drill shot plans
| note | 8cbd7e4f-f0c4-4138-9b2b-60a50c207da9 | METHOD: Visual
| note | 5ef70d38-6ac9-4612-ad32-c5aa3f6b51d9 | FREQUENCY: Prior to commencement
| note | dbf75564-f4db-435b-9fa2-e99668973c98 | CATEGORY: VP
| note | b2e9a40b-5971-4ddf-bf78-e5a24213c2ed | RESPONSIBILITY: SE
| note | 3125d71f-1c3d-49ff-ac0f-24fcff081748 | VERIFYING DOCUMENTS: This ITP
| textbox | 5b8ae2a7-6894-46dc-97c2-a01a488a9afe | Date Completed:
| checkpoint |  | 4.2 Ground Conditions
| note | 8d4dc07b-5fca-4850-ac7f-d27fc5d3822b | REFERENCE: IFC Design Report
| note | 3b18c569-3a23-44a9-b0f1-665cce489c69 | ACCEPTANCE CRITERIA: Assumed ground conditions are as per site geotechnical report.
| note | 5fef4952-5ffb-48e0-8cd4-f7f999a37ff6 | Geotech Engineer to be immediately notified if the excavations encounter different materials than expected
| note | b7e7f433-754d-4f7e-8d9b-22aaf7de1fe5 | METHOD: Visual
| note | 99c288c0-d076-45b2-9783-fc2e16f1a8ca | FREQUENCY: Each lot
| note | a5324ef6-9db6-432a-8ea0-0662a2889b92 | CATEGORY: IP
| note | 57ed9df4-0c90-49a0-ad97-6e734c1b4d7b | RESPONSIBILITY: SE/Site Supervisor
| note | 9d0c34f9-786d-45cd-89af-73995b5c07e5 | VERIFYING DOCUMENTS: Photos Sign ITP
| textbox | 9dd9c071-ce61-457b-b788-6a8a655a651f | Date Completed:
| checkpoint |  | 4.3 Pilot Hole Drilling
| note | 6c824da4-3919-4941-b604-8ca6d330f283 | REFERENCE: IFC Drawings
| note | e34d82f3-2607-4847-a0fb-831648f59648 | ACCEPTANCE CRITERIA: Assumed ground conditions are as per site geotechnical report.
| note | eb4a957e-0837-47f3-bb22-ec1d159ea1f0 | Geotech Engineer to be immediately notified if the excavations encounter different materials than expected
| note | 77941590-3f61-4fd8-9955-cf1f20fd13d4 | METHOD: Visual
| note | 516902c8-372b-4081-ae25-aa82e780e401 | FREQUENCY: Each lot
| note | 18c0fecc-1279-4291-a133-3308d211aa2b | CATEGORY: IP
| note | 3c6b3cea-ca87-4331-810b-306f47eee388 | RESPONSIBILITY: SE/Site Supervisor
| note | fe2152c0-9654-4ab9-9bbd-0477673f0cc2 | VERIFYING DOCUMENTS: Photos and Sign ITP
| textbox | d8aa55fb-10f8-4a46-bdff-f7d74668a8e3 | Date Completed:
| checkpoint |  | 4.4 HDD Monitoring
| note | e632b0b9-4a73-49e4-812d-f2c99c428322 | REFERENCE: IFC Drawings
| note | f611167c-5b23-443c-9caf-51e6a6108f18 | ACCEPTANCE CRITERIA: Inclination and path to be monitored as per design alignment.
| note | 79d3540a-db5e-4b1a-8f03-734087a23c76 | Ensure bore hole blockage and fluid losses are detected and addressed by:
| note | ee129e2a-f43b-4300-a876-c48c33787bab | Monitoring drilling fluid volumes, monitoring annular pressureand monitoring cutting returns.
| note | f716bb45-f307-4ea7-9875-e99be80c322b | METHOD: Measure
| note | 332a5817-ef1d-4d9d-92df-c481ba77e0de | FREQUENCY: Continuously through installation
| note | 7614a3b0-8759-49ed-8e3d-e2f0bd66c325 | CATEGORY: WP
| note | 3fbaf111-c7a6-4490-8dfa-f0be842ad9d9 | RESPONSIBILITY: SE/Site Supervisor
| note | 1c2c6689-790f-46ce-9db1-2ae4dac3b48a | VERIFYING DOCUMENTS: Sign ITP
| textbox | 02a66371-bd7a-4ef1-9afa-01f86efbc853 | Date Completed:
| checkpoint |  | 4.5 Conduit Installation and Trace Wire
| note | aeec6da4-6663-4c3c-a69c-eabd8ac5ad34 | REFERENCE: IFC Drawings
| note | f727d632-e933-457a-a42f-e0ba6a80597a | ACCEPTANCE CRITERIA: Min depth as per IFC drawings.
| note | bcfa0378-463e-4e23-a49c-ea39e8c48d3e | All bored communications conduits shall include the installation of 3mm trace wire.
| note | 7f314166-24c6-41ae-bc45-439764bd6ab2 | METHOD: Visual
| note | 02f59c15-7a3d-467d-bae3-a14f49dbdd3a | FREQUENCY: All Pipe
| note | 4e165543-c321-4052-b57f-4514d980cecb | CATEGORY: VP
| note | 3582d64c-52fe-4e81-a677-738493adc6be | RESPONSIBILITY: SE
| note | 0d0dc3db-24e0-45e2-a78a-20037d2ba15b | VERIFYING DOCUMENTS: Sign ITP.
| textbox | a364766a-2b14-4b18-8789-1fe5e6510f06 | Date Completed:
| checkpoint |  | 4.6 Pipe installation
| note | c9972718-4ba0-427b-82ec-fc2c0eed45cf | REFERENCE: IFC Drawings
| note | 88ad2be9-2e1b-4c8d-8f27-1fbfe9af7cd0 | D/17/62901
| note | 052294b1-1310-4b96-a879-4244a39a58b9 | ACCEPTANCE CRITERIA: Pilot bore to be reamed, then immediately followed by pipe being pulled through. Bore should remain supported at all times.
| note | 8b7a8852-6a5f-47b0-a7af-b5ac09826e80 | Diameter of bore is not to exceed diameter of pipe by more than 50mm.
| note | 568f848a-29a5-4789-ac1e-75592827cc13 | Pipes to be installed in straight sections with no excessive bending in the pipes
| note | 3c664fa6-64d3-4204-8cff-830f94c36f74 | METHOD: Visual and Measure
| note | 1fe0cf39-1e94-4e67-b256-9dccc0250bfd | FREQUENCY: Each lot
| note | 4cb0fae4-b796-44dd-b592-d3cc68361253 | CATEGORY: IP
| note | 4f3bcece-7a8c-4180-bd54-1130799a1cef | RESPONSIBILITY: SE/Site Supervisor
| note | 03c63007-57b0-4728-9309-fe403ad69f66 | VERIFYING DOCUMENTS: Sign ITP
| textbox | bcff9bfe-b769-4d2c-ba16-8c8f5b8ebb44 | Date Completed:
| checkpoint |  | 4.7 Conduit Installation and Trace Wire
| note | 428a27bf-325f-43fb-8655-ce2dcb070ec5 | REFERENCE: IFC Drawings
| note | 48f70c8b-51a9-4957-b5c0-f76a4e9ea9dd | ACCEPTANCE CRITERIA: Min depth as per IFC drawings.
| note | 1a762550-4674-44f4-83f6-67c6aaf4e8c7 | All bored communications conduits shall include the installation of 3mm trace wire.
| note | 28abacef-ec32-48f3-b749-ec6788122cee | METHOD: Visual
| note | 5fa0cfc3-58dd-4a0f-9597-443e4e45aa3b | FREQUENCY: All Pipe
| note | 6f7cec27-0ee1-4cab-be4d-afe46b2d6ffc | CATEGORY: VP
| note | 4ff58ef4-290e-4be3-945b-05f40590f1b2 | RESPONSIBILITY: SE
| note | cda8f9d9-254d-4e15-9607-2b992177252c | VERIFYING DOCUMENTS: Sign ITP.
| textbox | 3e277406-0210-493a-9b19-c1430de3167d | Date Completed:
| checkpoint |  | 4.8 Track Monitoring and Ground Settlement
| note | fe89bf27-1947-40cb-bacd-840b103b0748 | REFERENCE: IFC Drawings
| note | 14336edd-ef24-4376-84c7-5a03af099c13 | NIST-2706
| note | ef48ca6f-65e7-4f3f-b7be-edd5943b3101 | ACCEPTANCE CRITERIA: Both tracks are to be monitored at 5m intervals either side of the centreline of the under bore for 10m either side of the bore centreline (20m in total).
| note | 931e847d-cf56-4381-879b-695c9307997a | If movement above the predicted amount (> 15mm) is visible or any tension cracking is observed at the surface or within surrounding areas, then construction must cease, with drilling fluid still being pumped, V/Line and the Geotechnical Engineer notified immediately.
| note | d50a5838-6545-40e3-9401-5afa00547dc1 | METHOD: Meausure and Visual
| note | c4e1948a-5585-46d0-bfbb-8fcec39e9444 | FREQUENCY: Continuously through installation
| note | d25dfb9b-e196-43b8-a224-790a814c2ac1 | CATEGORY: IP
| note | c51c010c-e966-40d6-b318-5dbe02817c6c | RESPONSIBILITY: SE/Site Supervisor/Survey
| note | 4cd0b483-132c-4456-adb0-4b918852a388 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 78881d54-fa01-4bad-9c49-84305b944919 | Date Completed:
| checkpoint |  | 4.9 Conduit Welding
| note | ecc014ae-d283-48a7-90f8-8124c903c1ea | REFERENCE: IFC Drawings
| note | b6bf4c2d-a016-4e39-8456-77dd904ed92e | ACCEPTANCE CRITERIA: Joints are to be butt welded.
| note | 0bbd51d7-c7f5-4046-9140-1cc3427c983e | Weld map to be supplied and identify unique joint numbers.
| note | 26d2e99b-f667-4835-aaa9-237fa581964f | Butt Welding records to be supplied.
| note | 45c4176f-6b79-42f1-98cd-2fa12984863f | METHOD: Record and Review
| note | dd1552b6-4d17-447b-9bd5-bf6c31974c82 | FREQUENCY: All Joints
| note | f3cdf5d4-b571-45c7-b7b9-34fb7e0f93af | CATEGORY: IP
| note | e7b144d5-49c4-4e12-a95b-c0436f89841c | RESPONSIBILITY: SE/Site Supervisor/Survey
| note | add1a7c9-98ef-4854-a1c7-2a88171eb677 | VERIFYING DOCUMENTS: Sign ITP Butt Welding Records
| textbox | 33ee85be-611e-438f-854f-23b59c61c61f | Date Completed:
| checkpoint |  | 4.10 Draw rope
| note | 7cc9790d-db36-4bb6-950a-6c45e617946a | REFERENCE: IFC Drawings
| note | 9d827778-947f-4935-aebe-dfdf61e9494c | ACCEPTANCE CRITERIA: The draw rope shall be continuous for the complete length of the conduit run.
| note | ea7025e7-09de-429b-92e8-a8958e5ef97d | All draw ropes must be continious between pits and have 2m slack in the pit.
| note | 7ff50c2b-d978-4f7d-a4d7-f5d69478743d | METHOD: Visual
| note | 87e6957f-3e6d-4b0a-8b9a-b7dd011606bf | FREQUENCY: All Pipe
| note | 83e48b3b-dc61-48b2-bb4b-c3b4ef60132c | CATEGORY: VP
| note | 7914f23f-4072-4fa5-ba4d-1a75b5c0cac3 | RESPONSIBILITY: SE
| note | 47a33494-5f91-42b6-88d6-c1d23268602f | VERIFYING DOCUMENTS: Sign ITP.
| textbox | ebc00dfc-47bb-4c75-a51d-f66bdb5bb68b | Date Completed:
| checkpoint |  | 4.12 Mandrelling
| note | d12c0a3e-5beb-4bc6-bbfa-80f6db031d79 | REFERENCE: IFC Drawings
| note | a45d2b0b-2083-4a44-b397-f83ed0cc62d4 | ACCEPTANCE CRITERIA: Plug with 90% of the pipe diameter to be pulled through each conduit to ensure the conduit hasent been compressed.
| note | 34827249-73d0-4daf-aa50-71419924826a | METHOD: Record and Review
| note | 636698b7-733b-4836-959f-c17cc847a6e7 | FREQUENCY: All Pipe
| note | 81d508f1-68ab-4bb5-9ea2-477c6cc9bd00 | CATEGORY: HP*
| note | 96695c45-556f-477a-9ddb-dae53741b109 | RESPONSIBILITY: SE/SPE
| note | 487fa76a-bb3c-46de-9f25-8f908b48b6cd | VERIFYING DOCUMENTS: Sign ITP
| textbox | 221a8bae-40fb-40ad-92c7-b6d741a38187 | Date Completed:
| checkpoint |  | 4.13 Pipe Completion
| note | de5c22e8-6d58-4e44-8536-d8834cfda769 | REFERENCE: IFC Drawings
| note | b00515dc-ca39-448b-a6e9-8619c9b06dc3 | ACCEPTANCE CRITERIA: End of encasing pipe to be sealed at each end as per IFC drawings
| note | 9bfbaef3-7308-4215-878d-16e52d3cf58e | METHOD: Review
| note | ba6e635a-fd1f-4eaa-ac0c-58ddfa193d0a | FREQUENCY: Each end of pipe
| note | 341a8b52-e685-4452-b885-b5525a3d7ec3 | CATEGORY: IP
| note | 4b6b0bbf-98c7-4bc5-bbe3-b7721a7cfe1c | RESPONSIBILITY: SE/Site Supervisor
| note | c83de600-ad02-4718-909b-a62af30baa7f | VERIFYING DOCUMENTS: Delivery dockets Sign ITP
| textbox | e1cd869a-2ce2-4bc2-8e4f-d3db9445cf8d | Date Completed:
| checkpoint |  | 4.14 Reinstatement
| note | 13cb5a22-418d-40cf-81dd-045af742262a | REFERENCE: IFC Drawings
| note | e0dfc5e5-891c-4c9a-a770-95ffe6761be1 | ACCEPTANCE CRITERIA: Entry pits, exit pits and trenches within the railway corridor to be backfilled using approved fine crushed rock material. Backfill material shall be compacted to the same density as adjacent material or as specified.
| note | 0233bc99-62f2-46e3-9368-063ed957fa0d | Vic Track Engineer to inspect.
| note | 23874938-97e9-4fbf-a0ab-d4f0f6084db8 | METHOD: Review
| note | 1bb8bece-219b-44a9-9a8a-1421847bd4af | FREQUENCY: Each lot
| note | 9feb6a9f-79d6-44f4-9260-947ecd473175 | CATEGORY: IP
| note | e0d21c68-e674-4088-a560-106e8cb48fc2 | RESPONSIBILITY: SE/Site Supervisor VicTrack
| note | 536f2b61-93fb-4859-b3af-4bdf8a714664 | VERIFYING DOCUMENTS: Sign ITP
| textbox | ea8c8543-39ac-4c6b-919c-0af6dc674ce2 | Date Completed:
| checkpoint |  | 4.15 Marker Post Installation
| note | f43d0d9c-dc83-4e36-ba4c-cf118e393d4e | REFERENCE: IFC Drawings
| note | 43fbd636-374a-4659-93a4-72c25270cf3c | AS4799-2000
| note | 1d609af6-df2d-47a8-8278-28cf6f82e633 | ACCEPTANCE CRITERIA: Marker posts to be installed at every 200m intervals, any change in direction and at the entry and exit points of VicTrack property.
| note | 081a4653-7fad-4628-8974-2d324d699d75 | Marker Posts to be placed facing the rail tracks within VicTrack property
| note | 8b5d1c23-bd87-4cd6-b626-1cdfbc608c66 | METHOD: Review
| note | 6da0db10-ccfc-4357-9df6-fdd7fecae1cd | FREQUENCY: Entry and Exit Points
| note | 54834603-b0c7-4518-bf68-4617900aff66 | CATEGORY: IP
| note | a6a5d54e-b35b-4483-8939-ef0fd0166ab8 | RESPONSIBILITY: SE/Site Supervisor
| note | 6639bdce-bd97-49e4-8fd0-51532846fb28 | VERIFYING DOCUMENTS: Sign ITP Delivery Dockets
| textbox | b475dffa-0e05-4a37-9c62-26f4cecdf1d3 | Date Completed:
| checkpoint |  | 4.16 Marker Plate Installation
| note | d021eb6e-904e-4a5f-821d-e289ad812ff9 | REFERENCE: IFC Drawings
| note | 33c8036c-1ccc-41bf-9005-ed037ecafa4e | ACCEPTANCE CRITERIA: 50mm x 8mm Galvanised Steel Plate Welded to Post
| note | cf2cf09b-a398-4bfe-99f1-ac0be4b27966 | Marker plate riveted to post with 8mm insulated aluminium rivets.
| note | be7f67ec-0b82-453d-9544-14d9ee3b45f6 | METHOD: Review
| note | 82610160-2295-40a4-bfab-9f7c04474f42 | FREQUENCY: Each Post
| note | 85b1852c-4378-4003-b7d4-81e40f42233f | CATEGORY: IP
| note | 89700d42-144e-495b-9500-ad01d5a9c8f2 | RESPONSIBILITY: SE/Site Supervisor
| note | fe081bdb-6767-40f0-8754-8d7577b92dd7 | VERIFYING DOCUMENTS: Sign ITP Delivery Dockets
| textbox | 921a2a96-bf8b-4acb-859a-e8eb85432121 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 5.1 As-built Survey
| note | 5287e568-c5c9-4cf4-8604-d3cf891c8dac | REFERENCE: IFC Drawings
| note | d9dc704d-00e5-4add-a0ea-180f34e3688e | ACCEPTANCE CRITERIA: Survey as built report to be compiled.
| note | 1e9b2bec-d2b1-49f5-b933-c77d5e48d1a9 | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
| note | bfc45506-2466-44b5-96ba-bbbbe12ebab8 | Sleeve must achieve a min. 2000mm vertical clearance to tracks.
| note | cd0d00c5-33bb-4dfd-b2a8-b805c7c041f3 | Autocad and PDF reports are to be supplied to: services.applications@victrack.com.au
| note | 41bd171f-14d2-4a1b-ab04-b6cee3499faa | METHOD: Document Review
| note | 3c02a70a-3328-467e-ac74-27de1b0277ec | FREQUENCY: Each element
| note | 140079b1-0819-409f-8c58-f3a22f5a3cef | CATEGORY: IP
| note | b42539c1-d1b2-4156-8f28-4c489152c178 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 3915eaab-0422-43f9-a5b9-95aae1ab8540 | VERIFYING DOCUMENTS: Survey As Report
| textbox | d6fe7b02-1618-4d40-9124-a8bef597916a | Date Completed:
| checkpoint |  | 5.2 Track Inspection and Maintenance
| note | 8313b181-2d3f-4eb4-b22a-171d94bed82a | REFERENCE: IFC Drawings
| note | c23ec351-fd14-41bb-98a8-0fc112b5fd04 | ACCEPTANCE CRITERIA: Once works are completed, survey to confirm settlement of the track and ground are within the predicted design settlement values.
| note | 034dcf0f-d3f1-4c62-aed8-f8412f3b240f | Not > 15mm
| note | 4ece94e5-e356-4ed4-9f07-ec9b1a10da6e | To be provided to V/Line prior track hand back.
| note | 8fcee438-b9ff-4617-997c-034d255853b8 | Where track has been disturbed beyond the tolerances, realignment and/or maintenance is required by a qualified sub-contractor.
| note | da4b8540-c003-43d3-99a4-f0d62ad54667 | Attach: Track Inspection & Maintenance ITP/Taylor Rail ITP
| note | 9c3901d3-3abf-45fb-84a1-09df04df5336 | Attach: Track Measuring Sheet
| note | 5cf68bca-2c9f-4af8-85a0-227a02ebc1d9 | METHOD: Document Review
| note | 3c4f29b3-d6f3-44a4-9f98-2a564eaccfad | FREQUENCY: Each element Where applicable,
| note | 6f247950-0b44-48a0-8fb7-62daf9682d0f | CATEGORY: IP
| note | c86d1110-eb01-4078-8b2b-d46276741995 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 0eb4dc72-4c45-498b-afb5-3dd92a7eebb7 | VERIFYING DOCUMENTS: Survey As Built Report
| textbox | 4fdd7882-5b47-47db-ade0-4a4c48fe838c | Date Completed:
| checkpoint |  | 5.3 Red-line / As-constructed IFC Drawings
| note | e3ddec33-c83d-4cd2-9183-f2f264dbf873 | REFERENCE: MRPA Quality
| note | bb4da678-ae76-44ab-ad1f-920bd47e2948 | Management Plan
| note | d5d94580-9f88-48e4-b763-5217bc1cc42c | ACCEPTANCE CRITERIA: All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
| note | 8d2840b2-0cb6-4338-9831-d13d77edfb14 | METHOD: Document Review
| note | 2d680d1d-4af9-4aa4-8896-02f325f4b364 | FREQUENCY: Once, after construction of the design package
| note | dd671f63-18dd-4ec3-bd0e-bf5ebe37933f | CATEGORY: WP
| note | ec2c5c3c-3658-4f07-a310-6b6c4074b989 | RESPONSIBILITY: SE/PE/SPE
| note | c9a4f953-583b-4a7a-bc7c-bfbbde787c7f | VERIFYING DOCUMENTS: Red Line Drawing Pack
| textbox | 8c2ea7de-b4eb-4aee-95e9-311118ede10e | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 6b04834a-0fb7-49d8-aed3-6a0d5ded01bc | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 09e1dbbc-477a-42b3-a8aa-95d6ff4f9459 | Name:
| textbox | d0081f22-b88a-46cd-a5b6-55938954345b | Position:
| textbox | 5b84ffc7-08f5-45e2-9982-2aaa23323cbd | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Bonded Anchors (100 Year Design Life) Rev 0 | itp | ITP-STR-Bonded Anchors (100 Year Design Life) Rev 0 | 81a7ca0d-b684-4628-aace-5938bc6df306
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | d2d489cc-6448-44e3-9811-783c443aa6a8 | Document Title: ITP-STR-Bonded Anchors (100 Year Design Life)
| note | 704ebcf8-ec1b-4e44-828a-eda063dbea9c | ITP Description: Bonded Anchors (100 Year Design Life)
| note | 7b1146c0-7395-41da-809c-bc8b7a613d62 | Discipline (e.g. CIV/STR/RAIL): STR
| note | 7bf7cdfd-0916-4b19-87fa-698fb8cb5143 | Revision Number: 0
| note | 173ad3ef-4e9d-44dc-bf5d-5b0d1312a33e | Revision Date: 12/08/2021
| note | 84778511-7e29-42d5-b7a5-4fd7d35c7659 | ITP created by: Mike Freeman
| note | 6e98b237-ced3-48e6-816b-7e5ca7f447cb | 1.1 VicRoads Section 680 November 2018
| note | 953cd13a-d534-415b-825c-2bac56abdd40 | 1.2 VicRoads BTN 006 January 2018
| note | 7419f549-0e54-400d-b4f3-7a074d181b31 | 1.3 Teambinder Correspondence Number MRP-MRPA-GNC-XDM-1346
| note | 9e25ca41-c33e-4db2-9bf1-5ad962586c42 | 1.4 Teambinder Correspondence Number MRP-MRPA-GNC-XDM-2385
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Bonded Anchor System - Chemical Adhesive
| note | f2808601-d449-4803-b42c-48b00ef4791c | REFERENCE: IFC Drawings
| note | 4c5bd2c7-9ff5-40c6-abda-d623a8e935ff | 680.05 (a)
| note | d39c2cf9-efef-401f-9db9-893453cccf60 | 680.05 (b) (i - vi)
| note | ae8da5a9-7942-4c16-9180-56493219bc19 | MRPA-RFI-00660 & MRP-VICR-GNC-XDM-0052 & (Robinsons)
| note | ae6ff5b4-104b-4c22-b730-9c7f920c6bce | ACCEPTANCE CRITERIA: Bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
| note | f0fac3d8-655c-4501-91a5-6d6a09cf09f1 | i. ATIC SPEC 38
| note | cce9a6f1-e172-44de-be1e-1744a1af24d9 | ii. EOTA EAD 330499-00 or 01-0601
| note | fda66902-fe13-4282-9b6b-04b41ac18a73 | iii. ICC-ES (USA)
| note | 0e69d0c9-9b5c-443f-b2d5-40cb963c732f | Note: MRPA has D.o.T direction and approval to use only Hilti HIT-RE 500 V3 or Iccons BIS PE Gen 3
| note | f1ca961f-2e30-4fc8-959f-88ee97bedfd1 | Teambinder Material Approval number:
| note | 350b235c-cf9b-460c-9f80-fe9f8d5d5c91 | MRPA-MA-000192 (Hilti HIT-RE 500 V3)
| note | 766b210d-1297-4459-a62a-cacf9288ef61 | MRPA-MA-000275 (Iccons BIS PE Gen 3)
| note | 3cf5bb17-82bc-46d6-98d4-2e4d2bc0d376 | METHOD: Document Review
| note | aa4b3a6f-1cb1-4db0-b627-aae8ec2f8a3a | FREQUENCY: Once, per product, prior to commencement of Works
| note | a2f07542-d52f-4908-b216-35b5427b585c | CATEGORY: WP
| note | 6114926a-152c-48de-aabe-69c707752e6e | RESPONSIBILITY: Nominated Authority
| note | 3d0454ed-9076-40c6-866c-fb8717d9e231 | VERIFYING DOCUMENTS: This ITP
| textbox | 86769757-b70e-4b83-b86c-568bf7e9d16d | Date Completed:
| checkpoint |  | 2.2 Bonded Anchor System - Reinforcement
| note | c3c05ad5-2226-4fa8-8f19-a82709422293 | REFERENCE: IFC Drawings
| note | 498da3d3-e4e0-4730-88a7-ae86153ab7e8 | 680.05 (c)
| note | a2421e68-96af-4092-a530-587f203f8062 | 611.05 (a)
| note | 46cfccb6-168b-4ac0-932f-55a1f31ed612 | ACCEPTANCE CRITERIA: Where applicable, current ACRS certification for materials and for bar processing.
| note | 173a0b4b-306a-4053-a72f-47d18edf0f1d | Anchor bars need to remain uncoated (black) for durability purposes.
| note | b1c7ca3b-88fa-456d-9c8a-fa39f0bd83a1 | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | 91223d6f-895c-4b92-be32-9df14fd0d5d1 | Enter: Teambinder Material Approval number
| note | 776df62b-45df-47d5-8ff7-d709668d9259 | METHOD: Document Review
| note | c95a8b0f-2560-4877-bb57-3285885d9173 | FREQUENCY: Where applicable, once for each supplier, 14 days of award of contract
| note | f1549784-2b73-40e4-b662-5c158c2b1b54 | CATEGORY: WP
| note | b63da408-d935-4fa8-ba1c-c99257afc73b | RESPONSIBILITY: Nominated Authority
| note | 8e01ccc8-4b00-4d1c-85ef-5554f0d424c6 | VERIFYING DOCUMENTS: This ITP
| textbox | d614f767-b3aa-45b9-80a6-d4386bb13726 | Date Completed:
| checkpoint |  | 2.3 Bonded Anchor System - Stainless Steel Anchors
| note | e43cb656-48c8-4c31-a621-3545e0d83166 | REFERENCE: IFC Drawings
| note | 0e895f13-8f8a-40d6-b474-42afcbb14467 | 680.05 (c)
| note | c0f9bd24-763e-4c36-a975-d4e1caade236 | ACCEPTANCE CRITERIA: Where applicable, stainless steel grades 1.4401, 1.4404, 1.4362 and 1.4571 (marking A4) may not be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
| note | 9d26de5e-2d6a-4aaa-9730-1d56fad92bff | Stainless steel grades 1.4529 (marking C) may be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
| textbox | 7d2a8d73-db64-4d27-ab9a-dc23e3f1fbd2 | Enter: Teambinder Material Approval number
| note | f7ac8be9-1a71-44e1-8e11-8fe7dd87c781 | METHOD: Document Review
| note | e2c872a6-1e59-45e4-907b-9e932b823c04 | FREQUENCY: Where applicable, once, prior to commencement of Works
| note | 7955ab5d-c603-4e7e-91c5-128564299a53 | CATEGORY: WP
| note | b958ef62-0c31-45f1-9324-3b7c17bdb613 | RESPONSIBILITY: Nominated Authority
| note | 00881015-45dd-4384-9b51-4488bde73e5f | VERIFYING DOCUMENTS: This ITP
| textbox | 4861a16d-1575-40f3-bfa4-a8d439f0daf8 | Date Completed:
| checkpoint |  | 2.4 Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts
| note | 4217fa6f-e8e6-497d-a254-35955f290580 | REFERENCE: IFC Drawings
| note | 2e176d4b-3bc6-49d5-a96f-20ae35a77a9e | 680.05 (c)
| note | 3cd9c7b2-0612-436b-9096-646a269d5c47 | ACCEPTANCE CRITERIA: Where applicable, bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
| note | 2942f8ba-dbdf-4494-aa25-aba748e5d9e4 | i. ATIC SPEC 38
| note | 805bba6f-65ea-45db-b120-a6764b847ed8 | ii. EOTA EAD 330499-00 or 01-0601
| note | cbfe1d3e-51cf-440e-8673-0ef7b0bd4637 | iii. ICC-ES (USA)
| textbox | 0b15ae54-e827-41c8-8a00-f43279174d44 | Enter: Teambinder Material Approval Number
| note | 1a350091-5709-4a49-a47c-7829018240a9 | METHOD: Document Review
| note | 239dcb12-8f67-435f-a7ab-12f38e949df2 | FREQUENCY: Where applicable, once, prior to commencement of Works
| note | 12289c61-b30e-41a2-9ecc-e096abe22d41 | CATEGORY: WP
| note | a403d969-5105-494f-a581-cece72e7063b | RESPONSIBILITY: Nominated Authority
| note | 522e8c21-c27c-4106-93be-4764bcee1b5b | VERIFYING DOCUMENTS: This ITP
| textbox | b4c04a22-97e0-44ed-8f84-005ae221cc33 | Date Completed:
| checkpoint |  | 2.5 Alternate Product or Changes to Existing Product
| note | fa69e083-2fe7-4050-9bb7-2830d6e9fd7d | REFERENCE: 680.05 (a)
| note | ead236c4-f75e-42df-8c5e-50ac9d08ab2e | 680.09 (b)
| note | b6289ccf-ab99-489a-9700-09f9348a3168 | ACCEPTANCE CRITERIA: Where applicable, if an alternative system is proposed, where a bonded anchor system falls outside the scope of certification or where directed by the Superintendent, ultimate tensile load testing shall be performed to validate the bonded anchor system meets or exceeds the intended durability and load capacities.
| note | 5d445ba8-0b2d-465f-9e24-f0da5eaddc12 | A sample of 5 no. anchors per combination of adhesive type, anchor orientation, type, grade, diameter and concrete grade shall be installed in accordance with the manufacturer's installation instructions, load tested and results reported by a third-party accredited testing authority.
| note | a3d9a2f8-b7bc-4ee6-9da0-597ad87e92d1 | Results of the ultimate testing to be submitted to the Nominated Authority.
| note | cdf03600-46a5-4ec5-a4fd-3eb5b46805b4 | Note: MRPA designs are following the ETA certification of the adhesives
| textbox | 7217897d-f2a2-48e2-b733-5858fa549518 | Enter: Teambinder Approval number
| note | a590d74a-feae-4e64-8079-bf84f276b1a4 | FREQUENCY: Where applicable, 2 weeks prior to installation of anchors
| note | e5c4e115-73a0-47ba-ae5a-15cea9a8299b | CATEGORY: HP (N/A)
| note | a014a460-e07d-4e29-8dea-43b576c3122e | RESPONSIBILITY: Nominated Authority
| note | 0e87eda6-ecdf-4b29-8004-b292ef4020a4 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | a051085a-cb36-4afa-846c-bf212e3b69dc | Date Completed:
| section |  | Preliminaries - Documentation & Procedures
| checkpoint |  | 3.1 Design of Bonded Anchors Subject to Tensile Forces
| note | 0859be97-f359-4df0-8006-91cc5d3ffaaf | REFERENCE: 680.04
| note | fa1fd98d-4710-4f83-bccc-8dcdcc746546 | BTN 006, Clause 2.6
| note | 8729a1c4-6878-4bfb-9b34-6a53bbb1c73b | ACCEPTANCE CRITERIA: Where applicable, if it is proposed to use bonded anchors in full or partial tension, submit full details of the proposal, including a Proof Engineering Certificate of Compliance, for the approval of the Superintendent.
| note | 19d12e52-090f-414d-9695-816966b4e1a0 | See:
| note | 5746fd80-e131-4eb2-a6a3-515dcd18b111 | MRP-016-C-ACD-REP-17-NWA-CSW-0001 & TRP #181 (Clyde Road)
| note | 9c97b366-3cb1-42de-9f6a-8c8815dce975 | MRP-072-C-AURE-REP-20-DPK-CSW-0001 & TRP #326A (Robinsons Road)
| note | f3d174a0-9d58-4f4d-822a-2c469ffc76ac | METHOD: Document Review
| note | cd801670-91d4-4c23-b8ed-b7b99490d403 | FREQUENCY: Where applicable, 2 weeks prior to installation of anchors
| note | 2587a301-6159-4563-98fa-8e858f65d391 | CATEGORY: HP (N/A)
| note | 9152b267-7946-4e09-9da7-c4e7155f1d99 | RESPONSIBILITY: Nominated Authority
| note | 75c6f245-4f2e-40f0-a0f7-3931f7fafe73 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 3b8a03e2-7172-49cd-87f3-22d318510e83 | Date Completed:
| checkpoint |  | 3.2 Bonded Anchor Work Method Statement
| note | a22f3ea7-1207-4a07-8d08-05fa38845c86 | REFERENCE: 680.11
| note | fa48b3e7-6b31-4517-bfb9-c975c1b1359b | 680.07
| note | 52f185e9-407b-4ca5-829f-28079446ce5f | ACCEPTANCE CRITERIA: Bonded anchor WMS, detailing the method for locating reinforcement/tendons/services, equipment to be used, load testing regime and repair of concrete (spalled and cracking) to be submitted for review to the Nominated Authority.
| textbox | 51ab810c-19ab-4985-a55e-aa13e95427da | Enter: Teambinder Approval number
| note | 325a40f4-72e8-49d0-a3f7-c4fe39aab743 | METHOD: Document Review
| note | 29f53356-3afb-4774-90b2-94d4fa06058c | FREQUENCY: Once, prior to trial installation
| note | ea561620-86f4-41ed-95d0-380524d79f43 | CATEGORY: HP
| note | 19b6e105-3cd0-4782-bfcd-756b2f4177fb | RESPONSIBILITY: Nominated Authority
| note | a58d7bc5-4c7e-4aa5-9317-af9fb6c19a6c | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c57cb758-045a-4b9e-9e75-722dcc76fb1a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Load Testing Work Method Statement
| note | 5e9b6702-dd11-41cd-8238-088d81169f66 | REFERENCE: 680.09 (a)
| note | 84cf55ef-ccca-4942-aded-0a0dbd984e5d | ACCEPTANCE CRITERIA: Load Testing WMS, detailing the target loads (1.5x or 2x the design loads), load increments, duration for the load to be stained at each increment, testing frequency, measures if fail occurs and equipment to be used.
| note | 2ea48e2b-28e7-4fad-80f4-f31502f9f7b9 | Additional testing equipment requirements:
| note | e22439bf-1fed-4475-99c7-78fd16da1dc8 | i. capable of measuring the applied force to an accuracy of ±2%
| note | 477fd98d-7033-4635-93d3-4ad8e32eda3e | ii. capable of measuring the elongation with an accuracy of ±0.02 mm
| note | df445eca-97b3-4096-a7bb-48222a9c3322 | iii. have a valid calibration certificate
| note | a31f5b98-1926-4a87-8a57-85c79841d491 | The above is to be submitted for review to the Nominated Authority.
| textbox | ac85e9d3-661c-4fb4-92c7-e1de660a1147 | Enter: Teambinder Approval number
| note | 82e5ce77-b042-498b-9e0d-bbb8a3ae327a | METHOD: Document Review
| note | 133212ff-3ecf-4085-9f67-d4f1a7c44aeb | FREQUENCY: Once, 1 week prior to prior testing
| note | 7e175ad3-c4e0-4820-9538-9ad7a16946a8 | CATEGORY: HP
| note | c29e8033-391e-4baf-b31e-f5b992aad7b9 | RESPONSIBILITY: Nominated Authority
| note | 581ce4c0-aba4-464e-87f8-041cd3c79b86 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | fd523449-0f4c-4cd4-8736-1214070168ed | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Competency & Training of Personnel
| note | 1784d060-db79-41b2-8405-d67e3c18cb39 | REFERENCE: 680.06
| note | fb1244de-671c-4ab5-a121-d0563dfd83bc | MRP-MRPA-GNC-XDM-1346
| note | 95e53c8a-7b5e-49ee-b4dd-07b706113956 | MRP-MRPA-GNC-XDM-2385
| note | 931bf3cb-774f-4e15-891f-88615ccffb7f | ACCEPTANCE CRITERIA: All bonded anchor installation crews and direct supervisory personnel shall be listed on the "AEFAC Certified List of Installers" and evidence of this submitted to the Nominated Authority.
| note | 37017c57-2db6-462c-82a8-1e30b498f930 | See:
| note | 2455fd4f-45e7-4021-b3bd-56ae5a77f482 | TRP #181 (Clyde Road)
| note | dc1155ff-0d01-490a-be0c-291ff1b89d21 | TRP #326A (Robinsons Road)
| note | 2be6edf6-ca6b-4af5-9b5a-617484e9daff | METHOD: Document Review
| note | 81d8f450-0f95-4239-9e11-7a1a81444632 | FREQUENCY: Once, prior to commencement of Works
| note | 2d22d3c5-ca4d-4417-a0f8-735713a4ace7 | CATEGORY: HP (N/A)
| note | f2ceba81-d17a-4e34-be60-a667a3d79165 | RESPONSIBILITY: Nominated Authority
| note | c3a9a1df-8cf7-4f89-aa8c-78f792937caa | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 7fa7c9b2-2061-4eca-8ba0-3b57b922d00f | Date Completed:
| checkpoint |  | 3.5 Chemical Adhesive Training Toolbox
| note | 8a77e17c-12fe-4648-b4a6-7827b350bafe | REFERENCE: MRP-MRPA-GNC-XDM-1346
| note | dabc1f32-6ea1-4402-b16b-aad02f6f90d3 | MRP-MRPA-GNC-XDM-2385
| note | 207423fb-f42b-44c6-a81d-d594f44ad027 | ACCEPTANCE CRITERIA: Works shall not proceed until a toolbox is conducted by each chemical adhesive manufacturer, covering the specific installation, quality and testing requirements relative to the approved adhesive.
| note | 3e4ed5ac-8d2c-4619-a181-75acd583294a | Minutes of this meeting to be submitted to the Nominated Authority.
| note | 39f90fc2-50c3-4005-9212-bd014b718941 | Note: A D.o.T representative should be in attendance
| textbox | 491e7de0-e1ef-4d09-8da7-81e8e7803d60 | Enter: Teambinder Approval number
| note | 0608385b-a4a2-4953-8622-b1c6c16e7523 | METHOD: Document Review
| note | ec67ec2d-2544-4744-a48a-435fcec5541d | FREQUENCY: Once, for each work crew, prior to commencement of Works
| note | 7acee09f-0baa-4af5-96cf-9fa7e2e0172d | CATEGORY: HP
| note | df88f8c0-b61b-4010-b24a-a22cb6c4133d | RESPONSIBILITY: Nominated Authority
| note | 8a65bc1c-0409-4f87-a871-479760b68c3f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 8849810e-b81a-4252-acee-dc8947517aa1 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.6 Trail Installation
| note | 7258a85d-1d20-4b60-b51a-ff35ee7ca06e | REFERENCE: MRP-MRPA-GNC-XDM-1346
| note | 8f9960ed-136e-475d-94e4-0bf2855713da | MRP-MRPA-GNC-XDM-2385
| note | 9d9ee014-31f0-49f7-b603-4ccb2d742116 | ACCEPTANCE CRITERIA: Works shall not proceed until each work crew assigned to the project site can demonstrate compliance with the manufacturer's installation instructions by installing a sample of 5 no. anchors per combination of anchor orientation, type, grade, diameter and concrete grade as per the IFC design.
| note | 0e54656f-3403-475e-b52b-affa406595f4 | Where the presence of cracks exist or are to be expected, an additional 5 no. bonded anchors shall be installed in each combination to the above.
| note | 872ff902-0a0b-48cb-9961-600f9f1ffa2c | Evidence of this trial and attendees to be submitted to the Nominated Authority.
| textbox | 3fbe1f3b-7b1a-4f75-b772-a82d2a9d9f63 | Enter: Teambinder Approval number
| note | f1ac62b1-d9df-436b-bd55-16da79e9bd12 | METHOD: Document Review
| note | 88a58549-07f1-4ecd-8d8b-5fd54eb7e667 | FREQUENCY: Once for each work crew, 14 days prior to commencement of Works
| note | b3caa865-bd35-4be7-897d-c20d465b9150 | CATEGORY: HP
| note | b3fbdf2d-a273-4266-93ea-fc7c04661c45 | RESPONSIBILITY: Nominated Authority
| note | 339c4f41-0b7e-4443-9132-9c05b9711a6c | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b4fef4dd-5909-43b1-9027-ec8a9d4d1ede | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 4.1 Installation Equipment
| note | c4dc6a84-e81b-4596-a51b-1252dcd7f0db | REFERENCE: 680.07
| note | 009603bc-99ff-4e1c-9ee7-55e085a2c801 | Manufacturer's Installation Instructions
| note | 5eb47dfa-6e86-4ba5-ba04-5ec0d490a3eb | ACCEPTANCE CRITERIA: Bonded anchors shall be installed using the equipment specified by the bonded anchor system's installation instructions.
| note | 3f640437-3125-4dfc-bb63-e4c07fb67bf7 | This includes drill bits / dustless drill bits, diamond cores, roughening tools, cleaning brushes, mixing nozzles, piston plugs and extensions.
| note | de32ff01-eeb7-48d6-a9f5-ef8258599a77 | METHOD: Visual
| note | ef629f3f-1619-48b5-b584-f657f573cfe7 | FREQUENCY: Each discrete population
| note | 7f900efa-41af-4c30-ad4b-77ec70fbfec6 | CATEGORY: IP
| textbox | 9c2c44e1-27df-431d-b9cf-fb9b9a240e21 | Date Completed:
| checkpoint |  | 4.2 680.08 (a)
| note | ca134ed4-d39e-47fc-945d-fced3c035b6c | REFERENCE: Bonded Anchor Work Method Statement
| note | 72685135-f55a-4320-a260-b19bb67975e5 | 610.46
| note | aee638e2-577e-4889-8a39-0be3b553e71b | MRP-MRPA-GNC-XDM-1346
| note | 5db3ee7c-251b-4617-b187-334ba7ea0e54 | MRP-MRPA-GNC-XDM-2385
| note | 2258ef17-ee38-4136-afc2-0b5d9c12a6a9 | ACCEPTANCE CRITERIA: Locations of bonded anchor holes shall be positioned at the design spacings and angles using a calibrated covermeter or ground penetrating radar (GPR) to ensure that no damage occurs to reinforcement, pre-stressing strand, ducting and embedded services.
| note | d96cbfb8-275d-4579-817e-3a2d0c2b23cd | Where clashes are detected, adjust the anchor spacing locally if able to do so, maintaining the maximum and minimum spacings, edge distance and cover requirements.
| note | 47bc4a78-e016-4c65-afa4-220653022395 | If unable to adjust the locations, consult the designers to provide updated locations.
| note | eff770ec-cfb7-40b3-bfd6-baf07ccc064a | Note: The marked out locations shall be traceable to determine a discrete population of anchors and installed by the same work crew.
| note | 066ec360-9ef8-43b3-9537-aa847f050ba2 | Note: Installation of anchors must not occur until the concrete is both 28 days old and the concrete strength has achieved the 28 day strength.
| note | 121c8e20-73cf-4126-ae6d-e5381fabccda | METHOD: Measure , Visual
| note | f18be313-5dc5-4afb-a35c-8826fcf93889 | FREQUENCY: Each anchor
| note | a991d079-fae0-4d9c-bf31-d2cf09d7d412 | CATEGORY: IP
| note | dc721c13-c89e-43cc-b11c-fa53efeeffa9 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 78b3f35a-d001-463e-9806-d81f3e8e16ba | VERIFYING DOCUMENTS: This ITP
| textbox | cc1f1075-1b0a-4fa0-850f-4fb105735a25 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 5.1 Hole Drilling/Coring
| note | 07d018d6-921a-461a-84b0-e5787f3b9aab | REFERENCE: 680.08 (a) & (b)
| note | 482cec79-2606-495f-918b-a146bfc6a8bf | Manufacturer's Installation Instructions
| note | ad3df634-708f-41a1-a334-ee80e1cebbb2 | ACCEPTANCE CRITERIA: Holes shall be drilled or cored in the orientations, angles (if not perpendicular to the concrete surface) and depths shown on the IFC drawings.
| note | 6d3f8f2a-f185-4a8e-8a9d-a107102549ff | Drill or core diameters shall be those shown in the manufacturer's installation instructions..
| note | 1522f591-d1a6-4491-9dec-d912ce3303bd | Coring may require the internal surface of the hole to be roughened.
| note | 64baa3dc-de5c-4105-a263-44d8f4842c2c | If reinforcement is encountered during the drilling or coring process, cease drilling immediately and relocate the hole.
| note | 1e699e81-e97e-4360-96bb-452ce83a8e33 | Refer to section 6.4 for repair of abandoned holes.
| note | cc194e6c-3dc3-45ca-aadb-3aafba824b5f | If reinforcement is damaged, consult the designers to provide a clear direction moving forward prior to continuing installation of that discrete population of anchors.
| note | 3b25a123-b44f-408b-836c-93c888252ecd | METHOD: Measure , Visual
| note | 9ea34150-ef8c-4e7e-8582-ac842038dd5e | FREQUENCY: Each anchor
| note | 52fa8212-3613-4ab0-bb51-1ef19d5d3c83 | CATEGORY: IP
| note | 5a39d10c-6464-4f60-bfdc-a668186bb70b | RESPONSIBILITY: SE/PE/SPE
| note | 41b9dd98-758f-4b6c-92f8-211d7752bf0e | VERIFYING DOCUMENTS: This ITP
| textbox | beb6e08b-7689-43c3-bfde-4723325e6306 | Date Completed:
| checkpoint |  | 5.2 Hole Cleaning
| note | 976b02ee-7025-481a-8e49-80cc066dd56a | REFERENCE: 680.08 (a) & (b)
| note | ed8d48b5-bfba-4c8b-bd02-25d1590614ea | Manufacturer's Installation Instructions
| note | cdb44286-39b7-495b-93d0-623333556bbd | ACCEPTANCE CRITERIA: Hole cleaning shall commence as soon as practical following the drilling / coring process to remove debris, dust particles and moisture / free-standing water (where required).
| note | 96a1e67f-4892-4cad-9ceb-c4e0a979e422 | The process shall follow the manufacturer's installation instructions which is a repetitive sequence of brush cleaning and air flushing, resulting in no dust detected on a finger-tip when in contact with the internal wall of the hole.
| note | 4ba5d934-2fc9-4ebc-ac01-7712d5e598f0 | The minimum hole depth shall be verified before proceeding to the next step.
| note | b98265c4-87c7-4862-984f-5fe88b76aa3c | Note: Where hollow-tipped drill bits are used in conjunction with a vacuum drill, cleaning may not be required - consult the manufacturer's installation instructions.
| note | 16f52b28-180f-4bc9-9e66-16b23c520839 | METHOD: Visual
| note | 332e41b8-a2dd-4829-a544-f8d2de558957 | FREQUENCY: Each anchor
| note | 6aefadde-a2cf-45d5-98ac-cd465fef3e4a | CATEGORY: IP
| note | 0b0c8575-f9cc-465b-95c8-9767e470836c | RESPONSIBILITY: SE/PE/SPE
| note | 0e258782-aec1-40d0-9dc6-e698bd8302e8 | VERIFYING DOCUMENTS: This ITP
| textbox | d2e7f17a-aef8-4511-a16d-3ab4054fd3aa | Date Completed:
| checkpoint |  | 5.3 Substrate Temperature
| note | 38d5e326-e3c4-4f60-99bc-e1f51ae3f0a3 | REFERENCE: 680.08 (b)
| note | 455a0ae7-86f8-4bd9-93da-68ca60489cd7 | Manufacturer's Installation Instructions
| note | ccea916c-8621-4d98-991f-6486d862c99e | ACCEPTANCE CRITERIA: Bonded anchors shall not be installed where the temperature of the concrete is less than -5°C, or greater than 40°C or outside the limits shown on the manufacturer's installation instructions.
| note | fd64e85c-9d8b-475a-b45a-c7660992503b | Record: The substrate temperatures at the time of commencing the discrete population, the corresponding available working and curing times and the temperature at the completion of installation.
| note | c008042a-96dd-45ff-9cd2-a7d090c05287 | METHOD: Measure , Visual
| note | f006b8c1-4887-4c23-b609-21cb00a0d4da | FREQUENCY: Each discrete population
| note | 7b9ca191-1d10-4d08-872d-69c76602110e | CATEGORY: IP
| note | 7702ad41-bb6d-4544-b7df-a22fff82576e | RESPONSIBILITY: SE/PE/SPE
| note | 0c307fc4-b372-4edf-b78b-9999c7299ee1 | VERIFYING DOCUMENTS: This ITP
| textbox | 2c345601-2752-4819-8c3a-93563bd146a8 | Date Completed:
| checkpoint |  | 5.4 Anchor Surface Condition
| note | 694bef54-07f8-464b-bbdb-318aa5643de9 | REFERENCE: 680.08 (b)
| note | 31ba9e44-bdf2-4c7f-8b7b-fb8721ea121f | Manufacturer's Installation Instructions
| note | c048ef17-ab3d-4c05-b527-2d469cf254b6 | ACCEPTANCE CRITERIA: Anchors shall be clean, free from debris, oil and other contaminants.
| note | 9e9339a2-e8dd-41cc-b54d-f2e222b31629 | Note: Any coatings have been factored into increasing the embedment depth
| note | 9aa7fd84-4dcf-4184-8d38-e2a7a8f51a3e | METHOD: Visual
| note | 8b201c0f-5b6c-40d6-8e75-d772ce64c974 | FREQUENCY: Each anchor
| note | b03fd5c3-fca3-4a8f-bc49-00d8310505e0 | CATEGORY: IP
| note | f1e64ce8-a3a1-4cf9-8c0c-e81ccfb5021b | RESPONSIBILITY: SE/PE/SPE
| note | 67068104-e9af-4e62-8dd3-42f21af16499 | VERIFYING DOCUMENTS: This ITP
| textbox | 4f152f87-f4e8-4448-a7aa-5d65fe80dab6 | Date Completed:
| checkpoint |  | 5.5 Adhesive Injection
| note | fd08e36a-3ae7-4a43-9b70-dd80cc9694e3 | REFERENCE: 680.08 (a) & (b)
| note | 25bcff37-4a81-4ff2-80b9-b3f48864f941 | Manufacturer's Installation Instructions
| note | 8a4272c1-d779-4926-8f59-16d17df976bf | ACCEPTANCE CRITERIA: Connect the specific adhesive, cartridge gun and required injection equipment (nozzle, tubes, piston plug and valves) for the task and discharge the initial adhesive to waste to ensure that only fully mixed product will be used in the Works.
| note | dd405c39-07dd-48c0-ba4c-df9867d5c089 | Note: Repeat the "initial discharge to waste" for each new mixing nozzle used and do not modify the nozzles.
| note | d0cf7aac-ea87-48e8-85ed-f84e08b77321 | Inject the adhesive into the hole, starting from the base working towards the substrate surface at a rate that prevents the creation of air voids, until approximately 2/3 of the hole depth is reached, checked visually prior to the insertion of the anchor.
| note | 347b2c8d-8f56-4a6d-96f7-4c63c4b5b087 | METHOD: Measure , Visual
| note | 61949107-e854-4af9-a628-9be97f8497fd | FREQUENCY: Each anchor
| note | 1d92ee39-9ac2-4643-a72a-09738c1766a1 | CATEGORY: IP
| note | 7e636d07-9d68-4e42-bc92-9c3783acfc30 | RESPONSIBILITY: SE/PE/SPE
| note | 88d9abb1-5558-472c-91af-67317819e377 | VERIFYING DOCUMENTS: This ITP
| textbox | e2608463-44ea-47cc-acbf-36fa4324faa1 | Date Completed:
| checkpoint |  | 5.6 Anchor Insertion
| note | b0d793bf-4f99-4319-8961-c95d4c0c5c1d | REFERENCE: 680.08 (a) & (b)
| note | 0b7b6cf4-34e1-4c11-8b5e-910135682c10 | Manufacturer's Installation Instructions
| note | a55f4d08-1c30-4d06-808a-f43ade0d0a1e | ACCEPTANCE CRITERIA: While the adhesive is within the temperature dependent working time, the anchor shall be inserted and verified to the minimum embedment depth with a singular twisting motion, to ensure that the adhesive completely surrounds the anchor.
| note | 0ce1c348-9933-4a3c-82d1-c7b5a553337d | Where required, the anchor shall be centralised within the hole using temporarily supports to provide a uniform film of adhesive around the anchor and Excessive adhesive shall be cleaned from the substrate surface.
| note | 73969033-8964-4312-b9f7-4e104e73a590 | Loss of adhesive during the working time shall be prevented by sealing around the anchor as required.
| note | 144f1611-acd4-4e05-91e1-408a79bdcc23 | METHOD: Measure , Visual
| note | 62eb4fac-aaeb-4a20-871f-df30e18e163d | FREQUENCY: Each anchor
| note | c3754309-c7d9-4755-a78c-b41a8d1c2ccf | CATEGORY: IP
| note | 0a16916f-24a3-4161-b968-7d1ec82f98f3 | RESPONSIBILITY: SE/PE/SPE
| note | 0feea83c-ca6e-49c0-b652-bcc416e42d03 | VERIFYING DOCUMENTS: This ITP
| textbox | 1dc89f88-3dbf-4096-bf62-e902f7b3d11d | Date Completed:
| checkpoint |  | 5.7 Adhesive Curing
| note | d7da090d-07d6-456a-b90b-e273244b79fd | REFERENCE: 680.08 (a) & (b)
| note | fab2e36b-acba-468d-a870-66487bfbce5d | Manufacturer's Installation Instructions
| note | 91c1f701-123e-4d7f-9d9e-b98b2bf045cc | ACCEPTANCE CRITERIA: The anchor shall not be disturbed, moved, loaded or torqued during the specified temperature dependent curing period before proceeding to the next step.
| note | ee30a4c4-6c52-4096-81a7-fe0d1a7dce3c | METHOD: Visual
| note | 999e76f2-4677-43bf-a290-5c852e4f3493 | FREQUENCY: Each anchor
| note | 95eafba7-be6e-4168-9fd2-dabc34ac8f2a | CATEGORY: IP
| note | f6d70263-4e4f-41c8-a843-f20daf3c87da | RESPONSIBILITY: SE/PE/SPE
| note | eeb2bd0b-ef4d-4b17-9cf6-6bbb35b4cada | VERIFYING DOCUMENTS: This ITP
| textbox | a86e4611-3aa6-4168-8b2a-8b9b49ba78cc | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 6.1 Proof Load Testing
| note | 783fa4ed-697b-4a45-b82e-dc5427105c84 | REFERENCE: 680.05 (c)
| note | 8649e5c4-a84f-4e95-a017-b77ad7aadcf7 | Load Testing Work Method Statement
| note | 58752b88-17c6-4732-af00-6c657d9eb9c8 | Manufacturer's Installation Instructions
| note | 714132d6-79a3-4a52-aec1-e7cf3387f90d | MRP-MRPA-GNC-XDM-1346
| note | edcba557-726e-4158-a22f-3df75293216e | MRP-MRPA-GNC-XDM-2385
| note | 45ddc7b0-30d5-4ba8-a04a-594a2c830e2d | ACCEPTANCE CRITERIA: After completion of the curing period, bonded anchors shall be subject to proof load testing, as outlined in the approved Load Testing WMS.
| note | 1552c3d1-68e5-4fe0-aad4-67386c711d1d | Anchors subject to tension shall be tested at:
| note | 7a55aecd-eeb4-4ef3-9377-491ae39344c0 | i. 10% of the lot
| note | 1b91c025-aa20-4753-9f8e-8da0048050b7 | All other anchors not subject to tension shall be tested at:
| note | 28f2050b-5051-4a34-80fe-58339cd161f9 | ii. The greater of 2.5% or 5 no. anchors
| note | 2bbc8a6a-573e-430a-a06e-a6ecc1ac3d4e | Test results shall be equal to or greater than the factored tensile or shear loads and equal to or less than the maximum displacements shown in the Manufacturer's Installation Instructions.
| note | 19f41e42-a4a9-4036-be06-c138cce110cb | If any anchor fails the proof load or is displaced beyond the limits, the entire discrete population shall be tested for compliance.
| note | 020abd94-f6df-4abc-92f5-a022507ec293 | Refer to section 6.2 if the entire discrete population fails.
| note | 7a2db1e8-46b6-4829-af4a-86210f23f3a1 | Attach: Proof Load Test Results
| note | 5b367589-e619-40fc-a6eb-57dd6508187d | METHOD: Document Review
| note | ddf48462-13c8-4892-a5c9-1fe8759fee4d | FREQUENCY: Each discrete population
| note | 44822ce0-5235-4131-a4e1-8b95ce0d8697 | CATEGORY: IP
| note | 8016f675-d5c3-4b55-95dc-804900f90844 | RESPONSIBILITY: SE/PE/SPE
| note | 20b30354-b682-468c-bb1b-c856554c9238 | VERIFYING DOCUMENTS: This ITP
| textbox | 4beb61a3-1eb1-4064-a590-cebbbcb6e8e4 | Date Completed:
| checkpoint |  | 6.2 Failure of Proof Load Testing
| note | f91bd294-98f5-4a6d-922d-c37158939b9a | REFERENCE: 680.05 (c)
| note | bc454de7-06c8-48d2-8d39-172e4d9eda39 | Load Testing Work Method Statement
| note | 2fbcf37e-6ce8-4d6b-9f60-a7a3cddf16f4 | ACCEPTANCE CRITERIA: Should an anchor fail an ultimate tensile test, or an entire discrete population fail a tensile proof load; rectification proposals must be provided to the Superintendent for assessment prior to any further installation.
| textbox | 16033bed-eb33-486a-8821-92fd77b8a461 | Enter: Teambinder Approval Number
| note | b54368eb-8204-45fc-91e5-45a74828c847 | METHOD: Document Review
| note | a0a9a7d4-2e98-4185-9c4b-5e81ba54e665 | FREQUENCY: Where applicable
| note | d2e3cf3b-ac7a-4cfd-8170-0f65c22eca1a | CATEGORY: HP
| note | bbeb7047-e7cc-4877-b94f-a62ef10bc661 | RESPONSIBILITY: Nominated Authority
| note | 9ed5017e-0a92-4686-9f8c-fd975161fe82 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 13872398-ac73-495d-aa42-506bd47c854d | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.3 Surface Inspection - Cracks
| note | 5bd67bca-5dcc-47eb-8e77-33ed2e94aa93 | REFERENCE: Structural Concrete Crack Repair ITP
| note | c5eae7a1-05c7-4e9e-ae3d-12bc2931f3ec | MRP-MRPA-GNC-XDM-1346
| note | 6e698ee5-a568-46dd-914a-ccf1420102fc | MRP-MRPA-GNC-XDM-2385
| note | a39e6504-b550-47a0-8bd6-bc575be288ee | ACCEPTANCE CRITERIA: No cracks greater than 0.1mm.
| note | 3adb596e-904e-433c-95a8-6fbbe7eed13f | If cracking is observed follow Structural Concrete Crack Repair ITP (Specification 687), for investigation and repair but repair methodology MUST be via the injection method.
| note | bbe0dbc5-8780-47e0-8439-009a9e9eae28 | METHOD: Visual , Measure
| note | 257956f1-9f74-4093-ac49-67a4e0f2394e | FREQUENCY: Where applicable, each lot
| note | 80c9cdea-9a35-4303-b1b9-5a2996c2cc78 | CATEGORY: IP
| note | 6ff94c39-bc60-4b0f-a3f5-3a6540b9cced | RESPONSIBILITY: SE/PE/SPE
| note | 8e2b339e-8529-440c-a5f8-de4a29b9dff0 | VERIFYING DOCUMENTS: This ITP
| textbox | 60de2fb0-6b8b-4fcc-ab18-2c5edd801580 | Date Completed:
| checkpoint |  | 6.4 Surface Inspection - Abandoned Holes & Post-testing Spalling
| note | 5353ef77-7713-4ca1-a19d-895362d5e80b | REFERENCE: IFC Drawings
| note | 12f6796a-ce8a-4a23-86e7-496f5d4249a9 | Structural Concrete Patch Repair ITP
| note | 18afee94-027d-42dd-93a0-c048c5b6cf16 | 610.31 (a) - (n)
| note | bb981c20-fff4-4e2d-9e22-82c5c5e606fe | 610.32
| note | f4aaca53-4356-4603-9354-a4f06d323bd9 | ACCEPTANCE CRITERIA: Where holes have been abandoned, follow Structural Concrete Patch Repair ITP (Specification 689) for repair.
| note | c5625dd2-f233-47cd-8dd5-63b62f11666f | Where spalling around a tested anchor has occurred, preparation of the repair shall follow the Structural Concrete Patch Repair but the repair may allow for the newly cast concrete to create the cover.
| note | e4291d46-58cc-4af8-b398-f21956c63785 | METHOD: Visual
| note | d9f44671-f5a3-46a0-a16f-f69a822661ef | FREQUENCY: Where applicable, each lot
| note | 6d4e8828-43ae-40fd-8e9a-a66e326b27ac | CATEGORY: IP
| note | 8a8123f6-fa39-4baa-9f57-3f74963023ad | RESPONSIBILITY: SE/PE/SPE
| note | d4db0e83-e136-4356-b765-2e80a84c0178 | VERIFYING DOCUMENTS: This ITP
| textbox | 7f5fcd29-2a3e-402b-8fbe-5b2bacbd1701 | Date Completed:
| checkpoint |  | 6.5 Non-conformance Report (NCR) Closure
| note | d6171eb7-42b4-42b7-9eb8-f3b5e1586ea7 | REFERENCE: MRPA Quality Management Plan
| note | dc3a43fd-c828-467f-8d73-6827068b3b7c | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 127e2cdd-2a4f-451a-b1d8-a3d086b9738b | METHOD: Document Review
| note | 8736dd0e-17ca-42ba-8104-7745b902c63a | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | a1b4d2a4-2c06-4490-93ed-febdb714054d | CATEGORY: HP*
| note | b16815c6-137d-4bf5-9c12-7287374c2ce1 | RESPONSIBILITY: SE/PE/SPE
| note | d95082d5-c68a-45b2-81b7-1dea1d7842a4 | VERIFYING DOCUMENTS: This ITP
| textbox | e14ad00d-cb03-4566-9437-f575419f9d84 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | bf7f0aff-6957-4dc6-8fda-02f5009b761a | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 5c3f4d30-76bd-4730-835b-1348bcd24694 | Name:
| textbox | cdfe5fab-05b5-42c7-b631-832b3793694f | Position:
| textbox | 5c4ec767-ba5a-4222-a274-0810a0341b54 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-RSS Walls (Supply and Installation) Rev 0 | itp | ITP-CIV-RSS Walls (Supply and Installation) Rev 0 | 85837840-81c3-401c-9a8c-c717ba0d0c0e
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 6e25fa10-62e4-4ae2-892f-4f186106b71c | Document Title: ITP-CIV-RSS Walls (Supply and Installation)
| note | cec6e709-fbfb-4544-96c7-b9ed8a23c1a2 | ITP Description: RSS Walls (Supply and Installation)
| note | 9d876727-988b-45f2-8e7c-14a83eb11e15 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | f68bd4ce-eeb8-406a-a908-0107c0e9a7f3 | Revision Number: 0
| note | 3ad8384e-48de-49e0-a54a-212aadef57db | Revision Date: 19/08/2021
| note | 16a2be88-2b88-49e9-a06a-9699b87db4b7 | ITP created by: Victor Mira
| note | 86f96763-0491-4297-9e0e-b2f898930674 | ITP approved for use by: Aldrin Guinchoma
| note | d16b2614-f0cd-462f-8de9-6d27b89766a6 | 1.1 VicRoads Section 682 November 2018
| note | 686651d8-4ab7-43b6-a403-1a00a619d343 | 1.2 VicRoads Section 204 December 2015
| note | a3a9e388-9fba-405b-aeb1-10e872209b95 | 1.3 IFC drawings
| section |  | Preliminaries-Materials
| checkpoint |  | 2.1 Concrete-Levelling Pad
| note | 74a59495-0132-4759-be27-17900863d3eb | REFERENCE: IFC drawings
| note | 5dc0a9ad-fa1a-42ec-bff0-8dfd92d0b7ae | MRP-057-C-RFLD-DRG-20-ADR-CSW-1702
| note | d7744b31-3baf-4919-a103-e911730eead0 | ACCEPTANCE CRITERIA: CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
| note | 6c5d0b9f-3c9e-43cf-8d02-5687e859c639 | Reference: Teambinder MA number:
| note | 7375cb5d-b632-45b8-8e3c-e0813c99a981 | METHOD: Document Review
| note | 22a62401-e288-4f16-9617-633c66058e69 | FREQUENCY: Each element
| note | ed335eba-7118-4cda-bc97-04332145788d | CATEGORY: HP*
| note | 2f75c729-ec7a-4831-a690-b90408b6632d | RESPONSIBILITY: PE/Nominated Authority
| note | 950b7f64-735f-43f9-a0f9-b9729f0038b0 | VERIFYING DOCUMENTS: This ITP
| textbox | d3173215-6ab7-4cf6-9a7a-fdc67392454c | Date Completed:
| checkpoint |  | 2.2 Select fill
| note | f2be9eec-f7c5-486f-814e-f71eba30d59a | REFERENCE: 204.04 (b)
| note | 100aa0dc-363b-42e3-8e32-15aac10d61a5 | 682.131
| note | e9ab1ebd-aa23-4a33-888b-9ab7ca25616d | MRP-057-C-RFLD-DRG-20-ADR-CSW-1702
| note | 232bf5d2-6bc9-49bc-ba43-a6bb036e256e | Note 6
| note | 75519ed5-7d63-407a-8ad1-6c2151dd727a | Table 204.041 and 204.141
| note | 32cd8346-4795-40c3-9d8a-2e92273401de | ACCEPTANCE CRITERIA: Select fill shall comply with the requirements of the RSS designer, the minimum requirements of Section 204 of this Specification for Type A filling and shall:
| note | f36f850f-fd5d-4b19-8e14-faee16dda5bb | (a) consist of naturally occurring or processed natural material which at the time of placing is capable of being compacted in accordance with the specified requirements to form a stable mass of fill;
| note | 52f38a25-40d6-4969-86cc-71baf52208bd | (b) be free from organic or other deleterious material;
| note | fe4faa45-a4f7-4c5d-afa5-cc195d8329a9 | (c) have a particle size distribution, shear strength and coefficient of friction value to ensure the RSS design parameters are achieved;
| note | f69be076-e3d4-4a79-8d44-c7f9f9204d5e | (d) have the chemical and electrical properties stated in Table 682.131 and IFC Drawings
| note | f97e287b-01bd-4c0b-b0bb-8df4af1ed661 | Reference: Material approval in Teambinder
| note | 637c65bb-06be-4484-828c-ff211a032ec9 | METHOD: Document Review
| note | bb42bd6c-95bd-4e0a-85da-b25a8e1cd688 | FREQUENCY: Each element
| note | 1914e67d-ef25-437a-a58d-28ff51a6b427 | CATEGORY: HP
| note | 9d3d31c5-3862-4597-b6f9-5584e893693d | RESPONSIBILITY: Nominated Authority
| note | 70d104b0-f0f0-4fdf-9555-698cd765e59d | VERIFYING DOCUMENTS: This ITP
| textbox | ac7f2f3e-34b4-4e71-826d-68e12cd49c89 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Preliminaries-Documents
| checkpoint |  | 3.1 RSS Panels
| note | c9a9bbd3-1b51-48cf-a581-c78af45751e4 | REFERENCE: IFC drawings
| note | ea6812fd-530d-4870-bfa7-a05ed898ff01 | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
| note | 18893721-469a-44dd-a4f6-6c48e435497b | i. Certificate of Compliance / Birth Certificate
| note | 7a984dc9-f128-417e-b29d-01cfd0cfecd1 | 1. Concrete strength;
| note | c101bf3e-3e72-43c0-92ae-bb3743f38f63 | 2.Date of manufacture;
| note | 22a23710-7d38-463f-a6ca-276b8c0660dc | 3.Unique Identification number;
| note | bfba54d6-c4e7-47d4-ac2f-57cb45cc1b3d | 4.Mass;
| note | 531f94bb-7a51-4ad7-96a6-57a819a45c28 | 5.Confirmation of number, type and capacity of lifting inserts;
| note | 0efb255d-3fe2-4c4f-ab6a-0c78e375f57b | 6.Quality assurance sign-off.
| note | cb98c245-e32b-48d7-ae1f-d0d493df7033 | ii. Compressive strength test results
| note | 3703dc74-903a-44aa-a373-098ae4a8c8a5 | iii. Precast Lifting Design
| note | 52acc185-e52b-4e87-9996-cc0d33a09280 | iv. Pre-pour check sheet / ITP
| note | 5a388750-1527-46d6-83f0-d8f46f6c85eb | v. Post-pour check sheet / ITP
| note | 15ee0c3d-0d57-473a-b561-021f9977fdbc | vi. Covermeter check record
| note | b45aac06-4a06-410b-897f-0f09054ec876 | vii. Record of dimensional measurements
| note | d1d62ed9-4f3b-47dc-bc7f-4b504cea9ccf | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
| note | 0cee9dac-4422-458d-871a-60ba680ddca5 | METHOD: Document Review
| note | ba4ec8c4-ddf8-4e69-ba3d-89110c66a594 | FREQUENCY: Once for each type of panels
| note | fd44f6f0-85d5-4cb6-8cda-dd8a022a37ec | CATEGORY: IP
| note | c9d41094-0155-4114-a734-ef91e43ac749 | RESPONSIBILITY: PE
| note | 30574ea1-84ac-4e56-8740-b7c45e130fc8 | VERIFYING DOCUMENTS: This ITP
| textbox | 85a022ab-f665-4980-993f-800f2e533ec5 | Date Completed:
| checkpoint |  | 3.2 Straps
| note | b4309fde-d663-4d1d-9684-3b88d714aa06 | REFERENCE: 682.08 (a) i
| note | 6a759549-c5fc-4a6f-8269-b362846a6ca6 | 611
| note | fb9ef695-5311-4cbf-ad2a-8c70cb1cdf42 | ACCEPTANCE CRITERIA: All steel components for use in RSS shall comply with the requirements of Section 611.
| note | 2f36713c-5b3f-4b4e-8cc5-12e121b4638b | All steel components shall be galvanized in accordance with the Australian Standard (AS 4680) for Hot-dip galvanized (zinc) coatings on fabricated ferrous articles.
| note | 7c1876cb-e935-435e-bf93-e8ca9a1d5ce7 | Fabricator is required to provide the Manufacturer's Data Record (MDR)
| note | 64d8581e-3a7b-4dbd-b162-d321014cc469 | Typically this consists of but not limited to:
| note | 69537689-3405-4e27-b342-4a2ebe995615 | i. Certificate of Compliance
| note | 2ee024af-c2ca-4c8b-937d-0d74328e2ed3 | ii. Completed ITP
| note | c6a63fec-aabf-4c58-acf9-fc9cd549a167 | iii. Weld Procedure Specifications
| note | e11e5358-a924-4f58-a2ce-e67573db9045 | iv. Weld Procedure Qualifications
| note | 1984e969-9207-4da9-9d4d-1d3b2feb85f9 | v. Welder Qualifications
| note | da8e55e2-f41e-405c-a35c-b11b3095a0e9 | vi. Material Certificates and traceability
| note | 9c603a52-4f5c-4824-b503-78791fca064b | vii. Quality Assurance check sheets
| note | e0ee1972-6c69-4660-89cb-a9d27803c93c | viii. Welding Consumable batch certificates
| note | 4eb286d7-0a66-4f03-a10c-ac8b9d8b5202 | ix. Coating certificate(s)
| note | a2219147-5bfc-4982-9535-637851f187dd | x. Non-destructive Testing (NDT) Reports
| note | 961f9d25-0c00-42f7-8854-82c39ca75c24 | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
| note | 6b93328a-b5dc-49e8-b4a2-0075d18054b8 | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | 79e9c06b-82ef-4224-bc87-ca7548148469 | METHOD: Document Review
| note | 4891a3e3-a96c-44b3-929e-bf00088a71a9 | FREQUENCY: Once for each type of straps
| note | 6fe8c5e1-3f82-40ec-9acb-1fd6e889cf49 | CATEGORY: IP
| note | 82b17edb-7e29-49c3-8868-1b78c7b860e3 | RESPONSIBILITY: PE
| note | a50ead9b-e93e-49e3-a607-7a6576a75b32 | VERIFYING DOCUMENTS: This ITP
| textbox | 621b5dd5-f5a7-4561-9c12-f59b9507d8c3 | Date Completed:
| section |  | Pre-Construction Activities
| checkpoint |  | 4.1 Fill-Foundation
| note | 571a1d16-53e9-44dd-bd73-42e74468499a | REFERENCE: 204.11 (b)
| note | a4a151d4-68b2-476e-bc4c-b6b0cb59f1a6 | ACCEPTANCE CRITERIA: No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
| note | bb455424-0c94-44cf-9c0d-f5b842cced0a | METHOD: Document review
| note | 1e211d9f-68d0-4f92-9779-21c8ab6f4685 | FREQUENCY: Each element
| note | aa7262e3-ed29-41cd-9b55-ffdd334f469f | CATEGORY: HP
| note | a94eddfc-d458-403f-96cc-83791a18d7e1 | RESPONSIBILITY: Nominated Authority
| note | bb663361-594a-480c-a59a-89176fdb25ec | VERIFYING DOCUMENTS: This ITP
| textbox | 23feb192-ea5d-4a78-8e8b-df370389b7bc | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.2 Survey Set-out, Wall Panels installation-Levelling pad, Elevation and plan position
| note | c42fcfba-6549-4239-9810-c35ce607a6c6 | REFERENCE: 682.20
| note | 6a43cf65-a56b-437c-ada3-dc1351fe1163 | IFC Drawing:
| note | eb1951a0-ba19-4ba3-b727-c3e35e69b467 | MRP-057-C-RFLD-DRG-20-ADR-CSW-1701
| note | ee2c91c3-cd82-4f73-86bf-c4a7b091f70b | MRP-057-C-RFLD-DRG-20-ADR-CSW-1721 to 1724
| note | 86127d80-ae95-4924-bb81-0509987de884 | ACCEPTANCE CRITERIA: The levelling pad shall be placed to the required elevation and alignment to a tolerance as required by the project specification
| note | 3486d853-c8e9-4942-b9df-7ae0b5f231c7 | Survey Set out points of the levelling pad. Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
| note | 24b1a31e-d7be-46a1-bb14-aef1b33754cb | The levelling course level shall NOT deviate from the specified level by mor than ±3mm.
| note | 0ea14861-b44c-474d-8b8c-9b3baf4c7213 | METHOD: Measure , Visual
| note | 85614ff1-bd3f-49f4-bd44-789584e7c9cf | FREQUENCY: Each element
| note | b0dfbaef-ba9b-46ed-9ce7-2db56f8e892c | CATEGORY: HP*
| note | a2b203b4-0a97-4f6d-9e42-eb1bbe0fa53d | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | b66b6d74-2c67-4d9c-95cc-5a586bfd30e3 | VERIFYING DOCUMENTS: This ITP
| textbox | c42f7d24-518d-4a51-accd-2cf7f782402d | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 5.1 Wall Foundation requirement
| note | 60add051-ab2c-44e8-bf33-62dcf21131fb | REFERENCE: MRP-057-C-AUR-DRG-20-ADR-CSW-0012
| note | 84c34d99-b375-4335-87e3-1fd2313db5df | Wall Foundation Requirements Notes 1 and 2
| note | 15bbacda-6b78-410e-b5fe-56a0bb61ee61 | ACCEPTANCE CRITERIA: Required undrained shear strength shall be verified at site by suitably qualified geotechnical engineer.
| note | 0e603a5a-c0eb-46fe-aa54-66ed7ecc531d | Attach: Geotechnical report
| note | e6f9a257-eb8b-4b67-ad7b-42a50f815a93 | METHOD: Document Review
| note | fb2061fa-244e-46bc-b347-cc64653c6e76 | FREQUENCY: Each Lot
| note | 52f1c21b-38a6-4afe-8dea-abaf95f04867 | CATEGORY: HP*
| note | be6a87ca-ea65-433f-b8b8-fe5f6bf1d226 | RESPONSIBILITY: PE
| note | 2ae5da75-aae9-48a3-88e0-65627bb54c9e | VERIFYING DOCUMENTS: This ITP
| textbox | bd0bc137-66a8-4197-aca6-2c51d85bd336 | Date Completed:
| checkpoint |  | 5.2 Box Out Levelling Pad
| note | 1b2befe0-e112-4b02-a1ed-daa17c646403 | REFERENCE: IFC Drawings
| note | 858338f3-e001-4b8b-b2a1-396c04ded1ab | ACCEPTANCE CRITERIA: Box out levelling pad as per deign level and survey set out
| note | 76d8f226-b64f-482d-8c93-0191bb227bab | METHOD: Measure, Visual
| note | 098cf3a9-9b76-4d9d-b654-60ef1affb776 | FREQUENCY: Each Lot
| note | d1fc5d10-378d-405e-b622-7b515f67acbc | CATEGORY: IP
| note | 34bf60d2-3ff9-437d-8f63-49e42d4f42fb | RESPONSIBILITY: SE/Site Supervisor
| note | 719c5bda-5f05-4801-b239-1ce508fcaaf1 | VERIFYING DOCUMENTS: This ITP
| textbox | 2f636e5f-805c-4096-801e-f0ef5cdb9062 | Date Completed:
| checkpoint |  | 5.3 Form Levelling pad
| note | a215267f-6100-4511-96f7-42e49f3e11a0 | REFERENCE: IFC Drawings
| note | 4bb58b24-8158-4ea2-af66-c81c17205d27 | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
| note | 333988c7-9ce2-469e-8e65-c55713b3db84 | METHOD: Measure, Visual
| note | 099c41e6-0d2b-4acb-ae6a-8cf4ff001927 | FREQUENCY: Each Lot
| note | 3bdf9c75-7f87-4465-ba63-4c8b71e57ca0 | CATEGORY: IP
| note | 9e0f5f04-6996-4e56-b9e3-97558a549be2 | RESPONSIBILITY: SE/Site Supervisor
| note | 69f9def9-2ce2-40ea-b3f0-c9c524c9daa7 | VERIFYING DOCUMENTS: This ITP
| textbox | 0f766f5b-6f94-4d58-95d2-9c96931c7fa0 | Date Completed:
| checkpoint |  | 5.4 Concrete Pour
| note | 1aa29fa1-f973-49fe-8451-500224cc2a7e | REFERENCE: IFC Drawings
| note | 20634703-1eac-4cf1-ae4e-766cbd51168e | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
| note | f189e9e5-7c0c-4ba5-a89a-65953b79dc2b | Attach: Concrete Delivery Docket/photos
| note | 3b3ee6db-01f2-4422-b082-cb2cc881e7aa | METHOD: Visual
| note | e25842bd-7b1c-43d1-97f6-b97c95503ebc | FREQUENCY: Each Lot
| note | 1263f511-e482-4305-a821-b9e846d7d09d | CATEGORY: IP
| note | dc4812b7-1fd3-4985-8b10-5c3a4540c0b2 | RESPONSIBILITY: SE/Site Supervisor
| note | 52eb1f2a-898c-4890-92d4-eaac1c97df7f | VERIFYING DOCUMENTS: This ITP
| textbox | 49209bf6-245c-4db7-8516-5c4dc51f3809 | Date Completed:
| checkpoint |  | 5.5 Concrete Testing
| note | 548e030d-0b38-4b3e-a86b-0a09805c9b44 | REFERENCE: IFC Drawings
| note | cfed989a-cc1e-47ce-9bcd-de60ab93c0bd | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
| note | cf9551f6-b16b-4835-870a-a6c37218660e | Attach: Concrete test report
| note | 460e4677-fd32-4a98-8b24-5f58ec1e0a0c | METHOD: Document Review
| note | 2b997ff9-724c-4bd3-bd87-e5be65af5ab6 | FREQUENCY: Each Lot
| note | 728532a3-5a43-40b8-93bd-3e6a6b3b9c1e | CATEGORY: IP
| note | 0fa025aa-b24e-4f4e-bf1e-360ba32cffa7 | RESPONSIBILITY: PE
| note | 4033617f-b6ae-434f-9891-c0ca54630872 | VERIFYING DOCUMENTS: Attach Concrete Strength Test Report
| textbox | 5656fb60-644e-4432-997e-85d78adc9ab8 | Date Completed:
| checkpoint |  | 5.6 Concrete Curing
| note | e8b0b77e-1b75-4100-875f-d869a2396359 | REFERENCE: IFC Drawings
| note | 771de336-bd2d-426a-93d9-25d3afbbd01a | ACCEPTANCE CRITERIA: Curing Compound shall be applied post pour
| note | 86a3ff10-91ef-4809-8750-327e89669da7 | METHOD: Visual
| note | b64b59d4-aad5-470c-9005-adb1a16420e1 | FREQUENCY: Each Lot
| note | 6e53d9fa-b00a-4e84-966d-04654a759cb4 | CATEGORY: IP
| note | 69899580-5be5-464c-9bd6-3c91990eec30 | RESPONSIBILITY: SE/Site Supervisor
| note | 83236f1e-29a5-4dfe-9d49-d9bdb54a217f | VERIFYING DOCUMENTS: This ITP
| textbox | 3079e124-7c8a-4b22-8fd5-24d6e7d7007b | Date Completed:
| checkpoint |  | 5.7 Wall Panels Installation
| note | f6dcf8bf-8323-4f19-95b3-1237427dc5e5 | REFERENCE: 682.17
| note | c62940ee-1017-4dd7-9018-bad75b322729 | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
| note | 2699d32e-8615-433f-9a0e-b11ea9ac640f | Refer to checklist for each course of panels
| note | 337566e3-e7e1-4797-9541-5ad60210ecab | Attach: Lot map
| note | a64bc001-b262-4817-a769-c4b0df44c4bd | METHOD: Visual Measure
| note | a1824e61-f497-457e-a173-91a2ffbb5be0 | FREQUENCY: Each course of facing panel
| note | 5d6f5312-3b41-4c84-9afb-201d1a676be3 | CATEGORY: HP*
| note | 6de2e5d0-ec11-423c-bd39-8d6bb13b5292 | RESPONSIBILITY: PE/SE
| note | efb4c4df-c3a9-4ec5-a25b-8391f45dc2e7 | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
| textbox | 27a5b655-eca0-4449-be91-2c23a8941d5d | Date Completed:
| checkpoint |  | 5.8 Fill
| note | 0bd4e0fd-f9ae-46d6-991a-bea6980782d6 | REFERENCE: 682.16
| note | dc566281-4751-44f1-a043-05d4e1e3a808 | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
| note | 12bb5313-f799-44ed-8dc7-6ccadf30a113 | Attach: Lot map
| note | 6b4ba346-0729-42df-be57-2da3ae2cc60e | Refer to checklist for each fill layer
| note | fbfbcd4d-698a-4bd9-b713-09ff5b2fa0fd | METHOD: Visual, Test, Measure
| note | 2b2de127-ced8-44d1-bf3c-854939186337 | FREQUENCY: Each layer of fill
| note | 8b26c651-6950-4230-bd3b-ef67a4b5fca6 | CATEGORY: HP*
| note | 684e8bbf-5a56-49f0-b9a9-0632fc091a5a | RESPONSIBILITY: PE/SE
| note | d2c3da3d-ad2e-44d7-bb56-8b1d06cfa00a | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
| textbox | 094424f2-ea22-4adb-94da-119212d48b8a | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 6.1 As-built Survey
| note | 3a2eadb9-6bd2-4856-a0c9-c536d5183e0e | REFERENCE: IFC Drawings
| note | adca1c32-405d-4d2e-bfde-043a12b95d32 | 682.2
| note | eb2cf63d-5c6a-4109-aa32-13a1fd4569c5 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 682.20 as applicable to the element.
| note | 1af7e7a4-9760-43b7-aef2-778226b0d11f | Attach: Survey As-built / Survey Report
| note | 8ecdc11d-bf68-4e6a-b114-d49eb09afd65 | METHOD: Document Review
| note | b236f778-3758-4b51-8b89-841bb502b595 | FREQUENCY: Each element
| note | e1c1d900-816b-4401-babd-414c462c4ec3 | CATEGORY: IP
| note | ce1fe900-e7d9-4e7e-be54-cee8e3ce043d | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 98fd27e9-e9ab-404d-824c-2ad99a921e80 | VERIFYING DOCUMENTS: This ITP
| textbox | 282d2e54-9d93-4568-a13f-74649d2018a5 | Date Completed:
| checkpoint |  | 6.2 Non-conformance Report (NCR) Closure
| note | 4ca01c9b-cc20-4688-9e02-57c77e244803 | REFERENCE: MRPA Quality Management Plan
| note | a0ffa776-b922-4539-9be6-ea96347b3d19 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 19319290-08a9-4ff6-bcf2-667ff00d848c | METHOD: Document Review
| note | 85c9774c-44e8-4aea-b785-90a7041023d6 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | a146b92e-fc73-43a3-91d6-9d0f3cf8c5d0 | CATEGORY: HP*
| note | 53ff10a2-d089-4206-95cf-55910375a62e | RESPONSIBILITY: SE/PE/SPE
| note | a138f3f3-2eb5-4346-838d-b2ace4ab3650 | VERIFYING DOCUMENTS: This ITP
| textbox | 5cdd07e3-c463-4045-8c21-b380c714c9be | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | ec0f38e4-5f7d-4551-b944-6721e4d2211f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | fbdfc5d5-ddf5-4078-92d8-1690f5f89289 | Name:
| textbox | f1411cde-8aa6-4f41-9381-8f98beb6168f | Position:
| textbox | 01214156-3a86-4e31-8725-16b8526071c3 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-ACO Pit installation |  | ITP-CIV-ACO Pit installation | 86308729-8f07-46d7-8e67-7fe3e8851045
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 67ab6bb9-d217-57bb-8086-b798d73159bd | Document Title: - ITP-CIV-ACO Pit installation
| note | fa3255fb-a90c-5af1-9c15-799bc981f051 | ITP Description: - ACO Pit installation
| note | 262f88fc-7ce9-557f-b08d-75477057612d | Discipline (e.g. CIV/STR/RAIL: - CIV
| note | cf0d104c-40cd-584e-aefd-11dbfe7ad230 | Revision Number: - 0
| note | e6c1c898-60cb-51db-9a24-594d2e48d498 | Revision Date: - 44481
| note | cf564bb7-5117-556b-88b5-31441ded3184 | ITP created by: - Michael Daly
| note | 2868d420-830d-5d1f-9be4-c453f309e7fd | ITP approved for use by: - Aldrin Guinchoma
| note | 90d93f8e-957c-528d-8d2e-2d14b5f3e9d1 | 1.1 VicRoads Section 701
| note | ee28db9f-29ce-58fa-aa90-3d4fe5858036 | 1.2 VicRoads Section 705
| note | 04b65039-ebfc-5f8b-823a-1d1174609b4a | 1.3 ACO Installation Guide XDPG-BC
| section |  | Preliminaries-Materials
| checkpoint |  | 2.1 - Pit Details
| note | ff127e3a-33d9-51ae-9518-e50e37f8466b | Reference -VR 705.05, VR 705.09
| note | 64c54d96-00e5-53ba-9fa0-46630783818c | Acceptance Criteria - Pit Supplier: ACO Pit Lid Type: Grille/Welded Bar Grate Pit Type: ACO: XDPG-BC Enter: PIt ID, Line Number from IFC Drawings
| note | 37c85eba-38e3-5e22-983b-f2789ad5cc4a | Method - Document Review
| note | 43d3c035-4911-5bf1-bc19-620eb78c68d5 | Frequency - Each Element
| note | a0840e1e-310e-5554-b586-55886fb1946b | Category - IP
| note | a04b7392-60e7-5ba2-9143-2fa0e57d9eec | Responsibility - SE
| note | 472d9306-aa58-5694-817c-872d90106f15 | Verifying Documents -This ITP
| textbox | 22bc9083-9b4c-5db0-97ce-35b43831e142 | Date Completed
| checkpoint |  | 2.2 - Embedment material
| note | 22d1129f-5307-55b1-ab56-c20feb1b36a6 | Reference -VicRoads Section 701.09 (d)
| note | 1d120147-c428-561d-8897-c573fc9bf9d0 | Acceptance Criteria - Materials used for bedding shall be free from perishable matter and lumps and shall conform with the following requirements; 100% passing 19mm sieve 5-40% passing 0.075mm sieve PI (Max) 20 Enter: TeamBinder Material Approval number
| note | ea33b4d3-68af-5e0e-b555-eb150d9271f1 | Method - Document Review
| note | b877923e-58c0-525c-a2c5-d720bf28b58b | Frequency - Once for each Lot
| note | da3dabf8-9304-510f-a18b-e26ed94fef3b | Category - IP
| note | 81ed7176-cc14-58a1-8b8d-67ca1c8f44dd | Responsibility - SE
| note | 5368c811-980b-5140-ac57-ba3454a2dea6 | Verifying Documents -Material Approval Number Attach Delivery Dockets
| textbox | 4c5aee49-c2dd-5209-bdb0-fa6bc743873d | Date Completed
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 - Survey Set-out/Conformity with drawings
| note | 69fe861b-bb08-593c-846b-6c2f759e1b97 | Reference -VicRoads Section 705.09
| note | 9e504dbf-2921-595b-8be6-1c81e0bd4687 | Acceptance Criteria - drainage pits shall be installed at the locations and to the dimensions shown on the drawings.
| note | c35d67a8-2e0b-5627-93ae-dc44cfe45a3b | Method - Measure
| note | fb7e3594-9bb1-5d21-a20c-a9bdf8dc56f6 | Frequency - Each element
| note | c9d34251-5ab9-5dbb-aeba-4f2e147645a7 | Category - IP
| note | b730fda5-12db-5d06-a1ff-b71d7013d356 | Responsibility - Surveyor SE
| note | fb1e4b0d-85ad-5589-b96c-bf12d8e4ad12 | Verifying Documents -This ITP
| textbox | 4da97102-8c6f-52ce-8e97-df89be73ab03 | Date Completed
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 - Excavation
| note | 1f101e18-2495-5f63-aef7-cfdb2e006888 | Reference -VR 705.05
| note | f299e04d-8885-5f47-974d-c0bb5dae616d | Acceptance Criteria - Excavation to design depth. Foundation is satisfactory. For precast pits clearance provided to each face of excavation is not less than 400mm
| note | 6bda61b2-fe0c-5ede-a3c6-54f1a1aa1e62 | Method - Measure
| note | 943962ba-0f03-543c-a95b-75e2d97e6109 | Frequency - Each element
| note | 21af305f-19ba-52d2-8f9c-36d22599798d | Category - IP
| note | 56045bc2-79d4-5246-b0fc-0659530c8da1 | Responsibility - SE
| note | 8bc3b264-e141-517a-b6d4-0b1578984b4a | Verifying Documents -This ITP
| textbox | 769e613d-ab1d-5821-b02e-7d212b5b57b7 | Date Completed
| checkpoint |  | 4.2 - Bedding
| note | 590ae960-d435-5ff6-b623-2ce073d8ea1b | Reference -VR 705.05 VR 701.09
| note | cac0e3b7-391a-5c59-a65a-3ff1b7e850fa | Acceptance Criteria - Bedding for precast pits meet requirements of 701 and compacted to refusal. 80mm for clay and 150mm for rock foundation.
| note | 4e5434eb-c002-5589-912e-fdf00fb0624d | Method - Visual
| note | 97bcab21-638e-5078-855f-abaaaac1368e | Frequency - Each element
| note | b477483f-ef19-5eb1-ad4b-77378bf53719 | Category - IP
| note | aca86f98-6c86-5bff-8b34-18fff6dcabf6 | Responsibility - SE
| note | 80737883-c52b-5b4b-a3ad-494d8be96fd3 | Verifying Documents -This ITP
| textbox | 9769d168-1d30-5cc9-8784-a20ad8434970 | Date Completed
| checkpoint |  | 4.3 - Placing of Regulation Concrete Layer
| note | 1899bd43-a12d-5d60-8747-e3501345dd89 | Reference -Manufacturer Installation Guide XDPG-BC
| note | b52afb0b-871e-5916-9e82-aac13468c171 | Acceptance Criteria - Place concrete regulation layer of minimum 25Mpa with minimum thickness of 100mm
| note | a04a0a26-609d-53fd-a605-eaf7cbd0256f | Method - Visual
| note | b3b9ad06-3bdd-5142-aaad-26bc3c08e11e | Frequency - Each element
| note | 971dd41c-a628-5663-96aa-635df6693ce8 | Category - IP
| note | 6728f7e6-40b0-5f54-b19b-c25f4565f77f | Responsibility - SE
| note | 553b41a6-d806-52a2-8767-416b799032f6 | Verifying Documents -This ITP
| textbox | 93d96e19-f45a-5cb9-b402-e62acd841831 | Date Completed
| checkpoint |  | 4.4 - Placement of Pit
| note | ea38505b-6e74-51b3-801f-17e502560168 | Reference -VR 701.09 IFC Drawings
| note | 5a8ba958-d47b-540a-bd34-b1459b1b7acf | Acceptance Criteria - Survey pick-up to verify - Offset pits to kerb +/- 20mm - Plan location pits not adjacent to kerb +/- 100mm
| note | 7b33f161-8a0c-56c8-8a70-fbb920edb090 | Method - Measure
| note | 10b6df0b-5847-545a-b76e-ad83c7d53239 | Frequency - Each Element
| note | b0930f50-39a5-5cf6-88a2-47b8be99b21d | Category - IP
| note | f27bdc80-6a3e-58fc-be9b-0f7d800d71de | Responsibility - SE
| note | 16362754-61c7-53de-bd42-d4ef4c860a91 | Verifying Documents -This ITP
| textbox | 3624d3b5-8a12-5cde-8da5-c53396b3b82e | Date Completed
| checkpoint |  | 4.5 - Pipe drainage connections and jointing
| note | 0ba028f7-b504-5072-9839-ac4cb2929ccb | Reference -VR 705.1
| note | ceb2faa1-abc6-542d-9cf4-4cb186620003 | Acceptance Criteria - All stormwater connections to be neatly made. Where necessary, trim ends of drains and finish with cementitious mortar openings to be neatly saw cut to required size, not to exceed pipe diameter by 50mm Reinforcement exposed by the cutting of holes shall be coated with epoxy.
| note | af62c1a4-f829-5d34-bc1b-e90b7b9c91e5 | Method - Visual
| note | 57722888-ce6d-5bcf-8fb8-5e5349419cea | Frequency - Each Element
| note | 20a84fd0-e2b3-5048-87dc-bc46197c3d93 | Category - IP
| note | 556cfa61-af07-587b-8440-8fbfb0bcf2ba | Responsibility - SE
| note | 00fc51ff-88ac-54ab-beaf-f72384b37ee3 | Verifying Documents -This ITP
| textbox | f5656a03-cf31-5b30-b280-7d2fa723b2e7 | Date Completed
| checkpoint |  | 4.6 - Shape pit floor
| note | 1a377866-bb24-5d7d-8ee8-9937a0cf62b4 | Reference -VR 705.12
| note | 82dd99f3-2213-579d-840d-33630ee4c37e | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
| note | 3d5622b5-ebca-55a7-8351-f7d3c81def5e | Method - Visual
| note | e9744740-f148-5625-a586-a040a134c7e7 | Frequency - Each Element
| note | 3f8bd2a4-6754-5154-b40a-b49c7bde1056 | Category - IP
| note | a932ac1b-fc2d-5dae-966f-78296ea2c51a | Responsibility - SE
| note | 7c82e131-16c5-5508-8e37-54fba89dd232 | Verifying Documents -This ITP
| textbox | cbfd646a-cc7b-58b2-90d6-2c1055ac7610 | Date Completed
| checkpoint |  | 4.7 - Fitting of covers
| note | 0b77458f-0b41-5d6a-b00d-7030f2d9db09 | Reference -Manufacturer Installation Guide XDPG-BC
| note | c0be2882-0c3c-5643-8fd6-0516dcf2ec1e | Acceptance Criteria - Grille/Welded Bar Grate installed with ACO product with bars running perpendicular to direction of cyclists
| note | b0f0cb4b-2bd5-57f6-89d6-ff88493ad502 | Method - Visual
| note | a01ba719-048b-5e53-807a-b9a72ae1648d | Frequency - Each Element
| note | e8bd2cf6-ec42-520f-b6f2-4f9042e87bb1 | Category - IP
| note | b66f1dff-344a-5bcf-804f-e56cce3c32cc | Responsibility - SE
| note | 08382a68-8ca5-5366-9460-adb2937516d2 | Verifying Documents -This ITP
| textbox | ad2941ff-72e5-5a23-8763-775a0db30f74 | Date Completed
| checkpoint |  | 4.8 - Backfilling around drainage pits with compacted sand
| note | ef611793-b65b-5b98-9c74-b5bb9c929829 | Reference -Manufacturer Installation Guide XDPG-BC
| note | 3bd3034e-64f5-539a-96e2-67da08a5d6c5 | Acceptance Criteria - Backfilling around ACO pits using stabilised sand as per drawing requirements
| note | 124bc639-cb49-57cb-999e-e60cd59b3168 | Method - Visual Measure
| note | 70e0fe18-f704-5ab0-8de7-ab79fb9e3777 | Frequency - Each Element
| note | 58e63345-1b83-56ae-b1df-1abc9ea4d881 | Category - IP
| note | 1c55411b-325c-5e2c-a11e-b75d3d3a2623 | Responsibility - SE
| note | a5ee47cf-f474-5666-93e0-4695fab1520a | Verifying Documents -This ITP
| textbox | c500c4ec-8ee7-5555-a49d-e2f700a64e21 | Date Completed
| checkpoint |  | 4.9 - Backfilling concrete surround filling
| note | 4d0ff395-986f-5deb-9231-66c5ca04abc7 | Reference -Manufacturer Installation Guide XDPG-BC
| note | ea6f7086-2db0-5f66-bd2d-7c6c49b6c50b | Acceptance Criteria - Backfill top 150mm layer with concrete of a minimum 25Mpa
| note | 468a4f71-35a4-5855-9705-54e8a8bfb54e | Method - Measure
| note | 8494ef87-9473-555f-8015-4c237c14217e | Frequency - Each Element
| note | 04cc332d-e86f-5344-a651-ac3107551c57 | Category - IP
| note | 2a4a1b32-cdd0-5116-af40-7c8cb9580c47 | Responsibility - SE
| note | f53da344-a046-5dad-9076-b59379cfc5a4 | Verifying Documents -This ITP
| textbox | 7a27b0a0-3725-535a-af54-6e1e636b9f5d | Date Completed
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 - As-built Survey
| note | 88b6ece0-01ac-50d9-8614-d3f1aab6702c | Reference -IFC Drawings VR 701.10
| note | 2c44941b-f440-5da6-bdc8-92d8916d7812 | Acceptance Criteria - The location of each element shall be recorded progressively on the Contractor’s as constructed drawings.
| note | 35dd7ce3-c0d3-5598-b2e3-14c64129bf19 | Method - Document Review
| note | ffee7d9b-7788-5149-828b-77958e5ba76a | Frequency - Each element
| note | 5d0738bb-607b-5847-8462-b2d8c346486e | Category - IP
| note | 95d34025-bd63-5c17-9b1c-48437899b34d | Responsibility - Surveyor SE
| note | 4d297ba0-5583-5dce-9ff1-34e2484abc74 | Verifying Documents -Attach As-Builts Document
| textbox | 40506c41-1841-5d9e-876a-2e44c4083584 | Date Completed
| checkpoint |  | 5.2 - Non-conformance Report (NCR) Closure
| note | b7bfdcd9-e280-5bfb-978d-b9174df85b6c | Reference -MRPA Quality Management Plan
| note | 5a8f3eb1-3eb8-5053-b031-2b9728e0bab7 | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 783e94f9-4d1a-5f43-9c3d-8dba5173660a | Method - Document Review
| note | fc0d2017-70ac-53c2-bba9-bc9da159a204 | Frequency - Once, prior to closure of this lot / element / Work area
| note | 6dd56901-9976-5ae6-9661-83a0d6e2e37f | Category - HP*
| note | d65a0cf1-5cff-590b-925b-6b3a36eaa0f4 | Responsibility - SE/PE/SPE
| note | f39f097f-7f5a-53ca-9612-0205091a4847 | Verifying Documents -This ITP
| textbox | 1a870f4d-5330-5c90-b97e-d6839a4909b8 | Date Completed
| checkpoint |  | Final Inspection
| note | ba0bf02f-2043-59fa-8f97-538102e24870 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 855b7369-921d-5573-8934-55b520aec053 | Print Name:
| textbox | af71a5e0-47fb-5298-918b-f4de3f4dc870 | Position:
| textbox | 53b9a480-5d4f-5cce-81b3-e7c3816d5ad4 | Signature:
| textbox | 171d1947-ed2c-584a-b95d-5ffe158b3aef | Date:
| checklist |  | ITP-CIV-Landscaping - Ground Preparation Rev 0 |  | ITP-CIV-Landscaping - Ground Preparation Rev 0 | 8899272d-22da-4d6c-b22d-d84491c920fe
| section |  | ITP-CIV-Landscaping - Ground Preparation Rev 0
| checkpoint |  | Lot Information
| dropdown | bc2a9083-984c-5835-afaf-7fa0d10ebc7e | Lot Status | Identified, Open, Ready for Close-out, Under Review, Reviewed with Comments, Closed out
| dropdown | 99c6696e-cac0-53eb-9952-3909618503d1 | Responsible Engineer | Ben Kelly, Brigette Rizzario, Bunnarith By, Danniel Borrie, Danny Gannon, David Chai, Diana Delac, Jack Gascard, Jackson Nunan, Jadan Halket, Jon De Castro, Kia Menchin, Lachlan Summers, Luan Pham, Mazen Hamady, Mitchel Jacques, Plutarch Deliyannis, Ryan Dsouza, Sanjar Wasil, Scott Paterson, Sebastian Santalucia, Shane Voyer, Shayam Ajjarapu, Ty Qiu, Vince Argiro, Yokanth Ravichandrakumar
| textbox | 3e50a405-7b2c-599b-a0bc-17a5ad6cfa23 | Design Package No (ex: CBR-0017, AUD-0011)
| dropdown | f7087a8b-c365-599b-ac65-c5cd683b76cf | WBS Area | Robinsons Road,Fitzgerald Road
| dropdown | 5efdf029-692e-5ea0-9d99-6aaeefc9fd5e | WBS Sub Area | Rail - Track, Rail - Structure, Rail - Facility, Rail - Signalling, Rail - ICT/OCS, Non-Rail - Road Authority, Non-Rail - Area Wide, Non-Rail - Council
| textbox | e5265ed9-d1a5-596c-b9b1-3b5fc9701939 | Work Start Date (dd-mm-yyyy)
| textbox | 2907fa4e-c9fc-55c6-8b15-9c43eacd56bc | Estimated date of Lot Close-out (dd-mm-yyyy)
| textbox | 576ef6fc-bfa4-59ae-8fea-eaceefde8721 | Actual date of Lot Close-out (dd-mm-yyyy)
| textbox | 2f727910-7a90-5692-b414-a62320e39cc6 | Comments
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | f2aef9e6-b724-57ba-b5a9-68c769e8327d | Document Title: ITP-CIV-Landscaping - Ground Preparation
| note | 5dfb0423-7eb5-54db-85c7-418c2cea4ebe | ITP Description: Landscaping - Ground Preparation (Subcontractor)
| note | c16af12e-54c9-54fb-85b9-5c49f24fe65d | Discipline (e.g. CIV/STR/RAIL): CIV
| note | c80580c5-5733-5f1f-ae20-41a65fc63430 | Revision Number: 0
| note | 93c89017-704d-54b8-a187-2153f2a2f5f4 | Revision Date: 24/11/21
| note | de6f9be5-6ff7-51d4-95dd-0aafc98fd3b7 | ITP created by: Bunni
| note | 2ec43e58-68a2-5172-9f30-3873e6b2575c | ITP approved for use by: Josie Pavlou
| note | cab2ee77-810d-5ac8-884d-a039c99a4409 | VicRoads 720
| note | 29e4bcfe-bc38-5b83-b5bf-43916d850c2a | AS 4454
| note | b6e8ec74-7e1f-5e83-8780-f830461f13e3 | AS 4419
| note | a68fd942-9763-5366-98a2-cfda110922a0 | IFC Drawings
| note | eb98d40a-b20d-59a7-945c-8a3a99c17b47 | Sub Contractor ITP
| section |  | Preliminaries
| checkpoint |  | 1.1 Check for correct documentation
| note | 315aa2f3-b50c-5ed8-a284-87c92621d982 | REFERENCE: Drawings and drawing registers
| note | 491cd553-f838-59c6-87d6-a697226e8a1c | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | b7a00a94-9a63-5d76-bb67-4d5804cf9c44 | Using the correct and complete set of IFC drawings
| note | 4b8941d2-fe17-53ac-9fe3-97b94b4f5041 | All drawings are the latest revision
| note | 5ece3b13-008d-523b-8774-892731073bb3 | METHOD: Document Review
| note | de67512f-647c-5f15-ac55-83f876aa0cb5 | FREQUENCY: Prior to Commencement of works
| note | 360d2952-5358-5784-8257-b00d51858ee8 | CATEGORY: IP
| note | c6e2c3ee-c326-5df7-895b-a8b5f60dba12 | RESPONSIBILITY: SE
| note | 6038a19f-d33f-5a71-a269-bcd40f3d45ad | VERIFYING DOCUMENTS: Sign ITP
| textbox | c4e129c6-0186-59a7-a20e-5bafb920f2db | Date Completed:
| checkpoint |  | 1.2 Submission and records
| note | e2e540fe-03d4-5c3f-a0c1-c9bfd63cd37c | REFERENCE: Section 720.03
| note | 56060fc6-8ba6-562c-aac8-bf2dfa7a656c | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
| note | b8261e9c-5f1d-5719-ab48-e614eab790d4 | Following information shall be provided to the NA:
| note | 3f3c7352-7ae9-512b-8251-3d5b5e265580 | Samples
| note | c9d39be5-819d-5947-a998-0e15b3855330 | Mulch
| note | 1f99b1e8-5271-5e0f-a7c6-bf65148afc4a | Imported topsoil
| note | 45007712-4894-5e66-a8bb-8eed10f053c1 | Records
| note | 684f5a5c-50be-528e-a977-2331341dda3f | Details of suppliers
| note | 45cfd9fe-974d-51e8-a157-1b01f6a00a91 | Soil tests on imported topsoil
| note | dca8b65b-4295-5ec7-9c6c-98a471384134 | Copies/Photos of fertiliser labels
| note | b7dae592-1f46-50e2-8999-a5415373cd75 | METHOD: Document Review
| note | 5ac2853e-5aed-5ca2-8128-0b11e55960a6 | FREQUENCY: Prior to Commencement of works
| note | 4694a06e-4a34-5842-a2ed-05330c6ec499 | CATEGORY: HP
| note | 52bc9938-dd82-5b80-8d12-816db4ee75cc | RESPONSIBILITY: SE, NA
| note | c5a1826b-d767-524f-839b-56c58d49c791 | VERIFYING DOCUMENTS: Issue to TeamBinder Attach: Records & certificates
| textbox | 2bc47de0-3ae8-558c-8e10-e9c01e031346 | TeamBinder Approval No.:
| textbox | 6b37a095-9d1b-55c7-af22-147f6eb0a3b7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 1.3 Supply of topsoil
| note | 27ea1f84-6129-51b9-802e-d231ec0cc921 | REFERENCE: Section 720.04
| note | 283df959-96ae-5b1c-815f-2c72b8c85487 | Table 720.042
| note | 34b3f850-878a-5ba6-bf29-04350f2c76a8 | IFC Drawings
| note | 4798be18-0526-5bef-a3df-0306b5cf0014 | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
| note | abdb7689-3905-55de-a351-96bc88aadfd2 | Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings .
| note | 265a6128-a2c8-5828-9908-a65793fab21e | METHOD: Verify, Doc. Review if applicable
| note | f2ddff29-e6db-5a9f-a376-99d4c3a2da4a | FREQUENCY: Prior to Commencement of works
| note | 2f818ff0-6b32-5800-8c0c-3b19a5ee3e71 | CATEGORY: IP
| note | 31895768-ffea-515f-861b-89d5120e121e | RESPONSIBILITY: SE
| note | 2bb48d8d-8c48-553f-847d-42328471192f | VERIFYING DOCUMENTS: Sign ITP, Attach material conformance docs/Test Report
| dropdown | f0f6a54a-2a5e-53b9-9bd4-1aa67a60d516 | Select: | Site won top soil, imported
| textbox | e7534bc6-4578-59cd-92b5-570f178d5103 | TeamBinder Approval No.:
| textbox | 64f7d895-9c73-5312-9aa4-8df713131364 | Date Completed:
| checkpoint |  | 1.4 Supply of Mulch
| note | 01f33fd7-7dd1-5e0f-9f4a-a00c3a41bc44 | REFERENCE: Section 720.04
| note | a5399377-bd8f-5f08-b326-7d945829a546 | Table 720.044
| note | 6c9c2d26-7cad-54f6-9813-d22572869691 | AS4454
| note | 116cf5fd-5bc9-5410-8c3f-867c297e9451 | IFC Drawings
| note | bca7dd14-09e2-5784-b6ae-6f4619353633 | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
| note | b7fdd138-0ce2-5bc1-9646-585a3e0d377c | All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
| note | 28e50d99-abdb-5274-8910-9087e63c900c | Imported Wood Mulch shall comply with Table 720.044.
| note | f89c4ea7-510a-567b-aaec-40d1cadbecd4 | METHOD: Verify, Doc. Review if applicable
| note | 5f4a3801-8065-5f55-893e-fdc78536c49e | FREQUENCY: Prior to Commencement of works
| note | f9f67a04-c80e-59ab-b71a-eed2eddaee57 | CATEGORY: IP
| note | 6fd63e98-5279-5b10-b6df-158f4dd5b7f6 | RESPONSIBILITY: SE
| note | 2d9001ab-1cc5-577a-93a5-40de096f4bf8 | VERIFYING DOCUMENTS: Sign ITP , Attach material conformance docs (if applicable)
| dropdown | 7efa8e45-c8e7-5a1a-822d-8dd3a17fdced | Select: | Site won top soil, imported
| textbox | d054802c-3210-572a-8a60-dd5acb96fddb | TeamBinder Approval No.:
| textbox | 9846e520-173f-5ed4-accd-a0cca6735b8d | Date Completed:
| section |  | Site Preparation
| checkpoint |  | 2.1 Subcontractor ITP
| note | 5f6d16c8-26ee-5f4a-acbf-407cf806e666 | REFERENCE: Subcontractor ITP
| note | 143aed26-cbb3-5fb8-844d-23eb6f2e94d8 | ACCEPTANCE CRITERIA: Subcontractor ITP to be reviewed and approved by MRPA.
| note | 7700c124-946c-58cb-ab7d-ee2f74cfbdb3 | METHOD: Document Review
| note | 93de59f8-4abe-50dd-81fa-4bac10bab024 | FREQUENCY: Each Lot
| note | b3b7d582-7956-5540-898b-c35dde989a55 | CATEGORY: WP
| note | 88fd1fc2-9379-56a6-ac54-9f3753dd773a | RESPONSIBILITY: SE/PE
| note | 522dfbef-1088-59fb-bbc0-221df5b1209f | VERIFYING DOCUMENTS: Sign ITP , Attach completed Subcontractor ITP
| textbox | 77ef5a86-d176-5d7e-94ad-d6825a4e6bb0 | Date Completed:
| checkpoint |  | 2.2 Soil Additives
| note | a8d93ddb-9b62-52b5-85e5-504c4eed7872 | REFERENCE: Section 720.07 a)
| note | 0df7e627-8749-5b95-ac69-e4f7fe19d06f | AS 4419
| note | e3fc2099-8f36-5b6e-af09-0ae285993bac | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
| note | ec1380c4-b663-5b73-82c9-45abc6ed08cb | METHOD: Document Review
| note | dab55609-0d52-521f-8b3c-e5cb0ce2d061 | FREQUENCY: Each Lot
| note | 00217f95-04db-56ee-ae6e-888ce34b21d2 | CATEGORY: IP
| note | 9792e373-68cf-5e3f-bcaa-08b07828bcf8 | RESPONSIBILITY: SE
| note | ad5fabfb-bb05-58e0-ab2e-b3182c976878 | VERIFYING DOCUMENTS: Sign ITP , Attach Test Report , Attached Delivery Docket (if applicable)
| textbox | bcf37cfe-05d1-5465-917e-e3eaf9b7839e | Date Completed:
| checkpoint |  | 2.3 Ripping of subsoil
| note | 60659326-ec66-5ab7-ac2a-c62a46be8044 | REFERENCE: Section 720.07
| note | ad641305-21b0-5e5c-8d0a-690b9939167d | Table 720.071
| note | c1e13a06-799b-5e89-a01f-ebf02e25de46 | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP.
| note | 2d31f34a-1b58-5837-ab43-98d866399a00 | Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
| note | 35db6805-a777-56ff-9257-ee2a3dbffd1c | METHOD: Verify
| note | 36eeae1e-419f-5068-a8b9-a1d9f6941d73 | FREQUENCY: Each Applicable Lot
| note | 35f4e104-4312-57ff-9511-00c86550e513 | CATEGORY: HP
| note | b40698fc-d7f7-5574-b67e-4322ef989c16 | RESPONSIBILITY: SE, NA
| note | 1646b8e9-41f4-512f-b50f-722069e6c1ef | VERIFYING DOCUMENTS: Sign ITP , Attach Lot Map/Marked Up Area Inspected
| textbox | 1c989c27-4109-5979-86db-35384c1734c4 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.4 Topsoil application
| note | 23d09eda-7281-5a0b-8747-7e7e68b07e3e | REFERENCE: Section 720.07
| note | 3acaa962-6741-54ef-81cb-9cf1ca5123b0 | ACCEPTANCE CRITERIA: Site topsoil shall be used wherever possible, in preference to imported topsoil. Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in table 720.071.
| note | 30ac9c13-0011-5282-b242-d1ccc2cedf6a | Situation
| note | a303b835-e95d-5b09-91eb-5f2797631253 | Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
| note | 7fd26515-7839-5f6e-9684-6e59b15d9383 | Planting Areas in disturbed areas steeper than 3h:1v = 100mm Minimum
| note | 64ad427b-2cc8-52da-a912-7145f373fba7 | Grassing in disturbed areas =75 mm, except 100 mm in swales
| note | a9be704b-027e-57af-977a-3917889fc869 | Individual Tree Planting within grassed areas =150 mm in disturbed grassed areas
| note | a44fa73f-94de-5136-b0fe-d64c48acb469 | Topsoil shall be spread on planting areas and grassed areas.
| note | c181e9d8-68c6-59f1-bc1b-687089a853a0 | Note: Topsoil shall not be compacted.
| note | da713c1d-df2f-5290-b5b6-4e02a8897036 | METHOD: Verify
| note | 64dca2ef-2f9b-5186-abec-675cf7143d25 | FREQUENCY: Each Applicable Lot
| note | 18e0288f-4990-54fa-b7ed-aebc21ff4ee9 | CATEGORY: IP
| note | cad01da9-29e0-5834-af5a-f627e8bd0dfa | RESPONSIBILITY: SE/Site Supervisor
| note | 25ba12bc-4839-5156-a44e-46ceaab13030 | VERIFYING DOCUMENTS: Sign ITP , Attach Delivery Dockets if applicable
| textbox | aad0e5a0-9d73-52ec-b2f0-d3bbd9976448 | Date Completed:
| checkpoint |  | 2.6 Topsoil FSL - Topsoilling and Cultivation
| note | d4fb22c6-04e6-59e5-9e13-73d6f54a5450 | REFERENCE: Section 720.07
| note | 34668d36-a45a-5bc9-8f36-6c1861045a0d | ACCEPTANCE CRITERIA: Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
| note | e4a6d492-1f10-50c5-ab5c-9ec08125355e | METHOD: Verify
| note | 3d890516-aed2-57b2-a913-73a033f0f05a | FREQUENCY: Each Applicable Lot
| note | 2781edaa-f110-502a-b5d5-25fff402ac5c | CATEGORY: HP
| note | 3a934fa4-2158-5d80-b6ec-a923c8d97b17 | RESPONSIBILITY: SE, NA
| note | 1dd45739-6fad-53be-979b-4334a5ee2041 | VERIFYING DOCUMENTS: Sign ITP , Attach Lot Map/Marked Up Area Inspected
| textbox | 9b3180de-f0ec-5ce3-8439-9fd6fd0019f3 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.8 Mulching
| note | 70368140-8b28-56f5-aef3-1fb8ac9fe5c6 | REFERENCE: Section 720.08 a)
| note | 8641fea8-60c6-51e1-887c-dd8e9808e076 | IFC Drawings
| note | 7fe153bf-d044-5219-9e48-6456f974726d | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
| note | 257e2e49-e290-596e-b5b3-3e7e08895f73 | METHOD: Verify
| note | d8a3b679-f7dd-5278-b418-f5d2ded0d5bc | FREQUENCY: Each Applicable Lot
| note | 3adc54bf-e5aa-5f42-b8ca-11a1fa4239ae | CATEGORY: IP
| note | 51055d40-23c7-58c0-a670-77661970c370 | RESPONSIBILITY: SE, Site Supervisor
| note | 384c3dc9-01ad-5c6c-9787-9084e3742fbf | VERIFYING DOCUMENTS: Sign ITP , Attach Delivery Dockets
| textbox | 4a537145-9533-536e-ae30-a1c900dd9ef1 | Date Completed:
| checkpoint |  | 2.7 Weed and Erosion Control Mat
| note | 690d4413-cb75-5b19-941a-c849dd8ff1be | REFERENCE: Section 720.04 i)
| note | 085254d8-b983-5d66-9760-fd28019265a6 | IFC Drawings
| note | a1bc35b5-af95-5997-bd27-cc44106724f1 | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
| note | 03365bc3-2094-5a4b-b844-45b33f31ad1b | METHOD: Verify
| note | 38119d18-241c-596d-98ce-5251042a0f7d | FREQUENCY: Each Applicable Lot
| note | 6fc9ea87-4ed1-5e30-907b-f09d8fe26d82 | CATEGORY: IP
| note | db4e3058-b90d-5a06-807e-086542d01166 | RESPONSIBILITY: SE, Site Supervisor
| note | 21224c72-2cce-59ca-bcf7-b4021e1167dd | VERIFYING DOCUMENTS: Sign ITP , Reference TeamBinder Material Approval No. if applicable , Attach Delivery Dockets
| textbox | cb71858e-3053-5bf8-b0b6-a92365c21751 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 592a2619-6f24-56ef-85ed-e50921dd2627 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 639d1a90-4591-5e50-9a9d-3076e8dc9716 | Name:
| textbox | 5e09dcc5-7b6a-5b0f-b453-24988218d6a6 | Position:
| textbox | d4b89619-dd34-5a80-88fd-0d2fdddff915 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | itp | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | 8966913a-3e4b-4589-aa1e-c536ea7c3a63
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 3c018061-82c0-496e-a4b9-eac70bc371e7 | Document Title: ITP-CIV-Subsurface Drainage (Supply and Install)
| note | 790eb939-670c-489e-8f76-33e2c3e6cdb1 | ITP Description: Subsurface Drainage (Supply and Install)
| note | 01dfa365-a4eb-4c45-9613-61eb72bb0785 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | cdf5c38e-9ed3-4f50-85ac-159c273d369c | Revision Number: 1
| note | 2d797de5-d9bf-4053-a06f-38a97cfae59d | Revision Date: 11/09/2020
| note | 95e5f4ef-4f9c-4c6a-8cb7-ec45198ba919 | ITP created by: Josie Pavlou
| note | 226dffb7-5de3-4157-a37e-71507081fe5f | ITP approved for use by: Michelle Edgar
| note | 30c9ee35-d942-4c3f-a212-a2cca301882b | 1.1 VicRoads Section 702 (May '19)
| note | 7a28a3d1-8b15-4be5-b685-e498410cc801 | 1.2 VicRoads Section 204 (Dec '15)
| section |  | Preliminaries
| checkpoint |  | 2.1 Check for correct documentation
| note | e3711645-7a16-4d08-8086-8fd7bd1f9226 | REFERENCE: Drawing and Drawing Register
| note | c528f783-dd00-44c2-bd61-6621462f18a6 | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | a56d7f9a-335b-4555-bf1c-c6ede7a59c8a | Using the correct and complete set of drawings
| note | e03d2af9-0982-42a2-8bf3-bb1ee6b7373d | All drawings are the latest revision
| note | 720c764b-da12-4d6e-95b4-9f09e8b04f3b | METHOD: Visual inspection
| note | 4d338e51-dca3-4c42-8848-81d179258ecc | FREQUENCY: Prior to commencing any activity
| note | c577e0d8-4f9e-4631-8b5d-9902d14a784b | CATEGORY: WP
| note | b203c1a3-1eb9-40f2-95a2-e5cabca8394c | RESPONSIBILITY: SE/Site Supervisor
| note | 1da2d96d-6016-413e-aec2-9119008de44b | VERIFYING DOCUMENTS: This ITP signed off
| textbox | e09fcebb-b0d2-46f7-bf7d-52624dfb8904 | Date Completed:
| checkpoint |  | 2.2
| note | 49096da3-d20b-4a37-a50b-e2b5c98435c8 | REFERENCE: IFC Drawings
| note | 0e65f153-3a1b-49a3-a57f-cc3d3975af7c | Section 702.04, 702.05 & 702.06
| note | 3fba28d2-7f02-45f5-9e7f-eae41c4f1fca | ACCEPTANCE CRITERIA: Subsurface drainage pipes:
| note | 8510277b-cf65-446a-8cd3-9e3a33ffb162 | Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
| note | 6b0435fb-9e03-4432-9e98-887b621baa49 | Granular filter material:
| note | 8ea57a68-da9a-427b-b1cb-d1ed609f96ac | Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
| note | ec8ac6ec-85c0-49c9-9bd6-a4e58f828db9 | No Fines Concrete:
| note | c094cd3c-252e-481c-a5f1-659ef4583669 | Shall comply with 702.05 e)
| note | 8b9b790e-b749-4038-bac8-c161587bc138 | Geotextiles:
| note | 86359956-7766-4851-a722-3bb10bc2378d | Shall comply with 702.06.
| note | e50193b8-8385-406d-848e-d3906f02516e | Subsurface drain pits:
| note | 85c80531-d8d0-4896-a6bd-5d6c98a6eb5e | All subsurface drain pits shall be Type S1 to the specification of SD 1611
| note | 72755cc8-154f-4b66-8719-2d2e685ae9a9 | Pit Lids:
| note | c7057345-118b-4cad-ac6b-fb049d8ff6de | Type M3 circular lid (as per SD 1051) for Type S1 pit
| note | 2a3f0792-c4ce-4120-88b8-605f8565bbbe | Flushout risers:
| note | eff94199-f337-49ea-9cd9-fb731dc3347a | As per SD 1631
| note | 952c8f0f-d120-4e85-90c5-a1b0d7dda2d6 | METHOD: Verify, Document Review
| note | 514ffe78-b512-4555-b673-4c25bf019244 | FREQUENCY: Each Lot
| note | 4f61fe75-97cf-46df-a882-99e1e8eeee96 | CATEGORY: WP
| note | 5ada8afe-c77a-4c53-b203-42c4112dee23 | RESPONSIBILITY: SE
| note | 558d97a3-33d2-447d-bbd8-16a8d4a5f28b | VERIFYING DOCUMENTS: This ITP, Material Conformance Certificates, Team Binder Material Approval No.
| textbox | e08e55bc-8222-4ff0-8856-4dcdad4c688a | Text Box: Insert Team Binder Approval No.
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set Out
| note | 82784c1a-46d9-4b1b-a2c9-bd36d7ebb82c | REFERENCE: Section 702.03
| note | 8e780fa7-055d-4e1c-8428-5c9330df6355 | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
| note | 9f0b3422-4922-425f-85fd-25cca33dd421 | METHOD: Visual inspection
| note | d913c571-163a-40f5-997a-e8253702a106 | FREQUENCY: Each Lot
| note | 74992344-fb7f-4a51-a75f-98199338a7da | CATEGORY: IP
| note | e1159c2b-0ade-46f6-9094-9f3723503d1e | RESPONSIBILITY: SE/Site Supervisor
| note | 62111314-8a97-4d14-94e4-06298a21bfb6 | VERIFYING DOCUMENTS: This ITP
| textbox | abb483a7-4f26-4006-aec5-ff163d073c54 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Trench Excavation
| note | c7799003-87c5-40b6-9558-cf0ce816729c | REFERENCE: Section 702.08
| note | 414d04b5-2f80-4c28-b3ec-1b160332030a | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
| note | 084532ab-68f0-4fa5-b74d-a82035dd44f7 | There shall be no departures from the grade of the base of the trench that would allow ponding of water.
| note | 62dd2dc0-573a-4ab2-affc-e1690a5225d9 | Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
| note | 07440c3b-153d-48b6-90f5-252defe765a1 | METHOD: Visual Inspection
| note | 5c3137e9-3689-454e-a005-917a266ab3b7 | FREQUENCY: Each lot
| note | fe30ad11-bfa5-44fc-b8c5-88d0ef253087 | CATEGORY: HP
| note | 0c9221dc-eec1-41ee-b594-6ef1c5dc4934 | RESPONSIBILITY: SE, NA (Nominated Authority)
| note | c0c3d684-8e90-48a2-93b9-360707981fd6 | VERIFYING DOCUMENTS: This ITP
| textbox | 401b40df-e7c3-48f2-9ed3-a5778eef28aa | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.2 Placement of bedding
| note | 4a7fc11f-cd24-492c-8fba-4da35d0a8a6f | REFERENCE: Section 702.09 c)
| note | be151651-4981-4c2d-a9c3-f3893d7b1836 | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
| note | 60d0442a-fdff-493c-b48a-f1582dd1980e | METHOD: Visual inspection
| note | 9503dab2-841e-4201-9084-b70d34b974a6 | FREQUENCY: Each lot
| note | efef9d1d-40ec-4471-8e33-1c2a39add401 | CATEGORY: IP
| note | 80dfb8aa-7ff2-4b72-adb9-e655608ecae9 | RESPONSIBILITY: SE/Site Supervisor
| note | 78bd541b-e752-4916-9940-4ee6bdc3b053 | VERIFYING DOCUMENTS: Sign ITP Attach bedding material delivery dockets
| textbox | d21f3b8c-fad0-4bbf-9041-1394d7c2e060 | Date Completed:
| checkpoint |  | 4.3 Pipe and Geotextile Installation (if required)
| note | 46ee0f14-d251-411e-a278-b3e8ed913806 | REFERENCE: Section 702.03, 702.09
| note | b4af9681-ed9d-4a0f-a965-5559d8be6cdc | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
| note | b1e33b4c-c057-4153-b7c5-83b09be8a96c | METHOD: Visual inspection
| note | a0b00ca2-cad4-453a-b03b-d657c3f877e2 | FREQUENCY: Each lot
| note | daad278b-d924-4fc5-99f3-55cd95861ae2 | CATEGORY: IP
| note | 30d77a0e-2f21-4b66-bacb-afdfc860499e | RESPONSIBILITY: SE/Site Supervisor
| note | 7d3580c5-ed56-4c23-8c36-95603a47c818 | VERIFYING DOCUMENTS: Sign ITP Attach Subsurface pipe and geotextile delivery dockets (if applicable)
| textbox | 9f49f297-b231-4eaf-a56a-6f4bfb5478a3 | Date Completed:
| checkpoint |  | 4.4 Backfill Installation (Granular Filter Material)
| note | 4132a64e-dd82-401f-a309-f8dfb055c515 | REFERENCE: Section 702.09 (g)
| note | 7c2112c7-b4de-464a-972f-04f5220b0882 | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm.
| note | 232695b0-c924-497b-b8ae-3d444950c745 | The method of compaction shall be in accordance with the procedures and reviewed by the NA.
| note | 7c01cd5e-d0ba-412f-8ed1-d1e8d697db76 | METHOD: Visual, Doc. Review
| note | 8bf2e6fe-4bc6-4d20-9a06-f0c7c0b9e447 | FREQUENCY: Each lot
| note | 5ed347ed-389c-47e1-a3ea-f828ea97d21c | CATEGORY: HP
| note | 8c45dcda-47ca-45a2-ba93-ff8afef8ea76 | RESPONSIBILITY: SE, NA
| note | 644d1afc-634d-40e4-9733-797c8128905c | VERIFYING DOCUMENTS: Sign ITP Attach Backfill Delivery Dockets
| textbox | 4699dec7-1d0e-4316-9499-b9964dd1e785 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.5 Backfill Installation (No Fines)
| note | 52f2bbe4-0099-4976-88e1-b9a6b6f78c7c | REFERENCE: Section 702.09 (g)
| note | c1c46323-975f-402d-8d73-fb0a262ef2c4 | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
| note | ea1ed365-28c6-4a0a-9f81-1e09bbbce181 | METHOD: Visual
| note | d6fd22c4-d73e-4f37-abd2-d2bc165b54c1 | FREQUENCY: Each lot
| note | 201813bd-4f5e-4a26-8865-5322f4c5768d | CATEGORY: HP
| note | 90617d8d-17ab-4532-a812-026d7101a7c1 | RESPONSIBILITY: SE, NA
| note | 9a33067b-cba8-46a4-852b-c142b83bfc16 | VERIFYING DOCUMENTS: Sign ITP Attach Backfill Delivery Dockets
| textbox | 78e78252-a885-40fe-9ad0-31b5a2cab956 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.6 Install Pits and Flushouts
| note | 58b9ed6c-4492-49e8-b3e4-8b55286ba2f0 | REFERENCE: Section 702.10
| note | 26d25e37-aa64-4374-80de-13fc94996be3 | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
| note | b04667ff-81b1-4456-946d-30e142c3b1c8 | METHOD: Visual
| note | c3d2eaea-c68f-4c39-89c9-4481617a5196 | FREQUENCY: Each lot
| note | 8040a17d-fdff-4d06-9d2b-732db222555c | CATEGORY: WP
| note | 1fe20e55-5238-4c9c-919b-2f7a85e2131f | RESPONSIBILITY: SE/Site Supervisor
| note | 55d45292-df86-4714-953e-71d69f8c78b7 | VERIFYING DOCUMENTS: Sign ITP Attach Pit and Flushout Delivery Dockets
| textbox | b4c92aac-de0b-4962-90af-16bde2d8be08 | Date Completed:
| checkpoint |  | 4.7 Marker Points
| note | 74ad540b-6c04-4f17-bd95-1e484d948942 | REFERENCE: Section 702.11
| note | 2eeecf2c-5b98-4eb8-9543-7eb564a5ab51 | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
| note | bb2410fc-28ce-46f9-95ca-117261c02517 | METHOD: Visual
| note | 198b393b-9b76-4b9e-92ff-0c8373a8d6b8 | FREQUENCY: Each outlet
| note | fe98e145-6c94-496d-9c9d-a3debc1834b9 | CATEGORY: IP
| note | bbe168dd-d7ea-478f-9710-88b47cfc4319 | RESPONSIBILITY: SE/Site Supervisor
| note | 8723738b-931c-40d1-a43e-201a786e046b | VERIFYING DOCUMENTS: Sign ITP Attach Marker Post Delivery Dockets
| textbox | ac46c735-cda0-49c2-8f55-c8b5c68119fd | Date Completed:
| checkpoint |  | 4.8 Flushing
| note | 99ba903e-2d68-4333-b9a1-fc157a112f04 | REFERENCE: Section 702.09 (h)
| note | 064ae60f-f2fd-481a-b5d2-eecd53fc1197 | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
| note | 85347770-0afd-4e9d-b5a8-4405b6705a96 | METHOD: Record Review
| note | 19729922-5218-4774-9ba4-e62309a073da | FREQUENCY: Each lot
| note | b85f98d2-2414-4a1b-b265-7a9f5e944809 | CATEGORY: HP
| note | 1b2cc03c-e535-4298-a6f7-eba074781b71 | RESPONSIBILITY: SE, NA
| note | 43f7a915-6d17-4082-8ffd-975ab73f2483 | VERIFYING DOCUMENTS: Sign ITP Attach Inspection record
| textbox | 4fd8e163-6b25-45fc-8c47-0d2362bcff55 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.9 CCTV
| note | d773cb29-e080-4c01-8d95-4b4fc5806b78 | REFERENCE: Section 702.09 (g)
| note | 1464d8fb-30ac-40b3-a24d-528a94aa4458 | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
| note | edcf9cbd-0333-42ae-84c7-ad488334d8ad | METHOD: Record Review
| note | 2e7a0168-0648-47e7-a5c1-784a047b9dee | FREQUENCY: Each lot
| note | 51cd2fdb-1720-4869-a4c3-4f9310a694c6 | CATEGORY: HP
| note | 702da0a7-0767-4de6-adb1-4a560fbafb91 | RESPONSIBILITY: SE, NA
| note | 9f7b44b7-97ac-4a18-9593-c90e974e7494 | VERIFYING DOCUMENTS: Sign ITP Attach Inspection record
| textbox | 063f4e90-cc21-48b3-8304-85d3cee4d079 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 As Built Information
| note | 19d23dd2-9000-4fdd-b90c-dc392b1652da | REFERENCE: Section 702.03
| note | 98884de2-49e9-4ebc-acf8-62663e2c110b | ACCEPTANCE CRITERIA: The invert of the subsurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
| note | 1408f082-52c0-41e5-aa80-2d31285f77da | Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
| note | 31223f3e-1d6f-41e8-b494-08075468e442 | METHOD: Document Review
| note | 06015a87-3fc6-45f3-a4f8-36a285a235d6 | FREQUENCY: Each lot
| note | 7e92c9ee-e892-470e-9769-a56c6c2abce8 | CATEGORY: IP
| note | 343beeb3-63cb-437d-bbe6-b638851554b2 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | a12e5d6c-247e-4101-a3f5-6b46058ac881 | VERIFYING DOCUMENTS: Attach Survey Conformance Report
| textbox | c8189d4e-c6de-4a5d-aad6-388ef17ab8f9 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 58dda066-6f1f-4d5f-9966-210a0263d01d | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | d7992670-75dc-41de-81c2-0ac5f0b72acb | Name:
| textbox | 4c946b09-e726-45cb-aa6e-45ed2cb4801c | Position:
| textbox | cd0a8f67-42ac-48cb-871e-de80511ee663 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | CHK-CIV-RSS Walls-Fill Placement Rev 0 | itp | CHK-CIV-RSS Walls-Fill Placement Rev 0 | 89a5d957-a765-4b68-9a51-61aa94514254
| checkpoint |  | CHK-CIV-RSS Walls-Fill Placement Rev 0
| note | fcb9d00c-41f2-4d07-b5e1-6e68f0887978 | Document Title: CHK-CIV-RSS Walls-Fill Placement
| note | d549ff0d-ce25-4b8d-893d-97989b67bfb9 | Check list Description: RSS Walls-Fill Placement
| note | 63ca4ba9-2b76-44d3-b5b3-a7c8a69d2317 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 4c36e6c9-cb66-4cb5-bb99-be10564da442 | Revision Number: 0
| note | 3578ee29-2785-4c13-b338-f3f8f8b87059 | Revision Date: 19/08/2021
| note | 4383e70f-fdf1-43a3-8570-1d5b439bd114 | ITP created by: Victor Mira
| note | 9924a268-2bcd-469f-ba7a-28f22a927e38 | ITP approved for use by: Aldrin Guinchoma
| checkpoint |  | 1 Soil reinforcement-Straps
| note | 634b8069-7e43-4db6-85e0-c75f6fd046ca | REFERENCE: 682.08
| note | 18d1c1c8-3297-4a33-a33d-05ca0a04cf14 | ACCEPTANCE CRITERIA: Check Straps for damage to the coating or any cranks
| note | ebb4ebea-4333-403b-a60c-b5060aef4e50 | METHOD: Visual
| note | e95bc70e-883c-491a-b685-015630625132 | FREQUENCY: Each strap
| note | 4c1b5844-3676-408e-96eb-e551f7033a32 | CATEGORY: IP
| note | fcb01937-233d-41c0-9f3a-c9025730e300 | RESPONSIBILITY: Se
| note | 64ded1f8-e4f2-4e7e-a2cf-893883078e23 | VERIFYING DOCUMENTS: This Checklist
| textbox | a6aef955-1869-46ed-83ec-1f8b06171949 | Date Completed:
| checkpoint |  | 2 Soil reinforcement-Straps
| note | b5175801-a341-4af1-9f34-c4899410641a | REFERENCE: IFC Drawings: MRP-057-C-RFLD-DRG-20-ADR-CSW-1791
| note | ef9185e5-0d15-4e67-810b-e1bc41204506 | ACCEPTANCE CRITERIA: Correct number and type/length of straps attached to the panels in correct arrangement
| note | f535ed1f-147c-4515-922f-f752ae47c432 | METHOD: Visual
| note | d5ba3db8-26a6-4554-80cf-9012643dedd3 | FREQUENCY: Where applicable
| note | c6b9e623-107f-40e6-8f4d-a9c33e5d84b5 | CATEGORY: IP
| note | 5ba91f61-b8ca-4b6e-ab52-c5aba6aa6327 | RESPONSIBILITY: PE/SE
| note | e41203b5-0600-4696-9817-0c32ecf68af6 | VERIFYING DOCUMENTS: This Checklist
| textbox | 4d456b39-61e7-4f53-add7-f4f732f348f9 | Date Completed:
| checkpoint |  | 3 Soil reinforcement-Straps and Bolts
| note | 5b785fdb-5503-4043-9880-ba1cc10a3578 | REFERENCE: IFC Drawings: MRP-057-C-RFLD-DRG-20-ADR-CSW-1783
| note | 656b09ed-bdae-41c9-801e-78131947b322 | ACCEPTANCE CRITERIA: Straps are bolted to panels as per design
| note | 5e4cc298-0686-4652-bce2-8de2b3741120 | Bolts are tightened by hand tool
| note | 8556cde7-4d4f-4559-8925-d7987299e0da | METHOD: Visual
| note | 6435fd7b-004d-4f16-bc1b-07089aee2bbb | FREQUENCY: Where applicable
| note | 1abd71c3-ad8e-4cd3-bf4c-88d94230dff3 | CATEGORY: IP
| note | a2695b86-4446-4301-bfb8-1c9fedbd382e | RESPONSIBILITY: PE/SE
| note | 43b8cc70-4cca-486a-b8f2-1354b903d045 | VERIFYING DOCUMENTS: This Checklist
| textbox | 95f5fbf8-5f95-487c-aa1b-bf633cd4192e | Date Completed:
| checkpoint |  | 4 Soil reinforcement-Straps
| note | f7d1e972-04f8-4e60-a150-c28fc8de4889 | REFERENCE: IFC Drawing: MRP-057-C-RFLD-DRG-20-ADR-CSW-1701 682.16
| note | 05f971c9-a1d0-4d6d-b465-1a5cabc7fd98 | ACCEPTANCE CRITERIA: The condition of the soil reinforcement and connections to facing panels shall be inspected by the Contractor for compliance and a written record of each inspection shall be filed in the Contractor’s quality system prior to placing the next layer of select fill material
| note | 424fe9a7-a1fb-4e55-b04d-7b2b69282d94 | The vertical deviation of the soil reinforcement shall be within +1% (UPWARDS) & -0.3% (DOWNWARDS) of the soil reinforcement length, relative to the connection height.
| note | edd8192e-68f9-411d-8a84-5ceeb3f0561e | The reduced levels and position of the soil reinforcement shall not deviate from the specified level and position by more than ± 20 mm
| note | bcc460e2-6ea7-4254-9e50-675f17ad7fea | Attach: Soil reinforcement inspection photos
| note | 1d7aa01a-88fe-4390-9498-6ecf9b6e0b8b | METHOD: Measure
| note | dd02170a-bdcf-42a2-8a4b-96c044774255 | FREQUENCY: Each Layer of fill
| note | 5fa8cb23-a9da-429e-9c39-c638657fa2b6 | CATEGORY: IP
| note | 565e18fb-cf82-4d75-8a88-a72430ebb99a | RESPONSIBILITY: PE
| note | edcdd0bd-5770-4a32-a444-2f983befbc5e | VERIFYING DOCUMENTS: This Checklist
| textbox | fd606d92-d1e5-4209-ac3c-8bcd939588ce | Date Completed:
| checkpoint |  | 5 Drainage-Strip drain
| note | 85dd8583-ce1b-4579-b72a-98fe13908445 | REFERENCE: IFC Drawings MRP-057-C-AUR-DRG-20-ADR-CSW-0151 to 0155
| note | 5847f991-32ce-459a-850c-8c1a4420121c | ACCEPTANCE CRITERIA: Strip drains to be installed and connected to 100 Dia perforated subsurface pipe at 2m c-c
| note | 069cf211-0237-4566-bbb7-cf0d7583f4f8 | Size and distance from soil reinforcements to be according to relevant IFC drawing
| note | 12e268b3-9e32-4d20-9509-4aefbb8c1746 | METHOD: Visual
| note | 42e147c5-53c7-4722-967e-16fd7c7ca291 | FREQUENCY: Where applicable
| note | 9b5d934f-9079-4708-b0d1-21920e0c91c5 | CATEGORY: IP
| note | f56e5729-2159-452d-98e7-a5d4a7a90a3c | RESPONSIBILITY: PE
| note | 04995780-edb6-4f7b-a28b-9b4cac655f41 | VERIFYING DOCUMENTS: This Checklist
| textbox | 14e55167-5f2f-424a-83fa-57271fee8d29 | Date Completed:
| checkpoint |  | 6 Drainage-Perforated pipe
| note | 8b535c64-2628-4185-80b9-2b6351947e97 | REFERENCE: IFC Drawings MRP-057-C-AUR-DRG-20-ADR-CSW-0151 to 0155
| note | 4bfbbd1a-f2e7-4ab6-955f-656d3b3feeef | ACCEPTANCE CRITERIA: 100mm Dia perforated subsurface pipe wrapped in Geotextile and encased in free draining material
| note | 2c2fcb57-cce9-48bf-b2b4-450fbba09df4 | Nominal fall to weepholes: 1:100
| note | 692af79a-a7a1-42fd-b93b-62a50828fb17 | METHOD: Visual
| note | 0e3825dc-b122-4e97-bf99-e7576dc41d41 | FREQUENCY: Where applicable
| note | 0c89be4a-5607-4578-b404-e318020b98b5 | CATEGORY: IP
| note | 84db5181-c45e-461c-ba20-2547cb6c93d8 | RESPONSIBILITY: PE
| note | eb62a38e-25ab-4ada-91e3-371f66ed28be | VERIFYING DOCUMENTS: This Checklist
| textbox | f84c17bb-b6b4-4d7f-b4c6-4257fe02c354 | Date Completed:
| checkpoint |  | 7 Drainage-Geotextile
| note | a42bcf77-c8b2-4380-98f1-76a3a4b1a755 | REFERENCE: IFC Drawings MRP-057-C-AUR-DRG-20-ADR-CSW-0151 to 0155
| note | 35205351-745a-43b2-9dd2-7394c0f93569 | ACCEPTANCE CRITERIA: Bentofix geotextile to be installed according to the relevant IFC
| note | bd7e1499-1307-4466-ac45-ce73a6f70dae | Min fall from the back of RSS: 1:100
| note | f0edd2bc-2475-46c5-8798-40dc82c6a919 | METHOD: Visual
| note | b9c63001-3f05-4468-aa4f-c52c67b67e0e | FREQUENCY: Where applicable
| note | 50a80975-2931-4006-9e6c-e96ffbe80985 | CATEGORY: IP
| note | 19e8a966-8466-4597-9089-e6d4a6b04697 | RESPONSIBILITY: PE
| note | 11ccf40f-cb73-4d44-97fc-a6c1838909fb | VERIFYING DOCUMENTS: This Checklist
| textbox | a60a730d-0523-4808-b44e-23f0b8c09973 | Date Completed:
| checkpoint |  | 8 Fill-Placement
| note | 1b81b9f9-5b99-4390-9315-5f6116573d2e | REFERENCE: 240.10
| note | 58206ba4-2946-4c60-92e5-5b6745b3279f | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm or as agreed by the superintendent.
| note | b49c7d0e-92b8-40b6-819a-c4b6daf08eb8 | All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
| note | 2d1b4ea1-2910-4c98-a0c2-6b5114ae0b77 | METHOD: Measure
| note | 59c434ee-a931-4096-b6ef-32708f84bc38 | FREQUENCY: Each fill layer
| note | 195312b6-8ce2-4963-9276-cac9987afdc3 | CATEGORY: IP
| note | 4a120d40-e0f9-4666-9503-71e1cb910d1b | RESPONSIBILITY: PE/SE
| note | cd0e3783-e60e-4351-b8f8-ee3f2b2f7a60 | VERIFYING DOCUMENTS: This Checklist
| textbox | 165ca4c9-167c-4de7-bacb-a9456034c07f | Date Completed:
| checkpoint |  | 9 Fill-Test roll
| note | 28798b2e-9f87-4fea-987a-4729bd43f4fc | REFERENCE: 204.12
| note | e6def3dc-761b-43fc-84c8-67042ed9f397 | ACCEPTANCE CRITERIA: All layers of fill and cut floor level to be test rolled in accordance with section 173 with Nominated Authority present, using:
| note | d82cc332-08d6-4251-9eba-a330854d46bd | Static smooth drum roller with a mass >12T; or
| note | 1507f7fa-9e06-4e51-92f2-74e9b93ddb8d | Tandem truck or water cart with a mass >20T.
| note | ca37f889-0af0-4801-a927-2c91ef9565c8 | No visible deformation or springing during test roll.
| note | 78bf6bc2-66f4-4c0e-8280-91b16b0eb592 | Unstable areas rectified as per agreed method.
| note | 8b5402dc-0977-40e5-b4ae-ef5c68972198 | METHOD: Test / Visual
| note | d7083120-098f-474c-97f5-15d626720390 | FREQUENCY: Each Layer of fill
| note | 9b16e69d-4986-4e9c-aeb9-48877d9e3725 | CATEGORY: HP
| note | b6302597-b637-4ced-9a4a-4e6bdd5e603b | RESPONSIBILITY: Nominated Authority
| note | b099de67-ceae-4cef-80ff-ffa00cc23811 | VERIFYING DOCUMENTS: This Checklist
| textbox | 3b2b07f8-3527-4961-a90b-382c79f20621 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 10 Fill-Compaction test
| note | 7c1bb211-2b55-4ea0-b29d-9e2959c5694e | REFERENCE: 682.16
| note | 9cdf11de-fabc-4904-bb9f-8b3ea61306df | 204.11
| note | 7613e5de-2b53-4533-ab73-6ef4118b82fc | 204.13 - Table 204.131
| note | 76ea265c-0bd1-491c-812d-8cba50a99615 | IFC Drawing: MRP-057-C-RFLD-DRG-20-ADR-CSW-1702 Note:8
| note | 4698deac-51f4-42bd-af34-67cb6e22ca58 | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
| note | c581e574-1398-4b48-8e92-030049228e93 | SELECT BACKFILL SHALL BE PLACED IN ACCORDANCE WITH VICROADS SECTION 204 AND
| note | a170c418-2c1e-478d-9d23-2e98e2004212 | COMPACTED TO 98% OF STANDARD PROCTOR DENSITY
| note | 08079ed4-c51d-4d77-b107-cc9f33327e9c | Attach: Compaction test results
| note | b662f2d6-29bd-461e-995a-7eaba1d3de80 | METHOD: Test
| note | ba5e40af-829c-4eca-87ee-0633e6b2e870 | FREQUENCY: Each Layer of fill
| note | 432d56a6-00d8-4120-8e4d-cad5c5c133e4 | CATEGORY: HP
| note | 580f461d-2d8b-4152-a263-a34893898cf7 | RESPONSIBILITY: Nominated Authority
| note | 364f1568-196c-4c34-ac66-d11e9d13b82b | VERIFYING DOCUMENTS: This Checklist
| textbox | 234f4405-dcd9-42af-b452-7149b5ce17fe | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checklist |  | ITP-RAIL-Rubber Modular Units (Supply & Installation) Rev 2 | itp | ITP-RAIL-Rubber Modular Units (Supply & Installation) Rev 2 | 89b55126-1ca5-43fb-aac2-a91056ee6f32
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 66953186-43c5-4092-b82b-09b6f361112a | Document Title: ITP-Rail-PedeStrail Installation
| note | 2937c47a-c0e8-4916-8e39-a04b912cd1fa | ITP Description: PedeStrail Installation
| note | 6d1af35e-52ce-4abe-8e28-5b3222e522a9 | Document Number (in Teambinder): MRP-0000-MRPA-CLD-ITP-00
| note | bdaf2ca9-dfe7-4384-96d8-1c20ef8b743f | Discipline (e.g. CIV/STR/RAIL): Rail
| note | 0c908b4b-1c00-476f-aa11-ef16f24deb7c | Revision Number: 1
| note | a9dcac9c-0859-4698-9a74-0c74c30eeb58 | Revision Date: 15/02/2021
| note | c022af0a-8af6-4008-9eae-83ca20af1ae6 | ITP created by: James Porteous
| note | 23409b59-a7d7-4d92-ad8f-b97b84016568 | ITP approved for use by: Romualdo Magpantay
| note | 10e66d62-1ca8-4bb0-bfd5-a8142ac9c01c | 1.01 L1-CHE-SPE-316 Concrete Sleepers
| note | 9e2203c9-536c-432d-befc-90811eb51f3d | 1.02 L1-CHE-SPE-003 Heavy Rail Construction Tolerances
| note | a7bcc69f-3d45-4331-9c89-212cad3015ec | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | bded482a-7d5e-44d1-b9e5-ea8044acda00 | PTC Heavy Rail Track Construction Standards Drawing F598
| note | ca5e2abc-f245-481a-89c2-f07083cd1cae | Clyde Road Package 29 Design Drawings
| note | 993a7cda-ef04-487b-bb50-a7ee94ad8a74 | pedeSTRAIL Installation Instructions
| note | 62c829c7-54ba-462f-9966-a1c9bc3dcd16 | STRAIL Installation Lever Operating Manual
| note | 7620a3c0-50fb-49db-b3cc-928e5518d2bd | STRAIL Removal and Transport Tool Operating Instructions
| section |  | Preliminaries
| checkpoint |  | 2.01 Obtain and submit Material Certificate of Compliance Strail components: Rubber Panels. Concrete Kerbstones, Metal Rodding/Fastenings
| note | ce0b516d-5c41-4c55-a30a-3636092f452b | REFERENCE: IFC Drawing
| note | 1c0aaec3-bf6b-46c3-b6e6-9652e73c0f25 | Track Construction Site Mudmap
| note | e7866928-52a7-4789-957a-4ec715a2f94e | Bill of Materials
| note | 4a95e3b1-8fb0-4d91-8ef7-2e95fe2bc58a | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
| note | af8d1c3c-8636-4414-bd78-428275c120b4 | Attach: Manufacturer Certificates of Compliance/Material Test Certificate
| note | fe90827a-ad11-43e4-9553-d9ce63097dd8 | METHOD: Review, Document
| note | dee7b79c-a96c-48cc-8a69-e03de209dcd0 | FREQUENCY: Once
| note | 24830d82-7775-4835-b2b4-f22816e03916 | CATEGORY: HP
| note | c3b4caab-f865-4b8c-b484-c51292014e20 | RESPONSIBILITY: Track Supervisor, Project Engineer
| note | 59e92606-eb3c-4ed4-8b5c-cdd27007b24a | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | dfbc0b55-3894-4bb7-81d8-64fe4265a40e | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.02 Inspect currently supplied items upon delivery
| note | 6b09945c-7356-4253-bc05-8dd992ce3374 | REFERENCE: IFC Drawing
| note | b9ed7bf6-1f2b-4f0a-a948-aa0cc9352f22 | pedeSTRAIL Installation Instructions
| note | cc523ada-8c28-4080-9631-0ad7364f1981 | ACCEPTANCE CRITERIA: No damage or rust on components
| note | 941ef1b4-966f-4b5a-8c02-a3aa4d7bc9a3 | Validate total number and type of components matches drawing
| note | c69c28ef-f2c0-465b-b454-1f36369e0f55 | Attach: Photos on site;
| note | 2101333f-4078-4f1b-a9a9-5097fe077b4c | Rubber Panels
| note | 11076cc0-09f1-43c5-aad7-94e93d1f601e | Concrete Kerbstones
| note | 0d0d3b6c-eaf7-4592-9c92-eb8b59213f29 | Metal Rodding/Fastenings
| note | d5e175bc-1622-430a-b6a6-dfdde1b450df | pedeSTRAIL Installation Lever
| note | 5f705a96-de9e-43dd-9828-b1b9f994d114 | METHOD: Visual, Measure
| note | e607f832-45e0-40a2-aa89-72a598c9b17d | FREQUENCY: Per delivery
| note | 7246eff3-7512-44a1-a671-7c0cc0b56a85 | CATEGORY: IP
| note | 9ead2dcd-0212-44ec-97f1-e69afd923a9a | RESPONSIBILITY: Track Supervisor, Project Engineer
| note | 640676bd-e9db-46a0-8bef-ea23158cc26d | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | 70a3268b-f24a-4024-b001-49a9a32850d1 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 3.01 Inspection of Existing Track Condition
| note | 004e60c3-2246-459f-aec3-4adf7b6a9cc2 | REFERENCE: MTM Product Type Approval Certificate
| note | 19f2ba1b-2de3-4f8b-8f8b-dc46bcf2d818 | MTSP 030100-01
| note | 2f5f759d-d7d3-41eb-8543-3136fd4079cb | Appendix 1 Table
| note | e381bf2b-641a-4777-9c77-ab8a1019eb68 | MTST 000002-01
| note | 819ddbdb-8952-440c-9d54-a1a34c2f8093 | ACCEPTANCE CRITERIA: Correct Rail Weight (60lkg/m)
| note | 0ef09eb2-a653-45df-a85e-a573aa9fbd8c | Rail Defect Free (Surface/Internal)
| note | 81565caa-2938-49c2-9e62-e51c35ae470c | Track Geometry Defect Free
| note | 6c07459c-6895-4ffc-bdea-ffc5fe58616e | Wide gauge < 12mm from design
| note | db5714af-5322-4f49-b3be-75f7b52c50fb | Tight gauge <-8mm from design
| note | a1808dbd-7d06-4904-9f25-2aa1699dd6aa | Cant <25mm from design
| note | bd2d2355-89be-4a6c-85c7-349f9c38689a | Twist (3.5m) < 15mm from design
| note | 20bf933f-3ab0-43a3-b686-d20ba5087e8b | Twist (10m) < 30mm from design
| note | 8c670673-abcd-40f4-b84d-9d1254b620fb | Top <20mm from design
| note | 0d9cc624-74c0-4930-9d46-ae5fb9c85f17 | Line <18mm from design
| note | e549e1c6-fc8d-46a4-939e-e652fe66ebad | Sleeper Spacing @ 600mm c/c
| note | 8a446ffd-a9bf-4b81-8840-5344a27f04b0 | Ballast shoulder 450mm wide 1:4 fall
| note | 658ff17a-d832-4dda-abbf-4bf34b1a63e2 | Top of sleeper free from ballast
| note | 442b97f2-cfff-432e-86db-e277faf5285e | Attach Site Photos:
| note | a53eddd9-72ca-4f64-9e1f-1cd3d22d2c76 | Before Track Layout/Condition
| note | d79bb921-0c77-45ac-9475-07f0a044e0d1 | Track Measurement Sheet
| note | 6e289bdb-99a1-4197-bc6e-896b4841cb40 | Sleeper spacing measurement
| note | 521c0236-c27d-445e-a96e-1902e5cda63a | Ballast shoulder measurement
| note | c43e5261-f129-4719-b21d-d5f70849c777 | METHOD: Visual, Measure
| note | ff005eeb-7e13-4bf2-947c-5dff6804abc6 | FREQUENCY: Once
| note | dbeaaa0f-5476-4e5f-85ca-f75285fb9d44 | CATEGORY: IP
| note | b86d8fdb-c399-4456-ba93-d553ceecfff9 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | 19f48ec0-3942-4f87-aa45-8088236232c5 | VERIFYING DOCUMENTS: This ITP
| textbox | c8a1e3cb-e990-4284-ad49-ba77d364e390 | Date Completed:
| checkpoint |  | 3.02 Excavation of Granular Footings/Bollard hole Foundation
| note | e66d91e8-9b58-4b0f-bc7f-c2ac9e4b5464 | REFERENCE: Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
| note | 21e07f80-6b7d-47d1-954b-c211fa3adca5 | ACCEPTANCE CRITERIA: Survey Check that footings are placed in correct location and offsets to track;
| note | d69e0679-bd2a-4ab0-ab1c-adbd352080d9 | 50mm offset edge of sleeper
| note | c933004b-809b-44fa-bf96-4ed90750187e | 100mm below bottom of sleeper
| note | 109ae35a-d04f-4fa6-bb5f-c5b51f0795fd | Asset Search no underground assets
| note | 183f7692-fea7-4a10-ba80-f1df5d7bae73 | Minimum Excavation Dimensions; 600m wide x180mm deep x 24300mm long
| note | 16e57b57-8e17-4093-81d0-9d5fc17ab2d0 | Attach;
| note | 37e6f4a8-6c41-4858-bf04-c72f160a6ae9 | Survey Sheet
| note | 691fce9b-c426-48f7-a2c3-c6dfca2078ce | Asset Locator Readings
| note | 3fba01de-37e9-42b5-8583-c7eb65b3fffa | Attach Site Photos:
| note | cfe5e867-7c83-430c-a9d3-9d7ce37b3ecd | Survey Checking
| note | 2cf642e0-c4ff-46c9-92e9-bb65a5ade1b4 | Asset Location Checking
| note | f1fbb67b-ca75-43b5-a24f-429cc6d19de5 | Excavation works
| note | 37c41930-3bbe-466a-9722-7261a363451b | Sleeper Offset Measuring
| note | 5118b083-feb6-4ac2-a716-2d606ff2092a | Excavation Dimension Measuring
| note | 11947376-7c30-4508-97b4-2da2a3f3131f | METHOD: Visual, Measure
| note | fd91240c-85cf-47a8-a660-2c074101ef1c | FREQUENCY: Once
| note | 139f0945-c2fe-4ade-8335-cf973085c52b | CATEGORY: IP
| note | c04b8217-e7b7-4352-9ee9-b3cf85a435d4 | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
| note | 8be47af2-f504-4957-ae8f-45f0ac3c9c2f | VERIFYING DOCUMENTS: This ITP
| textbox | 2c9faade-ca85-4718-a6f7-e0f8c28e2720 | Date Completed:
| checkpoint |  | 3.03 Footing foundation placement (Geofabric/Cement Treated Crushed Rock)
| note | e5ca47a8-e16d-4a25-9842-015a5381c522 | REFERENCE: Material Installation Instruction
| note | 0845bec6-b31b-46ce-b4f0-51a888b0a2bd | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
| note | 318a0c48-6325-403f-8989-a4789661605c | ACCEPTANCE CRITERIA: Compaction of CTC to 5MPA
| note | 59d5a3eb-6f40-4461-93aa-91c851be93b3 | Minimum Footing Dimensions achieved ; 600m wide x180mm deep x 24300mm long
| note | 009a2f4d-2712-4fa5-91c3-21eaf72c311e | Attach;
| note | 48c2a504-83f5-4f96-a522-bbba4e29e55e | Certificate of Compaction
| note | 2d181d01-91c2-4571-b361-371eb93f81b7 | Attach Site Photos:
| note | 06c27487-d985-417e-a293-cafec99825ff | Compaction Testing
| note | 0b3b9229-3d2c-4372-bb3f-c3ad4cffb805 | Footing Dimension Measuring
| note | f43982b7-4196-4078-a874-a883b1bba18f | METHOD: Visual, Measure, Test
| note | 79de741f-cc45-40e3-b067-83f5b341bee8 | FREQUENCY: Once
| note | 6f4763b4-c85d-4bb3-b00d-af79b03f51da | CATEGORY: HP
| note | 64621ab8-10cd-41b5-9d67-3cc236f1ca68 | RESPONSIBILITY: Geotechnical Engineer , Track Supervisor , Site/Project Engineer
| note | 3fdfb2b8-d6a4-47a9-8070-143228812980 | VERIFYING DOCUMENTS: This ITP
| textbox | 90ccdc54-7e80-4560-89d3-6a5d48b82040 | Date Completed:
| checkpoint |  | 3.04 Installation of Bollards, Concrete Kerbstones
| note | 164dd812-41d5-41da-b4b3-36b3126fc6bd | REFERENCE: Material Installation Instruction
| note | 6e16df5e-5dd0-4567-80c2-9833c5034a85 | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
| note | e98b4e0d-3a7c-4636-858b-deaea3ea37aa | ACCEPTANCE CRITERIA: Bollard
| note | 86b14265-eacb-41f5-b879-bfdbe5f8956e | Concrete 25MPA with N20 Grade
| note | f0bf6d89-0256-4104-8993-31a11e0cb0b5 | 100mm Concrete below base of Bollard
| note | 5998cb87-168c-46e5-b44a-f456a9b97a4c | 1200mm protruding above ground level
| note | 1602d8eb-d43e-4c81-bf24-bb08b89ac73c | Kerbstones
| note | 9dbc2acb-fb9c-4937-b130-ae0f86e19f51 | Installed so inner top lip is 713mm offset to outer edge of rail
| note | 837a14ee-da9b-485d-9b1e-43022b212882 | 7mm screening used on top surface of footing to adjust height so that top of kerbstone in line with top of rail height
| note | 1e170ad4-1761-48e8-80dc-5c3ddc9bf2de | Attach Site Photos:
| note | a3b7e74a-b08f-401e-ab4c-853ce4bc6bef | Hole Depth Post Bottom Concrete mix
| note | 2e4d337e-d365-4bc6-8187-2442ace5cf6a | Height of Bollard above ground
| note | 5d633a7b-b9fb-4af0-956a-78744ebabd46 | METHOD: Visual, Measure
| note | 82a11552-da09-4f3d-8ab9-ce31e919952c | FREQUENCY: Once
| note | 423201ff-4dcc-4fa2-a634-bdb459315b5e | CATEGORY: IP
| note | b1dc1d86-da4b-4a1f-9a9b-82b975abbbcb | RESPONSIBILITY: Works Supervisor , Site/Project Engineer
| note | f9e9b9b5-785e-47d9-b466-6cbba57a7abd | VERIFYING DOCUMENTS: This ITP
| textbox | e575b565-cfda-43c5-bfc7-5f217e4c46ca | Date Completed:
| checkpoint |  | 3.05 Installation of Rubber Panels with applicator and metal rodding /Fastener
| note | e708cc7a-5e92-4d6e-b406-c334a5e1a9f9 | REFERENCE: Material Installation Instruction
| note | 12d1d757-da89-4726-ba36-958250207b3f | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
| note | df8448b3-311d-4eba-afc0-09d51ada3ec0 | ACCEPTANCE CRITERIA: Correct location and sequence of Panel Install
| note | 44c3a8c9-9d74-4f16-9a01-dc4fd4836c3c | Panels sitting within rail profile, no dip on outer panels
| note | 5082048b-5575-4f87-b4db-7bd129507828 | Attach Site Photos:
| note | 9d310408-6841-4f4a-a68a-2072e0ccee3a | Rubber Panel Installation
| note | 32c6f57b-7da0-43f8-86a4-e2ebda6d39bc | METHOD: Visual
| note | 6a8f2642-cb5c-4a2a-b775-db7efbe536b1 | FREQUENCY: Per lot
| note | 5e82377b-4e6a-458f-83f2-07c6addd1ecb | CATEGORY: IP
| note | 3bcd9713-3c01-4204-b997-50723ef5d783 | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
| note | 018f6bc2-f46c-4676-bd51-975309cdf482 | VERIFYING DOCUMENTS: This ITP
| textbox | 9da6be1d-bda4-4ce6-9a78-01b05434d868 | Date Completed:
| checkpoint |  | 3.06 Installation of Ballast Shoulders on Kerbstones
| note | 2ba0a751-61e4-4061-8b23-f086255402eb | REFERENCE: Material Installation Instruction
| note | 6635f474-e64c-4856-b7ff-9f53346efcb9 | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
| note | 8e9c181f-c9f5-44be-ad13-19d7bc71f8e7 | ACCEPTANCE CRITERIA: Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter
| note | 0d7961f6-3548-4e86-be48-1cd191bcd3c7 | No Ballast to be on rubber units/within gauge grooves
| note | 620dd3ab-69f0-418d-89d2-7fd615bb197d | Attach Site Photos:
| note | 64cfaf0d-29a7-47a5-9a50-95f9c46c326d | Ballast Shoulder Measurement
| note | a1b99c1c-3781-47be-b174-4b28f3ba5209 | Rubber Panels free of ballast materials
| note | 826efd03-2e26-428f-83fe-6830a8151dd1 | METHOD: Visual, Measure
| note | 5a0c525c-adce-4747-bf47-09ba68c0498a | FREQUENCY: Once
| note | e2e9f4ec-ec2b-4770-8f1a-3f1da72be799 | CATEGORY: IP
| note | 3f80c977-9cd3-45fb-bd8d-321caf556f73 | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
| note | 5090c6f2-833e-4d08-9696-1f7cee8f6513 | VERIFYING DOCUMENTS: This ITP
| textbox | 150407ee-f72b-48f7-a161-6a44917e57bb | Date Completed:
| section |  | Post-Installation Activities
| checkpoint |  | 4.01 As-built Survey
| note | e538fcf5-8d9f-41bd-8571-fb56aee99734 | REFERENCE: As Built Drawings
| note | eb02a535-7cdf-42f5-a01c-f1be90c31faa | Asset Change form
| note | 72d1ec49-16a9-4592-9570-d849124427bf | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
| note | c7cb059b-0494-41a3-9ce6-a2e303b4cd82 | Attach:
| note | dacb60ca-ab52-428d-aeb0-8c13fc6174a4 | Survey Report
| note | 280ab864-0042-4f5a-87f7-960686ac3508 | Engineering Asset From
| note | 05b1344a-eab6-4184-858b-aec26d04f056 | METHOD: Survey, Document Review
| note | 2ca37068-55e0-42c7-a82a-f71027b91228 | FREQUENCY: Once
| note | 548d5fa3-6667-4281-a9c7-bf481987c1d9 | CATEGORY: IP
| note | 9521b3c6-3728-427d-9219-6e1814f1d14d | RESPONSIBILITY: Track Surveyor , Site/Project Engineer
| note | f5f06b1d-024d-418d-9324-1aeb113fea02 | VERIFYING DOCUMENTS: This ITP
| textbox | aeb11516-1f64-4a99-a26c-ac9644ca6298 | Date Completed:
| checkpoint |  | 4.02 Track Certification
| note | 7a27c5ee-4029-488a-86dd-011f9eedceec | REFERENCE: MTMF020000-1 – Track Form A T
| note | bffc2acc-c4a6-4cc7-8769-b0a079baecae | MTMF020000-2 – Track Form B
| note | b094c369-985c-4470-a02e-a93262b6509c | ACCEPTANCE CRITERIA: Attach:
| note | 7970dc95-69f7-43e1-87e4-8eb1a1f06e34 | Track Geometry Conformance Certificate
| note | a75187eb-5707-4288-a603-f99a952d52a4 | Track System and Component
| note | bd520470-9b1c-40d6-a5ae-a6a589a003df | Attach Site Photos:
| note | bcf519e9-a06d-40f0-bfef-0613b4df5b85 | Before/After Photo of worksite
| note | 033e8c34-0d08-4f47-a27b-009bd56244b5 | METHOD: Visual, Measure, Document Review
| note | e663e65b-0811-4977-bda3-381248560de9 | FREQUENCY: Once when all occupation works complete
| note | dee31732-6314-4989-9b29-0765c31de5f9 | CATEGORY: HP
| note | 6f2e91cb-8792-452e-9474-48b24be52e45 | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
| note | 2733b7bd-4d43-4b6b-aea8-f150320340e8 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 976dd494-5d90-459e-8405-ad3f7d75f9a8 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 10bfed29-a9cd-409b-9b3e-08b6e342c27c | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 8cc3c356-1b38-4766-bea1-722bd2ddb55f | Name:
| textbox | faffcc54-5986-42a0-88fb-ae61bb17fa85 | Position:
| textbox | a0bb76d2-5d9b-4542-99ee-f30ea41e1800 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Bored Piling Rev 5 | itp | ITP-STR-Bored Piling Rev 5 | 8b708dbe-26fb-4054-a6c5-d76962a6520e
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 4ce27a64-6072-4635-9beb-2667e04f06fa | Document Title: ITP-STR-Bored Piling
| note | bcad1d37-a71f-4cec-9adb-40efb5180451 | ITP Description: Bored Piling
| note | 59cac514-c645-4f30-99a1-8e05c3a7b9e8 | Discipline (e.g. CIV/STR/RAIL): STR
| note | 397e2448-56c7-48bb-bb75-ec25c0a7b0c0 | Revision Number: 5
| note | 642e2366-7285-4151-854f-4b8255b244ea | Revision Date: 12/05/2021
| note | c2bb026f-15c0-455a-b602-fa783d59745a | ITP created by: Mike Freeman
| note | 68187e2f-c04a-4148-846e-582b97873920 | 1.1 VicRoads Section 606 July 2017
| note | 59d1c62e-cde3-47d5-84e9-80a09ca90a24 | 1.2 VicRoads Section 610 June 2019
| note | 409ecd45-d7d6-4856-81ef-7f55ab6ba6a8 | 1.3 VicRoads Section 611 November 2018
| note | 321f7abc-10fb-4210-85ab-eec4b58112ec | 1.4 AS2159-2009
| note | be1d894a-ed94-43ac-93fd-a214fc00f166 | 1.5 AS3810.1 2018
| note | b58506dc-164b-4e15-970a-357d843eba87 | 1.6 AS5100.3-2017
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Concrete Mix
| note | 3586338a-7fc4-4f83-8b7b-45b11d29c376 | REFERENCE: 610.07
| note | 78e5449e-b90f-4736-ac47-6d5cdc17c7c4 | Table 610.071
| note | c29d366e-55cc-4b5a-a9e2-8d8471965461 | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
| note | b55f202f-99c5-4dcd-8d83-fb3454307197 | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
| textbox | 9142bd13-2714-40cb-a5e5-f73272f9b913 | Enter: Teambinder Material Approval number
| note | 939fa100-4c63-4996-9f0b-92bfbcff6276 | METHOD: Document Review
| note | 630464ba-fcec-4d50-845b-37a65dd3fe8a | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
| note | b284cb9e-e026-47b0-9401-6002b2205975 | CATEGORY: HP
| note | 445634e9-85eb-4d12-8c6f-d1c9b211d85b | RESPONSIBILITY: Nominated Authority
| note | abe0279c-cf5e-45e5-9a90-e65c61b5c986 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 9dfee121-81a3-4ed9-ba7e-219ec1c04d15 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 ACRS Certification (for Reinforcement)
| note | 46df5941-f9eb-4c77-adaa-414262c0a71e | REFERENCE: 611.05 (a)
| note | f2d62a80-e3d7-46f3-9727-a57d6961ebbd | Table 610.071
| note | 51094f65-820c-4fcf-9fbd-b2e848dc8604 | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
| note | bfd4c56b-e876-4f0d-8f63-05a26506854e | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | f2917206-a4f1-4525-af90-853c2027aefe | Enter: Teambinder Material Approval number
| note | eef530c0-f16d-4551-a0a1-babcec465e52 | METHOD: Document Review
| note | dd7a2abd-8b1e-4ef7-9a7e-0add6ba192a5 | FREQUENCY: Once for each supplier, 14 days of award of contract
| note | 1d16cbb4-034b-48f9-a020-d82f3498373a | CATEGORY: WP
| note | 37d56fae-7f1e-4185-af45-b562577351d3 | RESPONSIBILITY: Nominated Authority
| note | b3462f5e-7c41-47b7-b512-ddbcc51e9dd7 | VERIFYING DOCUMENTS: This ITP
| textbox | f54d2639-af17-4108-8b6a-2b3129c3cc0f | Date Completed:
| checkpoint |  | 2.3 Bar Chairs/Aspros Certification
| note | 2ad69838-33f3-4615-b0b5-0327fc6ecc42 | REFERENCE: 610.26 (a)
| note | 0bf669a7-fc17-4593-ab92-d32e247bf2e9 | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
| note | 873830b0-a929-4c23-9999-521999f8b5f1 | Concrete aspros require annual compressive strength and soluble salt testing is required.
| note | 84c18b4c-3c6d-4aeb-ac99-5f831db3c34e | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
| textbox | fee9439c-a624-409e-bed0-a29506b35878 | Enter: Teambinder Material Approval number
| note | f10c0aeb-5b67-401d-bb7e-f7f816b0b4e2 | METHOD: Document Review
| note | 29a31b61-963c-41c0-8d7d-09524cff68ae | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
| note | eb6ba838-946d-40fc-a76b-734a3d7459f9 | CATEGORY: WP
| note | 023bd231-f9ce-4ffc-8538-7346b72e13bf | RESPONSIBILITY: Nominated Authority
| note | 544dde91-e1a3-4a02-899a-94b174cd4ed4 | VERIFYING DOCUMENTS: This ITP
| textbox | 4c866a36-88de-4b64-86ad-0b11cca9a139 | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Piling Operations Work Procedure
| note | 57714457-3083-4c43-9db8-5ff311f2fa38 | REFERENCE: 606.03 (a)
| note | 24b85304-51b7-4327-a7ea-b369a9669734 | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
| textbox | 6dff5fd1-e7b7-4f9f-8d3b-84330d347b7f | Enter: Teambinder Approval number
| note | be2f43cd-f68e-48bf-a11b-f03dcdf166bd | METHOD: Document Review
| note | 96921752-0a1b-4d77-acbf-a92818e0a599 | FREQUENCY: Once, 4 weeks prior to the commencement of piling
| note | fbc7a8f8-3cdc-404c-ac00-6875e7e6c079 | CATEGORY: HP
| note | a71126eb-6fae-416f-8fee-ccf3b8a4d5db | RESPONSIBILITY: Nominated Authority
| note | ac227da2-b5e2-48a0-9eeb-d4ff2e455645 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 14982e56-b79a-4406-88e5-07f867b3af4e | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Temporary Steel Casings
| note | 890e20aa-b4bd-47c8-ba83-678dc700e41c | REFERENCE: 606.03 (b)
| note | f249c9bd-8d16-44a9-ae9c-c63bfe2e66cb | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
| note | 7d853f5b-9cab-40b3-a7fd-4188c182333e | Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
| note | 63625a48-2a3c-41d6-8e04-9113bccc9615 | The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
| textbox | cea87cdd-3118-417c-919d-8c3fa206cc73 | Enter: Teambinder Approval number
| note | 1e306228-9a39-4f28-a6c2-8a6438751c32 | METHOD: Document Review
| note | 07fcb19b-9ca8-408c-a188-b2fa6372ed00 | FREQUENCY: Where applicable, once, prior to use
| note | bc5772db-6a53-470a-80f3-d3b0fc46b0e8 | CATEGORY: WP
| note | 04edda40-fb73-46ab-8c1a-32bf4fbd9333 | RESPONSIBILITY: Nominated Authority
| note | 122a6a53-13ce-4e7a-aa48-a5a1b338ce4d | VERIFYING DOCUMENTS: This ITP
| textbox | c1e8de60-20c9-4776-977e-04a040108bd5 | Date Completed:
| checkpoint |  | 3.3 Casting Under Water Procedure
| note | 4ea04ae9-cb4a-4907-ad1d-8f8af98fb5cd | REFERENCE: 606.06 (a)
| note | 5f43017f-b401-437c-a000-5907b4b7c03e | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
| textbox | d16f2622-87b2-4ead-924b-d178c7c0acc5 | Enter: Teambinder Approval number
| note | 4790ffbb-5c64-45ac-8f15-aa659a4c50e3 | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
| note | 3b3ce3b9-fef3-43f3-88a9-f00011e03477 | METHOD: Document Review
| note | 35fcf868-14a3-4088-b8fd-f57c0a774399 | FREQUENCY: Where applicable, once, prior to placement of concrete
| note | cd1cc6c1-e319-4093-b698-9185b2811d8f | CATEGORY: WP
| note | 710bd197-d82f-48ba-838c-d9876ef0b5e3 | RESPONSIBILITY: Nominated Authority
| note | 206375bb-9da9-4eab-b316-769cc77e061f | VERIFYING DOCUMENTS: This ITP
| textbox | 3078a295-5230-4aab-b0b2-33642f10ae8d | Date Completed:
| checkpoint |  | 3.4 Boring With Bentonite or Polymer Fluids
| note | 6f7a3030-25ed-48a9-ab81-9817da14663e | REFERENCE: 606.06 (c)
| note | b8cb22c7-e4ef-48f6-a32c-b2add8820515 | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
| textbox | 32502ad2-409e-4eff-b576-7f684936ec0d | Enter: Teambinder Approval number
| note | 1c089cac-15df-4eac-8fe2-74851b7aed0a | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
| note | 06f3aa9a-8daf-4331-92ee-41d32edab5e8 | METHOD: Document Review
| note | 85da2c07-e0ce-437e-af14-54c8f891d240 | FREQUENCY: Where applicable, once, prior to commencement of boring
| note | 64359c33-ace1-4077-8398-a136256c6ce1 | CATEGORY: WP
| note | 8a47f66e-ea24-4dda-9283-c6902f9ba85d | RESPONSIBILITY: Nominated Authority
| note | ddeedfaf-0d18-46cf-a51d-0c1c60abd2c8 | VERIFYING DOCUMENTS: This ITP
| textbox | 1383ce2b-a3df-4b31-a9d9-423e36d07373 | Date Completed:
| checkpoint |  | 3.5 Dynamic Pile Testing Procedure
| note | 6fec49f2-f53c-4d1b-9ae1-a4f28b6933e1 | REFERENCE: 606.07 (c)
| note | e5abe783-b111-4b32-ae83-47f9369c377a | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
| textbox | 4925717c-779a-4459-b537-d18216008a76 | Enter: Teambinder Approval number
| note | e4670812-5fc9-47fa-8965-2703ef0c2119 | METHOD: Document Review
| note | f8f65fb7-1d40-47f5-a276-90adea551595 | FREQUENCY: Once, prior to testing
| note | b41bf695-e214-483c-b6e9-30e20083496f | CATEGORY: WP
| note | 356cd7da-d0a3-4206-9b4e-f60a1cf48196 | RESPONSIBILITY: Nominated Authority
| note | bf4af1e6-9ca9-45a6-8063-d176e579b884 | VERIFYING DOCUMENTS: This ITP
| textbox | 00e80e6a-3f3a-402c-b173-fe4ca9759e40 | Date Completed:
| checkpoint |  | 3.6 Pre-qualified Pile Testing Consultant
| note | a1c81245-e826-4ec5-810b-2398ffb596b3 | REFERENCE: 606.07
| note | dbd7d7f5-38ab-4c2c-8903-db050ec63ea3 | ACCEPTANCE CRITERIA: All testing shall be undertaken by a pre-qualified consultant who is independent of the piling contractor.
| note | 5d81bf53-461d-477d-b877-1e64bc42a4f9 | Details of the consultant to be submitted for review to the Nominated Authority.
| textbox | 35293069-1b81-4270-b22b-779c85b86229 | Enter: Teambinder Approval number
| note | 1bbd8a28-1cd9-4ee8-89ee-5ece5e2ea654 | METHOD: Document Review
| note | e55498d4-24f0-4a2e-a947-44362fad9b7a | FREQUENCY: Once, prior to testing
| note | 2d45fff7-8f7d-43eb-a58d-9e37ef9ae9bd | CATEGORY: HP
| note | c2972f6a-033b-4910-9c24-d8de088ba84a | RESPONSIBILITY: Nominated Authority
| note | 5d3280d3-4904-494c-9da0-7d4ba22f4c1b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | a843d675-cc52-456a-9ef9-eccab21e8f21 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.7 Reinforcement Welding Specifications & Qualifications
| note | 13f94e35-7438-40da-9e46-fa4cc2197b31 | REFERENCE: 611.13 (a)
| note | 827092fc-bb29-4b51-9f38-d64f0f7fa4d9 | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
| note | 042039ad-c34e-4a5f-8b75-cc62c613e5f5 | 611.14 (b)
| note | c0f7944c-7bb2-483c-8e5a-38f0f96bb761 | ACCEPTANCE CRITERIA: Welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
| textbox | f64b4587-fd89-422c-b46c-0b7c076406a6 | Enter: Teambinder Approval number
| note | 7a83c3aa-80dd-4a3b-beee-d668111c2093 | Note: Tack welding requires the same documentation but is a Witness Point
| note | 3e054c06-5f0a-4d37-9478-e71199053b4a | METHOD: Document Review
| note | 68cf42f0-b1e3-4ab6-862c-6c399d3c09c1 | FREQUENCY: Where applicable, once, prior to welding
| note | 7b60b193-50ac-426b-8828-558ec43b5fd0 | CATEGORY: HP
| note | ee53201e-a8f0-40b5-9ff5-3f5be638d148 | RESPONSIBILITY: Nominated Authority
| note | f965c57e-0ccd-47d6-9c2f-b80e8c6a8eca | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ffecc083-44b7-4653-8000-eb5f2d6adcd7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 IFC Drawings
| note | 3e70abb4-a470-4a5b-a1cb-e574dde79cb7 | REFERENCE: MRPA Quality Management Plan
| note | b4caba83-36ef-49c1-aa7d-c42641b47262 | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 29d8b3c4-e7bc-49ef-8ab7-8ce42b75c3f7 | METHOD: Document Review
| note | 7c0456e7-12b2-4dc6-849e-ed7deaf25e0f | FREQUENCY: Prior to starting Works and at regular intervals
| note | c0035182-1d43-4d8d-972d-892ebad349f0 | CATEGORY: HP*
| note | 1ec4888b-70d8-436b-9cc2-0e0fc442a025 | RESPONSIBILITY: All
| note | d17a1cde-7e80-4e42-8d19-dc490219642b | VERIFYING DOCUMENTS: This ITP
| textbox | 8871ed34-c621-4421-aec8-26dd72453987 | Date Completed:
| checkpoint |  | 4.2 Survey Set-out
| note | 28ac12d5-23fa-4658-8030-67db454d2ee1 | REFERENCE: IFC Drawings
| note | 844bba13-8c8d-4b10-ac2c-680870783156 | 606.08 (a - c)
| note | 43029986-25fa-4286-b098-8c746262cc2c | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
| note | d60cafc8-5a83-4b7c-8c9f-1e381555b193 | METHOD: Measure , Visual
| note | a4c0e3fc-2dec-46a2-9a04-e6fb18b3a9fe | FREQUENCY: Each pile
| note | 09d8c1ab-07d3-4565-b61f-a461e3f74c0e | CATEGORY: IP
| note | f8eb96ab-57d1-433f-84f5-f26d2c22eb4d | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 843106f9-24bc-4810-9a47-937d5c53241b | VERIFYING DOCUMENTS: This ITP
| textbox | a48976e0-81a0-4284-b8ea-b9bf0e1f645d | Date Completed:
| checkpoint |  | 4.3 Protection of Adjacent Piles
| note | cb58e212-850d-43bf-9391-1041d4cc1ea2 | REFERENCE: 606.04
| note | aeb7c34b-f3bf-438d-b6cd-9916c1e56de5 | ACCEPTANCE CRITERIA: Pile construction shall not:
| note | 62522a97-d1f3-4b16-8bd4-420c6bc623a2 | i. result in damage to adjacent newly cast piles due to ground vibration.
| note | b8fabc60-6c61-4757-887c-2146280aafb2 | ii. commence within 2.5m from newly cast piles if that pile concrete strength <15MPa
| note | 5ba557d7-15ff-456f-99b3-092a5999d94c | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
| note | 15eedd64-a3c9-4d53-8093-7aa2c948f2ce | METHOD: Measure , Visual
| note | e70880a8-64e3-410d-8624-67965fd07d70 | FREQUENCY: Each pile
| note | f378614f-1112-4c19-b934-f0d65bba895c | CATEGORY: IP
| note | d5c84765-6b91-492b-a15d-0e0f9bb23240 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 3395ae19-a87d-4f48-9850-ed1e32c27f70 | VERIFYING DOCUMENTS: This ITP
| textbox | 4cdc1f57-3f3a-442b-91c3-ff1e7257eaa9 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 5.1 Boring Operations
| note | f54b29a0-5e33-486f-9ef2-4fa2b5119f24 | REFERENCE: IFC Drawings
| note | f7f3ab74-3c28-4d03-8d79-6e904b815dd8 | 606.03 (a)
| note | 68edcdf5-e643-4fdf-8445-7a856be63f17 | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
| note | cdae7343-a00b-4b50-bb5c-5fff4a9a683a | Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
| note | 50ae8e73-e275-4a1d-8a68-ea1b48ea00ad | Excavation clean and de-watered (where applicable) for inspection.
| note | c5b60b2c-98a7-4ace-b4c6-7537f1a1d3f6 | Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
| note | 3fd4073e-0d22-41e8-a46a-89a98c5dd3b2 | Excavated material to be disposed of as appropriate to maintain a clean site.
| note | 03824e49-0575-4475-8753-f596911fa337 | METHOD: Measure , Visual
| note | c9bf1ff2-7f63-4769-b796-372a413e968f | FREQUENCY: Each pile
| note | 29d448e5-aedf-45f0-9f5d-5acbbf336519 | CATEGORY: IP
| note | 077343ed-32f9-4194-8792-9bf987668c43 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | fb40bbc0-d6b3-4372-888d-4b20af637c71 | VERIFYING DOCUMENTS: This ITP
| textbox | fa04eb4e-30cc-406d-b5d2-3819d56d5143 | Date Completed:
| checkpoint |  | 5.2 Formwork Extension
| note | 171147d3-9f4c-43ae-8cbe-99f0cb672a50 | REFERENCE: IFC Drawings
| note | 6b4e7729-cc90-4688-a8ab-b8e983b3d3a5 | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
| note | ec52fb94-4d55-4df0-984f-5960c42af3c5 | METHOD: Measure , Visual
| note | bb956dbd-65ff-4f73-9ed1-22c19a9ad157 | FREQUENCY: Where applicable, each pile
| note | f8408021-ac6b-428d-97a0-d02d80940c16 | CATEGORY: IP
| note | 252d6702-a361-49ce-8bac-5548c27a8a30 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | adee2ae4-137c-4879-99f7-30393b19e99e | VERIFYING DOCUMENTS: This ITP
| textbox | 04a50c30-f476-40af-a4f3-4d99e60c90ab | Date Completed:
| checkpoint |  | 5.3 Inspection of Pile Excavation
| note | 625fae7a-4999-4033-a9c0-0a894867e0a1 | REFERENCE: 606.05
| note | 4bbd0267-8ed2-466b-b913-2adf9759e0db | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
| note | ad0f9a92-74c4-4e94-b5c4-ab00177d2ed3 | Attach: Geotechnical Field Sheet or Report
| note | 903ea199-1f42-41f5-86ea-c83770778220 | METHOD: Measure , Visual
| note | 5aa4a731-74c4-40fe-ba7c-03666bbc80e2 | FREQUENCY: Each pile
| note | c1a9f0d9-a4a5-4286-9120-5fb5e19a9342 | CATEGORY: HP
| note | 4d396aaa-7bbb-4653-9187-535b614ba6d7 | RESPONSIBILITY: Geotechnical Engineer or Nominated Authority
| note | 67182c9b-1f59-4989-b026-3bce014d5228 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 86b2604c-63dd-4e3a-888e-5df0fdce5057 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4 Reinforcement - Placement
| note | ea1dc11e-5633-4b9f-859d-99266519374b | REFERENCE: IFC Drawings
| note | d4b3ef9e-a16e-43aa-a3c9-daebbe615081 | 611.06
| note | 81a72bb0-bfed-457c-b400-56fbb013ddee | 611.09
| note | 6587dcde-db22-42a1-8395-9421a2b8f088 | 611.1
| note | ae9e24cc-7100-454c-b454-4f1c0b7b5a9f | 611.11
| note | b71cfbfd-7782-41e5-8a77-3aa87e6aa7b5 | 611.12
| note | eb03a509-dd2c-43ec-a393-a39cb9cee28e | 606.06 (a)
| note | ec502a6a-c88f-4041-9530-e22180692805 | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
| note | 90b2e3bb-217f-4fd0-aff5-66b3adcc49f4 | Projecting reinforcement is the correct length and location.
| note | fa3b141d-2fde-4fb5-8a22-e654d8c888e2 | Splice lengths achieve the minimum length and are in contact for this length.
| note | c2acb6bc-9b88-475e-8938-a254681c9c9f | The reinforcement surface condition is free from dirt, debris and damage.
| note | 75cbd0b0-259b-4e5c-a588-0dd68c05fa7d | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
| note | 2010cd7d-9b75-4ec5-85e5-dbd5fe00acf9 | Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
| note | 6d2adfc3-7c3b-42d3-b361-babecd13e8c0 | METHOD: Measure , Visual
| note | 507214f0-10f5-44a3-8461-89c7774c4b55 | FREQUENCY: Each pile
| note | ba643e76-36d5-48f0-8ca8-8d684607bcdd | CATEGORY: IP
| note | 881d3484-55cd-480d-a16c-a4e12dcde1b2 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | ee1aabc5-478b-4a2a-b867-bb1326119f1c | VERIFYING DOCUMENTS: This ITP
| textbox | 8a7d89f4-fb91-49e8-85d4-0eb65ff04fe3 | Date Completed:
| checkpoint |  | 5.5 Reinforcement - Electrical Continuity
| note | 703c5fa5-4260-4a4e-b19e-4ac16b08550d | REFERENCE: IFC Drawings
| note | 9f2b5798-11f1-498f-98d3-128fc4111a17 | 610.29 (d)
| note | d65c6239-2b5e-468a-b4f4-202bb24756b4 | 610.43
| note | ebf3122a-5a5d-411e-bd12-3d07b09cd079 | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
| note | 549d66b4-909a-43b9-9cf2-3e82e5d32cad | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
| note | 5e5900a8-883d-4eff-b18b-2adef6a6ea75 | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
| note | c4412293-408d-4170-bba8-ecd5bd4561bb | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
| note | 0291900e-2fd9-4b18-9a2d-d39599519873 | Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
| note | 60d2df14-dd19-4b83-9b16-113532455243 | Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
| note | e36d5337-af52-4b46-b48e-e49eedb4dc2c | METHOD: Measure , Visual
| note | 47d46334-5cae-4a3c-9266-e01ffa3df43e | FREQUENCY: Where applicable, each pile
| note | 88c138ff-960e-4b1d-a059-85bba1a3277f | CATEGORY: IP
| note | cdea8469-0c2a-43b0-b60b-ecb298c7d22b | RESPONSIBILITY: Earthing Engineer , SE/PE/SPE
| note | e0200b28-7d36-4249-bc1f-c5ef2dde5d99 | VERIFYING DOCUMENTS: This ITP
| textbox | 8353142d-216c-404d-855f-d53e858ba3f5 | Date Completed:
| checkpoint |  | 5.6 Cast-in Items
| note | 8bdec2f9-4702-4446-bfde-030d4f65a3bb | REFERENCE: IFC Drawings
| note | a720829f-5cf7-4025-90e0-2e97f7ebcb43 | 610.46 (a),
| note | e02f6703-eca4-4058-b9ef-d510527f049d | Table 610.462
| note | 26481499-7e05-447b-b521-b83caea14eba | (November 2018)
| note | 1a9258de-9c21-41d8-9f96-e528f0a24383 | 610.47 (a)
| note | c0125be7-8acc-4de3-a563-a3ecb1242c8f | Table 610.472
| note | 0fffadfe-7d38-45c4-93bd-50c1a043055d | (March/June 2019)
| note | 5f69c605-151f-4176-8865-a3d66c47ce8d | AS3810.1 Table 3.3.6.2
| note | b87ee896-3f2e-41f7-9051-9033ec1c589c | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
| note | 758bf293-eb97-4da8-af9e-ac4af16a9822 | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
| note | addadc43-b113-442e-91db-4c3d8b3df9d4 | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
| note | 8b56f3e1-4acc-45c1-8632-2e88c24a3fc1 | Grout tubes shall be fastened at regular intervals to prevent kinking.
| note | 7533d66c-9527-4cc6-b386-07d44c9adfe3 | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
| note | 3ba6fe61-e08f-453b-89ce-44d6a669e259 | i. Bolts, ferrules, projecting bars & couplers = ±3mm
| note | 09365aeb-6469-465f-9b82-167dc5699dbd | ii. Running dimensions of a group of the above = ±6mm
| note | 402b8700-3b63-4db9-8a71-31e7c7ef615f | iii. Ducts and conduit location = ±12mm
| note | 370e38ea-add0-47f1-8fa9-3c242cc8832e | iv. Diameter of ducts and conduits = ±3mm
| note | 837b07bd-1741-4bbf-9136-47f877e733dd | METHOD: Measure , Visual
| note | ed78e3d3-30df-4ddb-8014-e5b5fd30d6df | FREQUENCY: Where applicable, each pile
| note | d25a62cb-9f40-4d78-9dbf-133eb61de6e7 | CATEGORY: IP
| note | 86074b5c-9ea7-4b71-b4bc-a25073df87ee | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | fcc69ba3-38d5-4b49-840b-ca9cbc6bd0d7 | VERIFYING DOCUMENTS: This ITP
| textbox | fcff4233-ccbd-4411-ab26-f00714021991 | Date Completed:
| checkpoint |  | 5.7 Pre-pour Inspection
| note | 5eb30069-b8dc-450a-9dc0-a48540805d2b | REFERENCE: IFC Drawings
| note | 73e514b9-1178-4d93-9741-680362d7d4a4 | 610.18 (a) (ii) & (iii)
| note | 09cb9eda-6235-486f-8336-8dc021a4668a | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
| note | 9a284f10-ec4d-4110-9cba-5774b64372a0 | All foreign material has been completely removed from the excavation.
| note | b8a97a11-078c-417e-9e0a-955b421eb57c | METHOD: Measure , Visual
| note | c4f8e8a3-3b1c-4701-8349-894b6031d800 | FREQUENCY: Each pile
| note | 85cb4717-2fc3-415d-975b-505b3289cf05 | CATEGORY: HP
| note | f1a41fda-7acd-4a89-8ebf-4b033325530b | RESPONSIBILITY: Nominated Authority
| note | a0530d26-0d09-45ec-9fe0-1dae5e2e3fce | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | dd4065df-37e5-4278-8624-d568f2c16bee | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.8 Weather Conditions & Evaporation Limits
| note | 13dfc8bc-5189-45d7-8971-38be416b3926 | REFERENCE: Hot and/or Cold Weather Concreting Procedure
| note | 74951cf5-4a18-46c9-a670-c545a338c4e9 | 610.17
| note | 5481b9d4-9bdc-415d-9f40-dd205db3601f | 610.17 (a) & (e)
| note | 4a274ef0-d25a-420a-9f5c-36fb09b0622e | Table 610.171
| note | f90a9826-5ef2-4ea1-8ff9-bb493f732e97 | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | 089749f3-7b37-4d4c-9116-ffa664a2d09d | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | e55fee87-0dbd-4e98-ac28-cd8bf854f614 | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
| note | 258d74b1-02a0-4c57-b17a-f3175dfc0b37 | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
| note | 155b3666-c4c9-4625-86d3-3c0097099828 | Record: Required information on the Concrete Pour Record.
| note | 793cad2a-ee54-41ad-b17b-d8bccd28b932 | METHOD: Measure , Visual
| note | bff73a7c-50d4-43dd-9e0a-f759e8e37415 | FREQUENCY: Each pile
| note | 2e7c7290-6cfb-416e-9399-30e9a3c5741e | CATEGORY: IP
| note | 0b6baf18-d859-477d-9eda-2200478e772d | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 04fd6793-f652-4ce8-aa95-c01d1bffed69 | VERIFYING DOCUMENTS: This ITP
| textbox | d853b390-c6c4-4f1e-9647-9bf3616808ba | Date Completed:
| checkpoint |  | 5.9 Concrete Testing - Sampling Frequency
| note | dea5ac38-3765-44d5-8412-b34c249cd08e | REFERENCE: Site Sampling & Testing Procedure
| note | f38f2003-9154-425d-9fd6-f01aca3c5c98 | 610.16 (b)
| note | bd4db532-fb5d-461f-be1b-aac72f407002 | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
| note | 6807f8e1-13d0-4c18-8b66-a0cd1751d471 | 0m³ to 10m³ = 1 sample
| note | 57a935a7-80d3-4f5e-b529-cd3ee819836f | 10m³ to 25m³ = 2 samples
| note | 95faef3b-a96c-4eb2-b936-4c9e79c0b927 | 25m³ to 50m³ = 3 samples
| note | bfd79e90-70ae-4ee3-a437-f13d4eedba1f | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
| note | 58657bbf-b547-4a02-a2bb-1715640ec6e2 | For each additional 50m³ and additional sample shall be taken.
| note | ee8bb965-8096-48d4-ae91-28b20463984d | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
| note | 49c5e0f0-b49a-42e5-868d-4ce9644853ab | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
| note | cf9f0678-21e0-4176-8a02-d8dd9922194a | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
| note | ae077ddb-de49-4604-aa8f-25d30db10497 | Record: Required information on the Concrete Pour Record.
| note | fc31f4c1-9efb-46b5-86a8-94c662d1795e | METHOD: Test
| note | e9d1d11c-f4c1-4fb7-bf6e-9b69c505b597 | FREQUENCY: Each pile
| note | fcef2738-50d9-4378-9765-492063e526d9 | CATEGORY: IP
| note | 4e4d7438-1e52-4bc3-b8e8-50cc926c5c1e | RESPONSIBILITY: Concrete Tester , Foreman , SE/PE/SPE
| note | 9ef455d0-c868-4df4-a0d9-9735441ace5e | VERIFYING DOCUMENTS: This ITP
| textbox | 152b05d4-01f7-4044-bf60-6e2f92f263bf | Date Completed:
| checkpoint |  | 5.10 Concrete Testing - Spread, Passability & Viscosity
| note | e306100d-5fe4-472f-8894-675002baf6b4 | REFERENCE: 610.13 (b)
| note | 7e6f749b-ff82-46f7-8f67-fc03ed6bb649 | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
| note | 5caed2d5-83eb-46c5-9e59-02a1032e9862 | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
| note | f3fcdaa2-5095-4faa-beb6-b7f4ca6f8f7d | Passability = ≤10mm (aggregate height differential)
| note | 52ce8ae8-867c-40ad-b034-a61382c8dffa | Record: Required information on the Concrete Pour Record.
| note | 54b10a14-2017-4ed9-894c-320d1813d7b6 | METHOD: Test
| note | c2d44c1f-c3ba-4d47-9b92-c0e295cad230 | FREQUENCY: Each sample of Self-compacting Concrete
| note | 016525dc-dcb1-4063-b49b-ff99333b04f9 | CATEGORY: IP
| note | 7c88ef01-dcf7-49e0-8181-0947a602de20 | RESPONSIBILITY: Concrete Tester
| note | 3b3dae37-f30c-4323-870e-cdec58da14e3 | VERIFYING DOCUMENTS: This ITP
| textbox | 473ca3dd-fada-491d-b3c0-a446952cc67c | Date Completed:
| checkpoint |  | 5.11 Concrete Testing - Compressive Strength Cylinders
| note | b63fc3a3-37b7-4ac9-ad47-9eaf279a897b | REFERENCE: Site Sampling & Testing Procedure
| note | e6d014b8-d4fc-49e4-9c60-04a726875117 | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
| note | d5de5ba9-25ed-4abf-b98b-a475481b9c8f | Record: Required information on the Concrete Pour Record.
| note | 69307755-00d2-481c-81f4-1870dee4dbde | METHOD: Test
| note | d4e52f89-afdc-4d97-a6be-cbb05b0a59d7 | FREQUENCY: Each sample
| note | 1ffcce85-a885-46cb-9b61-d6c25300da21 | CATEGORY: IP
| note | df8eeeac-33b3-4625-bacb-3342c1620443 | RESPONSIBILITY: Concrete Tester
| note | 247ff6b4-5c7a-4ee0-8f2c-a2f865174a4d | VERIFYING DOCUMENTS: This ITP
| textbox | 53fd216b-f377-42d7-b988-837bfbef9bec | Date Completed:
| checkpoint |  | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
| note | 7ff43118-7587-4f34-b9ca-4b3248840b54 | REFERENCE: Piling Quality Procedure
| note | 89c7cf50-b4cc-42d3-b460-681c61954b4c | 610.18 (a) & (b)
| note | 4e11cbde-a9ac-4217-add6-6ce27fcc773a | 610.18 (d) (i)
| note | a2cb6003-b757-4f59-84cd-a913d2632920 | 606.06 (a & b)
| note | afde1153-4f4e-4f9e-a936-e126412f5ecd | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
| note | 641ed19b-fbda-45e6-84aa-f0d1219ab5dd | All concrete batches are traceable.
| note | c6ead33c-5108-4f81-8e8d-23135474cce0 | Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
| note | 2e6dc2af-4ea0-41e8-bf80-3ae6d15c63ef | The initial discharge is pumped to waste until a consistent workable mix is discharged.
| note | 2622346c-07d3-4875-9a50-49051432e903 | When placing under water, the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
| note | 0f07cf2c-fea3-4954-b154-7536aee0c639 | Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
| note | 0fd07e9b-a311-472e-b660-fe00c8b138fc | Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
| note | 6bbb3577-2e14-4fb6-9312-3f1933e35e6c | Record: Required information on the Concrete Pour Record.
| note | a2441358-fad6-4d70-951c-9721dd7eb1f6 | Attach: Concrete Pour Record
| note | 581a7887-440a-470e-adf5-ab1fc3f72340 | Attach: Concrete Dockets
| note | 8771d1ce-f518-4c3f-8114-30cd600a536d | METHOD: Visual
| note | 82935369-c78d-4a39-84b3-c9f7c46092f8 | FREQUENCY: Each load
| note | ac91128b-1b5e-4515-8829-bcd4ea873198 | CATEGORY: SP
| note | 3e37e72d-6951-422c-8e25-3941b546539a | RESPONSIBILITY: Foreman , SE/PE/SPE
| textbox | 4242ac6a-1ad1-4192-9233-799629147c88 | Date Completed:
| checkpoint |  | 5.13 Surface Finishes
| note | 66f13522-3b51-4deb-ba3e-e06106f87639 | REFERENCE: IFC Drawings
| note | 62f88edc-221e-4e67-a11b-44989c29dcda | 610.31
| note | 83b3f301-4c97-4abb-a6a2-7f24522b40cd | 610.2
| note | b5a796bf-1156-4c25-b4dd-b22e42298f32 | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
| note | 6d778437-b203-4e8c-9b0e-9151fd812bfe | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
| note | 82cb8284-e0e7-49c9-89d7-2e2aab6f08be | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
| note | afabe188-dc2c-4843-9ee1-5d93cecd6cc8 | METHOD: Visual
| note | cf937fad-3106-4f7e-9f93-aaea9c048307 | FREQUENCY: Each pile
| note | cb8ca219-dddb-4d9f-9c3b-70258bdce427 | CATEGORY: IP
| note | c721fb88-eda2-4db2-96ad-2949ff2bcbb1 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | e4e4ae65-68c6-479f-a3f7-13d3b8afcbf4 | VERIFYING DOCUMENTS: This ITP
| textbox | 2ac53d43-6049-483a-a0e9-239d244383eb | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Pile Trimming
| note | d1d5d446-02b4-4160-84f1-f1baa226ff82 | REFERENCE: IFC Drawings
| note | b14f0138-eb8a-43f2-82e5-4a8e728a1cb8 | AS2159 Clause 7.2.2 - 3
| note | eeb7d372-0a09-4022-9195-6fbe821443c7 | 606.06 (a & b)
| note | 29abbff2-4dd5-48d2-b983-30bd818e5e52 | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.\
| note | 4551876a-7351-4b64-892d-3aeb68c445ef | Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
| note | d04de5fb-032e-4332-b5c2-0667531e51d5 | Any weak or damaged concrete shall be removed back to sound concrete.
| note | 1f6f8e1b-4cd7-4358-9f81-6b5e5af560e0 | METHOD: Measure , Visual
| note | 03aa42ab-6d08-4d01-8a55-7651c30cfe98 | FREQUENCY: Where applicable, each pile
| note | 1edf2590-9c85-4cbf-b98c-e8c68d40edfc | CATEGORY: IP
| note | 62a34320-d0a3-4d77-b60b-a85445fdb713 | RESPONSIBILITY: SE/PE/SPE
| note | e1861c84-fd59-4697-b824-11ffb443275f | VERIFYING DOCUMENTS: This ITP
| textbox | 32c172e0-6afd-4cdc-a085-a6ef0a628290 | Date Completed:
| checkpoint |  | 6.2 Compressive Strength Test Results
| note | 1b2b8462-75a9-4952-9b6b-bdc1661cd2d9 | REFERENCE: IFC Drawings
| note | b85dfcd8-c70f-4df0-bc88-1e6056639bfa | Table 610.05.051
| note | e88cd26d-be66-42e8-93b8-b63ddaeb8613 | 610.16 (g)
| note | a4da2ec9-1df1-4567-864d-eacce977b658 | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
| note | 92af7c64-4198-4a8a-9740-dbd869d3b675 | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
| note | 8766b66b-def5-47ae-9479-28d381051164 | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
| note | 63123cbe-e463-4dc4-bd74-f571b4417609 | Attach: Compressive Strength Test Results
| note | f6bf04b2-192b-47a2-880e-f5be5f0b8a5f | METHOD: Document Review
| note | c32d6857-a2c6-4b28-baaa-6a73d0f0a260 | FREQUENCY: Each cylinder
| note | 66a28743-30d4-4140-8749-af29d3b9a32b | CATEGORY: IP
| note | ce830a85-8732-47a1-9983-d4efe9446500 | RESPONSIBILITY: SE/PE/SPE
| note | a8cb0d88-0128-48f4-b4d6-4a5e764981ad | VERIFYING DOCUMENTS: This ITP
| textbox | 3407a05e-8505-40a5-b59e-134cfd555e7e | Date Completed:
| checkpoint |  | 6.3 Pile Integrity Testing
| note | 2b5716eb-10b1-43b0-afce-9afbbd70ebc7 | REFERENCE: 606.07 (a, d & e)
| note | f7774ea3-4cf9-496b-9416-321f73ed1534 | AS2159 Clause 8.8
| note | 9f3157b5-9cab-4b5f-8825-0c5183cc71d1 | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
| note | 680d2cbe-bd5a-4e03-930d-230cff1b3482 | Cross-sectional area = ≥95%
| note | 1ef6e127-5626-46ec-9436-67cbe9701c99 | If any test fails, all piles shall be tested.
| note | 5b366b54-22de-4b14-ab7e-3bac53bd7ede | Attach: Pile Integrity Test Report
| note | b07aebc5-42f3-4763-b435-47889475e299 | METHOD: Document Review
| note | bd68c6c2-e6ed-4f4a-ba3d-2e94b2f775fe | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
| note | f1255442-82b4-4785-a7d7-b084d98e3d19 | CATEGORY: IP
| note | 88e3b8a3-264d-4d44-abda-7ff551172f96 | RESPONSIBILITY: Testing Consultant SE/PE/SPE
| note | 11b5810f-330f-4c46-b400-04fac8825fb2 | VERIFYING DOCUMENTS: This ITP
| textbox | 517b7c4c-c177-4b56-b093-15a5c6f373b8 | Date Completed:
| checkpoint |  | 6.4 Static Load Testing
| note | fc3971ba-6cab-4faa-b833-7c55583fbfb2 | REFERENCE: IFC Drawings
| note | 9057c971-858d-47d4-9b2b-e45d7ef4bbbb | 606.07 (b, d & e)
| note | e9a3a309-872c-4b40-9f7f-e449f1b00412 | AS2159 Clause 8.4
| note | 68ab0768-c903-4002-bd95-d5f1a56409aa | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
| note | 1e3346d4-7bf0-437e-a8c5-b99ed4c8de04 | i. Displacement vs Time Graph = linear or decreasing rate of creep
| note | f9c4e160-fcd5-4a2b-9b92-bd7451bb264c | ii. Creep rate = <2mm / log cycle of time at the test load
| note | a31e7e10-8a02-4ee4-a0d8-33421808eed9 | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
| note | 06370530-41a9-48bd-9b4f-5a46ad472a75 | Attach: Static Load Test Report
| note | a8700a9c-d3b1-4ec7-b8f0-166e7a2d950f | METHOD: Document Review
| note | 90159633-9f89-4fe6-abae-e254e4897190 | FREQUENCY: Where applicable, as shown on the IFC Drawings
| note | fa7f813c-3ecc-4dd1-b1f3-68f37508b964 | CATEGORY: IP
| note | 3a6ccc86-918d-4d2f-b6d7-80b934d4c09f | RESPONSIBILITY: Testing Consultant , SE/PE/SPE
| note | f62efad8-047a-4e6b-bd98-a4d6e4e6be26 | VERIFYING DOCUMENTS: This ITP
| textbox | bc1d967d-39f2-45bd-87bb-f211d67574d4 | Date Completed:
| checkpoint |  | 6.5 Dynamic Pile Testing
| note | 515170de-6a48-40fc-ac1a-beb4cb85b686 | REFERENCE: 606.07 (c, d & e)
| note | 83f9b8cd-df5d-4d8d-9502-9a5c3093fee7 | AS2159 Clause 8.7
| note | 67aff411-9aa8-4ddd-ac90-e18a8687e8a4 | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
| note | 52502f4c-c1fa-4c23-870b-a61a34df1f38 | Measured Ultimate capacity = ≥ values on IFC drawings
| note | 0322b52f-a1de-4b35-92f3-18cd5405e30d | Attach: Dynamic Pile Test Report
| note | 36f39a3d-522d-4eac-a126-6774e2dbe346 | METHOD: Document Review
| note | 33f27b14-5a63-4746-9c92-b549728c5939 | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
| note | 6496f4b9-93b3-4601-bf62-503e9968963e | CATEGORY: IP
| note | 6ba47f91-e945-4638-91ec-b046320da02f | RESPONSIBILITY: Testing Consultant SE/PE/SPE
| note | d885ad10-4071-4f4b-8f1f-15a069e5eec9 | VERIFYING DOCUMENTS: This ITP
| textbox | 8a21dd6f-c312-46d8-91d1-245f98b247b3 | Date Completed:
| checkpoint |  | 6.6 As-built Survey
| note | 57847950-41ba-4a10-8b6b-50001d9aba83 | REFERENCE: IFC Drawings
| note | f03c990a-95b5-4f9e-9231-128a41c7533d | 606.08 (a - c)
| note | 31e26405-7a1d-4a44-aec4-0ecf49b1797a | AS2159 Clause 7.2.2
| note | 7dbc8cd1-5335-4a03-b427-42cf758fcb3c | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
| note | e952d03c-592c-41cc-be4e-727724cd7b29 | i. Pile head plan location = ±75mm
| note | 4c95a758-bd5a-481f-b437-c5b64f2458f7 | ii. Variance from vertical or rake = 1:100
| note | 7b728822-9919-4bfa-84fc-61056d40912a | iii. Irregularities in straightness = 1:100
| note | 4177af16-05de-48e4-9cf2-f3ea01ef6777 | iv. RL = ±25mm
| note | feffa8a8-ad33-4998-b82c-b373556c6577 | Attach: Survey As-builts / Survey Report
| note | 74b5c54d-c03c-46c3-95d7-7fbcaf580d44 | METHOD: Document Review
| note | f55191e6-6609-49c0-898b-5976903ed2af | FREQUENCY: Each pile
| note | 81b08ccf-c622-44f0-b630-b8faa5824d77 | CATEGORY: IP
| note | 053839df-dea7-489d-83ee-a6014b3b1102 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 3b377502-ce42-4400-b340-128ce5b0f358 | VERIFYING DOCUMENTS: This ITP
| textbox | d245a07d-d913-471a-a34f-7be9cf5f4ffc | Date Completed:
| checkpoint |  | 6.7 Non-conformance Report (NCR) Closure
| note | 00f1c29c-2691-45a8-b9b3-f7b10df49f2f | REFERENCE: MRPA Quality Management Plan
| note | 21efda6e-ef7b-4a2a-8d45-08cd55b159af | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | ae870be8-0793-4a97-9a8b-31a103e72cc6 | METHOD: Document Review
| note | 54850229-8412-4f9a-aff4-778d0ff54919 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | a2e7d5ff-81c8-4f0d-aa21-22ecfb87f66d | CATEGORY: HP*
| note | 40e718f0-2a08-4e2c-8063-6e1c6227ed12 | RESPONSIBILITY: SE/PE/SPE
| note | cf5821f3-063f-4208-88b6-29a17e79b269 | VERIFYING DOCUMENTS: This ITP
| textbox | 58832145-468a-4c62-ab8b-f934237ec0ee | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 05f5693c-d1c4-49f4-8ac3-5513cd6da6ba | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | d97eea69-6a6c-4b00-8655-5e5a3d2510a7 | Name:
| textbox | bf4f1b3d-8be7-4d6b-afe2-6bd40a65297c | Position:
| textbox | 01af0182-a438-4f50-877f-71759b91605f | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Sheet Piling (Supply & Installation) Rev 0 | itp | ITP-STR-Sheet Piling (Supply & Installation) Rev 0 | 8e09d047-6bab-4e0c-b99a-c49ef0a8e5ca
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 89eb6a17-06d4-4659-bf85-988a7a4886a2 | Document Title: ITP-STR-Sheet Piling (Supply & Installation)
| note | c8d40034-3bd4-43d5-9312-174694bdea02 | ITP Description: Sheet Piling (Supply & Installation)
| note | 5fa027a0-1f78-49aa-8737-9c8c237fb75d | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | ea1db1e3-f531-4fbd-a749-1df8e69455b2 | Discipline (e.g. CIV/STR/RAIL): STR
| note | b40e9287-eb3c-4bdf-ac0d-c7ddbed93b7a | Revision Number: 0
| note | e322b9cb-18a6-45a1-865e-45748003044d | Revision Date: 08/02/21
| note | 21181af9-b8dc-4230-aded-cc36612b198b | ITP created by: Mike Freeman
| note | d18638bb-fc5b-433e-bfd0-82ea441f2c56 | 1.1 VicRoads Section 640 October 2013
| section |  | Preliminaries
| checkpoint |  | 2.1 Certificate of Compliance
| note | e350e8ed-0614-47ca-8786-9a45c0b8a265 | REFERENCE: 640.03
| note | f38c4765-d390-43d8-95fa-ca19d0a6d46e | ACCEPTANCE CRITERIA: Provide a certificate of compliance from the sheet piling manufacturer confirming that the sheet piles comply with specification 640, inclusive of the interlock seals where applicable.
| textbox | f7cb7e95-dfd1-41f5-8f23-f18d7f2f8f78 | Enter: Teambinder Correspondence Approval number
| note | 7f55d996-784b-4d71-82c9-0dd4d73610ee | METHOD: Document Review
| note | bba51025-ea78-4b66-a402-604856617d60 | FREQUENCY: Once, for each sheet pile manufacturer, prior to commencement of works
| note | dc6c6e41-94b7-4e64-afbe-c71ee382ee7a | CATEGORY: HP
| note | 855bebf2-3e66-401f-b403-182d9417fa2b | RESPONSIBILITY: Nominated Authority
| note | a722e1ea-dbc8-4faf-bbbf-ec3dd16a4c39 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 553415ec-538c-40ab-a981-f439fa9e7f20 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Driving Guide, Threader & Driving System
| note | 6185e8a1-10e7-4ce4-9993-bfc724efeefe | REFERENCE: 640.04 (c) & (d)
| note | 3a67d319-dd16-44da-aec7-8b2b6de9aa1d | ACCEPTANCE CRITERIA: Details of the proposed driving guide, sheet pile threader, driving system, installation calculations and helmet and cushion information (where applicable), to be submitted for review to the Nominated Authority.
| textbox | ab4f5869-3740-46ee-b8d7-336e2536bb00 | Enter: Teambinder Correspondence Approval number
| note | 57cc4521-73d3-493d-87a9-86cc536d8872 | METHOD: Document Review
| note | ec49dcb5-e8cf-496c-8b06-7c3e1e979fa3 | FREQUENCY: Once, for each different piece of equipment or system to be utilised, 14 days prior to commencement of works
| note | e90a6750-7a46-4f6b-a735-d69bb68e767b | CATEGORY: WP
| note | 0ad7572d-4392-4b3c-8a5e-11481dbaf03b | RESPONSIBILITY: Nominated Authority
| note | 98929fbc-4130-4796-99a2-62a6d385797b | VERIFYING DOCUMENTS: This ITP
| textbox | d3fb2f68-ad1e-4b85-b726-39ccf5befe43 | Date Completed:
| checkpoint |  | 2.3 Welding Specifications & Qualifications
| note | f9a0109e-5a82-443e-9512-00618452b9a7 | REFERENCE: 640.04 (f)
| note | 2421e4a9-ce9f-4619-910a-103a6e3bd625 | ACCEPTANCE CRITERIA: Where applicable, shear stud welding or welded splices and connections of the sheet piling shall not commence until the welding specification & qualifications have been submitted for review to the Nominated Authority.
| textbox | a04f41cc-2e04-4e10-8431-3280c4495793 | Enter: Teambinder Correspondence Approval number
| note | c7d9b787-5331-4d9b-a250-e81d6a610e31 | METHOD: Document Review
| note | 02e01e1c-3e49-425c-b4e4-21d3cc4ee0a1 | FREQUENCY: Where applicable, once, prior to welding
| note | cb9318e2-f823-4cc9-adb1-b0f55dbc1ee5 | CATEGORY: HP
| note | 01d0c947-cdcc-423c-a170-8a792d845f96 | RESPONSIBILITY: Nominated Authority
| note | d664d498-d55c-4ffe-aef6-36f5951a7b53 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 22b5290f-11c4-4720-9ef9-dd5b1c9c6acd | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | ad3fd172-a88b-479d-89e0-26eeb3d71ab5 | REFERENCE: IFC Drawings
| note | 19d57a63-8485-4656-9406-316ac2c0f6e9 | 640.04 (g) (i)
| note | b2b1185c-28a0-4143-a208-73037a52cc64 | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±50mm at the sheet pile head.
| note | bbda1e32-fb8b-497b-878b-e2ba72d12f4e | METHOD: Measure , Visual
| note | fa98e288-8b9d-4a2e-9d6a-0c7a2a566137 | FREQUENCY: Each element
| note | 6b900d2c-ac89-4209-8887-d8acde5a8005 | CATEGORY: IP
| note | 631217df-0772-4fc5-b62f-5bb9328e4859 | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | d7fd9078-052a-4d9b-bbf1-130de2db0da3 | VERIFYING DOCUMENTS: This ITP
| textbox | f91e95be-c19b-4db7-95fc-04c83d2da9a4 | Date Completed:
| checkpoint |  | 3.2 Marking Depth Increments
| note | 48fad793-2c87-46c9-8ea8-eacac4f46310 | REFERENCE: 640.04 (b)
| note | 4f26d0b9-647b-42e6-9c88-12629e507a5c | ACCEPTANCE CRITERIA: Sheet piles shall be clearly marked at 500mm intervals from the toe upwards to indicate embedment.
| note | 130412f7-e074-494e-a798-0ea0f495d9e2 | METHOD: Measure , Visual
| note | fa4aae8d-c214-4c1e-b5d2-0d03f02d2e4e | FREQUENCY: Each element
| note | 0e21e7dc-81b6-4883-b3e6-b82617c3075c | CATEGORY: IP
| note | 26d0e4d2-9444-4f4b-8262-0cb873e17b69 | RESPONSIBILITY: SE/PE/SPE
| note | f9b22216-c2fc-4875-9363-9590ac8ee11d | VERIFYING DOCUMENTS: This ITP
| textbox | 2761a6a5-b48a-40b0-98f7-f40b47878a75 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 4.1 Driving Operations
| note | 2899e630-c394-4314-80bc-c705ea4fd42f | REFERENCE: 640.04 (e)
| note | 391ea8f1-338a-481b-acd9-b6b20f19ad21 | ACCEPTANCE CRITERIA: After commencing driving, each pile shall be checked periodically for verticality, interlocking and to ensure that it is free from damage at least once prior to reaching full embedment.
| note | b41dac39-1709-4af8-a599-3fe6de997e85 | Sheet piles shall be driven to the levels shown on the drawings and care taken not to disturb adjacent piles.
| note | 670e5a96-892c-4c96-9b76-de74f1189f60 | METHOD: Measure , Visual
| note | 36da00e8-19f7-4862-b565-47126e076ccf | FREQUENCY: Each element
| note | 7a8dbd09-6de3-4fd4-898d-cf5d590dc8bb | CATEGORY: HP
| note | 8e709fb7-d400-4c7c-9906-3389ff918602 | RESPONSIBILITY: Nominated Authority
| note | 9d4a03ba-5f7d-4cf9-a93d-ac6aa22b401d | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c32df479-ab47-425a-96da-8cf8e77090bc | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.2 Trimming of Sheet Piles
| note | 850e256b-5451-4460-966e-97e79a0e7d4f | REFERENCE: 640.04 (f)
| note | 84407555-79b1-4ef9-85ad-7c8c744effb4 | 640.03
| note | 2c68c2b9-bc71-45f3-a27c-6e2029ab4979 | ACCEPTANCE CRITERIA: Where the required depth cannot be achieved, subject to approval, the sheet pile shall be cut off by suitable means such as flame or saw cutting, leaving the end square, straight and free from burrs or imperfections (if not encased in concrete).
| note | df1a222a-4de4-45eb-b8e0-1b5d2c7c3949 | METHOD: Measure , Visual
| note | 3c1d28ba-3291-444d-bba4-5774d30a9a8b | FREQUENCY: Where applicable, each element
| note | 0c6027a8-fcb9-40c7-a5d8-7ba1c1b967ca | CATEGORY: IP
| note | 934b9db5-4788-4fdc-8272-4ee32f68ed3b | RESPONSIBILITY: SE/PE/SPE
| note | d6abe02b-aac8-4355-bbd8-0a04ca2a13f7 | VERIFYING DOCUMENTS: This ITP
| textbox | 89b5f9a7-e38a-4906-97d9-c7d401c122cc | Date Completed:
| checkpoint |  | 4.3 Extension of Sheet Piles
| note | edf8eb5f-e646-4d05-99a8-0e02b10fb4d4 | REFERENCE: 640.04 (f)
| note | 50e71e0d-d3b6-43d4-9bf3-5894c2437dcd | ACCEPTANCE CRITERIA: Where applicable, extending the sheet pile length to achieve the required cut-off RL, shall be conducted by full strength butt welds as per the approved procedures.
| note | c3c88b6d-00af-4970-a4ed-ad3204125821 | METHOD: Measure , Visual
| note | ef21641d-fc6f-42f3-8497-ddc253c9c827 | FREQUENCY: Where applicable, each element
| note | 2839cb4f-6b55-4524-a1bd-859e757d34e0 | CATEGORY: IP
| note | f11355b6-034a-49c0-b631-5bdfd8fdf2be | RESPONSIBILITY: SE/PE/SPE
| note | 9146bb91-0058-4163-adc9-e61cf1441a62 | VERIFYING DOCUMENTS: This ITP
| textbox | 4d5dbcd7-27d2-44a7-bc13-857943454483 | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 5.1 Weep Holes
| note | d5d44097-6e28-48a2-8589-74c53cf249bd | REFERENCE: IFC Drawings
| note | cd2cf00b-4984-4ba7-a4ff-0a25a10bf32b | 640.06 (d)
| note | 46dff962-07ea-40a6-84be-d84d5a22ab6c | ACCEPTANCE CRITERIA: Where applicable, drill 15mmØ weep holes through the centre of the exposed sections of sheet piles at a minimum of 1m x 1m spacing.
| note | 5d5a31db-f654-4d1b-9bde-31fd9051018c | METHOD: Measure , Visual
| note | 4682d904-0f03-49c9-a861-2051503b489b | FREQUENCY: Where applicable, each element
| note | ea0c6f2a-b2e0-4097-a6ab-ce28c2173d8f | CATEGORY: IP
| note | 71bfb1df-d0ea-4738-ad59-4eb5c0edbf32 | RESPONSIBILITY: SE/PE/SPE
| note | d4c7c68e-a214-4cd9-b03a-d478791abd40 | VERIFYING DOCUMENTS: This ITP
| textbox | 5447e9ff-351b-473f-875d-c7e4261b7f45 | Date Completed:
| checkpoint |  | 5.2 Repair of Damage
| note | 403735e1-8972-4f4c-a047-c406d0f903c2 | REFERENCE: 640.04 (a)
| note | a8b05e9a-6615-4f46-968f-cb577408c3c2 | ACCEPTANCE CRITERIA: Where applicable, any damage to the sheet piles shall be repaired to the satisfaction of the Nominated Authority.
| note | a8eb41d4-3f7d-4668-8d11-cebc6d3ed514 | Any repairs that do not meet this requirement shall be replaced.
| note | 0c3b1b19-9103-47ad-a70f-7c2862f59161 | METHOD: Visual
| note | 37ca2df4-c17c-4613-8618-47e4eb09b50e | FREQUENCY: Where applicable, any damage shall be repaired by suitable means
| note | 2621ded0-f748-4182-ba95-49650d071dec | CATEGORY: IP
| note | 03092301-f2b2-41c5-9951-042322295e59 | RESPONSIBILITY: SE/PE/SPE
| note | b27e2ed1-9d32-4e93-8d57-282cb7e1b005 | VERIFYING DOCUMENTS: This ITP
| textbox | 0cb97dba-17a8-4a9d-a28c-221e1c33da75 | Date Completed:
| checkpoint |  | 5.3 As-built Survey
| note | 4f2c0c7f-1767-433c-8c2e-7ced847d88cd | REFERENCE: IFC Drawings
| note | cd2a7e6f-225d-4832-9127-09b1eef6c30a | 640.04 (g) (i) & (ii)
| note | 04b37b1a-c286-4750-ab06-c631fa5bf337 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that the installed elements comply with the following:
| note | 29a542f2-52f2-4b2e-9fd4-2297beff29c8 | i. Deviation of plan location at pile head = ±50mm
| note | 057d36ab-80c8-4a2d-8b14-ea284def498c | ii. Deviation from vertical = 5mm/m of sheet pile length
| note | d483ca8f-ab07-42b5-b63b-e6bbac8836ee | Attach: Survey As-builts / Survey Report
| note | 98cd9a01-671f-485c-b6b9-d1f3bc01ca3b | METHOD: Document Review
| note | 0763d3cf-ee02-4e92-9dc8-43596c73511f | FREQUENCY: Each element
| note | 0d79b74b-6c33-4c95-b478-754a3eae632a | CATEGORY: IP
| note | ce415521-a347-4576-931d-f133b7677502 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 61d51072-3dad-4ac9-9adc-0a30f8095c9c | VERIFYING DOCUMENTS: This ITP
| textbox | 58886459-0aa7-48dd-b7d7-82fafc8ee8ff | Date Completed:
| checkpoint |  | 5.4 Non-conformance Report (NCR) Closure
| note | f35da236-848d-4cf1-bbf1-a1a0f327422c | REFERENCE: MRPA Quality Management Plan
| note | 4be9dffb-82a8-4b2c-9a5c-740e53d86432 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | a71eea01-d32a-4872-ad28-c797f07a674b | METHOD: Document Review
| note | 13c678d6-3a4e-4da2-aedb-ce7e63777fc1 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 9eb8dd6a-3edf-49dd-a4b0-b75fd4d75948 | CATEGORY: HP*
| note | 495c0cff-1e26-404b-9c9d-9ae0fc4f6821 | RESPONSIBILITY: SE/PE/SPE
| note | 60ef4a46-d7db-4051-86c5-6d564b29591f | VERIFYING DOCUMENTS: This ITP
| textbox | 21d213f2-9d37-49ea-a124-02baa54ef5d4 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | e1f3e573-315e-414e-9296-98c6c20687b7 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 2a6f5c53-526a-4484-9ea2-57db1679fb6f | Name:
| textbox | ed8576e4-ddea-409f-9f8e-42aa061182ce | Position:
| textbox | f258b5a9-c68a-44f9-9b30-68759001b0c3 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-RAIL-Sleeper Replacement Rev 0 | itp | ITP-Rail-Sleeper Replacement Rev 0 | 8ef22fe7-2492-4c9f-bb08-d7be8e68fe9d
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | f85afb82-2c77-48a3-80ad-1385df535475 | Document Title: ITP-Rail-Sleeper Replacement
| note | bf14dcf4-1770-46d5-b8b8-5a8b15e664b5 | ITP Description: Sleeper Replacement
| note | 4701075f-78e1-41bb-9bcc-cb27a515379c | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
| note | 683bef8f-8ed1-4eb7-8470-95d48dc75901 | Discipline (e.g. CIV/STR/RAIL): Rail
| note | 1eb4b477-ec59-434d-ad29-506c85b57a1b | Revision Number: 0
| note | 5b780ed2-7adb-46e4-ac12-ea958880fc0f | Revision Date: 30/07/2020
| note | 77ad4e3c-5f55-49a8-902c-46057b3d6c35 | ITP created by: Mathew Holm
| note | 5051adcf-2e3a-46a1-ab58-761b55823e79 | ITP approved for use by: Romualdo Magpantay
| note | 9ea629ae-b9fe-4b3a-a94f-705c56478b27 | 1.1 L2-TRK-SPE-003
| note | dbdefe78-851d-49cc-9148-c8cc045caf7b | 1.2 L2-TRK-SPE-004
| note | 7a00c3be-d6d6-45ec-8f5e-822fe09e1ecc | 1.3 L1-CHE-SPE-003
| note | 2c2e91c4-70f3-4142-ac26-8d1bad1d7021 | 1.4 MTSP 030100-01
| note | babac4e2-a185-47bc-84a2-5756de0cc0a7 | 1.5 L1-CHE-SPE-316
| section |  | Preliminaries
| checkpoint |  | 2.1 Obtain and submit Material Certificate of Compliance for sleepers & ballast
| note | dfdb0fe4-0ad9-415d-bc32-a50897f41e09 | REFERENCE: L2-TRK-SPE-003
| note | 6ed5a74c-a39d-49d5-95d7-8071805ff900 | Material Design Drawing
| note | aed3c449-e876-4d7e-b089-2445fd4f72c3 | L1-CHE-SPE-316 9.4.6
| note | 1cec4e69-3d5e-4332-8e0b-a97e167a33e3 | L1-CHE-SPE-064 Ballast Supply Specification
| note | 203c2256-b442-4dc4-9031-1c28308d88e4 | AS 2758.7
| note | 024637f3-80ab-4a5a-aab1-44aebc86429a | ---------------------------------
| note | c110b071-8202-4a0d-a3ce-fcfdffc312a4 | ACCEPTANCE CRITERIA: Verify Sleepers to be in accordance with MTM standard.
| note | bb791ae4-2c55-44d4-aad1-fd558e84e322 | Sleepers with defects not be to be used for tracK construction(free from any damage).
| note | fc2f72d9-675b-4b01-904b-191484462c46 | Concrete sleepers supplied shall conform to the testing requirements as specified in AS
| note | 88217b20-3c90-4df3-a42f-20c84933ee22 | 1085.14 Prestressed Concrete Sleepers.
| note | 9542fef2-5fc8-4e62-9b98-bbf8acd7a816 | Verify supply ballast material (if applicable)
| note | 596849e8-b9d0-495a-9a8f-96baef84f1c5 | Attatch: Photo Sleeper & Ballast
| note | 7847d7ce-6964-421f-a28b-26f3efd2fcd3 | ---------------------------------
| note | 64b4dc9a-ffa4-4963-8df9-aaad1a63a8e6 | METHOD: Review
| note | 06dc142b-1959-4fc9-a9c3-2c632631b859 | ---------------------------------
| note | e3e8bd2f-d432-4ccb-a5d9-6023435b769a | FREQUENCY: Once
| note | 7b9ed2ac-2a2d-4151-ab30-e95f2e1f1e46 | ---------------------------------
| note | 28f06742-e235-479b-a5b5-df3e1ed0bdc2 | CATEGORY: HP
| note | 2ec987b6-db1f-4b91-be82-e5913de89283 | ---------------------------------
| note | 014db9d7-687c-46e4-be48-f4812982e0ce | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
| note | 17cfa5bb-4ba9-41d0-acfd-257827355a5f | ---------------------------------
| note | 3bda576a-7162-4293-ac0a-09b35949b7fb | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c4411409-2591-40ce-8e4a-ccbf8bc5dc41 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Obtain and submit Material Certificate of Compliance of new (Rail Jewellery) fastening assemblies
| note | 594b5d86-9a8e-46e3-9553-1cc0e4c82bdd | REFERENCE: L2-TRK-SPE-004
| note | 688162d0-79c0-483c-b832-024bcb1c338b | IFC Drawing
| note | 8a3c6e1e-4fe1-4253-94e7-8e6b30279be1 | ---------------------------------
| note | 31d9b01f-4940-4304-9e79-c3a0d460b994 | ACCEPTANCE CRITERIA: Free from damage and supplied in accordance with MTM specification
| note | e130c636-31a6-4287-8f97-fa0ce04ff377 | All fastening assemblies may be subject to inspection by MTM, or their nominated
| note | c97ede34-de00-4587-aaca-4f6794278a8f | representatives. This may be undertaken at the manufacturers, suppliers, and/or
| note | 3b800b9e-753c-41d3-8d27-b0b5448be328 | sub-contractor’s works facility or point of delivery to ensure conformity with this
| note | 4cdb3bee-482f-4a89-a19f-dd1eba02c73d | Attatch: Photo Fastening assembly(Rail Jewellery)
| note | 8fc9ec93-264d-4fa9-9157-739df5775e12 | ---------------------------------
| note | 50fcd5d3-17ec-4371-b6e3-4254c11d0816 | METHOD: Review
| note | e9d1a335-1e28-4b34-9a3c-a798448dc62b | ---------------------------------
| note | c5bdc7c5-6370-401e-af8f-522654cf594d | FREQUENCY: Once
| note | ea6a1c06-6ad5-4b98-80eb-3972ec192779 | ---------------------------------
| note | 383a41fd-8b0a-4d40-bce2-e73ce6a11096 | CATEGORY: HP
| note | c75d8bf6-36ce-42fd-be01-4f770b2977a6 | ---------------------------------
| note | e4af9669-eb56-4fa4-8c3b-278f5d41784c | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
| note | 99f0f000-525c-45c7-bd96-eac04ff21365 | ---------------------------------
| note | 806b097a-161a-4a40-b7b0-4160c2618663 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 242ef9bf-3415-48cd-848a-9a3a0684a93f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Inspect supplied items upon delivery
| note | f4a04fff-c2e3-40c6-b5d7-a25fe54b0799 | REFERENCE: IFC Drawing
| note | e4c5eb27-4fa3-49e4-b73e-c5267350f58c | ---------------------------------
| note | 05dea1d1-b685-453d-848e-1f1a51718be8 | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
| note | 8e0af55b-1917-4cd0-898f-83986ecde787 | ---------------------------------
| note | 754ab233-a6f4-4fef-beef-e084c49c46df | METHOD: Visual Dimensional
| note | 6ef33f28-3aab-4035-a3fa-c545b09eb582 | ---------------------------------
| note | de1b3e06-37aa-4aa9-9a48-4e14f786c6d3 | FREQUENCY: Per delivery
| note | afb95445-3196-4646-873b-22b860263fa1 | ---------------------------------
| note | 8afbcc3a-46de-4d16-b3dd-e64e26d040e7 | CATEGORY: IP
| note | 7f2a0f93-d632-41cb-aaf0-b3faccfdbf87 | ---------------------------------
| note | b0abf8c7-dfb3-45d5-aeda-3d6d1c6a5978 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 0b726337-c01a-4ef6-8552-1a186591ff0d | ---------------------------------
| note | cb9b19e3-5ab8-41d7-b73b-9799bb603584 | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | 7c6aa2ed-b27d-475c-bbb3-1e85c3d5ad39 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.1 Removal of Existing Sleeper(s)
| note | 9201b5b9-cd13-42f5-98dd-dbc28a97d9bc | REFERENCE: IFC Drawing
| note | d2db3333-e0d9-4d49-8321-224f7c7c89e7 | ---------------------------------
| note | 1e88e527-f1ab-440d-852b-3f9134c3e902 | ACCEPTANCE CRITERIA: All Jewellery is removed from rail/sleeper by use of approved rail tool
| note | fdb6e221-952d-474e-a104-428945ba4066 | Machine operaotr performs "side removal" technique to remove from track
| note | c8d506de-0aa5-48fd-91b8-4e807bc1ffbe | No contact with adjacent sleepers
| note | 4944eb54-8e46-48c2-be4e-9033d390294e | ---------------------------------
| note | 5a0ef7f7-82e0-42c0-bdc9-5f5c6917859e | METHOD: Test Visual
| note | ff77780b-1bb7-4609-8c6c-77716781c678 | ---------------------------------
| note | 77cf53dd-f0ed-4fde-86d3-6692d658622a | FREQUENCY: Per lot
| note | fdd1ee54-953c-40a5-aeb9-5df158286340 | ---------------------------------
| note | 33a099f3-0b62-4db9-9914-fb12795ca807 | CATEGORY: IP
| note | 54b1bde0-aae2-4f1a-a58d-c50f182d3f06 | ---------------------------------
| note | c8a21175-74d3-44f2-85b3-6a57f942de61 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | f4f63edf-7bfb-442c-8f07-df1703ddda04 | ---------------------------------
| note | c5d2f487-8331-4e62-b6dd-9a4e7d2a6e25 | VERIFYING DOCUMENTS: This ITP
| textbox | 1b6454c5-f066-48ad-ae32-bdafc5dd6f46 | Date Completed:
| checkpoint |  | 3.2 Ensure existing formation is suitable for new sleeper laying(if required)
| note | 30f2791b-2e73-4f50-bacf-533ffe1d33d7 | REFERENCE: L1-CHE-SPE-178
| note | 3f6462bd-efcf-47c0-8f28-a56e739c8880 | ---------------------------------
| note | b2d1550d-10cb-4009-a461-de18cadac0c0 | ACCEPTANCE CRITERIA: Compacted, even fall, no ponding and certer binding with sufficient width
| note | e70ef7da-332a-4304-bc8a-7673c8ac44ea | ---------------------------------
| note | a87af164-f68d-48cb-a443-bbbf96a7ed47 | METHOD: Visual
| note | 90241609-22dc-4cbe-8a56-5b07ab413f8a | ---------------------------------
| note | 0f5884f8-7277-4aaa-b55d-e2e441ea629e | FREQUENCY: Per lot
| note | e65fbd23-edfb-4290-adb0-ec1e69e69ae6 | ---------------------------------
| note | af17f285-5303-4f08-b114-e3f6760cc1c9 | CATEGORY: IP
| note | e78d3818-3ab1-4638-b066-16062da00de3 | ---------------------------------
| note | 5cb5e393-8d4d-4094-8449-b7bc296c2490 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 988953c8-ef33-477f-8ea2-ee70c91f4593 | ---------------------------------
| note | 5611a745-d1b5-43b5-bc3d-04c817b0d448 | VERIFYING DOCUMENTS: This ITP
| textbox | f23f9a08-48c9-4a67-993b-36954d324d65 | Date Completed:
| checkpoint |  | 3.3 Off-set centerline peg established to control alignment of track construction(if required)
| note | c0b023ca-47e8-42ea-b9b3-16d3f87d9d70 | REFERENCE: L1-CHE-SPE-003
| note | fcb1d201-1a9a-4ef5-a179-06d273f7c7fe | ---------------------------------
| note | 4a39393f-fae8-40ef-a49d-d60a50038598 | ACCEPTANCE CRITERIA: chainage reference for each peg
| note | bda9baae-1984-46a3-8a23-47f1f7b7fe2b | 20m interval on tangent track
| note | 42886ecb-65e2-42bf-8a0e-4375c5856b6a | 10m intervas on vertical & horizontal curves
| note | 79bb37fa-472c-4ead-a9ca-08d08c712b1a | ---------------------------------
| note | e253b99b-aaa3-4a51-a812-e4e0fc863ad2 | METHOD: Dimensional Survey
| note | 7be73f8d-cfea-4532-a06e-0d8362d84a13 | ---------------------------------
| note | f777e04d-ee02-4268-82f9-f11a36024c8d | FREQUENCY: Per lot
| note | 10dd1dd3-97a6-4f2c-b9bf-54a81e2f7e01 | ---------------------------------
| note | 1c1f3a3c-ef7e-46d8-94eb-42023ebc3d2f | CATEGORY: IP
| note | 02a363ca-ba93-49ab-80ce-afa73aa9d85d | ---------------------------------
| note | b517214c-7d5f-4d67-883d-62b910c24f40 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | ca41d757-eb00-4ae4-92eb-618a0cfa0340 | ---------------------------------
| note | c0e090d7-696e-4aca-bd93-c68ed9a1eb6f | VERIFYING DOCUMENTS: This ITP
| textbox | 61cfcce4-7e87-434c-9d63-c73cd30ea1ba | Date Completed:
| checkpoint |  | 3.4 Installation and verification of new concrete sleepers laid at correct spacing,square & pads are installed
| note | d573f0c7-a46b-4062-a830-b8299138811a | REFERENCE: L1-CHE-SPE-003
| note | f8e384af-1b0e-4bb9-b0d9-9e41c5ae1a49 | ---------------------------------
| note | df42b79c-8d9b-4975-94e0-5c5abc3c56ca | ACCEPTANCE CRITERIA: Machine operator performs "side insertion" technique to get sleeper into postion
| note | 04a387e5-a256-4c8b-9090-9855b8dd1ed1 | Sleeper pads present
| note | c93566d1-028c-444d-ad1a-6abe0c6bf4b7 | Rail insulation biscuits installed in lugs
| note | d872d57d-4add-4d49-9f81-1a729476c857 | Rail E-Clips installed by use of approved rail tool
| note | f38bb454-5ef2-4271-8e11-f3b0367b6d33 | Sleeper spacing installed at Plain Line Track: standard of 685mm ± 25mm
| note | 2a665612-6d4e-48f5-b439-8c37f1578d03 | ---------------------------------
| note | 3000874a-85e1-4003-a23b-dfa34a042105 | METHOD: Measure Visual
| note | 408badfa-d89b-48a6-bdb4-236a02ba7795 | ---------------------------------
| note | 0fcbaa7e-766b-49b7-9293-12f8ae40b185 | FREQUENCY: Per lot
| note | 0d7eda8d-182f-4a0c-8ebd-31b47e08cd31 | ---------------------------------
| note | 9b87ef97-6a5a-4d2c-a799-8560937b42c8 | CATEGORY: IP
| note | 4aa2717f-0421-4e8b-ae15-1697a4a36685 | ---------------------------------
| note | d809d2c2-50fd-40e8-a62e-007a8be11d62 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | f37bd4e7-da29-42ca-9474-f4b0cb447844 | ---------------------------------
| note | c5acddb0-2ba9-4cdc-bd01-60efd8a97e25 | VERIFYING DOCUMENTS: This ITP
| textbox | d648892c-da68-4a89-adb7-5aeb51260aeb | Date Completed:
| checkpoint |  | 3.5 Installation and verification of all fastening applied in accordance with the manufacturers instruction. Ensure that the Rail is 100% fully clipped up.
| note | c2735567-bfb8-464a-b3db-746839b5f126 | REFERENCE: As per specification
| note | bc3cdde7-cd92-420c-b885-f745b9137f8d | ---------------------------------
| note | 3b21cba1-1150-42ce-a0ec-bee654eaeb33 | ACCEPTANCE CRITERIA: Insulatora on field & guage side of each rail(if applicable)
| note | 928c4b83-8aa5-48c7-b1dd-0d20c55df4af | ---------------------------------
| note | 41e31387-36e8-46d6-bc62-f0cab0b7d4cd | METHOD: Visual Measure Doument Reivew
| note | 0af952e8-2bf8-43ab-aed3-cb8e2bb5e3c2 | ---------------------------------
| note | 23b9bcb9-bdbb-435a-b005-317e3cf7d230 | FREQUENCY: Per lot
| note | e558602d-1c01-4e09-9196-53bb7f6bf408 | ---------------------------------
| note | b1dfcf46-a80d-4aef-9319-7732c457a163 | CATEGORY: IP
| note | 8a370c58-ad35-4541-9b43-253eb046042f | ---------------------------------
| note | c13fb90f-6172-46e4-8f37-879ffb8d5e2b | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 264fb52f-8752-4e66-90a1-a29caaaef9ed | ---------------------------------
| note | 7897e06e-2f75-4995-b2a6-0181c3dc6535 | VERIFYING DOCUMENTS: This ITP
| textbox | 47e3a07c-47b6-4eb2-b791-e98f5ef36d21 | Date Completed:
| checkpoint |  | 3.6 Tamping /Boxing Works (Verify ballast profile complies with specification)
| note | 844c8e9b-ff4a-4ced-a8d8-2f779da4096a | REFERENCE: MTSP 030100-01
| note | ce0732a8-7296-4a74-a8f6-326e6237b138 | Appendix 1 Table
| note | 50821aed-f21e-4f3d-852b-f3345c5cba53 | MTST 000002-01
| note | 108fb67e-85fe-411f-b733-2106fcee6b0e | ---------------------------------
| note | 210414e9-a736-4b7d-b30c-7b3249069904 | ACCEPTANCE CRITERIA: Track Geometry
| note | 5d114891-b39f-4960-932d-1f23a0d98ef8 | Wide gauge < 12mm from design
| note | 9977514f-879d-4819-980e-0353bc479fb6 | Tight gauge <-8mm from design
| note | 2a04a52b-70b7-4b4f-9710-7b7db67a5ee5 | Cant <25mm from design
| note | fe3881b6-0247-4070-a8e8-259c6097a9f8 | Twist (3.5m) < 15mm from design
| note | dd2ca902-c076-4cc4-9a85-d78cfad3c0ff | Twist (10m) < 30mm from design
| note | 3306d1a6-7957-48db-a45f-7b9d53a08064 | Top <20mm from design
| note | 4b569b5a-6014-40ce-acf3-f3623d839552 | Line <18mm from design
| note | 5bd378b1-144c-4a54-992f-fc87d02130aa | Ballast shoulder 450mm wide 1:4 fall
| note | 68601537-39e8-42a2-9ba9-636bd157a867 | Top of sleeper free from ballast
| note | d48cd9f4-ded4-4954-94a9-5dd36338a557 | Attatch: Track Measurement Sheet
| note | d684af16-7ed5-4b6c-8ce7-4b86e5932e7d | ---------------------------------
| note | 66f30d2b-a4fd-46e1-a4bf-dd1adeeabc53 | METHOD: Measure Visual
| note | 61076292-9ffa-4e52-b749-b122acb7f590 | ---------------------------------
| note | cb17167a-c515-484f-96d5-c0a034072939 | FREQUENCY: Per lot
| note | 1c677a03-230f-4470-a2c3-dd707882da11 | ---------------------------------
| note | 3075dc9e-6e8c-4403-ad31-5064ad3e2ea3 | CATEGORY: IP
| note | e7ebd008-a978-4d52-af24-2c4a06a02dad | ---------------------------------
| note | 9f2af1f4-6af1-4ce7-8e61-ffc9d9235466 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 2f8ead7b-686a-48b7-8599-780c42e4c8cb | ---------------------------------
| note | 24bb0e93-5d92-42be-ae60-9be6ce5bcda2 | VERIFYING DOCUMENTS: This ITP
| textbox | 83e66edd-0927-4884-918f-9bd2e55cb57d | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.1 As-built Survey
| note | e71da790-0ba7-4227-b2c9-dff3dc76d443 | REFERENCE: IFC Drawings
| note | 95e5e61a-2abf-4a17-8d23-23029fd1e387 | L1-CHE-SPE-003 Section 11
| note | a56eb409-ff8e-4a38-8bb6-e153766af45d | ---------------------------------
| note | f120a1db-86bb-4ac3-a998-46715d78a772 | ACCEPTANCE CRITERIA: Survey activities undertaken to validate rectification works
| note | aa510acd-ea12-4383-b3b1-45dcd9ada316 | Attach: Surevy Report
| note | 951cf1e7-8358-4e6e-bfc7-b120488d7bf0 | ---------------------------------
| note | 638c0dc9-1921-46a2-93ab-391b811b8334 | METHOD: Document Review
| note | 99b046f0-3a43-41d8-a6e4-8f7dd75d8e17 | ---------------------------------
| note | de8d2954-b62c-4c09-b27f-c24aa61d3c9f | FREQUENCY: Per lot
| note | 0692f01f-b4ec-4b70-8201-6b3051148ce9 | ---------------------------------
| note | 135d7566-01a8-423b-a76d-5a205ae8771f | CATEGORY: IP
| note | 3568c95d-bd2a-46a3-a949-fd31484fdc70 | ---------------------------------
| note | 22ece7f3-0bf9-436a-82e9-b271ff8a157c | RESPONSIBILITY: Surveyor
| note | 591df421-12a6-4d1c-bd95-8d9280127f11 | ---------------------------------
| note | a793807b-c4db-4ca2-b53c-81ab5bd7855d | VERIFYING DOCUMENTS: This ITP
| textbox | 74b08283-debd-4666-b263-03bbaf8d1eb4 | Date Completed:
| checkpoint |  | 4.2 Track Certification
| note | be7e42d7-e1f5-4cbb-a37e-cc6f79dc024e | REFERENCE: MTMF020000-1 – Track Form A T
| note | 03500a0e-5fda-411d-a6b6-fc901500abff | MTMF020000-2 – Track Form B
| note | 847ac3e9-da7f-4bec-89de-5b658ca05b37 | ---------------------------------
| note | 22b312af-1abb-4a97-ab08-396447f4e1f2 | ACCEPTANCE CRITERIA: Attach : Track Geometry Conformance Certificate
| note | 5b8a1269-e2bd-494a-8bbf-5d39b16fa03f | Attatch: Track System and Component Conformance Certificate
| note | bbdafd9e-371d-470e-869d-09bf834b7507 | Attatch: Before/After Photo of worksite
| note | 62bd2c01-4b70-48e3-8f2e-786c9a88cadc | ---------------------------------
| note | 7eb137d1-048c-4c9f-87bd-c520e6e515bc | METHOD: Visual Measure Doument Reivew
| note | 6b74709b-af4b-4491-be80-a43933e9cabb | ---------------------------------
| note | 89b5721c-2cff-42d0-8e93-e72ecdac77b5 | FREQUENCY: Once when all occupation works complete
| note | 90a3587e-624f-4acb-ad72-666fa4229691 | ---------------------------------
| note | 273b692b-2444-426f-8b5f-74dd9c095ff5 | CATEGORY: HP
| note | 3831f3c6-b410-4f40-be3c-17bfa6376fec | ---------------------------------
| note | 8844fe01-231b-45f8-9e87-827dd6a87157 | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
| note | 1410197b-233b-4deb-a2cd-c6533367c3e9 | ---------------------------------
| note | c95f85cc-e852-4cb3-8221-b9e125d230f1 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 1a608cc2-b909-4e3d-999e-aa224ed29ca2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 69e91e5a-c2c5-4b01-a0b3-f948d138e42f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | ba185c2a-421c-4b02-a08d-f84b69cfc6b7 | Name:
| textbox | e6403de7-a7fd-4184-b95d-092fd671bdc6 | Position:
| textbox | 87fd2829-8428-4043-adee-8bd5357347ba | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Expansion Joints (Supply & Installation) Rev 0 | itp | ITP-STR-Expansion Joints (Supply & Installation) Rev 0 | 929f4132-7650-4129-9fd5-74ea74076aaf
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 8b254bee-1e2b-49eb-9f5d-0be3ab3ad04a | Document Title: ITP-STR-Expansion Joints (Supply & Installation)
| note | 5bb3a7da-c39c-48cc-84b2-d06cf978a412 | ITP Description: Expansion Joints (Supply & Installation)
| note | 5bd9ae11-a165-43db-abf0-3f38a2e57984 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 92d6be52-1f48-4e57-87a2-1c59d98da347 | Discipline (e.g. CIV/STR/RAIL: STR
| note | f8a9872a-c920-4a64-9a27-c78759d25cae | Revision Number: 0
| note | b7036f65-dcb4-4fd0-9627-1929a7a29b5f | Revision Date: 16/11/20
| note | b97c98d7-a339-4f53-b698-a5018e8e61c5 | ITP created by: Mike Freeman
| note | e79a63f9-0630-4e22-8d13-8d23ab191330 | ITP approved for use by: Mike Freeman
| note | 46836c3b-6682-41c1-98cc-30b8835c8bb6 | 1.1 VicRoads Section 660 January 2018
| section |  | Preliminaries
| checkpoint |  | 2.1 Expansion Joint Design
| note | e53e0264-114d-41c6-9d3e-4d1a95f948e7 | REFERENCE: IFC Drawings
| note | f104aece-7574-4cf3-86ae-1843542e3051 | 660.03
| note | 42884814-4a01-43d8-aefe-ccc7183f6e55 | ACCEPTANCE CRITERIA: The expansion joint system shall match the drawings.
| note | 7e49c84a-1ca2-4d0f-91cf-5d86391d94a6 | Where an alternative product is nominated, the following criteria shall be met and information submitted, (where applicable) and approved by the Designer (for Design & Construct) or the Nominated Authority (for Design only)
| note | dbce61ac-9d2a-4e23-a4a4-1a78aa0b984b | i. details of provisions for inspection, maintenance and replacement
| note | 8bd71616-fc0f-49a7-9c67-25a8eb3844eb | ii. anchorage system details
| note | de230b2f-4837-4707-91ed-32f0b10f30b4 | iii. geometry for casting block-out
| note | 61b457e5-9e92-4ae8-8767-3334a59bde29 | iv. product shop drawing or similar
| note | 3b1c79e8-7b6e-4d65-a4ff-53ee2330baad | v. treatment at kerbs, pedestrian footpaths and barriers
| note | 9ce3fd67-fed2-42bc-ab8f-681ee722c194 | vi. alteration of reinforcement and/or embedments
| note | 0a932221-68fb-45d8-8674-f4fc8d23cf29 | vii. details of nosing material, adhesive, backing rod, sealant and seal
| note | 1f428321-ab74-4ff4-b32c-d2573114df22 | iix. evidence of satisfactory performance and durability of the product under equivalent conditions
| textbox | 22d0aee5-edfb-4ed7-848d-a1e3f614ec70 | Enter: Teambinder Correspondence Approval or RFI Number
| note | b5fbc90a-da20-4686-bac2-faaa27a04200 | METHOD: Document Review
| note | 477b9f5f-8e58-4de5-ba79-50ed46d9b0e3 | FREQUENCY: Where applicable, once, within 4 weeks of acceptance of tender
| note | 5e0a9649-f2ed-404c-b7b6-e21a791d871a | CATEGORY: WP
| note | 7a666506-dae1-4601-a976-f7aa2c0a0c13 | RESPONSIBILITY: Nominated Authority
| note | db0ab6fd-c266-4759-b8df-06d54a43ef7b | VERIFYING DOCUMENTS: This ITP
| textbox | 659f047f-24e5-4c7b-a4b6-975837f593a2 | Date Completed:
| checkpoint |  | 2.2 Expansion Joint Components
| note | 409681d0-2cbd-4fda-b494-4416a2298908 | REFERENCE: IFC Drawings
| note | 976b182f-1e70-40b3-a2c8-729b5a2f9993 | 660.03
| note | 9228677f-444a-47a8-9c23-068e44911177 | ACCEPTANCE CRITERIA: Steel components are to be manufactured to the requirements of the Drawings and AS5100.4 and galvanised to AS/NZS4680
| note | 9db586df-1c39-4d3c-818c-0eb1b71ecda9 | Attach: Quality Assurance Records
| note | 35493bfc-5ec8-4206-928c-49bcc6b40db7 | METHOD: Document Review
| note | fbceb134-695a-4f49-8266-1990be070551 | FREQUENCY: Where applicable, for each element
| note | 8970b93a-3fef-4cf5-a232-af4720af5613 | CATEGORY: IP
| note | a512f783-e125-4fa2-bb06-aca77117adee | RESPONSIBILITY: SE/PE/SPE
| note | ce416428-a057-4a67-913c-dd1838447878 | VERIFYING DOCUMENTS: This ITP
| textbox | 12aca36f-04b1-44e3-af11-559f3a345941 | Date Completed:
| checkpoint |  | 2.3 Joint Sealant
| note | 646357a1-f94a-4f15-81f6-f005f12263d1 | REFERENCE: IFC Drawings
| note | 7892556e-5c5e-428a-acc7-c7734b5573ca | Shop Drawings
| note | 99a1f696-18aa-4c38-ac88-909de3539e27 | Installation Manual
| note | 69f4e9f0-013f-4608-aee8-44f507b86700 | 660.04
| note | 348b0296-ea2a-40b6-9309-528b24fd9d74 | ACCEPTANCE CRITERIA: Where applicable, the joint sealant shall match the Drawings and installation manual or be an equivalent product for trafficable uses.
| textbox | 121b609e-3d8d-4a64-8947-42369d5f6a26 | Enter: Teambinder Material Approval number
| note | 1446eb6a-cc91-4c0f-892b-2602f850fb03 | METHOD: Document Review
| note | f2a59651-6d52-49c5-a6a4-5446d9ab8271 | FREQUENCY: Where applicable, once for each product
| note | aa086e01-5771-4e1d-b09c-b7d45378df0a | CATEGORY: WP
| note | 02dcbb0c-1023-4777-8603-fd65c8e411b5 | RESPONSIBILITY: Nominated Authority
| note | 66a41890-46d2-410c-a766-61c0b793dacb | VERIFYING DOCUMENTS: This ITP
| textbox | f0e2b66c-017b-4db0-9afa-820232f9ebce | Date Completed:
| checkpoint |  | 2.4 Bolt Tensioning Procedure
| note | 3ab2e5bc-c82d-4a32-bfaa-ce9786c10a99 | REFERENCE: IFC Drawings
| note | aae0e4e3-22bf-4704-a4e9-870e4d4e4377 | Shop Drawings
| note | 38be4460-1004-4d3c-aaca-c069ac05df1d | Installation Manual
| note | 65aaa1ce-fcf0-4079-9268-242c0e62c30e | 660.04
| note | afc6635f-e93a-4b4b-aca3-933529db96c2 | ACCEPTANCE CRITERIA: The Contractor shall submit a bolt tightening proposal to the Nominated Authority.
| textbox | 033a50a9-4eea-4634-8106-a214710f02c7 | Enter: Teambinder Correspondence Approval number
| note | 4f14aac5-aa17-40d9-8d49-fa65d409b2a3 | METHOD: Document Review
| note | 38067f97-f518-4338-81cd-fcccf0daa35b | FREQUENCY: Where applicable, 2 weeks prior to installation
| note | 3f43943b-ccd5-472e-87c8-292156ecd025 | CATEGORY: HP
| note | 3337cd80-007c-43b8-a17f-75601c38bc0c | RESPONSIBILITY: Nominated Authority
| note | 055c04dd-af4f-4338-92fb-801809e77fa1 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 0a34b2a5-7233-48a7-b6e5-7a34e4975268 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 3.1 Installation Temperature
| note | 9a95e5db-deeb-417e-b0de-a790f8ca3827 | REFERENCE: 660.04
| note | d46f51c6-8f06-4b14-9ddf-81fa7184a8c1 | ACCEPTANCE CRITERIA: The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers.
| note | ca9ff464-22bf-4d58-b19e-8db35ca60f92 | Planned pour time to also be within this temperature range or adjusted.
| textbox | 4c2de4c7-50d9-46db-9d7d-829e7a78e51d | Installation Temperature
| note | aa353829-8327-4c22-8e35-a2206703facf | Ambient Temperature at Concrete Pour = See Concrete Pour Record
| note | e3d2b08c-d844-4d14-802d-b88141d340b3 | METHOD: Measure
| note | 3f95546d-9708-43f9-b0fc-3555b5219c39 | FREQUENCY: At the time of installation
| note | 647ec825-9113-4dea-a253-d50cd4017e16 | CATEGORY: HP
| note | 0b860b84-6454-416f-bd45-8f97560c1f42 | RESPONSIBILITY: Nominated Authority
| note | a809adc5-2522-483b-ba73-07c7d14da5eb | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 901bcbc0-f761-49a9-b37e-ee3d12244415 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction Activities
| checkpoint |  | 4.1 Expansion Joint Placement
| note | 7f324f0c-f8e6-4e89-bfd0-2b230fb477ad | REFERENCE: IFC Drawings
| note | bf7de9a0-ad5f-4a1e-9d60-a4d0bbeaf569 | Shop Drawings
| note | 8ddce515-023a-4718-8dc9-42b836d50c58 | Installation Manual
| note | bf6b4b80-c3ed-4609-a426-09a77a4d1fe1 | 660.04
| note | f31b6058-5eb7-4bef-b4e1-22cad92bea05 | ACCEPTANCE CRITERIA: Place the expansion joint to the survey marks to achieve a top surface parallel with the longitudinal grade and cross-fall of the FSL and in compliance with the Drawings, installation manual and tolerances
| note | 5d751ea1-b51d-4680-b7c2-b44e3b27cc15 | Joint gap = ±3mm
| note | 860365c1-4417-4135-ab40-ba9ddca565b3 | Deviation from plan alignment = 5mm max.
| note | a5e7f0d0-313e-448c-9456-8998c7fe2a57 | Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
| note | 36f90146-8982-4c73-a8ae-f9e55b0fad38 | Record: The expansion joint ID onto the Red-line Drawings or Survey Report
| note | df23167b-a29f-4faa-aca6-a3e7b71faebd | METHOD: Measure Visual
| note | 941273ac-3b1d-4a01-8584-39da21d3776e | FREQUENCY: Each element
| note | efc23e4c-f569-4489-8098-2d3d9d93c106 | CATEGORY: IP
| note | 3f93668a-a3eb-4c86-93b1-2abb4b1c6c30 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | a8eadb4c-2d9e-45cb-8cf9-b557d3545908 | VERIFYING DOCUMENTS: This ITP
| textbox | d8e95faf-a66d-4708-bce8-658f96b251d6 | Date Completed:
| checkpoint |  | 4.2 Pre-pour Inspection
| note | d66a7a47-20bf-4916-83f9-6dd8306a0f97 | REFERENCE: IFC Drawings
| note | de3834d5-04c2-4cba-996f-7c0e27458e44 | Shop Drawings
| note | 5c68bae8-c2f0-482b-8d1f-edcc18ae4c3e | Installation Manual
| note | f4ed2bce-b51b-44d1-a58b-e28811ed7046 | 660.04
| note | 78f94805-2e7e-4440-a510-572109e600fd | ACCEPTANCE CRITERIA: Reinforcement design to match Drawings and any RFIs to eliminate any conflicts with the expansion joints and/or embedments.
| note | 0b286e03-8ae2-4589-bf3f-cb9cbcef6318 | Tolerances to be within the stated values in 4.1 above.
| note | f5780a2b-8b57-421e-a6a9-1a37fd906c4f | Temperatures to be within range or adjusted accordingly as 3.1 above.
| note | 0e601b97-793f-49d0-94b3-b22fee61c9ed | METHOD: Measure Visual
| note | aeac60a2-dcc8-4098-ae7a-ada06fbd4893 | FREQUENCY: Prior to concrete pour
| note | 2b55e767-6f10-4b94-8270-fb2fd5b50d4a | CATEGORY: HP
| note | 2a178058-639a-4c0e-88b5-cb1576113a87 | RESPONSIBILITY: Nominated Authority
| note | e23838a7-3271-4394-a6b8-45cb639471ad | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 953e5419-eddd-46b1-af97-d8d9cc160c59 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.3 Concrete Placement
| note | 997c44cb-e119-4737-8cfe-00200e511ad9 | REFERENCE: 660.04
| note | 4199793e-bf1c-4396-90ac-5ffa13f686ef | ACCEPTANCE CRITERIA: Complete: The relevant Structural Concrete ITP before proceeding with this ITP.
| note | 3ffc4685-0535-453a-b0e1-d1f1235d4a55 | METHOD: Measure Visual
| note | f6db0a22-48db-4ba7-93d5-bff795c9342e | FREQUENCY: Each Element
| note | feeb5036-e472-4b3e-b072-5630f255eec4 | CATEGORY: IP
| note | 211a574b-5b4b-4ccc-9473-85d5910af0ca | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 578bfcf6-42b9-44fd-8cc6-47a692dd6e48 | VERIFYING DOCUMENTS: This ITP
| textbox | eef082a5-c99b-4dbe-b78b-ad3b16f318f7 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 5.1 Post-pour Inspection (Vertical Faces)
| note | b7caf674-80ba-4956-a0e0-90b778ff48b3 | REFERENCE: 660.04
| note | 05ef1817-5531-49c8-a946-55feb276e7cb | ACCEPTANCE CRITERIA: The vertical faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
| note | a56bbb28-2a56-4420-bdbd-41278c3ab04b | If voids are present: Complete: Cementitious Patch Repair ITP
| note | 458b7b38-3899-4b5d-909d-84e7271e963a | METHOD: Visual
| note | 20817ccc-2e02-4ae1-adfe-908bd4dd1b5a | FREQUENCY: Prior to joint sealant (where applicable)
| note | 509299d1-6779-4711-8cdf-53e277a40e15 | CATEGORY: HP
| note | c88e6608-3c58-480f-a100-fdc4f6849c28 | RESPONSIBILITY: Nominated Authority
| note | 0488a886-c48a-4d6a-88e0-e79f37de50eb | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | e49d341f-0854-4b35-b901-9f3455389e83 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.2 Bolt Tensioning
| note | ae1195c6-0220-4b7c-aff7-c0aea2b02264 | REFERENCE: IFC Drawings
| note | 2f50376a-3bb6-4608-95cc-1bc1704eb53f | Shop Drawings
| note | 7465657c-4a55-49ab-8ac5-74e53709bb5d | Installation Manual
| note | 1ed9b7e8-8212-4e61-9053-77f80ca22de2 | 660.04
| note | bdb50ce3-58fe-4f89-820c-410fd8692882 | ACCEPTANCE CRITERIA: Bolts shall be tensioned to a maximum of 65% of the ultimate strength of the bolt, using a calibrated torque wrench, the part-turn method or another approved method.
| note | e8dfbc37-0d4e-49cf-a8ff-676fb631f40a | Tensioned bolts shall not be re-used.
| note | 0660d4e7-23a3-444c-85b7-1e566a066113 | If the required tension can not be achieved, raise an NCR.
| note | a8790c19-3353-4c02-b2db-4d7a17473a07 | Attach: Torque Wrench Calibration Certificate (where applicable)
| note | 4f69220d-9d5e-4cdb-a3ba-0829ade75019 | Attach: Photos of Tensioning or Marked Bolts before and after tensioning
| note | 8684956b-4779-45be-9577-dfd7c9523734 | METHOD: Visual Measure
| note | c7a01896-a5af-4df7-844c-4a7aaab3ddcc | FREQUENCY: Where applicable, each element
| note | 17177683-5309-4c2d-8e38-d154dfa03442 | CATEGORY: IP
| note | e13c5e77-0308-43cb-87a8-fef36fdf1b0f | RESPONSIBILITY: SE/PE/SPE
| note | a012e970-d015-420f-a529-6a2b349fbb1a | VERIFYING DOCUMENTS: This ITP
| textbox | 3b489562-c6f7-431e-8be2-bd6678b5b5a3 | Date Completed:
| checkpoint |  | 5.3 Compression Seals, Inserts and Membranes
| note | b78764b6-926c-4bb9-a7a7-9dfef240305a | REFERENCE: 660.04
| note | bc3b6d13-fc70-4216-9ebe-cda9987de006 | ACCEPTANCE CRITERIA: Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
| note | e7f9c74e-ba08-4673-8c38-aa3ec3791cd1 | If seals are bonded with the nosing, the surface shall be prepared and primed and the adhesives placed in accordance with the adhesive TDS.
| note | 8325d6af-e9e9-4aa1-90de-f8345dae8a7a | Completed joints shall be watertight.
| note | c881d5e1-2775-4827-9e43-a56e14d4f208 | METHOD: Visual
| note | 461addc4-72d8-48d0-b685-7c16a84c2bcc | FREQUENCY: Where applicable, each element
| note | 916be061-9fcc-4f53-b9d3-29d671b7fd17 | CATEGORY: IP
| note | 2900140e-6dd2-468c-9507-2769c4030ace | RESPONSIBILITY: SE/PE/SPE
| note | a52288c5-553c-43c7-99a7-77eacc34e81e | VERIFYING DOCUMENTS: This ITP
| textbox | ee9c4aa4-ee7f-41bf-b485-4b1690c30ea9 | Date Completed:
| checkpoint |  | 5.4 Nosings
| note | 12032b67-d62a-4a9f-9eb5-71b1d719da83 | REFERENCE: 660.04
| note | 6e3a6118-b3fc-4b69-b6c2-94c35383f673 | ACCEPTANCE CRITERIA: Nosing materials shall be mixed and placed in accordance with the manufacturer's recommendations.
| note | 798081ec-628b-4abd-a4ce-ffd6fafec296 | METHOD: Visual
| note | 3875b1df-e9d2-42a9-8db8-81d0f4f76301 | FREQUENCY: Where applicable, each element
| note | f5c7d8f2-43e4-407e-b5f5-de210e6a5864 | CATEGORY: IP
| note | 2314cbad-433e-41e1-908b-8d90610b05c7 | RESPONSIBILITY: SE/PE/SPE
| note | f48b04e9-3a94-472f-b685-7b26ade01644 | VERIFYING DOCUMENTS: This ITP
| textbox | 4bfd3968-ddf4-480f-8ac1-8f452b48f1c0 | Date Completed:
| checkpoint |  | 5.5 Post-pour Inspection (Tensioned Bolts & Concrete Bearing Surface)
| note | dd8f20b2-12a1-43ef-bcc1-ff6da14a8511 | REFERENCE: 660.04
| note | e4481041-af73-4106-8321-9aa1207e3f8e | ACCEPTANCE CRITERIA: After the anchor bolts are tensioned, the full length of the joint shall be tested by tapping with a hammer to ensure that there is no presence of voids in the bearing surface.
| note | 2d6cbaa6-a3bb-4e9d-9b50-651ce4dc8032 | If voids are present: Complete: Cementitious Patch Repair ITP
| note | 478759b0-158b-4031-b8ce-861d4111b5da | Where joints are removed for inspection, the bolt tensioning process shall follow 5.2 above after replacement of all tensioned bolts.
| note | 4ca18b40-1e3c-4468-a3de-4c0077a1190c | METHOD: Visual
| note | 48029f07-2c39-47c1-b895-0b62e837da12 | FREQUENCY: Where applicable, each element
| note | 24bff3d6-e851-4249-8154-02a98bf05ea2 | CATEGORY: HP
| note | 142d99ee-0cbf-4408-8fdd-a4fdf83e238e | RESPONSIBILITY: Nominated Authority
| note | 9ecbaf76-d1f3-424d-a450-dffb7fcda1a4 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 2451852e-5002-4bb8-a97a-e2cc6195f634 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.6 Trafficking of Joints During Construction
| note | 8696988d-126e-4ab5-99eb-8c6a46059b66 | REFERENCE: 660.04
| note | 03c64da7-0668-4afa-a74e-dff5488650e3 | ACCEPTANCE CRITERIA: Joints shall not be trafficked until all components of the joint have achieved adequate strength to support the traffic loads without damage.
| note | e646822e-0993-44ca-833e-9a4bdd12a87b | Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
| note | 57e54513-ad0b-41e5-874a-87ed9958528a | METHOD: Visual
| note | 165326d4-aded-42ab-9867-ae3275679d3d | FREQUENCY: Where applicable, each element
| note | 883af806-1a34-43d6-a3da-9768e9689ca8 | CATEGORY: IP
| note | b58fd65d-4fab-4d68-85e3-ffaeadeb08fc | RESPONSIBILITY: SE/PE/SPE
| note | d7a975bc-6bd8-4c3b-8126-de5b7eab692f | VERIFYING DOCUMENTS: This ITP
| textbox | efb403a5-5e6a-4f1b-a61f-b14bdcbdf4bf | Date Completed:
| checkpoint |  | 5.7 As-built Survey
| note | d0208239-c036-4083-8bd1-eedb3d2f3d22 | REFERENCE: IFC Drawings
| note | 6f272cae-678f-4e3f-a65b-589440829af0 | 660.04
| note | 43d009c4-273a-44d4-9b90-b8edfdb13e72 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 4.1. above.
| note | 19d82847-aac4-4d10-b784-7c259a6f080e | Attach: Survey As-builts / Survey Report
| note | 40841cda-bf93-4dc9-a252-c1015d93817b | METHOD: Document Review
| note | 1432e9d5-fcc0-4380-b98f-3a1735083dee | FREQUENCY: Each element
| note | 2b30eb23-1d90-4b61-abdd-c8e843a07f35 | CATEGORY: IP
| note | 0d4c9a90-7f9d-4b5f-9d8b-abe65f344cfb | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | da6470cf-192e-4ba2-8b1e-88a4b5ab7fd5 | VERIFYING DOCUMENTS: This ITP
| textbox | a7186387-c61b-486a-99f6-e893a7e32582 | Date Completed:
| checkpoint |  | 5.8 Non-conformance Report (NCR) Closure
| note | 40ea4e55-c608-4d48-aa84-46ee81ce109d | REFERENCE: MRPA Quality Management Plan
| note | 85163165-1449-4160-a999-e513bc5aae94 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | ce9fa79a-5a87-4111-9e13-d8f59f26c214 | METHOD: Document Review
| note | 8ef5660e-55e9-41bf-9384-88160f747a23 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | a58ed3a9-af46-43bd-bd85-740cd9da5614 | CATEGORY: HP*
| note | e7482c4e-9edb-4b53-a508-3e97f4d34568 | RESPONSIBILITY: SE/PE/SPE
| note | aa85753c-70fd-4705-9ebe-6b24cfd038d3 | VERIFYING DOCUMENTS: This ITP
| textbox | 0868fcab-eb6c-415a-87a8-2f0b633c592a | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | c6441a2d-74fd-46d8-9fe9-42469d3fe3b6 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 90089a3b-ffa7-4280-bf7a-0ab118a045ea | Name:
| textbox | c769e556-e1b4-4ffc-9248-87ddd214fc26 | Position:
| textbox | 519be863-37e0-4147-8fe8-cabef142c2dd | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Conduit and Pit - Roads (Supply and Install) Rev 2 | itp | ITP-CIV-Conduit and Pit - Roads (Supply and Install) Rev 2 | 96b13393-7f95-45b7-b215-a0a9659e537b
| section |  | Reference Documents
| checkpoint-no-value |  | Reference Documents
| note | c66c8522-5c17-5312-8c18-869649f1eb98 | VicRoads Standard Section 733 (April 2019)
| note | 24210d5a-e327-5a72-967d-0a9dba7c2952 | VicRoads Standard Drawing TC-1220
| note | 230a8725-3fa0-5410-bd47-40f1acda69ad | VicRoads Standard Drawing TC-2204
| note | d3c67743-619f-5e9c-9046-124df8244646 | ITP Revision: Conduit and Pit (Roads) _00
| note | b8f9d9fa-9aea-5c85-9dae-74f3d2deecd1 | ITP template approved by: Romualdo Magpantay(October 2019)
| section |  | Products and Materials
| checkpoint |  | 1.1 - Electrical Conduit
| note | 740a8f8c-ae43-5330-8140-3a8b08938e42 | Details and Contract Requirements: All conduits installed underground for electrical wiring, traffic signals and traffic services shall be heavy duty grade, rigid orange, UPVC conduit to AS/NZS 2053.2 or Profile wall-smooth bore HD UPVC conduit to AS/NZS 2053.6.
| note | a97ec49a-07aa-56dd-b96d-0a82443d2b8e | NOTE: Profile wall smooth bore and sandwich wall type conduits shall not be used for VR works.
| note | 7db77ea3-2070-5f1b-85fa-2a71f1707f4f | References: 733.02(a)
| note | 5607592b-cfe5-5c50-bd16-3b2b914d6dc8 | Verification Record: Certificate of compliance from supplier. Record teambinder material approval number
| checkpoint |  | 1.2 - Communications Conduit
| note | 0ddc9e56-d3c9-5559-bf6b-39fb9a222531 | Details and Contract Requirements: Rigid white UPVC communication conduit complying with AS/NZS 2053.2 or Profile Wall-smooth bore HD UPVC conduit to AS/NZS 2053.6
| note | 49be4c38-102c-565b-a048-c963e8ad02ba | References: 733.02(a)
| note | 6c084cdc-b7af-51ac-bd74-867357fb8d34 | Verification Record: Certificate of compliance from supplier. Record teambinder material approval number
| checkpoint |  | 1.3 - Conduit for bored road crossing
| note | 79dd3812-72b2-512a-bcbc-21ad8a556e8b | Details and Contract Requirements: HDPE continuous conduit is permitted. Ensure internal diameter is not less than specified. NOTE: Profile wall smooth bore and sandwich wall type conduits shall not be used for VR works.
| note | 650f59fc-fef9-5a14-b53f-fdbeea28e70b | References: Table 733.021
| note | e669b3f9-f5d0-5079-aaf0-b0ff7cf81e01 | Verification Record: Record teambinder material approval number
| checkpoint |  | 1.4 - Bedding Material
| note | ac6a78e4-6c27-56c4-89c0-d9bf36fd2f16 | Details and Contract Requirements: Sieve size AS 19mm - 100% passing 0.075mm - 10-40 % passing Plasticity index 2 - 10
| note | 8d2dbfbe-54ab-5f9e-a7bb-6d99c961aea0 | References: 733.06 Table 733.061
| note | d159629c-097c-54c2-92d5-2aff38bd643a | Verification Record: Record teambinder material approval number
| checkpoint |  | 1.5 - Select Backfill
| note | f85cd115-12df-52c8-936d-e1af26417a2a | Details and Contract Requirements: Sieve size AS 75.0mm - 100% passing 2.36mm - 40-100 % passing
| note | 8bd4dded-b4e7-5c76-b8db-e99752d8b1df | References: Table 733.061
| note | e382202e-24bc-554a-b451-f117f794a991 | Verification Record: Record teambinder material approval number
| checkpoint |  | 1.6 - Common Backfill
| note | 092f6d9f-645f-5da9-b8d7-13da7b8383e4 | Details and Contract Requirements: Sieve size AS 19mm - 100% passing 0.075mm - 10-40 % passing Plasticity index 2 - 10
| note | fffffd01-48f8-581e-92e3-06428aba46f0 | References: Table 733.061
| note | 42ed84ef-7502-582f-85b2-32503e994923 | Verification Record: Record teambinder material approval number
| checkpoint |  | 1.7 - Pit Lids
| note | e1eeb08c-a38d-57f7-89d8-1317242f0244 | Details and Contract Requirements: Cable pit lids shall be VicRoads type approved, impressed with 'VicRoads' and 'Electrical', 'Communication', 'Traffic signals" as appropriate as per VicRoads Standard Drawing TC-1220
| note | 44ffa3e4-3e69-5666-b50a-7a706a978e98 | References: TC-1220
| note | 08cf4888-cc6a-54ff-8966-2cab420d31d4 | Verification Record: Record teambinder material approval number
| checkpoint |  | 1.8 - Pits and surrounds
| note | 31681a51-d487-5192-b185-810aeb757b0c | Details and Contract Requirements: All Pits and surrounds shall be VicRoads type approved. Pit, surround and lid are compatible together.
| note | a1287617-2e67-5cdc-b2cf-db1477a0acc2 | References: 733.07,
| note | 62205d51-2b1e-56fb-8b18-f67c3211e8ec | Verification Record: Record teambinder material approval number
| checkpoint |  | 1.9 - Details of boring
| note | d677a6d9-a36a-5a43-86ac-ca383eced417 | Details and Contract Requirements: Detailed proposals for boring under carriageways shall be submitted to the Nominated Authority for review prior to commencement of work.
| note | 72e8e412-acf1-5cda-a0ce-387bbef84077 | References: 733.03
| note | 358dbd6e-cf66-5986-acad-10c838aaf901 | Verification Record: Refer to teambinder reference
| section |  | Installation
| checkpoint |  | Refer to VR Standard Drawings
| note | f2ae42e2-d252-592a-9fd0-0ed1a7d7cfbd | Details and Contract Requirements: Install conduits, pits, and pit surrounds as per Design Drawings, VicRoads Standard Drawings and manufactures guidelines.
| note | 0fadad77-e14b-5356-9a53-91240eede608 | Refer to VicRoads standard section 733 for reference to applicable standard drawings
| note | d2f990d1-8494-591a-8fe2-9e5e99e1a99e | References: Table 733.071, Table 733.072, 733.073, Table 733.074,
| note | 14f2d550-06a4-5e84-a3a3-1dbda89a88e0 | Verification Record:
| checkpoint |  | 2.1 - Bedding
| note | c1b162d0-9691-5ae5-9ced-f1ae17a923bc | Details and Contract Requirements: Bedding material shall be placed and compacted to refusal for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation.
| textbox | b73c509c-cc7e-5652-b223-f4394d2eb0cf | Bedding Material used:
| note | 3c8b5c63-ba08-5bed-b694-d62e61ea8170 | References: 733.06
| checkpoint |  | 2.2 - Inspection prior to filling
| note | 1096cb0b-209e-509a-9a90-f5654f22242e | Details and Contract Requirements: The Nominated Authority shall inspect once the bedding material laid and conduits in place, prior to filling
| note | 31623145-3099-5de2-856a-3693da008e36 | References: 733.06(b)
| checkpoint |  | 2.3 - Marker tape
| note | c44a3133-af1a-5e0e-b908-fc7cc893b74c | Details and Contract Requirements: 100mm wide marker tape is to be installed 300mm above each line of conduits in all trenches. Where electrical and communications conduits are provided in a shared trench, electrical wiring is placed on top of a single traceable communications marker tape.
| note | 27d223e3-fe51-585c-a061-c6f3d6b6708c | References: TC-2204
| checkpoint |  | 2.4 - Filling
| note | 9f9ea2bd-632c-5b84-ae31-fae1ad01aa6c | Details and Contract Requirements: Bedding material shall be placed and compacted 150mm above bedding previously placed.
| textbox | df0cafff-c8e1-55d1-90e5-5706d1add291 | Backfill profile used:
| note | 0b362e9a-19f2-55b2-9dda-143f842c5564 | Conduits under area to be paved:
| note | 8d8312a4-5e06-55a0-9c63-eb2cf41cd1fa | Selected backfill to underside design subgrade level.
| note | 5c6ed6d4-cd28-50c8-b3e3-923333972d73 | then, Specified pavement material
| note | b4d30593-8b24-53d3-948a-c5ce8781d5b8 | Conduits under area not to be paved:
| note | a1f57465-6cd9-54fd-a4ed-35812b9b7a68 | Conduits under area not to be paved:
| note | ac4d0e79-b1b5-529c-a593-8dc978a28bd8 | Selected backfill to 400mm above top of conduit
| note | cd005616-0bab-5743-8da5-3dee807ac3d4 | common backfill to FSL.
| note | 37a9efd4-5022-5c24-9e0d-97a773ccf849 | Conduits through existing paved area:
| note | 3ccff7ea-2b88-543d-9695-92e4c1f3161e | Select backfill to existing subgrade level then, Restore pavement.
| note | 3921f05a-5528-5aa6-b870-68c90fe35f3a | References: 733.06(c.)
| note | 6f7467a3-059c-5b79-8f46-ef68ef9b2156 | Verification Record:
| checkpoint |  | 2.5 - Maximum number of conduits per pit type
| note | cd66ce0f-fc86-57f5-9445-b9117358b135 | Details and Contract Requirements: Conduits as per design, ensure the maximum number of conduits in a pit does not exceed the numbers shown in table 733.075
| note | 45e78067-70a9-5eb8-b0e3-b85e9e85bbf4 | References: 733.07(h)
| checkpoint |  | 2.6 - Pit lid surround inspection
| note | b75ffdf8-a660-57cd-b4f2-39be52c79b82 | Details and Contract Requirements: before the pit lid surround or pre-formed collar is cemented into position, works shall be inspected by the Nominated Authority
| note | f4338a4f-6e8c-56f0-9ef8-efb843fee110 | References: 733.07(c.)
| signoff |  | Nominated Authority Hold Point
| checkpoint |  | 2.7 - Draw Chord
| note | 21e0575e-5bb8-57c7-9684-65b0b32f74d6 | Details and Contract Requirements: Draw chord is installed in each conduit run where no cable is pulled.
| note | 316b7756-a30f-574f-bd1d-f0ef8705e71d | References: 733.05
| checkpoint |  | 2.8 - Certificate of Electrical Safety (CES)
| note | a39b2532-e7d6-5ede-9e09-bf98c14356a6 | Details and Contract Requirements: certificate of electrical safety for all conduits and pits installed.
| note | 6bbfece3-144f-5893-b5ff-bb94d2540145 | Suggest labelling each pit with unique ID on as-constructed drawings for ease of reference.
| note | 3290b3a3-d3b0-56f9-969c-dc04318caca7 | References: 733.11
| checkpoint |  | 2.9 - As-Built Records
| note | bd5b6bd4-ac62-587a-889e-af793d7a9138 | Details and Contract Requirements: Record on As-Constructed Drawings and Survey pick-up for master CAD file;
| note | b4804a5c-a2d3-5b6f-8e52-4d79df4efe52 | Conduit size, Location and depth.
| note | 578c6b43-02fb-52b3-a5f9-9d5e1f3fb16e | Pit location, size and type
| note | 9e1548ff-c043-54fa-a19a-a7126c475d49 | Check Works Agreement for project specific requirements relating to stakeholders.
| note | 40136bb8-1c9c-5467-b18b-99e5cd0450fd | Suggest labelling pits with unique IDs for ease of reference.
| note | 1644e1f4-32f3-5b51-a32d-cc3ac8ba9a7b | References: 733.10, 733.11
| checkpoint |  | 3.1 - Submission of details for Boring
| note | 3ddd4f34-1c2a-583b-9fbf-7602640703b5 | Details and Contract Requirements: Refer to VicRoads standard section 733.03. Details provided to the Nominated Authority
| note | 54597b2c-4e89-5f22-bdd8-e93cddc0fae2 | References: 733.03
| signoff |  | Nominated Authority Hold Point
| checkpoint |  | 3.2 - Depth
| note | 456718ac-302f-50e3-8757-fcf05fcd7050 | Details and Contract Requirements: Unless otherwise shown on the drawings, borings and trenches shall comply with the depth requirements specified in table 733.031
| note | 8c8f4b3f-f25c-599a-b425-7753aa0252dd | References: Table 733.031
| checkpoint |  | 3.3 - Grout the annulus
| note | 0850f3a2-92b4-5119-a9d8-dd1961bd2efa | Details and Contract Requirements: Before backfilling the bore access excavation, the pressure grouting shall be inspected by the Nominated Authority
| note | c4a3459b-1073-50eb-ab30-a4498bfc06d8 | References: 733.03
| signoff |  | Nominated Authority Hold Point
| checkpoint |  | 3.4 - Warning Sign
| note | 7906e46b-e7ea-5cef-9cf6-f99130fd9969 | Details and Contract Requirements: An underground conduit warning sign shall be installed in accordance with VicRoads Standard Drawing TC-1208
| note | f790cd3f-a70b-5fb4-a538-274144f71b6e | References: TC-1208
| note | 9b8dcefe-51ff-56db-8f46-f7dd712f67ba | Verification Record: Photo of sign
| checkpoint |  | 3.5 - As-Built Records
| note | ee445bc5-40cb-5f89-90aa-d84bc960d24f | Details and Contract Requirements: Record on As-Constructed Drawings and Survey pick-up for master CAD file; Conduit size, Location and depth. Pit location, size and type Check Works Agreement for project specific requirements relating to stakeholders. Suggest labelling pits with unique IDs for ease of reference.
| note | 62a2f767-eda7-564d-9b4e-b41d98e9d654 | References: 733.10, 733.11
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | acc70eb7-468e-5d84-936c-c43178ef833b | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | f6299c40-2245-59bc-b13f-6a8b3bfd5f6c | Name:
| textbox | aa6a380c-50de-51c0-9106-d6ef1c7414c5 | Position:
| textbox | 317b3edc-7512-53ae-a982-bbc2e57b3778 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Structural Concrete Patch Repair Rev 1 | itp | ITP-STR-Structural Concrete Patch Repair Rev 1 | 99dbdcfb-6816-401b-baa5-0cf0df28795c
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 5b2b10f9-ded5-4826-aa36-9c795e276236 | Document Title: ITP-STR-Structural Concrete Patch Repair
| note | b7e0bbf7-902a-419f-a23b-fcc64cd9d53d | ITP Description: Structural Concrete Patch Repair
| note | a6826a3a-5a2f-4ee3-be11-30b422146e3c | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | ec5627a4-6f4d-4728-8502-e9a8ee90ae99 | Discipline (e.g. CIV/STR/RAIL: STR
| note | 5ff276ab-a705-4e46-b972-f4124e4fe0b5 | Revision Number: 1
| note | fd2e9355-80c2-4a3f-bc74-47ed95bf8d28 | Revision Date: 8/04/20
| note | b369a0ad-7e80-42ab-a98e-5e159fd18caf | ITP created by: Mike Freeman
| note | 7c470a37-1221-4933-8b41-0abb820cdde4 | ITP approved for use by: Mike Freeman
| note | 067457bd-15c8-49d7-9576-366a47fcf263 | 1.1 Reference VicRoads Section 689 December 2017
| note | 4302dbda-fbc2-4187-89c1-64ff05308428 | 1.2 Reference VicRoads Section 610 November 2018
| note | 2ea7e4ff-0c66-4e35-b550-13fdc6e3c537 | 1.3 Reference VicRoads Section 610 March 2019
| note | ff7627ad-e156-4e39-a0e8-2e668aba971a | 1.4 Reference VicRoads Section 610 June 2019
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Repair Mortar Selection
| note | fafa99ad-224f-490a-9381-aa49f6b97f68 | REFERENCE: Product TDS
| note | 3ce068a0-c2fb-4b0b-bfcb-39c31b5b8535 | 689.06
| note | 9679ab33-ebb5-4296-9680-5bdd632751ce | Table 689.061
| note | 0428808c-ad32-420c-afdd-dce9177bdf4d | ---------------------------------
| note | 0d38088e-0bdf-4a97-a009-8eb8bd0d146a | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | a00a8b35-d7c1-4af2-9c50-38ee470626df | i. able to be hand applied in vertical and overhead sections up to 30 mm thick in one application with no slumping;
| note | d7623179-d0bf-4138-bfe9-9e8b152126fd | ii. drying shrinkage ≤600 microstrain;
| note | 24a0b5a8-75a9-4815-8a1a-9d672079ed1f | iii, minimum wet density of 1600kg/m³;
| note | eaac8acd-f3f9-443a-87ff-58916f5c10d5 | iv. achieve the strengths and bonds conforming to the requirements in Table 689.061.
| textbox | 7e5d18bd-ff0d-4bb9-9ee7-7af183ab0b82 | Enter: Teambinder Material Approval number
| note | e6a2d119-22d2-418d-bd20-935159f9b2a6 | ---------------------------------
| note | 5b48517e-ebf0-42bf-86c4-8cbb07a179f1 | METHOD: Document Review
| note | b3c28374-d6cb-4583-92a8-369b49430cfe | ---------------------------------
| note | 692ee2b4-3dda-48ba-8a35-093afe19b635 | FREQUENCY: Once, for each product, prior to placement of product
| note | 827edc20-07fc-436c-89c4-d0aa68eb9e04 | ---------------------------------
| note | e46cef70-efda-4d78-a17f-0cd1e0156be4 | CATEGORY: IP
| note | c0b92e69-1554-4a9d-854b-effbdf1bdc1d | ---------------------------------
| note | 2150f4b7-75e4-43a6-bba7-2246edcddbb0 | RESPONSIBILITY: Nominated Authority
| note | 54e11387-2ae8-45d1-859a-e939bdff26dd | ---------------------------------
| note | 2a9f0558-5858-4f64-96c1-0c91ea79bb01 | VERIFYING DOCUMENTS: This ITP
| textbox | b6186714-add9-41d3-9c87-0e826120bfac | Date Completed:
| checkpoint |  | 2.2 Fairing Coat Selection
| note | 00de30c4-c92e-4283-b40d-0b55950dff25 | REFERENCE: Product TDS
| note | de4c2f98-f54d-499c-9e5f-d2ebdcde4dc0 | 689.06
| note | 408c8f49-0988-41e4-86c0-e75ecc773be3 | Table 689.061
| note | 177ca05e-4662-4e62-b234-d9ac9326b2da | ---------------------------------
| note | a761dd10-ee44-4443-89df-f343cb700b79 | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | 16201cbd-37c9-475e-b68f-9e2746a83778 | i. able to be applied to 0-3mm thick;
| note | c232bd32-84c6-47f4-af39-51b350056c21 | ii. able to cover a large area without shrinkage cracking.
| textbox | 66850e4f-36aa-46ce-9e7a-40f697623637 | Enter: Teambinder Material Approval number
| note | 3051e39f-79ac-4e74-af4a-77cf7d58d5c4 | ---------------------------------
| note | d25c639f-8e45-43a5-afb7-8e1ed7f67e39 | METHOD: Document Review
| note | 8bce07e1-2a91-43ec-ba23-17fac8756b3e | ---------------------------------
| note | 1c7544c7-e27e-421d-b7f7-b222df35c0ee | FREQUENCY: Once, for each product, prior to placement of product
| note | dcfcbd11-756e-4861-9e16-1ceb2236b7a9 | ---------------------------------
| note | 0205f4dd-3260-4891-9ad6-c2ae75ba896b | CATEGORY: IP
| note | fad40178-aa47-4c77-b238-5c4098d2eec5 | ---------------------------------
| note | 272a1508-21b5-4c94-8ebb-93ad3379e1c1 | RESPONSIBILITY: Nominated Authority
| note | 16ef2411-306f-4083-9907-dc88fe84dd41 | ---------------------------------
| note | 89612f38-62d3-408a-a274-d266c310964f | VERIFYING DOCUMENTS: This ITP
| textbox | f8f65431-c471-4ffd-8665-06e3fc8cb57b | Date Completed:
| checkpoint |  | 2.3 Reinforcement Primer
| note | b88e4f15-8f47-4003-ae0b-a683e01ddfe1 | REFERENCE: Product TDS
| note | bff63de7-b443-4d30-8932-e5d01ce7cdba | 689.08 (d)
| note | 8e4c4bec-2cf3-438f-ad69-5a67cfca8760 | ---------------------------------
| note | 2b179438-78a5-4196-8250-f9e8f14f2241 | ACCEPTANCE CRITERIA: Product nominated as part of a repair system (normally nominated in the repair mortar TDS)
| textbox | e5fd59fe-ab93-4576-bc78-f0f2a513022a | Enter: Teambinder Material Approval number
| note | f5a06b93-3951-40fa-ab2d-206719704717 | ---------------------------------
| note | f77ea602-e161-4b22-a3c7-df7aaceae959 | METHOD: Document Review
| note | 49a18862-7ada-49d0-be26-4859fbd64f9d | ---------------------------------
| note | 9c74b68a-6b19-4d5a-9e05-15377158c945 | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | fd859987-dfd2-4bc1-812f-b81773926f16 | ---------------------------------
| note | d3d01471-a04e-408e-8663-b1fd65f5588f | CATEGORY: IP
| note | 769c92db-7686-4ae5-b2f4-43d5a62a39c4 | ---------------------------------
| note | 5dc151d3-e333-4b5b-9478-1f3edab7f293 | RESPONSIBILITY: Nominated Authority
| note | 83d83cd9-4022-464a-80b2-4b17ad58a88f | ---------------------------------
| note | cef30284-e70d-4364-af15-1bf88855ddc7 | VERIFYING DOCUMENTS: This ITP
| textbox | 146b0f42-3071-4074-bd3f-0f2698bda729 | Date Completed:
| checkpoint |  | 2.4 Substrate Bonding Agent / Primer
| note | 246e7bc5-6fb8-4355-90fb-447e9c10ec6d | REFERENCE: Product TDS
| note | c9880a9b-cae5-4192-a7de-f3d5a786526f | 689.08 (d)
| note | 2fb8c68e-5577-468b-968b-25c507e43974 | ---------------------------------
| note | 4ad58189-b17b-4757-a374-079e594fe2e8 | ACCEPTANCE CRITERIA: Product nominated as part of a repair system (normally nominated in the repair mortar TDS)
| textbox | a100b6be-3541-4ab6-a85a-316d8ed3d784 | Enter: Teambinder Material Approval number
| note | c5dd672d-7810-4c09-91a4-e77354bd2d55 | ---------------------------------
| note | bf063b12-c36a-42a5-89dd-cfa0b3b7eb9e | METHOD: Document Review
| note | e03935be-057e-42a4-b5d7-51d7162ebcb1 | ---------------------------------
| note | d99776a5-4d1d-4d2b-9efc-173306e1cf9d | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | 5cff9936-65e6-4f7a-894b-0988646098a0 | ---------------------------------
| note | eadfb269-d7b5-4997-917c-3f5d19a805e2 | CATEGORY: IP
| note | ec047144-7189-4429-b469-7784f1fc18b5 | ---------------------------------
| note | 48ecf719-3c3c-4ff7-8f63-f54b3195d547 | RESPONSIBILITY: Nominated Authority
| note | 8cbcf79a-4146-47bd-97c3-863db368b86e | ---------------------------------
| note | ee912972-5303-4b59-9f4d-c02c44ebfb73 | VERIFYING DOCUMENTS: This ITP
| textbox | d90b1c97-ad85-4754-a9e0-84eea64ebcaf | Date Completed:
| checkpoint |  | 2.5 Curing Compound
| note | 6a74cefc-05b9-4ead-9bc2-0a713f3a6774 | REFERENCE: 610.23 (d)
| note | 532a84d0-dae8-4bde-81ea-6ad749f8fd58 | ---------------------------------
| note | 577b0ea6-3bb0-43b7-8a55-08e8b3c1a7db | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| note | 38a12c7e-a604-447b-aece-deb05da1f5e4 | Note: This may be the same product used for the concrete curing
| textbox | 131f6f76-a220-444c-aee0-2195000d9e2d | Enter: Teambinder Material Approval number
| note | ce22dcda-3183-41ee-bbcb-0e81a042b108 | ---------------------------------
| note | 24d8e068-16a0-48e1-996e-2abdb66a10a8 | METHOD: Document Review
| note | ce2335e5-236e-44da-ae56-86221647cb66 | ---------------------------------
| note | 4d40f52c-1bad-402c-a38b-3ecabc82549e | FREQUENCY: Once, for each product, prior to placement of product
| note | d827f42a-2e64-464e-80f1-51fc0800f337 | ---------------------------------
| note | 9c0089b1-d788-4dfc-b638-bbb02a2c7699 | CATEGORY: IP
| note | e3fea4a8-7b50-45ab-938c-eac7f2dc3140 | ---------------------------------
| note | 32605f4f-f7ac-4ed0-8a94-a0a09aef95e2 | RESPONSIBILITY: Nominated Authority
| note | 932661d1-7099-43e7-a7c4-a7613182a305 | ---------------------------------
| note | 09031b73-f407-438a-93d1-3a181fbc9367 | VERIFYING DOCUMENTS: This ITP
| textbox | d532f57b-8c28-4ceb-9fcf-ee11c408b0b8 | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Assessment of Affected Concrete
| note | cdaf0f1c-897f-4899-91a6-e3cd904847de | REFERENCE: 689.02
| note | a3ed64e1-c088-4d09-9f96-7160f34c5731 | ---------------------------------
| note | bfadc984-3a5c-4eb4-8ac9-ebb1d59b6a21 | ACCEPTANCE CRITERIA: Contractor shall assess the affected concrete to determine influence of spalling, deterioration, and honeycombing on the load bearing capacity, serviceability and durability of the structure.
| textbox | 60508cc6-c020-4d19-8f67-09574a7aa31c | Enter: Teambinder Correspondence Approval number
| note | c5b29312-1c98-46ef-b6ca-f4d56a9e60d2 | ---------------------------------
| note | 857dfdcc-537f-4196-9eb9-da63f72ac987 | METHOD: Document Review
| note | af5ee9d0-f800-4ab6-953e-3b246816808d | ---------------------------------
| note | a9d334d1-a805-4b10-809d-bdeee0114082 | FREQUENCY: Once, for each product, prior to placement of product
| note | eb85d9dc-8008-4b9f-a715-343709234687 | ---------------------------------
| note | c3d26577-08cb-4d91-a253-b2e7fed7673d | CATEGORY: HP
| note | 682b9ddb-4217-4247-a67e-2155527e30aa | ---------------------------------
| note | 85cc873f-c789-4d2b-b736-bbddc7227d07 | RESPONSIBILITY: Nominated Authority
| note | f4ad9b1e-8eca-4017-b030-76c2de3271c8 | ---------------------------------
| note | 3d156451-b007-4aed-9d65-4cafd31de2ea | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | a4ccc68b-b95c-4011-b433-9cee6a3485c3 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Concrete Repair Work Method Statements
| note | 5c188a06-38e8-4a13-9e22-653e3861e98c | REFERENCE: 689.13
| note | 121ec46a-e831-42f1-b530-ee4828a972e2 | 689.08 (e) (iii)
| note | 9a8fa520-236f-4fb0-a9ee-5856068ae13a | ---------------------------------
| note | e3c0bc6b-a10b-4642-9179-f3b58148c317 | ACCEPTANCE CRITERIA: Contractor shall submit a detailed procedure for the specific patch repair works.
| note | a4a7153e-b305-4db6-a1c0-ec817c3b43bb | Generic or incomplete WMS's and ITP's will not be accepted.
| textbox | 529da29c-61d5-47f2-8cc6-1fafe45a086a | Enter: Teambinder Correspondence Approval number
| note | 7594645a-cd94-406d-a7c8-1b810357b705 | ---------------------------------
| note | 06354b28-f5fb-47c1-ac38-1353b2b544a1 | METHOD: Document Review
| note | 9e894c29-0304-4d23-943b-cbfe54423250 | ---------------------------------
| note | 6665668e-b1fe-4be1-929a-3358d3757c4f | FREQUENCY: Once, for each product, prior to placement of product
| note | 316188b7-1ae2-4aa4-8b94-b77ba9043d91 | ---------------------------------
| note | c9956221-ff1b-463f-8956-f0739d1b017f | CATEGORY: HP
| note | 6a885e78-c954-4bc9-879a-768ee943cc6f | ---------------------------------
| note | 886888ce-9bee-4d66-9ef7-8e052df6c265 | RESPONSIBILITY: Nominated Authority
| note | 9178d1f6-99b5-4fbe-9266-3be543950bb4 | ---------------------------------
| note | e52fb047-1790-4ed6-8b80-745208d56004 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 63a54008-fbfa-4f37-a48a-5c16bb2809dc | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Deviations from Manufacturer's TDS and/or Specification
| note | f57082c5-80cb-47dc-8148-2f869424caba | REFERENCE: 689.08 (a)
| note | 04ce70dc-13a5-46fa-a1e0-71f1d583117a | ---------------------------------
| note | 483c2f35-ef74-4e1d-a60f-7788cab3683f | ACCEPTANCE CRITERIA: The contractor shall perform concrete repair work in conformity with the manufacturers specifications.
| note | c8148f8f-b16e-4e1b-941d-78ed64d84940 | Any deviations from manufacturers specification must be submitted for approval as an updated WMS and/or ITP.
| textbox | 162159e2-17d3-4015-8df6-63f9822feb84 | Enter: Teambinder Correspondence Approval number
| note | 4576dd63-e05e-4d84-90e9-1050baff6b3a | ---------------------------------
| note | 8eb1a504-77db-4070-bcf0-204ece18e086 | METHOD: Document Review
| note | 568ea0ec-0f92-4d99-b1b8-819933be3a3d | ---------------------------------
| note | 414efc4f-a2a7-46c5-96b2-3ad7b996d754 | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | c6ea5d28-55c8-48ec-bf28-94f8cd648677 | ---------------------------------
| note | 8ec0af17-2ffe-418c-b2ee-6dc761255b4b | CATEGORY: HP
| note | 413d78a8-bb4b-4400-9f12-a1aee3c6b883 | ---------------------------------
| note | cac01e05-9563-40c8-887f-110eab416426 | RESPONSIBILITY: Nominated Authority
| note | 88771eb7-fb20-4bf0-a113-0fab808f4271 | ---------------------------------
| note | 1d035fb8-ae38-41ef-908a-684d5fc1b5f0 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 48b8a738-b99c-4c89-9221-fa2cacc8ea9d | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Curing Methodology (for Concrete, Grout and Mortar)
| note | 4a84be27-edb8-408d-9498-8965631205c6 | REFERENCE: 610.23 (a)
| note | fcff4d57-f030-4e03-ab73-2aa0070e46ba | ---------------------------------
| note | 60a1ffb8-2bb9-4d26-a9a1-0232d68974b8 | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
| note | afb718d0-9e37-4c31-be1e-fc9d25abfdd0 | Note: This may be the same document used for the concrete curing.
| textbox | 906fcfc9-146b-4e47-8595-ffbd83586612 | Enter: Teambinder Correspondence Approval number
| note | 8b235128-f9bc-4440-bdaf-7722861dea08 | ---------------------------------
| note | cc7315f8-7f33-4901-892d-20e04af7e68b | METHOD: Document Review
| note | 07eada80-eb87-4c4b-bf89-582d797f89fe | ---------------------------------
| note | 79b40ad9-8e7f-45df-89e5-20f8d1b5f0fc | FREQUENCY: Once, 4 weeks prior to placement of product
| note | 6975a73e-b4e9-4863-9a94-6f99327fd71a | ---------------------------------
| note | c2670b97-6ce2-441f-b9d3-aae0ed64df85 | CATEGORY: HP
| note | 883521d4-7e0f-4bbd-b0af-099e21f06b11 | ---------------------------------
| note | 1205c9fb-1fdc-45c9-a43b-fee507b230d4 | RESPONSIBILITY: Nominated Authority
| note | a34107dc-0f8a-40f8-904e-5a5f93b193e2 | ---------------------------------
| note | 3ae8ec31-4542-476f-8545-4c7831b24944 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 3e7804af-b878-4b4d-9807-1afe096a9af4 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.5 Concrete Patch Repair Toolbox Meeting
| note | e79b08eb-a455-41a9-b6d1-5171363c7b26 | REFERENCE: 689.13
| note | 1b505857-fbef-45e0-841c-435b905e46e5 | ---------------------------------
| note | 0042f9b7-2f68-4410-9a74-627701911059 | ACCEPTANCE CRITERIA: Concrete patch repair toolbox meeting held to discuss the quality requirements.
| note | 14a44a3a-eada-4a2b-9b79-eb4043814e4f | Minutes of this meeting to be submitted to the Nominated Authority.
| textbox | ec945db2-af71-41ca-8834-5e8bb4e069ae | Enter: Teambinder Correspondence Approval number
| note | 5427d97f-467e-4234-8cd5-240a693775b3 | ---------------------------------
| note | 4993c266-25cd-445e-9c39-dd96651087dc | METHOD: Document Review
| note | 6f85f4f1-297b-47f8-ad60-334d0a0e38c7 | ---------------------------------
| note | 1f5b67d0-af36-4fe7-aaad-47411ec36647 | FREQUENCY: Once, for each product, prior to placement of product
| note | 3bc250e8-1466-46f6-b12a-c7320a8d5773 | ---------------------------------
| note | da01043e-43bc-45c0-9129-856be5e395e0 | CATEGORY: HP
| note | 9c04615a-1673-454d-aefe-9c39fc66e2b8 | ---------------------------------
| note | cd922ace-9825-4991-ab07-3f20aef0c003 | RESPONSIBILITY: Nominated Authority
| note | fb252a55-e9c3-4763-97b8-ce26bd42565c | ---------------------------------
| note | a2090e0d-b23b-42d3-848a-971e31926290 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 85c641a1-0c6c-40eb-b9fe-22203023f47a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 Contractor Competency
| note | 8ff33e61-e2c9-49ff-bd83-8777481913c9 | REFERENCE: 689.05
| note | d7c44d82-c8a3-4a63-8188-48ee2ec5abd9 | ---------------------------------
| note | a46106be-e95a-4e54-8102-699313987e1e | ACCEPTANCE CRITERIA: Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application.
| note | c0261025-19ff-44b1-b7c8-fe0888d2aba3 | ---------------------------------
| note | 43131a24-b012-447b-9fb3-a3361ea19289 | METHOD: Document Review
| note | 121cd89b-e3a8-4d75-9e1f-cd1f46d53b3a | ---------------------------------
| note | eb8facd1-045d-4954-819d-35642e253b85 | FREQUENCY: Once, for each personnel, prior to starting Works
| note | 0dfbf1b2-1ce5-4cfb-a6ca-0cd9f766110f | ---------------------------------
| note | a44f77f6-e78c-4865-9c21-7eadb7834e9e | CATEGORY: IP
| note | 0f214849-f2e3-4503-9977-fcc5b22a29d7 | ---------------------------------
| note | 32613ce0-d01c-4bb5-847d-c8b7a00d2784 | RESPONSIBILITY: SE/PE/SPE
| note | 047dfc37-edfe-4fd1-998c-1ca23b905cf5 | ---------------------------------
| note | 04c9a30b-74b5-40c4-8882-91d889cd5c6a | VERIFYING DOCUMENTS: This ITP
| textbox | feca91da-f544-4109-8596-e3ced1aaecf7 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 5.1 Surface Preparation
| note | 65c9fe26-5dfe-4143-bb3f-4cb60f3b9870 | REFERENCE: 689.08 (b) , (c) & (d)
| note | dbc8742a-ecc1-4d96-92c7-492fed89a27a | ---------------------------------
| note | 5a2b9b0a-d709-4714-bb2b-27e1b78f1d53 | ACCEPTANCE CRITERIA: Concrete broken back to dense, sound concrete.
| note | 397ac08c-ca81-40e7-8b9a-9b388eff9fed | Any exposed reinforcement witnessed.
| note | 179ac2b3-d446-4f2d-872f-5b1c1d14f04d | Resulting cover allowance:
| note | e0cf811a-9ab9-4dce-9b17-a24c5de15e4b | Exposure classification A and B1 = 20mm minimum
| note | 9b3ed7e1-3c50-4b59-9857-2381040782d1 | Exposure classification B2, C1 and C2 = 50mm minimum
| note | a5151b57-f965-44b8-8a06-84a047366a3d | Where applicable:
| note | abe4f6eb-ac88-4d80-bd56-63ddcb81dbec | Reinforcement primer applied with no or minimal concrete coated.
| note | 7012e0e1-1535-49f7-ba8e-ea213bb78e60 | Substrate bonding agent/primer applied, waiting for it to be tacky.
| note | 8e1440bb-04fb-4c44-82b1-47f4ba8a0000 | ---------------------------------
| note | 404abd1a-87c6-489d-93b4-96eb77fc8452 | METHOD: Measure, Visual
| note | 5e1b76c2-c0a7-4500-8194-16c783e65a5a | ---------------------------------
| note | da5948fd-6fca-4bcb-95dc-478998634baf | FREQUENCY: Each element
| note | bd2618a9-5a29-40ff-a087-90bb8fb1f410 | ---------------------------------
| note | 5b17a0c2-ea73-477f-a61d-18113b31d8e9 | CATEGORY: IP
| note | c223d711-b1fc-4b45-bc65-a57fd49d49c0 | ---------------------------------
| note | 8dff1ae9-a668-4042-9286-8609e2ab1107 | RESPONSIBILITY: SE/PE/SPE
| note | 3332dbbf-ae12-4a0a-bafd-e08c1f52e44e | ---------------------------------
| note | f2290790-79ec-4dab-8ab8-b5e2f456e71d | VERIFYING DOCUMENTS: This ITP
| textbox | 6e4818ae-f75b-4940-9ee8-9ea048f32536 | Date Completed:
| checkpoint |  | 5.2 Pre-application Inspection
| note | 7a47ed7a-0373-4e8d-9164-21a33fb348b7 | REFERENCE: 689.08 (e) (i) & (ii)
| note | 9b01c8b0-3eee-480e-9c33-c2daa3889bd4 | ---------------------------------
| note | 1cac1c80-5042-4248-a7b6-ff7db6cca758 | ACCEPTANCE CRITERIA: Reinstatement of prepared areas shall not commence until:
| note | b4538e8c-839e-480a-81a1-215fc36e2fd5 | i. a joint measurement of the repair area by Contractor & Nominated Authority
| note | 05b78ac9-43b0-49a4-ad1f-5c886b817012 | ii. evidence the area conforms with specifications
| note | ea261931-2445-40b7-8d6c-c1ce56c0a00f | ---------------------------------
| note | 5a72362b-3d73-44bc-a455-580bb9ffd397 | METHOD: Measure, Visual
| note | cd2f2d1f-4dcf-4aa2-9b01-db35b0787ba8 | ---------------------------------
| note | bb5a00e3-6e82-4a0d-919d-4c4d28f5af78 | FREQUENCY: Each element
| note | 291fbff1-53f3-4146-aa4b-b47fc567e716 | ---------------------------------
| note | d938974a-7bd3-4676-a543-bd90af3a635d | CATEGORY: HP
| note | 9b939b94-75b5-4999-a306-902416320898 | ---------------------------------
| note | 1855575c-2d7b-41cf-aa1a-b004abe6eeac | RESPONSIBILITY: Nominated Authority
| note | 89610fcc-701f-40ce-a30c-afa204059439 | ---------------------------------
| note | ae8face5-ccc1-4f0d-a338-c7d62199efc5 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 8c06b87e-eefe-460c-a789-b184cc97e2ed | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.3 Material Reference
| note | af6d7cf8-3eaa-4390-9d4f-1d63e07b6c8a | REFERENCE: 689.07
| note | fb0f433f-78c0-453b-8be3-c88aad5fbbb7 | ---------------------------------
| note | 75698d75-1ea1-4472-8397-12877ad02737 | ACCEPTANCE CRITERIA: The following information shall be provided with each batch of material, clearly marked on each bag:
| note | 3b7f9172-507e-47eb-832a-82503a72681a | Manufacturer's name and address
| note | 8c90f948-76da-4e52-9f3f-91386feae24d | Product reference
| note | be777465-2fd9-4b81-9d08-2fc6c8700e82 | Batch number of identification
| note | 9c949e86-63e9-4458-a8d3-6d835e4e9ba7 | Quantity manufactured in the batch
| note | abcbc27f-0b0d-4a2e-84ac-35d36b2885b3 | Certificate of date of manufacture
| note | ee534695-fbdb-45c2-bf65-a546561bea25 | ---------------------------------
| note | 27319e51-a0d0-44b4-8172-bf7550c1907c | METHOD: Visual
| note | d9486c46-7b50-4ded-9cb4-dd8573dd4852 | ---------------------------------
| note | eb86ec47-90d4-456e-a4ba-fa535e3cf516 | FREQUENCY: Each bag of product
| note | 29058753-e4bf-4839-863c-b23ea02346b9 | ---------------------------------
| note | b4b6abdb-91f2-45df-b687-7f3717f1b5fe | CATEGORY: IP
| note | f2d3fdcd-bc53-4ab5-ae41-ec3aa17801d0 | ---------------------------------
| note | e29b6a28-5aa8-4598-a68a-8deb3eb6a8c0 | RESPONSIBILITY: SE/PE/SPE
| note | d4a05a32-af7c-48c4-959e-d98084999d16 | ---------------------------------
| note | fea4ff34-66fb-441d-8411-6460dca59e1b | VERIFYING DOCUMENTS: This ITP
| textbox | 1adb271b-3d7a-4f3a-ad10-42f93765741c | Date Completed:
| checkpoint |  | 5.4 Weather Conditions
| note | 926338f2-a915-4f71-b036-bbb534b47019 | REFERENCE: 689.08 (e)
| note | 4f329fef-7480-4b34-8f98-f1c27d63fbca | 610.17
| note | 01fcd892-c42d-41a6-bdcc-64e19e023a30 | 610.17 (a) & (e)
| note | 2a836a4f-3dbc-4be8-b93f-5f0f9c366e19 | Table 610.171
| note | aa989a99-1730-4dcb-90b2-45f6e981638b | ---------------------------------
| note | cdec453e-62e9-4239-bfd4-a3144c4bed23 | ACCEPTANCE CRITERIA: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | 8faa8a80-5c3a-4b88-bb48-9968152bf0a0 | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | 0809f5f5-40b5-4d7e-905a-24404ea17018 | ---------------------------------
| note | 0cc2f8f1-f508-4e0d-8023-5d9e6c5623f7 | METHOD: Measure, Visual
| note | 253acfd7-141f-4141-a828-f1abbba23db0 | ---------------------------------
| note | c0b06e01-590a-461e-b39c-3928d5d72fc2 | FREQUENCY: Each element
| note | 4d24f523-beff-4deb-acb5-800ab4fbeef6 | ---------------------------------
| note | 14606707-8113-463e-af38-cba6e37ece8d | CATEGORY: IP
| note | 18c55dfe-a8fe-4706-9deb-fe913fc9519c | ---------------------------------
| note | df9bf0a1-be71-4e63-871d-5cfd7816a104 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 1a6798c2-e113-45b6-bfd7-aae8ada9f6a6 | ---------------------------------
| note | deb088dd-3982-4907-a268-e403718e96ff | VERIFYING DOCUMENTS: This ITP
| textbox | a3c2c429-e37b-47b3-aa10-ccfeadc46f0a | Date Completed:
| checkpoint |  | 5.5 Mixing Product
| note | edef4e66-acea-47bb-979a-4b1bf8a6d459 | REFERENCE: Product TDS
| note | 0b696145-f58a-49a8-8b2f-47bbdbcbdec0 | 689.08 (e)
| note | 2d93369d-b6ed-440e-8203-3b45d2af7838 | ---------------------------------
| note | aa018888-6e38-4aea-9505-a5de7d8e5def | ACCEPTANCE CRITERIA: Size of mixer should match the application.
| note | 0c553581-6b48-42fd-91f5-9ffccff1af26 | Only whole bags to be mixed with potable water.
| note | fde322c9-08db-4a6a-a366-9840df6dbfec | Volume of water matches the required amount for the consistency required and accurately measured.
| note | 04eed40c-ae0e-4b61-850e-14f66574d922 | Product poured into the mixer slowly.
| note | 580a239e-8790-4777-8c2c-9146c85b65f3 | Mixing time as per TDS so that a smooth, even consistency is obtained.
| note | dfb1b968-54a9-42d4-95b2-9aa4daa50cc4 | ---------------------------------
| note | c4589e41-15ac-4109-a8f1-d298f21e50da | METHOD: Measure, Visual
| note | dcc4a2df-2d8f-4832-b924-016a6ab3551f | ---------------------------------
| note | b9306c29-23ca-40bd-9e1c-fe7415cca73f | FREQUENCY: Each batch
| note | e63c8182-19d4-4315-8281-d21280e3c831 | ---------------------------------
| note | 3b30a659-2d95-4a57-bb2c-e0487651c21c | CATEGORY: IP
| note | effe935d-9e12-4b93-acdf-0c8dc3b4d549 | ---------------------------------
| note | 897cc8b8-65b9-44ec-956f-470078bf2997 | RESPONSIBILITY: SE/PE/SPE
| note | 9fd424bf-cbf6-4a30-ba79-6ac479f81972 | ---------------------------------
| note | c10e1b16-42e2-4875-b518-ea9fc116d89c | VERIFYING DOCUMENTS: This ITP
| textbox | 7c16b831-f6fa-48ac-b981-caada1c38126 | Date Completed:
| checkpoint |  | 5.6 Product Testing - Compressive Strength Cubes
| note | 55e836c1-fcdb-43a6-a0ec-122022647b58 | REFERENCE: 689.12 (a)
| note | 63fe7cb0-c9d4-4105-9f03-3e5aa687acde | 610.28
| note | 344d28fb-6b59-4acf-81fb-5219bee61fc5 | 610.33
| note | 32a10c23-9317-4930-9388-ea493ae652d4 | ---------------------------------
| note | 9eb30fdc-2bf3-4c78-9d9f-82f922e0990e | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
| note | c19689f0-2200-4998-be03-eb20eda4dd4d | Testing is be in accordance with the following frequencies:
| note | 855aa999-b8d5-44f4-987a-2ae86b3eb0f0 | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| note | 8619dca2-f5fc-4277-8481-c5869505e669 | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| note | a1218f86-8295-4c9c-9168-458cbc3ce308 | ---------------------------------
| note | 9818492c-645e-4535-926c-1fd1ee9b1797 | METHOD: Test
| note | 2dbf1a84-6a89-4ea4-bad5-fb2f6495c93f | ---------------------------------
| note | 073a8e1c-c748-45f6-a822-bc4c282f6261 | FREQUENCY: Each element
| note | 762037e2-767e-4f38-b7e1-59fe1c9e48f4 | ---------------------------------
| note | 97da932c-a1bd-4683-9df3-8f551082da67 | CATEGORY: IP
| note | bb2385d4-928e-4207-9ca3-346bc49f79b0 | ---------------------------------
| note | 2a9e7c7b-4386-45e6-9381-e585867a06bb | RESPONSIBILITY: Tester, SE/PE/SPE
| note | cd8d07f2-2aeb-402f-b932-1b13279a3f47 | ---------------------------------
| note | d41360ea-1d50-448d-9234-de2238cd570b | VERIFYING DOCUMENTS: This ITP
| textbox | ad889ff0-a2f2-4be8-a0ea-42383f0024e2 | Date Completed:
| checkpoint |  | 5.7 Application
| note | 55744848-a62b-4622-9e64-9d5e51028339 | REFERENCE: Product TDS
| note | fc051730-3795-47e2-b75f-c8cf3c925223 | 689.08 (e)
| note | 0a9db5e6-d9ea-424c-b86f-a3cef358763f | ---------------------------------
| note | 77825dc1-105b-475d-9c2d-dfe20ec89fa4 | ACCEPTANCE CRITERIA: Where a surface primer has been used, ensure that this is still tacky - if not, reapply and wait until it is.
| note | 012ca93f-33d6-4488-832a-1c2c121a3695 | Where formwork has been used, ensure that this has been coated with release agent to prevent bonding to the repair material.
| note | e8e9f023-f41d-4ea7-9f4a-6b7380fa3176 | ---------------------------------
| note | 3ee6e33b-46c1-4ab6-895f-6d315c7ff60e | METHOD: Visual
| note | bfcb23b8-9536-498e-835d-96a22cac1fc8 | ---------------------------------
| note | ef156230-cb67-48b9-af74-f811e857f822 | FREQUENCY: Each element
| note | 8eebe25a-c12a-42c6-b4e8-f04c257f6fad | ---------------------------------
| note | 45346493-8efa-4918-86f2-3e5233234c8c | CATEGORY: IP
| note | b59d06e0-b6ce-4ec6-8aec-28017ae839bc | ---------------------------------
| note | b6169c6a-9787-4064-b221-90208d429e14 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 62da5176-57bd-4148-a2b0-22fd77a3a027 | ---------------------------------
| note | 5d0ea684-db6d-41af-9456-81b0ef561e44 | VERIFYING DOCUMENTS: This ITP
| textbox | 8fae63d0-6521-40b2-803f-c64d4ee3e067 | Date Completed:
| checkpoint |  | 5.8 Surface Finishes
| note | e098bce9-2741-4911-b226-a2ecf92ae908 | REFERENCE: 689.10
| note | a43d4644-6a95-4180-8988-e3497fff3559 | ---------------------------------
| note | db8660db-4c39-44f7-a75b-5c38ef059193 | ACCEPTANCE CRITERIA: All surfaces to match the surrounding surface finish by use of steel forms or steel trowels.
| note | 48895bf0-ba49-4182-a390-dcf9e66970f8 | Craze cracking to be limited with no cracks at the interface between the substrate and patch, however, a maximum crack width of no greater than 0.1mm.
| note | 3b2b9227-1388-4621-9a84-36c9e2d7f292 | If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
| note | c9720c40-c26c-47c8-a670-4a7426b82c31 | ---------------------------------
| note | da29ce77-84c8-44eb-90d0-bfc4d77cb7b8 | METHOD: Measure, Visual
| note | f132185c-1f07-4c37-ac30-baf6b0cb0345 | ---------------------------------
| note | 87f6033b-4b82-40d1-90f7-bb15ff916e4a | FREQUENCY: Each element
| note | 9b5ae303-50c1-49d4-898c-1b4eeda83319 | ---------------------------------
| note | 6f34bbbf-925b-4b17-b991-08a3ee3a9e19 | CATEGORY: IP
| note | 174ed91f-e930-4f54-9100-88eae5c7580c | ---------------------------------
| note | 1f560b0c-43ea-4406-bce6-e2c606344bd8 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 12281a97-9455-488f-8d15-ec6cdd128cf9 | ---------------------------------
| note | a6b96c3d-ff9b-4e91-99a7-8291f75af342 | VERIFYING DOCUMENTS: This ITP
| textbox | 01eb7dc5-24b3-42ec-8f23-24f0c223d4cb | Date Completed:
| checkpoint |  | 5.9 Tolerances
| note | b735b7aa-fb64-4375-b284-ac91b4e0d417 | REFERENCE: 689.11
| note | 3673f47a-a45e-4dfb-a6cd-57ad15ca4710 | ---------------------------------
| note | 20233b40-5b51-422f-8e54-feed46f9ba6d | ACCEPTANCE CRITERIA: Tolerances applicable are:
| note | 9e820638-aecb-4476-9d88-08f6b9590608 | Edges: ±3mm
| note | f9d1ddc8-048a-406d-b295-a83a2e8557f0 | Surfaces: ±3mm
| note | eea2eaf2-269f-49ea-82a5-cf11cb2f16ed | Maximum allowance for irregularities: 3 mm with a 2 m straightedge
| note | c78d5efe-d0c5-442c-962c-65da6fadfdca | Maximum allowance for unevenness: 1 mm with a 300 mm straightedge
| note | a55b6d98-e8a0-45b4-8633-1946eba4792a | ---------------------------------
| note | 5fcc097d-e705-4adf-abbc-cc95a69efa58 | METHOD: Measure, Visual
| note | 06bb2a58-99bc-4797-8d2f-0e4d1dee90da | ---------------------------------
| note | 2841fdee-1073-4bba-be24-344d48538283 | FREQUENCY: Each element
| note | 55c8ae9a-0029-4615-a58a-52e98ed516c1 | ---------------------------------
| note | 2393641b-64de-4780-a363-e5fd279bdbfa | CATEGORY: IP
| note | 953d1582-cc25-4514-ba00-ca10c01b406c | ---------------------------------
| note | 112f5bf3-6caa-426c-942b-17c3a88cf2f6 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 05bfdb14-a990-4962-8b45-24208f5c93d0 | ---------------------------------
| note | a22240a0-5ec7-4feb-8dd9-ec6338e99fb1 | VERIFYING DOCUMENTS: This ITP
| textbox | b0a3988b-0ec2-41d7-b402-0950ddcd758e | Date Completed:
| checkpoint |  | 5.10 Curing
| note | 1d17263f-6ad5-40d1-86e6-9a40a747e544 | REFERENCE: Curing Methodology
| note | 02e7af74-bd47-4f35-bb44-79ae08de0926 | 610.23
| note | 0c7d1427-d6dc-4c8f-9800-c53b83adce37 | Table 610.231
| note | 3b792212-7667-44f3-a5a2-8db580861974 | ---------------------------------
| note | 34f7d206-271e-4dd3-912f-3433097e5502 | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
| note | c4e33a93-eb9e-4710-b157-2b96c5ea3fe4 | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | b8cfda32-867f-4483-820b-69e82072ce54 | ---------------------------------
| note | 120a2ffd-89ee-4c89-96a4-0c0b2782898c | METHOD: Visual
| note | 3bdba693-06d3-4db9-a375-c5eb3a03c5c2 | ---------------------------------
| note | d0375e93-851a-4ec4-989a-2df6d2fd380e | FREQUENCY: Each element
| note | 502584f4-9e88-46a2-9af8-5dc2fe1d8d75 | ---------------------------------
| note | 024ebbfb-e88a-4e5f-a074-76c6cf6856b7 | CATEGORY: IP
| note | 661aecf1-c135-4809-92b3-a4b22a73055e | ---------------------------------
| note | a73c3732-4941-450e-ba41-c4c8af32ef6c | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 83f9b9a9-98aa-476c-b118-bb902d94e83a | ---------------------------------
| note | 626ede88-2ef1-45f2-b54e-4113c2c64da9 | VERIFYING DOCUMENTS: This ITP
| textbox | e869795f-8759-407e-918a-7f3a3ce907f6 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Compressive Strength Test Results
| note | 1d80c81a-593c-4532-b82d-46e1292ce86c | REFERENCE: IFC Drawings
| note | 505c3499-f333-499e-a6e8-ae37f9bd24aa | Product TDS
| note | df972ca4-8651-4c31-a5c2-a191314ac553 | Table 689.061
| note | 22097c79-a6bf-430d-a749-fe0394441abc | ---------------------------------
| note | ba657202-a4b0-402f-a2e2-d6836ab62090 | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
| note | af3d1d67-b1be-4d3a-b69a-d028ca9ffac4 | 28 day compressive strength per sample comply with the design strength.
| note | bfdc44da-8395-4e2e-9b71-a42bb2553d68 | Attach: Compressive Strength Test Results
| note | 0acd5c03-6c5a-46e8-8103-8e4c75864e32 | ---------------------------------
| note | fd8dea1c-964a-4a60-8244-3bef5c2f73aa | METHOD: Document Review
| note | 3d79aa8e-a18f-46be-8899-638741f3f0dc | ---------------------------------
| note | 09a4dd9d-d5e8-445a-b0ac-e618495a2d03 | FREQUENCY: Each cube
| note | f50ced4d-311b-48ff-b60b-1040c03a3b4b | ---------------------------------
| note | da0a28f6-fafc-4376-aea9-f6e6765e415c | CATEGORY: IP
| note | 285c1bb9-4215-4a85-b205-57246fb18bd4 | ---------------------------------
| note | 5058b43e-4fa2-46c9-b264-06a819d59329 | RESPONSIBILITY: SE/PE/SPE
| note | 3ad7d01b-d8c9-45e3-95ad-ed87fe6b2306 | ---------------------------------
| note | 16241405-8a6d-456c-9a62-fadd27512abf | VERIFYING DOCUMENTS: This ITP
| textbox | 8b39d5e4-7988-4804-aac2-70987cc36081 | Date Completed:
| checkpoint |  | 6.2 Non-conformance Report (NCR) Closure
| note | 1fc9d1fd-0f03-4f19-80ad-adab513a1085 | REFERENCE: MRPA Quality Management Plan
| note | 540041cd-0882-465a-b69f-9567185034e4 | ---------------------------------
| note | a5f1acb7-d490-4b81-a9e3-c6ee7e70fddc | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | b60c104b-6178-4b14-b721-5a79de45e5d8 | ---------------------------------
| note | c30178ce-e27d-4037-9126-15536dbcb388 | METHOD: Document Review
| note | cd7db235-5bbc-4066-93d8-38fe0869b29f | ---------------------------------
| note | e26214e5-59ad-42da-a45c-e6858d461054 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | eb190034-591d-417d-91f6-dc87338d8de3 | ---------------------------------
| note | e7ab022c-3358-400b-a571-5bc1afc899f1 | CATEGORY: HP*
| note | 7b247b39-6a6f-4fab-8b0f-8f2426ae20cb | ---------------------------------
| note | cd10105b-4ac7-4026-bcc3-caf5a4a267a7 | RESPONSIBILITY: SE/PE/SPE
| note | 04c79f0a-b99f-477b-b254-59b18cf4231c | ---------------------------------
| note | 087dfe87-3295-4d28-9e8f-055eb6ce77c0 | VERIFYING DOCUMENTS: This ITP
| textbox | 1618f0a3-7f71-45bc-b829-5b9316d74d5e | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | e77793de-75a6-4239-b274-168ef643440c | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 855ee6f2-ff42-48a9-919f-72ca61a34f47 | Name:
| textbox | 2f3836e7-62a0-4759-90f8-724792e2a9e5 | Position:
| textbox | 7328fe71-68af-4767-9dcd-bf18dea22e56 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Ground Anchors-Soil Nail Rev 0 | itp | ITP-STR-Ground Anchors-Soil Nail | 9b2cfd66-313e-4973-a34e-81785dd5b19b
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | acb1603b-561c-5812-a073-f95bc273cf42 | Document Title: ITP-STR-Ground Anchors-Soil Nail
| note | b04ec975-346f-5d70-be06-924fd785afbd | ITP Description: Ground Anchors-Soil Nail
| note | 6529e7d8-975e-557e-985b-3bc9b94b173c | Document Number (in Teambinder): n/a
| note | c1e8f81b-670c-5807-8b0a-3472c52b33cc | Discipline (e.g. CIV/STR/RAIL): STR
| note | d2ed2c27-4400-5d09-84fe-bedc55f253bd | Revision Number: 0
| note | 5159e25e-0f4b-5aca-b6d3-70653cfc2bd4 | Revision Date: 10/05/22
| note | 14c1b020-bbc2-5e18-af09-3e132bc66c9d | ITP created by: Furqon Edwars
| note | 21d4a901-47dd-5dee-a0a0-ee9ae6c7b515 | ITP approved for use by: Romualdo Magpantay
| note | c8fcbd5d-a9fc-50f1-aaa7-1bde146f5b5d | 1.1 - Non Dependent - VicRoads Section 610 June 2019
| note | 09383f85-f1b7-573a-b43c-bf597f494d3d | 1.2 - Non Dependent - VicRoads Section 611 November 2018
| note | 57a4ff9c-3357-5b89-8ec3-68b37e28544d | 1.3 - Non Dependent - VicRoads Section 683 April 2019
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1- Design
| note | e72249b0-0d72-5c37-bdd5-9e4056b37544 | Reference - 683.04 683.04 (d) (i - xi)
| note | 44579dd3-1728-5a61-8426-ea7a2e9bc4e0 | Acceptance Criteria- The Contractor shall submit construction drawings for review by the Superintendent prior to soil nail installation.
| note | 058a70ea-1fc3-519f-9510-3fb9bff08f12 | Method - Document Review
| note | a15ca02c-d2e6-5451-bbc7-1fc8708cec9c | Frequency - Once, 4 weeks prior to installation of soil nails
| note | 0acb4823-407e-5749-ada7-3426e73e0cf4 | Category - HP
| note | 232774ff-5915-527f-85b0-f5267641aa7b | Responsibility - Designer/ Consultant
| note | 7d7f8f70-3b73-53ff-ab51-4e2d88e47660 | Verifying Documents - ConQA Hold Point Release
| textbox | abf05e87-3d1a-54b0-b56e-55ec7459d07c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2- Soil Nail Testing - Type I / Design Verification
| note | 25d4e7de-43c6-58c3-8bb3-a8558ef072f5 | Reference - IFC Drawings
| note | e5c5802e-3e07-5e98-89b8-b1863777678b | 683.12 (a, c - d)
| note | ee9f2437-9a20-5816-8ba0-0e9e5bacc8f2 | 683.13 (a - b)
| note | d07601ac-61c5-5c8a-859b-7bdf60b3e74f | Table 683.161
| note | 2b4f6eaa-73b1-5362-87a8-0b2389d6cc06 | Acceptance Criteria- 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
| note | 8f535b54-bd7b-581e-b1a3-3d4f93448911 | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
| note | 12b75238-a8f2-52da-8934-62a5c196541b | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
| textbox | 73b1bcdf-d671-5564-b5ac-c251bc63f00c | Teambinder Approval number
| note | 02de78ed-8843-5bb1-a3be-9a2cec8dd8fe | Method - Document Review
| note | 571d1663-9620-5bb7-8083-7cc755dc248e | Frequency - Once, 3 no. tests per soil/rock type
| note | 7d98ed88-14b2-5325-bf6d-945e3e7ebcf4 | Category - WP
| note | 80089141-0c9c-507b-8a81-49b7bf7431f3 | Responsibility - Testing Technician/ Consultant
| note | ecda9d0e-4e16-5979-a76f-86c358c744ac | Verifying Documents - This ITP
| textbox | 841ab862-25ff-5565-8559-aed1841e409a | Date Completed:
| checkpoint |  | 2.3- Testing - Type I / Design Verification Test Failure
| note | df5d6dfb-1461-5e29-8fb9-ed984cd40035 | Reference - IFC Drawings 683.13 (b)
| note | dd0d2cbc-ce29-505b-9ee2-a62561c99b06 | Acceptance Criteria- Where applicable, if any Type I / Designer Verification Test results fail, Type II / Sacrificial Testing & Exhumation Testing shall not proceed. Where this occurs, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
| textbox | 0154746b-8d7e-5522-9c82-70fce19696e7 | Teambinder Approval number
| note | 19743cb2-222f-565c-b54d-b12ab644b581 | Method - Document Review
| note | eafa75a5-aee2-5d6b-9ee7-b8a78718e3f9 | Frequency - Where applicable, per failed test result per soil/rock type
| note | dffcf3df-d752-5bfd-99a7-64cc66282a48 | Category - HP
| note | 7491ed1d-b50d-5606-bba0-3a462240118c | Responsibility - Testing Technician/ Consultant
| note | 79a7c82c-d54c-515f-bb27-7caa0b813368 | Verifying Documents - ConQA Hold Point Release
| textbox | 1ff05bc8-fcb0-5bef-aa90-f76cc931f8cc | Date Completed:
| checkpoint |  | 2.4- Testing - Type II / Sacrificial Testing & Exhumation
| note | ff9e9692-0a30-5aff-953c-8117830fc500 | Reference - IFC Drawings
| note | c42beb3f-5352-5f1e-b4bd-d3c460a3b27b | 683.12 (a, c - d)
| note | 6b879c1d-9630-5124-878d-47c369067b00 | 683.14 (a - c)
| note | 8e86c92e-deac-5475-840f-f7b4e7773af1 | Table 683.161
| note | f5907918-da3a-590a-9918-6490515f07c6 | Acceptance Criteria- 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
| note | f9b8b099-4b7d-5bae-8c00-af02aeb20822 | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
| note | 1538f0b3-e14c-5e52-97d4-345a796516a3 | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
| note | fca2a31f-88c4-5089-96bc-48ac066f5875 | Exhumation of the sacrificial nails shall be conducted in a manner to avoid damaging the grout column and cut into 500mm lengths with ends photographed to prove grout cover of the nail.
| note | 0a914294-1da1-5d63-af56-a6f02f4606ea | Note: Dispensation from Type II testing in rock can be requested if:
| note | 0e197296-84e5-5d3d-acc3-e92890b467f8 | i. All Type I test results pass in that material
| note | 6726f049-6c17-5bb6-b48e-e75df5068b09 | ii. The material is not weathered more than slightly weathered and/or less hard than a Rock Quality Designator (RQD) of 50
| note | a4b4524e-392b-52d2-b683-28ab9dec4414 | iii. Encapsulation sheaths are used for steel nails
| textbox | 660225b5-6de0-5edb-8775-edb60e78310f | Teambinder Approval number
| note | 842ac650-4174-507e-af09-6ca5dbc7b193 | Method - Document Review
| note | 5d0ec4e7-dd27-5438-bdbf-62f9cae47e72 | Frequency - Once, 3 no. tests per soil/rock type
| note | d634f367-f3b6-5b55-ab7c-a07cf19346a8 | Category - WP
| note | a4ff1455-bca6-5aad-811a-15cccbdddeeb | Responsibility - Testing Technician/ Consultant
| note | af231946-9696-5311-adf9-2b9c6d80daa7 | Verifying Documents - This ITP
| textbox | 154e640c-a11c-5cc9-ba68-71563b7c270c | Date Completed:
| checkpoint |  | 2.5- Material Approvals and Certification
| note | c010e994-9917-55e0-b9c0-d5b48c3c6599 | Reference - 683.06 (a)
| note | 2c620ff6-4b5b-5d30-9043-e9fba557968b | 683.07 (b)
| note | a41235ff-2e99-5271-b24f-7422cb063d6a | 683.11 (a)
| note | 1f405d46-930b-558c-b67a-0137d033f2cd | Acceptance Criteria- Bar shall not be installed until the test certificates for each batch of bar have been submitted for review by the Superintendent and written approval for use has been granted.
| note | 8858f515-91b4-5d8c-a7e8-f7b157dd1ae5 | Coatings for corrosion protection on all steel materials shall be either:
| note | 0896bf16-d9e9-5e57-97e1-12dbef0473e8 | i. Galvanised to thickness as per AS/NZS 4680
| note | 0dcdb41d-a8f6-5ca5-87ca-2419d197efe4 | ii. Thermo-diffusion coated to Coating Class 80 or ≥80µm
| note | 2a5525ae-da5f-5552-bdf6-ebbd117eff85 | iii. ≥80% zinc-rich product with ≥100µm DFT
| note | e1743577-d66a-50a3-a634-f5a2f1681869 | The proposed low shrinkage grout mix design with supporting test results to be submitted for review to the Nominated Authority.
| note | 0a70747f-b6a6-521e-8b3c-b00ce104501c | The following test results and information shall be provided:
| note | 5f9e19a4-743c-5580-96bb-a47434142f02 | i. Water cement ratio between 0.38 - 0.45
| note | ef0526e4-ecf0-5f64-939c-a4ef53cb182e | ii. The chemical admixture
| note | 61542a4e-c8d7-5a07-8df0-97668b4cc55f | iii. 7 day compressive strength test results ≥32MPa
| note | cee1b3c0-f0ed-550f-bdd2-154e2f54a133 | iv. 28 day compressive strength results ≥40MPa (Robinson's Road)
| note | 3fce1877-4fac-5ab8-b414-331e90dca18d | v. Flow cone test result between 10-30 seconds
| note | 8c9050e7-9740-5b01-84be-7929147d0710 | vi. Bleed test result ≤2% 3 hours after mixing, ≤4% at any time and separated water absorbed within 24 hours
| note | 9c547e2a-d3fb-5a86-a566-36e035a2527b | vii. Chloride-ion content ≤0.07%
| note | f36e3540-b547-57a3-8142-7d9e5f79f300 | viii. Sulphate content ≤5%
| note | 0812d6d3-e4bb-5cd2-aa3d-1bc99fc48486 | The grout shall be made strictly in accordance with the approved grout mix design and in the event of changes, re-submitted for review and approval to the Nominated Authority.
| textbox | 23a67463-b80a-5121-979e-1964ee6f19c0 | Teambinder Approval number
| note | 4a889052-9050-5067-a178-d3be3e1c48ff | Method - Document Review
| note | 101fea73-00ee-5b5a-aa32-2e235cfdccb3 | Frequency - Prior to works
| note | d59c5bff-66a9-5c79-b9d5-1c3232e82865 | Category - HP
| note | e6974fa5-f73c-5426-9ccb-83cfaa74fee7 | Responsibility - Nominated Authority
| note | 09e93bf4-036d-5e57-ba94-b476c5d93cec | Verifying Documents - ConQA Hold Point Release
| textbox | aa08c917-3201-5eba-a371-1169c762eca2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.6- Soil Nail Installation, Grouting & Testing Work Procedure
| note | ceede95c-870a-53df-b9b6-2b309cef7299 | Reference - 683.12 (b)
| note | 63ca8c7e-b6d7-5a82-a6ed-bfac4b72ff74 | 683.11 (b)
| note | 94b44130-0471-5493-8480-3e39196b6846 | 683.1
| note | e4d28900-4650-5642-8a31-90c938d642cf | Acceptance Criteria- Soil nail installation WP, fully detailing the proposed drilling, grouting & testing equipment, methodologies and reporting, to be submitted for review to the Nominated Authority.
| textbox | 30fb435a-f18d-5d89-be12-72a16769d3c7 | Teambinder Approval number
| note | 913679f4-f8c6-5185-8da6-dece560aa0f9 | Method - Document Review
| note | 8b767d71-80a8-5df8-852d-45c7564b8c77 | Frequency - 2 weeks prior to installation of design verification testing
| note | 4d53c8d5-0144-52e6-b5cc-da5bd6511d02 | Category - HP
| note | 15a019e8-6171-5a95-8f4e-f0b9821407d3 | Responsibility - Nominated Authority
| note | fdab9943-0faa-5808-932b-140cd0fea56d | Verifying Documents - ConQA Hold Point Release
| textbox | 7cefc8be-90f5-56e5-8427-db86aa529da7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 3.1- IFC Drawings
| note | 9725ae3d-3ded-5687-8d01-6de9b8ea5eb2 | Reference - MRPA Quality Management Plan
| note | bdb814f3-e754-5514-bed2-f5b63021eb72 | Acceptance Criteria- Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | adefb816-243d-521c-850d-3f82179ae233 | Method - Document Review
| note | 757bd1ef-bb1d-5773-b407-f2662bd9a3e1 | Frequency - Prior to starting Works and at regular intervals
| note | ddbaf5e6-bada-5752-a819-9e4513b8832f | Category - HP*
| note | db068d91-67e0-5f30-b0b0-5028a6b653c9 | Responsibility - All
| note | 970eb0cd-0d99-5d5c-a020-69159895da6c | Verifying Documents - This ITP
| textbox | ba4325c5-3817-5805-bc32-8bde16c22db5 | Date Completed:
| checkpoint |  | 3.2- Survey set out
| note | 64629b83-515f-5a49-817c-f6a2f310b136 | Reference - IFC Drawings
| note | cc5e6a8c-c77d-5866-99c8-2526c5586e0e | Acceptance Criteria- Constructed as per Design Drawings
| note | a282c9b7-82b2-51a9-bb59-90915a0a65be | Method - Survey
| note | fee6a7ee-9c3d-5353-ac1c-a5c8b68a88b5 | Frequency - Every Ground Anchor
| note | 8ac8207e-d74b-5ee3-af1c-117041bddda0 | Category - WP
| note | 9f0a981b-a4a0-5dd0-8e98-f2e86dc7c602 | Responsibility - Foreman
| note | 04d2d18b-3b5e-5689-ba55-aa37d43cbf62 | SE/PE/SPE
| note | 2601aee7-8bc5-513f-869d-3f2883c02d6e | Surveyor
| note | 5bda7867-2e68-5e32-98a3-3adde33793cd | Verifying Documents - This ITP
| textbox | e6c8d599-0b67-5487-a4f9-b126eb3c1150 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 4.1- Drilling of Holes
| note | c7b8f8fa-9506-5a7b-bbc5-ba3d19536c89 | Reference - IFC Drawings Soil Nail Work Procedure 683.08 683.10 (b)
| note | db1035ad-8ca1-5261-b69a-283c764afad7 | Acceptance Criteria- Drill holes shall be the depths, diameters and angles shown on the IFC drawings using the equipment stated in the Work Procedure.
| note | 493dac0b-9ad0-5b18-8bf6-2335aec7eea7 | Where casings are used or sheathing is omitted, the hole diameter shall ensure that the cover to the nail is 40mm min.
| note | 80079234-9f17-57cb-af0f-9b3e39378900 | Drilling records shall be kept including any observations or difficulties encountered.
| note | 15fb9fcb-fc42-5843-8f64-6fa86aa1f1a3 | Only air flushing is permitted, no drilling fluid or water shall be used.
| note | 04dba812-1932-51ee-9a53-a67ff51c08aa | Placement tolerances to comply with the following:
| note | c019eb75-b948-56c6-a06b-1b31de558038 | i. Horizontally = ±50mm
| note | 88b71825-04c6-5374-853f-faa7702ed530 | ii. Vertically = ±50mm
| note | ac7d0f8c-4cd1-55a3-a772-ed2e55ef2bec | iii. Alignment = 1:20
| note | 23e71481-8bf8-512c-b5c6-1024fcc57530 | iv. Straightness = 20mm in 3m
| note | 683cd475-7c91-5600-9bf9-86a010648ae0 | v. Inclination = +0° to -3°
| note | 6fc899cb-c789-5edf-9615-52eab23e38fa | Attach: Drilling Records
| note | 1d581696-5586-5c8f-a596-f432eb6bfb83 | Method - Measure
| note | 0518ffa8-b109-55ea-b564-c5bb2b3d6423 | Visual
| note | 6474ff8b-d792-56a7-a7ae-67cc6795f68f | Frequency - Each drill hole
| note | f77076e5-f769-5a56-a815-4e187330d272 | Category - IP
| note | 3311573a-8012-5f9c-a7f5-cf1220497128 | Responsibility - Foreman
| note | 0c4d7d43-a4b5-5635-a27f-7bcd65a2fe48 | SE/PE/SPE
| note | 4d470e7e-7ab7-56c2-aa2f-d111dccb68ff | Surveyor
| note | d3ad5657-811e-5def-8978-f10d70006687 | Verifying Documents - This ITP
| textbox | 8e55b444-45da-5b46-8408-2489de238910 | Date Completed:
| checkpoint |  | 4.2- Geotechnical Inspection of anchor bore samples by the Geotechnical Engineer
| note | fd9a7443-8785-57a7-8952-0ed5de555485 | Reference - IFC Drawings
| note | b87421bc-1a46-5759-8eab-53151ff897b1 | Acceptance Criteria- Alliance geotechnical design representative shall record ground conditions. The bore logging frequency will be locally increased to every anchor should any of the ground conditions encountered are different from what is stipulated on the tension anchor schedules
| note | be7b497c-483c-548c-a11b-cde3794c626c | Method - Document Review
| note | f09d4815-6fc0-57cd-9027-2f1bf869ef07 | Frequency - All anchors
| note | 499cf622-0cf6-571a-8611-dab680a2aa67 | Category - WP
| note | d3b937b5-dc13-5999-b8ad-b4b2d30a128a | Responsibility - SE/PE/SPE
| note | e4700c58-6076-5867-99ec-828fe6e09716 | Geotechnical Engineer
| note | 65b3a655-ab3e-5e3a-aa36-392d100d383d | Verifying Documents - This ITP Borehole Log
| textbox | 7f7728de-ce18-52fb-9ddb-2017432c5863 | Date Completed:
| checkpoint |  | 4.3- Hole Inspection
| note | 747e12f3-45b7-531a-9836-d9fdd73927cf | Reference - 683.10 (c)
| note | 58686fac-d4b3-5224-8be1-a23bed2c3318 | Acceptance Criteria- All drill holes shall be inspected following air flushing and prior to insertion of the nails. Drill records shall be made available for review.
| note | 8f13f021-1dcc-52a7-8d32-f793153059f2 | Method - Measure
| note | 93a1c544-42d1-5405-a372-b8720a3ba8a0 | Visual
| note | 3bcdea57-99ad-5c30-a30e-35ba5d5e2ed2 | Document Review
| note | c308ba4c-6b6d-5ffb-8464-3b28d4777740 | Frequency - Each drill hole
| note | e2859a1f-ed4d-5211-a25d-82622b026ba9 | Category - HP
| note | 4acbce01-07bb-56a1-882c-f60969b6d683 | Responsibility - Nominated Authority
| note | a12709af-a3d6-590d-8e27-9ccf01596229 | Verifying Documents - ConQA Hold Point Release
| textbox | 1a6a60a9-0526-50f8-8b8c-63e9cca69e7c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.4- Nail System Installation
| note | f28729bf-26d5-5d55-a41e-02ccaba095a7 | Reference - IFC Drawings
| note | 070937fb-31f6-59d8-b187-a97ca2a03edd | 683.07 (c - f)
| note | 999d6977-6254-5a21-9385-d58d68ee6625 | 683.09
| note | 82b978dc-89de-5850-ac6d-09c353c8e01f | 683.10 (c)
| note | 2f87dda5-94d1-5158-8a77-7520e9738068 | Acceptance Criteria- Each nail shall be made from the correct material, be the diameter and length as shown on the IFC drawings and be free from defects or damage.
| note | d02352f8-c3a5-581e-8def-e37337207868 | Centralisers shall be spaced at 1.0m max., ensuring that 40mm min. cover is maintained all around.
| note | c0b1e910-6c4b-5833-8d43-c0a8e13c8523 | Steel nails shall be encapsulated by a corrugated sheath unless previously approved during the Type I & II testing.
| note | 77569167-2d91-5b71-afc2-29ce9eabc25a | Steel nails shall be isolated 300mm min. where they are to be in contact with the shotcrete facing using tapes or other approved methods.
| note | c878929e-4d3d-5aae-8c08-275f8d59113e | Grout tube shall be positioned at the base of the hole to displace any moisture present in the hole and to prevent entrapping air.
| note | d58dcd32-8124-5d64-a389-fe5944714d4c | The resulting set up shall achieve the minimum bonding length, projection and be able to resist the forces expected during the grouting operations.
| note | 32d74d3e-0e10-590d-bf1b-e6f1b1d82cf9 | Method - Measure
| note | 6c02fc39-0db0-5681-a4b9-2bd19540fe52 | Visual
| note | e132ba73-2ed5-5029-924d-91624e4d4d26 | Frequency - Each drill hole
| note | a68f78ab-20b7-5653-a869-a88096d591aa | Category - IP
| note | 9602d3ce-b36d-5035-9486-5a43db4f35d4 | Responsibility - Foreman
| note | 610ed5c2-d255-5ae1-b7db-ba43c79854b4 | SE/PE/SPE
| note | 3b015f17-c0ec-5c03-a8ea-8ba349fe1a06 | Surveyor
| note | d293599a-a505-54a6-9086-04f0e291ebaa | Verifying Documents - This ITP
| textbox | 01e106eb-5367-560c-93de-65443bee8dd0 | Date Completed:
| checkpoint |  | 4.5- Grouting of Bars
| note | bdc0ed95-b5f8-5018-ac4f-527f45f5e6c2 | Reference - IFC Drawings
| note | 6376eac6-9193-5b9d-8feb-f25d09316bd0 | AS1478.2
| note | 5e0d85f1-5bb0-5b39-ba94-c2be0d9ae21b | Soil Nail Installation Work Procedure
| note | e5c9375f-4ef2-5399-a7fa-db1ee073cc14 | Acceptance Criteria- Drilled holes can be grouted up to 24 hours after drilling has occurred.
| note | daa826b9-d9e3-593d-95d7-ee72a0830b37 | The bar shall be centrally placed in the hole with centralisers at min 1500mm spacing. Centralisers to be used shall ensure a min 45mm grout cover around the anchors:
| note | 4281217d-d407-5202-b61e-9a116153d6c2 | - Internal, between borehole and sheathing and bar: 20mm
| note | 19dbaf68-a19a-51d4-9973-a38739e23844 | - External, between borehole and sheathing: 25mm
| note | 2d5ed025-ee2c-5fb3-9f46-7d50dd65a096 | Method - Visual
| note | ef55351a-4deb-52b4-b7ec-892ae3862d2f | Measure
| note | b85a0afd-c277-5aca-8142-251106de35c7 | Frequency - All anchors
| note | ca4d5649-399e-5046-ac8e-cffbd34617c5 | Category - WP
| note | 7e3ce156-ee1e-5d02-8748-82f710130ce9 | Responsibility - Foreman
| note | 642253d4-f4c6-552d-b8f8-dc848460bca8 | SE/PE/SPE
| note | 5d99ee70-2bf8-5d94-ae38-897b610c05a2 | Verifying Documents - This ITP
| textbox | beb1f0a8-48d0-5dd1-8b0f-e9011728caf5 | Date Completed:
| checkpoint |  | 4.6- Grout Sampling
| note | d1e1d8e0-5fe5-5d9c-b8fd-0af404ef6f13 | Reference - IFC Drawings
| note | 1c2d1de6-14f4-50e6-b701-60460be58d6c | Soil Nail Installation Work Procedure
| note | 5921847e-6b2b-5bf4-858a-ef4999037cac | 683.11 (a) (iii)
| note | 13343a9f-b64a-5b79-a645-05e543b85ac0 | Acceptance Criteria- Each test shall consist of:
| note | 9ce27422-376a-5701-8aee-205f5f4e671d | i. 3 no. compressive strength cubes = 2 no. 7 day strength, 1 no. 28 day strength.
| note | e156eb94-e8e6-50db-835c-5b2922b3c70c | ii. 1 no. flow cone test = result between 10-30 seconds
| note | 84fecb35-cbef-59cf-96b3-7a920ce9cdf1 | vi. 1 no. bleed test = result ≤2% 3 hours after and shall not exceed 4% at any time with all separated water gone after 24 hours
| note | 7043866c-59dc-5f08-ad13-50b042ba261e | Record: Required information on the Grout Pour Record.
| note | 5935f434-e2b1-5c4d-a40b-1beb38a3b7f7 | Method - Visual
| note | f8e69d47-e9cd-5901-b820-1de96a343680 | Measure
| note | 3de71378-4f24-5bd9-a2cb-bb8ea6f5b76d | Frequency - Each 5m³ or part thereof batched per lot
| note | 4bd3e16e-2bfd-54a0-b57d-649ef5ee8362 | Category - IP
| note | a24109f0-f4d5-57bd-84cf-4c8f22146892 | Responsibility - Foreman
| note | 6fe0704b-fcc3-5ec9-b1ab-175de9fa4f19 | SE/PE/SPE
| note | 6766f6a0-42b5-5b40-83e7-ae985d2b383c | Verifying Documents - This ITP
| textbox | 00bb153e-5b83-5f70-8f8f-3e0eab2bb6f5 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 5.1- Testing - Type III / Production Testing
| note | ab256c55-cc06-5891-9cbe-80fec4cca8a2 | Reference - IFC Drawings
| note | e410aad4-1ce5-5e88-9591-fd10f54d5f45 | 683.12 (a, c - d)
| note | b6fb9243-7888-5e17-8fc9-e24eabb529f6 | 683.15 (a - c)
| note | 554cad5c-a917-57ba-a260-b7ab6049f95b | Table 683.162
| note | 62e05c4f-474c-5c56-b024-694c655104b5 | Table 683.163
| note | 9c1d503e-ef83-5515-8791-8f7fc8b2b4d8 | Acceptance Criteria- 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
| note | 8b7eb1cb-feb7-5e17-900a-ee4f3ed481c3 | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.162.
| note | 682474ef-d560-59a3-aa51-b1e8769abdf3 | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
| textbox | 911edece-56e3-50e6-824b-02752209b196 | Teambinder Approval number
| note | 86abf46d-65e9-5963-a22a-fcf775196c50 | Method - Document Review
| note | 61e7542a-0403-5548-864d-6e445238e043 | Frequency - The greatest value from, 5% of all nails, 2 no. soil nails, 2 no. soil nails per type of soil, 2 no. nails per installation method
| note | 75dad876-344f-5d14-84ca-d4574c806dcd | Category - WP
| note | 45d0d558-d7ad-5e25-90e5-459e63937018 | Responsibility - Testing Technician/ Consultant
| note | f75b1365-09a8-5f2b-8ab7-55d990225c05 | Verifying Documents - This ITP
| textbox | 7279b75a-bf23-57f2-a203-915ab868f133 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.2- Testing - Type III / Production Test Failure
| note | 5238dbea-06bb-5c53-aff2-3c2954190487 | Reference - IFC Drawings
| note | 71f1cccf-5da8-57e6-81bc-bc1dd7dffb5d | 683.15 (c)
| note | 59e19df4-ce5b-5151-a7ab-5c42ef108368 | 683.16 (b) (i - iii)
| note | 2e84ae9b-dab3-5990-8f2d-fbaeb0b235a8 | Table 683.163
| note | ac461083-f07e-5ae3-8b74-d1a694f30dcf | Acceptance Criteria- Where applicable, if any Type III / Production Test results fail, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction. An additional 2 no. nails are to be installed using updated installation procedures, either side of the failed nail and shall pass the load test - note that the loads may require updating.
| textbox | c2ca1d9d-b841-5af3-a22c-20e03407919c | Teambinder Approval number
| note | 297bb47c-85a1-55f8-a6dc-561145f3bd7a | Method - Document Review
| note | 766e5770-c7cc-5b76-8be0-240491098762 | Frequency - Where applicable, per failed test result per soil/rock type
| note | d6ed5a92-6a31-5014-be35-41af3222063a | Category - HP
| note | 5d805ef3-a1b4-5cb8-983c-6e122f939ec3 | Responsibility - Nominated Authority
| note | 18c66ee8-2dcd-5ac7-a2a2-990134f02a53 | Verifying Documents - ConQA Hold Point Release
| textbox | 3be85b93-1dd6-5559-94f5-81687dc4de0a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.3- Acceptance of Test Results
| note | dc4d1ab7-0d09-5c94-aebc-b2eb7998928f | Reference - 683.10
| note | 85e2f1e9-73eb-5c23-a6e4-789c86c20489 | 683.15
| note | 21d094eb-e083-5236-9e91-71272992a3a0 | Acceptance Criteria- Installation of production nails shall not commence until the Type I & Type II test results have passed the design requirements (inclusive of any re-design assumptions).
| textbox | 8235bff3-26f4-5ba4-bbc1-c196264ce9c0 | Teambinder Approval number
| note | de15af8f-8e23-5294-a180-de635589592f | Method - Document Review
| note | d50c707a-974a-5524-9e69-3deae3234af5 | Frequency - Once, 7 days prior to commencing production nails
| note | 03d24bba-009b-50e5-80a2-c38c67c4167d | Category - HP
| note | 33663b52-828e-5a9d-8b9b-575d6d620a88 | Responsibility - Nominated Authority
| note | d77f78a6-b194-50f2-828d-1a8f791786b1 | Verifying Documents - ConQA Hold Point Release
| textbox | 1adc6412-8a8a-550f-9132-879609a95bde | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4- Grout Compressive Strength Results
| note | 61392bef-3b2a-5201-8206-9988ce8d913e | Reference - IFC Drawings
| note | 6cafaf51-954b-5e7a-91dd-6ab5ce49af3d | Soil Nail Installation Work Procedure
| note | 2c8aa063-4740-5817-9003-b966b29701ba | 683.11 (a) (iii)
| note | eea94c89-cc00-5d04-a597-c0b210658fc2 | Acceptance Criteria- 7 day compressive strengths to achieve 32MPa min. 28 day compressive strengths to achieve 40MPa min. (Robinsons Road)
| note | e0784693-9b2f-5508-b3a7-bb0a53f98193 | Attach: Compressive Strength Test Results
| note | b6810662-169f-5711-91e0-385d5d23b48a | Method - Document Review
| note | 9b2a7fcd-757b-54d9-a673-853c1c2117f4 | Frequency - Each cube
| note | 99791e07-740c-5faf-b6b9-ed26d0e18e8f | Category - IP
| note | 1c696913-a1ae-57df-a3a4-a2ab41c783af | Responsibility - SE/PE/SPE
| note | f1e91d60-721f-56a9-8c63-c89810955376 | Verifying Documents - This ITP
| textbox | 889fafd0-95f3-56eb-9e34-3d4906c6ab0b | Date Completed:
| checkpoint |  | 5.5- As-built Survey / RLMU
| note | b7a98a73-3fd0-580b-99a9-302d03393562 | Reference - IFC Drawings
| note | 4ed3d180-6671-5cab-a60f-bce4c0f343e7 | 683.10 (b)
| note | 2e9fbb2e-4ec5-5727-8078-f094c5f924df | Acceptance Criteria- Provide record of dimensional measurements to demonstrate nails comply with the following placement tolerances:
| note | 2d9f540a-f12b-592e-aa20-f8137466bd65 | i. Horizontally = ±50mm
| note | eebf8830-3f10-5f7e-b0e8-abbc895c5ff1 | ii. Vertically = ±50mm
| note | 4d9dacbb-832a-5293-be73-466d42fb0a88 | Attach: Survey As-builts / Survey Report
| note | c97bdb7b-f254-5c61-8d48-3fcb76667fb2 | Method - Measure
| note | 51ae3777-4978-5e36-8284-d49b9027a32b | Document Review
| note | e3cc0bba-a95c-5bc2-9237-2ffcbfd4fe7f | Frequency - Each nail
| note | 3fd60a98-85f9-5668-8032-e83841204538 | Category - IP
| note | bea41b53-6ec9-50f3-9d24-53c3b4c04052 | Responsibility - Surveyor
| note | 9c73157e-e7f7-5f22-a88b-fa665708ecf4 | SE/PE/SPE
| note | c7379c2f-7910-5d15-8f40-e2a5b1d956df | Verifying Documents - This ITP
| textbox | c78e6c28-7fae-51cd-8b2f-616740c41b6d | Date Completed:
| checkpoint |  | 5.6- Non-conformance Report (NCR) Closure
| note | 7321af90-a2a4-57aa-b17f-689ea0df17b0 | Reference - MRPA Quality Management Plan
| note | 2f113118-66b5-55c7-a532-788a4507d6eb | Acceptance Criteria- Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
| note | cc1ee73d-e372-566b-8770-a6f90b16bc5d | Method - Document Review
| note | adc85f38-60a9-58a4-bf35-c7e7624a2067 | Frequency - Once, prior to closure of this lot / element / Work area
| note | e697884d-2add-5a61-ab59-38df453bb0c3 | Category - HP*
| note | 7ff1e808-db3a-54e0-a311-1458a26687ce | Responsibility - SE/PE/SPE
| note | 43885de0-7d68-5067-a9cb-c753fa5025e0 | Verifying Documents - This ITP
| textbox | 226c076d-d0ab-55cb-9cdd-39056ba6dba8 | Date Completed:
| checkpoint |  | Final Inspection
| note | 63915900-285e-5a9c-bc66-0dce6ba7272a | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | f32a396f-b66a-5338-a966-23fe34dbebe4 | Print Name:
| textbox | a372cfbf-705a-5be4-a839-046bc7e1dcc0 | Position:
| textbox | 62fba154-dd98-5de4-8bb3-2083304599f7 | Date:
| checklist |  | ITP-STR-Shotcreting Rev 1 | itp | ITP-STR-Shotcreting Rev 1 | 9f12c000-4af8-4a12-a7f4-1a36cf8c8185
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 41adcd6e-0345-4936-8f19-cedf30d5db01 | Document Title: ITP-STR-Shotcreting
| note | bf1feeb4-1c33-4a20-a5eb-3230369361cc | ITP Description: Shotcreting
| note | 511c9f10-bfd6-4299-92a6-327dc4aff723 | Discipline (e.g. CIV/STR/RAIL): STR
| note | 4829b04f-2721-4c60-bac5-eb5485ce82f7 | Revision Number: 1
| note | 58334cee-f66a-4fc0-8dcb-50313b406a75 | Revision Date: 28/07/2021
| note | 1a87b040-edff-4994-bdf7-8aa7be758b58 | ITP created by: Mike Freeman
| note | 3abdd379-65a8-479e-8454-01894558b2a6 | ITP approved for use by: Mike Freeman
| note | 9a029364-773b-4cc2-a2ff-d219580a1f71 | 1.1 - VicRoads Section 610 June 2019
| note | 457348f9-b1c8-4c5a-9796-745ee40faaf9 | 1.2 - VicRoads Section 611 November 2018
| note | 34a3001a-bc5a-4dca-88b2-9b02531f0536 | 1.3 - VicRoads Section 684 April 2019
| note | 2f47a365-794d-4869-90ff-20ffbe710234 | 1.4 - AS3810.1 2018
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Concrete Mix
| note | d155242e-606a-4869-a57d-f5e7997cee77 | REFERENCE: 684.04 (a)
| note | cd47303e-b761-4842-bd1b-0f0f21d9c412 | 684.04 (d) (i & ii)
| note | 9e3bb931-bbdb-44a0-8365-bd7211b0a3a7 | 684.05 (a) (i & ii)
| note | dac8ee86-68aa-4240-8545-a6f78041d0ca | Table 684.051 684.05 (b)
| note | 54910d22-bea2-4929-b844-1dfc4765f018 | Table 684.052 610.07
| note | 73d087eb-b80e-4e5e-96dc-fc79e31559da | Table 610.071
| note | dc73970b-9f07-42b2-aa1e-d11be0601c98 | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
| note | cfaaff3a-f260-4093-aa9b-77b785667e6d | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
| note | 2794c66a-6bba-4eac-a460-eb19a8e2a7d9 | Maximum drying shrinkage shall meet the values shown on table 684.052.
| note | c4552330-4b80-4f6f-b1dc-e9ebd1923cb0 | Where applicable, steel fibres shall:
| note | b000cf5c-c2c8-4294-9573-d73d5d44e128 | i. be deformed
| note | bc0e4716-bf48-4690-9834-d31c54fb84d7 | ii. have a minimum tensile strength of 800MPa
| note | 66c0225f-bbb9-45e4-ac38-b6ddd89b1aef | iii. have an aspect ratio between 40 and 70
| note | 40839424-00fe-45a4-ad6c-11c63d76f339 | iv. have a minimum dosage rate as per table 684.051
| textbox | cfc99e83-ffb0-4d34-8c2b-4d146cf6a765 | Enter: Teambinder Material Approval number
| note | 70eb4438-6b94-4b1c-9056-1387804fc36c | METHOD: Document Review
| note | b7a80d04-8964-48a7-a6f1-b61cb4deaccb | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
| note | cc123db4-388a-47ab-975b-c129cd9bc160 | CATEGORY: HP
| note | 97396fa8-75ae-4341-8560-3b296b1c2046 | RESPONSIBILITY: Nominated Authority
| note | 701e7db2-0667-4869-a3d3-281a46e3cea8 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 27e849a4-8109-451e-b3f2-2c5c3d29e58f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 ACRS Certification (for Reinforcement)
| note | e8813b7f-45f0-4d57-b23c-f851b6e4ca20 | REFERENCE: 684.04 (c)
| note | df4af71f-3726-4e9b-8d51-ca9d41187736 | 611.05 (a)
| note | 5c1349eb-b0b4-4a10-b5a0-3898514c483b | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
| note | 1e3834eb-ade0-414e-ba79-803b9c2e0349 | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | 189e12ce-4856-4545-a97f-d53149e42895 | Enter: Teambinder Material Approval number
| note | f97fc394-4844-4d13-9dee-f72a1e53df58 | METHOD: Document Review
| note | 06b35ade-c9c6-4729-9685-f75722186135 | FREQUENCY: Once for each supplier, 14 days of award of contract
| note | b415008e-36a5-4dcb-9d63-ec612fdd4750 | CATEGORY: WP
| note | a01a368e-5aef-4ef1-aab7-be303f7aa70f | RESPONSIBILITY: Nominated Authority
| note | 275c1555-87e7-4e12-9d08-118ea972bcaa | VERIFYING DOCUMENTS: This ITP
| textbox | 5107be92-dd4e-4c97-b89f-3996031ad40d | Date Completed:
| checkpoint |  | 2.3 Galvanising (for Reinforcement)
| note | f72b6653-43a1-422f-94e9-4ce99cd36c40 | REFERENCE: 684.04 (c)
| note | cb1edbd0-1f79-463e-83f2-97145c17ead1 | ACCEPTANCE CRITERIA: All reinforcement and tie wire used in the Works shall be hot-dipped galvanised in accordance with AS4680.
| note | ee9216a6-147e-4c72-b364-fc09fe291683 | Note: MRPA has D.o.T direction and approval to use black anchor bars
| note | d7577aa9-17d1-4eba-94db-a77d50a1af18 | See: MRP-016-C-ACD-REP-17-NWA-CSW-0001 (Clyde Road)
| note | eab7aeee-c7aa-4294-9caf-91cfa780b656 | MRP-072-C-AURE-REP-20-DPK-CSW-0001
| note | 3b8ac503-ea5b-4e6d-866f-e2aa1c1c6d1c | (Robinsons Road)
| note | 69e0c471-e124-4580-bf3a-acf44215fa0a | Attach: Galvaniser's Certificate of Compliance
| note | ae4b5b69-8f07-4272-a844-e433aa38bda7 | METHOD: Document Review
| note | 13a90de2-9466-4801-a84f-e65feaba95f9 | FREQUENCY: For each reinforcement delivery from each galvaniser
| note | 732e6a30-dacc-48a1-905b-f9e8a33d4c9a | CATEGORY: WP
| note | bc5dc116-0800-4a8e-9cb4-935d3929c4a6 | RESPONSIBILITY: Nominated Authority
| note | abc47b34-d603-4ef8-bdb6-ebc569711068 | VERIFYING DOCUMENTS: This ITP
| textbox | 7ce58341-ada8-4c86-95e8-7d7f050a61cf | Date Completed:
| checkpoint |  | 2.4 Bar Chairs/Aspros Certification
| note | 6347a3d8-51e3-4f23-a4cb-c6b01ffe4838 | REFERENCE: 610.26 (a)
| note | fc304d97-dc54-40ae-a729-6f4a39dd59a5 | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
| note | c374def6-575f-45b2-b692-5afa0a41986b | Concrete aspros require annual compressive strength and soluble salt testing is required.
| note | 5bcc60ef-d9e1-4c73-95ba-6804338485a2 | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
| textbox | 7b19c8c8-edcd-4e30-b2bd-831b426b8c0a | Enter: Teambinder Material Approval number
| note | 13dbd291-3c2d-4f65-ba65-795e3710e127 | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
| note | 803f5b2c-d2d7-4420-94ec-081ea013f246 | CATEGORY: WP
| note | 5ad100c8-3bdb-4186-9b55-a19e93290114 | RESPONSIBILITY: Nominated Authority
| note | aa80ab91-36d5-4c83-9b6a-74e93fccfada | VERIFYING DOCUMENTS: This ITP
| textbox | 1cbd9911-a2e2-4fab-9cce-dbbde98a8e4c | Date Completed:
| checkpoint |  | 2.5 Evaporative Retardant
| note | 21de5518-5f6c-4b8d-8c77-48aa12de4cb8 | REFERENCE: 684.10 (b)
| note | 1a4a4aaa-d17d-4683-940d-608880939990 | 684.11
| note | 8e7dcd68-808b-49df-82c9-4ec71cf343e1 | 610.17 (f)
| note | f73ef01e-0702-47e1-b910-c3ceb12bdd01 | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
| textbox | 937ec9db-5b85-41a9-bc59-542c5aaa98d5 | Enter: Teambinder Material Approval number
| note | 354ce309-04cc-4bd7-a90e-cadecf78709f | METHOD: Document Review
| note | b1124d79-d596-41ab-bda3-4d14db1d3248 | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
| note | 50c2998b-0063-4543-ac95-1c23762a0182 | CATEGORY: WP
| note | 30521dd0-7ab4-401c-9286-384de37c514e | RESPONSIBILITY: Nominated Authority
| note | 624588c7-9e02-4737-9d38-336e4d326ed4 | VERIFYING DOCUMENTS: This ITP
| textbox | b4097172-5ecd-454a-ba47-96c4e6448161 | Date Completed:
| checkpoint |  | 2.6 Curing Compound
| note | 072050a6-b5ba-4196-9ef1-0370e3080b45 | REFERENCE: 684.12
| note | 5c792006-acc2-417d-b4d1-73453e6ef655 | 610.23 (d)
| note | c7696cb4-e92c-4786-b8bd-8f022f652f10 | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| textbox | dc359f60-5bc7-4754-84f9-483943dd3e8f | Enter: Teambinder Material Approval number
| note | 98d69525-adb1-4e61-80bf-6b7c7f8c82f5 | METHOD: Document Review
| note | 310fe358-f83d-4019-b42f-e531e38816f6 | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
| note | 0cf7f08b-b1b7-4fb1-a11a-1b53bb03e5ba | CATEGORY: WP
| note | 04bda8f6-ebe3-4c43-8cc6-453dd93473c7 | RESPONSIBILITY: Nominated Authority
| note | e5f87d47-81be-44b1-aed3-6a0e04923301 | VERIFYING DOCUMENTS: This ITP
| textbox | 6bbdcc48-7a6e-4019-94c5-9d97885b57d8 | Date Completed:
| section |  | Preliminaries - Procedures & Documentation
| checkpoint |  | 3.1 Shotcrete Work Method Statement
| note | a7e13f0c-e007-4b56-b547-69043e451b7d | REFERENCE: 684.07 (a)
| note | 51c70a05-cf9d-49d9-93da-64b440248198 | 684.07 (d) (i)
| note | a68bc113-fe21-4fe2-8497-29f1bce23a66 | 684.07 (d)
| note | 2f0034aa-d3e6-4160-84da-2e28510e653d | ACCEPTANCE CRITERIA: Shotcrete WMS, detailing the proposed equipment and preparation works, to be submitted for review to the Nominated Authority.
| note | 0230df72-9d20-4426-8769-02cfcb033816 | Any changes to the approved WMS shall be deemed a new Hold Point.
| textbox | ee53122d-ae6b-4e1e-9218-10503452b4a7 | Enter: Teambinder Correspondence Approval number
| note | 2bfc23ea-1da9-4f5e-af9f-a71bfdfc2149 | METHOD: Document Review
| note | e7d1859d-25d1-4f49-93fb-fa5235302f12 | FREQUENCY: Once, 4 weeks prior to placement of concrete
| note | bba56401-3430-4fcc-853d-96e7320aa1f0 | CATEGORY: HP
| note | 35834025-3d55-4bb8-94c9-5163b60d7f67 | RESPONSIBILITY: Nominated Authority
| note | 9d9a4b15-81fd-4b2b-b00c-36373447f060 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 475a83ed-6801-49a2-80d7-883dfdbeee22 | Date Completed:
| checkpoint |  | 3.2 Contractor Competency
| note | c894212f-0b02-46f1-9d7a-f7c88ccac310 | REFERENCE: 684.06
| note | cb98e004-9cdb-46b5-872f-8eed738bbfba | 684.07 (a)
| note | d76facc1-b290-4a37-a5b5-cb0ddd430dfd | 684.07 (d)
| note | d9fd99ac-40b4-40a3-8460-0cb107baaa4f | ACCEPTANCE CRITERIA: Personnel undertaking the shotcrete works, including the nozzle operator, supervisor and finisher, shall have a minimum of 5 years experience in shotcrete application.
| note | 2e3ca2ce-b72c-4cf6-921d-e10f2b326d43 | Any changes to personnel shall be deemed a new Hold Point.
| textbox | 4dbd81e1-16d5-4832-b684-498f18930512 | Enter: Teambinder Approval number
| note | f402557b-1e41-45ae-9d2a-2a9811b533b7 | METHOD: Document Review
| note | 1d7e0ac5-81cc-47de-b31d-3995d73e2027 | FREQUENCY: Once, 4 weeks prior to commencement of works and for any personnel changes
| note | a5bbc02e-aa5f-4da4-a025-69ca5d37f5d7 | CATEGORY: HP
| note | fb2b565c-9458-4f34-8b4b-415b704ee1b7 | RESPONSIBILITY: Nominated Authority
| note | 574ac80b-7b6b-46e3-a15f-f82352eae9f7 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b8fd3925-ebbf-4dff-81ee-24e576a82ea5 | Date Completed:
| checkpoint |  | 3.3 Test Panels
| note | 45826a85-fac9-442f-8efa-7daef3e11904 | REFERENCE: 684.07 (b - d)
| note | 12a49a83-cba9-424d-bdf7-0f29c7bbd7b9 | 684.07 (d) (i)
| note | 93f23701-7718-45ac-a0b8-63e7bb213af2 | 684.10 (a)
| note | f7b83e43-e50d-4e77-9c94-5f31249096f2 | ACCEPTANCE CRITERIA: For each combination of nozzle operator, concrete mix and spraying equipment, 2 no. test panels (750mm x 750mm x the maximum design thickness or 150mm min.), shall be cast.
| note | 4a0f4bd4-6cb0-4c8f-82fb-4671788f9146 | The panels shall be cast using the same reinforcement design and in the same orientation as the Works - panels shall not be cast horizontally on the ground.
| note | e14231eb-033a-4b22-97db-036774254315 | For each test panel, 8 no. core samples shall be taken, perpendicular to the surface, no closer than 125mm from the edge and after 48 hours minimum.
| note | 4fbd9bee-92c3-4661-96ef-81716651ce5f | Core samples shall be tested for:
| note | 5a0aca80-d0c5-4cf2-92f9-cccb5f4a4e92 | 1 no. 3 day compressive strength
| note | 2e3d1e08-0858-4140-a768-63d8fa2555f1 | 1 no. 7 day compressive strength
| note | 667ad2d6-4110-4c59-a3ea-e190aefffc86 | 2 no. 28 day compressive strength
| note | e5c43163-8183-42ab-8b52-4d75ccda5c0c | 2 no. VPV tests
| note | 2322e774-02f2-4325-af35-25abfada8693 | 2 no. visual inspection showing reinforcement encasement in concrete
| note | efd9a5b4-4018-45ce-ac1a-5fe2e0c9f625 | Any changes to approved test panel combinations is deemed a new Hold Point.
| note | bc4331ec-053a-4fa7-be43-0081c2d0b4f6 | Where existing test results for the same combinations exist, this is considered to be a pre-qualification and new test panels are not required.
| textbox | d0b2db2b-3c7e-4c8f-8e7c-6478fe432590 | Enter: Teambinder Approval Number
| note | 953905e7-1d7b-4281-acec-f12d63082e2e | METHOD: Document Review
| note | 7861f990-8384-4a46-b006-b654819757d0 | FREQUENCY: Once, 4 weeks prior to placement of concrete, for each combination of personnel, concrete mix and equipment
| note | 313be4a4-e1b5-4411-b5cd-6ac9d262c4b6 | CATEGORY: HP
| note | 23d3f406-3938-45c0-b50d-57ea5af35e12 | RESPONSIBILITY: Nominated Authority
| note | c6e00682-a994-4930-a5f6-833f49f512fd | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | e3ce912a-1ab4-43f6-97bc-1b5206c55466 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.4 Concrete Sampling and Testing Procedure
| note | 456c2665-cdac-4709-93f6-8233bf5758dc | REFERENCE: 684.08 (a)
| note | 76792b43-f6f3-4fdb-9638-9629baab6dc1 | 610.18 (a) (v)
| note | 85b31c6e-a31a-4b66-900c-a5780b9dd1bf | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
| textbox | 2998479e-ed72-4330-b16d-e73b84d12539 | Enter: Teambinder Approval number
| note | 6de1d7c6-86c2-4372-9cf4-474d6518b6bd | METHOD: Document Review
| note | bc572843-206b-4bae-b512-b8589be769e0 | FREQUENCY: Once, 4 weeks prior to placement of concrete
| note | 8015a0b7-d8bb-43f1-be8b-ae787cfd9f93 | CATEGORY: HP
| note | d4e82f98-a471-42d6-a71a-17d14a895fa6 | RESPONSIBILITY: Nominated Authority
| note | 72006e69-0bc4-4566-a7b3-d2256b502866 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 4cc95de1-0e89-49ba-bf11-62bd38182a56 | Date Completed:
| checkpoint |  | 3.5 Shotcrete Prequalification Toolbox Meeting
| note | 246b9bb5-e5bd-45f8-88dc-3530f0633a94 | REFERENCE: 684.07 (d) (ii)
| note | c107e1be-46ee-4700-8b02-bccb47442ee8 | ACCEPTANCE CRITERIA: Shotcrete prequalification toolbox meeting held to discuss the quality requirements.
| note | 23126e75-c0d8-4e7f-9282-ccaf1088cc1f | Minutes of this meeting to be submitted to the Nominated Authority.
| textbox | edb53fed-ca2e-47fd-9af2-e837dcb49ae9 | Enter: Teambinder Approval number
| note | 0caf3553-849d-44ff-b443-8949b6898039 | METHOD: Document Review
| note | 6c166043-9808-4fe9-b921-81bee2aea56f | FREQUENCY: Once, prior to placement of concrete
| note | 53f97852-80a3-43bd-b56f-4649fe1453ce | CATEGORY: HP
| note | ba6c36c1-93b5-4a5e-a955-164c38fe0830 | RESPONSIBILITY: Nominated Authority
| note | 7fdb6486-40f2-45ed-9f12-8bbea7c0b051 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | cd048d3e-353b-4de9-a826-90bdd92eefc2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.6 Hot and/or Cold Weather Concreting Procedure
| note | 4b5735ef-8cd4-40ce-af2e-3fdea39a0108 | REFERENCE: 684.10 (b)
| note | 7074c68a-6a39-417e-be38-fad2d8c0d3d5 | 610.17 (a)
| note | 3389882d-b561-4c7e-ab20-5296aad1c862 | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
| textbox | 401e9c05-3ee2-4b5b-a72b-873fad57daa7 | Enter: Teambinder Approval number
| note | 7ff513e2-bc20-4e97-9522-ce42e9905c6b | METHOD: Document Review
| note | 7859ea1f-b13c-4c96-bf8a-c4643e4500f6 | FREQUENCY: Once, 2 weeks prior to placement of concrete
| note | 0317a8b6-cc83-4a7c-92db-1769f0f0df1c | CATEGORY: WP
| note | 2ff9a0e2-ff01-4f05-8703-6ac442c93363 | RESPONSIBILITY: Nominated Authority
| note | 6c475607-c3c3-4c54-b2eb-556c1cb93c32 | VERIFYING DOCUMENTS: This ITP
| textbox | 055ee742-3876-479f-aa64-1c6e5654a3b9 | Date Completed:
| checkpoint |  | 3.7 Curing Methodology (for Concrete and Grout)
| note | 3ade36cd-bcb0-4606-8b04-a950278422fc | REFERENCE: 684.12
| note | 7bc78f50-d25f-46cd-9d08-4b1ee920c7a8 | 610.23 (a)
| note | a4b47890-0973-41c4-b200-78146565e831 | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
| textbox | 300d6c80-d14e-4e87-88ee-382ba96c2885 | Enter: Teambinder Approval number
| note | 0cf14049-8336-4549-81e9-41a44af91407 | METHOD: Document Review
| note | 1e216253-0dfa-4460-9b56-cb936646dde5 | FREQUENCY: Once, 4 weeks prior to placement of concrete
| note | d9072e26-21bb-4395-905d-5ef422571493 | CATEGORY: HP
| note | 2a319890-11a9-4397-85ba-2be8052aa69d | RESPONSIBILITY: Nominated Authority
| note | d47ba9a6-0580-4c50-bd67-3a0523d7e03b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b67aae34-affd-4dd9-b074-d68765b1d217 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction Activities
| checkpoint |  | 4.1 IFC Drawings
| note | 7065d7df-50e5-4323-b6a9-fd9df270ef93 | REFERENCE: MRPA Quality Management Plan
| note | 1cb61228-2128-4646-b230-81d89ade8795 | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 4a6deb73-91e3-4e85-a882-0cf884474c24 | METHOD: Document Review
| note | 3bb58844-2fa6-4216-af85-4207f4d2726e | FREQUENCY: Prior to starting Works and at regular intervals
| note | 8cf96be3-3685-4ae4-a626-332773142932 | CATEGORY: HP*
| note | 894e6b91-f58d-47fc-aca7-898597bfaa8d | RESPONSIBILITY: All
| note | f6bdf463-a828-4e3f-a62c-2bcb91f7335f | VERIFYING DOCUMENTS: This ITP
| textbox | 834ac63f-067d-4516-b395-190b82d3f3ce | Date Completed:
| checkpoint |  | 4.2 Substrate Preparation
| note | 035c680e-6d5b-4307-bcb0-118b5b536ec4 | REFERENCE: IFC Drawings
| note | b3e61861-5b15-4baf-91b9-ce8d882684ff | Shotcrete WMS
| note | b15bb8ac-2da4-4f38-b57d-5aea00572f92 | 684.09 (a - c)
| note | 5b7a8b50-d7d0-4489-865d-ce58f9ebbc85 | ACCEPTANCE CRITERIA: Substrate shall be formed to the correct line and grade to provide adequate thickness for the works and shaped (or repaired - for concrete) to prevent any abrupt changes in thickness of the shotcrete.
| note | 77f6f095-af8b-44de-b851-2accf4869009 | Any loose materials, oils, grease and coatings of any description shall be removed.
| note | 22ccc597-7ea6-4161-a698-3e14d2712dbe | Smooth concrete substrates shall be roughened to create a construction joint.
| note | 862180a2-4433-491e-a931-264a56de8d9f | METHOD: Measure , Visual
| note | 4a7de42b-1488-458f-8222-bd5d0b274e40 | FREQUENCY: Each lot
| note | e1a99575-ce83-4841-912b-3110029a1919 | CATEGORY: IP
| note | 12adfbaa-65f8-4847-a668-97d1902ec693 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 9d0e2b34-74bc-42d1-bc2e-640f83f02501 | VERIFYING DOCUMENTS: This ITP
| textbox | 62a5fc14-b1b3-4aa9-8552-2d60a50dcfed | Date Completed:
| checkpoint |  | 4.3 Subsurface Drainage
| note | a66cd44b-6334-4775-94b8-027b39ef5f5f | REFERENCE: IFC Drawings
| note | 9370e551-9a70-4af3-946c-e7e4dc0a65e1 | 684.09 (a)
| note | eb0b5d05-d140-475c-965a-3d01cdb1bb9f | 702.03
| note | 9f1bf49c-c86a-4849-943b-446c76a14941 | 702.06
| note | 02111ed5-f59a-484a-b28d-1b2f1327b0df | 702.07
| note | acd5b049-0ecd-49d6-ac16-9e2e73da20ff | 702.09 (f)
| note | e63366c8-df8b-4074-86c4-a4fe20e88fd5 | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
| note | df74a01e-6a9f-4e18-b134-47ed4e508f75 | The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings against the substrate to prevent encasement in concrete.
| note | f5163164-3ede-4222-94d2-d5b6d6e51a05 | Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
| note | e2001503-fbcb-4518-b73b-0e9c3ab414c2 | METHOD: Measure , Visual
| note | 2bc723c3-bcb1-4b4f-90cb-750934a48942 | FREQUENCY: Where applicable, each lot
| note | 359b45c8-6ec0-4ec8-93ac-39cfd502459c | CATEGORY: IP
| note | 1478c259-674e-4967-bf81-c34c458f546a | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 64dfea6c-7003-43d8-9ec7-fd61e4fd96f1 | VERIFYING DOCUMENTS: This ITP
| textbox | 73a29f1e-d825-4c58-840c-bd73e6112f6d | Date Completed:
| checkpoint |  | 4.4 Waterstop Seals, Compressible Seals & Isolation Joints
| note | 6606e333-0e2d-42e5-8b2c-f5e32a486a0b | REFERENCE: IFC Drawings
| note | 0d674b4d-bcc5-4471-980d-54f712024833 | Product TDS
| note | 48251624-225a-4678-868b-ca63743d8f44 | ACCEPTANCE CRITERIA: Waterstop seals, compressible seals and isolation joints shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
| note | c8f68e12-2aef-4f95-a690-40e19b43ce75 | Seals and isolation joints must be full height of the structural element(s) and located as per the IFC drawings.
| note | a081992f-0357-4edd-8036-2400d01f1a6d | METHOD: Measure , Visual
| note | af287750-988a-4e2b-a0e4-b069fca6d14b | FREQUENCY: Where applicable, at each existing structural element
| note | f9e0789f-cca1-4e4e-93e6-ac3616556cdd | CATEGORY: IP
| note | e66d912c-8b40-491d-8b4e-0ae3986d1570 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 2b7343d6-b265-48a6-bb8d-e77abd8b4e02 | VERIFYING DOCUMENTS: This ITP
| textbox | 741e94d5-b86a-4224-944d-83b694c11794 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 5.1 Reinforcement Placement
| note | 6daa8186-61d5-4af8-9713-0ad0f13cf30f | REFERENCE: IFC Drawings
| note | 7a38d420-94fb-4997-93b7-58b6e52a6e0f | 684.04 (c)
| note | 886df7ab-7d5b-48db-8eac-6e003b71ddc6 | 684.09 (c)
| note | 54fc25a7-9b4c-4839-8002-5fc861ee3763 | 611.06
| note | 1b72cfc7-54b0-416e-8f6e-06211285e918 | 611.09
| note | b73e9ea1-fdf6-4a3d-9125-55c7281c8446 | 611.1
| note | e04e4c37-a94e-4ea8-b61a-165bf7d486d7 | 611.11
| note | 7f0ea5aa-a47a-4fca-a414-f98a636a240d | 611.12
| note | dffe4162-dcd2-497f-a351-46392e987fe0 | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
| note | a91d29f2-6977-42b9-9db1-39388be8c7e9 | Tie wire is to match the reinforcement it is securing, with contact between dissimilar metals isolated with zinc-rich spray paint, electrical tape or have a minimum gap of 10mm.
| note | cbfd92be-0d00-46df-98a6-da3576574162 | Layers are spaced apart using bent reinforcement, not bar chairs.
| note | e56cb0d0-1d06-4dc1-8759-73189b5ce515 | Projecting reinforcement is the correct length and location.
| note | 423a182d-624a-4350-a327-779703f79496 | Splice lengths achieve the minimum length and are in contact for this length.
| note | 3d60fb88-34aa-47a9-ade9-203d1327f5c5 | The reinforcement surface condition is free from dirt, debris and damage.
| note | 086a3967-95f3-4bc7-89b3-6169417c917e | The resulting cage securely held with sufficient ties to limit displacement or deformation during the shotcrete application.
| note | 50cee997-526b-426f-a886-93dfc4d6ae52 | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
| note | 84aca4b8-7b8c-43ce-b0c7-b548c142ac84 | METHOD: Measure , Visual
| note | 60789238-f495-462c-8df5-f34e8d78999e | FREQUENCY: Each lot
| note | 4be9fbf3-9ffc-44f9-bed8-9fc8cccb082f | CATEGORY: IP
| note | 037f6828-fcb7-4b9c-aa27-f20a885c9c8c | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 94c45b2f-b7b1-4099-9d18-da98caaaaaba | VERIFYING DOCUMENTS: This ITP
| textbox | f9fdb273-2b9d-40c6-b92f-f6d7e0785a87 | Date Completed:
| checkpoint |  | 5.2 Cast-in Items
| note | f063c5d0-6810-440f-96ba-80aa647c6a1b | REFERENCE: IFC Drawings
| note | f747f68a-1a15-4348-8100-4aadd9a579ae | 610.47 (a)
| note | ff2acf69-5b76-4b9a-b5de-8bb5b2e29229 | Table 610.472
| note | 756f1012-ca30-4f94-9005-587ab422a025 | AS3810.1 Table 3.3.6.2
| note | 5534ed4c-c3bb-46e5-8373-48c455b8b691 | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
| note | ac0284b1-0a69-49d6-b464-30b88907b5ae | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
| note | 1ec31c4f-05b8-4027-9d5c-10a4f6a5121a | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
| note | a7099a29-ff24-46ef-a966-24eb35d7b0f4 | Grout tubes shall be fastened at regular intervals to prevent kinking.
| note | df33e1f7-1c54-4c1b-98ec-60d8b4676ce2 | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
| note | ad7b8fe4-0bf8-4178-abcd-5b834f420b9c | i. Bolts, ferrules, projecting bars & couplers = ±3mm
| note | d92dd42e-0263-467c-b158-9e72fd53fc1b | ii. Running dimensions of a group of the above = ±6mm
| note | 2ae80667-694e-4677-bf03-3ba0bb3caf37 | iii. Ducts and conduit location = ±12mm
| note | 93ceabae-d33b-4187-b26f-7ea2eeaed82e | iv. Diameter of ducts and conduits = ±3mm
| note | 0777275f-192a-4c2e-bae2-78c02a63c4cc | METHOD: Measure , Visual
| note | 5594d6ea-da94-46d9-b281-2506d205bce7 | FREQUENCY: Where applicable, each element
| note | f903e120-3bc9-4e40-8397-387b76e0bab6 | CATEGORY: IP
| note | 0d8194c9-ae35-4500-a16e-6f4c1dbe4045 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | abac52a7-591e-4547-b83e-7b5259247f8b | VERIFYING DOCUMENTS: This ITP
| textbox | b0c5c9d7-741f-499a-937a-4bc0f55098be | Date Completed:
| checkpoint |  | 5.3 Pre-pour Inspection
| note | 69932611-758a-47b8-9dda-549313688388 | REFERENCE: IFC Drawings
| note | c58f0450-6692-4fc2-bb3d-27d11b905c21 | Bonded Anchors ITP
| note | e7c2f02c-b2ab-461d-8c6a-670e6c3acad8 | 684.10 (b)
| note | ea8d1f5a-58df-4537-9cd1-40dfc2e3c398 | ACCEPTANCE CRITERIA: All preparation works on the substrate have been completed and the surface moistened without free-standing water to prevent premature drying of the shotcrete.
| note | aae7c1b3-0aac-4f62-8083-bd7c96f95487 | Evidence that the reinforcement and embedments are conforming to the requirements of the specifications and the IFC drawings.
| note | 0e67638b-71a3-45e0-9fb9-0748f4be83d8 | METHOD: Measure , Visual
| note | 9c938b52-deaa-4ae9-bc55-6e9a2fb0a3d2 | FREQUENCY: Each lot
| note | d761a7ac-f808-4993-bcd2-5d7fd3972d11 | CATEGORY: HP
| note | bdebf9b0-3cce-402d-8c2c-77403629775a | RESPONSIBILITY: Nominated Authority
| note | f885bec7-99b7-45cc-b75d-a25f15644023 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 9f72a3ff-4920-4a9b-8757-f1c2d7c86dee | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4 Weather Conditions & Evaporation Limits
| note | ea807600-0514-4ce9-9ffd-9d6ee3f399f9 | REFERENCE: Hot and/or Cold Weather Concreting Procedure
| note | 94ab2fa4-b0ba-4364-9071-79bddbca086d | 684.10 (b)
| note | cf61a046-b688-4677-a963-608a0dcbae8e | 610.17
| note | d0d6bba5-4715-4400-bf45-29804a55d757 | 610.17 (a) & (e)
| note | 83c3abbd-1f73-4b00-9dab-f1262cf4339e | Table 610.171
| note | 7b559305-2bc4-4386-b192-d9d7f07cc6ff | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | e1d89f4d-a4da-47cd-8148-7877810acd01 | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | dbfd0f77-3865-4347-ae47-e806b56d48df | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
| note | e118aef7-e130-4308-9720-be2f441891bd | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
| note | 57da3947-cd22-4b14-8fd7-f373cc6f0da1 | Record: Required information on the Concrete Pour Record.
| note | d4cec654-cfe3-48d3-87a5-d7b386837186 | METHOD: Measure , Visual
| note | 9984abe4-296d-4350-8045-93f7605ab2c1 | FREQUENCY: Each lot
| note | 365b55db-6307-4fa3-8de0-54d3d5f816d0 | CATEGORY: IP
| note | 77fb0502-db5a-4c9d-80bd-6facabdaf1c9 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 3be73f60-14fa-4456-91bf-3278e82dfa4e | VERIFYING DOCUMENTS: This ITP
| textbox | cf5fe15e-baa9-4768-b644-8acc3ad3b227 | Date Completed:
| checkpoint |  | 5.5 Concrete Testing - Sampling Frequency
| note | 3cf40926-fd44-4d03-96e6-d9b3d8362e13 | REFERENCE: Site Sampling & Testing Procedure
| note | 279c2987-e3c2-48a7-b73a-606f8e430ea5 | 684.08 (a)
| note | 0d2a30fb-4767-4337-b5be-6ccc7bc72ad2 | RC 377.01
| note | e363f8f4-d236-4c2e-ac48-ae7f7c5c33a7 | 610.16 (b)
| note | 2c301276-90f0-4413-9aa4-807ac2be294a | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
| note | 2ed33af1-9631-4c78-b3c4-99dc91191206 | 0m³ to 10m³ = 1 sample
| note | 4bea8762-4a2e-40c8-aa22-4f14ff226dec | 10m³ to 25m³ = 2 samples
| note | 91c55158-9ed8-48b7-9886-6926f0788a5e | 25m³ to 50m³ = 3 samples
| note | 883cb0a1-17c5-4799-a1e8-a8878bffeb28 | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
| note | 95896596-9cdb-4a05-a1fc-5355f19242e9 | For each additional 50m³ and additional sample shall be taken.
| note | 602de633-ca0d-4623-9717-54645aa42416 | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
| note | 9ad6dd05-16d0-4896-8517-f0d60c74912d | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
| note | cb6dda14-9fc0-489b-a4f0-71281e6e4a4c | Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
| note | 3a199311-927b-4637-904b-6dc737207e5d | Record: Required information on the Concrete Pour Record.
| note | 6abc1add-54c7-46d1-ba35-86ad00770940 | METHOD: Test
| note | 4aedbc0d-2a53-4468-bc04-6ffdba543108 | FREQUENCY: Each lot
| note | 5f421ddc-656b-4a01-bde9-3c7b7c4c9066 | CATEGORY: IP
| note | 52d0ef4b-2705-488a-879f-1167cd09a4f4 | RESPONSIBILITY: Concrete Tester , Foreman , SE/PE/SPE
| note | 227f84f6-c66d-4aea-9b13-675e423b45cf | VERIFYING DOCUMENTS: This ITP
| textbox | cd3f47de-994f-48a7-a486-da76516d92e5 | Date Completed:
| checkpoint |  | 5.6 Concrete Testing - Slump
| note | 48fbe640-6e7a-4c8f-adb3-88fbc2db03b2 | REFERENCE: 684.08 (a)
| note | 638737d3-78a8-4862-9a59-f88b5596ce4e | 610.16 (c)
| note | c77f9fcc-aa5b-411b-8992-4dc29975314a | ACCEPTANCE CRITERIA: Slump testing tolerances =
| note | 8cbff3ac-666e-4f83-9ba3-f54f0a86ccd4 | <60mm = ±10mm
| note | 4504cb60-0602-4e36-bf45-0d5bc40040a1 | ≥60mm to ≤80mm = ±15mm
| note | 2ff37ae4-0c2d-438b-91b6-030da6eba71a | >80mm to ≤110mm = ±20mm
| note | c6bcaa25-26f8-4f67-a6bb-77480bc7fd42 | >110mm to ≤150mm = ±30mm
| note | 781b7a53-2858-4e82-83de-5b55f9de9eb1 | >150mm = ±40mm
| note | ccf68014-e233-414f-b659-9151e03fad56 | Record: Required information on the Concrete Pour Record.
| note | 670c3d84-b9b4-49c0-9856-5e5a979498d5 | METHOD: Test
| note | 3c885789-f8d1-4791-a289-b4e6fb48f6cd | FREQUENCY: Each sample of Standard or Superplasticised Concrete
| note | 535ab6b8-b152-4f26-be17-aa49641dbdf1 | CATEGORY: IP
| note | a91662e2-0b1a-4868-8f13-4ab98615f9d1 | RESPONSIBILITY: Concrete Tester
| note | c5ba8356-c5e2-4c9d-ae83-de6c92ee3b16 | VERIFYING DOCUMENTS: This ITP
| textbox | 5c0dd82a-dc88-478b-a9f6-6919d337d05b | Date Completed:
| checkpoint |  | 5.7 Concrete Testing - Compressive Strength Cylinders
| note | 98ef6720-a48e-44d9-9868-e28e9f22d932 | REFERENCE: Site Sampling & Testing Procedure
| note | d2c44b96-026f-40f3-88c9-86f4f072348f | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
| note | 60751016-0ae0-4581-b709-d087a9d9ab88 | Record: Required information on the Concrete Pour Record.
| note | 66b5f01a-878d-441b-8877-47cd88bca8c0 | METHOD: Test
| note | 9d48f9af-8eca-4e2c-8650-48b9b47a9273 | FREQUENCY: Each sample
| note | 314fe36b-4302-4dd0-94f8-307d64434d3b | CATEGORY: IP
| note | 09a55f61-7817-496b-afe9-911501b8ca01 | RESPONSIBILITY: Concrete Tester
| note | 273abb97-b387-46a5-8cc6-ad075d9aa655 | VERIFYING DOCUMENTS: This ITP
| textbox | 8322a424-d230-4fb9-b07d-3b0b1b7370ba | Date Completed:
| checkpoint |  | 5.8 Supply & Discharge Rates
| note | d6a1ee97-e6c1-4ebd-9505-ba83612b7894 | REFERENCE: 684.05 (c)
| note | abec1b47-fece-4332-807e-4272d5302827 | 610.13 (a) & (f)
| note | 52acf65e-0e3d-4db0-bfc4-c51482631ede | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
| note | e617ff43-ba0b-44f1-929e-b46ba1d30213 | No water is to be added once discharge commences.
| note | b6c897fa-37ab-4c38-9b2e-63360ac4a669 | Maximum time between batching trucks is 25 minutes.
| note | e27b7f0d-88dd-45c3-bd01-1c742f2f7ed2 | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
| note | 53de54ae-b94e-4f63-9750-568e0d6dfdd9 | Concrete that stiffens or is showing signs of stiffening shall not be used.
| note | 61e6589c-6ffa-4ba7-93f5-1f9d09644ab4 | Record: Required information on the Concrete Pour Record.
| note | 756f3355-340c-4bf6-ac8e-4b162c76ef40 | METHOD: Measure , Visual
| note | 41d04dbc-4330-437c-8e72-1d9d4ab1a63e | FREQUENCY: Each load
| note | f54f7b0c-e077-4db7-90be-66344d4fd6c7 | CATEGORY: IP
| note | 03b68e50-779d-4974-bc88-d8ba1ec0204d | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 5b593e21-2bf2-4b41-a5b0-1718601cc63e | VERIFYING DOCUMENTS: This ITP
| textbox | 8894c3ea-8d80-4942-b17b-98f2075f0b62 | Date Completed:
| checkpoint |  | 5.9 Shotcrete Work Method Statement
| note | 6113a39b-81c7-4e08-a257-3539c1a1e2b7 | REFERENCE: 684.10 (b)
| note | f33eac60-61ad-47d3-b25f-00595dc6fd2a | 684.13
| note | 5551661f-79d5-437f-a1cb-e0b66ae68914 | 610.18 (a) & (b)
| note | fee3f88e-f334-4257-87c8-a5befc6f5252 | ACCEPTANCE CRITERIA: All concrete batches are traceable.
| note | 32c2503e-8607-4444-95bb-df8d9f17b4cd | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
| note | e41e898f-ecbd-48f1-9f96-5464daef6782 | Probes or non-corrosive thickness indicators shall be used during the application to determine the actual application thickness.
| note | 58ebc98b-8714-4a15-98f9-6e6a46c8b2c7 | The spray nozzle shall be held to ensure placement of concrete behind and around all steel reinforcement.
| note | 7ae4b159-4df7-4945-b7ae-b1df6bc74384 | For vertical surfaces, application shall commence at the bottom and overhead surfaces shall be applied from the shoulder to the crown.
| note | c53332fc-1c47-4455-b17f-dcfa99b853d1 | Each layer of the sprayed concrete shall be built up by making several passes over the working area with a maximum layer thickness of 150mm.
| note | f6e65e5f-ab84-4bc2-837b-5360ca881b37 | Concrete shall not be sprayed through more than one layer of reinforcement in one application.
| note | 9ade1ac1-9295-48d0-bfc6-b6a3e4d4955e | Where a layer of sprayed concrete is to be covered by succeeding layers, it shall be allowed to set prior to application of the succeeding layer without the need for curing compounds.
| note | a1003797-800a-440c-bea1-1016ffff36a9 | The surface shall be checked for soundness, segregated, loose or otherwise uncompacted sprayed concrete removed, repaired as specified, cleaned, and wetted using a blast of air and water, leaving a dense, homogenous monolithic layer.
| note | 10989eec-f152-440f-81f0-0b564932b118 | Record: Required information on the Concrete Pour Record.
| note | 6689d4a4-5456-42fc-9b83-dd2d1ccfe6b1 | Attach: Concrete Pour Record
| note | 3c59aa8f-3ec1-430b-b127-65a5ce411d9a | Attach: Concrete Dockets
| note | fcf23966-b8ac-4bcc-ad9a-05947a7dc98d | METHOD: Visual
| note | d60b602c-a435-4016-9b50-83a61e95bddc | FREQUENCY: Each load
| note | ba219edb-dec3-4978-925a-1d0e3ffa50cb | CATEGORY: SP
| note | 71a0e764-c59b-4cc7-937a-8f731b38de95 | RESPONSIBILITY: Foreman , SE/PE/SPE
| textbox | 9b4c26e2-3db3-4793-aedc-b656a51643b4 | Date Completed:
| checkpoint |  | 5.10 Surface Finishes
| note | d4f249b6-17b2-48e8-bb18-93154905ccee | REFERENCE: IFC Drawings
| note | 244e55aa-003a-40a1-ae07-4d339cd10b42 | 684.11
| note | 972cf51a-a389-4612-81c0-04d524fe1a1c | 684.14
| note | b64762f4-0a5d-4315-878d-eae094a1f7c4 | 610.31
| note | 1d570293-a9ec-4d60-b1ac-20935437ac8e | 610.2
| note | ad208640-ab77-4dc9-8af5-b9ab1fa6da2c | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
| note | b07cafe5-f3d7-4784-bf20-2b52d110ee78 | Where surface finish is not detailed, structural concrete retaining walls, soil nail walls, tunnel linings, CP Overlay and other structural components forming part of permanent Works shall have a class 2 finish to reduce the chance of cracking.
| note | 631dde9a-11c5-49b6-9c26-05ca3da9deb6 | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
| note | 10ddb101-6a13-495d-a7c2-8860e3956d61 | METHOD: Visual
| note | b49aeeef-0e4a-46bc-b3ef-a97d3304974d | FREQUENCY: Each element
| note | 8bbd1b56-b959-4212-bd10-d8868a19f24e | CATEGORY: IP
| note | 50a5c285-2702-479b-a447-137a9f830c6f | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | a4b79d1f-36b2-4fbb-a344-605279c6ef93 | VERIFYING DOCUMENTS: This ITP
| textbox | 69fdefc7-70df-441e-8c30-8ad55f36de97 | Date Completed:
| checkpoint |  | 5.11 Curing
| note | d2a0241f-61e7-4d60-9204-103c143a8587 | REFERENCE: Curing Methodology
| note | 5c7e1f78-bcde-4738-97b7-fa03f6460979 | 684.10 (b)
| note | c64b2fda-a423-4f62-aae3-32d687a9519e | 610.23
| note | 851b246a-e244-415e-84ca-935648b12194 | Table 610.231
| note | f6bb2a43-766d-4821-aa00-4e4ebb1103a8 | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
| note | 387ba238-723c-4af2-9c93-1f371e06648e | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | 91ad1077-1902-4c3f-8504-c16dbfeeb804 | METHOD: Visual
| note | d40774b4-3c64-42f1-af93-5b123b9e7317 | FREQUENCY: Each lot
| note | 367138df-4fa5-4c93-80b7-a5aadacd7cc5 | CATEGORY: SP
| note | 352c3f32-d926-458d-9a8b-be56ddaa2ee6 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 2e5467b5-edcc-4f04-949a-09e2b3a3a4a3 | VERIFYING DOCUMENTS: This ITP
| textbox | 8fc86315-3b04-4934-ac5e-9682af720077 | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 6.1 Concrete Testing - Core Sample Frequency
| note | 4095e588-18f9-43b6-a436-8c3720642dd6 | REFERENCE: Site Sampling & Testing Procedure
| note | 144e4f07-3a14-42e8-90a4-1cf75f332e5d | 684.04 (d)
| note | 2b10a646-5e64-4fb1-8606-bcf4ae43fe49 | Table 684.041
| note | 050b9e75-f098-4907-9230-3b7492a6003f | 610.16 (b)
| note | ad66fc8f-dccc-46f1-bc60-8ad087713eac | ACCEPTANCE CRITERIA: 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
| note | 1c02795e-30d6-4616-b8ed-a0249132083c | 0m³ to 25m³ = 1 sample
| note | b15b60a9-f0b3-4745-9075-cf28decdd960 | 25m³ to 50m³ = 2 samples
| note | 55cf6754-26a7-4229-a5c0-f039beec4df0 | For each additional 50m³ an additional sample shall be taken.
| note | b2a90c1e-d928-451a-ac03-7f4a521ffdc5 | Each sample shall consist of 5 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
| note | 93871d5f-ba22-4c52-ab2b-84899f096805 | Core samples shall be tested for:
| note | c402fecf-df63-4e80-8fee-bd07216c01bc | 1 no. 7 day compressive strength
| note | 031b131a-d57f-4fc4-ba7b-0033d8959b8a | 2 no. 28 day compressive strength
| note | 2e6b90c3-cd7c-48e7-ae2d-15a1c6acfa22 | 2 no. VPV tests
| note | f6e56e15-6a19-400d-8d97-8986b7a3520f | Note: MRPA has D.o.T acceptance to remove the 3 day core and take core samples on test panels in lieu of completed Works
| note | 97b63043-e4a9-4a2c-bf15-6aaeeefc1e12 | See:
| note | 41f74a87-d495-4b8e-9c88-575ae30eeefc | MRP-MRPA-GNC-XCN-0096
| note | dbabf04b-f2cf-48b5-b861-2b4f3f1b22f3 | E-mail from D.o.T 7.06.2021
| note | e2e8d0a5-67fe-42c3-9926-53fefd09c1f5 | METHOD: Test
| note | f890d1c7-4b41-4522-a99c-bd5cc27840eb | FREQUENCY: Each lot
| note | 2ed56aa2-4e24-4549-a4aa-4c7409744e89 | CATEGORY: IP
| note | 97fff06d-3726-416a-850d-94ce1f9634eb | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 46730626-b8c0-413b-8d95-8c7020cf47c9 | VERIFYING DOCUMENTS: This ITP
| textbox | e2508878-8df8-483b-84e0-69b59708f705 | Date Completed:
| checkpoint |  | 6.2 Compressive Strength & VPV Test Results
| note | 4da5eeae-3d17-45a9-b63f-22fcee41d162 | REFERENCE: IFC Drawings
| note | 51407a0d-6588-4c28-a71b-fb9b212f307b | 684.08 (e) (i - iii)
| note | f8ea89ad-8363-4799-a39a-b290e468328f | Table 610.051
| note | 397bf962-e515-4541-89d6-a3069552781c | Table 610.061
| note | db936c22-7801-4bd8-92c1-303ea8d67e33 | 610.16 (g)
| note | 5f797d50-2a29-4abd-94cb-e6444082cda4 | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
| note | 8970c6c2-a79a-4a61-b10c-4027234c17b8 | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
| note | 71680a4c-4248-492e-ad80-075c87cdbb68 | Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
| note | 2b5fa82c-2d39-451a-a941-abba0507c56b | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
| note | d6645b40-8713-4ce7-91ae-2fee5a1e8a16 | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
| note | 326e58ee-e7f6-4029-a8c7-36da0eba5f74 | Attach: Compressive Strength Test Results
| note | ca3020da-09d4-4fb0-bba6-bd83cbc6d25b | Attach: Core Sample Compressive Strength Test Results
| note | 4af7ff67-27b1-4eac-9331-017607522465 | METHOD: Document Review
| note | 3c1d6d78-8dcf-43da-8573-5a08a84a2160 | FREQUENCY: Each cylinder and core sample
| note | 042b26b6-4217-44d2-ab24-686c2d178fce | CATEGORY: IP
| note | 5cdf8c7b-41c4-4dc7-bea2-dbf413419b51 | RESPONSIBILITY: SE/PE/SPE
| note | 2bf46c5c-275f-462c-bdff-e95d77f4fdbb | VERIFYING DOCUMENTS: This ITP
| textbox | f51ec6ca-3115-43f4-8edd-0b219e128372 | Date Completed:
| checkpoint |  | 6.3 Surface Inspection
| note | 01541e35-39ba-47e7-8706-001a4658614b | REFERENCE: IFC Drawings
| note | 42b3fce8-e9c0-4334-a70f-42ad938b21f5 | 684.08 (b)
| note | fc91e928-3d8b-489e-998d-ccea04c2f39d | 684.15
| note | 7b92f162-1286-46b9-9385-06daf295a087 | 684.16
| note | ddf773d0-bd61-4777-9e75-9dcca74209f2 | 610.31 (a) - (n)
| note | 6aa65662-6eb7-4bae-a9bf-6f052b9bfca6 | 610.32
| note | a9157ebc-7271-4f33-b1fb-a1a1ac64536b | 610.24
| note | 3dc128eb-e431-4216-9ed5-43d1e1631da1 | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
| note | e245f38e-e186-43a8-9590-63b5a5269ccf | Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
| note | d4d32443-e5d1-4f9a-9bbf-ee9c10ec14a6 | For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
| note | 4b679161-3bd1-40af-858c-cb09d548fa0d | No cracks greater than 0.2mm (exposure classification B1)
| note | 6d314723-8387-428a-8d58-812cfb4db172 | If cracking is observed, complete the Structural Concrete Crack Repair ITP for investigation and repair.
| note | dd44757e-6c41-41fa-a5c9-5c01cea6442b | METHOD: Visual , Measure
| note | caefc209-7c8b-4748-b6b8-79f3b30ca4c0 | FREQUENCY: Each element
| note | d7f460e7-4a48-4f31-9311-55bcd3fd5222 | CATEGORY: IP
| note | c772fc82-b173-470d-81a8-74679ef4aaf5 | RESPONSIBILITY: SE/PE/SPE
| note | 05987f71-4c03-4ccf-90d0-0c12af8fadad | VERIFYING DOCUMENTS: This ITP and/or Structural Concrete Crack Repair ITP
| textbox | 959bcc32-a4ea-47a8-a12b-ca8968457ec8 | Date Completed:
| checkpoint |  | 6.4 Fibre Wash-out Test Results
| note | 3d3a51e9-3617-4226-9381-8c38e179af96 | REFERENCE: 684.08 (c)
| note | ed615112-0562-4ceb-a9b3-38e7b6840421 | ACCEPTANCE CRITERIA: Fibre wash-out test results shall be within 1% of the concrete mix design fibre dosage rate.
| note | 8e748919-65f0-4af9-8acf-637484487054 | Attach: Fibre Wash-out Test Results
| note | f18c665e-f7ab-4b32-bf3b-6c20caa7c357 | METHOD: Document Review
| note | 0a5bddf0-b196-428f-95ce-0820ff1ff0e2 | FREQUENCY: Where applicable, each test
| note | 0f673c7c-f048-4cce-813f-5cb3566bc8e0 | CATEGORY: IP
| note | d8f4101d-e029-4a16-9589-d9460c2bd6a2 | RESPONSIBILITY: SE/PE/SPE
| note | f11ea395-056a-47cf-9eb0-b07208aa0050 | VERIFYING DOCUMENTS: This ITP
| textbox | 2e72cf24-96fd-40ed-9401-8f9f11719dc7 | Date Completed:
| checkpoint |  | 6.5 As-built Survey
| note | c05addb1-e9fa-4e9d-9985-6902647f7f0b | REFERENCE: IFC Drawings
| note | f1d2a83c-ec43-4c70-b98d-911379fe8c5a | 684.13
| note | 33dc3645-7a2a-42ae-b8d2-ec2eb9054f95 | 610.47
| note | c95067bd-1bd7-412c-8efc-4a5a5832e949 | Table 610.472
| note | 0257dd40-bd4b-4340-b454-644f7957ef36 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
| note | e71b2456-764d-4427-819d-a18841e6e631 | Where a shape is required, ±25mm with no depressions greater than 15mm.
| note | dd5c1a2b-9b60-4fd0-9a13-172481e836dd | Attach: Survey As-builts / Survey Report
| note | f581e297-ccfe-4284-be2c-a8415fe9f236 | METHOD: Document Review
| note | f5147482-cd45-45cc-9101-0a2294cd83e1 | FREQUENCY: Each element
| note | 542ad597-62c1-4e24-99a5-99f348419bdb | CATEGORY: IP
| note | 1a24b77a-8e18-4274-9267-15cba6af3ca9 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 457a5b92-ed79-4768-8c5c-9bf8c11be929 | VERIFYING DOCUMENTS: This ITP
| textbox | d0a7a3af-11b3-4da8-9536-239d3f50c5ac | Date Completed:
| checkpoint |  | 6.6 Non-conformance Report (NCR) Closure
| note | 5c2f1d21-3e0d-48d3-9f2c-68ea2f9c1c3f | REFERENCE: MRPA Quality Management Plan
| note | f750f7af-2203-42c9-ac2c-51a450309a37 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
| note | e0406cc6-a5d0-46c1-932d-b62e542eb8f8 | METHOD: Document Review
| note | 469fe4f8-4bad-4255-9c21-0e799f001587 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 6b6b1442-cfda-4737-bb37-c25fd6963e85 | CATEGORY: HP*
| note | 2f1962c3-2d9c-4f20-aaa5-04a32cf40c45 | RESPONSIBILITY: SE/PE/SPE
| note | d0da31f8-ef86-4a24-a1fd-5f609b828a5b | VERIFYING DOCUMENTS: This ITP
| textbox | 78df584b-43bd-4e9b-a93d-ee19acd430ca | Date Completed:
| checklist |  | ITP-CIV-Piling Pad (Supply and Install) Rev 0 | itp | ITP-CIV-Piling Pad (Supply and Install) Rev 0 | a3e1672a-50ce-4a5d-9d1b-23aed4592abe
| section |  | Piling Pad - Document Reference
| checkpoint-no-value |  | Document Reference
| note | df34cbec-0989-496f-8905-28fdb9755d0c | VicRoads Standard Section 204 (December 2015)
| note | 199c8ee1-6154-40bc-bc47-6d894a254ef4 | VicRoads Standard Section 173(October 2008)
| note | 3fe3fce0-0692-4910-a6b1-eaf2ddcc1b9d | ITP Revision: Piling Pad _00
| note | 5a5c1126-531c-43ee-874d-bb47db922717 | ITP template approved by: Romualdo Magpantay (November 2019)
| section |  | Piling Pad-Set out and Materials
| checkpoint |  | 1.1 - Check location of underground and above ground utilities
| note | 57fb8e74-75ec-42e8-a0f0-291132bdee91 | Ensure that;
| note | 3947a03d-64c7-4fef-88b4-ecc1fbc3e250 | ▪ Dial Before You Dig
| note | 0a8f86cf-44aa-4e23-aa11-c7e93adbc21e | ▪ Services Isolated and Permit is obtained from client/internal.
| note | 731877f0-5b13-4078-a3fb-5b3214a731c8 | - - - - - - - - -
| note | 1d75e39f-19d9-40c1-8d10-c0dbebf21045 | References - QMP
| note | ba0831bd-d334-4b03-a3a5-d74802957f33 | - - - - - - - - -
| note | 91266e8a-2928-4385-8121-018343a353db | Verification Record - Signed ITP/permit
| checkpoint |  | 1.2 - Set out
| note | 00aef667-a259-4634-856f-c39e62716568 | Survey Pegs in place and clearly marks out the limits of the works.
| note | 3c9d1a99-262f-4f13-bf34-9e41c176c620 | - - - - - - - - -
| note | aa400c40-df1a-4754-8287-3164711dedcc | References - Temporary work design Drawing
| note | f8fba00e-4817-4c93-abac-989635c94875 | - - - - - - - - -
| note | 1552d37a-204b-41af-9634-da945f43745e | Verification Record - Signed ITP
| checkpoint |  | 1.3 - Verification of Type of back Fill Material
| note | 830ec16c-c861-400d-bc4b-01142a882b17 | Material shall meet the requirements as per Temporary work design requirements
| note | 958b4095-2cdb-47cf-90b3-a9d2abed2947 | - - - - - - - - -
| note | a40ed0ed-79c6-47a2-a50e-b14bf7bceb6a | References - Vic roads 204/173 Temporary work design Drawing
| note | 2d9adbeb-455e-45ad-8185-db2fb8305cd9 | - - - - - - - - -
| note | f5b29108-59c8-4036-993f-2a155393723a | Verification Record - NATA Test –Material Test Report PSD,LL,PI,PL ,MMD & OMC
| section |  | Piling pad--Fill construction and Testing
| checkpoint |  | 2.1 - Preparation of piling platform foundation(proof Roll)
| note | 31250b90-3903-4b7e-965f-c9879d337256 | Temporary work Design Drawing and equipment design requirements. No waving indication.
| note | 736cb0af-fd73-45b3-ae05-099fcdf3fa60 | - - - - - - - - -
| note | 3a19ef66-0c1e-4f9d-bd8b-5367d67fdfd8 | References - 204.12,Temporary work design drawing
| note | 83dc1e9d-627d-4dde-ae50-9a7b69e59a73 | - - - - - - - - -
| note | e2c78241-00ec-4169-a47f-03ce3103c76e | Verification Record - Hold point record
| signoff |  | Hold point
| checkpoint |  | 2.2 - Fill, Compacting and testing
| note | bd9f2f1f-fde9-491f-b0a5-aaaf1e1596ec | Plate bearing Test to support piling rig (as indicated in temporary works design)
| textbox | fc86ad60-e0f7-47ea-8d12-4ea1873003a1 | Specify
| note | f5338617-26df-4bb4-8b9b-3252122117a0 | - - - - - - - - -
| note | 33d3a250-3083-434b-9a5a-ccb2a516affb | References - 204.10/IFC drawing/temporary work design
| note | a2af0dab-08cf-48c1-8697-5d6c384eecca | - - - - - - - - -
| note | dcfb2210-3ed1-4e70-8e20-de984ac0eb84 | Verification Record - NATA Bearing Test Report Visual inspection
| checkpoint |  | 2.3 - Verify survey conformance (final FGL)
| note | 184e5327-ebcd-4d61-9142-0d41658de298 | Construction Tolerances finished ground level ± 40mm or equipment requirements
| note | f4092946-4a41-4fea-8e9f-bdca05b2eaa6 | - - - - - - - - -
| note | 6980112e-19a9-46cb-8265-a68f91d59845 | References - VR 204.03/Temporary Work design Drawing
| note | 2ce90eac-ad0e-40e8-a808-f0749421e8af | - - - - - - - - -
| note | 57a72f12-30dd-4c52-9b4d-c74b0f1f0015 | Verification Record - Signed ITP/Survey report
| checklist |  | ITP-CIV-Guard Rail (Supply and Install) Rev 0 | itp | ITP-CIV-Supply & Installation of Guard Rail Rev 0 | a836450e-6484-4287-84e0-f2b0f62c821b
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | cb93b6bb-a08a-4dd0-b28e-ac0ff6803414 | Document Title: ITP-CIV-Supply & Installation of Guard Rail
| note | bef6c0de-bdca-4e80-8797-6f0e848e43ab | ITP Description: Supply & Installation of Guard Rail
| note | 25a5283e-eca1-4498-aea3-f371ef0376ca | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 3469950e-33ee-4c10-bf0a-d4b0305358f0 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 8239104f-702b-4c99-8627-d2d9aaf6f45e | Revision Number: 0
| note | 88cbf0f2-ded1-4d9c-bbcd-abbd2a3a686e | Revision Date: 09/062020
| note | 405db14c-bb79-42d9-acc5-cf07768522ac | ITP created by: Romualdo Magpantay
| note | b18f4089-b7ff-4109-bc78-f653d4546e41 | ITP approved for use by: Michelle Edgar
| note | f58af8a1-5712-443b-a92d-28c359839c5d | 1.1 VicRoads Section 708 November 2018
| note | c22bfd4b-2dae-4b20-9a83-8428e69edc13 | 1.2 VicRoads Section 703 April 2019
| section |  | Preliminary
| checkpoint |  | 2.1 Accepted Products and material confirmation
| note | 664f09df-7e38-4cfc-b452-df8ccff8e0c2 | REFERENCE: VicRoads Spec.
| note | 35ac2b19-b1c8-4993-b779-2a4dd9ad1c2f | Cl.708.04
| note | e7677f7c-82d3-461b-baad-8f56ce87140b | ---------------------------------
| note | bd135d6f-4e73-482c-a033-0a4969cd9a1d | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
| note | 66f2393a-d2f5-469b-b997-fc8bd9284010 | Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
| note | af18778b-a827-4c94-a6dc-fb8e6e88d0a5 | ---------------------------------
| note | 1eb57a5f-ac7d-4c17-ac66-8893842d48b6 | METHOD: Document Review
| note | 0e33f39c-b252-4222-9f91-b4f957241889 | ---------------------------------
| note | 8c920a66-33bc-4aa7-98a8-1ebf043bb30b | FREQUENCY: Each member material component
| note | 0b4b3006-4b39-4395-a456-f33caf849ada | ---------------------------------
| note | 34f5dc88-da1f-44a7-adcc-76d53fb0d290 | CATEGORY: HP*
| note | 9eb29a49-ca7e-4867-b235-28a12ec1637e | ---------------------------------
| note | f070b85a-f78a-4059-a8ad-06996201d82b | RESPONSIBILITY: Nominated Authority
| note | f1f5e403-6177-4a4d-9a5e-ea5f30ce6d47 | ---------------------------------
| note | 75d34057-1362-42e5-b123-dc213b39b16e | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 4240b1df-f730-4eb0-a309-fd8a576438f8 | Date Completed:
| checkpoint |  | 2.2 Identification of guard fence components
| note | 1ab94afa-3ca9-45d9-a414-582274b64359 | REFERENCE: VicRoads Spec.
| note | 52366cbd-8b23-417b-a9be-dc091e677fa9 | Cl.708.05 (a)
| note | 7a719430-a704-475d-b38a-d2995e1d4180 | ---------------------------------
| note | 8d3d948a-2cc2-4a19-a384-2d9e4f8200f9 | ACCEPTANCE CRITERIA: w-beam sections, both ends of posts and all plastic components of proprietary end treatments unotrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
| note | 824e06a5-5065-44c9-acc5-10dd3ff6f277 | ---------------------------------
| note | f14efbff-28ff-473e-98c7-37f7bfcedc34 | METHOD: Visual
| note | 2d8f193c-9937-4ee5-83c0-7c6cd0c5e69f | ---------------------------------
| note | 0727e723-d985-42ab-95e9-c08d8d0a1990 | FREQUENCY: Each member material component
| note | 90fe285e-91aa-48e6-bb57-79690e6f900e | ---------------------------------
| note | f0af6cac-aa86-48fd-8e79-8548769ee745 | CATEGORY: IP
| note | ab09f33c-e042-4d8e-b903-103d933c643b | ---------------------------------
| note | 8b40806d-add1-4038-9fe7-b0d257e675f6 | RESPONSIBILITY: SE/PE/SPE
| note | e7f17db4-5f4b-4182-a09d-a014edd810d7 | ---------------------------------
| note | dde2df8b-29cc-4b8f-946d-8f806b9f3477 | VERIFYING DOCUMENTS: This ITP
| textbox | 54c84473-0753-40e4-8f0b-7bf12af354fd | Date Completed:
| checkpoint |  | 2.3 Obtain and submit Material Test Certificate of Compliance for the barrier systems
| note | d429e854-4910-4b41-8c16-85ca3fab710a | REFERENCE: VicRoads Spec.
| note | ef0fa972-bb72-485d-a0aa-6097759a0acd | Cl.708.05(b & c)
| note | 072a8690-4f1e-48f7-b3d2-0795359291f5 | AS/NZS 1594, AS1627, AS 4680
| note | 6c1b0b2f-60c9-4a05-8091-a2669bf881ff | ISO/IEC 17025 a
| note | 79737947-dacc-47a0-83a7-ae00de403fde | ---------------------------------
| note | f3f9891b-7e0c-433b-ba11-8d264bcd7544 | ACCEPTANCE CRITERIA: W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
| note | f85a2a5f-4625-4b8a-8077-38bf67bc220f | ---------------------------------
| note | e85359ba-4717-466b-9ec1-aaf347d4cacd | METHOD: Document Review
| note | 4ba0a63a-ac41-4a41-b6ca-349d83b7b649 | ---------------------------------
| note | 71d4698e-7910-4406-9b21-590e25446960 | FREQUENCY: Min 14 days prior to commencing, 1 per 1000m of material
| note | 2d678d41-d18a-4a8f-9d0e-922156164d85 | ---------------------------------
| note | 7e02c901-92d5-427f-a8cf-850f62913289 | CATEGORY: HP*
| note | 0963bc39-ca10-4ee2-b72b-aa524e225e86 | ---------------------------------
| note | a2243320-f5ac-43bf-826c-1d85fbf55301 | RESPONSIBILITY: Nominated Authority
| note | d9afb97f-4190-4b55-b46c-61fa91f2298f | ---------------------------------
| note | b6a12eda-19d6-431d-aad5-22815dd0fb93 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 885703ac-3a39-47a0-b2a7-a9b48262cfa2 | Date Completed:
| checkpoint |  | 2.5 Verification of Protective treament/ galvanisation records
| note | fd2338a2-2168-43e8-b9d3-e54426414f6e | REFERENCE: VicRoads Spec.
| note | ed430ae3-3c03-48a1-a606-b7d26f9bf2e0 | Cl.708.05(d)
| note | 835dec1d-c57c-4342-88e6-92231b0b61f3 | ---------------------------------
| note | a2bdfd5c-3c32-4c5d-9de4-4c0069f6765d | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214
| note | 6f132675-5228-44ed-b05c-8e88c2465c19 | ---------------------------------
| note | 0ff9879d-e528-4f4a-bdf0-bd94dfedff29 | METHOD: Document Review
| note | 0e6560ec-76f4-46b6-a533-3f5871627201 | ---------------------------------
| note | eb492865-05a9-40d8-a1bb-959bf6e8119a | FREQUENCY: Min 14 days prior to commencing, 1 per 1000m of material
| note | fbc114d8-927c-4581-bc49-0bf2370245e2 | ---------------------------------
| note | 37c42ba0-2788-4dab-a24c-f4797a4d179d | CATEGORY: HP*
| note | 4723774f-aa8f-4969-9c62-6178d69b56ea | ---------------------------------
| note | a594026f-9ba9-4443-8394-6e7766314f42 | RESPONSIBILITY: Nominated Authority
| note | 86567967-d7b0-4ee7-9406-3b707ef5fd4a | ---------------------------------
| note | 7775fa34-f348-4171-9dc5-b5e44e61874f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | db05669d-de3c-4da8-8b6c-b24daacb7eda | Date Completed:
| checkpoint |  | 2.6 Concrete mix design
| note | 2f54a3e3-9027-4015-8a26-e829b364f135 | REFERENCE: VicRoads Spec.
| note | 3e95d0a6-f54d-4aff-ba75-68a6e82729d9 | Cl.703
| note | ebd1643b-e284-499b-851b-005f80556daf | Cl.708.05(g)
| note | ae488979-05c6-49d0-822b-12ea373015e4 | AS1379
| note | ea0bf1a1-5dbb-4ce4-8ffc-effe9b4440fd | ---------------------------------
| note | 2041dad9-2211-41c2-bfa9-0672297c05d4 | ACCEPTANCE CRITERIA: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
| note | 9afbf3ac-0e79-4bbc-be72-8173dd95ef39 | (i) Portland cement-based concrete, N20 strength grade, or
| note | 23e90b89-1973-41f8-8442-1970079b3139 | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
| note | 8c279a43-7b25-4e06-a6ea-86c9f98f9ce5 | ---------------------------------
| note | 5b5e568b-47a4-44f8-b7c1-39cdd61a1b7f | METHOD: Document Review
| note | d746fecd-4e33-413f-b3aa-21efa94ed13a | ---------------------------------
| note | d70c5037-ec0d-4eeb-b514-20df7eb90f3a | FREQUENCY: Prior to Commencing
| note | ad533048-7300-47d1-9293-b13eb7270ad8 | ---------------------------------
| note | 3fc8555f-a699-4557-ad87-77c3ef4172d0 | CATEGORY: IP
| note | 22ff322e-a0bc-45b4-b920-2d38f56ebe8c | ---------------------------------
| note | 7e113bcf-664b-4474-92ab-f672fd87eed9 | RESPONSIBILITY: SE/PE/SPE
| note | 1e1fdeb6-f49d-4e36-a5d3-6db77a1d2cad | ---------------------------------
| note | 7e508892-c33e-46e4-8adf-bd21f51aa060 | VERIFYING DOCUMENTS: This ITP
| textbox | 97d6cd91-0eda-4960-815a-a16a5300e755 | Date Completed:
| section |  | Construction Activities
| checkpoint |  | 3.1 Survey Set-out
| note | 8539b7fb-b808-4bcd-bdd7-94e596c4a084 | REFERENCE: Project Spec.
| note | 4020a7be-6a5a-430f-a258-4a7f0e6cea3a | Cl.1190.07
| note | 2ff47e26-8e4a-4923-b907-085884bd87bb | IFC Drawings
| note | 84ebce4b-06d9-4706-9f07-33fc5c44049a | ---------------------------------
| note | f458756d-584e-4e01-b3ed-0062235d71ab | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element.
| note | 91579024-473e-4b2c-b399-d8879c49165e | Attach: Survey As-builts / Survey Report
| note | 61b4b284-5cfa-4ea6-b518-db01f1188ed4 | ---------------------------------
| note | 6fefa7ae-56d4-4528-9cfb-095b01c899dd | METHOD: Measure, Visual
| note | 3edb77f2-61e2-4d82-8086-32df24b83625 | ---------------------------------
| note | bf72a6cb-68f4-481e-8d65-60950b23a9e0 | FREQUENCY: Prior to Commencing Excavation
| note | 04caceab-98aa-4cb6-9b39-10d78fea8969 | ---------------------------------
| note | 3710e4a2-bd87-4823-82e5-050b1af944f8 | CATEGORY: IP
| note | 9a2b3e88-56ff-4b98-b664-eb2ed1f8d48b | ---------------------------------
| note | 013baa1c-8fa0-477e-bcba-c60d5030ccef | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | 95bc68fa-794f-4b38-972d-6adda833684b | ---------------------------------
| note | 2c85ff03-ec49-49c1-9b3f-eaf6c821fbb9 | VERIFYING DOCUMENTS: This ITP
| textbox | e8e76f6d-294e-48fc-ae71-81198965756e | Date Completed:
| checkpoint |  | 3.2 Obtain approval of location and length
| note | 36d99d49-5408-4065-8d3c-105a3b9f8427 | REFERENCE: VicRoads Spec.
| note | 1942d9a0-3a39-448f-9495-81184fcc9931 | Cl.708.08
| note | 751832c5-e91f-4ee4-af75-22634b9e80d7 | IFC Drawings
| note | 682176f8-a837-4888-9100-6c8293289381 | ---------------------------------
| note | 6a984d38-381e-4514-8069-68bc60e0234d | ACCEPTANCE CRITERIA: The required location and length of all guard fence shall be confirmed with the Superintendent.
| note | c4f16e82-f478-4671-87e7-d8350f81eac8 | ---------------------------------
| note | 59e44ff2-8def-4e9c-a973-dd358edddc73 | METHOD: Measure, Visual
| note | 9139d000-28ed-4589-806d-e977affb2944 | ---------------------------------
| note | 6a1426a7-e198-4f51-a26b-902532110020 | FREQUENCY: Prior to Installation
| note | 370fb5d4-8b07-4f8e-b18a-4aee92bec5ce | ---------------------------------
| note | 1b517da4-04fd-4ed3-8114-3011608b2deb | CATEGORY: HP*
| note | 7799a854-7ea4-4a03-8cce-910297197a4e | ---------------------------------
| note | a27687fc-104e-4453-aa5f-ccf0374ea660 | RESPONSIBILITY: Nominated Authority
| note | f3fbe496-acde-4ccb-b665-8d2c363df275 | ---------------------------------
| note | 6c9b63a7-1cd8-4784-8eab-0eb85970d9c9 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 8f34667c-00ba-4c67-981a-885a5b5e1371 | Date Completed:
| checkpoint |  | 3.3 Install posts, rails and terminations
| note | 43d266f5-e073-4492-b551-45a997ea0cb2 | REFERENCE: IFC Drawings
| note | 586ac785-bc75-4290-8828-63e8556c621b | VicRoads Spec.
| note | a93e097b-d0db-4a6d-9a02-af579e18f808 | Cl.708 .07(a & d )
| note | ce868c1f-e62d-4047-8c23-e35121aea5cf | IFC Drawings
| note | edef8674-4d95-4f57-aa59-7c27cb4bc888 | ---------------------------------
| note | 10d7f799-44d9-4315-8c35-b613be2ffad7 | ACCEPTANCE CRITERIA: Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
| note | 97d4a350-e3bb-4c75-801a-afb0e1287e76 | ---------------------------------
| note | 0b334649-d320-482f-9ac8-83f8cf5ad308 | METHOD: Measure, Visual
| note | 78260b58-149c-45f1-aa8e-3154f417cab0 | ---------------------------------
| note | 5b55f462-b1fc-449a-90ef-86e3c27d64b3 | FREQUENCY: During construction.
| note | a9eacf13-4fa2-401d-9c18-ede45651cfc2 | ---------------------------------
| note | 1af7e840-24ba-4eb3-85bb-424f8b78ee2b | CATEGORY: IP
| note | d4d29876-4cad-4edb-bbd5-682ad286b03d | ---------------------------------
| note | 4ec40d54-1f89-4475-af3d-f3bd700026c1 | RESPONSIBILITY: SE/PE/SPE
| note | a95d8656-32ce-4fde-90db-8c37ac9e2fdc | ---------------------------------
| note | 191ef6ed-5854-4473-aea2-79b67e61eb48 | VERIFYING DOCUMENTS: This ITP
| textbox | 7ebd9c01-aba3-4e58-967b-69aab861a39f | Date Completed:
| checkpoint |  | 3.4 Construct crushed rock base for maintenance strip
| note | ae042442-cf58-4691-99e8-48e50e892290 | REFERENCE: VicRoads Spec.
| note | 27331a3e-b864-48ab-9212-2950b322aff3 | Cl.708 .11
| note | 6ad3479c-9ac3-428f-a744-d03b36c1b7c5 | Cl.812
| note | 1e0ad0a1-1a5d-4052-82df-1827360d9da0 | ---------------------------------
| note | 97017a5b-7e0b-42f0-b67f-df9ab03c9fa4 | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
| note | 519e4a2c-81cb-4b01-bade-87c61af60cda | ---------------------------------
| note | 7922151f-1d36-4074-8993-98e4a51a36ca | METHOD: Measure, Visual
| note | 9b8b8f5a-c288-4653-b941-a50aa317420c | ---------------------------------
| note | dcbcea35-d5c7-42a9-b8f6-0981f024e2dd | FREQUENCY: During construction.
| note | 14217e29-2d2e-4a29-a9d9-e6c795bdb956 | ---------------------------------
| note | beed8879-8dc8-465f-8b7f-b6bccfe45334 | CATEGORY: IP
| note | a6825c83-1997-4566-930c-2cf2d4d71c13 | ---------------------------------
| note | 9ddc610c-bc50-4a40-b0d7-304026ab9c75 | RESPONSIBILITY: SE/PE/SPE
| note | a37ca4ad-d378-4c8c-9115-61ba1c144c16 | ---------------------------------
| note | 4a6cb9c8-6294-4d7f-9962-eb6d45c946d6 | VERIFYING DOCUMENTS: This ITP
| textbox | e0653313-473a-4fa5-a64e-e5456d3346e1 | Date Completed:
| checkpoint |  | 3.5 Construct concrete maintenance strip
| note | a56daa7a-8912-4301-9497-d072169e29d3 | REFERENCE: VicRoads Spec.
| note | 66eb0bf3-be38-4bde-9844-d8fba916def2 | Cl.708.12a
| note | 83c7f96a-aeb9-4d03-a27a-cce347b3df86 | Cl.708.5g
| note | 7e447915-c62c-4fcd-9cc9-2cb907fa1fce | Cl.703.11
| note | 08e97734-6a88-40a2-a1ec-c73f495b743d | ---------------------------------
| note | 486f7b54-39ca-499e-99d1-65b1ac5a234a | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
| note | b5ff2491-c574-4062-be2d-d707085280f0 | ---------------------------------
| note | d47c9b9a-cfab-4c8f-b3c4-bca0ba91bac2 | METHOD: Measure, Visual
| note | 659dc0a0-9291-4915-a417-a330d0ee8797 | ---------------------------------
| note | 3e430a14-95b3-4b0b-9c50-223c4f660708 | FREQUENCY: During construction.
| note | aaf2411d-f6e8-402c-84da-43a9eec94c98 | ---------------------------------
| note | 04bc1cf0-6c60-406d-a9d7-c05805574b11 | CATEGORY: IP
| note | 04932370-7568-4c60-b64c-27071d563bab | ---------------------------------
| note | 23cfb672-c506-4e6b-b1af-8370669cf566 | RESPONSIBILITY: SE/PE/SPE
| note | 4453ff58-6d93-4022-8cc0-b2561442dc44 | ---------------------------------
| note | 1def0acc-5e52-4d73-85da-ff1190b7dded | VERIFYING DOCUMENTS: This ITP
| textbox | 40ef8667-5603-4df4-ae84-6a1c67dbf2fe | Date Completed:
| checkpoint |  | 3.6 Curing of concrete maintenance strip
| note | a7ad03cf-ab05-4188-85c7-06d356c72826 | REFERENCE: VicRoads Spec.
| note | 2a74bb66-b736-4b96-9621-68d2bcea3692 | Cl.708.16
| note | 5ca7fd45-2896-40d4-832c-1364537a2066 | Cl.703
| note | df024125-29c9-44df-8386-d80a88fd2e17 | ---------------------------------
| note | 570a9279-39b8-42fd-8b9f-c78f96906353 | ACCEPTANCE CRITERIA: Concrete shall be cured either by water curing,wet hessian,polyethlyene sheeting adequately sealed against moisture losses, curing compound or combination thereof.
| note | b4574bb4-4fad-4b25-89bd-79c868db93f1 | Curing compounds to be in accordance with AS3799.
| note | 620b18b9-6946-42e4-9384-d3efbba354e8 | ---------------------------------
| note | 5be7850a-8d0e-4f46-bc47-ca32aa20cd95 | METHOD: Measure, Visual
| note | 89b1b4f7-8caa-437b-8583-67be14ec6fdd | ---------------------------------
| note | 3842fc5d-774a-4708-970c-67494d0978cc | FREQUENCY: No less than 7 days after concrete placement
| note | edb04e63-5fa2-452f-b62e-e6366c30ae11 | ---------------------------------
| note | efcae276-faa6-48f8-9fef-32ec503d48c8 | CATEGORY: IP
| note | 8ca60abc-fa99-456a-a035-584bb28edfa0 | ---------------------------------
| note | db5a1b5a-cfba-41a9-a383-da6ca7897cac | RESPONSIBILITY: SE/PE/SPE
| note | 94b09d66-455b-41e2-85fc-2c1190f0e26e | ---------------------------------
| note | 1bafdba8-82f2-47b5-9c26-3b3119777c21 | VERIFYING DOCUMENTS: This ITP
| textbox | 33b6306f-9950-4c72-9840-900642335059 | Date Completed:
| section |  | Completion
| checkpoint |  | 4.1 Delineators
| note | 1d8087cc-53a3-4b2d-80dd-f147eb3b361a | REFERENCE: VicRoads Spec.
| note | 06cb5d0b-fb49-4c8c-ae91-8c90908f1ba0 | Cl.708.11
| note | 521be77e-6e90-416b-aed7-589ddc1cf908 | Cl.703.12
| note | dce5d562-3528-4be1-bf37-56ab7f520be4 | ---------------------------------
| note | c19a9bf3-c59d-4a38-bf7c-1858e34981e5 | ACCEPTANCE CRITERIA: Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
| note | be158b69-2c72-4ca5-b65b-73f6b2250a24 | ---------------------------------
| note | 607a3834-6e64-4e89-af8e-0f99a0b97311 | METHOD: Visual, Document Review
| note | a68c25ec-5cc2-41a7-9755-0b8a20d7e0f9 | ---------------------------------
| note | 2330059c-1ff6-4e8d-9299-163dddc09301 | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
| note | 56669472-9783-4f51-8f16-c0d392524328 | ---------------------------------
| note | 25bfaf31-630e-4aad-bf74-24cd658555c6 | CATEGORY: IP
| note | eb9652ee-ee72-42ab-ba3d-61820c2a3dfe | ---------------------------------
| note | f5b045f7-9bdc-44dc-8642-703d9b11c860 | RESPONSIBILITY: SE/PE/SPE
| note | 11bc717c-af40-437f-be10-9202008dba61 | ---------------------------------
| note | 93c07f7c-dbd8-41ad-9b02-58645c23f5bc | VERIFYING DOCUMENTS: This ITP
| textbox | 0360fdcb-6a08-433a-b892-26ee1e07ed39 | Date Completed:
| checkpoint |  | 4.2 Existing Sign & markings Reinstatement
| note | e9bc1187-58ad-4d9e-93fc-cc292b5b1be6 | REFERENCE: VicRoads Spec.
| note | 1aaefa20-1511-468b-a9dd-0def640929db | Cl.708.17
| note | 54e37862-6eb3-435a-8cdb-cd3b7cd2d894 | IFC Drawings
| note | e20e217e-043a-4981-8977-9af47a2b14a0 | ---------------------------------
| note | 4f6e03a3-06c6-43e5-a246-377a73ac2ccc | ACCEPTANCE CRITERIA: The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
| note | bec21cc4-026d-4331-a6f1-8a56a362d42b | ---------------------------------
| note | 4348306f-b58e-4741-acc7-fe57bac9f7ec | METHOD: Document Review
| note | 94bdeed4-2694-4ddb-8d40-f398b3348657 | ---------------------------------
| note | 3d9e6100-4ea8-4c49-ad2f-ce67dd1b0e80 | FREQUENCY: Each element
| note | dc79cca7-12e8-4581-9577-aff31c187f31 | ---------------------------------
| note | eff9a4d5-fdd8-4b0e-9bb3-1877fc0d75a3 | CATEGORY: HP*
| note | b324685a-14d8-49b5-9c37-78851c43d920 | ---------------------------------
| note | 789ba0d5-5f11-4faf-9f9c-a6a6d16fdfe1 | RESPONSIBILITY: Nominated Authority
| note | 1a3f4e50-78a0-4c67-beaf-6d79f4ce4e8c | ---------------------------------
| note | b907131c-eb90-43eb-918b-9eaced909722 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b18a30f1-9ddb-454d-9868-ef1e28cece00 | Date Completed:
| checkpoint |  | 4.3 Compliance Audit of Safety Barrier System Installation
| note | 3b134e76-cbf1-4a3d-834f-b8ed92930890 | REFERENCE: VicRoads Spec.
| note | 9a592707-1884-4a77-8e5f-7fe3257363f9 | Cl.708.10
| note | b7320eb8-242e-486f-9bc4-684886a924f3 | ---------------------------------
| note | 870113d2-7e79-4a90-954c-fc22b3e914c0 | ACCEPTANCE CRITERIA: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufactures installation Manual and specifiction for each end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
| note | 8b1e0b98-79c6-4221-8518-cc833336fe6b | ---------------------------------
| note | 84a03148-4071-4ab4-830e-e3fbaeae78f2 | METHOD: Visual, Document Review
| note | 14c32c6e-37a9-40c0-9c75-671d786ba58d | ---------------------------------
| note | 592d6329-e60a-4fa6-9484-e3774fe72ec8 | FREQUENCY: Each bridge beam
| note | eda9abd1-28d5-4b68-b28c-fdda1b01b072 | ---------------------------------
| note | 901cf460-a087-497c-a4c9-d1ece0df957c | CATEGORY: HP*
| note | eeb1b6f6-a119-4a5c-9712-5ca0da7b56db | ---------------------------------
| note | 57233f9a-9fa5-4c8e-a21a-4b3e64aa5500 | RESPONSIBILITY: Nominated Authority
| note | 7a59c018-da00-457a-9f9c-59d14efe1264 | ---------------------------------
| note | 24b61409-82fb-400d-a238-a6b285de1ae2 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | bb8a0aa8-c8bf-46f3-bc67-17793e51cf74 | Date Completed:
| checkpoint |  | 4.5 Survey data captured for as-built purposes
| note | 11ae5bcc-bd97-49ae-8bfb-ec1945e1dcf6 | REFERENCE: IFC Drawings
| note | 8bf85656-af68-4cb3-b852-de4b1eb01d80 | VicRoads Spec.
| note | ad0029d8-e719-4d88-8b94-baf496cbcd45 | Cl.708
| note | 7d8e8746-b124-484a-9679-785fcda7d5c6 | ---------------------------------
| note | 941ea664-065a-425e-96cd-2fb69f330416 | ACCEPTANCE CRITERIA: As-built Drawings
| note | c48609b5-f01e-4f87-86f0-7fba42457c64 | Tolerances as per VicRoads Specifications, Clause 708.
| note | 33f25985-46ba-4ca1-9391-379c651cef2c | ---------------------------------
| note | 23360799-7e9e-4443-affd-3f936c9b80a4 | METHOD: Visual Document Review
| note | 037f72d4-365b-4eed-ada2-fe3663b78090 | ---------------------------------
| note | ab8abde7-e67d-4673-9ecf-9fece2268ff3 | FREQUENCY: Where applicable
| note | 41f3e896-6c11-4566-9eda-e1d894f9601f | ---------------------------------
| note | 7fc96454-4466-4705-9d53-8d6971391aaf | CATEGORY: IP
| note | f3c97c71-d75d-41b8-bc6a-7bdf253092f6 | ---------------------------------
| note | 6a9cf5b1-dc50-4bbb-9073-57b40cbc2366 | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | 2b960e37-eec5-4301-a85e-3a20d2ba08b7 | ---------------------------------
| note | 19d3635d-ff9e-446c-9c9f-d481ab664b59 | VERIFYING DOCUMENTS: This ITP
| textbox | cc6ac47a-14b5-4a57-b3da-52253f3bf46b | Date Completed:
| checkpoint |  | 4.5 Non-conformance Report (NCR) Closure
| note | 2427dcf7-8488-4f69-9d01-857c4a9f7fa4 | REFERENCE: MRPA Quality Management Plan
| note | 261fd618-724b-477a-81b8-f3aa84978a53 | ---------------------------------
| note | 63e14932-c9dc-4a62-9d71-cd4db7ba0b92 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 907a9998-ef8a-47bf-8e72-2530a002507b | ---------------------------------
| note | 5cc19204-3d64-4833-8f85-bf8c38cf4d4f | METHOD: Document Review
| note | 12a3e8d0-0668-4727-959f-b2ce77cfd2e5 | ---------------------------------
| note | 262a7701-c5c3-4cba-8311-33a8a7b0b8c1 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 7abc72c6-d478-49aa-bf04-0b60837aa8eb | ---------------------------------
| note | 5532773a-aa3b-48e1-961a-b9fb26018675 | CATEGORY: HP*
| note | b8ca3f91-11e3-41ed-96c3-b2158b082646 | ---------------------------------
| note | 6539e55b-97c0-4302-9f38-88d3badecd85 | RESPONSIBILITY: Nominated Authority
| note | 019de8b2-a9e9-41d7-80e4-ab67512b956f | ---------------------------------
| note | 70ff4f2b-e31b-4b74-aacb-215d8bf028ff | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c28e342e-3898-4dc5-b552-f62d26fcef63 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 03814465-bf05-437c-b507-5491df3a32a3 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 890db5ed-1cec-4229-81b9-68eb503e9c23 | Name:
| textbox | d17be69e-d562-426d-bf9d-deaef9078385 | Position:
| textbox | 62f1f9f7-9c45-495a-96e2-0f830d811521 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Site Clearing and Grubbing Rev1 | itp | ITP-CIV-Site Clearing and Grubbing | afe4ca61-69db-4e55-bf48-b83a489a8b12
| section |  | Referenced Documentation
| checkpoint-no-value |  | References
| note | 0dd2190e-1f9e-4a45-ba06-27c2f77b1b47 | Document Title: ITP-CIV-Site Clearing and Grubbing
| note | 45fcd6d8-a7b3-4902-bad3-d8391b3b8a1b | ITP Description: Site Clearing and Grubbing
| note | 1ce3e520-506d-4cae-aa79-7d6470b369e0 | Discipline: CIV
| note | 57370afb-6a1d-4fbd-8ed0-1e2dea07ded8 | Revision Number: 1
| note | 92d49dcf-bea7-440a-9f62-1eaab5999398 | Revision Date: 24/04/2020
| note | ae0fe4f2-7043-413e-99bf-67d93d6ca615 | ITP created by: Mike Freeman
| note | 8a7bf617-6c24-4e4b-b438-f5630881a964 | ITP approved for use by: Josie Pavlou
| note | 22decfbb-98a0-4871-9e15-b9894411e032 | VicRoads Section 201 January 2016
| note | cefbf6ce-b5d1-4b66-b229-cf6d5daf8fe0 | VicRoads Section 204 December 2015
| section |  | Preliminaries
| checkpoint |  | 2.1-Environmental Controls
| note | 29a137c0-6d08-4b09-89e8-362c1c4e06b6 | References - MRPA Environmental Management Plan
| note | 6fc9e2b5-d90d-44af-b492-242f2eb4dcd3 | Acceptance criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
| note | 74fc77f8-28ad-4270-9cef-891917f049e9 | Method - Visual
| note | 3466a574-df12-424c-83c8-bcb32cb32678 | Frequency - Where applicable, prior to starting Works
| note | d0acc6cf-25db-49de-ba74-2f90a0e59443 | Category-WP
| note | 5bb8efed-5522-4e26-a62c-a48e35a3cce5 | Responsibility - Foreman SE/PE/SPE
| note | 41ff5077-6535-46ec-b4cc-876e179d7766 | Verifying Documents - This ITP
| checkpoint |  | 2.2-Vegetation Removal Permit
| note | e2eeda8b-0703-4b96-8f01-bad37b7d6d85 | References - MRPA Environmental Management Plan
| note | 6486c7be-ba09-458f-8c0d-e08f17ee65c1 | Acceptance criteria - Prior to removing any vegetation or habitat:
| note | a2a532be-3da0-4f65-9597-943a1ec06a5a | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design
| note | 0dc96946-789d-430f-99f0-19d5f9290e4d | Documents and any relevant permits.
| note | 90fb9c97-98f5-4d8d-ace4-7ec37266f1c4 | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works
| note | f910e52e-60ce-4623-b0a7-9192c3eccad7 | ii. fence and sign all sites nominated as No-Go Zones.
| note | adc8f3ae-2464-4f69-8334-4d037abbfd80 | Attach: Vegetation Removal Permit
| note | f1f27a4e-3ab8-4777-bd79-360b2a098e77 | Attach: Ecologist's Report
| note | 561831a0-23e7-4dad-b924-ff19ec1b2369 | Method - Document Review Visual
| note | 630e86ec-9210-4786-b870-de5614a84a18 | Frequency - Where applicable, prior to starting Works
| note | 284eea83-e0c5-4d45-8b12-10b643930543 | Category-HP
| note | 1b0e8062-f79e-4a23-9910-89ca05d0bfba | Responsibility - Foreman SE/PE/SPE
| note | 07a0824f-76bf-4ac8-be7a-467715e73094 | Verifying Documents - This ITP
| textbox | cb16a795-2fc3-4b1f-9d78-37007aefaaeb | Date Completed
| signoff |  | Nominated Authority Holdpoint
| section |  | Pre-construction Activities
| checkpoint |  | 3.1-Survey Set-out / Limits of Work
| note | a21d863d-618d-40d3-8dfa-0d79a4fdf8ea | References - IFC Drawings, 201.03
| note | 82867e44-deec-433f-84af-74badbce4ba8 | Acceptance criteria - The limits of clearing and grubbing shall be:
| note | 4d8c461b-290a-4164-9bb8-4e59fbde4abe | a. the limts defined on the IFC drawings
| note | 38ef60c2-28fc-4469-8dfe-e7e15848d956 | b. the whole width between the outside edges of any batters, including any roundings, togther with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
| note | 249bcf11-e5d1-477f-b49e-7be8b060b766 | c. no more than the width required for completion of the Work under the Contract
| note | 9bd7108d-67b7-42c8-9b2e-99d0ee43ae73 | Method - Measure, Visual
| note | 13b3a0dd-b079-4f00-9786-c29bca7b63ca | Frequency - Once, prior to starting Works
| note | 4352c012-dba9-4b25-aa07-7a28b6a319ce | Category - IP
| note | 5e715d54-d182-43fb-9b78-b62de960cd4d | Responsibility - Surveyor SE/PE/SPE
| note | 5a7649d0-3d14-4ed2-9d0e-127d28881f8d | Verifying Documents - This ITP
| textbox | 9e85d936-b9c1-45c6-8dc0-8dd6d1450954 | Date Completed
| checkpoint |  | 3.2-Cultural Heritage and Areas of Significance
| note | 87ae8a91-166a-4f60-bc86-1c10cd86614f | References - MRPA Environmental Management Plan, 201.10
| note | c402acb8-278c-482b-b5d0-81092eaab228 | Acceptance criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
| note | 2ed3b30b-b730-4227-b790-ae1e6a6bce1b | Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
| note | 8287edb3-40c6-4888-bcde-0785b9ee406b | Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
| note | f434f95f-e475-4ac9-9868-e1e81ae003fc | Attach: Cultural Heritage Report
| note | 4e1037e7-53db-4442-8e6c-f1b866f0ab14 | Method - Document Review Visual
| note | 518252c0-9ab7-40cb-96cd-c3c1c6e23b0f | Frequency - Where applicable, prior to starting Works
| note | 4028dce0-dc71-4f1a-8676-229fa45661fe | Category - IP
| note | fd62547f-fc62-4eb9-bcee-cf35788a12ce | Responsibility - Surveyor SE/PE/SPE
| note | 498bf327-9711-4103-b5a2-a11dded93fba | Verifying Documents - This ITP
| textbox | a1a326c2-c0f1-4cff-87c5-b209bd6a4989 | Date Completed
| section |  | Construction Activities
| checkpoint |  | 4.1-Stripping of Topsoil
| note | 88d4d33e-a055-4bb1-b826-d2d79a5e2c5f | References - Section 204.05
| note | e590c85f-ddf1-4740-a597-37c62cbf54ff | Acceptance criteria - Topsoil shall be stripped for the full width of the formation.
| note | 4a6a2c5d-4107-4bd2-9094-d0efeeb03ce1 | Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
| note | 59b6c97e-e3ed-4d62-aaee-11b9842b52ee | Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
| note | 4d0d59c4-f7f4-4152-ada7-b3b6bff7e2fd | Method - Visual
| note | 9a4def3e-ec8f-44c7-a9f9-811af8de8e69 | Frequency - Each Site
| note | 35f547ff-a24e-4655-90a6-88cbf6c0d9fc | Category - IP
| note | 4d46ad0d-11ff-46e7-9ec0-e89e0029b72a | Responsibility - Foreman SE/PE/SPE
| note | 23d64e7f-92ab-4271-bd9a-228d841432a7 | Verifying Documents - This ITP
| textbox | a46eb09f-0c6a-4fd9-8c4e-36a81a756944 | Date Completed
| checkpoint |  | 4.2-Stockpiling
| note | 946dcd9e-a245-45ea-a40d-a8317e6f182b | References - Environmental Management Plan, Section 204.05
| note | 56d333a8-474c-4a8f-9584-1525dd0135ab | Acceptance criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways. If this clearance is not possible,additional protection shall be provided. Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
| note | 0587b6b7-20c9-473d-a6ba-113bfbf5b671 | Method - Visual
| note | 3f622497-5e5e-4548-ad91-d8d402bf6208 | Frequency - Where applicable, each Site
| note | 235ef78e-e704-42cd-af26-113494b3a915 | Category - IP
| note | 860348a2-09b8-4b73-bd48-c4b72063ca41 | Responsibility - Foreman, SE/PE/SPE
| note | 87a48164-aacd-4938-b2af-43c085b42cf1 | Verifying Documents - This ITP
| textbox | 9e6ba0b8-4097-4b5e-9e4b-0a122f29d34a | Date Completed
| checkpoint |  | 4.3-Abandoned Services
| note | b3d998ed-f106-44a2-8714-45ab02a29b3c | References - IFC Drawings, Excavation Permit, Section 201.05
| note | d84adde5-9c11-4aeb-b4a8-efb32e06431f | Acceptance criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
| note | f643eec6-8af7-4ce3-a8cc-bf673ebe51f1 | Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
| note | f8a996f2-8ba1-4e06-b8d7-06aec35eb635 | Decommissioned services to be disposed of in a suitable manner.
| note | 5e20daff-6a28-4910-b2e8-e835f1de51e7 | Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
| note | d0d23877-9f68-42fb-9322-90d6e814292d | Method - Visual
| note | 3b57192f-129b-4286-9943-7dc2e38019e1 | Frequency - Where applicable, each Site
| note | 28680669-88e3-463b-8fbb-dcc3d1cf0303 | Category - IP
| note | 2dabff08-6e41-474d-9e79-438b9386aa14 | Responsibility - Foreman SE/PE/SPE
| note | 6ecb8927-d83a-448f-a7cd-3599e1f8e9a2 | Verifying Documents - This ITP
| textbox | fa0a3ed0-15f5-4d17-a2e5-9ce7e58fb505 | Date Completed
| checkpoint |  | 4.4-Clearing of Trees and Vegetation
| note | e4707315-aa21-42c5-83cc-1d484a471fdb | References - Section 201.04
| note | 6f142b39-0ee0-499a-9196-505bdd828cb0 | Acceptance criteria - Clearing work shall not be undertake outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
| note | c988eae3-aac1-409d-8771-679fcd0633b0 | Method - Visual
| note | a05e4316-aafc-43aa-ac64-a875c5a0811f | Frequency - Where applicable, each Site
| note | f60ae2a2-4640-4e46-8e5f-e7bdfed65698 | Category - IP
| note | 70a292d8-83cd-400c-a474-50b9df89f63c | Responsibility - Foreman SE/PE/SPE
| note | 9ef31c0d-b73f-47f5-bad3-65fbb539ee34 | Verifying Documents - This ITP
| textbox | defbecce-2012-45d8-bd79-cc872bb59079 | Date Completed
| checkpoint |  | 4.5-Grubbing of Vegetation
| note | 57f8ecbd-654e-4f05-9057-33ec99c23c1d | References - Section 201.05, Section 201.06
| note | 80ac5d11-3a60-48bb-98fa-a8afd9b618b1 | Acceptance criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
| note | 3e8a1a1a-7bc7-4324-962b-2fe4cda9351c | In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
| note | f0161308-05af-46cd-a9f8-0d4c7401277e | Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
| note | c1b1210a-59fd-4a67-a242-4a35e85a7426 | Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
| note | 65189b1a-b823-4ef4-a898-46eadbeb516c | Method - Visual
| note | 918eaede-f6d6-4302-aba2-2de75c997bb3 | Frequency - Where applicable, each Site
| note | 1a28e8f1-4160-4d2f-aa91-489370f7ae1b | Category - IP
| note | 446f05c5-9fc2-4a99-8b8a-1d830916b9b5 | Responsibility - Foreman SE/PE/SPE
| note | 80a554db-080d-46cc-ac12-1c3f7b0fdd46 | Verifying Documents - This ITP
| textbox | 2511281b-fee9-4be1-ad5a-bd365b147648 | Date Completed
| section |  | Post-construction Activities
| checkpoint |  | 5.1-Disposal of Materials & Vegetation
| note | 24194825-4b90-4f7d-9055-c3869d5e6a05 | References - Section 201.07
| note | d7a1fa5c-9874-424a-8dc4-0c993894ab63 | Acceptance criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
| note | b2eaa2dc-3d43-4fc7-8075-cebcfb9eeadc | Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
| note | 0f33ecd8-4a16-469a-b647-3ea6b499f4cd | Tree trunks and large branches shall be removed from the site.
| note | 6c5c5be2-8a72-4948-98d7-7764290570af | Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
| note | 3ba79727-86e5-46d7-a511-7ba828f67f76 | Attach: Delivery Dockets (for Items sent off Site)
| note | fe3b2a0f-106d-41c2-a62e-5cddaefe7c22 | Method - Visual
| note | 15d05d8a-94d6-4c60-9ec5-737b8dec9db9 | Frequency - Where applicable, each Site
| note | d03fa16a-afe9-4467-98ed-139e5e876a53 | Category - IP
| note | 86bfdaad-60cb-49f5-81f2-8fd14995d62e | Responsibility - Foreman, SE/PE/SPE
| note | 8f10db6b-2be5-49de-a2cb-24b782ee99cd | Verifying Documents - This ITP
| textbox | f5f1d182-d85c-4f61-a128-27d61d05013d | Date Completed
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 5ab5f80c-8e4a-41ac-9d82-6b65b6efe63d | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | ff35b538-7103-47ee-8cbf-04e99250d2c6 | Name
| textbox | 83258ac8-0429-4e79-a221-7ab837317fd6 | Position
| textbox | 0079383a-60c0-40b2-9eb0-74f8d688a888 | Date Completed
| checklist |  | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | itp | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | b184e264-c5b0-448c-89f7-b20f42d29d2d
| checkpoint |  | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0
| note | fddd66a2-0d68-4f80-9df1-8b1f2e7e5279 | Document Title: CHK-CIV-RSS Walls-Pre-cast Panel Installation
| note | d2ceb5bb-51f5-4cde-b3d5-3683fb13d66d | ITP Description: RSS Walls - Panel installation
| note | 8e17b1ec-b1a2-4150-bcd3-f5db0f881306 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 32194343-4c26-43cf-8fa6-668a18f79389 | Revision Number: 0
| note | 612e7845-f435-453b-a03a-f039e147e88b | Revision Date: 19/0802021
| note | 77b363ae-076f-4f62-9c79-e3b6f37dabbd | ITP created by: Victor Mira
| note | 3f37b9cf-60c7-46b0-8d35-0173bfcf8ec4 | ITP approved for use by: Aldrin Guinchoma
| checkpoint |  | 1 Wall Panel installation
| note | 27295dad-52f9-4d6f-afe5-8407c154b29c | REFERENCE: IFC Drawings
| note | c3b0a9bf-b45e-4765-aa9d-53fec0858eb4 | MRP-057-C-RFLD-DRG-20-ADR-CSW-1783
| note | bebd63fe-3edd-45fb-beeb-b78d22767558 | Temporary works design
| note | 47bf3881-822d-484e-9b99-43ad09c6115b | ACCEPTANCE CRITERIA: Install kicker board or rebar to top of the levelling pad if applicable
| note | 6c15c390-fd12-4e64-8020-82d04a0e1daa | Install Bearing Pads
| note | 1507283f-db46-48fd-a8ff-cb375473cc67 | Confirm correct panel as per Drawings;
| note | fa67f93d-f215-4189-a9be-dcd9582ac7ee | Check if panel should have a weep hole or block out for sacrifical strap;
| note | 717263f6-a7d4-49a0-8d4f-b94b64afc748 | Check 19mm gap is maintained in vertical joints
| note | 76b94073-6191-4709-be12-f1797761186a | Install temp support as per Temp Works Design and complete Precast Erection Sign-Off. Temp support must remain in place until 400mm of fill has been placed above the bottom straps.
| note | f2a3b0ef-9855-4706-99f9-1df3762683f8 | METHOD: Visual / Measure
| note | c82a0b7e-387f-40ea-806a-0ea1e3ef0b1d | FREQUENCY: Each course of facing panel
| note | a289848e-3865-4096-b2a1-6116792f28ac | CATEGORY: IP
| note | f96b89fd-b225-4bc9-b36d-c409ea1f67d3 | RESPONSIBILITY: PE/SE
| note | d7fb2d51-c50e-49cf-be7e-ade0413cd018 | VERIFYING DOCUMENTS: This Checklist
| textbox | f041f853-b255-47ab-8ec7-84e88e9b7418 | Date Completed:
| checkpoint |  | 2 Filter Fabric
| note | ebf7ea76-6eb1-4dac-8e53-0b50c715005f | REFERENCE: IFC Drawing: MRP-057-C-RFLD-DRG-20-ADR-CSW-1783
| note | 6dfb5210-2feb-4dd9-b5be-58f5611a770a | Filter fabric to be installed against all Vertical and Horizontal gaps
| note | c7cd4955-5d5a-44d8-80aa-2fcdc7761b3f | ACCEPTANCE CRITERIA: Install kicker board or rebar to top of the levelling pad if applicable
| note | 7996ed64-24f0-4df9-b47b-85c1394d3ec9 | Install Bearing Pads
| note | 85a14b87-4c94-4cd7-b0b6-252b49bad765 | Confirm correct panel as per Drawings;
| note | db653857-4fce-4414-9338-e94630f60e19 | Check if panel should have a weep hole or block out for sacrifical strap;
| note | 2c721a91-3608-4000-85e7-126a4ade34be | Check 19mm gap is maintained in vertical joints
| note | a65e4cd7-0e2d-4df4-a0fc-f50bb9773c71 | Install temp support as per Temp Works Design and complete Precast Erection Sign-Off. Temp support must remain in place until 400mm of fill has been placed above the bottom straps.
| note | e0bb4ed3-acad-487a-97d9-8e9c73ac3090 | METHOD: Visual
| note | e3d1d8ae-4b09-4be2-aed8-9b703c157716 | FREQUENCY: Each course of facing panel
| note | ffa2313f-80ff-426b-80be-ab1994f0dd7f | CATEGORY: HP*
| note | b76e50ba-b3bf-4199-83bc-021c6379f603 | RESPONSIBILITY: PE
| note | 621cc6a3-1e2f-4eef-b06a-103350e75050 | VERIFYING DOCUMENTS: This Checklist
| textbox | 1f6f5155-6838-4600-bc14-938c3366ea4e | Date Completed:
| checkpoint |  | 3 Wall Panels installation
| note | 35695fde-1763-4fe2-82b1-43b440aa5516 | REFERENCE: 682.17
| note | c69313df-5733-46c3-899c-ec42a622e37f | 682.2
| note | e1d1cbf6-240e-4c6f-9f56-cd8270f70f0d | IFC Drawing: MRP-057-C-RFLD-DRG-20-ADR-CSW-1701
| note | a951fb23-bff2-4661-8a5d-ef13d3b1cf77 | ACCEPTANCE CRITERIA: The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
| note | d4350800-2aac-460d-9973-dd8ff2b0c83d | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
| note | a84e59d0-f05e-4689-b27e-77ba633c01d3 | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
| note | 156d4e77-f9d8-4afb-aa2e-b549aa2d4542 | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
| note | c23d7dde-a1e6-4f34-95ae-fe71fa0a37cf | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
| note | 2f5e966e-ad0d-4a18-ba7b-34f20fdae741 | (e) the wall level (after completion)shall not deviate from the specified level by more than ±20 mm;
| note | 4c283c04-4c6b-4df3-bd1a-2e095ff9f69d | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
| note | 8e87dc50-70f2-4988-a92c-b775dc32b8bf | Attached: inspection photographs
| note | 52826085-13fe-44e2-ab8e-12ef400595b8 | METHOD: Measure
| note | 084ada3e-0de9-4098-92af-fca20de04390 | FREQUENCY: Each course of facing panel
| note | c10a6922-c8d3-435a-8d40-2bf5f0a79390 | CATEGORY: HP*
| note | b603d859-6791-4e62-8e25-3a52d934c5fc | RESPONSIBILITY: Surveyor PE
| note | f1b7de0e-e935-4a78-921c-34a8858bd1bf | VERIFYING DOCUMENTS: This Checklist
| textbox | d66e1722-5ca0-48f5-9237-e319f9d7b323 | Date Completed:
| checkpoint |  | 4 Traceability of pre-cast units
| note | da35958d-b6c6-4b48-9d31-00280cb29c9e | REFERENCE: Record location of each panel
| note | cb85e0fe-d559-4915-bf6e-c84b62db47de | Production lot number, panel type and date installed is to be recorded on the lot map
| note | 2913bb2c-91b0-4fc8-b000-de0eac91f6e7 | ACCEPTANCE CRITERIA: The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
| note | d2679096-1e42-4c25-ad39-0b54d30c7796 | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
| note | a57b9657-c450-4300-81cd-89ddb07877f2 | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
| note | c32e713e-53f4-482c-a463-ec265c583e93 | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
| note | 82dd0768-144b-41fb-9903-a2dbcc6b8618 | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
| note | 5d3e1797-6447-422a-8c59-48a3faacc6cb | (e) the wall level (after completion)shall not deviate from the specified level by more than ±20 mm;
| note | 94f5d78e-3ab2-4473-85bd-d0bb9997cd1a | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
| note | f03d5ba7-333c-4d77-9990-9ea6ebb21b1f | Attached: inspection photographs
| note | c65bd9d7-1a48-4ad7-b25a-9c236fdbc78e | METHOD: Document review
| note | 79f3376b-53f1-471f-bcfd-6f9335741877 | FREQUENCY: Each pre-cast element
| note | 59e4c832-f5c0-4c7e-8740-35fb62ebd496 | CATEGORY: IP
| note | 3fbfed7b-3418-4516-a7d8-0da7b45e9237 | RESPONSIBILITY: PE
| note | c94fb4a5-ece1-464f-924a-68bf97a4e302 | VERIFYING DOCUMENTS: This Checklist
| textbox | db6e17c5-11cd-4145-ba03-ed9f2fde9863 | Date Completed:
| checkpoint |  | 5 Wall panels - Survey reflectors
| note | 536ec6c6-6bad-4275-aa5f-7e08ff0fc557 | REFERENCE: 682.21
| note | 14a641e6-a80e-4b2c-9898-ad62be4f11fa | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS.
| note | 504461e4-3586-4b28-b437-ff8f45cf79f2 | METHOD: Visual
| note | 55bdfdcf-5fa1-424b-8d9c-f95608247abd | FREQUENCY: Where applicable
| note | ff48a5bf-b552-4d61-9062-c70e4b0d9fb0 | CATEGORY: IP
| note | 49faad2f-f00d-40ed-88fb-9109a845d9cf | RESPONSIBILITY: PE
| note | 547052be-466e-4386-8210-eb0f724fab6d | VERIFYING DOCUMENTS: This Checklist
| textbox | 44739847-849d-43e2-9a24-0d1c0bf427b4 | Date Completed:
| checklist |  | Stormwater - Products and Material Rev0.0 | itp | Stormwater - Products and Material Rev0.0 | b87e2a34-a4f7-4404-9292-9318f4443510
| checkpoint-no-value |  | Document Reference
| note | f6b73463-360b-4efe-ad4d-166f3cbe640e | VicRoads Standard Section 701 (April 2019)
| note | 03d37880-bfac-49a6-acd4-178808436fb0 | VicRoads Standard Section 705 (October 2018)
| note | d14bce29-c37e-46b7-8f5c-848a3ce1ff21 | Revision of ITP template: Stormwater Drainage_00
| note | b10d6ced-59f2-42e5-9372-9d6936188485 | ITP template approved by: Michelle Edgar, October 2019
| checkpoint |  | 1.1 - Drainage Pipes
| note | 94875218-aa3f-43e5-8add-16181dc34c6d | Drainage pipes and culverts supplied in accordance with 701 and AS/NZS 4058.
| note | ce277469-1890-469b-8a7f-341be04fcdce | Documentation as per 701.05 is available in Teambinder Material Approval form
| note | b55849e9-70df-47ea-afc0-d3b104a4fdc3 | - - - - - - - - -
| note | 93c7dc05-45e1-4f5c-86db-b74a291bd70f | References - 701.04, 701.05
| note | bcdddd38-500d-4077-8d1e-f3401315223e | - - - - - - - - -
| textbox | a46b9919-4624-4341-91b3-214fefa433a1 | Verification Record - Teambinder Material Approval
| checkpoint |  | 1.2 - Drainage Pits
| note | 02580a92-c0a4-4bd5-b5a6-58406c48896c | Drainage Pits are supplied in accordance with 705.07.
| note | 5c8edaea-27f6-451c-b696-a2c027b556a3 | Suppliers documentation has been submitted via Teambinder Material Approval form
| note | 8981b8ac-42b9-48e1-b6dd-0050d0d2b9ac | - - - - - - - - -
| note | 144b9ab3-8d40-4f9d-90b2-e166995c6b20 | References - 705.07
| note | 917580eb-8a20-491c-b40f-2941f03fcf0b | - - - - - - - - -
| textbox | bcdf34f7-cdad-4dbf-8996-e031305fd488 | Verification Record - Teambinder Material Approval
| checkpoint |  | 1.3 - Drainage Bedding Material
| note | 3defbde9-2d46-49c0-bc07-136ffc273b7e | Bedding Materials comply with Table 701.081 and 701.082.
| note | b85fc77f-a7ee-4dfd-9dcd-dfaaf3aa17a9 | Material Approved via Teambinder Material Approval Form.
| note | e1e6433c-fb28-4eec-b9b6-984241b76d0a | - - - - - - - - -
| note | aac9350f-51a7-4a35-a52d-168dfa30add5 | References - Table 701.081, Table 701.082
| note | 4b58706b-c9bb-4fa5-ad7b-10324792d3c4 | - - - - - - - - -
| note | 80fce6c5-d8f1-4b6a-a0e2-9f7cb1a1607f | Verification Record - Teambinder Material Approval
| checkpoint |  | 1.4 - Drainage Backfill Material
| note | b8369b39-dae0-4f02-be89-8b1c7c0ad07a | Select and Ordinary Backfill Materials comply with tables 701.081 and 701.082
| note | 5daad35a-f0d6-49ee-97cf-66efe2f9ebe1 | Material Approved via Teambinder Material Approval form.
| note | 5ec011a8-5ba6-4613-97c8-a2763fa1bdc4 | - - - - - - - - -
| note | d4b1209d-093e-4333-80c5-df5d610bd06e | References - Table 701.081, Table 701.082
| note | ecd43df2-ed82-4115-a897-78258c5a3a48 | - - - - - - - - -
| note | 44e74f3d-8df6-4fa7-b59c-0171a6637721 | Verification Record - Teambinder Material Approval
| checklist |  | ITP-CIV-PE Rising Main Supply & Installation Rev 0 | itp | ITP-CIV-PE Rising Main Supply & Installation Rev 0 | b8bcad88-3bbc-4ed0-9a66-a3e4c756aaea
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | f562eb69-1529-4d10-ae1e-d577ae761768 | Document Title: ITP-CIV-PE Rising Main Supply & Installation
| note | 4b616cfe-e1df-4ff0-8bc7-e2d0a8feb491 | ITP Description: PE Rising Main Supply & Installation
| note | 42f49c8f-8fa8-4371-9f28-0249bd0a066f | Discipline (e.g. CIV/STR/RAIL): CIV
| note | dc589b5b-8d36-46c2-a5ec-3bd9d01ffaf5 | Revision Number: 0
| note | 5029f95d-d1e5-4adf-971e-482bc9c30966 | Revision Date: 5/02/2022
| note | 9b0bb2e0-a712-46be-8cbc-a8cc9a327f6a | ITP created by: Michael Daly
| note | 160763ae-241a-450e-adf3-514878c5a83e | ITP approved for use by: Romualdo Magpantay
| note | 9ae1f20d-214c-4405-aefa-1704418fceab | 1.1 AS/NZS 2566.2
| note | b113f6ef-9d4a-4c54-b3bd-6111247dab45 | 1.2 VicRoads Sec 204
| note | 22f8e15f-94d0-4bca-ad08-e434af181e0c | 1.3 VicRoads Sec 610
| note | 29c32d67-d7df-456e-aed2-4c2f01bddfe0 | 1.4 VicRoads Sec 611
| note | 8ef32f8e-ac31-440e-97a2-c02b4adb2f99 | 1.5 VicRoads Section 701.22
| note | cdc2e58a-027d-4688-8833-9d629365108f | 1.6 VicRoads Sec 706.03
| note | 256c4480-f9d7-40cd-aad1-876546be7fcd | 1.7 WSA 03-2011-3.1
| note | ff6afeee-82f2-4755-85cb-964dd264c3ec | 1.8 WSA 05 2013
| section |  | Preliminaries
| checkpoint |  | 2.1 Compliance of Pipe Material
| note | c52c852c-f205-44a4-8146-6f3e74c1ff54 | REFERENCE: AS/NZS 2566.2
| note | 7bbe7b86-f48d-4237-9efc-d156960710d5 | ACCEPTANCE CRITERIA: Product shall be reviewed prior to delivery to site and uploaded and approved through Team Binder
| note | cfafcd11-204a-4e7f-8882-a49b3d995b83 | METHOD: Document Review
| note | ac63361c-d964-4463-a541-6e64bc906b65 | FREQUENCY: Once for each different supplier
| note | 24d1a428-9c18-4374-bf86-6f3c55fd9f6f | CATEGORY: HP
| note | b50ca0e2-f0ed-4421-b5ca-18c87dd19a2a | RESPONSIBILITY: SE/NA
| note | 58cc0d5e-059f-4a1d-8dcf-ffd6da9f6d54 | VERIFYING DOCUMENTS: Material Certificate and reference TB number
| textbox | 56a1b94d-436d-4b2a-98c5-3ad16451ae26 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Compliance of Concrete and Reinforcement
| note | 013da6c1-730a-4ff4-96f7-17b64aa473b2 | REFERENCE: VicRoads Sec 610 & 611
| note | 95edf999-57b3-4d8c-872e-71130f39761c | ACCEPTANCE CRITERIA: Concrete mix and reinforcement shall be approved for use prior to use on site
| note | 8154a83d-9886-4379-b6ba-b8ba18c483cf | METHOD: Document Review
| note | a865e18a-6011-4a46-a960-e09e2bbbaa50 | FREQUENCY: Once for each different supplier
| note | 30033f4a-aae8-4b3d-af5a-ad06bdc8bcee | CATEGORY: HP
| note | ac8ee829-7092-4128-96c4-be3fe60643c3 | RESPONSIBILITY: SE/NA
| note | 5e3f2410-9ca4-44b1-a694-601fcbf84b0c | VERIFYING DOCUMENTS: Material Certificate and reference TB number
| textbox | 00fe48a8-5f61-4daf-83e2-69b640b5c9a8 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Compliance of Backfill materials
| note | bb97d993-d03a-4bd7-b6ea-465742bb9083 | REFERENCE: VicRoads Sec 204
| note | f640dcfa-7f51-4e49-bb28-820f129841d7 | ACCEPTANCE CRITERIA: Product shall be reviewed prior to delivery to site and uploaded and approved through Team Binder
| note | bf919bb9-5005-47db-a4ec-fd1cb250191e | METHOD: Document Review
| note | 8571008b-2314-423f-a652-e9c4af320818 | FREQUENCY: Once for each different supplier
| note | bbb734ff-a7df-4842-910b-cc0c839e8b07 | CATEGORY: HP
| note | 16fac2dc-3857-4255-94bd-dfadca528ae6 | RESPONSIBILITY: SE/NA
| note | f91b6f6e-7420-4222-8053-ac7f2a72bb33 | VERIFYING DOCUMENTS: Material Certificate and reference TB number
| textbox | e0993ab7-c69c-4247-9807-b1119bd255a1 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.4 Transportation, unloading and storage on site
| note | d70e7225-10c3-4f44-8e8d-20c1c41376b4 | REFERENCE: AS/NZS 2566.2:2002 Cl 2.2, 2.3 & 2.4
| note | 27757a16-fd69-4f44-8698-7da770d0b60a | ACCEPTANCE CRITERIA: Pipes shall be transported in a way that prevents damage to the pipe in terms of bowing or twisting, scratches or rubbing etc.
| note | 62a3f514-5717-4390-a3c7-2879bc046c7e | Pipes shall be unloaded in a manner that prevents damage to the pipe in terms of permanent deformation, scratches etc.
| note | a3a24e93-f7c0-481c-99e3-f9c7ea3de3d5 | Pipes shall be stored on site on a level ground if necessary, clear of the ground using sand bags etc. and with spacings to prevent excessive sag. Pipes shall be limited to the height they are stacked on top of one another. Where pipes will be stored for longer than 12 months, or is expected to affected by high temperature or UV exposure, additional protection to exposure should be implemented.
| note | 2db70028-6302-49ad-82f1-34c2964767eb | METHOD: Document Review
| note | 7ad863e7-470d-4d7b-858b-2ec80f26aa33 | FREQUENCY: Once for each different supplier
| note | cca0c2ef-4a3d-4281-a076-c0f3cf1c055b | CATEGORY: IP
| note | 1c4a2a0b-7554-4344-abbe-4007400b2722 | RESPONSIBILITY: SE
| note | a5ad783e-9524-4c20-b195-08c23c89c4b0 | VERIFYING DOCUMENTS: Attach Delivery Dockets
| textbox | 341e17fe-8f53-4366-8521-6e6f03e63bf4 | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | 48e357f9-5727-477b-9049-2509e0a7690c | REFERENCE: Design Drawings
| note | a9e74675-5baa-45e0-92b5-65920a7d9f5d | ACCEPTANCE CRITERIA: The Contractor shall set out the drainage work in accordance with the drawings and approved by the superintendent prior to construction activities commencing
| note | 65e4d38f-e7f5-4b4b-9da9-58fbbf428194 | METHOD: Measure Visual
| note | efba4a25-090c-4fb6-8ae7-fada79858596 | FREQUENCY: Each element
| note | ec3f9743-4f4a-40fa-b367-caecb00eec4d | CATEGORY: HP
| note | edb985c0-3f5c-42a2-8925-6250534a4355 | RESPONSIBILITY: Surveyor SE
| note | 4a183544-3130-48f0-9483-efde07df545e | VERIFYING DOCUMENTS: This ITP
| textbox | 9c4dd8cc-1968-4bfb-8b26-80f3f10bdb53 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Excavation
| note | def30729-866f-4990-9f44-56284953508e | REFERENCE: Design Drawings
| note | 485de098-ed12-4c60-acdb-fcb0fff7d09c | ACCEPTANCE CRITERIA: Excavate to the trench dimensions as specified in the IFC drawings
| note | 96b4661f-5d68-4e24-a696-953809a4024b | METHOD: Visual
| note | 5e750220-994c-4007-b24e-e64f702c6f3a | FREQUENCY: Each lot
| note | a7d77464-ef59-4a40-84c7-b8dae33835ed | CATEGORY: IP
| note | 20f405b7-5e29-4682-b007-8a596d719d82 | RESPONSIBILITY: SE
| note | 0716921e-61e9-4e03-a935-2310d521c651 | VERIFYING DOCUMENTS: This ITP
| textbox | 641c75af-e866-4116-ac69-311a4194b284 | Date Completed:
| checkpoint |  | 4.2 Minimum Bedding Depth
| note | edfc4373-ae12-4df2-b51e-e8b17231a8e9 | REFERENCE: AS/NZS 2566.2:1998 Table 4.2 and Figure 1.1
| note | e3b6d891-dbfc-41ef-b820-40907c332b0a | ACCEPTANCE CRITERIA: Where pipe diameter is between 450 and 900mm, minimum bedding depth shall be 150mm, refer to design for bedding depth
| note | 8ddfe34f-2b51-4e15-9125-10e8e69930e9 | METHOD: Visual
| note | ebbffe1f-7759-49fc-a84b-03fcc573ba2e | FREQUENCY: Each lot
| note | 53deb70c-6018-4085-94db-1d4996ea6703 | CATEGORY: IP
| note | 59aafa9b-b420-4d8a-b474-5e18adcc450c | RESPONSIBILITY: SE
| note | 4a817622-9560-4679-aefa-d60748163ffe | VERIFYING DOCUMENTS: This ITP
| textbox | 73da799c-9f79-4a1e-8b98-218046a17187 | Date Completed:
| checkpoint |  | 4.3 Minimum Embedment Width
| note | 49d2e2c7-a33f-4419-880a-b2201860357a | REFERENCE: AS/NZS 2566.2:1998 Table 4.2 and Figure 1.1
| note | ea5f235c-9e6f-4399-a835-20e32dea1e11 | ACCEPTANCE CRITERIA: Where pipe diameter is between 450 and 900mm, minimum embedment width shall be 300mm, refer to design for embedment width
| note | 8175017b-00d9-4e93-b026-19558955a326 | METHOD: Visual
| note | 294a1e61-06b7-40dc-9903-c59ebc7982bd | FREQUENCY: Each lot
| note | da474660-45f5-4b60-9d11-05ba97ee3c8e | CATEGORY: IP
| note | 365ef5d9-4b07-4a1f-bf69-caeb3239f846 | RESPONSIBILITY: SE
| note | 97830999-005d-40a8-8ebe-b4c8306893a0 | VERIFYING DOCUMENTS: This ITP
| textbox | dd67460b-0d4b-4a8c-b687-3a4a252de214 | Date Completed:
| checkpoint |  | 4.4 Minimum Bedding Overlay
| note | 5c824c73-c08e-4791-9b4c-a13c9730b2d8 | REFERENCE: AS/NZS 2566.2:1998 Table 4.2 and Figure 1.1
| note | af15444a-5187-43dc-b7f8-471893cb2fcd | VicRoads Sec 706.03
| note | 4622cdef-800f-44f2-aefb-06c0d1c5c601 | ACCEPTANCE CRITERIA: Where pipe diameter is between 450 and 900mm, minimum bedding overlay shall be 150mm, refer to design for overlay requirements.
| note | e0b9e3dd-b2ef-411b-8f33-ad6aa65c2cf1 | Pipes within the road reserves shall run parallel or perpendicular to the centreline of the road.
| note | 92291899-c066-4062-a042-44a0377b8a4c | Pipes should have a minimum cover of 1200 mm to the finished road surface level and a minimum 750 mm cover to the invert level of road carriageway open drains
| note | 90196e8d-0480-4d27-b6ce-081e7c6291f7 | METHOD: Visual
| note | 78b0db7b-e498-4291-a249-3525f1cf81f0 | FREQUENCY: Each lot
| note | 03516af0-c7bc-4ad5-a570-d569c244ef53 | CATEGORY: IP
| note | 8a4f65a6-5610-450b-b3a0-b5a2ecf99d1a | RESPONSIBILITY: SE
| note | efffaea9-381d-4b91-bbf3-83ba457ec620 | VERIFYING DOCUMENTS: This ITP
| textbox | be5af695-e0b1-4e84-81a1-860721795f7f | Date Completed:
| checkpoint |  | 4.5 Welding Pipes and installation
| note | fd18139c-ca96-42d6-862c-22dba989d1c0 | REFERENCE: WSA 03-2011-3.1
| note | ac9296e3-f10b-41c6-8234-e4632229c1bc | WSA 03-2011-3.1
| note | 36db5d4f-e6af-4f38-b33f-2eec39d145e3 | ACCEPTANCE CRITERIA: Welder should be competent and qualified
| note | 5231891e-f554-4e5b-b807-942cfc9c99eb | Welds shall only occur in dry and dust-free environment. Ends of pipes shall be capped or blocked prior to welding to prevent air flow through. Welders to use a shelter unless completely rain and wind free
| note | 63875fd2-37dc-442e-8afe-cd7f3f49b7a2 | Record sheet of all welds should be provided by the subcontractor.
| note | f107e246-99a6-4b08-8611-a602e5db540d | Undertake single pressure low fusion jointing pressure (SLP) unless otherwise approved
| note | 63e3c4f6-fe4c-43b3-9727-8dadb741b5f7 | Stamp all beads with the welder's identification number which shall be recorded as part of the record sheet
| note | 291aff43-e8b9-4de7-b332-a3a4d5c55fb6 | Destructive Test one in every 40 and at least one in every project for welds greater than 280mm in diameter
| note | b67cef61-3178-4d01-97b5-a491633b51db | Pipes shall be positioned so embedment material can be placed and compacted as required. Any adjustments to the alignment of a pipe shall be done by re-lifting the pipe without disturbing the integrity of the joint and placing it in the correct position.
| note | d16a3bd3-587e-40f3-bb51-f1126386aece | METHOD: Document Review
| note | e8d82e2d-447b-4425-a3ef-3c2cf2d57b5f | FREQUENCY: Each Lot
| note | 1dbc0b01-dbad-4474-adea-466a7406ddcd | CATEGORY: IP
| note | b00f4b35-6941-4837-8c40-1a1b01d4ca37 | RESPONSIBILITY: SE
| note | 7f810100-7ebd-4445-bf97-77fa48a0a8b9 | VERIFYING DOCUMENTS: This ITP , Upload welder qualifications , Upload Weld Record Sheet , Upload destructive test results
| textbox | 7d305b3a-9786-47f9-97eb-78e2402f0034 | Date Completed:
| checkpoint |  | 4.6 Compaction of Embedment Material if Applicable
| note | 12b171e8-1323-43f3-99b9-7fd261463c84 | REFERENCE: VicRoads Section 706.07
| note | 44143a28-b08d-4707-9e78-8576b6559099 | ACCEPTANCE CRITERIA: Where bedding material is required, bedding shall be placed below, around and above the pipe or carrier-conduit for the full width of the trench. Not less than 25 mm compacted depth of bedding shall be placed below, and not less than 150 mm compacted depth of bedding shall be placed above, the pipe or carrier-conduit. Bedding shall be placed in layers not exceeding 150 mm loose thickness and shall be compacted as specified.
| note | 34312d72-c5f7-421d-8201-b96066b72574 | METHOD: Document Review
| note | 9fcb0249-dde6-457b-a382-fb4603485f37 | FREQUENCY: Each lot
| note | 6d9cefc3-e320-467b-837e-06334b96cea7 | CATEGORY: IP
| note | bfcd6095-a1f8-4b19-9dbd-2903cc8a42fd | RESPONSIBILITY: SE
| note | 806f5a2f-d789-40a5-9496-ba7e8ecd8b77 | VERIFYING DOCUMENTS: This ITP
| textbox | b3e46cbd-eabf-4a3c-8757-7450d35b4376 | Date Completed:
| checkpoint |  | 4.7 Concrete Encasement
| note | 82aac220-171d-4f52-ad21-a271f91b5138 | REFERENCE: AS/NZS 2566.2:1998 Cl 5.8.3.
| note | 5ce84f60-7083-4158-bc6e-4fe4278b042d | ACCEPTANCE CRITERIA: Where used, construction joints in a concrete encasement shall align with pipe joints where an elastomeric seal joint system is being used. During placement of concrete, or grout, around a pipeline, flotation of the pipeline shall be prevented, deformation of the pipeline shall be prevented, and the allowable hydrostatic buckling pressure of the pipeline shall not be exceeded.
| note | f776a623-aa34-4bde-aa16-028c65ecdb6f | METHOD: Visual
| note | 6efa82e3-0d60-495c-ae99-9a8930601e5a | FREQUENCY: Each lot
| note | b76cef10-1444-43a9-8310-aea4935a6599 | CATEGORY: IP
| note | 474d653c-8b77-4e46-ab7c-068e6293594c | RESPONSIBILITY: SE
| note | 41871c87-6c7c-4f65-a383-4d1b7b988c67 | VERIFYING DOCUMENTS: This ITP , Attach concrete test results
| textbox | 73a81d2f-bf73-42e0-99c6-1c1cc90034b2 | Date Completed:
| checkpoint |  | 4.8 Pressure Testing
| note | 64b03e4a-11c3-43de-88d2-f107921399da | REFERENCE: AS/NZS 2566.2:1998 Cl 6.3
| note | 255f94dc-8718-4107-bf7c-6fc964bf7a15 | WSA 03-2011-3.1 Cl 19.4.1.1
| note | 9402d31b-4c67-4837-9390-4cb91ee6c0b5 | ACCEPTANCE CRITERIA: Test and measure pressure of pipeline for PE pipe in accordance with WSA 03-2011-3.1 Cl 19.4.1.1.
| note | 2c8b447e-56ce-4429-b656-f7c97ba0ebb7 | Ensure steps of WSA 03-2011-3.1 are followed and pressure is raised to level as per design drawings
| note | 493d26dd-5bb4-4914-87d2-1cf57400c2f0 | Ensure test passes as per WSA 03-2011-3.1(g)
| note | 11989a9f-6d23-416d-9aa5-1b43fa124a21 | METHOD: Visual, Test report
| note | 4fe369b8-2c1d-4f5f-ba4d-124e689aa2ff | FREQUENCY: Each lot
| note | dd58adab-a990-47f0-923d-2b9bb1a2679d | CATEGORY: HP
| note | 026f589f-1e06-4276-a018-53bd1f689173 | RESPONSIBILITY: SE/NA
| note | 90cb3f8f-e289-473c-b182-686d0631da42 | VERIFYING DOCUMENTS: This ITP, Upload test, report/subcontractor ITP
| textbox | 0e6020c7-6d34-4ab2-9c1a-fa6fa1a07dae | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.9 Assembly of Buried Flexible Pipelines
| note | 2a8f42d1-5937-4539-ad38-8999663aefdc | REFERENCE: VicRoads Section 701.22
| note | 195dcd4e-7ed6-4b6c-b472-f4e97cab7001 | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied by the Contractor shall be assembled in accordance with the manufacturer's assembly instructions.
| note | 45a8e51b-75e5-4537-80f2-9e581e07f56d | Where sections are supplied free to the Contractor, the following will be provided:
| note | 316ba6b1-ab92-4763-b823-0508390ef0ab | Manufacturer's Assembly Drawings
| note | 19689c00-dd56-4571-baf9-f3a4ec096210 | Schedule of Parts Supplied
| note | 03e5857b-9410-4344-8224-f7bc51331e03 | General Assembly Instructions.
| note | 0b03ecfe-c51e-4e01-9bd8-2091f555af8f | METHOD: Visual
| note | 2863f726-d7de-41a1-bc61-b30f22b443fa | FREQUENCY: Each lot
| note | 491be692-14e4-4c0e-85e3-100c4773cc31 | CATEGORY: IP
| note | fc8ad485-f3c9-4d1f-b896-84f2fb479ebc | RESPONSIBILITY: SE
| note | 16a14b5b-03df-4a9d-9672-dc0894788330 | VERIFYING DOCUMENTS: This ITP
| textbox | 589b6b4b-10ce-45fe-9cb4-9f9c47f70068 | Date Completed:
| checkpoint |  | 4.10 Backfill and Compaction
| note | bd81589d-ffb4-45bb-8c54-32f43ec4cd60 | REFERENCE: VicRoads Section 706.08
| note | 97c43b02-dd6a-46db-a0d6-5b42e2d09a95 | ACCEPTANCE CRITERIA: Backfill in paved areas including shoulders and verges
| note | 0f5f9f5b-873a-4dcd-a706-8689c859784b | Where trench has been excavated from designed subgrade level or above, the trench shall be backfilled with selected backfill in layers not exceeding 150 mm loose thickness
| note | e4b03750-380b-4afb-8a82-180752e25933 | Where the trench is excavated from below the nominated or design subgrade level, the trench shall be filled with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness.
| note | 55cf0f55-2a4c-4b63-a82d-609209347743 | Backfill under area not to be paved
| note | cc0264d3-4886-4c42-ac60-cfa62d6918cd | The opening shall be backfilled with common backfill placed and compacted as specified in layers not exceeding 200 mm loose thickness.
| note | 719328fe-c107-4746-9b38-0d00b0127b2d | METHOD: Document Review
| note | 4511d38c-ee08-4304-8767-7cf53c975043 | FREQUENCY: Each lot
| note | 2d019f44-6536-4c42-ab61-4ed5759533ce | CATEGORY: IP
| note | d03ed659-a218-46cb-8186-c82defa2202f | RESPONSIBILITY: SE
| note | 6bd16905-11d2-46ec-bcc6-bbe5fba89096 | VERIFYING DOCUMENTS: This ITP
| textbox | bb745fee-7f0c-49bc-a0bd-8e0422b7053a | Date Completed:
| checkpoint |  | 4.11 Compaction of backfill (outside of pavement)
| note | e55009a3-3bc4-465e-b7c8-66779e5730b6 | REFERENCE: VicRoads Section 706.09a
| note | 0608389a-7b3a-4ed3-84ee-122a30937e11 | ACCEPTANCE CRITERIA: Unless otherwise specified, bedding and backfill shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard compactive effort. For backfill of nominal size greater than 40 mm the fraction of material passing the 37.5 mm sieve shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined for that fraction in the Standard compactive effort.
| note | 470ca0c7-7d8a-44be-909b-f615cf873924 | Bedding and backfill shall be compacted to refusal using hand held mechanical equipment.
| note | b515a2ee-fd02-448f-b5e1-2579a46048f2 | Backfilling beneath areas to be paved shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97%. The calculation of density ratio shall be based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
| note | 9bb62efa-2c8f-4f79-83db-7f239cfbe54c | METHOD: Document Review
| note | 1be282aa-2b4a-4908-a3a5-73528d36844b | FREQUENCY: Each lot
| note | 0c741b78-f041-4f9a-be29-162a4df2d5c9 | CATEGORY: IP
| note | f774c46c-1994-49f1-8e01-93f6640cb708 | RESPONSIBILITY: SE
| note | 34e35f55-d1f0-425a-8433-b68aa26612c4 | VERIFYING DOCUMENTS: Upload Geotechnical Report
| textbox | c9219178-d7d1-484b-bab1-f68a1f525645 | Date Completed:
| checkpoint |  | 4.12 Compaction of backfill (inside area of pavement)
| note | ee52b08e-ec6f-4513-b9c8-328bc5bc2aba | REFERENCE: VicRoads Section 706.09b
| note | 6ecb36db-07ee-46db-aa9d-e79096630a06 | ACCEPTANCE CRITERIA: Unless otherwise specified, pavement material shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified compactive effort.
| note | 9fa7b3c8-0a11-4a2f-99db-a69dbb66465c | Pavement material shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three. All pavement layers shall be compacted to a mean value of density ratio not less than the percentage specified in clause 706.12(b). The calculation of density ratio shall be based on Modified compactive effort. All pavement layers shall be tested.
| note | f9fc6096-e471-4750-99eb-e93ba57e6c97 | METHOD: Document Review
| note | e6aee4ff-d1b2-4ad4-bbd2-1e3bdd81ef0e | FREQUENCY: Each lot
| note | d05fee4b-5b9b-4f03-b51b-6529224a7368 | CATEGORY: IP
| note | b52ff374-e35a-4464-9562-dee61046fafc | RESPONSIBILITY: SE
| note | 2a4ad3e6-b873-471a-a3ec-c81324a153d9 | VERIFYING DOCUMENTS: Upload Geotechnical Report
| textbox | d4818ecc-e61b-4f4f-b8c4-7b32fe121dad | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 As-built Survey
| note | e2c276d9-5334-4f4a-82cf-b9c59cfa9ada | REFERENCE: IFC Drawings
| note | 52a5a748-20f3-4bf7-95e3-ce0ce2948625 | VicRoads Section 701.10
| note | a1af34b4-c274-42b6-b9b9-f1850879716a | ACCEPTANCE CRITERIA: Provide As-Builts survey of installed PVC Pipe
| note | d8bdfcb9-7b66-4f3a-b5f5-c7c42f1119fd | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
| note | 1aa86af6-76a0-48b9-a570-d8363ead4ccc | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
| note | 1240578a-26c5-4101-b8b1-9aec9d4c86a8 | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
| note | d424bb6b-57ca-4bb9-9380-4ebde9dcfd0a | (c) invert level of pipes at pits ±50 mm
| note | eaa4d5a4-731a-493f-8832-b48126d51cbd | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
| note | 2aad1061-87c0-4326-8dd8-d2eb7beba5e2 | METHOD: Document Review
| note | 930449ad-4a7e-404b-a3dd-738dc4b45fd3 | FREQUENCY: Each element
| note | 0c932a3e-3987-46a2-af21-4cc197f68e1c | CATEGORY: IP
| note | 5120a9e0-da1a-4b0a-86fc-774f1b4bcd78 | RESPONSIBILITY: Surveyor , SE
| note | 413af77e-3daa-408c-b242-2fe3b1cac017 | VERIFYING DOCUMENTS: Attach As-Builts Document
| textbox | 2e3d729b-a9c9-4cea-8618-f46c77095062 | Date Completed:
| checkpoint |  | 5.2 Inspection of Drainage Lines
| note | c169af65-55f1-454b-a885-af0621275e20 | REFERENCE: VicRoads Section 701.30
| note | f8695166-ad09-44b7-9eca-706c052e3606 | WSA 05 2013 - Conduit Inspection Reporting Code of Australia
| note | c65d9640-b386-4694-820c-77eadcb458ef | ACCEPTANCE CRITERIA: Flush the pipe to remove sediments.
| note | af04d584-663a-40a2-996b-880c9412ab8e | All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
| note | 58664443-f88e-4ef9-ba39-73bdd63b73b4 | Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
| note | c3c2fc30-d3f8-49fb-9b52-5d1c3b78f32e | The report shall be provided to the Superintendent, with a copy of the CCTV record including any video recordings and a summary of the location of any defects detected by the survey.
| note | 96554e69-cb60-44d4-ac21-86274be1135a | Any sections of damaged pipe or box culvert which do not comply with the requirements of Clause 701.31 shall be removed and replaced.
| note | 5369b22b-6e1f-416d-b3b7-fdb4e383edc2 | Where approved by the Superintendent defects shall be repaired in accordance with the requirements of Clause 701.31 and a further CCTV survey shall be undertaken to verify correction of the defects.
| note | 5a3c9af8-bb52-402d-ad8e-72ff00a97ba0 | Inspection of existing drainage lines shall be as specified in the drawings and specification.
| note | f78fcb90-022c-4124-b9fb-26a2fa20ef68 | METHOD: CCTV Document Review
| note | 37f005a8-5f90-4f93-bfb7-d322ae8db4df | FREQUENCY: Each lot in its entirety
| note | 79b89486-83ae-4df7-bbe4-2ba63e2d7260 | CATEGORY: HP
| note | d96f3871-6fcd-4445-b742-a0c080c86a8e | RESPONSIBILITY: SE/NA
| note | 275590a3-58d8-4aaf-8d84-8cdfbc8a3070 | VERIFYING DOCUMENTS: Attach CCTV Inspection Video
| textbox | 7028fe3d-740a-47f7-9d81-1ccfe2db7899 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.3 Repairs to damages
| note | cbbeef33-8a0a-4ac2-99d7-e3a6ea0e88af | REFERENCE: VicRoads Section 701.31
| note | 7f576216-8e76-4950-80bf-397258a742a2 | ACCEPTANCE CRITERIA: Flexible buried pipes which exhibit defects or are otherwise damaged prior to laying and backfilling shall be rejected.
| note | 132a0288-30ab-4c54-b5e2-2568750850c2 | Where inspections after backfilling identify any defects, such pipes shall be removed and replaced, unless the Superintendent approves repairs to be undertaken in accordance with the manufacturer’s repair procedures and materials.
| note | e9f01b0a-e594-4b94-aedd-485807adf7f1 | METHOD: Visual
| note | 4e56d80c-acdf-4e5b-bb46-260fc9e83b9f | FREQUENCY: Each element
| note | 4266d6c5-5ac1-4fa3-9e72-4c412bcfc766 | CATEGORY: HP
| note | 1883f81a-dde1-48f3-804c-d1f779b8ed86 | RESPONSIBILITY: SE/NA
| note | ae0604ec-c493-44e2-b52b-1ec0e4278825 | VERIFYING DOCUMENTS: This ITP
| textbox | 781d1eac-3906-424e-bcc2-9a4578d83711 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4 Non-conformance Report (NCR) Closure
| note | 3f77c5a2-26f6-436b-a7c3-741f58495698 | REFERENCE: MRPA Quality Management Plan
| note | 4057d3e3-2059-4bf6-ba14-d682b57c7f0c | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 2de8752f-74f2-4ea0-b976-dd06e90557e3 | METHOD: Document Review
| note | 0f247321-abd1-4e21-815b-6199f9977e60 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 2efe071a-5de8-45a1-b567-acc73ad9aa38 | CATEGORY: HP*
| note | 4031b6de-dce4-4ef1-8980-a4d9afee0824 | RESPONSIBILITY: SE/PE/SPE
| note | b80dce77-350d-4eea-87ab-cec0b8358d4f | VERIFYING DOCUMENTS: This ITP
| textbox | 16b3a33a-c642-4553-89c3-4de78206e3c5 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | f96daf8a-b20a-434e-8a25-77fc7f257cd6 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | bb7fca47-e8b8-41ff-b2ac-a7dae8694d4f | Name:
| textbox | 67341cec-bef3-4bfd-baf8-eb04a90d29e6 | Position:
| textbox | 362641b1-5baf-4d88-afe8-ccb28d92211a | Date Completed:
| signoff |  | Sign ITP
| checklist |  | Materials Inspection Checklist |  | Materials Inspection | b93cf35f-729d-4065-b63a-91f768955d6d
| section |  | Details
| checkpoint |  | Details:
| textbox | d7357789-b485-4963-abe1-485435e60709 | Project Details:
| textbox | bd1ddad0-59b7-41ca-8b93-ec569e72b217 | Project No:
| textbox | f1e4c619-3444-4b23-8aef-a0d040aa1aa0 | Lot No:
| textbox | a69655e5-d413-408d-bca5-94497d2cc9b6 | Delivery Docket No:
| textbox | bb3c7c3e-0681-446f-a30f-b7fb67b96621 | Nominated Equipment:
| textbox | 26898025-afc6-40cd-b0c4-098cf03bdf54 | Delivery Date:
| section |  | Packaging Inspection
| checkpoint |  | Is the condition of the packaged goods acceptable?
| checkpoint |  | Number of packages in the delivery match that listed on the freight list/packaging slip?
| checkpoint |  | Does the delivery match the order?
| checkpoint |  | Do the contents of the delivery match the freight list/packaging slip?
| section |  | Material Inspection
| checkpoint-no-value |  | Verify each item meets all the criteria listed below:
| note | 93b7c5e0-c656-418f-8805-00b82e1a7be7 | Is supplied in the correct quantity
| note | 88443e14-0b4f-4fcf-8ab2-f4c5cb639582 | Is complete in all respects
| note | 10feed41-a26c-4242-9970-378d373bc40a | Is the correct make and type
| note | 2517b9d9-7851-4b21-a841-38f99422b352 | Shows no evidence of transit damage Is clearly and correctly labelled
| checkpoint-no-value |  | Fault ID:
| note | a19bfef3-b531-4ff7-b7b5-d0d1015a9896 | OK = Meets all criteria
| note | 712a9688-1f5b-4d5a-a243-27e22ed89501 | QI = Quantity incorrect
| note | 015d505b-e6a8-444a-a6a9-dddd4bf8ba20 | IN = Item incomplete
| note | 78a27a91-6fe1-4b82-a95b-665f92a2c949 | MI = Make or type incorrect
| note | 7b38f4cd-0c9f-4b40-85f8-e57aac1dd7aa | TD = Damaged in transit
| note | 9b04ee90-80fd-452b-8b8a-90ac0f251931 | NI = Not properly Identified
| checkpoint |  | 1
| textbox | cfcf00cb-3fdb-4a2c-8914-84bf4783a252 | Qty:
| textbox | 8fc186e7-4992-434b-a117-b590cb65b559 | Description/Part or Serial number:
| button | 2299a5e4-5757-4c98-acff-5be7a2daf30f | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 2
| textbox | 3e9e7e94-49e7-4547-bc37-d0d376384142 | Qty:
| textbox | e2114911-6794-447a-b411-60dabb199968 | Description/Part or Serial number:
| button | 999907ab-b121-4659-bbff-defd56904185 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 3
| textbox | b09b9382-3ad4-4f7d-8432-e5b9d7514de7 | Qty:
| textbox | 8ac87746-0fd3-4bdc-9532-1effe9bbe9c5 | Description/Part or Serial number:
| button | f75729b7-fe67-4edb-a68f-d7f78cb8cfe1 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 4
| textbox | bfded274-3b12-4965-8bfa-3e16ef7e3a9d | Qty:
| textbox | 246e6d9c-fc52-4801-b975-9114115dbb8b | Description/Part or Serial number:
| button | 2e33d34c-bf54-4be1-a03b-3bb632187291 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 5
| textbox | 00391823-f930-4b07-97d2-02a5f32d9a6a | Qty:
| textbox | 20bc3b57-ec49-4c07-8c25-0347765015a9 | Description/Part or Serial number:
| button | 942b3e55-54c9-49ca-85cd-03d85fc25278 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 6
| textbox | 513b8587-47a8-44ac-8d3d-14558bf39bb9 | Qty:
| textbox | 0c7de041-9cb1-4132-9215-ee5d6f4d5683 | Description/Part or Serial number:
| button | af7767cb-4d53-4e67-ba6e-f43ddafdc441 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 7
| textbox | 75364265-03ac-4d33-ae82-d8c85ab72dab | Qty:
| textbox | e235474f-8d6d-4cce-91c0-79a14ca0568a | Description/Part or Serial number:
| button | 74187bb8-083c-487e-b298-064d9cb9015b | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 8
| textbox | 2b9c5a01-8510-40a9-8ca6-779e7ac7f64c | Qty:
| textbox | 44b3e9ec-0c4c-4d24-b4ae-aa0896666ced | Description/Part or Serial number:
| button | 63ed11d3-8348-4d07-a481-e43200f5384a | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 9
| textbox | fee46d09-cfe3-4d8b-98a7-8dee87d86fc5 | Qty:
| textbox | 21c40884-e591-4087-817b-35604a1e8146 | Description/Part or Serial number:
| button | bf79ef2c-c40f-4b4b-ba7e-3f2414a8f19d | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 10
| textbox | a5bf3863-d854-4c23-93f0-7bf7b45dd7a7 | Qty:
| textbox | e50c7dbd-ca7d-43f3-9cb8-5504d22825d9 | Description/Part or Serial number:
| button | cd78f640-7166-4198-b6b5-3633122d04b5 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 11
| textbox | 6ceb426a-61e0-49dd-98d8-1bc81317abd0 | Qty:
| textbox | c5bb3dae-9b0d-48ad-92ef-99ab6471c494 | Description/Part or Serial number:
| button | 4481d520-87e0-435f-84f7-537c6dd460dc | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 12
| textbox | d8dedce3-0261-4ef4-ba4c-936bca5efbeb | Qty:
| textbox | 6e05e689-7b61-46b0-a322-6f9e72441074 | Description/Part or Serial number:
| button | 8ec72698-0ea9-4523-a206-de51d127d054 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 13
| textbox | afb5b7c4-b561-4edb-8071-ac0dc8e21389 | Qty:
| textbox | 6e5e115b-355b-4b1e-b4b5-ac5452dfe28e | Description/Part or Serial number:
| button | 0a51a108-ed32-4e1b-8392-b11132718158 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 14
| textbox | 9b6146d4-7f6b-4bd4-adcd-860627b1628c | Qty:
| textbox | 0df3ef3d-9902-42f8-8901-141a3c85a97b | Description/Part or Serial number:
| button | 417e7ca3-0b2f-4ce2-9743-b8e202ccd645 | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint |  | 15
| textbox | 07588345-b577-44b9-8169-8dc5f4845373 | Qty:
| textbox | 99ba23b6-9fab-4643-959a-cb86a5a5604d | Description/Part or Serial number:
| button | f692a24b-3711-4e04-98bb-5b7a174d1ceb | Fault ID: | IN, MI, NI, QI, TD,OK
| section |  | Sign Off
| checkpoint |  | Accepted By (MRPA)
| textbox | 53931074-0dc6-468d-9ea5-6de0c4c7e125 | Name:
| signoff |  | Add Signature
| checklist |  | ITP-CIV-Pits & Conduits - V-Line (Supply & Installation) Rev 1 | itp | ITP-CIV-Pits & Conduits - V-Line (Supply & Installation) Rev 1 | b95ea496-169a-42a1-aefe-d17409183b83
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | e41f7184-2e7d-4f8b-92eb-f97e4be23c40 | Document Title: ITP-CIV Pits & Conduits - V-Line (Supply & Installation)
| note | 396b8a47-341f-4854-a6a2-12a7f9a25b0b | ITP Description: Pits & Conduits - V-Line (Supply & Installation)
| note | 1d8d5227-2b68-4302-a6dd-af67efe000b5 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 93623c56-ed2b-4b86-85cd-aaf59bc53235 | Revision Number: 1
| note | b2e77acd-0fc5-4ba9-9c2b-ab16a5917ee6 | Revision Date: 26/04/21
| note | 75cfe026-1169-42af-a9c8-cc16e15c9257 | ITP created by: Michael Daly
| note | efe43dd4-1e41-4312-a781-a5029a40d637 | ITP approved for use by: Josie Pavlou
| note | bd3937c9-3bf3-44b6-8f31-6364437e251b | 1.1 IFC Drawings
| note | c392f232-bd26-4e54-8096-839e65e7f1e4 | NIST 012.2
| note | ac727707-2e8c-402e-8c67-549b09b33c60 | NIST 012.2.1
| note | 0f88190a-118c-4ebe-a62c-0ea1833adbbf | Australian Standards
| section |  | Preliminaries
| checkpoint |  | 2.1 Conduits
| note | 23bfbc0a-2836-4a46-9e8b-3f2462833c13 | REFERENCE: HV Conduit: AS 2053
| note | 3314cada-70e1-466a-b19f-c59ddea11b89 | HV Conduit (boring): AS 4130
| note | ba6bae6b-77f2-46d0-b1bb-02ba0d0061ce | Comms Conduit: AS/ACIF S008:2006
| note | 7b94c62b-dc5a-4e9b-bb5a-622813f07bd1 | LV Conduit: AS/NZS 3000 - 2000.
| note | fed6d4ec-7c35-465a-86b5-4a5568390fce | NIST 012.2
| note | 01b75df8-aef6-41eb-ab8e-b8efefd43b02 | NIST 012.2.1
| note | 3776b8af-9be4-47d4-b26e-45b63dd42dc0 | ACCEPTANCE CRITERIA: 22kV Conduits: 150Ø (160mm OD), orange electrical heavy duty 8.8mm wall thickness, greater than 1.65x cable diameter for single cable
| note | f57216b5-2886-4a00-aff2-d5ce297dc860 | Comms Conduits: 100Ø (114mm OD), PVC White comms conduit 4.6mm wall thickness
| note | c23d07b6-2766-4ba7-9753-62a7da4d402a | LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
| note | cd465f4b-8c1c-4047-a91a-1aafaeeadc23 | LV & comms conduits to have a min. 600mm bending radius
| note | d408c316-b9a2-4310-9f3a-f2449fa22c30 | HV conduits to have a min. 2000mm bending radius
| note | 7c026868-facd-4e74-acc7-c13f1ed33596 | Inspect materials upon delivery and attached delivery dockets.
| note | e043a620-5435-464a-a1a7-0e2601e41a50 | METHOD: Document Review
| note | fa5dffe3-0b83-4f70-acff-f732bea697f6 | FREQUENCY: Each Material Type, Each Delivery
| note | 641eaad3-5bd9-4c36-9de0-45f9608c2b71 | CATEGORY: IP
| note | 7b2f7c37-d866-4355-8740-7479f4e30bac | RESPONSIBILITY: SE/PE
| note | 36785d60-6ec6-4670-b8a4-83f6c04fceae | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | 9d5deb4f-a4ac-45a1-8fef-d9df413e2f7d | Date Completed:
| checkpoint |  | 2.2 Pits and Pit Lids
| note | 89ee0e29-0109-40e5-83e4-e6eec7d6580d | REFERENCE: IFC Drawings
| note | f7d8cd8c-7815-40b8-a5c6-b2f644e8cee4 | NIST
| note | 4e8f5094-445d-4dc1-9608-8fdadf5c2d80 | 012.2.1 Section
| note | ccc933d5-6d43-4e39-8580-7694e5edecc5 | 6.15-16
| note | a767c262-a5d4-4545-b753-37979afe6e11 | NIST 012.2.1 Section 6.9
| note | 829aff51-87b8-4d2f-a39d-9cdb9c0ec537 | NIST 012.2.1 Cl.
| note | 5215de08-f40a-4c02-82d4-f071415d5871 | 6.7 (c)
| note | 70b50f9e-353d-4006-8f50-ae8d213c9556 | AS1289
| note | 70011c94-f6f2-4325-9096-2ea4c35efd44 | ACCEPTANCE CRITERIA: Pits: located within 1.5m of nearest rail, pit to be 300LA Railway loading
| note | 0352c935-0ecf-4a7a-8ab3-12fadb1bf3a9 | Pits 900x900mm or greater, multipart pits lids to be used.
| note | 7ce6be36-cc8d-4e92-a52e-86a74fa1e983 | Concrete Pits to be made as per AS 3600
| note | 72adaf1d-8e03-4919-ae3d-4d7eb793d6c0 | Pit lids: Covers shall comply with AS3996-2006
| note | d756764a-85af-45c9-bd3e-8d804a3763d8 | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
| note | dfac5b89-81fb-451c-b46d-4c5971f0738b | HV Pit Cover: pit covers shall be labelled with the words “DANGER - Railway High Voltage” (L1-CHE-SPE-070 13.4)
| note | 6382e073-a281-44c9-bd85-a3539ae158c4 | LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
| note | dc869616-60cf-455b-ade3-b90f3f3160cf | Inspect materials upon delivery and attached delivery dockets.
| note | e10b2ccf-34c6-41d6-93ed-68e0809e8112 | METHOD: Document Review
| note | 1ed40f3c-b870-42d8-9fce-685883ab5d7b | FREQUENCY: Each Material Type, Each Delivery
| note | 9464e792-30e2-4b50-b41e-2e7902fd80f4 | CATEGORY: IP
| note | db148af4-ac18-4a39-b3f6-12eac1315978 | RESPONSIBILITY: SE/PE
| note | bc811172-5c98-4363-98ef-2dfb99f668b7 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets , Attach Precast Birth Cert
| textbox | a73316c9-cf0e-457f-85e9-a0e72d1de9fb | Date Completed:
| checkpoint |  | 2.3 Warning/Marker Tape
| note | de41f661-904d-4bb5-a97b-7fc551e44ff0 | REFERENCE: IFC Drawings
| note | 2c88f87e-c35e-451f-a6c6-b9dc568ffbc6 | AS/NZ 2648.1
| note | c31e32b2-147a-4ee5-b361-ca14c6d0bff6 | TS-SP-013
| note | 0ddc128a-2787-4c6a-b740-e74541c6bee2 | L1-CHE-STD-043 6.4
| note | a8a56caa-421b-4d67-90ad-32176ee0aaaf | ACCEPTANCE CRITERIA: Warning/Marker Tape:
| note | 1495b5d9-8722-4917-8e4a-dd46da042119 | Above LV: 150mm minimum wide orange coloured PVC
| note | 462fd5d3-9dcf-46f0-a51c-b8d00232cd9e | ‘DANGER RAILWAY SIGNALLING CONDUITS’
| note | 734dd97e-8634-4812-909b-21f8f38d4a25 | Above Comms: 75mm minimum wide white coloured PVC
| note | 25db3de8-1a8e-4f50-a247-9d897d6dbf3f | ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
| note | 9893dbb5-7e29-469b-b54d-9f0463bb98ff | Above HV: 300mm minimum width orange coloured PVC 'Danger - Electrical Cable Below'
| note | 570a8f44-ad29-498b-8294-2aa351b97566 | Inspect materials upon delivery and attached delivery dockets.
| note | 42d2a336-0665-40d0-b6bc-92cdf6cc4c17 | METHOD: Document Review
| note | 4ad849a3-f697-41d0-b594-31cd1fc5519f | FREQUENCY: Each Material Type, Each Delivery
| note | b3ae2562-626b-4f33-bcda-36d95fc45c7f | CATEGORY: IP
| note | ddc7ad9b-7455-4a94-af8f-f3e3d75367e6 | RESPONSIBILITY: SE/PE
| note | 27cbd160-a21f-416c-a6c0-c9ad172507d4 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets , Attach Precast Birth Cert
| textbox | da81c633-0442-4d7c-b5ba-862b71d958f9 | Date Completed:
| checkpoint |  | 2.4 Protection Barriers
| note | 2147606e-b55f-47db-b849-95ce127dbecf | REFERENCE: IFC Drawings
| note | 2a2ca921-4805-4f3b-88d1-57326ec334b7 | NIST 012.2
| note | f1bce9e3-db39-4e43-abf7-5af99825a9e0 | NIST 012.2.1
| note | 192d0c55-bd0f-4fb4-80ed-67f3564af078 | AS4702
| note | 45844938-d586-4f8f-a11e-13f488a9fdc2 | ACCEPTANCE CRITERIA: Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
| note | c790d09b-a9a2-4cfd-a33a-c2ebe685b045 | Inspect materials upon delivery and attached delivery dockets.
| note | 51291e77-270d-4a9d-8bc4-1140f82e64a3 | METHOD: Document Review
| note | d1e91d63-76e1-4501-9df8-7d4ac2aeea2a | FREQUENCY: Each Material Type, Each Delivery
| note | 97d1353c-32e3-49db-b334-2d448c42b183 | CATEGORY: IP
| note | 0dc44a96-2e94-47dd-ad19-e1ecb55063a3 | RESPONSIBILITY: SE/PE
| note | 5703e82c-b827-4f2f-b14d-3f121e9397f0 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | 6f75dd19-d7c1-4284-9793-c8f8cd133816 | Date Completed:
| checkpoint |  | 2.5 Backfill Material
| note | bcd17a72-12ae-4ccf-872d-4a3609829344 | REFERENCE: IFC Drawings
| note | 89bb1a4e-a756-418c-9e18-9ab6243fc451 | NIST 012.2
| note | 7ac397c2-e5a6-4dfd-9024-b5a3062f121e | NIST 012.2.1 Section 2 Table 1
| note | c319573f-5865-4ed4-bac4-8636fe3b2877 | ACCEPTANCE CRITERIA: Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could damage the conduits.
| note | 1213ddba-ebc8-4173-b82e-df46d9478dcc | Inspect backfill material.
| note | 7d82396f-419f-4cb0-9028-dbbb756e9303 | Attached delivery dockets (if applicable).
| note | 0834fc5a-1d9d-46a2-b0dd-fcdc35e96d43 | METHOD: Document Review
| note | 96c5fe01-5c72-431c-a68f-9b9bfee45dad | FREQUENCY: Each Material Type, Each Delivery
| note | ff7df895-655d-473c-968c-09b60f13ffa5 | CATEGORY: IP
| note | d8d4e58b-7947-41ec-9cc9-64706789d523 | RESPONSIBILITY: SE/PE
| note | d7b1d41d-f7fa-425c-9b7b-77b7a08a1545 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets (if applicable)
| textbox | 7223c796-a9cb-4397-813e-5d0ee69005fa | Date Completed:
| checkpoint |  | 2.6 Bedding Material
| note | b1bd1e89-5115-472c-a923-4d7637bdcca6 | REFERENCE: IFC Drawings
| note | c44c84b7-fb9d-4a9f-a1a0-0337e5b277b8 | AS2758.1
| note | 27d69fb3-284c-45ae-897c-7e4db2024626 | ACCEPTANCE CRITERIA: Bedding Sand shall be a clean sand and/or Crusher Dust that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
| note | 37858d8d-56e6-49f9-8d5c-41a003fd2c1e | METHOD: Document Review
| note | 8824cf19-cd28-4848-8006-4f54b8f6b63e | FREQUENCY: Each Material Type, Each Delivery
| note | f497bb1a-555c-4f8c-9649-319003eead67 | CATEGORY: IP
| note | 0cbd1802-b5e2-47d8-993a-f90fa4569748 | RESPONSIBILITY: SE/PE
| note | 042b5695-88c3-446b-9805-e846200511c3 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | f04b1e54-7736-4010-8861-80e1ccf4f0eb | Date Completed:
| checkpoint |  | 2.7 Draw Wirer
| note | 1fe19a24-561b-40ce-beea-d60ecc543985 | REFERENCE: TS-SP-013
| note | 0d63971a-c306-4272-93eb-bc5dc679b8b6 | AS 4142
| note | de048a50-d098-40bd-b73a-42c66fcd3d8a | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
| note | f0c23281-978a-4cde-b931-5ce464e3f36f | METHOD: Document Review
| note | f15e4884-5541-417e-9204-897f3a36c167 | FREQUENCY: Each Material Type, Each Delivery
| note | 2656a63e-c30f-45e9-92a6-887d690d6a4a | CATEGORY: IP
| note | 6e59f149-2180-4e6c-bbc8-4a98107e761b | RESPONSIBILITY: SE/PE
| note | 3b40e3ad-beb2-4b5a-8cb8-ebd248046075 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | 39c2f988-5e1f-4392-8c54-71fdf8dd1ddd | Date Completed:
| checkpoint |  | 2.8 Concrete Mix - Trench
| note | c3cb281b-9e44-49b5-8228-dc8c7b1d35fd | REFERENCE: NIST 012.2
| note | e7a99f91-f30b-4cdc-8f9f-2b95b6ebd789 | NIST 012.2.1
| note | b9efd187-c2e3-4def-857c-7bde5868a37e | ACCEPTANCE CRITERIA: Concrete strength at 28 days shall be not less than 25MPa.
| note | bda25d6f-e6d6-4fcc-876a-7233d3ff8129 | Chemical admixtures or fly ash shall not be used
| note | 481e09c0-447f-4829-95c5-acfeec8290b9 | METHOD: Document Review
| note | 051824b7-9dbf-4f4b-8f82-cd4fae646b6c | FREQUENCY: Each Material Type, Each Delivery
| note | 0544e265-3770-48bb-8797-c8b03b85740d | CATEGORY: IP
| note | 60dcd84c-71d3-49de-ad75-6fdd07a36a28 | RESPONSIBILITY: SE/PE
| note | ee6c3628-7b1a-4270-9793-e3eebb7710d7 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | ac8887ff-f41f-4352-8d85-001d993e488b | Date Completed:
| checkpoint |  | 2.9 Markers and Marker Posts
| note | d5882551-b22f-45d5-aac0-e55b8c743675 | REFERENCE: NIST 012.2
| note | 06523b00-8c1c-42e6-83a1-6752a6581f01 | NIST 012.2.1 Cl13.2
| note | 51591dcd-8946-4e8f-a1c2-b939d9d3f308 | AS 4799
| note | 3f433f67-c258-475b-95a2-9ece2df69e47 | ACCEPTANCE CRITERIA: Markers and Marker Posts are to be manufactured in accordance with AS4799.
| note | e877e2b5-1ff3-41f5-a885-5649e6633623 | METHOD: Document Review
| note | 06a59b40-712f-4258-8510-adaf27757227 | FREQUENCY: Each Material Type, Each Delivery
| note | 43b7ad10-551a-4bb4-b04e-6b9a07bee4a2 | CATEGORY: IP
| note | c5ea8c5f-ff39-4214-8caf-7daca80430e7 | RESPONSIBILITY: SE/PE
| note | b6a5f526-24a3-4bf4-835b-2883a0eb1921 | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
| textbox | 039247c8-5c90-4489-8084-571785e0bb04 | Date Completed:
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | a55ff193-1d8e-401f-b741-d6ced1f9a8c0 | REFERENCE: IFC Drawings
| note | 49cbc8d0-baf5-42d2-9c5f-26e17b92d0d9 | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
| note | 2d8979c8-b0cb-4eff-824a-b4dd15f77f60 | METHOD: Measure , Visual
| note | 87d477b7-ed44-48d1-8075-e6252f07bd6b | FREQUENCY: Each element
| note | 177199a4-04d5-4939-9887-73b3b3ada94b | CATEGORY: IP
| note | dbc3b158-60a3-4783-9524-e1c4588340d1 | RESPONSIBILITY: Surveyor , SE/Site Supervisor
| note | 1d2210ab-d029-4e29-a732-7b219a20e8d1 | VERIFYING DOCUMENTS: This ITP
| textbox | 13c04529-d8be-4d81-999f-05328d5cbe52 | Date Completed:
| section |  | Permits
| checkpoint |  | 4.1 Services
| note | 45738035-d281-41e2-8184-82e9715890a0 | REFERENCE: Services CAD file
| note | 00824d1c-195b-4d1f-96f1-836034eddb06 | ACCEPTANCE CRITERIA: All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
| note | 9fb65a50-989a-4db4-b0b7-6ab5c3ac233a | Survey to mark out existing services.
| note | 70c6ff84-f543-46ee-a52f-2b85d2ce8d94 | METHOD: Visual
| note | c94eb207-b2c9-48cf-aa0d-27c8b5afd15d | FREQUENCY: Prior to commencement of works
| note | 3c580d5f-2a3b-4e8c-9621-bfd453f8cd62 | CATEGORY: IP
| note | 5eebbb38-f1d7-48e3-be70-3f6cbff16b7e | RESPONSIBILITY: SE/Site Supervisor
| note | 9af205d5-69cd-48ae-8737-3823e543a953 | VERIFYING DOCUMENTS: Sign ITP
| textbox | efc9d016-e279-4939-a808-638498ccf57f | Date Completed:
| checkpoint |  | 4.2 Excavation Permit
| note | b676a942-e43f-424c-b77a-488ca094fc00 | REFERENCE: MRPA Excavation Permit
| note | bc57515d-7dbb-41eb-b4f9-988385f810f3 | Ground Penetration Permit
| note | 4b68b925-e924-4f6a-ba44-ca2f0138b87f | V/Line SAP
| note | 2cc7eaaf-8ca2-4d48-8b0f-015c191e9c33 | ACCEPTANCE CRITERIA: Insert Permit No.
| note | 855348bf-b46f-40c2-99ec-1202eaef7f2d | METHOD: Document Review
| note | 53bc7e5d-b87d-4087-99e2-ecbf0fa95dc0 | FREQUENCY: Prior to commencement of works
| note | 011727a5-33a1-47e0-8a16-4dab51d6dc5e | CATEGORY: IP
| note | 093275c8-2d9d-49e2-a9c2-8136373d595f | RESPONSIBILITY: SE/PE
| note | 75828901-5339-4fc2-8292-60734adadeb4 | VERIFYING DOCUMENTS: Sign ITP
| textbox | f4b7a98b-6097-4ccd-9e6b-4994aa0294e8 | Date Completed:
| checkpoint |  | 4.3 VicTrack PTW (if applicable)
| note | d7a4c936-f4e5-4122-8ff9-86089fbd4312 | REFERENCE: MRPA Excavation Permit
| note | 47fc7c22-295d-4770-ad07-b1aa75a3dfe8 | VicTrack PTW
| note | e9c02cbf-57a0-4f40-8a30-427581aa63bb | ACCEPTANCE CRITERIA: Insert Permit No.
| note | 17cc0df5-23da-430a-8b8c-9656ecadce62 | METHOD: Document Review
| note | 8ceb13c4-e365-468c-8954-5fee497a65b5 | FREQUENCY: Prior to commencement of works
| note | 65b27990-5de0-4391-a231-9f20f3976451 | CATEGORY: IP
| note | 0cc3ea80-91ad-4373-b7b3-85a8596d501b | RESPONSIBILITY: SE/PE
| note | 5eefdc7f-5ea0-4496-89ae-fa1956d6e240 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 757c1840-2791-48fe-8a5d-91bb2a81ff34 | Date Completed:
| checkpoint |  | 4.4 V/Line SAP (& Monitoring Regime)
| note | 14431445-4275-4c5f-944e-b959e86b8b0b | ACCEPTANCE CRITERIA: Insert Permit No. or Notification Email
| note | 90934e7b-744d-4223-b0ea-9ace36de5b8e | METHOD: Document Review
| note | d50fbd15-9b34-4df0-b20f-a0b655ee4b69 | FREQUENCY: Prior to commencement of works
| note | 3e08cb46-04ce-4a2a-8b3c-6bfab62cbc1c | CATEGORY: IP
| note | a584b8e4-f69f-4877-814a-f99c6eec91c8 | RESPONSIBILITY: SE/PE
| note | 42912388-c679-425b-aebd-1d394075e1f9 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 7f68ad29-ac5a-4519-b25d-956f10394118 | Date Completed:
| section |  | Excavation Activities
| checkpoint |  | 5.1 Trench Excavation
| note | 5e494f03-a309-4f4c-bca2-796bfe182a83 | REFERENCE: IFC Drawings
| note | aef4e26f-84aa-4d03-9032-79c525dffc21 | NIST 012.2
| note | e4b21b0e-6cfe-4097-b6ba-351bc48b1f35 | NIST 012.2.1 Cl7.1c
| note | 87887441-279c-4d5e-89b2-a4e07242cf2c | NIST-2659 Cl6.3.3
| note | c2bf3bac-184e-49c2-a47c-e7c0292df8b6 | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
| note | 5ddd2a42-e9ac-4ea8-83b3-8603bbaa8607 | Edge of trenching to be a min. 2m from structures/pile foundation (unless it is mounting the structure) and a min. 4m from edge of rail for LV, HV & Comms
| note | 9c1f2b0c-e314-4825-8615-61f4f0d2d70f | The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
| note | 968335f4-4e51-4abf-8f3d-c460fb798a37 | The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
| note | 10850fdb-48e6-43c6-9651-054407a3faeb | Level and compact base making sure no low points exist. Soft earth should be replaced with a suitable fill material.
| note | b8725b6e-7a1d-4897-8959-6700b60a22e6 | METHOD: Measure, Visual
| note | bf343bcb-b0b8-4779-9a45-1b2c2e66efaa | FREQUENCY: Each lot
| note | 924f4d4c-5527-4422-8ec5-ab0e22a3a8c0 | CATEGORY: IP
| note | 71c3e960-4323-490c-a206-7ce54e7d3076 | RESPONSIBILITY: SE/Site Supervisor
| note | 14a5968e-fb99-42c3-9bb9-859f7588dd8a | VERIFYING DOCUMENTS: Sign ITP
| textbox | 15378231-9a88-48ac-9b88-8eba653995af | Date Completed:
| checkpoint |  | 5.2 Trench Stability
| note | c60dc44b-4a5a-4d57-b84e-d3043a7e6b90 | REFERENCE: NIST 012.2
| note | 928e7c37-92aa-419b-b4fb-6fca826f9cf7 | NIST 012.2.1
| note | cd1c5548-78b9-4684-80d4-357f20c6d7ba | IFC Drawings
| note | 1662f7d8-b8e7-4c1d-bd96-ea921ab6d942 | MRPA standards
| note | 7f736d73-a612-4632-81ac-0a9a68aa47f0 | ACCEPTANCE CRITERIA: Trench stability check:
| note | 329047b7-2a99-4c0c-9341-9fb86f11bbed | Shoring,
| note | 1aed3396-91b6-4de1-9811-c84222d7d6f7 | benching
| note | 5d39f7bd-8ff3-4dc8-b8db-7e4b414ae6e2 | Geotech signoff
| note | 6a13724b-c694-4b34-b760-e82f5bd996d8 | METHOD: Visual, Document Review
| note | bba555ff-a9c9-42b8-8f4a-810d01ac9782 | FREQUENCY: Each lot
| note | caa04300-ae91-423d-809a-4c6ae0ea627d | CATEGORY: IP
| note | dc6b9e63-8cb7-4c08-ad0f-83cf3aa51555 | RESPONSIBILITY: SE/Site Supervisor
| note | 001aa2e3-7673-467d-a3c6-2ed2fe74aa99 | VERIFYING DOCUMENTS: Sign ITP, Attached Geotech Report
| textbox | 77b37abc-ed1f-426c-b388-1a2560f90fd2 | Date Completed:
| checkpoint |  | 5.3 ULX Trench Excavation
| note | 72e47914-58f9-4cbe-865f-85fe2b11d888 | REFERENCE: NIST 012.2
| note | b86af846-a13d-4825-a441-f824c88a34ee | NIST 012.2.1
| note | f0a25601-45f5-4692-8cef-40f5fe975309 | IFC Drawings
| note | 2d4a7b00-4684-4bc0-972d-9c44411c5fd3 | TS-SP 013 Cl7.3.1
| note | b84b8264-2bdb-48d7-a9b9-392d59ec292c | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
| note | 2da13690-6c53-4952-b5c9-8bb1c63e1ac0 | Trench alignment to be perpendicular to the tracks and extend 3m past the edge of rail on both sides of track.
| note | ec485b91-4400-4ba7-af34-13d34f5c8189 | Top of conduits to be 1.2m below top of rail.
| note | e72ca423-8dfc-486e-b4f9-53a6acb1e908 | METHOD: Measure, Visual
| note | 36064cd1-9fc4-424b-b437-05970b49cb0c | FREQUENCY: Each lot
| note | 0099e0fb-e97b-4d25-a529-c7b2f7d4715d | CATEGORY: IP
| note | 4d6ba660-ff7e-4e66-a04f-1155847922e2 | RESPONSIBILITY: SE/Site Supervisor
| note | eb323020-27e7-4f54-832c-c436cc45bfcc | VERIFYING DOCUMENTS: Sign ITP
| textbox | ade710be-24ef-460d-9808-0730ab4b4a13 | Date Completed:
| section |  | Conduit Placement
| checkpoint |  | 6.1 Bedding Sand
| note | ed6a54c9-c890-414c-9449-95a16842bc73 | REFERENCE: NIST 012.2
| note | dbf96bb3-f556-4b7a-bd6d-ba9667fa6cf2 | NIST 012.2.1
| note | 0c65aec2-18fb-4292-be32-f82c574f79d9 | IFC Drawings
| note | 17629cd6-f8d2-46ae-8082-3bbb24efa190 | TS-SP 013 Cl7.3.1
| note | e3137343-1fb7-4440-90e6-5fdb339c3f38 | ACCEPTANCE CRITERIA: 100mm of bedding sand/crusher dust to be places at the base of trench.
| note | 544dc319-0079-4be1-9d2e-e85a05f2f2fb | METHOD: Measure, Visual
| note | 65ff79b5-5d8e-4c7c-b7cc-05c02a87e6f2 | FREQUENCY: Each lot
| note | 5153db19-2911-4d47-8b70-523ebf7f7393 | CATEGORY: IP
| note | 3cd68c55-48da-469e-9da2-c40a18c649ad | RESPONSIBILITY: SE/Site Supervisor
| note | a2e53ee6-25d1-42c1-9f5c-205ad7d6e10a | VERIFYING DOCUMENTS: Sign ITP
| textbox | f93d618a-2fa8-4906-a217-7ebfdf7c352b | Date Completed:
| checkpoint |  | 6.2 Conduit Configuration
| note | 9fd237e5-15db-4029-becb-fb2312fd274d | REFERENCE: NIST 012.2
| note | c3eb2709-bace-43f6-856d-dcaee4faa6d4 | NIST 012.2.1
| note | 487361b8-7ce6-4f7b-a8cf-255af6d4a0bc | IFC Drawings
| note | 7a71341e-cdca-496a-972a-1fe1c545e3b9 | NIST 012.2 Cl7.3(f)
| note | 96cac7ae-69fa-4c25-be45-a48f2024461c | TS-SP 013
| note | 8ab98420-8788-48f0-9cf7-2051f9cfe1a6 | ACCEPTANCE CRITERIA: Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
| note | b9c92e5d-7bf5-4eae-96f8-28611b050b8a | Min Cover
| note | 6116798b-9e97-4b5d-b4cb-d8356d7818da | HV: 1000mm
| note | a1edd39e-4b73-4d55-91ee-d2e4e2de396f | VicTrack: 650mm
| note | 1d7e7ff7-a95a-4ffa-ad21-ed53f014c515 | Signalling: 800mm
| note | 0ffe8c76-c3d2-4a25-b425-572367b02b1a | LV: 800mm
| note | bf4701a1-f3c1-4314-a838-2ecb6ff8ca19 | Electrolysis: 800mm
| note | 9ef5deaf-4721-4cbc-b9c0-12939a7a76d1 | SCADA: 800mm
| note | 539e283c-9c61-42a7-a70b-da3a6b04fadb | Where Water Courses encounted: No less than 1000mm below water course. Conduits shall be covered to a minimum depth of 300mm with porous bags filled with stabilised sand and the remainder of the trench then filled to the top with approved heavy grade fill (vline req.)
| note | 6e8c8cd2-4348-4274-b897-0c3ca3a72134 | 1200mm Under VicRoads Roads & top of Rail
| note | 6bb72222-231b-4408-ad24-bc559addcfa1 | 900mm below council roads
| note | 95db045f-0cf6-4afa-90ac-87879a72582c | METHOD: Measure, Visual
| note | 74ba2908-dd09-498b-aabe-163b128184e5 | FREQUENCY: Each lot
| note | 8dd8ec4f-d80b-4b14-984f-722886bcc38f | CATEGORY: IP
| note | eca2caff-a1cf-4fc2-9ba4-3719be19ea23 | RESPONSIBILITY: SE/Site Supervisor
| note | f58a249f-f6a2-4586-9741-7347aebd963a | VERIFYING DOCUMENTS: Sign ITP
| textbox | 0e471b48-8067-4758-a3f5-c1336cfeb7d7 | Date Completed:
| checkpoint |  | 6.3 Separation of Services
| note | af98ad75-3b48-4726-b910-81afd00b7272 | REFERENCE: NIST 012.2
| note | 301645ef-c703-42f8-beac-56d22afc5d4c | NIST 012.2.1
| note | 8702ad89-24d4-4e25-bc78-5d33296226fe | IFC Drawings
| note | c2548dcd-8153-4d65-acae-84754bfb073d | ACCEPTANCE CRITERIA: Separation of services
| note | e96408e4-e37a-44d9-8574-4cc6c61313b3 | HV: Min. separation distance between HV conduits at least 50mm
| note | abcb64c2-eb8c-4f21-b3b0-f9ac7d2a7676 | VicTrack: min 300mm from HV
| note | c7d96f42-c6de-4737-adf0-17291a7b68f7 | Utility: 300mm to utilities
| note | 378d8793-8829-4887-9839-89509d39574f | METHOD: Measure, Visual
| note | 680cb3c4-35b7-498e-8e52-d841bdca0d21 | FREQUENCY: Each lot
| note | 565717f4-8c80-472a-9b82-666d3c907d0d | CATEGORY: IP
| note | 8d66fa60-e3e4-4ce1-bd47-6e00474320c7 | RESPONSIBILITY: SE/Site Supervisor
| note | 91627d09-f1f8-4445-b5e1-7ead1b389cec | VERIFYING DOCUMENTS: Sign ITP
| textbox | c41d83b6-20d4-4b16-85a7-b944421cbe6c | Date Completed:
| checkpoint |  | 6.4 Joints
| note | 7bf44024-1b46-4496-95c9-6cf40c111ed1 | REFERENCE: L1-CHE-SPE-070 (MTM)
| note | b61c53a7-0b17-4bfa-bd18-4d78e6616294 | L1-CHE-STD-043 (MTM)
| note | a3b5b401-bb8f-48a1-89bb-8295047c4895 | L1-CHE-STD-070 (MTM)
| note | 0d04a54f-d785-45ed-a51e-49ce7b4591eb | IFC Drawings
| note | acfad146-efbe-4405-8a5c-121ff230a434 | NIST 012.2 Cl7.12
| note | 48f07e8e-46da-4283-bf12-feae88ce0b0b | TS-SP 013 Cl7.3.5
| note | 5d1bc766-34df-40f0-9d7c-c263825accf3 | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigot;
| note | e1feb276-6e81-4325-89ee-e3d70dca78d1 | The ends of the conduits, both spigot and socket shall then be coated for the full length of the spigot /socket with a conduit-manufacturer approved adhesive and connected together for the full length of the socket.
| note | 9ad710c9-7a59-4be2-bd03-c68a28269f92 | Spigot type or bell mouth fittings shall be used on all conduits to ensure that cabling is not damaged during installation.
| note | a805cffe-90d3-4d92-b64d-0b4d46324c20 | Internal spigots must not touch one another. All spigots must be flush to the pit wall.
| note | 14a9bf90-508b-4d4e-bb6d-b3338c9e9fa7 | METHOD: Visual
| note | 3c2fd0b9-5fb0-4538-abc5-0061eecd9e48 | FREQUENCY: Each Joint in each trench
| note | 9a2d8fd3-6230-4005-b3a8-d68e94d4e57c | CATEGORY: IP
| note | 5df17752-6bf6-47f3-beec-eadfda1e04d7 | RESPONSIBILITY: SE/Site Supervisor
| note | d5cf2ef1-2572-446c-abfb-12b0484e6a52 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 9e9ebc64-ac79-4d0a-ac32-f91a58fd00d4 | Date Completed:
| checkpoint |  | 6.5 Conduit Inspection
| note | 8e95d514-8725-4787-a64f-d263abb6dc2e | REFERENCE: NIST 012.2 Cl16
| note | bd1205d9-4f20-4f4c-bd2a-7b0a46401a85 | TS-SP 013 Cl7.8
| note | 94e953b4-88fe-4248-957d-9d140d2c9570 | ACCEPTANCE CRITERIA: Provision shall be made for inspection of cable routes by NA, V/Line/VicTrack representatives prior to backfilling.
| note | 42bed759-842d-4a7f-b6ad-965808924ec9 | VicTrack will witness the first layer of backfilling of trenches with clean fill material, compacted to minimum 50mm above the top of the conduits.
| note | 934d3dc2-27fb-4e72-ac23-4dc0e54e5f5e | METHOD: Visual
| note | d7e75a4b-1e4d-404b-9aa5-df848fd9ee4c | FREQUENCY: Each lot
| note | 9568c24a-fd1e-45c2-ae9c-5907abe02767 | CATEGORY: HP
| note | d7a85952-b08c-48f9-9cef-2d78596accc3 | RESPONSIBILITY: SE, NA, V/Line/VicTrack Rep.
| note | 46ba08d7-ba9f-4dbc-9458-09446fef1f64 | VERIFYING DOCUMENTS: Sign ITP
| textbox | da2586d4-cfdb-40eb-84cf-04105de32bc7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.6 Survey As Built
| note | a4705820-8c76-4077-b3bd-3ac87fd32fdb | REFERENCE: NIST 012.2
| note | aca8d735-21bc-439f-840c-d9e1f3b78de1 | NIST 012.2.1
| note | 62677189-e53d-4d46-98d8-c4e19359d3d4 | IFC Drawings
| note | 773557e6-76d3-4e2a-8fb9-c6b404a5792d | ACCEPTANCE CRITERIA: As-Built survey to be completed and recorded before backfill
| note | e458fc1f-b9dd-4e8d-994f-f71d26ec8987 | Cable joint locations.
| note | 2b29baaa-f598-42a8-a87b-12906429b694 | Cable pit locations (Corners)
| note | 319486c9-c835-472a-8bea-eb5d30502ad0 | Pit dimensions & pit lid type
| note | 55a4df86-cff1-42ed-b545-b9bce511cc49 | Under line crossings
| note | ea99411a-d8bf-4848-b82e-10967923b026 | Under road crossings
| note | e0cefcc6-53b5-4680-be8a-bef720ad517a | Changes of direction
| note | f7fcc38f-2dba-454d-8136-121c3d7223eb | Spare Conduits
| note | ae81b35d-f1ef-4aaa-a4e1-b87dabae9e68 | Conduits labelled as per trench profile
| note | 2c43e659-44c0-44b7-8eeb-6d0ee4c38b8e | every 10m
| note | 81c81da5-5769-43c9-861d-9f98e030f8ab | Other significant points of the cable route
| note | 49632754-1f2f-46a6-821a-6053b59553d8 | METHOD: Measure
| note | 2e533107-f832-463c-8dea-1ff3913b9344 | FREQUENCY: Each lot
| note | faf37ae2-be58-495b-9ef8-6a049eff7ce1 | CATEGORY: WP
| note | 82ee2c73-4c70-402a-a0e8-a8a5bb584b28 | RESPONSIBILITY: SE/Site Supervisor
| note | 2dea24e7-2b12-45d6-840b-4da05b6c9507 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 6d69906f-cb63-4300-b5b5-b0d394d22507 | Date Completed:
| checkpoint |  | 6.7 Bedding Sand Installation
| note | d780eb16-177c-4880-8708-60e780af6826 | REFERENCE: NIST 012.2
| note | 9ad830cd-7fa3-4634-9b21-512823b559c7 | NIST 012.2.1 CL13.1
| note | c738a797-512b-46f8-a8b1-cbf71fcc0d3d | IFC Drawings
| note | 46f10956-5f0a-44c4-9bf0-662095962998 | ACCEPTANCE CRITERIA: Bedding sand/crusher dust extends 100mm past edge of conduits.
| note | 7fac4506-9218-4411-b561-af449228063f | Bedding sand/crusher dust extends 100mm above conduits.
| note | b90854e9-dcf0-4b80-bbfa-18f256ed5f24 | Conduits shall be laid on a clean bed of sand 100mm thick
| note | 719c12e3-925c-405e-ab7a-e2d7ef80fcda | METHOD: Visual
| note | c799cc4c-c72a-47f7-bc26-bb3861a71702 | FREQUENCY: Each lot
| note | 1a223b03-f0cf-42f2-a7ae-b30c50b40ef4 | CATEGORY: IP
| note | 0aa190c3-2a32-482e-8a74-b43725450779 | RESPONSIBILITY: SE/Site Supervisor
| note | cb754180-c61c-414c-abfa-de3e100f16cf | VERIFYING DOCUMENTS: Sign ITP , Attach Delivery Dockets
| textbox | 9bb5f168-0f5f-4b0f-883e-8e3140def16a | Date Completed:
| checkpoint |  | 6.8 HV Protection Barriers
| note | 233a8f44-c81a-4f02-8bf3-e980ae1789df | REFERENCE: L1-CHE-SPE-070 Cl10.3.3
| note | 346c1019-a540-4381-a313-45e85e838849 | ACCEPTANCE CRITERIA: Top of HV Protection barriers installed 150mm above and 50mm beyond vertical line of any HV conduits
| note | 6d73a3aa-376e-4e7a-955e-4b699652dd8e | METHOD: Visual
| note | dabb8d46-d54f-40f2-a295-266b4308ebfd | FREQUENCY: Each lot
| note | 8b2910c0-09c5-47e2-a7e9-8ec1096a33c3 | CATEGORY: IP
| note | c62847e3-b6bb-4017-a5d7-638f5ebc77ec | RESPONSIBILITY: SE/Site Supervisor
| note | 832fd556-b38f-4ac4-9d8c-9f208d17a045 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 2a7dd8e0-af76-4524-a1c1-dd450e0c1847 | Date Completed:
| checkpoint |  | 6.9 Marker Tape
| note | 5dd74616-2289-46c1-8852-99cfba7abb15 | REFERENCE: NIST 012.2
| note | c9c015c7-1bf9-4ddb-aeff-16a0be3feab1 | NIST 012.2.1 Cl10.3.3
| note | e43a963a-2f0e-491f-9da3-80389c4221c9 | ACCEPTANCE CRITERIA: Warning Tape installed a min. 300mm from FSL.
| note | 3682daf4-d6a7-4886-ba0e-3c179e84e7f8 | Tape to be one continuous length.
| note | aac8ec6d-3e88-4ee5-9a8d-59a885e327ae | VicTrack to inspect the Marker Tape placement..
| note | 6359c8fc-3168-4cc8-b823-f8efe9a6d2a6 | METHOD: Visual
| note | 0e38bf0b-8820-4d19-8be8-8dc9a42de5a7 | FREQUENCY: Each lot
| note | 40646308-7c95-46e9-8ee1-df631dabf7cf | CATEGORY: HP
| note | 45201f76-8ebc-45d8-9294-4e17abe8faf5 | RESPONSIBILITY: SE, NA, VicTrack Rep.
| note | 786bd856-e48c-4d2e-a8b7-ee26fb578052 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 44061ab8-e6ed-4e97-a2e2-60b9511b44a2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.10 Backfill Installation
| note | 6552288a-feba-4e02-a43b-c2b7d1359992 | REFERENCE: IFC Drawings
| note | 47dfb5b3-a5e6-4cb9-b0fa-69e164bebc31 | NIST 012.2
| note | 8b4e8d8d-a279-4c73-b0ba-d2fc48efd708 | NIST 012.2.1 clauses 6.15 and 6.16 and 6.5
| note | 6d3d0821-92b1-4002-84b5-2f83a79add09 | ACCEPTANCE CRITERIA: Backfill per trench profile
| note | 7491ab54-bf17-4ca3-9d28-13bccb471e6a | 150mm layers
| note | f6cfb5a9-5c2e-4018-8407-8c0740a16aca | CBR >3% for existing material to be used
| note | d1c962bd-3682-44b5-97ef-843ab83e37d2 | 95% compaction
| note | eae9ba5c-6896-4076-8f78-c16581c4a76a | conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
| note | 1d498a9d-65fa-4229-8de6-97e2807471f2 | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
| note | e518e532-9a04-4e49-a446-6fde756bea16 | Trenches under road pavement - backfill to be same material as the road formation material.
| note | 7a6ca838-8559-49a1-a733-49aa4ed434f2 | Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
| note | aba5d36c-1d51-4b6f-a847-6c982dbe221e | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
| note | 24bfdb5f-db9d-4679-82ee-47ff37ac42d8 | VicTrack to be notified and witness the first layer of backfilling.
| note | 000246d0-0f49-45bb-bf18-546af8cb0ba7 | The final 150mm of fill of trenches in rock areas shall be stabilised sand, or concrete (minimum 25Mpa) if in vehicle access roads.
| note | 5a1d71b6-d828-4a86-a64e-6e7b39f1f5c4 | METHOD: Visual
| note | 39b26aa4-65ea-45d7-8a40-0c78df3f9826 | FREQUENCY: Each lot
| note | cad1162d-fa40-4634-b841-e3f509b2dbef | CATEGORY: HP for first layer only, IP for the rest.
| note | 6545489f-9bc2-4200-9547-b5f00b2ec7e6 | RESPONSIBILITY: SE/Site Supervisor/NA/VicTrack Rep
| note | 76f30f69-c2f5-4f36-93ea-97c282598148 | VERIFYING DOCUMENTS: Sign ITP , Attached Delivery Dockets
| textbox | 9cd26cce-fef5-4296-bcd0-df5005b5c5b6 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 6.11 Compaction Testing
| note | 8f4cf778-634d-4212-a166-d6d74ae53a8d | REFERENCE: NIST 012.2
| note | ae527268-f464-4e2c-a5cc-c051c09deaa0 | NIST 012.2.1 clauses 6.16
| note | e2d6ba93-e0be-49f7-8583-dd797e13edca | AS3798 Cl 5.2 table 5.1
| note | 9e0532bd-e126-467d-90ac-7230ba4473c8 | ACCEPTANCE CRITERIA: Compaction to achieve 95% Standard Compaction using an approved Mechanical Vibrator.
| note | 45cc4cb1-0807-4d5c-b939-86032b47f65e | Under no circumstances is the cable trench to be compacted by driving excavating machinery or other vehicles along the trench.
| note | c32f3443-7980-4268-97b0-51813079df64 | The tests shall be taken on a frequency of one (1) test per 200 linear metres per layer or one (1) test per area per layer where any area of excavation is less than 200 metres long.
| note | 33453c5f-7070-411a-b735-4e0fde6ca9dd | METHOD: Document Review, Visual
| note | c3619c80-3399-4a87-835f-f5317e840ddb | FREQUENCY: As Per L1-CHE-STD-043 6.16
| note | 6c2e4e41-67ba-462b-91c2-0a5aceec4bdb | CATEGORY: IP
| note | cf67d87e-047c-48fd-a568-d39695c8c6bb | RESPONSIBILITY: SE/PE
| note | 12477f87-b5af-43ad-ba07-d7a458494f80 | VERIFYING DOCUMENTS: Sign ITP , Attached Test Report
| textbox | edc74160-eb7d-480d-840e-828796537dea | Date Completed:
| section |  | Pit Location
| checkpoint |  | 7.1 HV Pits
| note | 3efa0466-442a-4e39-9580-391b21cf5e3e | REFERENCE: NIST 012.2
| note | eb82fde8-4c86-47e7-9fa4-e72cbd122746 | NIST 012.2.1 (Cl 7.21c) CL9.2,9.3
| note | cc183b54-f169-4fa4-8569-352f6cba824d | ACCEPTANCE CRITERIA: HV Pits intervals no greater than 400m
| note | 5415f8b4-6431-4674-aff1-27f379eb39f8 | 3m from rail
| note | 5b078365-1c13-45c6-afbd-dd0e230cbefe | Access Roads, Class D lids
| note | 6c159667-e14f-40ba-85e3-f38881517ea1 | Footpaths and non traffic areas, Class C Lids
| note | 49b96844-89f7-47e2-9d42-f51623128723 | Alignment of square pits parallel to property line
| note | c3376f5d-4b9d-43b5-8958-c8e814ddad69 | Pit size as per L1-CHE-SPE-070_9.3.2
| note | dfa3108e-35dc-4f23-b11b-bab0601df6c9 | METHOD: Visual
| note | ab4d3ef2-e4f4-4600-be52-d044ede9552c | FREQUENCY: Each Pit
| note | 697d82e7-c0df-499c-b19b-71e811281997 | CATEGORY: IP
| note | 61cc844d-cc31-49fc-8e76-ea2ec9dc6f40 | RESPONSIBILITY: SE/Site Supervisor
| note | f7b8c7a8-9be8-4a80-b509-e8438f5b7af4 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 23ebd4d4-50a3-4b10-9087-fff680cfa6d5 | Date Completed:
| checkpoint |  | 7.2 Sand Pits
| note | 33a26724-d15f-4c42-bed6-60ffaf473bab | REFERENCE: NIST 012.2
| note | 9e44568a-0b20-4b14-a89d-39e57af241b5 | NIST 012.2.1 (Cl 7.21c) CL9.2,9.3
| note | 131c2c06-9b6f-47d9-a0fa-6ef2b37b341d | ACCEPTANCE CRITERIA: Min. clearances from:
| note | 7fb6c402-2b45-430c-9481-4a84744da064 | 5000mm CLEAR OF VICTRACK ASSETS
| note | cf4c28d5-5684-4b0a-867d-fd0cc5e230a3 | 2000mm CLEAR OF V/Line SERVICES
| note | 2a5df54f-a6e3-4375-8f5c-c1662fceca44 | 3500mm FROM NEAREST RUNNING RAIL
| note | 6236df3c-a3ad-4d2a-aaa9-8cd1af458fe1 | Sand pits shall not be used within paved areas and access ways
| note | 4fc1bfb6-c354-4d95-a32d-c95e79435a6e | Not to be deeper than 1500mm
| note | 8d73c611-b387-48b5-8b69-d2dd3f740c93 | METHOD: Visual
| note | 254014fc-1b52-4486-957f-47cef59b56c5 | FREQUENCY: Each Pit
| note | 7ce17764-b09b-407b-a8e8-88ca61c6409c | CATEGORY: IP
| note | d8c42c6c-a5b3-4657-a1c2-267701b8a4f9 | RESPONSIBILITY: SE/Site Supervisor
| note | 04e9ff6a-28cc-4a7e-8900-cfbb5a16a0c9 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 8a4338f5-b426-4c90-bcc8-1b2506d28696 | Date Completed:
| checkpoint |  | 7.3 Vic Track Pits
| note | dd5af289-2af1-40ac-8dcb-f75aff677b56 | REFERENCE: NIST 012.2
| note | 7ba1b351-8bd3-4a8b-9a5b-dfd24e32fd90 | NIST 012.2.1
| note | 0777bec2-8d02-4700-b4c6-f03bbd1d7bc4 | TS-SP-013 7.2.2.vi & 7.3.7
| note | 7e628150-d52c-4548-a4ef-6e88871c5f6b | ACCEPTANCE CRITERIA: VicTrack Pits:
| note | 57302754-9d1a-4c9e-85d6-17e52f152032 | intervals no greater than 380m
| note | a806550a-2cd1-450e-9b53-f4eb45a7ac24 | no lateral deviations of conduit from the straight line between pits greater than 2 metres over the nominal 380 metre pit spacing not all at a single or several distinct points. If this cannot be achieved, then the pits need to be at a closer spacing;
| note | bd063064-52aa-4042-8320-1a7558311ad2 | 4m from rail (if within 4m a physical barrier at 3m is required)
| note | 04c80209-5a7d-472e-bf64-5d6d6b97548e | Access Roads, Class D lids
| note | 519ecd5f-9d83-4298-b67c-ccc4363be6bb | Footpaths Class C Lids
| note | 8c99da98-dde6-4f04-8140-5dfe15c8cfe0 | non trafficable areas Class A with bollards
| note | d215d07d-43a3-45b7-b118-3ac20db6252c | conduits to enter from ends of rectangular pits
| note | b82547c0-8027-4e9f-894f-4f2e9087edcc | METHOD: Visual
| note | e995cddb-91d5-4648-a860-fc8e1180cd82 | FREQUENCY: Each Pit
| note | 437b8530-c42d-4b14-8efe-4fc87d388a60 | CATEGORY: IP
| note | d791f03f-64f1-442b-96c3-5e3dfb65ca96 | RESPONSIBILITY: SE/Site Supervisor
| note | 6e97f3d9-81a4-4aa2-9bf5-f579a8050993 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 8d50dffc-d1ce-488a-93d9-221fa4b64384 | Date Completed:
| checkpoint |  | 7.4 Signalling Pits; LV Pits; Electrolysis Pits; SCADA Pits; V/Line Comms Pits
| note | 68daa169-ddc6-4936-abd2-33baa41faf80 | REFERENCE: NIST 012.2
| note | 09aa171a-544d-44ea-af28-08c29a84dc8e | NIST 012.2.1 Cl7.14.o, Cl7.14.g
| note | 2e39cede-15b5-4a02-bc74-520b743f664a | ACCEPTANCE CRITERIA: intervals no greater than 400m (electrolysis 190m)
| note | ed6bdaa9-28e3-4652-a8cf-2221f5dd9051 | 3m from rail
| note | 95b3b781-9f57-4943-8689-ccdb44f66b56 | Access Roads, Class D lids
| note | 578b8b8f-7bdb-4635-80fe-50e7467e9ade | Footpaths and non traffic areas, Class C Lids
| note | cb6adbd5-6e2f-4145-9920-0b24b16df597 | METHOD: Visual
| note | ceafc6f6-fd89-46d5-9629-1183aec283ce | FREQUENCY: Each Pit
| note | c22e2378-8ffe-4908-8509-cb3c54d9f1e4 | CATEGORY: IP
| note | e975d6c3-c055-48e7-bca1-2855ea37f9c4 | RESPONSIBILITY: SE/Site Supervisor
| note | aa53ee5a-bc37-4515-92c6-5a32d6d9b221 | VERIFYING DOCUMENTS: Sign ITP
| textbox | e193b0df-405f-43a3-b6b0-5e2092ae79ce | Date Completed:
| checkpoint |  | 7.5 Additional Considerations
| note | e9291e57-f555-492a-bda5-344fe1009cdd | REFERENCE: IFC Drawings
| note | 1e22a626-6a61-4ccc-8cb0-70949090a53d | ACCEPTANCE CRITERIA: Access tracks to pits
| note | c9dd1d5a-67f5-47fc-bfce-014dfeb837d7 | Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
| note | cd661119-7665-4a98-a3b0-471dd9106a87 | Hand rail & retaining wall installed as required
| note | 3d163121-c97b-4445-9b45-d46580abc106 | METHOD: Visual
| note | f55f18af-f484-4dfa-9bd7-dee5167b11f8 | FREQUENCY: Each Pit
| note | 730643d1-893d-431b-94b7-6d49d7cdb5cc | CATEGORY: IP
| note | 99aab169-bd0d-4c7b-9489-0558ab2c1084 | RESPONSIBILITY: SE/Site Supervisor
| note | 1c35544e-5464-4097-a8a6-aec5e74a3d29 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 60735713-6be6-4a7a-ba84-51f8656d158d | Date Completed:
| section |  | Pit Installation
| checkpoint |  | 8.1 Bedding
| note | 427b08e1-a525-4c13-930d-4ab1cec1c6a9 | REFERENCE: NIST 012.2
| note | 67c747c0-c76f-4938-9e16-780ae53687da | Cl 7.21.u
| note | 311eb256-31c1-438d-a46d-07052c716b09 | NIST 012.2.1
| note | ac2fa6f7-b234-42f3-923a-29e2d14c235c | ACCEPTANCE CRITERIA: 150mm of compacted crushed rock under pit extending 500mm past the pit
| note | 463993b8-6e91-4508-b9f7-e8bda391af97 | Drainage arrangements shall be provided at the base of each pit.
| note | db3b50a7-555b-49ef-9555-ac7ec47afc97 | METHOD: Visual
| note | d20e29f0-6ac6-415e-8fc8-ba7d5e1a0e6b | FREQUENCY: Each Pit
| note | 2225e9f8-a5eb-44f7-9bae-0ff55da48400 | CATEGORY: IP
| note | 2af28a12-1a55-4b12-a3fb-a34b7fca2345 | RESPONSIBILITY: SE/Site Supervisor
| note | 6fd4465b-dee0-4d89-b962-35feec02eda6 | VERIFYING DOCUMENTS: Sign ITP , Attach Delivery Dockets
| textbox | b48e7869-6bc8-4c7b-ae38-aa6b7ae645bf | Date Completed:
| checkpoint |  | 8.2 Pit Orientation
| note | 6005cb16-825f-41c8-a903-fe9695541875 | REFERENCE: IFC Drawings
| note | 382b11ed-6c2b-4822-82f3-fa5e88b6058c | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
| note | da60bbbc-8ee4-4550-bcc2-2299bd4518f7 | METHOD: Visual
| note | 4489a212-6dc5-4ac5-b763-89bd68db661e | FREQUENCY: Each Pit
| note | b042cf51-2ed7-4ad1-82a5-6ba69303acdc | CATEGORY: IP
| note | a285d050-b539-4d1c-9189-93f733629b8d | RESPONSIBILITY: SE/Site Supervisor
| note | 8bf44f81-f579-41bd-a86d-5a81c5c971d8 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 89959920-573e-4f53-86c5-7f5271bb9ff2 | Date Completed:
| checkpoint |  | 8.3 Pit Installation
| note | 9adc493f-c951-4b77-9f8f-66f3c490ef7c | REFERENCE: IFC Drawings
| note | 21eb5c19-f0ad-4140-b473-222235331e2b | ACCEPTANCE CRITERIA: Pit installed to design specifications
| note | 24d045eb-b98c-4099-8d5c-2760552fbdc6 | Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
| note | ad5ce0df-30a5-4230-85b0-10d537bb676a | METHOD: Visual
| note | fff2ddc4-197c-42b9-bcfe-c4217ca664d7 | FREQUENCY: Each Pit
| note | 2160e400-c590-4b6a-bbd1-799220cd478a | CATEGORY: IP
| note | 5721d2d0-5efd-4a94-8767-684e3f2f9775 | RESPONSIBILITY: SE/Site Supervisor
| note | f897ac1d-c74b-42f6-9e8a-8f3287c03054 | VERIFYING DOCUMENTS: Sign ITP
| textbox | e3e079d6-6d67-4120-8cea-aa729b88d65c | Date Completed:
| checkpoint |  | 8.4 Pit Greater than 10ft
| note | 50f82ed1-0701-496c-b355-b4b962778893 | REFERENCE: MRPA Procedure
| note | 65a5a5db-a1f6-468f-b4f0-859131134532 | ACCEPTANCE CRITERIA: Each pit if non standard lift (greater than 10t) the following is required:
| note | fc6ec7b6-5d2d-4ecb-8571-419c657987ff | Certified Working Platform
| note | 89f910d6-d22b-40b0-97e7-0b3b4d2087bc | Certified Lifting Anchors
| note | d682b4d8-314f-4c94-8521-18c968eb2a71 | Approved Lift Study
| note | cf114b75-6e22-4f07-b4a3-2849138274bb | Check Birth Certificate
| note | a88dd273-7ff9-457c-8ad2-fea464d05f2f | METHOD: Visual
| note | e60720ed-68ec-4ef2-ad6a-d9b604599b07 | FREQUENCY: Each Pit
| note | a5eb4775-3615-47e4-8a85-0bd14c053860 | CATEGORY: IP
| note | f5ac9f06-8333-483c-97bb-b435eb81de16 | RESPONSIBILITY: SE/Site Supervisor
| note | 904e36cb-1f60-4918-9da4-0a572c419ec5 | VERIFYING DOCUMENTS: Sign ITP , Attach: Geotech report, lift procedure, shop drawings
| textbox | 5c4d974e-9a0d-49af-9b7a-785fdfa9f36c | Date Completed:
| section |  | Pit Fit Off
| checkpoint |  | 9.1 Conduit Entry
| note | 769eaed2-b267-422b-9129-6ce816ad99f6 | REFERENCE: NIST 012.2
| note | ab5e6073-d047-4679-8158-f2c20dedf6ef | NIST 012.2.1
| note | b04ef8f5-12b2-406d-822d-82a6533fea54 | IFC Drawings
| note | 0c085676-6ac7-41ad-b46d-0f1864eb0e3f | ACCEPTANCE CRITERIA: Conduits entering pits shall slope away from the pit such that water does no flow into the pit with lowest conduit 100mm from the pit chamber floor.
| note | 4361c72b-3c3a-4189-99fc-07292f66f2a2 | The exterior entry points for conduits into pits shall be sealed by mortar (ratio 4:1 sand/cement) or both externally and internally using an approved, expanding silicone based or similar type sealant
| note | 6bbc7c0e-37e4-4757-b7ca-9b4ad8c11062 | Penetration holes through pit walls shall be 1mm to 5mm larger than the conduit outer diameter and created by either:
| note | 09ce778d-773b-4267-a66c-1732fdab7da5 | a. Preformed (cast) holes
| note | 45f6d199-18c1-4ef9-965c-6e9e05764aa3 | b. Hole saw cut (or diamond drilled in the case of concrete walled pits)
| note | fcb1af88-4286-4622-b361-9de921bb1aed | c. Comms conduits entry into concrete pits shall be via drilled holes only
| note | 6fe219fd-d629-44f9-8091-6f29b9a6b84a | METHOD: Visual
| note | bb55913d-2eb7-41a4-b0d1-dcc70312c6a4 | FREQUENCY: Each Pit
| note | 4fc1410c-0a9d-4203-bd0b-c0593421ed09 | CATEGORY: IP
| note | edc4f111-bd33-4893-82d2-9ae87bcffb23 | RESPONSIBILITY: SE/Site Supervisor
| note | 2ca25bba-1a78-47d0-8040-9bdf07a87ae1 | VERIFYING DOCUMENTS: Sign ITP
| textbox | ee7e6ee6-e43a-415b-a2b0-405360b1a26b | Date Completed:
| checkpoint |  | 9.2 Tracer Wire
| note | 33db5c2d-cb27-40e8-b03b-95714b1fc749 | REFERENCE: NIST 012.2
| note | 99744e7a-30cd-4f4a-ab21-165bfc1d9341 | NIST 012.2.1
| note | 78b5be5f-f3ee-4e02-a47a-1132e6af8c9a | IFC Drawings
| note | 723dd26b-68a7-4860-93cf-6e4a611ec1af | ACCEPTANCE CRITERIA: Warning tracer wire for Vic Track routes to be drilled into pits and crimped off.
| note | d8449411-5b77-4a2c-90e1-2aed1dcd21bc | If tracer wire broken needs to Crimped
| note | 7db5ff5e-1aa2-4694-ac79-425450659cd0 | METHOD: Visual
| note | f5102461-6b90-4c2d-9ace-4fe0f48d0f50 | FREQUENCY: Each VicTrack Pit
| note | c2e3086a-ce3e-4a95-b288-4fddf2135017 | CATEGORY: HP
| note | 0f18af91-cce0-4303-a296-550236742996 | RESPONSIBILITY: SE, NA, Vic Track
| note | fc84e7e1-8fee-48b8-a1fb-543ae38475f6 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 3819ade1-efa6-46f4-86cf-52d4ca927af0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 9.3 Spigots and Bell Mouths
| note | 5685eb74-cc8e-4260-b9a0-66d56d21f987 | REFERENCE: NIST 012.2
| note | 3a813338-d928-4df1-a330-756d05e2cf18 | NIST 012.2.1 _9.3.4
| note | c01e74a2-4a51-4b19-8edc-5e91cd546bde | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush (if conduit type isn't mentioned below) with the pit wall and not touching any other spigots.
| note | 6e97814c-eaed-48d2-8ca3-1c0cd1943356 | HV Conduits entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
| note | 50775579-b395-422c-9b1c-93646e698da6 | Comms conduits are to be correctly fitted with Comms entry spigots mounted flush with the pit wall to ensure no damage to the cables during installation.
| note | 2aa25575-1475-4e8d-9ca4-dfcd62955b05 | Signals conduits must protrude into pits by a minimum of 10mm and a maximum of 50mm and are to be fitted with a spigot to ensure no damage to the cables during installation.
| note | d194f26f-c0fe-4821-a415-00bdf338c7a8 | METHOD: Visual
| note | bc5c43b4-a6b1-4f53-8896-41cff0d83064 | FREQUENCY: Each Pit
| note | cef145cd-bf9b-4020-84bd-8e55cefb6fbe | CATEGORY: IP
| note | 0b7e664c-d458-4795-bcee-9c261a0f13b8 | RESPONSIBILITY: SE/Site Supervisor
| note | c40ad348-9275-49cf-ad7a-50ec9a38b5d4 | VERIFYING DOCUMENTS: Sign ITP
| textbox | daf67065-269a-4824-a2d2-73f4b7cd1fbc | Date Completed:
| checkpoint |  | 9.4 Draw Ropes
| note | 1bd89ba9-8525-4054-8c2c-d16f0a08142a | REFERENCE: NIST 012.2
| note | 8178d9f0-cb40-4dca-a767-b9cda927cea4 | NIST 012.2.1
| note | 40bc63e8-1cda-419c-bf63-8a19d8d12b26 | ACCEPTANCE CRITERIA: The draw wire shall be continuous for the complete length of the conduit run.
| note | 45db4b7d-d836-4eb1-842a-0738cbd736e3 | The draw wire shall have a minimum of 2 metres of slack within every pit.
| note | 7708af2e-4fd3-47e3-a242-e83c892ccb67 | METHOD: Visual
| note | 8f69d9e8-1e35-43bd-854f-867a0b7cb63d | FREQUENCY: Each Pit
| note | e9687708-2183-45d5-a36b-0254ea203e8e | CATEGORY: IP
| note | 89f5733c-d318-4bb1-ae10-64ac25896306 | RESPONSIBILITY: SE/Site Supervisor
| note | 60388f01-b2d0-4896-8b86-c4a6ab9aa7c7 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 79d2fe6f-6383-401a-b187-0bf61958c2e6 | Date Completed:
| checkpoint |  | 9.5 Backfill and Compaction Testing (if applicable)
| note | ae63433a-4fed-42ed-bf94-cc64118a277d | REFERENCE: NIST 012.2
| note | 9ec36e73-b860-4200-8b0a-d13ee539fd08 | NIST 012.2.1
| note | 33c5b2c3-4bf1-4a3e-ba48-79c840425c85 | IFC Drawings
| note | 83345b6a-3616-41f6-ba4a-67bfdf5d7b1e | ACCEPTANCE CRITERIA: Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
| note | 6967fd96-74ae-49ba-8380-401324463a6e | Sand within sand pits to be compacted in layers no more than 250mm layers
| note | c8f09a1b-0ae1-4e31-b796-140eb254c3a9 | Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
| note | e0edf96b-4501-4aef-aafe-4ba2e6b651b8 | METHOD: Document Review, Visual
| note | fe66c7ca-3059-4f83-a184-d83a6955f23f | FREQUENCY: Each Pit
| note | 3eb8b3ca-a940-43b8-abe9-3cd59cef40c6 | CATEGORY: IP
| note | 32beb8ac-9abc-4be4-82c1-41083a6e7785 | RESPONSIBILITY: SE/Site Supervisor
| note | b0fae444-98e6-4b9e-a084-7e87f531fd01 | VERIFYING DOCUMENTS: Sign ITP , Attach Test Report
| textbox | 4da12824-2b4a-4674-9faa-e107ae7c6d0f | Date Completed:
| checkpoint |  | 9.6 Step Irons
| note | 02848c68-fe0f-4857-ba6a-2e90eab7c011 | REFERENCE: IFC Drawings
| note | 35a4bb80-f6a0-4f11-afe7-7a873db3f267 | NIST 012.2.1 0_9.3.7
| note | fe66646f-9d60-40fb-92e1-fef50a4c0b65 | NIST 012.2_14.2
| note | c6adb3a8-3340-4313-a918-f7b868ca2c77 | AS1657
| note | fdd26088-f6a1-46c8-8297-41b1a41de248 | ACCEPTANCE CRITERIA: Unless otherwise noted on IFC drawings, the below is required:
| note | 0b76e2f1-93ed-409f-985b-243a0a3aa10b | High Voltage Pits: Step irons/rungs to be installed if pit is greater than 1.0m in depth (including lid thickness)
| note | e242979d-6a4f-454a-bfa3-42526ca8b282 | All other Pits: Step irons/rungs to be installed if pit is greater than 1.2m in depth (including lid thickness)
| note | 0e34e506-f8f4-4e63-ba14-fb7ec2e08aeb | METHOD: Visual
| note | 613cde81-3f69-4dc4-bbc1-e41fe99a2855 | FREQUENCY: Each Pit
| note | b082aa98-6224-4cc7-8749-192094a1004e | CATEGORY: IP
| note | b8a436d0-ce61-4ee6-b0a2-8316cc35099d | RESPONSIBILITY: SE/Site Supervisor
| note | 0bb81efd-5fa8-478f-8715-b499c2e6f2ab | VERIFYING DOCUMENTS: Sign ITP
| textbox | 153fb56c-fa98-4ba9-be2c-52257979ecc1 | Date Completed:
| checkpoint |  | 9.7 Spare Conduits
| note | 1abbb044-7f9c-49f8-b9bc-30c876c1cebc | REFERENCE: NIST 012.2
| note | ac6e3ed4-0c0e-41a7-8a87-b3cceb4be8ee | NIST 012.2.1
| note | 46d5610d-11d5-4474-8acd-85b67d609cd5 | IFC Drawings
| note | 8c850df1-ccce-4171-9258-76cf18668c0d | ACCEPTANCE CRITERIA: Spare conduits to be sealed with a tapered polystyrene plug and to be included on survey report.
| note | 061c9c47-38ce-45f2-a91e-5b55b669a683 | METHOD: Visual
| note | 4cfffb1b-91bb-4564-997a-6663de55db47 | FREQUENCY: Each Pit
| note | b5fc70ff-a717-44f9-843a-01cf9615251a | CATEGORY: IP
| note | 2fa5eb30-1f3f-4b1d-83a6-e95cad8ee624 | RESPONSIBILITY: SE/Site Supervisor
| note | 1a235a3d-4ae7-4db5-9535-3d5bac8d3b81 | VERIFYING DOCUMENTS: Sign ITP
| textbox | c7bba506-9c8d-4739-8b8b-247130020ae8 | Date Completed:
| checkpoint |  | 9.8 Pit Labels
| note | cee6ab31-d0c1-4365-96ba-7d6c9ef80a93 | REFERENCE: NIST 012.2
| note | 14db544f-e83f-4d5c-9e3c-855195bd4288 | NIST 012.2.1
| note | 07214b12-8d53-4285-8d64-9ed2fc379de0 | IFC Drawings
| note | 061de332-062d-4ed7-aafc-d72cb0e282a1 | ACCEPTANCE CRITERIA: Pit labels Brass Label (30mm x 150mm)
| note | a26e1360-dcf7-4115-b16d-25f5218da549 | HV: DANGER - Railway High Voltage
| note | 559dfdef-7d0f-4b0e-b4ca-8b963ec900b1 | VicTrack: Victrack Comms
| note | 775b94d8-c867-46dc-ad52-ed30a308f5f2 | Signalling: Rail Sign Comms
| note | 3c0fcf8d-c853-43ff-b5b0-20bda4a4fdab | LV Pits: Electrical
| note | 2a0800bc-5ea9-4fcf-ae63-23541b5ca8d5 | Electrolysis: Electrolysis
| note | b481c644-8825-4ee3-9d1a-eadb345c3298 | SCADA: Rail Sign Comms
| note | bbc52363-f332-4eb4-81fa-5c7bb9504364 | V/Line Comms: Rail Sign Comms
| note | e3f3d4d6-f0b6-4778-b7dd-e5cc01cb20b8 | METHOD: Visual
| note | 32c1b77b-6e24-4ee5-a568-4bb2939545bb | FREQUENCY: Each Pit Lid
| note | 3f6b1854-20e9-43fc-9dbd-8793929a3e51 | CATEGORY: IP
| note | 72d6c40e-03c9-48ab-8e30-5571eb76e523 | RESPONSIBILITY: SE/Site Supervisor
| note | 45a27ecc-191e-4a76-9496-2c4a30068776 | VERIFYING DOCUMENTS: Sign ITP
| textbox | b00e0d64-9e1d-4fed-9eaf-ae0124bec8c3 | Date Completed:
| checkpoint |  | 9.9 Pit Numbers
| note | 02ba594f-7c6a-494f-b1e8-fc2097931314 | REFERENCE: NIST 012.2
| note | 8ad32636-c5ff-4ef1-9e1f-b3183ac09cce | NIST 012.2.1
| note | f2dfa5a0-9179-43dc-9c84-ae7133f3da3c | IFC Drawings
| note | fd51c4f8-c290-42ec-97fa-91f15e86701a | ACCEPTANCE CRITERIA: Pit Number Brass Label (30mm x 150mm)
| note | dbcdc5a7-f1c5-4e66-aeed-4037d8acce0e | HV (22kVV Feeders): ###HV
| note | 1a03c5c8-a4b2-4fe0-b92e-4eb58f6939a4 | DC (HV Feeders for OHLE): ###DC
| note | 14870288-5121-42e0-9ce5-32877039503d | VicTrack: ###C
| note | 8377d771-ce15-488f-94e4-aef5d11abc3e | Signalling LV: ###SL
| note | b675f193-3c72-42d4-8898-ff9bd825cac7 | Signalling HV (2.2 or 3.3kv): ###SH
| note | 1ce1b96e-06ac-4ec1-bd7f-85c64a801143 | LV Pits: ###L
| note | e78df3f0-f43b-4bb5-8887-a442f9501e5d | Electrolysis: ###E
| note | 9d4e480c-9877-42ee-9f21-49a550fe93a1 | SCADA: ###MS
| note | a65d482f-b923-4ca7-9788-957a5875e7a0 | V/Line Comms: ###M
| note | 2c7e7ab2-3e4f-4bc7-bf97-abf848c38abb | METHOD: Visual
| note | 12a4cd5a-00b2-4875-8702-32dc19edd1ce | FREQUENCY: Each Pit Lid
| note | 5aab0bb1-9e90-4e48-9632-f2ec15160c3c | CATEGORY: IP
| note | fb3cbc76-1564-466c-9dc3-95eb2326e572 | RESPONSIBILITY: SE/Site Supervisor
| note | 5403458e-4f26-440b-8f27-3eaffd508cf7 | VERIFYING DOCUMENTS: Sign ITP
| textbox | ed3220e8-7a83-4541-bf93-d974eae3eb22 | Date Completed:
| checkpoint |  | 9.10 Mandrelling
| note | df85469e-cc01-4f28-ba2a-936454bfaaab | REFERENCE: NIST 012.2
| note | 28b726af-6aff-4a3b-9235-aa23f73e9d3a | Section 16.1
| note | 3d529fa7-e72d-41f9-be0d-471a123272e4 | ACCEPTANCE CRITERIA: The mandrel shall be solid, have diameter not more than 12mm smaller than the internal diameter of the conduit and be a minimum 230mm in total length and 130mm in flat length. It shall be pulled through every conduit in both directions by hand or with a machine to ensure their integrity.
| note | 7cc0bf78-a67f-4aa7-988b-0ce59c694f41 | MTM/Victrack Witness
| note | 527b4412-751b-4c1e-8612-bef77c9aaff3 | METHOD: Visual
| note | 6d4587a3-2d0f-4420-8b60-8f8cc902988d | FREQUENCY: Each Conduit
| note | 2d7912e3-41f3-4093-a52f-d33d241c1779 | CATEGORY: HP
| note | 8c80aa78-6a9b-43a9-92d4-954df982ff45 | RESPONSIBILITY: SE, NA, V/Line/VicTrack Rep.
| note | 1e7e60ad-761a-4bc6-b06b-2374c598127e | VERIFYING DOCUMENTS: Sign ITP
| textbox | 26ffcfd4-fff4-4fa0-8e1c-1228228f9874 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Protection and Labelling
| checkpoint |  | 10.1 Non Trafficable Pits
| note | 3cb8d862-b784-44f8-b877-cfced91f8564 | REFERENCE: NIST 012.2
| note | 5d93b4c0-931b-4cba-b876-eca001b6123f | NIST 012.2.1
| note | 16b70b14-0aff-41ac-9d17-de27f5759e6d | IFC Drawings
| note | 94ccf78d-5a14-4b3d-8cbf-9506ca813301 | ACCEPTANCE CRITERIA: Non trafficable pit lids to be 50mm above FSL and to have 2 x white bollards installed at the corners of the pit.
| note | 837fd1fd-0ab1-40d2-98d0-082a4a5e4f4d | METHOD: Visual
| note | 2b614ed9-410b-4e69-b55c-87bc91f138a5 | FREQUENCY: Each Pit
| note | 23cffead-22bf-4539-bb7a-130d3b5df645 | CATEGORY: IP
| note | 03c6df97-cfa1-4d14-ad78-3438308c81c0 | RESPONSIBILITY: SE/Site Supervisor
| note | 272d043d-65d2-46df-8345-1b6249b041ce | VERIFYING DOCUMENTS: Sign ITP
| textbox | 3ff2aa03-888f-4711-bc1e-4c06b66b6b79 | Date Completed:
| checkpoint |  | 10.2 Sand Pits
| note | 3d35b51c-5007-451d-a757-e614ad3206cb | REFERENCE: NIST 012.2
| note | 6e1f0133-e3fb-4872-87ca-5d93b31c195d | NIST 012.2.1 Cl 9.4.3
| note | 620a9fd8-e35f-4167-93be-0915d3018a6e | IFC Drawings
| note | a0133873-e5ad-4a10-8671-970de46798b8 | ACCEPTANCE CRITERIA: Sand Pits (HV)
| note | 81273f85-aeac-49da-aaed-3134ed06cd9b | 4x yellow posts installed at the corners of the pit and 2 of which shall have cable route markers attached
| note | 9e3e317c-e5e3-4430-ab16-1bc69d691cc0 | If posts are impractical, 4x monuments with cable route marker plates affixed and a cable route marker nearby indicating position of the pit
| note | b4347702-b410-41b7-80ef-c996823a8968 | METHOD: Visual
| note | 4738d428-5e25-47bd-bd9c-4f4ebc932646 | FREQUENCY: Each Pit
| note | e60f074b-5f56-4908-82e9-c668ae6b152f | CATEGORY: IP
| note | 9911d309-2ef2-4e2b-aac3-fc22d47cfae4 | RESPONSIBILITY: SE/Site Supervisor
| note | b459e014-be98-4103-90eb-a45343bf85fc | VERIFYING DOCUMENTS: Sign ITP
| textbox | 27cde6a1-2718-4240-858e-59f26eaaf261 | Date Completed:
| checkpoint |  | 10.3 Cable Route Markers
| note | 4e8f24b9-4f04-4273-a12c-c284a27c8fc0 | REFERENCE: NIST 012.2
| note | 9ab8f74d-5ee2-4f9e-afb8-6575b5a04aaf | NIST 012.2.1 Cl13.2
| note | a6f1ba99-758d-4701-accc-1816b6b6c901 | STD_E0169 and STD_E0170
| note | 742bf9e1-f010-4b99-93ee-b6e09c0a9ca1 | AS 4799
| note | bd168bdb-1912-4347-bffe-967bae15a664 | STD G0003 and STD G0004
| note | 01c99150-6e54-4986-b6c0-a9f2137508b5 | ACCEPTANCE CRITERIA: Cable Route Markers
| note | 7125f739-320d-4748-91fc-95f8e6733d5c | points entering & leaving the rail corridor
| note | 564add37-4565-4712-a21d-6c57ff84ccbe | no greater than 100m spacing
| note | fb515b6f-b15b-4f9a-85c8-4cb0e4d1fbe9 | Change of direction (more than 5 degrees)
| note | 3e7a274e-0110-46e9-9dff-6499326151e5 | White posts with marker plates for conduit runs
| note | 49f24223-b75f-4211-8b96-7878b2afc361 | METHOD: Visual
| note | 820d3899-d5fd-4795-9c40-701f1168d7d6 | FREQUENCY: Per Cable Route
| note | b9f7c8b2-9e10-4729-9332-20081fa44bbe | CATEGORY: IP
| note | 832a2c7e-4f61-42a3-8ff7-8a488613b0e5 | RESPONSIBILITY: SE/Site Supervisor
| note | cf8d43ea-0942-4b91-895f-195a0ede68c5 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 0f5b0d1c-289e-4ab9-a43a-0124082699d2 | Date Completed:
| section |  | Cable Route Handover
| checkpoint |  | 11.1 As-built Survey file
| note | 3ad31385-12bf-4092-9b0b-2858cbc4860e | REFERENCE: NIST 012.2
| note | fffb4572-8428-4c85-83f0-d2fa10759591 | NIST 012.2.1 Section 13.1
| note | 1d2e3cc5-5819-4dc4-9ae7-c37d44755237 | ACCEPTANCE CRITERIA: Survey report to include but not limited to:
| note | c7d030b9-b742-44be-a35b-b126628fa44a | Cable joint locations.
| note | fb0ecc90-34a2-439c-b9c2-b2fcfc7925d2 | Cable pit locations (Corners)
| note | f0992457-80ee-4d4b-b7de-87a0ceafcc08 | Pit dimensions & pit lid type
| note | 4adcb18b-d90d-4260-822e-978c2208ea7f | Under line crossings
| note | 475ae567-50ac-4ec8-b9e0-fe8846e5cda6 | Under road crossings
| note | 790da2de-d0bd-4337-b81f-95e63c656315 | Changes of direction
| note | 53f709a9-9f07-4f3f-bfc0-e8c4472c001c | Spare Conduits
| note | bdf0ffe9-f0d6-40f8-b891-c6ff241116e7 | Conduits labelled as per trench profile
| note | cff3fe90-517f-4d9b-ba3b-b8967cb51ca8 | every 10m
| note | a68586fe-10da-429c-b307-f03e6f120fb4 | Other significant points of the cable route
| note | a5806a93-ad66-4765-bd3c-5dcb95426bcf | METHOD: Document Review
| note | eb881245-077d-47d6-89f1-eeeb643f27ff | FREQUENCY: Each Design Pack
| note | d0c19f04-93c2-4b90-af3b-7cb52bfb000f | CATEGORY: IP
| note | bce788a9-8560-44f5-9d61-4394da39579b | RESPONSIBILITY: SE/PE
| note | 66c257af-1fcf-41a8-be23-97883190709b | VERIFYING DOCUMENTS: Sign ITP , Attached Survey Report
| textbox | dd6829fa-0261-404a-a06e-832a0f022bc2 | Date Completed:
| checkpoint |  | 11.2 Engineering Redline mark-up
| note | b6aea00e-3e18-412d-8a8c-e14ccfc8af1a | REFERENCE: IFC Drawings
| note | dd58bad8-ca6a-4913-a7a7-6e529f9b472d | ACCEPTANCE CRITERIA: As constructed cable plans shall be provided for the entire cable installation and in accordance with AS 4799 and the PTV Infrastructure Drafting Standard.
| note | ca02366e-43a2-4380-a4da-4fbd43291018 | METHOD: Document Review
| note | 70c109cc-5457-421f-a651-0802b98d7f63 | FREQUENCY: Each Design Pack
| note | effd60a1-490c-46be-a279-b18e6aad9d67 | CATEGORY: IP
| note | 1b6c7a90-d62a-4de8-869a-f97eef548aaf | RESPONSIBILITY: SE/PE
| note | 470522a0-15a3-4f5c-9f52-c6b244a4285c | VERIFYING DOCUMENTS: Sign ITP , Attached RLMU
| textbox | f563e1e8-2785-4627-8b9a-64dd0a94d1bc | Date Completed:
| section |  | Cable Pulling and Terminations
| checkpoint |  | 12.1 Cable Pulling
| note | 366f109c-83b6-44ae-b8db-b8c4084104a9 | REFERENCE: NIST 012.2
| note | a49a6096-1e02-4f13-b67e-430e87450c57 | NIST 012.2.1
| note | bd8c3633-0f02-4217-81ed-340dcb97d725 | IFC Drawings
| note | c77a58a1-c617-4ba1-be63-3809c385d374 | ACCEPTANCE CRITERIA: Cable pulling to be witnessed by V/Line/Vic Track and to be signed off.
| note | 0aec241a-b4a0-4714-8bf4-bce7d2b55d99 | METHOD: Visual
| note | 98c72e0c-abc4-4578-99a5-2c0278033efc | FREQUENCY: Per Cable
| note | 48bc00dd-f6a0-491b-ab7e-ea46090c9ee1 | CATEGORY: HP
| note | ef6ad673-4fbd-4526-b68c-2c302da0da1a | RESPONSIBILITY: PE, V/Line/VicTrack
| note | 3276b038-3af0-462d-a738-254e1017e4fa | VERIFYING DOCUMENTS: Sign ITP
| textbox | febe3f20-1665-48e3-86be-dcb024e35ccd | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 12.2 Cable Labels
| note | 24b53930-2dcf-4c4d-ad4e-6579f34579d7 | REFERENCE: NIST 012.2
| note | b3f91929-d947-4cae-96d2-728d875f4a16 | NIST 012.2.1 Section 13.3
| note | a032e91a-48cb-418c-8d7e-b9fa7ee92959 | ACCEPTANCE CRITERIA: All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
| note | 2b849c39-403a-4233-ad4c-b74f4da88eb1 | The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
| note | 17ed9dc8-2a62-44b4-9fae-f1721e450015 | METHOD: Visual
| note | 8cc08c5f-c79f-4473-ba3c-aabc452417b7 | FREQUENCY: Per Cable
| note | a1ac9781-708a-4858-8e71-9ceed9f8c02a | CATEGORY: HP
| note | e343df0a-d38b-444b-a9e6-62d0cee1eed0 | RESPONSIBILITY: PE, V/Line/VicTrack
| note | bda8e9fe-cd92-4d94-b22d-ba1b576d32f7 | VERIFYING DOCUMENTS: Sign ITP
| textbox | abb94d22-c059-4455-aadc-c392d0154267 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 12.3 Cable Joints
| note | 620734a5-a8da-48be-a259-11ff8e1e7910 | REFERENCE:
| note | 614ab40b-0dc8-41dd-8d6d-3aadae2dff6e | ACCEPTANCE CRITERIA: Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
| note | c6eeed25-2aa7-4c24-b778-a302624581b1 | METHOD: Visual
| note | 1fb2352f-d044-44c7-814c-46c02a0cb3ff | FREQUENCY: Per Joint / Termination
| note | 1aaf6693-0a3a-469b-b223-a010ff1c642d | CATEGORY: HP
| note | 5413b90a-ecb7-4346-9df8-22ced67da211 | RESPONSIBILITY: PE, V/Line/VicTrack
| note | d819db89-59a7-48e4-8c1c-f2aa1eee7fe4 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 78a674a6-e531-4f07-843c-52a45505e94c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-installation Activities
| checkpoint |  | 13.1 Handover Check
| note | e0576fb1-da84-4918-b911-0b1ad050ec14 | REFERENCE: IFC Drawings
| note | 0bdc409b-fd2f-49b6-ba63-ec368c9e3634 | ACCEPTANCE CRITERIA: Handover check completed for Testing and Commissioning.
| note | e417dea1-7922-4380-97d3-3a6f66a09991 | METHOD: Document Review
| note | 4f6f1f87-7e25-40ce-a74b-1db4066fa0c6 | FREQUENCY: Per Lot
| note | 00bcd09b-6168-4b1f-b9f8-d5007150410e | CATEGORY: HP
| note | 660b96cc-627b-46ff-9740-9713f34aee0a | RESPONSIBILITY: PE, V/Line/VicTrack
| note | 7f7b7318-c16e-41c4-aa52-a94cebd0894c | VERIFYING DOCUMENTS: Sign ITP , Attach V/Line/Vic Track Check Sheet
| textbox | 8b573af1-f1ec-4297-ad5f-514be41970bc | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 13.2 Testing and Commissioning
| note | 1b7deb4a-3b3f-4762-8e5f-2872e0fd74ae | REFERENCE: IFC Drawings
| note | 1ade78fc-da5e-43f4-b070-f27e48462b75 | ACCEPTANCE CRITERIA: Testing and Commissioning to be completed
| note | d3ccfe62-6d55-4ba0-9645-b497999eccde | METHOD: Document Review
| note | d97cb813-4d43-4415-ae63-eb65c05409b4 | FREQUENCY: Per Lot
| note | 89d76a46-3810-483c-b8e5-98eb294b6877 | CATEGORY: HP
| note | 35693f83-7a56-455c-932d-c5bf1de1a1ae | RESPONSIBILITY: PE, V/Line/VicTrack
| note | 4aeec143-09bc-45d9-8c8f-b3d3c00611f5 | VERIFYING DOCUMENTS: Sign ITP , Attach T&C Report
| textbox | 29637765-d00f-4cbe-8394-b7e25352e4b7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 4d5c75ce-7771-4691-af4e-bd9b353acf23 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 867364db-3352-4fdf-99ff-aacc2c35a128 | Name:
| textbox | 54edd2a9-3b6c-435c-8d94-18c4d5affea1 | Position:
| textbox | 8784eb75-0059-4632-a704-a98491518140 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | itp | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | bda42295-a1f6-4fe5-b4df-28cca3444faa
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 219d439f-ddf0-49ca-8216-5eda342d520a | Document Title: ITP-CIV Type A Fill - Road (Supply and Install)
| note | 09929009-dcd4-46d4-9752-761ec78464ec | ITP Description: Type A Fill - Road (Supply and Install)
| note | 2d3d2701-1923-4241-a254-8c94bb310c98 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 8afcfe72-198e-4298-adcf-4d9c4f81a175 | Revision Number: 1
| note | 0c899010-3dc0-4247-9b45-c25f6faac4bc | Revision Date: 8/07/20
| note | 0a64eec8-eed2-4eb4-b918-82aa5f48dd1f | ITP created by: Patrick Cusenza
| note | 68f2f666-c2cd-4621-8cd5-8e77d20d5572 | ITP approved for use by: Josie Pavlou
| note | 908d3433-587c-493d-a210-12c86eb49dd5 | 1.1 - IFC Drawings
| note | fb0a7ed8-08c8-4b53-bcb6-306c58b80f76 | VicRoads Standard Section 176 (Sept 2008)
| note | f8d5b79c-76dc-42bd-9df7-379501253d86 | VicRoads Section
| note | a93042c5-ce6f-4dc8-a39d-cb7ea9f53f7e | 204 (Dec 2015)
| note | 167433c3-5c86-41c5-ae8a-d5dbe3945a4b | Code of Practice RC500.20
| note | 9bed7f54-a292-4583-a70d-69eeed77ba4e | Code of Practice RC500.5
| section |  | Preliminaries
| checkpoint |  | 2.1 Material Conformance
| note | 42547e9c-c2e0-45d7-8ab6-ab7117d26f7b | REFERENCE: Section 204.04 b)
| note | af1d2486-1bd5-430b-b7aa-893ec48a5760 | Table 204.041
| note | 0cfdab94-781e-4892-9f03-0527319984d7 | ---------------------------------
| note | 0f479c18-23c7-4216-b582-de44b5451e33 | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
| note | 3b010a35-7542-455b-aaa8-61122a5ac9ce | Assigned CBR≥%3%
| note | 0d36e2fc-dd2d-4f09-965a-28027e2bea4e | Swell ≤ 1.5%
| note | e109b111-2e1f-4be0-be57-9bd5f2983b9c | Max Permeability = 5X10-9 m/s
| note | d589edc4-f996-4716-8c2b-2a064d45c0dc | Grading: 75.0mm 100%
| note | a7fb5b76-f7aa-4e9e-bdb9-56ee007aafe4 | 4.75mm 40-80%
| note | e0349b15-551a-434b-a706-c4806aa48d99 | 0.075mm 10-40%
| note | bf45b632-0091-417c-8a82-e027f6677f3b | ---------------------------------
| note | 4f812e72-58c5-4486-af77-fa6b16c8e40d | METHOD: Document Review
| note | 4973117d-4eef-4b92-96a0-0d5945c92a67 | ---------------------------------
| note | e516d65d-ca74-4580-b5c0-362d9625504e | FREQUENCY: Once, for each material type
| note | beccf82c-18be-4962-a215-d37cb0d2aa23 | ---------------------------------
| note | e5fa5fc0-60b3-4238-b2cb-30bb5e8e3a2e | CATEGORY: HP
| note | 7c2796ec-5154-4357-ba3a-dfb2239d6f1d | ---------------------------------
| note | 9be23f25-ad8c-472f-9f59-814319e0fb1a | RESPONSIBILITY: SE/Nominated Authority
| note | 173bbd53-02df-445e-8398-3cb8a002daa8 | ---------------------------------
| note | 376e1eb2-046d-4505-8bd8-3f090a507fb9 | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
| textbox | 357c0388-73f1-485b-aa2f-10c33f81a737 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set Out
| note | 0df6bffc-e42f-45bf-bf65-915c692f3d30 | REFERENCE: Design Drawings
| note | c66f1132-4e19-4e8d-b210-7b0667695097 | ---------------------------------
| note | 370908e9-2e9f-4ae1-b135-b5c11b190d3a | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
| note | f334377e-711d-4441-b4c5-0abf32bb17c5 | ---------------------------------
| note | 2d37f062-7696-4d14-8aa1-f6e118f8e699 | METHOD: Visual Inspection
| note | 68d8ad05-8863-4f7d-9e33-c43a06eef07a | ---------------------------------
| note | 18e7b653-916a-47c6-a8dc-8edfb66f8363 | FREQUENCY: Each lot prior to commencement
| note | ab7e4f0b-911a-44be-a9d7-fb8336bc39a6 | ---------------------------------
| note | 6ee20ca2-0579-4dba-af0e-f377a69879d0 | VERIFYING DOCUMENTS: Signed ITP
| textbox | 061918c1-d092-46ab-8733-7c4afa230b82 | Date Completed:
| checkpoint |  | 3.2 Pre-Commencement of Fill Works
| note | f5f19406-993a-4a2b-a530-3f3975aca133 | REFERENCE: Section 204.10 (b)
| note | 4c3b9028-1ca8-461e-b851-0fe44a9526aa | ---------------------------------
| note | a7597711-3e0b-461a-ad90-ded8f4b8e404 | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
| note | b6804ac7-b690-4505-b7d0-c7cb00147eef | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
| note | a3d48aab-365e-40ba-b3cc-acc08278fb6f | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
| note | 94492296-ca50-48b9-93e6-2040429b1b0f | Refer to ITP-CIV Subgrade Preparation - Road
| note | bdb5e1a5-68e0-4176-913d-3ebf4e905c4d | ---------------------------------
| note | c811fb2a-8d9b-4265-9dd1-680bde18f633 | METHOD: Visual Inspection
| note | b49d7e32-b320-4a68-a11b-8ad22c2257e5 | ---------------------------------
| note | d7043bc7-d23b-4bbf-9cb0-72dd86fe68ce | FREQUENCY: Prior to commencement of fill works
| note | de502fe5-20cd-41b8-8c15-5a4bc9971e66 | ---------------------------------
| note | dfa464d9-d3c2-43b3-a3e6-ea1baadc5977 | CATEGORY: HP
| textbox | 1a88b67c-f9a2-4d6a-9f8a-2f3aba8fb835 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Type A Fill/Verge Activities
| checkpoint |  | 4.1 Placing of Fill
| note | a44726ad-2ccc-4ac9-929e-6aaf64efef78 | REFERENCE: Section 204.10
| note | 38d95a9a-f1c9-4011-b5df-081bf1104103 | ---------------------------------
| note | 79ae5220-512c-4472-89e7-3f3efe58d5f9 | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
| note | 2706119b-af09-4ea7-a5d6-08d9e710c11a | ---------------------------------
| note | 2a6cd35e-68cc-48f9-b341-a81756e82956 | METHOD: Visual
| note | 4edfb2ca-4173-4086-b12b-78a5e06fe2db | ---------------------------------
| note | 4b636ddd-320e-40be-a333-a47665ae4079 | FREQUENCY: Each Lot
| note | 87693c2d-4eaa-4ac6-beb0-91e63f942d9c | ---------------------------------
| note | 6366be23-e927-4431-a389-14f20bfaf4d6 | CATEGORY: WP
| note | a65611ca-4993-4628-aa04-98831077e2b0 | ---------------------------------
| note | 2c83d07e-75c8-4b94-934d-df45c4c5c0a2 | RESPONSIBILITY: SE/Site Supervisor
| note | a4a46bab-689f-4681-83d3-b5fa721ad979 | ---------------------------------
| note | 2e5bb2c6-366b-4c10-a8da-278d801fec3b | VERIFYING DOCUMENTS: Sign ITP
| textbox | 6a1c7457-829d-492f-9177-2dc11f512637 | Date Completed:
| checkpoint |  | 4.2 Test Roll
| note | 75d6575f-6329-4392-8906-8630bf9f0162 | REFERENCE: Section 173.03
| note | 678c69b2-1a11-4e1a-b958-535349ceb6a0 | Section 204.12
| note | 4910082d-57b0-498c-8ae0-07c9e4f98216 | ---------------------------------
| note | 057b94e0-13f2-4b22-ae90-2d93df803b0c | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with
| note | 3426f03b-04be-4138-af05-f81e4cf5bb5d | Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
| note | 0378aa55-3b80-4c0c-8eb2-5fc2a61b8a85 | ---------------------------------
| note | ad150cc0-7233-4b0c-a85a-0bfc1cdd110d | METHOD: Test Roll as per 173.03
| note | e7a69b63-6085-42f8-826a-e7a28ace5683 | ---------------------------------
| note | 658300ae-8d8d-46ad-85fe-45a0664e8530 | FREQUENCY: Each Lot/Layer
| note | b070a571-bec7-4dd2-afb0-f16c28558c76 | ---------------------------------
| note | 2ceba451-731c-4799-ba5b-7a305ebb71a3 | CATEGORY: HP
| note | 29d70c61-08b7-4a26-9938-92f53be44b6f | ---------------------------------
| note | d45677c7-dcc6-4823-a324-165248e6fbf9 | RESPONSIBILITY: SE/Nominated Authority
| note | 93aa9547-186a-402b-a63b-84c6ed8391a6 | ---------------------------------
| note | ed7504fb-1836-4c72-a103-46d421acf621 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 2bbb7272-3999-45ab-aa8e-ab2ceb1689f9 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.3 Compaction Testing
| note | 7eba1e98-37bf-472d-aed8-c939b57ab24b | REFERENCE: Table 204.131
| note | 2bbd22de-5da2-4cb8-a376-918dcb1574ba | Section 204.14 c)
| note | d7cc5b20-a948-4b16-9e18-ee3e79081012 | Table 204.142
| note | eafe4e3f-9f03-4ecb-86dd-27a4344192c4 | ---------------------------------
| note | 738e8dec-4e1f-4b42-8b68-22e71ebce8e6 | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
| note | 5a09891b-da46-49b4-be5a-f341a00875a9 | Standard Compactive Effort
| note | eb92d6f8-00d6-4f97-afc0-bbe1c7e9b83b | Compaction and Moisture content
| note | 48bb0c0e-3549-4573-b907-891361acaa92 | Scale A: Characteristic Density Ratio 99%.
| note | 4f0e7d31-42c4-483d-bfef-f1db74d11740 | Scale B: Characteristic Density Ratio 98%.
| note | 0e32aef7-d0e5-4b3f-855c-e1919294ee6c | Lot size - the leser of one day's production or 5,000sqm
| note | 6d67d4bf-979a-45a3-9303-464e01c9d168 | ---------------------------------
| note | 5d218863-1eb1-415d-ab29-ab7d781681d5 | METHOD: Review Document
| note | fd5c9f8b-0f82-49d1-8590-e40fa904ac41 | ---------------------------------
| note | a3592c64-a632-4668-9a77-070153a8b60b | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
| note | fa9ebe1c-8bbc-424f-a18f-ac64eface7ef | ---------------------------------
| note | b343511c-4505-4e4e-8c8f-ab791f093b4a | CATEGORY: IP
| note | 6421c93f-d98d-42e3-b925-7bebceaa5eb5 | ---------------------------------
| note | 17d6dc4d-7781-4b18-bfb5-2f1d54368239 | RESPONSIBILITY: SE/Site Supervisor
| note | 4e2e56e8-e1a2-473d-b215-9f52fb2e14b0 | ---------------------------------
| note | 323d7ec9-46ae-4bd9-859e-25f4d92032b8 | VERIFYING DOCUMENTS: Sign ITP Attach Compaction Test Report
| textbox | 734bf24a-1416-4304-a560-1738f3affb13 | Date Completed:
| checkpoint |  | 4.4 Post Compaction Material Property Testing
| note | 43f66991-589b-4474-8f26-c5b70e34490d | REFERENCE: Table 204,041
| note | 140b613b-4d4d-4152-b869-d23ba77cc89e | Table 204.141
| note | 5ae143b0-3771-40f3-acf6-080c0cc04071 | Section 204.14 a) or b)
| note | b2d7d8fd-6d1c-4a86-a930-445884d75f52 | ---------------------------------
| note | 0b7a6c39-8751-4d1c-b335-fc388a2231a9 | ACCEPTANCE CRITERIA: Material Properties:
| note | 6426037d-7981-42eb-8648-14204cd5052e | CBR ≥ 3% and Swell ≤ 1.5%
| note | 6494dff9-fc88-4af4-833b-f2b469830f9e | Max Permeability = 5X10-9 m/s
| note | 6973cef3-cda6-4b62-b975-46232743a57e | Grading: 75.0mm 100%
| note | 0971e328-3f80-4646-a3fd-ebdb8ddb2dbd | 4.75mm 40-80%
| note | 648ffd46-4052-42c9-88a4-849fc4b984bb | 0.075mm 10-40%
| note | 2194e04b-4aa7-4e6a-b2cb-a3afd58357bc | Max. PI x%Passing 0.425mm = 1000
| note | c9068f8b-7803-4bf3-a47a-4e2533c16f43 | PI = 6 to 25
| note | 7535fe25-4cee-4f68-a9d0-d96aaa637b8b | Scale A:
| note | f07c7716-3cf2-442d-bc78-a8f621401183 | CBR & Swell
| note | 0f7c3138-f4be-4308-aa2e-2d1bedf44ac7 | Initial - 1 Lot Test to determine Assigned CBR and swell
| note | 9ac73700-d385-4ba3-b600-a331521fb132 | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
| note | d83dabfb-c542-466e-bd5d-1f4e549ad218 | Max Permeability
| note | 1495640d-267c-4ec7-8573-64072eb66396 | Initial - 1 test per 2 lots
| note | 8f05969e-6595-46b4-8473-7984abaff49c | Reduced - 1 test per 4 lots
| note | dc3dbf41-273d-47fd-b093-2411f485c33a | Grading:
| note | c06552d9-1035-4b95-9526-f4c98feeda7a | Initial - 1 test for each lot tested for compaction
| note | 28e66ff7-b799-467e-ba53-cb763238ac87 | Reduced - 1 test for every second lot tested for compaction
| note | 4eca4b3b-d631-4234-a083-a5eff33e0fbb | Max. PI x%Passing 0.425mm & PI
| note | f95b4a63-1a40-4e2b-949a-69aaf78e9ae6 | Initial - 1 test per 2 lots
| note | c5d78da3-70b6-4fb7-b394-0f5b6e962da5 | Reduced - 1 test per 4 lots
| note | e4b23851-1b00-4320-bd06-b634573db7ce | Scale B:
| note | 1f15857b-6f92-4ea7-9106-3bb155e3c150 | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
| note | 34c1d0f6-195d-4b65-b1b7-fba1850a3275 | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
| note | c8f9e8a4-0149-4457-8e21-2bc004e41d7d | ---------------------------------
| note | 94918d22-db18-471b-98c0-91698f66f2ac | METHOD: Review Document
| note | 43820ba7-ea11-4e71-8c85-693c55cb42ed | ---------------------------------
| note | a18458e9-c67f-4a9d-b61c-406a5c87fe10 | FREQUENCY: Refer to Section 204
| note | 1b2909ce-bbe3-4d02-af46-755ec4656f2d | ---------------------------------
| note | cee5c35c-c478-4030-a289-25ca93642c23 | CATEGORY: IP
| note | 5da16fba-9624-4c0a-a118-483967680852 | ---------------------------------
| note | 6ab86650-c57a-48b0-bd87-4b43827feac0 | RESPONSIBILITY: SE/Site Supervisor
| note | fc63a1fc-e691-406e-b073-6fe805c5fef4 | ---------------------------------
| note | 5b90ed4b-0dab-40b5-ac98-e96416161b2a | VERIFYING DOCUMENTS: Sign ITP Attach Material Property Test Report
| textbox | 6bf9d139-7947-4542-8d88-d76239e114ed | Date Completed:
| checkpoint |  | 4.5 Preparation of final surface
| note | 39518ab9-935f-4969-b2c9-1a047f05b801 | REFERENCE: Section 204.15, 204.03 (g)
| note | f831e189-5275-440a-aac8-e69a33876bb9 | ---------------------------------
| note | 3584ddc1-85fc-4882-bef7-c26d50f7e669 | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
| note | b7ef2000-be4b-42da-a681-7b95601772c8 | ---------------------------------
| note | 1792068f-871b-47a9-8e62-f10ffa4bb5c5 | METHOD: Measure
| note | c6315073-881f-4570-8544-a8897bb42cad | ---------------------------------
| note | b0909279-f843-45c8-825a-3fdd71cae347 | FREQUENCY: Top layer
| note | 40761473-5969-4d85-b242-a75d010d2460 | ---------------------------------
| note | a5ed9020-fa32-4bfd-badc-5e3de6f6e1ff | VERIFYING DOCUMENTS: Signed ITP
| textbox | 8d9e6b07-6de7-4081-8235-30b396e82ebc | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 5.1 Survey Conformance
| note | 74c733df-da93-4e5f-b0cb-ee72a9a26e34 | REFERENCE: Section 204.03
| note | 08775571-f557-4aba-8276-d6a6b55bd8a9 | Table 204.031
| note | 1ed1f88e-62c2-4144-abb1-9ffa56003850 | Section 204.16
| note | f411fbec-394f-4931-b564-fe3b253b44b5 | ---------------------------------
| note | 645a5aef-5e88-4ff6-b38a-5c4774cf1f9b | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the drawings within the limits outlined in 204.03.
| note | 24f638f0-4536-47d0-8452-f1dffcdfe642 | Scale A (Princes Highway):
| note | d9caf690-74a5-4461-a5ca-a7c9af6ba867 | Min. 80 measurements per lot tolerance from theoretical surface level;
| note | 75cdf1f3-6b78-4fd0-8fa4-e6babb4a2e6e | x,¯ range (mm) = +5 to -15
| note | 8aabb123-f103-42b3-a4ed-6377d013fc78 | Maximum S (mm) = 12
| note | 0471ad4e-f849-4ff7-88b1-ceee9a2c4e4a | Scale B (South Gippsland Highway):
| note | 27b2fb24-8117-4462-9267-a88a50ee75da | Min. 40 measurements per lot tolerance from theoretical surface level;
| note | 1bafcdbb-5905-4d12-b8d3-8081bd72347b | x,¯ range (mm) = +5 to -25
| note | 3028f528-9f66-4aca-8bd0-0796b052ecb7 | Maximum S (mm) = 15
| note | 4517a37b-a62f-4440-8dd3-592c4fcb5069 | ---------------------------------
| note | c54afb63-6b0f-4ae5-9e44-30f83ddd095e | METHOD: Document Review
| note | f0b91cef-7421-4598-b190-92488dcf16f9 | ---------------------------------
| note | 2a26051b-a928-4aad-b5c5-f89a96d6cb7e | FREQUENCY: Top of Type A/Verge
| note | f0549f21-d125-4db1-b9d9-e53c7119a8b8 | ---------------------------------
| note | 563a7d6f-9385-47c3-bae9-2dbe0359e8e8 | CATEGORY: IP
| note | edef4f99-512d-4a26-add1-2df4fa601666 | ---------------------------------
| note | 5084883a-a622-4d8b-8294-1524d8070a1a | RESPONSIBILITY: Surveyor SE/PE/SPE
| note | eca7dcc2-2fd8-4198-a6d2-ea25aac4d178 | ---------------------------------
| note | 18bf0ae1-5091-4574-b885-440281f0442d | VERIFYING DOCUMENTS: This ITP Survey Conformance Report
| textbox | 5501b81b-11bc-4ced-8226-64bf8e17837c | Date Completed:
| checkpoint |  | 5.2 Non-conformance Report (NCR) Closure
| note | 9d107f59-d768-4f8b-90da-d2d373e46967 | REFERENCE: MRPA Quality Management Plan
| note | 366a44cb-e607-4cea-86ac-2dcab5c81ed4 | ---------------------------------
| note | bf30af91-cb89-4ace-8271-3804aa6c4b03 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 6125d760-9dac-43be-ae6b-6a59a60e9c88 | ---------------------------------
| note | 227a6304-fac0-4add-8165-915645ca2c66 | METHOD: Document Review
| note | 35574fce-7fde-495a-95ba-166ef7227904 | ---------------------------------
| note | cc377d2a-d13b-47f0-a639-252b235852c5 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | d03c2671-9ec0-4f66-8d5b-528cc121255e | ---------------------------------
| note | 797d5660-6639-4273-bb4f-16d40e863a8d | CATEGORY: HP*
| note | e0579878-e822-4356-8ce2-56e5426333f8 | ---------------------------------
| note | d3355213-d6df-4f69-949f-1a054a9f5b9d | RESPONSIBILITY: SE/PE/SPE
| note | 00c531ae-393d-43b5-abdc-c0d1d7ce3c01 | ---------------------------------
| note | 346e41b4-7726-448f-a295-523a59d0bcc5 | VERIFYING DOCUMENTS: This ITP
| textbox | 1e9c50c7-ffd0-4792-b441-51376a49ebe7 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | d896ee54-cba6-45da-a02c-a1333a4349ee | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 04a8c85a-1a11-4bd6-a85c-e1f721aebaa3 | Name:
| textbox | 2f51d681-8707-4c71-9f17-60935bf9e689 | Position:
| textbox | 50c4749e-d7c9-45a1-accf-842b6fdf5f67 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Precast Retaining Wall &/or Architectural Panels (Supply & Installation) Rev 0 | itp | ITP-STR-Precast Retaining Wall &/or Architectural Panels (Supply & Installation) Rev 0 | c49e840d-40c5-406e-9e99-011192b2afd9
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | ab436776-0af4-44f4-a2f1-7945ffc4cb5a | Document Title: ITP-STR Precast Retaining Wall &/or Architectural Panels (Supply & Installation)
| note | db1fc482-72ac-4b79-b820-50397385ac1c | ITP Description: Precast Retaining Wall &/or Architectural Panels (Supply & Installation)
| note | fe65410b-7be2-4313-bd93-66a8048bb0f9 | Discipline (e.g. CIV/STR/RAIL): STR
| note | 2d795fde-1ffb-4b77-9c62-21ab8ed8a4ba | Revision Number: 0
| note | 1236a960-1f6c-4615-85aa-aeb931a67e59 | Revision Date: 17/05/21
| note | 38404bcc-2797-4902-80eb-11d2f1b07220 | ITP created by: Mike Freeman
| note | 297de441-4e27-41b8-9a9b-84937a37cd8d | ITP approved for use by: Mike Freeman
| note | c865a67f-2335-4a9e-b9aa-acd3bf08b613 | 1.1 VicRoads Section 610 November 2018
| note | 9113a3b8-6c61-4870-9bc7-a1c4c7b3182c | 1.2 VicRoads Section 610 June 2019
| note | b82d2a61-91f4-49e9-8551-593d79c1c97f | 1.3 VicRoads Section 620 May 2009
| note | 4f0ab1da-5143-4e11-bcfb-49336dc5ad8b | 1.4 VicRoads Section 630 October 2013
| section |  | Preliminaries
| checkpoint |  | 2.1 Precast Elements
| note | 37ad8f2e-e078-4ed4-9387-6a2689d1884e | REFERENCE: IFC Drawings
| note | 2af46d61-eff0-424c-951a-7b681de3caa3 | 610.46 (a), Table 610.463
| note | 0a8ea8e7-b63f-4dd3-80ef-411823fe6129 | (November 2018)
| note | d31daef7-0936-4cb0-90c9-4793c94b201a | 610.47 (a), Table 610.473
| note | b95fb8ba-cb50-4353-8cbf-1614f3a48fe6 | (March/June 2019)
| note | cc0c60f5-bdd8-4cc0-9504-247027b8125c | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
| note | fe8c1899-9e91-4ac6-a72f-b75ed3135bdc | i. Certificate of Compliance / Birth Certificate
| note | 2da0dc1d-a407-4cfd-819f-77b08c70937b | ii. Compressive strength test results
| note | 148f80f3-506e-47fe-9801-f4fd31b95192 | iii. Precast Lifting Design
| note | d15ca526-04aa-4a1b-94fa-e78b56fe6288 | iv. Pre-pour check sheet / ITP
| note | f928df53-f3d1-4550-9ca3-77f50724e4c2 | v. Post-pour check sheet / ITP
| note | 65452a84-e287-4a01-b654-f6bd90598ffe | vi. Covermeter check record
| note | 9f5f0229-04b6-40d9-86d5-ba0cb336e5ac | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
| note | 3f3311a9-4db2-4b6c-9146-20d8f290be6b | Note: Different revisions of 610 have different clause numbers
| note | 7b072dbc-78cf-401b-923b-6b0813def773 | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | abdfad39-8b83-4e81-ba3a-d3106f0ed814 | METHOD: Document Review
| note | 1795034a-3518-4346-b512-429fe0c89943 | FREQUENCY: Each element
| note | 58a511b4-28ab-412b-980e-6bf4e0b8d3b7 | CATEGORY: IP
| note | d8ca013f-b0ac-4271-bfa1-949b214c9c61 | RESPONSIBILITY: PE/SE/SPE
| note | 3fa8eeed-b164-4300-9516-17426f4a0916 | VERIFYING DOCUMENTS: This ITP
| textbox | ecdfba2c-18fb-4366-8ac4-5c1526a5fbb7 | Date Completed:
| checkpoint |  | 2.2 Joint Sealant
| note | 2c477879-6128-4a98-aa9f-0409243db27d | REFERENCE: MRPA Quality Management Plan
| note | 875506dc-4330-46f5-8327-233b21fb08b0 | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
| textbox | ebb645c4-d0d1-43b1-a4ef-112cfc3e88b1 | Enter: Teambinder Material Approval number
| note | 15af57a3-1602-4def-a313-3c4bac94556f | METHOD: Document Review
| note | c505e0e2-0a62-4787-8ebb-3e8ada96617d | FREQUENCY: Once, for each product
| note | c873f0c0-4388-49c9-bb19-e04623e78bb0 | CATEGORY: IP
| note | 11db6580-c045-45c1-8165-d8e5cf37357f | RESPONSIBILITY: Nominated Authority
| note | c11ff783-a182-4587-b30a-12dbe2bfe5e4 | VERIFYING DOCUMENTS: This ITP
| textbox | ab56ba16-dd88-4135-85d7-7a1ba143587e | Date Completed:
| checkpoint |  | 2.3 Foundation Concrete Compressive Strength
| note | 95743a71-9501-418f-94ec-872896b68675 | REFERENCE: IFC Drawings
| note | 8363ce26-a94e-4953-85a9-1d035350d827 | Temporary Works Design
| note | 48f8d544-f05e-41a4-8a3c-1df9c0b1d4a2 | ACCEPTANCE CRITERIA: Check that the strip pad, strip footing or post hole compressive strength as shown on the Temporary Works Design or IFC Drawings has been achieved.
| note | 441c553a-8533-43c6-80b9-d1f1cb20240d | METHOD: Document Review
| note | fd7d4841-ec52-480a-8ff4-4655dd934512 | FREQUENCY: Each installation location
| note | f2cd830a-c5da-45d7-b128-f47ccfdd049b | CATEGORY: IP
| note | 9f815e92-8a38-41a8-a676-5114fbbe2a93 | RESPONSIBILITY: SE/PE/SPE
| note | e83ec123-91ed-419d-b8b8-4018fe607005 | VERIFYING DOCUMENTS: This ITP
| textbox | 22dba871-cbee-4882-8a28-28722afccba1 | Date Completed:
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out of Precast Elements
| note | a9f28b59-1451-4691-8f4f-be18e6c58161 | REFERENCE: IFC Drawings
| note | 4cd7f92c-a232-4c7e-a6ee-fe62df08e178 | 610.46 (a), Table 610.462
| note | 984d19ef-7084-4758-b731-ab3bc6acfc44 | (November 2018)
| note | bf4644ca-2d05-488f-b342-4a17c8e2cbc3 | 610.47 (a), Table 610.472
| note | 55d1d677-8f3f-4cdc-a0bb-9dc446e9137a | (March/June 2019)
| note | 2a4bbc9c-e5f7-418a-bc3a-6d9ca9537b08 | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
| note | a4e9f0a8-0633-4fb4-a363-2cbec79bded6 | Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
| note | 16b855cb-0979-403d-abc9-9877cdf8cfd3 | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
| note | 0dd242ed-86a2-4962-b1c1-bc3a7e0e2d8c | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
| note | 59943a1d-9cf0-4e3d-a320-2f81b6ca92ea | METHOD: Measure , Visual
| note | 79283429-c253-4e1c-857e-6415180ff466 | FREQUENCY: Each element
| note | 3250133b-6a82-496a-911a-588fc26f8da8 | CATEGORY: IP
| note | 2444731c-786e-4188-b3a6-5f50bd7c401c | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | c6056e44-dec8-4e88-912b-c0ff8bbf4458 | VERIFYING DOCUMENTS: This ITP
| textbox | 3cedf09b-7706-45de-a731-fd239740ae11 | Date Completed:
| checkpoint |  | 3.2 Bearing Shims or Bearing Strip Placement
| note | 2dc4777f-0a92-47c1-92b4-a7c282d79a92 | REFERENCE: IFC Drawings
| note | 78b09c04-b550-473d-9399-476fbbefb635 | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
| note | 50b8ddba-1e1b-4801-b536-161ff701a09f | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
| note | 51a5217f-63c4-4cc8-969d-368b61098040 | METHOD: Measure , Visual
| note | 18741869-7016-4f01-a6ec-55715efd730f | FREQUENCY: Where applicable, each installation location
| note | 1c3b612c-b0da-49bb-ac73-59740df8001d | CATEGORY: IP
| note | 55ea403a-4afc-4e0c-b402-f164cd6186d0 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 6b1c8518-6de5-41a2-8636-2bde5701cd25 | VERIFYING DOCUMENTS: This ITP
| textbox | a7c4c61b-9d56-487b-aee4-979164f07a45 | Date Completed:
| checkpoint |  | 3.3 Materials Inspection Checklist
| note | 2544f5c1-5265-456e-b640-6e3b89c50920 | REFERENCE: 620.06
| note | da4fed6f-37f8-4ae3-8c14-0df932c216fc | 620.07
| note | 52c10d52-ff89-4ad8-976c-d0b2a55abef3 | MRPA Quality Management Plan
| note | 7bf6ffac-37b7-4bcb-956f-fe0c279846e1 | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
| note | 0552fbfd-fc68-44e9-a4e4-836c37ed94e2 | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
| note | 24f344a3-20b5-49a2-b45e-96581b9dc048 | Elements shall have unique identification and orientation marked (if applicable).
| note | 27c56e9f-157e-44a7-ace1-c6bc41f631c7 | Complete: Materials Inspection Checklist in ConQA
| note | 10efd20a-b35e-464d-9cfb-c27029443178 | METHOD: Measure , Visual
| note | 62a4d486-b7ae-4c5d-ad00-35563d18dee8 | FREQUENCY: Each element
| note | ab9e8d9c-4153-4bbd-908b-688b613ae431 | CATEGORY: IP
| note | 46c0a81b-a2eb-4caf-8cd5-88e7473c6af2 | RESPONSIBILITY: SE/PE/SPE
| note | 05ceb81b-0d0e-4342-a3d3-a3db804938eb | VERIFYING DOCUMENTS: This ITP
| textbox | 362cfaa9-20ea-45b7-af1b-801533f8274a | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 4.1 Precast Handling
| note | 58377d5e-dc01-4ff5-8a62-c07cd7ef4f9a | REFERENCE: 620.07
| note | d9bc5419-79e3-4e7b-bff3-dfa607f553c9 | Crane Lift Study
| note | 1e93dbdc-d6f4-4507-8b1c-c3fd6ab818f1 | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
| note | 373088ea-f27d-4371-87b2-2e337adf85f7 | METHOD: Visual
| note | 5c7344fb-aaab-4942-93bb-170eeecf7df6 | FREQUENCY: Each element
| note | b81cffc2-ea82-498b-94e4-4e3e4f7391ac | CATEGORY: IP
| note | 5b2b71a5-36d4-4e02-88d0-6da977635b3f | RESPONSIBILITY: SE/PE/SPE
| note | 0a170c07-28b4-451d-98dc-f9b0864bee5d | VERIFYING DOCUMENTS: This ITP
| textbox | 284a3d43-ed85-447b-b83c-4d7487942814 | Date Completed:
| checkpoint |  | 4.2 Precast Placement
| note | 75762cf5-99e6-4160-953c-c466c92890c8 | REFERENCE: IFC Drawings
| note | 2be4b610-f514-4ce2-8fdb-f63ef0fd035f | Temporary Works Design
| note | b940fdec-5137-401d-b089-2aaa0ae84a02 | 610.27
| note | a689b8aa-bdb2-4440-94e4-f9369ba390fa | ACCEPTANCE CRITERIA: Precast elements shall be placed into location or and not released from the crane until sufficiently braced, wedged or restrained by bolted connection, in accordance with the approved Temporary Works Design and/or IFC drawings.
| note | b99a28f1-7005-41a5-bb3e-59a37ef78672 | Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
| note | 94f6282d-25a1-46d9-aab7-56f6eb979163 | The nominal gap between elements is as per the IFC Drawings.
| note | 40b6a88c-7a64-4bf7-b47f-a888ffaac761 | METHOD: Measure , Visual
| note | d37c2373-ee5f-4e5f-8e33-4fc4e5826492 | FREQUENCY: Each element
| note | a2690dea-d610-427b-a45c-0ae2cb332b2b | CATEGORY: IP
| note | 75b6476e-6ff7-4105-8b57-8010b38aee05 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 14e9536e-7d8b-4be6-941c-f280bc3030cc | VERIFYING DOCUMENTS: This ITP
| textbox | c7d52025-c424-4a2c-a151-00ef89bb7e1c | Date Completed:
| checkpoint |  | 4.3 Waterstop Seals, Compressible Seals & Isolation Joints
| note | 76df939c-326c-409c-906c-35c37583cc0f | REFERENCE: IFC Drawings
| note | 39b4fd98-0b50-46cc-8712-9ad5705c9a17 | Product TDS
| note | 5c16de3e-d5b4-42ac-899b-e6e698ff2e33 | ACCEPTANCE CRITERIA: Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
| note | 1dbefda1-987f-411b-8d24-ee076878c407 | Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings.
| note | f260e124-2054-465c-888e-cfa1513f2523 | METHOD: Measure , Visual
| note | 645fa5dd-8305-4563-9a07-ec969b97e095 | FREQUENCY: Where applicable, each installation location
| note | b791695a-9675-4407-8c17-a4794aacf7cb | CATEGORY: IP
| note | 09a106cb-6e1f-48db-ab56-a438582ee740 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | cb419c62-a807-46da-9719-40548a56c5c7 | VERIFYING DOCUMENTS: This ITP
| textbox | fdfe6457-2ea5-43bf-bd5d-b25811c89246 | Date Completed:
| checkpoint |  | 4.4 Subsurface Drainage
| note | e957a144-5669-4d46-9c17-f735daf1c104 | REFERENCE: IFC Drawings
| note | 5343a765-ea31-40d9-80a8-a75958974ad4 | 702.03
| note | 256f295e-93dd-41f7-b96b-3658bac9a50d | 702.06
| note | 2093889b-182a-4512-9f91-161c635bd53c | 702.07
| note | 1abcf9a3-871d-4939-a4a5-25c232ab3b67 | 702.09 (f)
| note | a6523a6e-4449-4988-b18f-ac16af10567c | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
| note | fa42ac6f-443d-4770-bb8d-bda1fa6455b2 | The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings.
| note | d0f85196-6ca0-417a-878b-89227deca6d3 | Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
| note | f5995131-2bbc-4535-a41a-d0ae4f26680c | Weep holes shall be checked for obstructions.
| note | 8671c066-f230-44c2-80c0-8a80fb969918 | METHOD: Measure , Visual
| note | bcb92cc3-afe0-46e5-a185-59a95290f856 | FREQUENCY: Where applicable, each installation location
| note | e1eb52ff-7b4b-477d-8c98-b731810a464b | CATEGORY: IP
| note | 7043f277-53f0-401b-b4b9-896fb4bfdf15 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 6fee2287-e7e7-4d11-9d89-fd7efe07cbaa | VERIFYING DOCUMENTS: This ITP
| textbox | fc62dca5-9ae4-402c-be0f-34c1879abe9f | Date Completed:
| checkpoint |  | 4.5 Connection Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
| note | 836f6707-7ed2-40e9-9d68-6e83f189defa | REFERENCE: IFC Drawings
| note | 4c445415-f50c-423b-9308-bc7e050ac4dd | AS5131 Clause 8.3
| note | d22c0b6d-a599-46cb-81a5-fce4f04bdcc2 | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
| note | 33ac55ae-6bed-492d-8bf4-57be501cdc13 | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
| note | 92e3163f-4ad3-48e6-8c25-7a28699cc8c3 | Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
| note | 71bdacc3-6eb5-45b2-a48d-d6274bfc70b7 | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | f070061c-d0bf-4901-a37b-9a55bfede484 | METHOD: Visual
| note | 32266bf3-299b-4a3a-bf57-30f70bc08bd3 | FREQUENCY: Where applicable, each bolted connection
| note | 9cb7bf32-7ba2-4e55-9353-c11cb13303c3 | CATEGORY: IP
| note | 8c202596-3cda-42dc-8df6-4177fc3252ba | RESPONSIBILITY: SE/PE/SPE
| note | d30bb5c8-ac42-48c2-9741-ec6ac09f3d37 | VERIFYING DOCUMENTS: This ITP
| textbox | 0b4056cf-3c71-40bb-a370-f7083060f224 | Date Completed:
| checkpoint |  | 4.6 Precast Traceability
| note | f0acf8cd-7832-46e1-a848-30802f2e9744 | REFERENCE: 620.09
| note | 5c99101d-c8c9-4b9c-8674-72322305a34e | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
| note | 1e2dc898-d383-4d00-9b7a-bbe85bb00219 | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
| note | e9955b7a-e38d-45fd-bea9-26a406882046 | METHOD: Visual
| note | 4f8f6b69-defd-4358-8aeb-a57b4004b97a | FREQUENCY: Each element
| note | d0740e32-12ff-4739-bc44-b5016c7e057f | CATEGORY: IP
| note | 79144f68-89cc-4117-a9ed-be008c6b176c | RESPONSIBILITY: SE/PE/SPE
| note | d601e267-04dd-41a6-8995-7977e31bb664 | VERIFYING DOCUMENTS: This ITP
| textbox | 2321de1f-26bb-4972-9d55-15f6003cac17 | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 5.1 Joint Sealant Application
| note | 06455960-8b06-4cec-a217-a0eec6e60909 | REFERENCE: IFC Drawings
| note | 9b6c20a5-4048-4c5c-86be-47bca616fda5 | ACCEPTANCE CRITERIA: The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
| note | 37f07066-8e1d-4a10-a997-908bf421fdd7 | METHOD: Visual
| note | eaa6e5a5-2eb9-424d-b437-f5ad0a200642 | FREQUENCY: Where applicable, each element
| note | 2d3b5c49-60fd-40b7-9a8c-79fb1bf997d8 | CATEGORY: IP
| note | ce8ec1c0-c149-4ca2-9488-3732f53e4348 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 778774ef-fd9b-4ef0-aeb5-7658774dd46f | VERIFYING DOCUMENTS: This ITP
| textbox | 818d5fd3-b086-4b3b-ae86-b511ec5dc1f3 | Date Completed:
| checkpoint |  | 5.2 Flowable Grout Pour
| note | dd76d734-8730-45a3-9e25-35ac1ff672e2 | REFERENCE: IFC Drawings
| note | a769c43e-d7f4-47b1-870a-e9e83f9ca6cd | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the foundation following full sealant application.
| note | ed61ccb8-6cfb-4a26-b7e6-c6243c0f188f | Complete: Grout Pedestals & Bearings ITP
| note | 83cbaaa5-35bb-4210-823c-6601d81c4c80 | METHOD: Visual
| note | 14e450e4-935d-4b47-8e0d-5b1dbd795e3c | FREQUENCY: Where applicable, each element
| note | d63dd605-1c1d-456a-b692-af42b4013732 | CATEGORY: IP
| note | 5b54a946-273a-4b19-b9c3-bdda35207faf | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | fe818544-abb6-4fa7-8aae-0b879675f27b | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
| textbox | 537e2ce0-99cc-435d-8ad9-0473b4341429 | Date Completed:
| checkpoint |  | 5.3 Backfilling
| note | 1a34bc3b-a070-422b-8e10-ee7ab1e50a8c | REFERENCE: IFC Drawings
| note | 2f9cbca9-8aae-4fac-971c-d1717ff9951c | ACCEPTANCE CRITERIA: Backfilling materials and compaction shall be the type and layer depth shown on the IFC Drawings.
| note | 0251437c-6977-4432-a867-abea87279f45 | Complete: Subsurface Drainage (Supply & Installation) ITP
| note | b2b88c73-43f8-4c5e-9d10-f44bc757fd89 | METHOD: Visual
| note | e643d989-7958-467c-8669-9f4c8ce55bfa | FREQUENCY: Where applicable, each element
| note | 69b0c805-e48a-440f-9fd0-77d9d812153c | CATEGORY: IP
| note | 49eae735-d614-4128-ac23-a81e8c327d4e | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 6be2913e-62b9-4e14-8d19-630d649065a7 | VERIFYING DOCUMENTS: Subsurface Drainage (Supply & Installation) ITP
| textbox | 1fb22962-08f5-4300-8513-492a25ae9988 | Date Completed:
| checkpoint |  | 5.4 As-built Survey
| note | ee25bc72-2561-4563-87e8-ee34c01bee01 | REFERENCE: IFC Drawings
| note | cb24c207-d26f-4eae-8e18-bc777dca6135 | 610.46 (a), Table 610.462
| note | 40031ff5-05a8-44e5-aeda-13368a9ad72d | (November 2018)
| note | 68833ebd-b9f8-490b-ba7f-c4f485b13de0 | 610.47 (a), Table 610.472
| note | 6a4775cc-fec5-4615-85f9-57e1f382ee16 | (March/June 2019)
| note | 429fee73-cf02-45c5-8243-b4e6fc005376 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
| note | c33a77d6-c4aa-4c5a-8a30-07dd7732bad1 | Attach: Survey As-builts / Survey Report
| note | 5216f382-699f-4d1c-b946-0afa0c5fa349 | METHOD: Document Review
| note | efff3fb7-4e2f-413b-82e8-851f1d01b8e5 | FREQUENCY: Each element
| note | e768a244-9270-41e0-901a-0ab9099e54d7 | CATEGORY: IP
| note | 98e1b6a6-2027-4d94-938e-6e6b381e94d3 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 2c1cb16b-b4c3-4cf0-bc56-498e917ce994 | VERIFYING DOCUMENTS: This ITP
| textbox | abf7b47f-813a-4202-9b8b-cfe2a83bbc55 | Date Completed:
| checkpoint |  | 5.5 Non-conformance Report (NCR) Closure
| note | 13f99117-8368-47d8-a59a-649a3abe7c50 | REFERENCE: MRPA Quality Management Plan
| note | 7c4cc8f4-b586-44cd-8cca-3a29a1ebc13c | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | e7f4dea4-db17-4982-875f-aae96e9d40fc | METHOD: Document Review
| note | fb3340aa-0789-4e54-9bc5-72fe432842c1 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 3caf00f7-17fe-42c3-b6d1-7a3158c4c3ef | CATEGORY: HP*
| note | 3412b306-fe71-4237-9f72-cf986b64753d | RESPONSIBILITY: SE/PE/SPE
| note | bf267a41-38ba-4782-8f4d-2b63b1dfb9f1 | VERIFYING DOCUMENTS: This ITP
| textbox | 2f84147b-03c3-4893-8190-ea32f0307126 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 6c8ba6c0-3fb2-4388-ac80-058c4f0150a9 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 2da25a10-abc1-4d2e-af56-224a3c69101e | Name:
| textbox | 0f49156e-a3bb-4e34-8ac9-bc0370f044e0 | Position:
| textbox | 423b4649-0aae-4440-b21d-a882d6b76172 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-RAIL-Track Removal & Construction Rev 0 | itp | ITP-RAIL-Track Removal & Construction Rev 0 | c723d07c-646b-40d5-b280-57f94c3a35cd
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 5b053327-be3c-4d0f-b725-f74a5f1e52b2 | Document Title: ITP-Rail-Track Removal & Construction
| note | f17d5362-99bc-4020-a998-9b167d081eef | ITP Description: Track Removal & Construction
| note | 12908a13-3077-4c38-86ea-a1fa3c93cc75 | Document Number (in Teambinder): MRP-0000-MRPA-CLD-ITP-00
| note | bcf7660e-cf1e-417f-8cdc-a7b228d95d2e | Discipline (e.g. CIV/STR/RAIL): Rail
| note | 2950d653-6879-424e-b91c-bf3f0227f0a8 | Revision Number: 0
| note | af659f3c-f505-4649-964c-b55f9f58f77e | Revision Date: 15/02/21
| note | 5515a12b-3bc3-4b05-a567-ad95cbe4aa47 | ITP created by: James Porteous
| note | 95ad2880-9f53-4853-bfb1-d90afafcbb2e | ITP approved for use by: Romualdo Magpantay
| note | 91dd4b82-b982-4597-a242-234f986acf53 | 1.01 L1-CHE-SPE-316 Concrete Sleepers
| note | ff475a91-1b4c-4b91-9ee4-d002f37a1799 | 1.02 AS 1085.1 Railway Track Materials – Part 1: Steel Rails
| note | c3fbea2b-a447-4ac6-937b-7507c6f469b6 | 1.03 L1-CHE-SPE-003 Heavy Rail Construction Tolerances
| note | 410b0311-dd87-4a42-99a2-59be97d3bb56 | 1.04 L1-CHE-SPE-064 Ballast Supply
| note | 49632316-de04-46cb-9af8-65a64ed5b7cc | 1.05 L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | 11634d8f-7298-49e5-a30e-e3aaaf644e70 | 1.06 PTC Heavy Rail Track Construction Standards Drawing F598
| note | 3e3692cb-f6f9-4975-90b8-86a7b9f14729 | 1.07 AS 1085.20 Welding Rail Steels
| note | 32a6120b-bdec-4082-aaeb-cce6985c33ed | 1.08 Clyde Road Package 29 Design Drawings
| note | 06de04d1-0461-4041-972a-748197ecc034 | 1.09 L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan
| note | a0a96441-970f-44b8-907c-63b5d04433b6 | 1.10 L2-TRK-PRO-028 Requirements for Welding Track
| note | d546afd6-6c93-4d16-bb1a-25eb29687b75 | 1.11 L4-TRK-FOR-074(2) New Weld Return Form
| note | 9058e33c-2576-4e3c-bd40-40c64ce157d3 | 1.12 Welded Track Management Chapters 1-16
| section |  | Preliminaries
| checkpoint |  | 2.01 Obtain and submit Material Certificate of Compliance for Track Materials: Track Rail, Track Sleepers, Track Jewellery, Geofabric, Ballast 60mm Aggregate, Welding Kits, Welding Crucibles
| note | d61860c5-3289-48c0-bceb-0c23516593d7 | REFERENCE: Units to be free from damage, total and types of units for full set validated No signs of discoloration
| note | 81b97b1d-a89d-4340-b0a5-d0a05fe80d30 | Attach: Manufacturer Certificates of Compliance
| note | e7253771-6430-41e8-ab88-28767ff37632 | ACCEPTANCE CRITERIA: Attach:
| note | f13400f7-3b40-4339-8bb5-c104c8782123 | Track Geometry Conformance Certificate
| note | e47734e1-86cd-4589-99d0-d9c77f770bf7 | Track System and Component
| note | f86d71de-716e-4b47-bd67-7eecd7296456 | Attach Site Photos:
| note | 0b293d81-6f63-4438-bb9c-c87ce79d193a | Before/After Photo of worksite
| note | cbd83430-05b8-4d41-85e1-0cb7c8240a61 | METHOD: Review, Document
| note | f8e9a157-ec70-4842-91bc-419b0323d6f0 | FREQUENCY: Once
| note | 61438082-3f77-4e15-9cb2-719aed2ba922 | CATEGORY: HP
| note | 8220bff9-bd3d-47f8-a934-26c6e95f52ff | RESPONSIBILITY: Track Supervisor , Project Engineer
| note | 79bd3d57-14e5-48a3-9ba0-cbc4c028cda2 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c5565c9c-11d1-4434-9221-7d5611ba9907 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.02 Submit Welding Procedure/welding qualification welders Record
| note | 092bc665-644c-430f-a35f-ac0106efe757 | REFERENCE: L2-TRK-PRO-014 Welded Track
| note | 5aefa641-ea0d-4dcc-a4d2-afe221040df9 | AS 1085.20 Welding Rail Steels
| note | aa555e39-ecd2-444c-90f8-dea3af126917 | ACCEPTANCE CRITERIA: Qualified personnel & welding accordance with manufacturers specs.
| note | 129d7269-7d78-4893-a9b9-b139d990c383 | METHOD: Review, Document
| note | e3de9d1b-5891-42d8-9997-4b20e55b577c | FREQUENCY: Once
| note | 0fa854b1-6be8-47d2-891d-d3341d2c3371 | CATEGORY: HP
| note | d5611385-506d-4049-93b2-598cd8c26960 | RESPONSIBILITY: Track Supervisor , Project Engineer
| note | 09465299-d999-41a9-b403-fb0960bdaca9 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ca5d7e5c-c1f5-4b5b-b8a2-e1e1d6944ace | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.03 Inspect supplied items upon delivery
| note | 6c2340a7-b586-49d3-88b8-ab2c1cf9dbcf | REFERENCE: IFC Drawing
| note | 753b7a3f-8da7-47db-ab65-0ca04bf13d71 | ACCEPTANCE CRITERIA: No damage or rust on components
| note | c98a3e81-724e-4bdb-b45f-4609cf50b62e | Validate total number and type of components matches drawing
| note | 9c5495b2-db51-4080-bdfc-d793aa48532f | Attach: Photos on site;
| note | 52152902-d14e-440a-8ce4-f17acb796ccb | Track Rail
| note | b632a778-615a-46f1-807e-4be2952dc9df | Track Sleepers
| note | e8822232-acde-4ec7-a3c4-4905caa22be2 | Track Jewellery
| note | 987cbc7c-84d4-4b36-baab-94b26b7d2fcd | Geofabric
| note | 8c689c6f-e564-44bc-8f00-07de46c8ecaa | Ballast 60mm Aggregate
| note | 219c4523-820a-4b30-ad93-c266cd9bec76 | Welding Kits
| note | 6029c868-7a71-4d63-80d8-ccadedc5df99 | Welding Crucibles
| note | 045327d8-0648-4858-9870-871d1646124c | METHOD: Visual, Measure
| note | 0c89e869-5a53-4c85-b5c8-ecce1c57e2e1 | FREQUENCY: Per delivery
| note | cfdaf278-506a-434c-85b3-af8c3fb60bdc | CATEGORY: IP
| note | 994ea362-5b0e-4918-9f35-ae6ae804eafc | RESPONSIBILITY: Track Supervisor , Project Engineer
| note | 6f8ce056-5912-4db6-afcd-ecd452600a34 | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | be2feea3-fa41-4188-94bd-4c1e2b1595f3 | Date Completed:
| checkpoint |  | 2.04 Confirm extent of track removal required for piling & civil works
| note | 05da6729-27d5-4e93-a01a-cd6ed0a23f8d | REFERENCE: IFC Drawing
| note | e5b1f08d-2b2c-4b09-8ded-be43683a827e | Track Construction Site Mudmap
| note | 7f26d8d9-49d4-4815-851f-fc4a9abccdf2 | ACCEPTANCE CRITERIA: Extent of removal to be confirmed with MRPA civil team, limits of removal to be marked up on site
| note | a4168520-93c4-43e8-af41-e2b175480b32 | Pre-removal survey of existing track alignment
| note | 714acfd9-81e0-47da-b6fa-b111c06a0d3a | METHOD: Visual, Measure
| note | 8961751f-4afe-4592-898d-357bb27e1fb1 | FREQUENCY: Once
| note | 6c30a205-2a87-4e45-babd-8f158a1ced43 | CATEGORY: IP
| note | 7dfafe37-bb76-4ea7-8bdc-53f1734a3717 | RESPONSIBILITY: Track Surveyor , Track Supervisor , Site/Project Engineer
| note | b29ab0dc-87fa-4525-9904-375af7728565 | VERIFYING DOCUMENTS: This ITP
| textbox | 814c87ac-cc0f-4bdf-9419-de371d447811 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.01 Deconstruct and remove track components, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
| note | 0ba9846c-b947-48ec-aac4-1c04d2b40b98 | REFERENCE: IFC Drawing
| note | d7f818d9-8b94-44bc-92d9-78563d584467 | Track Construction Site Mudmap
| note | 3fcbaeab-2e20-410f-92ea-442542dba03c | ACCEPTANCE CRITERIA: Track structure to be removed to the designated limits as identified.
| note | ed3f3a94-0844-45fe-bf03-251ffc6dbe74 | Visual confirmation of removal on site
| note | a64ede6c-bdfa-4792-abb9-75315f6e579e | METHOD: Visual, Measure
| note | fd7ca96f-ff3a-4b3a-86e8-2ea3b14168ae | FREQUENCY: Once
| note | 27399f11-6f0d-4017-a021-78733d09fcc3 | CATEGORY: IP
| note | 668788ff-bb17-407b-bb82-3a986d183e96 | RESPONSIBILITY: Track Surveyor , Track Supervisor , Site/Project Engineer
| note | 8c7fd5c9-4a1b-427e-84d1-45d63fa2338c | VERIFYING DOCUMENTS: This ITP
| textbox | 8b4cac34-53bc-45b0-a6c2-40b8f45416f6 | Date Completed:
| checkpoint |  | 3.02 Earthworks completed and site handed over from Civil Contractor
| note | 8449fd54-6500-460e-bb5f-3a72fc71e34a | REFERENCE: L1-CHE-SPE-178 Engineering Specification Earthworks & Formation Specification
| note | d7702b58-09b5-4846-b1b5-7d4d110dd944 | Design Drawing
| note | 6dd3a97b-0c0e-48dc-9778-260fe4fb5d96 | MRP-056-C-AUR-DRG-70-LBK-CPW-0011
| note | 83fa2ca5-7196-4f0b-9524-908a320c5c50 | ACCEPTANCE CRITERIA: Confirmation of completion of underlying ITP(s)
| textbox | 31d693a8-aa01-4180-ab83-9b70d5bc5749 | Underlying ITP reference:
| note | f242d45a-23f1-441b-b127-be21f0f6f848 | METHOD: Visual, Measure
| note | 564bcca8-e01b-49b1-b075-7273974c0e06 | FREQUENCY: Once
| note | 7d04b0ba-4bce-45f5-846e-0be2080cad7d | CATEGORY: IP
| note | 3a53dbe4-b6f2-466f-bb45-aa806ce3ff38 | RESPONSIBILITY: Track Surveyor , Track Supervisor , Site/Project Engineer
| note | 6041076b-da04-4c07-a2bf-cbeca6a12d39 | VERIFYING DOCUMENTS: This ITP
| textbox | ee1b9b5b-f6f3-4a0f-b685-32fe203b749f | Date Completed:
| checkpoint |  | 3.03 Installation of Bottom Ballast
| note | 4a138a1c-47c2-4351-b429-0858b273f4e3 | REFERENCE: Design Drawing
| note | 88815c72-e645-4fb9-91fe-512ac15e8e76 | MRP-016-C-ACD-DRG-03-NWA-CPW-3011
| note | 5bdfc5fb-6c29-4f5c-b440-509e91ec184a | MRP-016-C-ACD-DRG-03-NWA-CPW-3012
| note | 2f0b843f-49c6-474e-bba4-95b47dae5e84 | PTC Heavy Rail Track Construction Standards Drawing F598
| note | 06a0fe57-00fe-43c0-8e48-45b0c9f80f62 | ACCEPTANCE CRITERIA: Overall Minimum 300mm bottom ballast depth
| note | ff491776-8aa2-4f83-86e4-348b3e39ae01 | Ballast to be placed in 150mm max layers.
| note | ecc065db-0618-4371-959e-f685d7aab9c7 | Bottom Ballast to be left 20mm below final design level – Tolerance (under sleeper) -0mm, +25mm.
| note | d17872c2-ac2a-468a-970e-c432ea3253ba | Layers rolled 10 tonne smooth wheeled vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compacted using a vibratory compaction plate
| note | bb6e29be-4dfd-4934-a0d2-64cc4dcd4b38 | Attach: Survey Measurement
| note | 5c754bed-926a-4cee-929f-811806980278 | Attach Site Photo: Installed Bottom Ballast Layer
| note | 9e316df4-bec0-4916-9c40-549d78497b7a | METHOD: Visual, Measure
| note | 4096ad25-df53-4181-8c62-7cee19dbf707 | FREQUENCY: Once
| note | dcd95ee3-e833-4896-a21d-2b55d7c6c1b2 | CATEGORY: IP
| note | dc7bba7d-6867-4180-804c-cbfcb86a8c85 | RESPONSIBILITY: Track Surveyor , Track Supervisor , Site/Project Engineer
| note | 35e9dfdf-76a1-4ea3-b896-8a3ea2f5b9c5 | VERIFYING DOCUMENTS: This ITP
| textbox | ce45a3c1-d856-42e4-97e9-8e5a333f21f2 | Date Completed:
| checkpoint |  | 3.04 Laying of Sleepers
| note | f3652c5b-ccfe-43a8-ab2f-08252f4fd2ce | REFERENCE: Design Drawing
| note | e325d740-ff15-4069-b920-feb8cb1afe84 | MRP-016-C-ACD-DRG-03-NWA-CPW-3011
| note | 6426574a-3abe-41f5-922a-6cd885944a93 | MRP-016-C-ACD-DRG-03-NWA-CPW-3012
| note | ee5e0ce9-21f8-49a5-952e-f6ecff424611 | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | cc234432-1618-422c-80f3-9b7045d4c409 | ACCEPTANCE CRITERIA: Sleepers Square at nominal 685mm ±25mm for open track
| note | a07c6840-4827-4829-8e41-166dd0b13571 | Sleepers Square at nominal 600mm ±25mm through level crossing
| note | 0a34df7b-df71-4f3b-9577-875e73c75586 | Attach Site Photo:
| note | ac476ff8-49f9-41ec-904f-5469aebb8afa | Laid Sleepers
| note | 113dd43b-bb8d-450e-80ee-7d6fe0ef4878 | Sleeper Spacing Measurement
| note | 121b4f20-11b6-4e34-8b38-7b289915c1df | METHOD: Visual, Measure
| note | 49e4569e-cb4f-40ca-90e3-f7b0d9b53648 | FREQUENCY: Once
| note | dc35cc35-4fc5-4df6-853b-5aa3cde824c3 | CATEGORY: IP
| note | 3625b2cf-5919-4cd7-b6e7-21f8cbda9035 | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
| note | fe09f0cc-62ab-4144-b81d-25a4a81575d2 | VERIFYING DOCUMENTS: This ITP
| textbox | 93238da5-3aeb-4944-9972-1e85c5f35da4 | Date Completed:
| checkpoint |  | 3.05 Rail & Fastening Installation
| note | 83219f14-201b-4da8-aac4-b6a58540f861 | REFERENCE: Design Drawing
| note | 72f2a7dd-628b-46e5-90f9-8e3cc4ac080d | MRP-016-C-ACD-DRG-03-NWA-CPW-3011
| note | 4a34cc63-e81c-4740-8325-1e8bce87d4a3 | MRP-016-C-ACD-DRG-03-NWA-CPW-3012
| note | 28752e07-cb9d-45cc-a0dd-52105562b064 | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | 184fd493-629d-4b5d-99c7-65a8fb0ca4c4 | AS 1085.1 Railway Track Materials – Part 1: Steel Rails
| note | 86198220-26db-4919-bea6-107e7a75c1ed | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators
| note | 4db98463-7bbf-434a-9d5f-9f8e80225164 | All rail fastenings installed
| note | 17db26f3-6cbd-4176-a39d-b889cc070e1c | All Rail Ends, positioned midpoint of sleeper bays +-25mm
| note | fa4eb5a7-6146-4d57-97e1-1e090b956294 | New Rail lengths installed to be as per Clyde Road Track Mudmap Piling Occupation V8
| note | 70a46782-4aae-4179-a692-6d1dd8029326 | No Existing Welds Within 4m of new rail tie in point
| note | 5324be29-329d-4878-b4b0-9271ce8eedf4 | Attach Site Photo:
| note | f75cbe5d-61d3-416c-ad69-b91ee1c22d20 | Laid Rail
| note | f2839df9-7566-4da7-8711-93db648be5ce | Rail Joint to existing weld measurement
| note | 5bad4308-c440-4f90-97b8-75947c7766bf | Weld joint between sleeper bay measurements
| note | f0c2683e-ac73-4925-ba0d-fee46b2686e3 | METHOD: Visual, Measure
| note | 5bda05db-31ef-43af-bbe5-184d50aa56c7 | FREQUENCY: Once
| note | 4c8c7abe-2f96-4746-bcc7-fa8a2b5ee4f5 | CATEGORY: IP
| note | bcf0d7f6-2173-4b35-8387-0b565dc049b9 | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
| note | 1e4f1f2b-cd38-4969-a0a4-a6884049c284 | VERIFYING DOCUMENTS: This ITP
| textbox | 1ccb5e4f-8bf0-4b58-993d-4a93421fab86 | Date Completed:
| checkpoint |  | 3.06 Track Tamping
| note | aa6aee8e-4214-4ea8-938c-d361a7299c47 | REFERENCE: Track Tamping Design Drawings
| note | b0859c6f-8d3c-4100-bc5e-d372a42eaabd | MRP-016-C-ACD-DRG-03-NWA-CPW-3015
| note | ec5dba6b-f60a-4cd5-a618-4c492fa7f1e5 | MRP-016-C-ACD-DRG-03-NWA-CPW-3016
| note | a28120f6-b025-483b-a722-d3774e103b63 | L1-CHE-SPE-003(1) Heavy Rail Construction Tolerances Table 1
| note | d72aabea-3129-4fe0-a552-6b4638cb66d9 | ACCEPTANCE CRITERIA: Tamping Ensures Track Geometry Tolerances are not breached (dimensions are in mm);
| note | 27ae9716-4e28-4149-8738-00f5d2f52a47 | Gauge +3 / -3
| note | 1c7acc13-e0e3-4c6a-bee6-fa10d904be25 | Gauge Variation in 2m 4
| note | 9cc30355-f063-46e7-a15b-49406fa4f373 | Line (10m Chord) +4 / -4
| note | 5e73517f-a01b-4b41-85ad-3a2a6e8014dd | Twist (3.5m Chord) +2 / -2
| note | 911af163-c644-49f2-b398-6600325b682d | Top (10m Chord) +5 / -5
| note | 07992833-c517-4334-877b-a5c5adf713bc | Cant +5 / -5
| note | b8094bc3-a248-49c6-a993-8eb84aa2bbe6 | General Alignment +0/-20 of original alignment
| note | 9d3c7d5d-4d3c-415b-bc2a-a64ed010031a | Survey measurement of RL of top of rail head
| note | 1cffbc49-09b7-4725-8384-bcc2c67281f0 | A minimum horizontal clearance of 3.0m from track centreline to structure.
| note | 71355fef-d227-4312-87fd-e1bcda16228e | Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached (Covered in Overhead Wire Works ITP)
| note | 738a7908-9126-4d0f-9c44-8febff77caa7 | Attach;
| note | 0250a01c-76ce-4695-acbf-067579f4b992 | Tamping Geometry Recording
| note | 39f9c78b-929e-4472-8919-813ac7672405 | Survey RL measuring sheet
| note | b55e6da8-f14c-4012-b1a1-a9a3933a2b42 | Height and Stagger measuring sheet
| note | 2b079048-ec51-4c3b-a714-2e5db8ff0591 | Attach Site Photos:
| note | 9eb7e2e7-45a2-4d32-a1d3-484f5e7c9267 | Tamping Activity
| note | 92a592a2-1ccb-4b45-9ee8-d2303e08b3b8 | Overhead measuring Activity
| note | f9e11e0f-c361-49c5-a3a3-53d5f69f2b9a | Structural Offset Measurement
| note | e671c16a-460c-4259-b5b7-39370020cbc2 | METHOD: Visual, Measure
| note | c0e0393e-3551-4667-99cb-664489c0a2ed | FREQUENCY: Once
| note | 3be12bd9-6114-49fc-b161-b83b5a080d43 | CATEGORY: HP
| note | a7d370d3-f584-4394-aba8-e025f4ff0bfd | RESPONSIBILITY: Tamping Operator , Track Surveyor , Overhead Engineer , Track Supervisor , Site/Project Engineer
| note | 09141e61-ad74-4cbb-8323-e9cb43eaf218 | VERIFYING DOCUMENTS: This ITP
| textbox | dbfbc48f-ffaf-4d01-bfc9-4163bd78056e | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.07 Regulating and Ballast Profile
| note | 97ba4f05-d421-49c0-8727-08ae359153b3 | REFERENCE: Design Drawing
| note | 1aea775c-f6d1-41c2-9b86-2a6041930c16 | MRP-016-C-ACD-DRG-03-NWA-CPW-3011
| note | 462a7b3d-74b7-47fb-bd21-9242a9d72e7c | MRP-016-C-ACD-DRG-03-NWA-CPW-3012
| note | d7bb6f9e-f418-44e8-a354-10a6973f1fa2 | L1-CHE-STD-029 Earthworks and Formation Standard Section 13
| note | ee044dea-ce99-4c7b-9d9f-f382298eafb8 | PTC Heavy Rail Track Construction Standards Drawing F598
| note | fbdddda9-1cd3-472a-a871-468fd9815c9b | ACCEPTANCE CRITERIA: Ballast shoulder of 400mm width from outer edge of sleeper and with 1:5 angle of repose thereafter
| note | f46004dd-fa08-4266-9eee-8bd13073f91c | No Ballast to be on top surface of sleepers or around rail Fastenings
| note | f3970dd2-14cc-4c2c-9a66-e283beddf20c | Attach Site Photos:
| note | 5c9e6d5e-0455-497b-835e-2983fc4c602f | Ballast Shoulder Measurement
| note | bd57e83a-c62d-41f1-8f7a-70e3ed1e4798 | Rubber Panels free of ballast materials
| note | 2689f593-0a88-4e4b-ad9a-8728a3608c2b | METHOD: Visual, Measure
| note | 8707fe08-9e39-4b14-ae7e-885757fecb41 | FREQUENCY: Once
| note | 749027da-8a23-4b3d-ad87-1df1e0104e13 | CATEGORY: IP
| note | 2f59af58-449b-4324-8613-91b38bed7735 | RESPONSIBILITY: Regulator Operator , Works Supervisor , Site/Project Engineer
| note | a714d29d-b8d2-44c2-89f3-29af6828dc18 | VERIFYING DOCUMENTS: This ITP
| textbox | 0c5353ce-ec31-4c56-9f3f-c6eb8e7cc686 | Date Completed:
| checkpoint |  | 3.08 Aluminothermic Welding
| note | 645f311e-8daf-4410-a83f-b109b3ffbae9 | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
| note | c42094c2-cb4e-4873-87f8-027c4bbc7261 | L2-TRK-PRO-014 Welded Track Management Manual
| note | 0d9e5ad6-1bb7-4929-8292-5ccdaf9e2fbb | Chapter 11 – Rail Welding Process Section 4.9
| note | 08a33b0b-ad93-48cc-a19a-243c20a99bc5 | L4-TRK-FOR-074(2) New Weld Return Form
| note | 11b284eb-ede4-43bc-9aa9-3f78c7528f7c | ACCEPTANCE CRITERIA: Alignment inspection shall be carried out on each weld and record results.
| note | 58094594-5358-4771-a482-af935c106b20 | Horizontal Alignment ± 0.5mm
| note | b835507c-bd33-473f-b843-f5b26005f983 | Vertical Alignment + 0.5mm, - 0.0mm
| note | dbeaa2cc-e737-43cc-9b36-519cf0f45618 | Verify Aluminothermic welding carried out in accordance with AS1085.20
| note | 165f3362-696a-4d55-a6c8-15a06673eb64 | MTM New Weld Return Form Welding Section Completed
| note | e2fe5717-aec4-4e55-a7f5-415f4fbde772 | Attach: New Weld Return Form (Weld Section only complete)
| note | 657a8cc6-fecd-48c8-9f9f-4d0860ebdb0b | Attach Site Photos: Welding Aligning, Welding Process
| note | 1e69a984-5a47-4d83-b1e7-7f1012faa66e | METHOD: Visual, Measure
| note | 4666c409-63fd-45ab-b837-5d02c7b5e451 | FREQUENCY: Each Weld
| note | ce09298a-1212-4a0a-9b00-eb3def807444 | CATEGORY: IP
| note | 326c8d98-993b-4f3c-9f6f-8ef5ab0cd179 | RESPONSIBILITY: Track Welder , Works Supervisor , Site/Project Engineer
| note | 1af82a5d-d4e2-4417-b17e-0e67d8f8862f | VERIFYING DOCUMENTS: This ITP
| textbox | 4e7a6ae7-8284-4aab-a184-6f6844a7a2eb | Date Completed:
| checkpoint |  | 3.09 Track Stressing
| note | 25fcee05-ac55-4cbf-83ce-4025efff3c69 | REFERENCE: L2-TRK-PRO-014 Welded Track Management Manual
| note | 6f2469ff-586a-4397-96be-b00631ea872f | Chapter 11 – Rail Welding Process
| note | 431938f7-350b-4f46-a740-645f4a84a223 | L2-TRK-PRO-015(4) Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail
| note | 3104e959-af01-4856-b8e4-cd4aa207ce68 | L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan
| note | 828ed7be-f8ce-4193-980b-e6e01395e5e1 | ACCEPTANCE CRITERIA: Stressing Rail in line with MTM Chapter 11 – Rail Welding Process
| note | 066ced66-6e6d-4766-95f4-b70032c7db3d | Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
| note | 7e19f303-a181-4542-9bf5-c410335cc162 | Under Rail Roller Configuration: 1:10 (Curve radius greater than 800m)
| note | 4f2866e8-cec2-4142-84bf-35458cf7615a | Maximum pull length in one direction not exceeded; 300m (curve radius between 801-1200m)
| note | 8bb2cdf8-dfc6-424f-bb98-ad192607e455 | Reference Marks recorded pre and post tensing of Rail
| note | 756d6345-8f4d-4974-be09-3b4db9ef0ab2 | MTM L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan Completed. Validation that SFT 38 degrees is achieved
| note | 99c8b12a-bf32-420e-8173-d473ba4e971c | MTM New Weld Return Form Welding Section Completed
| note | 3899fe44-5f89-4487-87a4-15e2cd5d45b1 | Attach: New Weld Return Form (Weld Section only complete), Stressing Restoration Plan (Fully Complete)
| note | 7ace26ce-c309-4028-b146-402904743e15 | Attach Site Photos: Stressing Activity, Under Rail Roller Spacing, Before/After Reference Mark Measurements
| note | 038c1df0-de59-44bc-b573-ac619d4ef66f | METHOD: Visual, Measure
| note | 57d123c7-4cf0-4d63-9695-d3441c00ea33 | FREQUENCY: Each Restress module
| note | 35ba211e-cf4c-4061-ae09-a09f6faf8846 | CATEGORY: IP
| note | a2e40297-0ab8-40e2-a0fa-716563f4ffdc | RESPONSIBILITY: Track Welder , Works Supervisor , Site/Project Engineer
| note | 0425fede-f668-4088-90fd-fc84625f3db1 | VERIFYING DOCUMENTS: This ITP
| textbox | 7c5a241a-0430-4fbc-bf10-409453887962 | Date Completed:
| checkpoint |  | 3.10 Weld Ultrasonic Testing
| note | 9e12ca87-cb6d-4662-9d3b-5f0a72d42bd1 | REFERENCE: MTPR 031000-01(3) L2-TRK-PRO-049(3) Non-Destructive Hand Testing of Rail
| note | f29fc8bf-5117-4248-9971-2ab4bcd8813d | AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
| note | b88c0b00-27ed-4c36-9e6f-0954d5b16140 | L2-TRK-PRO-014 Welded Track Management Manual Chapter 11 – Rail Welding Process Section 7
| note | a77f99db-041d-4632-8213-312b300ae3f9 | ACCEPTANCE CRITERIA: Ultrasonic testing to be carried out within 14 days and in accordance with MTPR 031000-01(3) L2-TRK-PRO-049(3) Non-Destructive Hand Testing of Rail
| note | 6e1c1121-b17d-4ec6-a978-0b63d9732720 | The cross section of the area of the head and web shall be completely scanned;
| note | 7f629755-1802-4532-b50e-1ce580dda7ba | The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
| note | 3bddfbaf-fdf6-4285-9a7e-4fb745992c6d | Welds shall be scanned to both directions.
| note | 60cb700f-a60a-4cda-9b11-e543a78da462 | No classified internal defects found
| note | b85114f7-526b-4fc6-b3a9-7591c44213d1 | Geometry of rail head does not exceed 1mm peak 0mm for dip
| note | e8180c5c-99cd-4549-bc15-48afa336ab43 | MTM New Weld Return Form Testing Section Completed
| note | 9fd1586b-b4f5-436d-9939-a799c7e33ba6 | Attach: New Weld Return Form (Fully Completed)
| note | 82836faf-515e-4bd9-bbb9-7a091a5b1775 | Attach Site Photos: Welding Aligning, Welding Process
| note | 6a3853e9-b9c8-426c-a68c-96d78772201c | METHOD: Visual, Measure, Test
| note | 6b480aee-815e-41a5-8fa4-100299368e61 | FREQUENCY: Each Weld
| note | 5484e755-5c6a-4690-aafc-f4dbef6ab7b7 | CATEGORY: HP
| note | ad2f899d-e449-4a41-8d13-a57d1f9ba08b | RESPONSIBILITY: Weld Tester , Site/Project Engineer
| note | 64663b95-8fed-4626-860c-9d4e273bd6e5 | VERIFYING DOCUMENTS: This ITP
| textbox | ce22f517-2b72-4f2b-8267-20d999480224 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.01 As-built Survey
| note | 41d0d8be-3537-431e-a3ed-ce32ae9e9cb8 | REFERENCE: As Built Drawings
| note | cdd84454-a6a1-4ca3-9300-0525c46f0c71 | Asset Change form
| note | e79e01e0-b5a3-46bc-b7cb-978b3d828a55 | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
| note | 7733fa76-66f1-45ac-aa22-9e8665edd4e0 | Attach: Survey Report, Engineering Asset From
| note | 23252030-de0a-49ee-8c41-71c1f8da208b | METHOD: Survey, Document Review
| note | 9f0419a0-a16b-457f-9f7b-578a47273bd2 | FREQUENCY: Once
| note | 619e599a-49e8-480a-b23f-80f447e582db | CATEGORY: IP
| note | df4ce0da-e7a5-4d5b-92a5-89e01c8d7676 | RESPONSIBILITY: Track Surveyor , Site/Project Engineer
| note | 567665b0-a9b8-4c0b-8f3f-053b77cee820 | VERIFYING DOCUMENTS: This ITP
| textbox | ceaaf739-9423-44be-a31a-7529fa608586 | Date Completed:
| checkpoint |  | 4.02 Track Certification
| note | 226080e8-a07b-405a-a209-514cd59efd19 | REFERENCE: MTMF020000-1 – Track Form A T
| note | 7a98c16e-debf-4d0f-b0c8-cf57ebdeb861 | MTMF020000-2 – Track Form B
| note | 89bc2868-db14-4017-934a-dbe29dd563f7 | ACCEPTANCE CRITERIA: Attach :
| note | 6df0d045-dabd-47bc-aaa3-a8a5a2f83baf | Track Geometry Conformance Certificate
| note | 03ae06f7-644d-4622-97a1-11fe6ec4972c | Track System and Component
| note | e9131bd2-5272-48cc-9a0b-277641913036 | Attach Site Photos:
| note | 51157ea5-6d10-4607-a8fc-ace7855e1e6f | Before/After Photo of worksite
| note | 70b2f85a-8b80-4876-95be-1f23a4f6f260 | METHOD: Visual, Measure, Document Review
| note | cda59a5d-bf84-4b67-b985-238f9c98c17f | FREQUENCY: Once when all occupation works complete
| note | 4c743b5e-1938-49ac-9fd6-ec21a19a4a7f | CATEGORY: HP
| note | 3ddf177b-db6c-487c-85c5-13724a7e6d9a | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
| note | b3f7aa27-3d81-4673-bf1b-9fff71ff56f4 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 2e78ddb2-be59-495c-ac38-5606a3c583a3 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 57b65779-9d1c-4ef2-b987-86f306497917 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | ac4b856b-6149-4732-804d-89063551a32d | Name:
| textbox | 5769c598-3172-458d-be49-f4b17116d033 | Position:
| textbox | e6cd2e9e-1934-446c-9d4f-fc37f9284618 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-RAIL-Track Tamping & Regulating Rev 0 - | itp | ITP-RAIL-Track Tamping & Regulating Rev 0 | cadc561f-5a89-42ad-a9d9-691eeaaff014
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 0be77242-03cc-476a-a1f0-3c55a432b493 | Document Title: ITP-Rail-Track Tamping & Regulating
| note | 2278cb76-0277-46e0-b26f-7b22708f0d15 | ITP Description: Track Tamping & Regulating
| note | c87e5dfb-f559-474c-b791-81173143cd32 | Discipline (e.g. CIV/STR/RAIL): Rail
| note | f18d37aa-5fc7-492c-b5aa-3225b80915d9 | Revision Number: 0
| note | 2620ce97-15d9-498d-b3c5-d8223d218d94 | Revision Date: 8/02/2021
| note | 52d1073b-7861-478b-b93c-6397da00248a | ITP created by: James Porteous
| note | 82f22a33-4624-414a-90f7-636725932f67 | ITP approved for use by: Romualdo Magpantay
| note | 848993a1-c2c5-4c7a-b8dc-99ec4f2343de | 1.01 L1-CHE-SPE-003 Heavy Rail Construction Tolerances
| note | c899dbde-f33e-4f45-a4ec-edbf8ed7d852 | 1.02 L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | e307af18-fc76-4366-b44f-c9a6dbdfe0c3 | 1.03 PTC Heavy Rail Track Construction Standards Drawing F598
| note | 865146c3-77a4-405d-aa4e-4139069850c9 | 1.04 South Gippsland Highway Package 10 Design Drawings
| section |  | Preliminaries
| checkpoint |  | 2.01 Track Tamping Pre-Survey
| note | 12ed9e2a-cdb6-400b-8052-4c5e89d920a0 | REFERENCE: Track Geometry & Profile
| note | 016c8cb2-bdbe-4db7-924a-c1ad2718e500 | ACCEPTANCE CRITERIA: Complete pre-survey of track and required lifts/pulls
| note | d17876df-f1a0-427e-8677-f39d9d699334 | METHOD: Review; Document
| note | 97cd470c-2799-4b24-820f-b46c8f703ad8 | FREQUENCY: Once
| note | 67959c7b-4b76-4ef1-ac80-5076d9029797 | CATEGORY: HP
| note | 9799059b-d861-4133-ab84-1c06d611bac7 | RESPONSIBILITY: Access Planner
| note | c1654d52-a6bc-48c1-bd8b-6f62712818b6 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 0408e655-debc-4a97-bf6a-90770362e9dd | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction / Installation Activities
| checkpoint |  | 3.01 Track Tamping
| note | 3a59d527-0285-484f-849a-356b6c2a267b | REFERENCE: Track Tamping Design Drawings
| note | eee9d5a1-e311-4860-81f6-399962314ade | MRP-045-SMEC-C-DRG-70-DMG-CPW-5001
| note | 04a699b1-bc59-4df0-8f70-ed5c4ed858d7 | MRP-045-SMEC-C-DRG-70-DMG-CPW-5002
| note | e93c7bd1-bdad-4a26-a8ba-55683da45f54 | L1-CHE-SPE-003(1) Heavy Rail Construction Tolerances Table 1
| note | 0d950dfd-0614-4a8b-8f30-202e962a1ba6 | ACCEPTANCE CRITERIA: Tamping Ensures Track Geometry Tolerances are not breached;
| note | d42443be-518c-4737-89ce-f1eab2dca6b3 | Gauge +3 / -3
| note | 39b79f6a-232c-4490-a995-020a5ed0fd91 | Gauge Variation in 2m 4
| note | 36ca85da-2b8c-441d-88e5-51e802ca2532 | Line (10m Chord) +4 / -4
| note | d4ccb368-0cff-40ba-8211-6f6305ad5b9b | Twist (3.5m Chord) +2 / -2
| note | 37eea74a-2fff-444a-ae05-1cd0ee213d90 | Top (10m Chord) +5 / -5
| note | 5623a83d-49e2-4508-a632-f4ddcd947fd0 | Cant +5 / -5
| note | ec62a0e9-7087-48fa-8cfe-87711c24d718 | General Alignment +15/ -15
| note | 0817a28f-3a41-430d-ba28-62f39a86562a | Track Gauge Check for Geometry Faults
| note | 3734e1d7-876a-4ea1-ae76-64aa6e87af32 | A minimum horizontal clearance of 3.0m from track centreline to structure.
| note | baa11a9a-cb7f-49fb-bd68-edb26534511a | Attach;
| note | 2aaa880e-6061-413a-bf33-ac3e501781e3 | Track Gauge Record Sheet
| note | 17c2df46-9d7d-4826-8365-4be746176e67 | Attach Site Photos:
| note | 62a51964-abe9-4f25-b8a2-b7589967a2b9 | Tamping Activity
| note | faeec467-cadb-4309-a17f-7f8be4d8fe03 | Track Gauge Activity
| note | 801797e5-2aa2-400b-a052-235496f859d5 | METHOD: Visual; Measure
| note | d62118a5-2576-48ec-b893-d177d636d0e0 | FREQUENCY: Once
| note | 7585d2df-dd41-4292-b4cb-61e7fa6043d2 | CATEGORY: HP
| note | a6ef3291-c35a-47cb-98fe-dd5ce130fc5a | RESPONSIBILITY: Track Supervisor ; Site/Project Engineer
| note | 54fe9df4-62aa-407a-bad7-2f40b25e1e46 | VERIFYING DOCUMENTS: This ITP
| textbox | 0d2866f4-b907-44ca-ab83-16ab303c0e65 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.02 Regulating and Ballast Profile
| note | 2e2d96bd-226f-4dcb-a141-1c4305cf69ca | REFERENCE: Design Drawing
| note | 8e968d0d-c49c-4dfa-8103-7a17231b99cb | MRP-045-C-SMES-DRG-70-DNG-CPW-2001
| note | 5972b541-948f-413e-a8fb-1c1df824e1f3 | L1-CHE-STD-029 Earthworks and Formation Standard Section 13
| note | 95bc06bd-6180-4321-ac83-7a2538f58b70 | PTC Heavy Rail Track Construction Standards Drawing F598
| note | 162c0300-6851-4048-9109-1723d1802e8f | ACCEPTANCE CRITERIA: Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter
| note | cc5af263-4820-4d6f-8a49-20db09577c58 | No Ballast to be on top surface of sleepers or around rail Fastenings
| note | d8f9a674-814d-4079-89e9-d4d8426f8e4d | Attach Site Photos:
| note | d6ef8127-d814-4052-ade1-052eac7dcd5e | Ballast Shoulder Measurement
| note | 841ad6e6-ae2a-4062-a193-808894b6894c | METHOD: Visual; Measure
| note | 6294f93a-af60-45d3-9b6f-dfd0fc19c881 | FREQUENCY: Once
| note | 0705f533-d51b-459f-a222-57660fe9066c | CATEGORY: IP
| note | a4310c22-df1d-48ec-99fe-220a66c1e9c5 | RESPONSIBILITY: Track Supervisor ; Site/Project Engineer
| note | a5b3f090-5fa0-49b1-badc-e60a15046dea | VERIFYING DOCUMENTS: This ITP
| textbox | abf0bc87-a6a3-4178-8cf8-afc5b4331548 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.01 Track Certification
| note | 2565dbbf-45d0-4bd5-b535-1ab0f504f842 | REFERENCE: MTMF020000-1 – Track Form A T
| note | 90b5af5e-f6d4-4940-8303-ab09b8cd3cab | MTMF020000-2 – Track Form B
| note | c980dda8-1c63-43b4-943e-f8673f8618a2 | ACCEPTANCE CRITERIA: Attach :
| note | 0919db66-d213-4e0b-a697-6edcb4fb307f | Track Geometry Conformance Certificate
| note | 1ed5ab07-7838-4993-b5d6-dc7e97d36a58 | Track System and Component
| note | c5399700-33fd-4a8f-831a-dab724fdacb8 | Attach Site Photos:
| note | ed124baa-74b6-4609-9bc7-e34d72476c45 | Before/After Photo of worksite
| note | 9221bfb0-94ac-4f7f-907d-f95a496b02dd | METHOD: Visual; Measure; Document Review
| note | 775ac133-01d4-46d5-a418-383a54879c3e | FREQUENCY: Once when all occupation works complete
| note | 5d70f7f6-fa4a-4767-8d44-ba7bc64bf409 | CATEGORY: HP
| note | 052872fb-efc0-4b11-936e-edc8f9a37835 | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
| note | 0575ab4a-2e6d-428a-95a8-07645ddca943 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 5d1fdcba-3abf-471b-8c54-0bb1a4fcd3c2 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 5a5bae54-62de-4fdd-aea5-7f643fe96e96 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 1d39a244-c273-482c-abdb-4c5e0efd1df6 | Name:
| textbox | 2b735592-4bc1-4725-bffa-b199336ff032 | Position:
| textbox | 91eac561-f24d-47b5-ba2e-6f86a1dbfe4f | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Rail Delineation Fencing Rev 5 | itp | ITP-CIV-Rail Delineation Fencing Rev 5 | cd56c7e7-0455-4cec-b915-2a01342bedf7
| section |  | Referenced Documentation
| checkpoint |  | Referenced Documentation
| note | 586e3d73-67fc-552d-af7d-abea349b095f | Document Title: ITP-CIV Rail Delineation Fencing
| note | 15d10078-4f9d-59a2-a3e4-ac367c96740c | ITP Description: Rail Delineation Fencing
| note | 3dd064e4-0411-5175-85f5-3e42ceba7305 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 69817054-073d-5faa-8ecd-91b1a7b8f704 | Revision Number: 5
| note | bec84ae3-fe57-5ad6-949c-90957caa8779 | Revision Date: 19/08/2022
| note | 9aa09596-8fa2-5ccb-ae48-6302c533bdf3 | ITP created by: Ethan CARUANA-SMITH
| note | 6380f050-aefe-50db-b286-bf7070fd2900 | ITP approved for use by: Pradeep TALASILA
| note | 8cf3f40a-4860-51f2-bd53-58717ef141b5 | 1.1 - Non Dependent - IFC Drawings
| note | d8e8c8b0-0d81-5687-a494-8cb015d31745 | 1.2 - Non Dependent - NIST-0001(2)
| note | cc6039ac-e605-54b2-855f-ecc2afe950d7 | 1.3 - Non Dependent - NIST-2617(3)
| note | 17da50ee-6994-517d-b69a-21fd4c4de046 | 1.4 - Non Dependent - NIST-2662(1)
| note | cc710ecc-5a29-559f-a478-d433a5b0c3ae | 1.5 - Non Dependent - SAST-3281(1)
| section |  | Materials
| checkpoint |  | 2.1 Concrete
| note | ed4f4152-6160-5ae2-91b7-d4821e430b71 | REFERENCE:
| note | 5266b546-b763-5bd2-a09c-6d389728314d | IFC Drawings
| note | d00ad28b-5085-5311-8d68-ac756e380688 | Section 610.07
| note | fd91ffcf-3473-5af8-898d-4719af6dc7f9 | Table 610.071
| note | 080ab21a-80d4-52cc-a96c-05713e5027dd | ---------------------------------
| note | 0fe76c4d-2398-5b55-b3a3-e316eb07e189 | ACCEPTANCE CRITERIA: Unless otherwise stated the following will apply: Concrete Mix is to be 25 MPa concrete per IFC drawings.
| note | 92e80bea-c689-5eeb-acd2-2504b175750a | ---------------------------------
| note | f5fcaba7-291c-5513-8f89-9ac42b53706c | METHOD: Document Review
| note | b045be4a-84db-55d1-98c4-850c75ccef40 | ---------------------------------
| note | f3715e75-2ee4-5f9c-883b-6f51613df8ca | FREQUENCY: Each Mix
| note | fa258129-d434-5630-8f17-6dfe89871106 | ---------------------------------
| note | a3c7cf20-2c9a-5818-a193-a3e5d54ab7c9 | CATEGORY: HP
| note | 31a0d2b2-69f9-5267-8ee5-4e78f4092071 | ---------------------------------
| note | d7665cd8-d3a0-5366-8998-9878ca02fcfb | RESPONSIBILITY: SE/Site Supervisor
| note | d3010911-b66b-5083-b909-b0645c92348b | ---------------------------------
| note | 03e2e1a9-71e7-5f78-919c-182b8aef6c9a | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
| textbox | 71113772-1b20-5a68-83b2-f141ed5e230a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Steel components including posts, mesh and fittings
| note | 5d626abf-f664-55ef-986d-85b94cba6e92 | REFERENCE:
| note | 85ae5494-3852-5083-a6b7-346bb2e9d74d | IFC Drawings
| note | d4e49323-8131-5c63-b63b-0a7e9cd3bb93 | AS4100
| note | 313a826c-ebf6-5b2b-add3-4fb11cb8d599 | AS1163
| note | 012f2a1a-dbc7-59e6-8f58-796fa0d5a552 | AS1101 Part 3
| note | dfa60e09-f0f4-5fda-a81f-f0a06b93cc69 | AS1554
| note | 536945b9-f434-5503-9984-a07d8634577e | ---------------------------------
| note | 05f450e9-c5df-5b24-adca-0796f5bf49ff | ACCEPTANCE CRITERIA:
| note | 87aa237a-0ee5-5f2e-9dc0-093a46592a83 | All Steel must comply with Australian Standards.
| note | 1a986ae1-a974-564c-97c3-8ca3cbf88345 | Steel section sizes must be checked on site.
| note | 7a9b3d48-669e-5932-b52d-43f21d88482d | Steel posts to be CHS with a grade of C250
| note | 5fe3d223-0467-53d5-b9df-b22fd0612035 | ---------------------------------
| note | a208bb65-8206-519b-9f02-34da2735b31b | METHOD:
| note | 2f1ce9af-8df7-5dc6-9351-0c85d3d7dc7f | Document review
| note | 122e9557-b9cc-5e3f-bb1d-4c8d1e68094a | Visual and Measure
| note | 043926e4-a93d-54da-ad66-30464d53fb65 | ---------------------------------
| note | 518199ab-d865-56c2-b9c5-38750e36d78c | FREQUENCY: All elements
| note | 1b8169d1-e5f8-573d-92aa-ddb9c2865b44 | ---------------------------------
| note | 5cfc0d50-39dd-591c-991e-e2696bae8138 | CATEGORY: IP
| note | 74636671-099e-5be4-a1d4-9ac9c7dc9c16 | ---------------------------------
| note | d801b636-38ca-5063-ac06-6ae6aef3b6e4 | RESPONSIBILITY: SE/Site Supervisor
| note | 3850b366-dff5-598a-8d41-9128ea16bd7d | ---------------------------------
| note | 31961a51-de79-5902-bacb-83b77172049c | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
| textbox | 89d87af9-4586-5fee-86b8-6655c3264334 | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | 36ab9cbc-42f5-5c95-8c5a-cd8546d197da | REFERENCE: IFC Drawings
| note | f8e86cb3-1e0d-52c6-8ac7-70b24d5160e6 | ---------------------------------
| note | 3bfeb884-eb39-5d93-9716-6007c0fdd33b | ACCEPTANCE CRITERIA:
| note | 8e346aa0-ec39-5639-b32b-8c896433c677 | Survey to set out the following but not limited to: existing services, refuge bays and fence start and end points.
| note | 15c4b554-6788-5161-b320-84f318923181 | Offset checked against the running edge prior to installation of posts.
| note | 6343c190-f16f-59be-abf5-0b08d4b85230 | ---------------------------------
| note | 6e1752e2-dcab-507a-a225-d1f2343cabb7 | METHOD: Visual and Measure
| note | 12d676c2-e45e-5def-9ff7-7413eb34e217 | ---------------------------------
| note | 9233b3c9-bc44-5b5b-9a14-f0a187f73d3d | FREQUENCY: Each element
| note | c5cf92e7-251d-559d-86ef-3a813231baca | ---------------------------------
| note | 11b8f44f-7cd3-5ec9-8c99-becb48a69045 | CATEGORY: IP
| note | 8d4a7a3d-af4f-5522-9bda-601852bd7f24 | ---------------------------------
| note | f97b819a-b5dc-5589-879e-76276e94269f | RESPONSIBILITY: Surveyor, SE/PE
| note | f8ccf5de-650a-5907-89e6-c21f94c02bdd | ---------------------------------
| note | 10139c34-e96a-5d3b-ace7-f30c82aee920 | VERIFYING DOCUMENTS: This ITP
| textbox | 7457089f-d876-5498-be63-4e0fb4d50fb9 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Excavation works
| note | c1c82e65-3e17-5cac-a66a-f96cd35d38b0 | REFERENCE: IFC Drawings
| note | 2c9eb698-4261-5b3c-9767-e1e5413766fd | ---------------------------------
| note | 430cc545-ba11-5e9c-a35a-abd91000347d | ACCEPTANCE CRITERIA:
| note | ce5f5564-211b-5aa8-ab30-15556b406feb | Excavation completed by NDD
| note | 2aca8320-35d6-5726-9950-35c8d8a5e3c2 | Follow asset owners guidelines for work around their service.
| note | b8b3b79d-ad3c-5115-86d2-0d9e4ed96404 | ---------------------------------
| note | 11079b91-99c6-5d06-b1e4-096346896ccc | METHOD: Visual
| note | b55a6d30-e9f7-59f1-af95-be74e3b50b4e | ---------------------------------
| note | c076cf98-7bd3-51b0-83aa-456d62777455 | FREQUENCY: Each fence footing
| note | dba77478-59d8-5854-97a2-88497b88e689 | ---------------------------------
| note | 31988112-8d0e-581e-947f-9c3c9bbec45a | CATEGORY: IP
| note | e37bec59-70ed-5566-ad05-9fb210532da5 | ---------------------------------
| note | a891f0a1-ae14-5fad-be9d-c7b3a3bce425 | RESPONSIBILITY: SE/Site Supervisor
| note | e8299555-08e1-5dd8-aaeb-03f98e1deba9 | ---------------------------------
| note | 86da1b0e-791d-5c65-a079-9c5271a41ae8 | VERIFYING DOCUMENTS: This ITP
| textbox | 219bfa49-6327-5198-89b4-7f8c4408b2d8 | Date Completed:
| checkpoint |  | 4.2 Ground Conditions
| note | b61be3cb-8e10-550e-9665-751e0746d630 | REFERENCE: IFC Drawings
| note | 2130ec30-394f-571d-90b2-c321b6cc2d6f | ---------------------------------
| note | ad2d432d-21be-5d54-a6ef-9e33374bb0d8 | ACCEPTANCE CRITERIA:
| note | 544f5ec0-1eae-53d4-8fdc-cb1a7ebc35e6 | All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
| note | 3d688135-6052-5341-810d-1b6942efe46e | If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
| note | d0ba8fbe-11f9-591a-82c6-32ac33865230 | ---------------------------------
| note | 0d027ca9-3c0b-5843-8d88-ba57d91de1c4 | METHOD: Visual
| note | 58fb0bf2-e0d7-5b33-88c7-4352764511d3 | ---------------------------------
| note | 89e48bd7-7c88-5e28-b57f-cfdbe355726e | FREQUENCY: Each post
| note | fb4c26ca-bf61-5339-a0d2-12d71458c97c | ---------------------------------
| note | 625f833b-439c-5095-8814-ab4acf9dbd99 | CATEGORY: IP
| note | 632b13c5-1541-504f-a826-575d887dec5e | ---------------------------------
| note | a4c44ca8-d03e-58d3-adf7-3e4677c08f67 | RESPONSIBILITY: SE/Site Supervisor
| note | 92c00f09-ec27-5abc-b86b-ce5dff032b7b | ---------------------------------
| note | 66a6f120-e9e6-56d8-a7ce-9ad42de601b2 | VERIFYING DOCUMENTS: This ITP
| textbox | a5e68011-2cb5-599d-ab1a-f19eb05a9d8d | Date Completed:
| checkpoint |  | 4.3 Fence Footing
| note | 92d75dda-148b-5518-9d25-18464005785a | REFERENCE: IFC Drawings
| note | 9a78401c-48c8-5b4d-9581-3475f803e73b | ---------------------------------
| note | 72851e16-4ca1-5dff-a19e-d3c729522775 | ACCEPTANCE CRITERIA:
| note | 1c2268cc-6c5e-5085-b348-e5f53cf47007 | Footing dimensions 500mm deep x 300mm diameter.
| note | 5ae1a6f6-5a61-5911-a29e-b349e2a2fee2 | 32 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample.
| note | b5c94f58-a725-5ab2-9300-7a76027945f4 | ---------------------------------
| note | 2e5ef30f-d84d-5f57-9279-d880b08b693d | METHOD: Measure
| note | d0b8bc1e-ffb4-5ce1-90dd-7cd928ba2d59 | ---------------------------------
| note | 69863338-aeb3-5f51-909e-3f0d3f4ba135 | FREQUENCY: Each footing
| note | fca09822-fa11-5ad2-894b-014a2f5c3891 | ---------------------------------
| note | 229eb23c-7695-58f4-a3dd-cd7e99b91e62 | CATEGORY: IP
| note | 5fa05c82-f013-524f-8016-5e9efd39ab4c | ---------------------------------
| note | 2d73f09b-3b7f-56f7-9d3d-92cc1d9c56e1 | RESPONSIBILITY: SE/Site Supervisor
| note | 1433d4e0-9a47-5a46-8f1e-f67c9ddb016c | ---------------------------------
| note | cdf2ca60-d48b-5e3b-bf94-da66ff1defcc | VERIFYING DOCUMENTS: This ITP, Concrete Dockets
| textbox | 8c4c7989-de46-5e61-8ca1-755844fd1a2a | Date Completed:
| checkpoint |  | 4.4 Fence Post Installation
| note | d9505aa4-2e94-5b35-879a-05baafe6961b | REFERENCE: IFC Drawings
| note | deea7459-14ed-5b94-bc61-c30ad8d9ef24 | ---------------------------------
| note | dbaa3dfb-652d-52ad-b84d-9b3e573af975 | ACCEPTANCE CRITERIA: DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover.
| note | 206a736c-06da-5f4e-8aaa-3dd46d8d14e3 | ---------------------------------
| note | 4193e3a8-7379-5abb-a6ee-c7f178fc2f61 | METHOD: Measure
| note | 6d5fcb88-d319-5b16-85c3-508d76c7c335 | ---------------------------------
| note | b0657917-251f-5bde-b28e-e7b8e9324586 | FREQUENCY: Each post
| note | 79f642b1-cb5a-5acf-a9f0-bd52dd01fd6d | ---------------------------------
| note | f93e445b-7ecb-5f94-9bca-bf17caa99e4a | CATEGORY:
| note | 2519c3c5-44d2-55d7-8fb2-e255bf67561f | ---------------------------------
| note | e603aa7d-ddc9-5cc2-b656-b49153dddb67 | RESPONSIBILITY: SE/Site Supervisor
| note | 8d18519e-f062-5f6e-b200-1a369e4c9cd4 | ---------------------------------
| note | 0848b096-eb1d-5ddd-8f6b-d33a339684b1 | VERIFYING DOCUMENTS: This ITP
| textbox | 46a6301e-61b4-5a00-b508-509b1227a1b9 | Date Completed:
| checkpoint |  | 4.5 Chain Wire Mesh Installation
| note | 321069e4-92a0-5346-a714-a83d2e4b42db | REFERENCE: IFC Drawings
| note | 9d680bba-68ec-556c-b9ee-55eb5b4811e5 | ---------------------------------
| note | fb923271-30fc-5d47-820a-8e18cef2230c | ACCEPTANCE CRITERIA:
| note | 76519946-1b8e-5689-8a3f-4355ab452f0f | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications.
| note | c868f032-622e-5c68-9d65-d002a862ea11 | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
| note | 7f07224a-0af1-5800-a885-5025197248d2 | ---------------------------------
| note | d0c14973-4a5d-54ef-a313-efa824e076ff | METHOD: Visual
| note | 0ca6ac29-0ab5-549f-8306-64cb25d8aab5 | ---------------------------------
| note | cae7c4fa-93af-53c3-bb4b-dc7eb4035ce0 | FREQUENCY: Each element
| note | a6660b26-240c-54d8-9ef8-7242b5110dab | ---------------------------------
| note | 9396ccd9-bdc9-525a-af82-3d46a94ada8b | CATEGORY: IP
| note | d52729ab-6924-5c36-abf5-4a017e4f2a5e | ---------------------------------
| note | 01fe1892-3391-5639-b3b8-58548e9f7c35 | RESPONSIBILITY: SE/Site Supervisor
| note | f6a67107-29cf-5b6e-895e-d21fe5df4c71 | ---------------------------------
| note | fd6fec4e-ee4f-5ef1-be26-79ef3bdf94ca | VERIFYING DOCUMENTS: This ITP
| textbox | 27e42284-d301-5b8a-bd11-90d185389795 | Date Completed:
| checkpoint |  | 4.6 Welded Mesh Installation
| note | 2f49069d-701a-58a2-8a4e-3de842eeb145 | REFERENCE: IFC Drawings
| note | 5618314c-26c0-54e9-a3e6-15f7f4d27cae | ---------------------------------
| note | f3bd5139-8e70-5121-84c1-236ebc6e51a8 | ACCEPTANCE CRITERIA:
| note | c2a489da-da02-5f55-b549-5239599c268b | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications.
| note | 87a0b28c-bfc6-5d98-a5ac-a5a8eb6fba73 | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
| note | 29b4f7b7-7f33-5ca5-9ea5-773dfaa8a46c | ---------------------------------
| note | b7288d65-7aed-5b5c-bf6a-17fb96362919 | METHOD: Visual
| note | f85f1938-2f8f-5223-a290-1d9f396922ee | ---------------------------------
| note | 8d7321f9-024f-5049-ab9f-6b6a6f4fd49b | FREQUENCY: Each element
| note | af97c9c9-97d9-5ebe-9e00-3558ee0e60db | ---------------------------------
| note | 5af57ac6-c004-580c-aa16-a3e7bba675e5 | CATEGORY: IP
| note | 9c4a7446-8ca0-5b9e-9784-233739333bc1 | ---------------------------------
| note | 370020b3-f361-5018-bfc6-2f894b26b406 | RESPONSIBILITY: SE/Site Supervisor
| note | f0fcf522-d1fb-5129-a5fe-b1913123b947 | ---------------------------------
| note | bdc1687f-f277-55ac-bb50-4069c2331863 | VERIFYING DOCUMENTS: This ITP
| textbox | 858cc7bc-7f8e-5d2c-b640-2cf8f3da7db7 | Date Completed:
| checkpoint |  | 4.7 Refuge Installation
| note | 18a48593-66a2-59cf-8d40-626c45c56531 | REFERENCE: IFC Drawings
| note | 546c8d2a-356f-548a-a58c-b5d4cbf5323d | ---------------------------------
| note | e9791d57-50c4-5f39-9bf9-2f6d379c913e | ACCEPTANCE CRITERIA:
| note | a2404a17-9054-5cdd-a6b1-4e1e67e7aef4 | No chain wire mesh to be installed at refuge access.
| note | 17115b9f-f998-5b30-97ab-5ad36cf14d54 | Refuge Access to be located at max. 20m intervals along the fence.
| note | e1c3a7fa-209d-5a4b-920f-4e086af2698a | Install additional refuge bays or reduced spacing to allow access to rail assets
| note | 26c1be47-ca4d-56dd-8542-c0df587887b9 | 50mm dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
| note | 987b3775-4235-5be2-9bc8-f40975a04f3e | Refuge access to be 1200mm wide
| note | cfaf2cde-556c-5ae7-babc-ab7e8d0ef61b | ---------------------------------
| note | 6267fb63-3a37-5b98-b66a-0a378e73c83b | METHOD: Visual/Measure
| note | ecea2b21-3b76-5eaf-8b1c-7dae4ba82e85 | ---------------------------------
| note | 9d627eb6-da09-5222-b301-98f595ab4ccf | FREQUENCY: Every 20m Max.
| note | 43280c98-afac-5c19-a2c9-30d1d7902bda | ---------------------------------
| note | df5ad8f8-44bb-5c0b-bed6-c139d151f8ca | CATEGORY: IP
| note | 9bb61343-a0f0-59bc-aa0e-363d2560d2ff | ---------------------------------
| note | 7d1c665b-f591-5bc2-a0e1-dcf966d58b5a | RESPONSIBILITY: SE/Site Supervisor
| note | 4f92ddcf-722e-5d3d-a88f-c137ef56186f | ---------------------------------
| note | 81dd1c35-9697-5597-b7ff-64350e45bb2f | VERIFYING DOCUMENTS: This ITP
| textbox | 38dcf38f-0f71-5dbe-b425-2eae2cd2aff9 | Date Completed:
| checkpoint |  | 4.8 Gate Installation - Gate
| note | 66c62e1c-d850-588d-bef8-4bd8a6b70082 | REFERENCE: IFC Drawings
| note | 26f67e22-1b65-54b6-a105-eab43acd01c3 | ---------------------------------
| note | 4f43078b-2a71-5b1d-8cd4-a95cb32edac2 | ACCEPTANCE CRITERIA:
| note | eb30bf97-6b87-5a1c-9230-501f22bbea01 | Foundations and posts installed as above with 2400mm spacing.
| note | 7906c9fd-28a6-5cf8-84ae-bbe086443ee2 | 2 no. 1800mm (H) x 2400mm (W) gate panels per gate.
| note | fdd7f69d-9995-5d59-a1d0-d78b14888226 | Centre post of gate to be sleeved and positioned on the side external to the construction site to ensure gate only opens into construction site and gates that are parallel to track when closed open away from track.
| note | 4f93b9ac-05b1-5640-88b8-fe4406743390 | ---------------------------------
| note | f147d0ef-4c49-5065-87a0-5bdd0aecfd00 | METHOD: Visual/Measure
| note | 5f72b2f5-14f3-51e8-a350-7b10653af341 | ---------------------------------
| note | 950e5ef2-3912-5580-a79e-4af5ca3dd38d | FREQUENCY: Each Gate
| note | 7572b5a6-25a2-526e-9c1b-cb63c00e8746 | ---------------------------------
| note | 900090e2-4c2d-5be9-a216-b9cb5f25d1d1 | CATEGORY: IP
| note | 1f1ddb5c-9497-55c9-b826-a775c7aa67a2 | ---------------------------------
| note | e3060365-62b2-5b14-92ae-7239cae7e888 | RESPONSIBILITY: SE/Site Supervisor
| note | 09c2390b-36c2-5ebc-95b1-054fcb689ade | ---------------------------------
| note | 510d1c25-6d03-527e-8f7d-33f0a2b6e7b7 | VERIFYING DOCUMENTS: This ITP
| textbox | 06af211d-6a91-58bf-aec2-14797f5d2982 | Date Completed:
| checkpoint |  | 4.9 Limited Clearance Sign
| note | 244dab96-aff7-5c15-9ff4-f661eaf572e4 | REFERENCE:
| note | 7fd8eb7a-2ffc-58ab-ab99-c7fa943ef5b5 | IFC Drawings
| note | 3a737c05-6fd2-558a-8df3-80098a9997cf | NIST-2617 Appendix A3
| note | 3f90a900-a25c-53be-984d-cf959c8f781a | ---------------------------------
| note | 718bab2d-af95-5440-87c3-0f4ef1f09016 | ACCEPTANCE CRITERIA:
| note | fb01f13b-7577-5073-b314-3e2e02a813ac | Limited clearance signs to be erected at all refuge locations and at each end of Delineation Fence where fence is offset at 2.4m from the centreline of track.
| note | 9a1ee7fe-1c62-582a-abd4-fe6950071440 | Sign to read "DANGER LIMITED CLEARANCE DO NOT OCCUPY DURING PASSAGE OF TRAINS"
| note | 82145b27-6a6b-57dd-8297-fca00f68b59c | ---------------------------------
| note | 2c116292-0e11-50c9-b33c-be429b3df3a0 | METHOD: Visual
| note | 2f6c1b76-ccb1-5d15-9ac5-7eae5c287a34 | ---------------------------------
| note | fc4f79c3-6abe-588d-b972-55ad02cef7fe | FREQUENCY: As required
| note | 2916ec31-d98b-53c4-bd90-c34a83ce2003 | ---------------------------------
| note | 33c5ffe4-bd73-5442-8ee9-d420211e26a6 | CATEGORY: IP
| note | ee4dfb88-0f47-5754-b6db-97c7ba6ef339 | ---------------------------------
| note | 58ffb908-94ca-5c6d-b538-4d125995a0c4 | RESPONSIBILITY: SE/Site Supervisor
| note | 0da88e2d-7bf5-5f22-976a-2821cb504542 | ---------------------------------
| note | 1be25313-f436-51b1-915e-033eaecaa7b7 | VERIFYING DOCUMENTS: This ITP
| textbox | cd6164dc-6ccc-5f1f-8122-50914adf7a73 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 Fence Height and Track Clearance
| note | 455024da-4e14-5f8e-adc3-2339d6c88d5e | REFERENCE: IFC Drawings
| note | eec707cc-3eeb-58a0-b918-6a02d36079f8 | ---------------------------------
| note | 0faa54a8-aa28-546d-a409-2b0123875dc7 | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to nearest rail.
| note | e9339615-5a3e-5780-bb49-d150c1710e4b | ---------------------------------
| note | afa80959-09cf-5d4f-beaa-c5ccefe85db7 | METHOD: Measure
| note | ea07e844-378b-5fec-be70-6acba4f93a43 | ---------------------------------
| note | f3cc2aa7-7a41-5177-b885-ebec02aa4b64 | FREQUENCY: Each lot
| note | 60c467da-c604-5ce9-bb30-178f26690ce7 | ---------------------------------
| note | 54acfe22-38c4-57be-a03d-e4da3ac349f2 | CATEGORY: IP
| note | 895278e0-830f-5d25-aa10-f232ffa9f643 | ---------------------------------
| note | 5b2ab764-263f-5a2f-9c1a-53b3dc0c5c1b | RESPONSIBILITY: SE/Site Supervisor
| note | 825db782-716b-590b-8446-2e52e498531c | ---------------------------------
| note | 4a205ed0-fb23-5e53-9e21-f33ac743cc77 | VERIFYING DOCUMENTS: This ITP
| textbox | 02931319-7084-5b69-bdb1-9e05804ca3ac | Date Completed:
| checkpoint |  | 5.2 As-Built Survey
| note | beeb38e7-c2e3-5152-ac0c-5a901d61020d | REFERENCE: IFC Drawings
| note | 3cff871a-14f9-5fc5-b170-380dcab4376d | ---------------------------------
| note | d66276af-4db9-56f5-86ea-eea6424e56ab | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure spacings do not exceed standards.
| note | a12bf8f5-f546-56b3-8532-6a2fab33222c | ---------------------------------
| note | e441a87f-59af-569c-af90-d203eabc34f8 | METHOD: Measure
| note | ac08e716-653f-536d-935d-c1b09e42699b | ---------------------------------
| note | 4d70af15-44a5-52f3-8e73-612100433a27 | FREQUENCY: Each lot
| note | 735e4f97-810c-5f90-9b54-335db5d7de63 | ---------------------------------
| note | 967b761b-702e-5fd4-be21-a54c28bacf7c | CATEGORY: IP
| note | 11d1d339-436b-556a-b7b7-84805159dc34 | ---------------------------------
| note | ec053309-0499-5014-aaf9-af7c0de14686 | RESPONSIBILITY: SE/Site Supervisor
| note | fea45220-767b-5f8e-8795-9521bd8d8849 | ---------------------------------
| note | b99f00f0-cf5b-5917-a519-563a587e747e | VERIFYING DOCUMENTS: This ITP
| textbox | 5c52aa01-a204-53e4-b331-90cd14004aac | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 0c98edbe-5c33-56cb-9673-68b76865b883 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | f4891f16-b98c-57b5-8f85-968f3cf8d23d | Name:
| textbox | 9baefa19-0c9d-50bc-88d0-889401fadef4 | Position:
| textbox | cbea557f-fba5-50d8-bfb1-7aeac1c7c225 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-uPVC Buried Flexible Pipelines Rev 0 | itp | ITP-CIV-uPVC Buried Flexible Pipelines Rev 0 | ce6a98b9-5bf2-42a0-99d7-f9823b946a08
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 1f64b15b-9ca3-4e4b-930f-a499f7e67619 | Document Title: ITP-CIV-uPVC Buried Flexible Pipelines
| note | 9eceea5a-1642-4c46-a630-9009109ca42b | ITP Description: uPVC Buried Flexible Pipelines
| note | 9343e499-b5c7-45e7-b9d8-d35b11c0bddf | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 49a545c0-6847-407c-a5cb-0a429f1777a1 | Revision Number: 0
| note | 99a28907-1ca2-4e84-8922-5406b32fd816 | Revision Date: 1/12/2021
| note | 6dedd3d5-ed02-4682-b9aa-ae5b87c355f5 | ITP created by: Michael Daly
| note | f06eabf2-48cd-4e72-92ba-65c7a6d28ad0 | ITP approved for use by: Aldrin Guinchoma
| note | 9b4258ae-4b5a-4516-b31f-dbcc9a97ee7d | 1.1 AS/NZS 1254:2010 (Incorporating Amendment Nos 1, 2 and 3)
| note | 9c2d4714-09ab-46d0-93a4-07d48877a752 | 1.2 AS/NZS 2566.1:1998 (Incorporating Amendment No.1) Reconfirmed 2018
| note | bcbb1910-3214-4f9f-b7ee-97a7bc872bd0 | 1.3 AS/NZS 2566.2:2002 (Incorporating Amendment Nos 1, 2 and 3)
| note | 171835a8-066e-42af-b8a5-560ec7a5080b | 1.4 VicRoads Section 701
| section |  | Preliminaries-Materials
| checkpoint |  | 2.1 General Requirements
| note | f4003381-fff8-478f-a644-faa0a31f4b5f | REFERENCE: AS/NZS 1254:2010 Section 2
| note | 9f2b1f25-fc84-45e9-9fc2-7271452f86c6 | VicRoads Section 701.11
| note | 3ac73f7d-2665-4aff-946f-2e41dadc88b3 | ACCEPTANCE CRITERIA: PVC-U pipes' minimum general requirements are to be met in accordance with Section 2 such as;
| note | ac81ed62-fb6c-4837-b032-261f5ce1075c | 2.2 - Composition
| note | f83d7d43-2073-44b6-806c-d596ac14c2e6 | 2.3 - Colour
| note | 2eb98fc7-fac5-4fe4-b34f-9978ca27c0bf | 2.4 - Freedom from defects
| note | 4d9b4028-ad2b-402a-a6f9-bd50977adde2 | 2.5 - Elastometric seals
| note | 7c49e999-59a2-4fad-b941-e3ef40707e65 | 2.6 - Solvent cements
| note | 7c6058ba-9ab9-451f-90fd-2f1307cd5450 | 2.7 - Packing, storage and transportation
| textbox | 49d3325f-a945-4001-bf6d-d11493d9329f | Enter: TeamBinder Material Approval number
| note | 77e9a0e8-f816-4d14-abad-3060749994a7 | METHOD: Document Review
| note | c74ab30e-968f-4368-bedb-ad843d0e169f | FREQUENCY: Once for each different supplier
| note | dd3f9788-788d-4861-bdbe-d1d12355fd80 | CATEGORY: IP
| note | 5dbf665f-8e6e-452f-b192-d663820fb5a4 | RESPONSIBILITY: SE
| note | 64c52e2c-ffb7-48f7-b1e9-077dc3d10609 | VERIFYING DOCUMENTS: Attach Delivery Dockets , Attach Material Compliance Certificate
| textbox | b17874ca-6b57-4d7b-93c7-07b0c78ba6c5 | Date Completed:
| checkpoint |  | 2.3 Selected backfill material
| note | 64cfbfc8-ad7c-48bc-8358-42d85e39c6d0 | REFERENCE: VicRoads Section 701.09 (d)
| note | e50d5bab-99b5-4b30-aa7c-b26cb791cf9a | ACCEPTANCE CRITERIA: Materials used for selected backfill shall be free from perishable matter and lumps and shall conform with the following requirements;
| note | a24f7241-fc10-4f1c-a271-5b48d6beff2d | 100% passing 37.5mm sieve
| note | 84f1f48b-845b-4328-bc93-702ab76a4d3f | 5-40% passing 0.075mm sieve
| note | 55cfe3fe-6982-4a2e-a26d-a3179a90b939 | PI (Max) 20
| note | 9d09b4b9-e7d2-498c-9ec0-964102c26485 | Enter: TeamBinder Material Approval number
| note | e575a6f2-9bae-44ee-bf01-017ad7c6602b | METHOD: Document Review
| note | 1b20c094-c4a9-4731-b19f-f73e97a6332c | FREQUENCY: Each different type of embedment material
| note | 05dfcca7-40d0-40ec-a93d-f15d7a330f17 | CATEGORY: IP
| note | ffc62351-b3df-4c92-a3a1-48d335f5bb39 | RESPONSIBILITY: SE
| note | e2e4ae06-f49b-469a-aaf6-0c0933a32e30 | VERIFYING DOCUMENTS: Material Approval Number , Attach Delivery Dockets
| textbox | 6618522d-ad1a-4841-ba60-a3f8481eb5d1 | Date Completed:
| checkpoint |  | 2.4 Ordinary backfill material
| note | 12438e3a-917e-4039-816c-73b608944a34 | REFERENCE: VicRoads Section 701.09 (d)
| note | dae7db48-b6bc-4d3f-ba16-aaf6f764d57c | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with these requirements;
| note | 0d8bfb80-aacf-47e2-9ca5-14983ad705b3 | 100% passing 75mm sieve
| note | bde86b3a-1135-43c7-a306-58b9d9fa5858 | 40-100% passing 2.36mm
| note | 66c72214-4532-4e9c-9308-db8b1724c857 | PI (Max) = 20
| note | 3b12cbba-d1e4-428d-903a-ad310f7ec152 | Materials used for selected backfill shall be free from perishable matter and lumps and shall conform with the following requirements;
| note | 14bcadbb-ebfc-4e37-a146-13d134a6462a | 100% passing 37.5mm sieve
| note | 9481c966-63dd-4ef7-8d37-07c3b2b0a314 | 5-40% passing 0.075mm sieve
| note | 4d547f2c-105b-471b-9005-81acb5474e9b | PI (Max) = 20
| textbox | f909e1e1-8ca8-4aae-b1e7-54dc8b4f3325 | Enter: TeamBinder Material Approval number
| note | 671e5f00-1b0c-4c6d-93e6-90f2f1914b49 | METHOD: Document Review
| note | 6773928d-54a9-4b1c-b823-db360f5dd417 | FREQUENCY: Each different type of embedment material
| note | 4cca804c-b204-4782-87d2-bfbce03e1f12 | CATEGORY: IP
| note | 3211fa16-67b6-4a06-8b64-509e80be2e0a | RESPONSIBILITY: SE
| note | bd3a4f3e-92b0-4975-b93b-e14b1307471e | VERIFYING DOCUMENTS: Material Approval Number , Attach Delivery Dockets
| textbox | 7c026ba5-cae2-44d2-ad0d-e5d4509272de | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out/Conformity with drawings
| note | 45ff5b3f-a1cb-4184-9a80-9e268e99ca81 | REFERENCE: VicRoads Section 701.10
| note | 7167b593-4ab7-457b-8636-e68e64a510e7 | ACCEPTANCE CRITERIA: The Contractor shall set out the drainage work in accordance with the drawings
| note | 06c468e7-5654-44b6-a93f-54a79b44918f | The culverts constructed shall be constructed true to line and level.
| note | 9a88224a-0ca9-4599-a0b1-3bf96bed8db7 | Where it is necessary to modify the line or levels of drainage lines shown on the drawings the Superintendent shall be notified of the proposed design change prior to excavation for the drainage lines. The design change notice shall include certification by the designer that the change complies with the design requirements.
| note | 35459018-ec33-48c4-9ff7-42fcc004f96e | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
| note | 081b7591-371e-4d26-863e-37a3e305d807 | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
| note | d18f258a-5e4a-4767-8b74-698613864bfd | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
| note | fa6a1904-5a28-4a88-8d7d-dbd304e35cac | (c) invert level of pipes at pits ±50 mm
| note | 788cf4a4-fd2a-4299-ab44-076d5244fcb4 | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
| note | 57e499b7-3bb5-4bd0-8848-ad16bdc68bf8 | METHOD: Measure , Visual
| note | 45e29f54-bd1b-475b-b866-e1d031c3843a | FREQUENCY: Each element
| note | fe42aa09-754c-456b-853b-b1c3e501c3b6 | CATEGORY: HP
| note | eb54977c-abe6-4751-8c21-e3058ebff8a6 | RESPONSIBILITY: Surveyor , SE
| note | 3e9fa8ab-cd69-47c7-9079-0125999e881a | VERIFYING DOCUMENTS: Attach Survey Report , Attach certification from designer that the change complies with the design requirements
| textbox | 3e93f466-eccb-4c15-941a-4c1b5fa21f84 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Minimum Bedding Depth
| note | 1197d07b-7d3a-4c9e-bd33-065d835a0502 | REFERENCE: AS/NZS 2566.1:1998 Section 3.2.2 (Figure 3.1)
| note | 9d605a50-9663-4413-bc48-6579fd6e1032 | ACCEPTANCE CRITERIA: Bedding depth shall be a minimum of 100mm in a trench where the diameter, D is greater than 150mm and less than or equal to 300mm
| note | 1dfef30c-16e9-479b-94c2-667e1b23e8b8 | METHOD: Visual
| note | 3509accf-ea0a-472b-963b-e9de44d2b3e0 | FREQUENCY: Each lot
| note | ea8dbc16-e03e-4702-bc26-53a00065b81f | CATEGORY: IP
| note | bba3fbdb-1e5c-4507-af7d-92f923c587a2 | RESPONSIBILITY: SE
| note | 51d14386-0703-4307-95a8-f0ae459ded09 | VERIFYING DOCUMENTS: This ITP
| textbox | 82547219-b250-448f-8fd3-1a2e575269a3 | Date Completed:
| checkpoint |  | 4.2 Minimum Embedment Width
| note | c47ecfc1-30f6-4f1e-9f37-5ccfd6c370c3 | REFERENCE: AS/NZS 2566.1:1998 Section 3.2.1 (Figure 3.1)
| note | f2070eb7-6d86-4a29-bd15-50b9d7e48073 | ACCEPTANCE CRITERIA: Width of embedment shall be a minimum of 150mm in a trench where the diameter, D is greater than 150mm and less than or equal to 300mm
| note | 4e47548d-697b-4468-a0bd-0a2bfa6c8cde | METHOD: Visual
| note | d41c120a-fdfb-414e-a298-8d4517448a7b | FREQUENCY: Each lot
| note | 223abcfe-8afb-4f7d-8305-b2d2bdd3b351 | CATEGORY: IP
| note | 8671f2a3-1d4c-420a-8d52-084514dcb336 | RESPONSIBILITY: SE
| note | 55c08cde-1c6f-4de8-b73c-9b5834f5a554 | VERIFYING DOCUMENTS: This ITP
| textbox | a1601024-3dd1-4f68-b1ab-360beeb4f751 | Date Completed:
| checkpoint |  | 4.3 Minimum Bedding Overlay
| note | f712150e-0494-4d53-bb55-68c2a606cfcc | REFERENCE: AS/NZS 2566.1:1998 Section 3.2.2 (Figure 3.1)
| note | 491a2394-ce69-4297-90ac-2006b98d5e15 | ACCEPTANCE CRITERIA: Bedding overlay shall be a minimum of 150mm in a trench where the diameter, D is greater than 150mm and less than or equal to 300mm
| note | 4ab0be5d-622b-424a-8da3-1fb6d7646288 | METHOD: Visual
| note | 9f73252f-4b01-4b50-bbce-6831bf6e84e5 | FREQUENCY: Each lot
| note | eef6abcf-6a00-4d0f-9708-3283059d6861 | CATEGORY: IP
| note | 3f70223d-1ffc-49ad-86a9-c95d7fe0f890 | RESPONSIBILITY: SE
| note | 5daf9da7-3bfb-434a-ae5c-75635d0a50b4 | VERIFYING DOCUMENTS: This ITP
| textbox | 052d97d0-483b-4c5b-9eac-a22f9e1a231a | Date Completed:
| checkpoint |  | 4.4 Assembly of Buried Flexible Pipelines
| note | 91113aac-a584-475e-b215-aeb85d81946b | REFERENCE: VicRoads Section 701.22
| note | bb6a8d7a-3de0-483e-84b4-7932304d31dd | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied by the Contractor shall be assembled in accordance with the manufacturer's assembly instructions.
| note | 122324c0-3f70-4d03-8e0a-aff4c56b46a0 | Where sections are supplied free to the Contractor, the following will be provided:
| note | a25c9c15-5b38-4faf-83ea-f0359c0473ca | Manufacturer's Assembly Drawings
| note | cd80cdff-f4a5-4122-8dbd-96cde59e3f14 | Schedule of Parts Supplied
| note | 1057ec1d-9825-4a65-9672-b1d8ef9e537b | General Assembly Instructions.
| textbox | aea3ae2e-4b7f-4504-97b7-3a22a811dfd6 | Enter: TeamBinder Material Approval number
| note | e4ae1b8f-ef34-4dc1-8c7e-de064337973c | METHOD: Visual
| note | bae63706-c2b5-4e85-9605-3c2d445484fe | FREQUENCY: Each lot
| note | b7f1955e-0aab-4aa9-a430-94cfd7a73aa4 | CATEGORY: IP
| note | 5fcf36e8-8a99-4726-b4f9-178fa1e8d8e7 | RESPONSIBILITY: SE
| note | 9501b748-ec3d-4ce0-a606-d17d7c5e553a | VERIFYING DOCUMENTS: This ITP
| textbox | c61265ee-5f9f-44c7-b746-260c94cdeb17 | Date Completed:
| checkpoint |  | 4.5 Location of underground drainage
| note | 14b06736-8934-4982-b835-cdd8d19b0f86 | REFERENCE: VicRoads Section 701.10
| note | ac3b7fd0-059b-4154-9d57-755717ba0c8a | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts.
| note | 80b565cf-0986-4443-8ef3-2081885e39d5 | Attach: Survey certificate
| note | c79bcd65-4ff5-4f3b-b84b-efd21befae1f | METHOD: Measure
| note | 81302814-e571-4885-857e-53601f7eb63c | FREQUENCY: Each run
| note | 302ecdce-8e3e-49c6-ab21-33096cb63dbc | CATEGORY: HP
| note | 46663c26-842b-4ec9-84b9-66b1351d35fa | RESPONSIBILITY: Surveyor/SE
| note | 7a2dcb9c-6854-488d-bb70-011fec091815 | VERIFYING DOCUMENTS: Attach Survey Report
| textbox | 96683b8d-45bc-45c8-aeb7-8f6ec72567c0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.6 Placement and Compaction of Embedment Material
| note | afeaab3d-7354-482b-b97c-29e2a8a5a783 | REFERENCE: VicRoads Section 701.20
| note | 63485840-d184-4a5a-976b-0bbfd6c70a9f | ACCEPTANCE CRITERIA: Bedding material shall be placed in layers not exceeding 150mm loose thickness
| note | 3fe4dbaf-d825-4148-8899-3937af95272f | Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
| note | 832d32eb-0381-42a4-872e-ff1963bfa1d5 | Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three.
| note | e7a0a3b5-79af-4e10-bbf3-811c88146180 | A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
| note | 4484cd8c-f77a-4c38-bccf-0c66224a17cd | The calculation of density and moisture ratios shall be based on standard compactive effort.
| note | 0bf542a6-c976-4061-9f29-a7686cc68ebc | Attach: Geotechnical Report
| note | 81fe4ee6-5d69-453a-8ef6-4c63be8f34f0 | METHOD: Document Review
| note | 8cf6ec5c-29ea-4543-9bcb-7c0331fd4be0 | FREQUENCY: Each lot
| note | 705bf196-821e-49f6-88de-d52e6233d4d7 | CATEGORY: IP
| note | fbd3bfe9-a22c-42d3-8843-2a273ea159c1 | RESPONSIBILITY: SE
| note | f8f5220d-ef03-466f-b399-5b47fd53903e | VERIFYING DOCUMENTS: Attach Geotechnical Report
| textbox | 1849ee77-cb10-4180-a425-eca101fd9c6d | Date Completed:
| checkpoint |  | 4.7 Minimum Cover
| note | a68088a5-37d3-45d0-ae22-50386b7fbaa7 | REFERENCE: AS/NZS 2566.1:1998 Section 3.2.5
| note | d08bb0a5-2736-4549-b5df-7358c205c4e3 | ACCEPTANCE CRITERIA: Minimum cover to flexible buried pipe not subject to vehicular loading shall be a minimum of 0.3m
| note | abbaee30-eed9-400c-a228-69d942aa061a | METHOD: Visual
| note | ce901ee4-c25a-4bc0-8c8c-2582585b029f | FREQUENCY: Each lot
| note | 7a0c2b29-b01a-4c68-b129-069255b6e7c7 | CATEGORY: IP
| note | 723ea96e-8277-4afa-bb0e-a0c8639572d6 | RESPONSIBILITY: SE
| note | cb4b2e88-01ac-4c7a-a888-2fe26154c740 | VERIFYING DOCUMENTS: This ITP
| textbox | a5dd6a7d-1342-47c4-99da-b8eaeb6b8a54 | Date Completed:
| checkpoint |  | 4.8 Compaction of backfill material
| note | 880899b5-8172-4e00-91f4-96a379dcd9a2 | REFERENCE: VicRoads Section 701.20
| note | 2a8cd5a9-7777-4518-817a-80dcdc7880ad | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
| note | 36281954-bee3-4284-ae5e-674364a09918 | Material of nominal size 40 mm or less after compaction;
| note | e2cc703f-784c-40a5-a3b4-c34279f24a4f | Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
| note | 4d7c6fe9-7c0e-45c0-822e-5e8485632ad3 | Material of nominal size greater than 40 mm after compaction;
| note | d256a829-bdf2-4d1d-be4a-9a80987cb8e0 | Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure.
| note | ee45c114-2177-477e-8ee6-18a5250b4adb | Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
| note | f306fdb0-db84-4c33-b608-cfdd531a3aaa | Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three.
| note | 48f3c935-65bb-48d5-aa0f-0bb335fc9d38 | A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
| note | 7fc0722d-9057-495c-a3c2-65862b7f6b5b | The calculation of density and moisture ratios shall be based on standard compactive effort.
| note | 6ad98bf6-2662-4ffb-a4ac-6118df438184 | Attach: Geotechnical Report
| note | 202839f7-4b3c-4cdb-9fed-afdb8dbe112a | METHOD: Document Review
| note | a30045c4-69d1-4e49-970a-63c2f2cbda56 | FREQUENCY: Each lot
| note | 7e1c1bb3-3564-4755-8676-65045b7fac80 | CATEGORY: IP
| note | cc1c4c11-0cf8-4fb3-a21a-a268561524e1 | RESPONSIBILITY: SE
| note | 5230e666-813c-4f10-813d-78ce7e4a0486 | VERIFYING DOCUMENTS: Attach Geotechnical Report
| textbox | 5953466a-b6b7-484f-8c7f-22548e420291 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 As-built Survey
| note | d9ac1957-3fcd-4613-b93e-cace42718cf9 | REFERENCE: IFC Drawings
| note | a965cfe1-0e44-49bd-ae82-fb134e217079 | VicRoads Section 701.10
| note | bab87db4-93a9-4695-8358-4643c1386c40 | ACCEPTANCE CRITERIA: Provide As-Builts survey of installed PVC Pipe
| note | cd7476b9-a91f-437a-a75f-b214d7ab03fc | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
| note | cc0421cb-3cba-48a3-94b5-3c1b8e411ade | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
| note | 5bbcf547-e3cc-4a33-82a5-33960b45a12a | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
| note | bf5e63f2-a0de-4a68-a74f-04ff07785747 | (c) invert level of pipes at pits ±50 mm
| note | 261b9c2d-c128-42c7-af46-5df82ab8dfc1 | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
| note | 5201138e-3692-4d59-9c3b-fe93eec8afc2 | The location of each run of underground drainage shall be recorded progressively on the Contractor’s as constructed drawings.
| note | 4cbf46c5-012a-4bf9-a435-4bbea11bbbc1 | METHOD: Document Review
| note | 604f5c35-dc7f-483b-a023-57a00a9bece0 | FREQUENCY: Each element
| note | 70440da0-a84b-4e7b-8ecc-2c5a47eb2cb6 | CATEGORY: IP
| note | 7beb27ca-0811-40f7-94bb-6aeddb852c2c | RESPONSIBILITY: Surveyor , SE
| note | 84fae3ee-3134-472e-a26f-ed3ffee10dd4 | VERIFYING DOCUMENTS: Attach As-Builts Document
| textbox | 7816aa57-2cdc-428c-9f2a-b7acec534af2 | Date Completed:
| checkpoint |  | 5.2 Inspection of Drainage Lines
| note | 8d8f813c-0a3c-4699-a642-dde5c2d5cfce | REFERENCE: VicRoads Section 701.30
| note | 67032fa1-883e-48e8-9776-072550716f1c | WSA 05 2013 - Conduit Inspection Reporting Code of Australia
| note | e53a7bbe-f66a-4769-9a82-0c2f51d5ac3c | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
| note | 60862646-4b15-4227-b1b6-2d66c69cf834 | Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
| note | f7e6f1ee-c2bb-4086-b602-b2f0ff0a0ca9 | The report shall be provided to the Superintendent, with a copy of the CCTV record including any video recordings and a summary of the location of any defects detected by the survey.
| note | 53d866ee-62d9-415c-8038-f16d365b4c64 | Any sections of damaged pipe or box culvert which do not comply with the requirements of Clause 701.31 shall be removed and replaced.
| note | c3086e2d-4810-4106-8e65-5d2eeb5aead8 | Where approved by the Superintendent defects shall be repaired in accordance with the requirements of Clause 701.31 and a further CCTV survey shall be undertaken to verify correction of the defects.
| note | eb9b8ff9-e112-4118-bf65-bde486791961 | Inspection of existing drainage lines shall be as specified in the drawings and specification.
| note | 52406ebf-c2ca-4c36-a5fa-a9e9a15e309f | Attach: Inspection records
| note | 1b27e36b-b2cb-4304-9a01-11efab23fa4b | METHOD: CCTV Document Review
| note | 3fc6ad42-1333-4644-baaf-3b89925b1596 | FREQUENCY: Each lot in its entirety
| note | 0c4e794e-a90c-4bb7-af69-3bb802a45f4c | CATEGORY: HP
| note | a3acf2af-5635-47c0-ad17-09878428ca4f | RESPONSIBILITY: SE/NA
| note | 42dc25be-57de-48a2-b115-63a34551a16f | VERIFYING DOCUMENTS: Attach CCTV Inspection Video
| textbox | b131a352-4dfc-45b2-b61a-91e569917f01 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.3 Repairs to damages
| note | cbcdd113-9762-4d08-a368-d111475ed372 | REFERENCE: VicRoads Section 701.31
| note | c7801089-7d90-4452-bc01-8e2af650d6d9 | ACCEPTANCE CRITERIA: Flexible buried pipes which exhibit defects or are otherwise damaged prior to laying and backfilling shall be rejected.
| note | db8d3633-8b5c-44ff-8678-a2baeb5ad8d6 | Where inspections after backfilling identify any defects, such pipes shall be removed and replaced, unless the Superintendent approves repairs to be undertaken in accordance with the manufacturer’s repair procedures and materials.
| note | e3cc3d5c-5cbd-41f9-be55-ff8539ae9d08 | METHOD: Visual
| note | 765767ae-8f81-4d17-a7cd-2e6f94926d93 | FREQUENCY: Each element
| note | 9de02ff9-ca71-47ea-aa11-2f480cecdf84 | CATEGORY: HP
| note | dbeb0185-28c2-4790-9407-57069f6246f6 | RESPONSIBILITY: SE/NA
| note | fa9022f2-7782-49a5-bee6-7096fb946c64 | VERIFYING DOCUMENTS: This ITP
| textbox | cd9b3b1c-96ae-476c-862a-2d3c0f4673e7 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.4 Non-conformance Report (NCR) Closure
| note | a8e7c68d-0c8e-47c5-9ada-0eadbb8ae4cd | REFERENCE: MRPA Quality Management Plan
| note | 06bc6443-1fdd-482a-9f15-9958aa728b24 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 072d3f7a-ebd3-40e2-bc9d-cdaa012eaee2 | METHOD: Document Review
| note | 3bc92c48-f29c-4251-a5a0-1251b4bc2980 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | bd4f7706-8b96-4f1b-bcd9-e88d1b9ab9b2 | CATEGORY: HP*
| note | c4019435-c630-47dc-bf23-6c91f3499304 | RESPONSIBILITY: SE/PE/SPE
| note | c7e07753-a7ea-418d-bf6d-01827a2decd7 | VERIFYING DOCUMENTS: This ITP
| textbox | 7568505e-4b68-4d4f-a052-6b905985f3d9 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | cf812140-bfc5-4cb9-a922-161c4607920c | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | ea98aa25-54fd-4a0f-ac73-e19a881cb3f3 | Name:
| textbox | 37bfd66f-fe80-4f4a-9bd5-1f52a5986c19 | Position:
| textbox | e0ba3816-bdb9-41b5-8cad-50146a6cabaf | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-RAIL-Track Construction Rev 0 | itp | ITP-Rail-Track Construction Rev 0 | ce90d133-4e5a-44d8-ad7d-e9ddada1357e
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | f8f30f2a-cff2-4c6d-b81e-394d4435e661 | Document Title: ITP-Rail-Track Construction
| note | 1b48dbf2-1ff3-410a-997f-297a8e2af0f0 | ITP Description: Track Construction
| note | 2dda0461-97d3-47c3-8a76-2e6552955f37 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
| note | 80882fef-07a0-46f4-90b4-e5720f7f724c | Discipline (e.g. CIV/STR/RAIL): Rail
| note | c532c033-4502-4d1c-8ffb-991fc50b3f64 | Revision Number: 0
| note | d43898f4-4236-4583-81d4-3c2c4ff49753 | Revision Date: 1/10/2020
| note | c6ec85a5-c3d7-438b-abaf-2781d1b087cc | ITP created by: Mathew Holm
| note | 4cab7486-b580-4a49-9eb5-230e40136d03 | ITP approved for use by: Romualdo Magpantay
| note | df4eb6e1-b892-4bb1-b0b0-bf28627a3574 | 1.1 L1-CHE-SPE-316 Concrete Sleepers
| note | 756c2c3a-a3c2-4e3b-a8a7-ccc10b5e3079 | 1.2 AS 1085.1 Railway Track Materials – Part 1: Steel Rails
| note | 52942988-8201-4aec-b5f0-4a7f38abe418 | 1.3 L1-CHE-SPE-003 Heavy Rail Construction Tolerances
| note | 32b7f17e-60b7-4322-9d74-520bd708d423 | 1.4 L1-CHE-SPE-064 Ballast Supply
| note | d0b9fff2-4745-414a-8d39-9b37a25a2650 | 1.5 L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | 9ec5c507-9b77-4802-a372-f43f36fcd31b | 1.6 PTC Heavy Rail Track Construction Standards Drawing F598
| note | 4cabb8b9-c5b6-4e28-b77f-9f7eff404648 | 1.7 AS 1085.20 Welding Rail Steels
| note | 73027814-a95f-48b2-87d4-891921cb4bbb | 1.8 Evans Road Package 70 Design Drawings
| note | eb0bb8f2-2f93-4e60-9278-aded3a12385f | 1.9 L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan
| note | f4425cf0-67fd-4fcd-b6c5-e4250bb49c20 | 1.1 L2-TRK-PRO-028 Requirements for Welding Track
| note | 5ae597a1-4ab3-463c-86c4-dafe1d67eb3f | 1.11 L4-TRK-FOR-074(2) New Weld Return Form
| note | 04ca0389-a4e8-48ce-8741-d3f8b744e03b | 1.12 Welded Track Management Chapters 1-16
| section |  | Preliminaries
| checkpoint |  | 2.1 Obtain and submit Material Certificate of Compliance for Track Materials; Track Rail, Track Sleepers, Track Jewellery, Geofabric, Triax, Class 4 Fill 19mm Aggregate, Ballast 60mm Aggregate, Welding Kits, Welding Crucibles
| note | 51cac508-3039-48dc-b50e-2b2db9403b50 | REFERENCE: IFC Drawing
| note | 564ec3e4-f8ed-4790-bdd0-0e455f276093 | Track Construction Site Mudmap
| note | c13156a4-4eb5-49c0-93f1-2b650a4e4c61 | Bill of Materials
| note | dd9ad706-990d-42a9-a79a-bfaecd23eced | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
| note | 00df2d21-994d-44e9-86b2-11a6f969b037 | Attach: Manufacturer Certificates of Compliance
| note | 924a54c4-1f34-480e-88ce-427b1cb3c0e7 | METHOD: Review Document
| note | a63e8fd7-1232-4cd5-b192-53d32febb186 | FREQUENCY: Once
| note | a3c05dda-4723-4da7-8ddf-c47743ea92b4 | CATEGORY: HP
| note | 732d8006-67a9-421a-8805-1ddb4c6c9dc9 | RESPONSIBILITY: Track Supervisor Project Engineer
| note | e7882f6b-4645-422a-8e66-76b932be583f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | ad9ee6a6-7834-4869-ba05-c36cf37a471b | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Submit Welding Procedure/welding qualification welders Record
| note | 265dc96a-9107-47f9-9b05-591a1bb01255 | REFERENCE: L2-TRK-PRO-014 Welded Track
| note | 0ae3d7e0-4654-45dd-87a6-d719fb8252ba | AS 1085.20 Welding Rail Steels
| note | 88fc5d66-77ae-4904-bc8f-008b7e6e2461 | ACCEPTANCE CRITERIA: Qualified personnel & welding accordance with manufacturers specs.
| note | 76a8ed88-c838-41bc-8b40-883fb53266df | METHOD: Review Document
| note | 438853b4-fc99-483a-a710-7d38d3e79425 | FREQUENCY: Once
| note | 248f85cb-d562-4174-abd7-4afead6f8bf9 | CATEGORY: HP
| note | 34cf63db-84c7-4882-aa3d-130503f0d894 | RESPONSIBILITY: Track Supervisor Project Engineer
| note | 3ee1be49-91e9-4e66-aa21-245cbcb71311 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | c4293e80-065b-4568-a98b-98995e50ee04 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Track Tamping Travel Network Path Circular
| note | e4eed68f-dc4d-4337-a613-2ffb9bce526e | REFERENCE: MTM Access Resource Management System (ARMS)
| note | ab9a8ec5-8a27-4ee5-ad17-43521683a040 | ACCEPTANCE CRITERIA: Approval of Travel Path
| note | 7aa34334-3e0d-4a92-9231-5e99663a733d | Attach: MTM Approved S'Circular
| note | 9c48c98a-be0d-4e35-9a6a-288e8931cdbb | METHOD: Review Document
| note | b750c0b5-e014-4f43-9786-a13f1d6bb333 | FREQUENCY: Once
| note | 2ead369a-2765-4506-b795-a77f4e0bf03b | CATEGORY: HP
| note | 6a433739-3924-48e1-9a9a-74022bf02fe4 | RESPONSIBILITY: Access Planner
| note | 85214a42-45f0-40ff-935b-e8a1d32e39b8 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b60142ad-6a07-4612-a8cb-34dad5486437 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.4 Inspect supplied items upon delivery
| note | 1b9208c6-effc-4244-9822-22ddc1ef396d | REFERENCE: IFC Drawing
| note | 1bd339dd-a8f5-4021-b170-ab048ba88e6f | ACCEPTANCE CRITERIA: No damage or rust on components
| note | e37e88f2-abd4-4bb1-8406-aa31c11a36b3 | Validate total number and type of components matches drawing
| note | 28a643c7-f161-4d3b-990b-9df6f5fd9457 | Attach: Photos on site;
| note | 8d22ddb4-f5f3-46ac-8f7c-b18feb6060c4 | Track Rail
| note | dfb4f24d-f8cf-4b94-9f9a-919bb89c84c5 | Track Sleepers
| note | 5f1be02c-66f2-46ca-a12d-cee242138b9f | Track Jewellery
| note | da5ca2d5-4eda-487b-8c59-d59df1085eff | Geofabric
| note | 74077734-885a-40de-b455-f060348fa120 | Triax
| note | 6ab0a1e0-4588-45ae-a3cf-90b0f2b2a2cd | Class 4 Fill 19mm Aggregate
| note | 0c67f0b8-a7a5-4e1f-a192-49422e87ce9c | Ballast 60mm Aggregate
| note | 4df97448-7eef-4bb9-b35d-609f92ffe4d2 | Welding Kits
| note | f3c03025-5529-4f72-a8f0-26c62ad01061 | Welding Crucibles
| note | 73d46a61-2f03-44d5-9ff1-e0e9649d37fb | METHOD: Visual Measure
| note | d4e2d1db-9598-4114-b4c5-ca2b8bfe811f | FREQUENCY: Per delivery
| note | d7379b56-2edb-4630-9800-5e7ae5e2d537 | CATEGORY: IP
| note | 2139e4fa-089d-4c11-a3bf-2a8eda4b46cf | RESPONSIBILITY: Track Supervisor Project Engineer
| note | 3771e23c-8da6-4a22-905c-3c4bf95147f3 | VERIFYING DOCUMENTS: Material Inspection Report
| textbox | c56453cd-6da9-4d15-b2b7-b7ac46e31b30 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 3.1 Earthworks ITP/Formation/Ground improvement/capping layer
| note | 8a968423-7795-49f8-ada5-924f10dbd106 | REFERENCE: L1-CHE-SPE-178 Engineering Specification Earthworks & Formation Specification
| note | da571ee1-a17c-4bce-8c13-76af9979321d | Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
| note | 75291aeb-cd6d-4f78-8ce2-2bc3e9b4c60b | ACCEPTANCE CRITERIA: This Item will be completed under the checklist Earthwork/Ground improvement
| note | 58cc258f-20a2-480a-9461-f115ce90aa29 | METHOD: Visual Measure
| note | 183df5f7-f109-4b9a-b020-f1c595106550 | FREQUENCY: Once
| note | 20078e59-6488-454c-aa1d-67e940289ff8 | CATEGORY: IP
| note | 4c218745-73e4-4e0e-aa81-279a34fd6ae7 | RESPONSIBILITY: Track Surveyor Track Supervisor Site/Project Engineer
| note | 38437a37-6f05-4940-99f0-bfd70cc06080 | VERIFYING DOCUMENTS: This ITP
| textbox | a35ac486-003c-4a76-9b9a-374bbe7ed018 | Date Completed:
| checkpoint |  | 3.5 Installation of Bottom Ballast
| note | f6a99638-1aaa-4b5c-a45e-8de2dad05f91 | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
| note | 6740ca0a-e7da-469f-9314-0f9d40f2b6f7 | PTC Heavy Rail Track Construction Standards Drawing F598
| note | db788d98-938d-4bed-81ab-a1f5bc23db3e | ACCEPTANCE CRITERIA: Overall Minimum 300mm bottom ballast depth
| note | fa4bb694-e088-40ac-8876-c72570e9fcc1 | Ballast to be placed in 150mm max layers.
| note | 5fe139c5-d035-4c08-8f86-b85885b9cff6 | Bottom Ballast to be left 20-40mm below final design level – Tolerance (under sleeper) -0mm, +25mm.
| note | b7e1d80f-0135-4298-9c13-c5f361346457 | Layers rolled 10 tonne smooth wheeled vibrating roller with minimum 3 passes
| note | f9263448-a96a-4f89-b6db-f668ee1cbb01 | Attach: Survey Measurement
| note | 4217e304-849d-4f5c-a1c5-9e760f0b34fc | Attach Site Photo: Installed Bottom Ballast Layer
| note | 27b4d2e5-3007-4980-a6a6-5d006066940d | METHOD: Visual Measure
| note | ca25525b-e5e5-443e-a723-82298d37ec0c | FREQUENCY: Once
| note | 0ee1dcc0-6597-4bc4-8c16-374716db672a | CATEGORY: IP
| note | 7a1aedfd-54ad-4929-9079-b839c1cbee81 | RESPONSIBILITY: Track Surveyor Track Supervisor Site/Project Engineer
| note | bfdd6385-6236-42bd-a00f-f84fe45d4bab | VERIFYING DOCUMENTS: This ITP
| textbox | 24347e1e-4b75-464c-88f8-b8bf4d5ef78b | Date Completed:
| checkpoint |  | 3.6 Laying of Sleepers
| note | 728e976f-e621-401f-9cc6-5fa9a6f087f7 | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
| note | c4030808-4dd2-4f7e-87f5-c71ec2af9336 | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | c877b8a7-ed25-4b9e-9a37-634dc01f3757 | ACCEPTANCE CRITERIA: Sleepers Square at nominal 685mm ±25mm for open track
| note | 8cb11af2-36d0-482f-87c8-49e24cf7bb48 | Sleepers Square at nominal 600mm ±25mm for under RRV pad
| note | c04ef8c3-7072-4e67-b811-db78588aa42e | Attach Site Photo:
| note | 04315c0f-cc37-45f4-85d1-99e6598cda4d | Laid Sleepers
| note | 73cac4c9-5ca7-440c-8ac9-439632fddc82 | Sleeper Spacing Measurement
| note | 06b5da96-6e5a-416d-be9f-23099fb57c6b | METHOD: Visual Measure
| note | 3951a1f2-d084-4d3b-9f1d-50b9e9d6d441 | FREQUENCY: Once
| note | 907a7f2d-8154-40bd-8448-185f25975413 | CATEGORY: IP
| note | 72f3cf3e-e63e-4b0b-8c24-345f5f020b12 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 09cc4917-0c45-4df0-b48f-ccb50aaebc12 | VERIFYING DOCUMENTS: This ITP
| textbox | de98f145-7d47-4343-8b9a-07ac5549c5eb | Date Completed:
| checkpoint |  | 3.7 Rail Installation/Clip Up
| note | 5a570371-57ec-4c2e-bfd2-7acbade31202 | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
| note | 49341872-3366-41bc-bbaa-021f03199902 | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
| note | ec6f4692-de46-450e-a475-e4ba16f3604d | AS 1085.1 Railway Track Materials – Part 1: Steel Rails
| note | 2cc2a231-0243-4395-af28-9742dc8936ff | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators
| note | 874bf5fb-9a52-44ad-ac05-61307c88f4f5 | All rail fastenings installed
| note | 6e127860-9377-498d-aeaf-e36922f78c29 | All Rail Ends, positioned midpoint of sleeper bays +-25mm
| note | 500870d9-aff5-440b-aff6-9d652ea63c77 | New Rail lengths minimum 20m
| note | ec0a912e-19c0-4aa4-8a8e-bad1e85bb179 | No Existing Welds Within 4m of new rail tie in point
| note | b2610c80-154e-4263-a78c-8e86c4cdd9bf | Attach Site Photo:
| note | 4bdd343f-b781-4830-834b-5624e6d9c937 | Laid Rail
| note | 7cb1cd49-88eb-48bb-aeef-93c57ed92131 | Rail Joint to existing weld measurement
| note | ecb8dfeb-5969-4f5f-a534-bc7366185240 | Weld joint between sleeper bay measurements
| note | 9b5eaeaa-cd4a-4a2c-8313-5f3739b0af42 | METHOD: Visual Measure
| note | 64754d1c-8be2-4acb-b83f-2c515281963f | FREQUENCY: Once
| note | 48fe3278-c28f-4794-8836-dc4d13f29713 | CATEGORY: IP
| note | 15f0c698-63b4-4743-9eef-87dc274cf204 | RESPONSIBILITY: Track Supervisor Site/Project Engineer
| note | 1477a5a4-ae97-4ee8-b371-228d2e89aacf | VERIFYING DOCUMENTS: This ITP
| textbox | ffad57f4-efe0-477e-b559-c0013dbd5129 | Date Completed:
| checkpoint |  | 3.8 Track Tamping
| note | 8d2183d1-b89a-4801-8f42-cdd36beddba6 | REFERENCE: Track Tamping Design Drawings
| note | 66d78d7a-98f0-48a3-aa18-a4cddcbd7eea | MRP-056-C-AUR-DRG-70-LBK-CPW-0025
| note | 456ad63a-a3b2-426c-8726-75e7c1c753cb | MRP-056-C-AUR-DRG-70-LBK-CPW-0027
| note | e2aeedb7-57a1-4db2-ada5-0f12d5619997 | MRP-056-C-AUR-DRG-70-LBK-CPW-0028
| note | b642f537-f337-458d-a4d2-3f372a5e2f37 | L1-CHE-SPE-003(1) Heavy Rail Construction Tolerances Table 1
| note | 4954be49-bf8f-486a-b7ff-c965874936d3 | ACCEPTANCE CRITERIA: Tamping Ensures Track Geometry Tolerances are not breached;
| note | 2df42e6c-0857-4973-945a-55e7a22087b7 | Gauge +3 / -3
| note | 3f038f51-6e14-4b1f-a4ea-7ff24350dcef | Gauge Variation in 2m 4
| note | 80eafdb0-c055-49e7-960c-0a0aedcfd1e5 | Line (10m Chord) +4 / -4
| note | e01b981d-0df8-4f38-8d4e-29ae16bcddc9 | Twist (3.5m Chord) +2 / -2
| note | 77f985e0-4186-465d-baec-96362180d624 | Top (10m Chord) +5 / -5
| note | a1d23b1e-9867-4a23-b1a8-ef4c88d576a3 | Cant +5 / -5
| note | 5bdafbb9-87d9-4d2b-8b63-ca5d3c912211 | General Alignment +15/ -15
| note | 2b5a2058-83fb-424e-96dd-27035cd08290 | Survey measurement of RL of top of rail head
| note | 928820a1-2b65-4a4a-a73c-0d7a5b1187da | A minimum horizontal clearance of 3.0m from track centreline to structure.
| note | cf08d156-d312-4272-a136-60399514303b | Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
| note | 0e248eaa-f1bc-44b8-ac06-38fdaf7a1abb | Attach;
| note | e20afa1d-4701-4e43-afd6-11be7755fa49 | Tamping Geometry Recording
| note | 53e41c0d-5a4e-4f87-81bf-334af66bb571 | Survey RL measuring sheet
| note | ad856dab-3cb5-4fc4-b7dc-59758c66f200 | Height and Stagger measuring sheet
| note | 1e940e60-3d12-4549-ba9c-4eea938b5f54 | Attach Site Photos:
| note | 8e6b3222-301c-4b10-a979-272cc9f18082 | Tamping Activity
| note | ad964b90-f664-417f-aa40-b28c6e079cd2 | Overhead measuring Activity
| note | 32bf39f6-30c3-42ba-b75b-763bc370e49b | Structural Offset Measurement
| note | cdc8f437-d422-4336-a8c0-5a866ad30af3 | METHOD: Visual Measure
| note | 828e1a38-b4e5-42e6-9a25-4b0443e2a2f4 | FREQUENCY: Once
| note | 11f85026-8aa6-449c-ae5f-7d4b9d242d0b | CATEGORY: HP
| note | 1c5a80d7-c084-495c-bb0b-6f16d3fae76d | RESPONSIBILITY: Tamping Operator
| note | 81feaae6-44b0-4b74-9dd8-422d9dfc5244 | Track Surveyor
| note | 928be37a-d37e-4fa5-843f-d233ad2e6ac8 | Overhead Engineer
| note | 04928cd0-5bd8-4a7b-9f6e-0de494dc8a81 | Track Supervisor
| note | f75ca4e5-872c-4164-bcfc-60696d1efe26 | Site/Project Engineer
| note | c987ddd0-7bc2-4e08-88db-b8f4c6db5a0f | VERIFYING DOCUMENTS: This ITP
| textbox | db846f47-020d-4dc9-adf7-4a0a9b7b4825 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.9 Regulating and Ballast Profile
| note | b8dd34fe-638b-4f04-a6cc-3ed7a8b83d8d | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
| note | c0cd50bf-3f1a-46fb-9931-052622ea99e2 | L1-CHE-STD-029 Earthworks and Formation Standard Section 13
| note | 2a9df466-02bf-4c8d-ae1d-4bbdfe82d8a3 | PTC Heavy Rail Track Construction Standards Drawing F598
| note | 1c285c82-a222-4e1a-833d-1898b4b48050 | ACCEPTANCE CRITERIA: Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter
| note | e31e3e5a-dbf7-4b46-8588-119e222f2b6d | No Ballast to be on top surface of sleepers or around rail Fastenings
| note | 7b8dd67d-e28f-4785-9778-fe43ed6e77b1 | Attach Site Photos:
| note | 28a91792-e236-4f54-b538-a55e6838969c | Ballast Shoulder Measurement
| note | f6a0f8cd-46e9-4498-9d80-766932445d37 | Rubber Panels free of ballast materials
| note | 71fbc656-94ea-4951-ad4a-c79e8daf143a | METHOD: Visual Measure
| note | 30db6cc5-b831-4dc8-b449-781c2c5d6171 | FREQUENCY: Once
| note | 6e629658-c9b3-4361-9a51-9b001c1db340 | CATEGORY: IP
| note | 1a121340-7e6d-4118-aa7f-f8900e88fd85 | RESPONSIBILITY: Regulator Operator, Works Supervisor, Site/Project Engineer
| note | c7fed342-17dd-4b47-ac63-948b4187e622 | VERIFYING DOCUMENTS: This ITP
| textbox | 7f2c32bf-36d7-41f7-ba91-6d6d10765d5d | Date Completed:
| checkpoint |  | 3.10 Aluminothermic Welding
| note | 23efbdf1-d8a0-4d8f-97b9-6ad3735fb7e7 | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
| note | 35e9e93b-b544-41d3-b81e-38e85fe62449 | L2-TRK-PRO-014 Welded Track Management Manual
| note | e9575865-a371-44dc-bc9d-fb6905dbd572 | Chapter 11 – Rail Welding Process Section 4.9
| note | 5b4caee2-e444-4abe-98f2-63f8deacf8ce | L4-TRK-FOR-074(2) New Weld Return Form
| note | 1cbfb9cd-35c9-48b4-a5cf-e7efba2cda54 | ACCEPTANCE CRITERIA: Alignment inspection shall be carried out on each weld and record results.
| note | b44097a7-eb0e-4daa-b4d4-d5c2d80929fa | Horizontal Alignment ± 0.5mm
| note | 7da29f16-be3f-4452-9ef6-796013bee78f | Vertical Alignment + 0.5mm, - 0.0mm
| note | 835119f8-dcd7-4793-8d05-90c8be80ffa4 | Verify Aluminothermic welding carried out in accordance with AS1085.20
| note | d6ac40b8-7d27-4249-886a-0e667766ca5c | MTM New Weld Return Form Welding Section Completed
| note | 21b1d903-74a4-40b5-9b6d-19227c5dc853 | Attach
| note | f863a863-b39c-4337-b7cf-b1bc6af9b851 | New Weld Return Form (Weld Section only complete)
| note | 3a2f7ed3-28d8-4177-ba93-6d45aced1b11 | Attach Site Photos:
| note | 7def3cfe-6f62-4dfe-b04b-14320933ce1f | METHOD: Visual Measure
| note | 39726de6-11d7-4a2a-b4a6-2acac76628fe | FREQUENCY: Each Weld
| note | 19c3786b-49c2-4ad3-93a4-f98b6d489454 | CATEGORY: IP
| note | 87f65d69-0e13-432a-ae27-1f4c3e025ae9 | RESPONSIBILITY: Track Welder, Works Supervisor, Site/Project Engineer
| note | b0083d18-9ccd-43b9-b207-031f8f3e7ca3 | VERIFYING DOCUMENTS: This ITP
| textbox | ca54f299-6fe9-4532-837c-318492e3161c | Date Completed:
| checkpoint |  | 3.11 Track Stressing
| note | b306269e-1c98-4f30-9424-7e8e9128c4fb | REFERENCE: L2-TRK-PRO-014 Welded Track Management Manual
| note | c1cbe7fc-d4b0-40bb-be17-9601ea17345e | Chapter 11 – Rail Welding Process
| note | 0c85a709-fbd9-423e-b350-a97fcc6e6a05 | L2-TRK-PRO-015(4) Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail
| note | 934dcc60-ae17-44c3-a1e3-56cfe29568a5 | L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan
| note | 94550e67-abef-4348-b929-5e58db802cda | ACCEPTANCE CRITERIA: Stressing Rail in line with MTM Chapter 11 – Rail Welding Process
| note | 25c98aa5-9a8a-4c59-964c-5abf8e9f832b | Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
| note | dac58644-2450-408a-85a8-d01f2081f110 | Under Rail Roller Configuration: 1:10
| note | 3cc990db-52dc-4227-933d-be0bcdec7ae1 | Maximum pull length in one direction not exceeded; 900m
| note | 225b3f5b-89d0-4d8f-a184-74dafa311b6f | Reference Marks recorded pre and post tensing of Rail
| note | 2d8706a1-e257-41d9-8bca-23c628c94704 | MTM L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan Completed. Validation that SFT 38 degrees is achieved
| note | 64648202-9e38-4457-95ed-860c685e9893 | MTM New Weld Return Form Welding Section Completed
| note | ca48d57b-d263-4266-b6a7-16cfab94d16e | Attach:
| note | 94786d6e-b011-47e1-b1e9-5d87fa298566 | New Weld Return Form (Weld Section only complete)
| note | 6d01054e-cbcb-4cc5-8bcb-f9e6b4c607f6 | Stressing Restoration Plan (Fully Complete)
| note | 0d10efe1-d36f-4eca-a675-a0e8e598ac5c | Attach Site Photos:
| note | 24d66808-ef12-4e00-9c45-83eb89264568 | Stressing Activity
| note | 2f7bc85c-f220-4ffb-bfb6-ade4ae7b83c1 | Under Rail Roller Spacing
| note | 3a6fd3b1-4eb6-4c2b-98a3-2c0f58a09b3a | Before/After Reference Mark Measurements
| note | f3e00e50-73ae-4174-a1b2-ffb34a62787c | METHOD: Visual Measure
| note | 0d7fecd5-5666-4ad0-abdc-e9e60f3b89e9 | FREQUENCY: Each Restress module
| note | 2025a0fc-21e5-430a-ab31-1eb38e164a15 | CATEGORY: IP
| note | 7fbfcb97-cd4a-43ac-addf-23c38b3c31e0 | RESPONSIBILITY: Track Welder, Works Supervisor, Site/Project Engineer
| note | 16617f1a-47b7-4277-b4d4-2bfe7009e782 | VERIFYING DOCUMENTS: This ITP
| textbox | f84a3d59-b921-49ec-a4dc-746e98ba2676 | Date Completed:
| checkpoint |  | 3.12 Weld Ultrasonic Testing
| note | f3b833b3-b6c3-4f0f-a1cd-8874e3b6efd2 | REFERENCE: MTPR 031000-01(3) L2-TRK-PRO-049(3) Non-Destructive Hand Testing of Rail
| note | c45f8b07-9909-4ab4-9665-7d1899804936 | AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
| note | 5fb1b398-41a1-4568-86cf-82188c04ef4f | L2-TRK-PRO-014 Welded Track Management Manual Chapter 11 – Rail Welding Process Section 7
| note | 7997d7a4-23db-4a16-973f-9afa5f467397 | ACCEPTANCE CRITERIA: Ultrasonic testing to be carried out within 14 days and in accordance with MTPR 031000-01(3) L2-TRK-PRO-049(3) Non-Destructive Hand Testing of Rail
| note | 6c7798f8-d358-4e07-8809-879758ff535e | The cross section of the area of the head and web shall be completely scanned;
| note | 1ded24a3-1f6c-49af-bd47-56e69f66dc8a | The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
| note | 2b496d51-1d17-4f84-bdf7-7ec3bf35a355 | Welds shall be scanned to both directions.
| note | 0663b8c9-7023-41fa-a705-2bd8a25ca863 | No classified internal defects found
| note | a4c5e2f3-2646-415e-bc55-e0fd5d24e7fe | Geometry of rail head does not exceed 1mm peak 0mm for dip
| note | 955d068f-7185-4323-85a1-a618f4758b8f | MTM New Weld Return Form Testing Section Completed
| note | b2339048-0853-4ec5-abc6-c9da33f46303 | Attach:
| note | fca35104-dc1c-4c8f-be4d-63ce5e6c29f8 | New Weld Return Form (Fully Completed)
| note | 27a2250c-fcdc-48e1-a6c1-371e8c028f19 | Attach Site Photos:
| note | 57046db5-0b48-452e-81f9-0c6162906c5c | Welding Aligning
| note | 37931567-1292-49a8-99cd-cc198e252b02 | Welding Process
| note | 8545fbd2-3855-43f2-956c-f1992f32e668 | METHOD: Visual, Measure, Test
| note | 0031243a-1447-46ad-aedd-305bfcfda63a | FREQUENCY: Each Weld
| note | 2c851ecd-305b-4c95-9ae6-cfa3a3ce715b | CATEGORY: HP
| note | b7e4f7bd-c83f-42fe-8a9b-c17fe5eaf815 | RESPONSIBILITY: Weld Tester, Site/Project Engineer
| note | b1d63c34-39b0-4f6a-acd5-aab6151a14a0 | VERIFYING DOCUMENTS: This ITP
| textbox | 24aa780c-3017-4b6f-a6b6-063cf26d2564 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.1 As-built Survey
| note | 9d85f450-1eb9-4e47-9d90-ff035db0cb6c | REFERENCE: As Built Drawings
| note | 678d5207-2528-4cc3-b099-64aeb790188b | Asset Change form
| note | 0e93b3cc-cc43-40b8-ae18-5ee821176ceb | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
| note | 780d5ef7-416c-4d0e-99cb-c9e39970374d | Attach:
| note | 3bc08b1d-7af3-4a17-b560-2d958bd5f339 | Survey Report
| note | 9879da9c-1fc2-4165-aabc-a5335a376a1d | Engineering Asset From
| note | a62f964a-37e3-48a9-8486-0ed47812222f | METHOD: Survey Document Review
| note | 9e2f7817-99ad-4a5d-8d9a-c3b331e777d5 | FREQUENCY: Once
| note | bdba6359-db68-4eae-8f89-3ab98e299a15 | CATEGORY: IP
| note | 75730f13-79b4-4a30-a3d5-614c95cd9324 | RESPONSIBILITY: Track Surveyor Site/Project Engineer
| note | e8a65ba9-3158-45d5-83be-32a51085e7df | VERIFYING DOCUMENTS: This ITP
| textbox | 1a03c929-6ca3-4f74-b00f-8bab60eadd44 | Date Completed:
| checkpoint |  | 4.2 Track Certification
| note | e0a81f40-6a70-4271-b53e-09900e1edc08 | REFERENCE: MTMF020000-1 – Track Form A T
| note | 273a1393-af3f-4a1c-bddf-e7a2ef8f5ac3 | MTMF020000-2 – Track Form B
| note | 66cf3be7-3eaf-4613-b7f1-ed4c4c70bd99 | ACCEPTANCE CRITERIA: Attach:
| note | a0c390e1-2b6d-40f0-9f8c-f9b1c01d7b9c | Track Geometry Conformance Certificate
| note | acb2b1d3-5b1d-4717-a387-4d39ae3ad66e | Track System and Component
| note | bdac960f-da53-47cf-ae76-fa05388202c7 | Attach Site Photos:
| note | 2295b374-f03b-48df-a689-bd50efef6c68 | Before/After Photo of worksite
| note | f42dd88b-d6b3-45ec-b8a4-1e6b5b3fb9eb | METHOD: Visual Measure Document Review
| note | 2656043c-e4ae-4a6d-a9aa-011724a62caf | FREQUENCY: Once when all occupation works complete
| note | f74c3777-239a-4928-a6db-735906f4da21 | CATEGORY: HP
| note | 9c52d923-456a-4dac-bc97-c7e4e5fa8c68 | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
| note | d148f783-fd73-48c7-981f-d97a01f9d56f | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 8974d3bc-afba-4fc5-b6fe-26fc00e9f0f1 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 56fd08f4-2bd7-4442-8e79-1194daeb6a7c | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 7ee336a4-3be9-4331-8358-32caa55eab08 | Name:
| textbox | ae4e1c50-1456-45f6-9939-eee7dc44def4 | Position:
| textbox | b05c1cb2-b79f-4156-8a01-3c5ce28d2fdb | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Structural Steel Posts & Screens (Supply & Installation) Rev 2 | itp | ITP-STR-Structural Steel Posts & Screens (Supply & Installation) Rev 2 | d434c700-9cff-448e-a8e3-9c59bdba3e90
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | bb4097ea-2cb1-4f83-ac89-5bee0c07acd3 | Document Title: ITP-STR-Structural Steel Posts & Screens (Supply & Installation)
| note | 756079e5-d786-4723-9baf-078e5798c117 | ITP Description: Structural Steel Posts & Screens (Supply & Installation)
| note | f68ea9e5-70b7-41bb-a66e-a11119c44975 | Discipline (e.g. CIV/STR/RAIL): STR
| note | c02e7950-0752-4ed7-96b5-345c091ee1fa | Revision Number: 2
| note | 95c99d0c-6e4c-4cdf-a3f2-06a095fc3521 | Revision Date: 4/05/21
| note | 0a79d60a-8151-4325-acc9-1022cff2eb79 | ITP created by: Mike Freeman
| note | 9f1b7248-c493-4706-a565-b46695fde042 | 1.1 VicRoads Section 610 November 2018
| note | a46f5f67-dab1-4b55-a9bd-7b9455800e3f | 1.2 VicRoads Section 610 March 2019
| note | 6e24c483-f6c0-4b4f-a5ff-5f86b6ef5bcc | 1.3 VicRoads Section 610 June 2019
| note | a7fbd5b6-91f1-4e31-915c-caa1ff94e7e8 | 1.4 VicRoads Section 630 October 2013
| note | cec09a61-63b0-4cf8-9899-226d5f1a62e8 | 1.5 VicRoads Section 631 February 2009
| note | a20f00f1-757c-4ae3-958f-0baa08f6b6f0 | 1.6 AS4100-1998
| note | f693c218-c2dd-460d-af27-a4305bc055f5 | 1.7 AS5131-2016
| note | 6c3724f3-0d09-4079-a82b-d25e15029485 | 1.8 AS4680-2006
| note | a914761c-d45a-45e5-9ae9-63bb261099b5 | 1.9 AS2312.1-2014
| note | 811f4d00-2b3f-4ccc-9236-8905b7d7f254 | 1.10 AS4506-2005
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Structural Steel Components
| note | 1672f1e5-95a1-45f3-b17e-f117a4a0ca41 | REFERENCE: IFC Drawings
| note | f146bce4-e715-42de-b3ef-f753fca214a5 | MRPA Quality Management Plan
| note | 5f94b32d-06e6-4878-bceb-3c6589e80aab | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
| note | d7fcad22-2252-457e-bc1f-5d4667933d5a | Typically this consists of but is not limited to:
| note | 9c4ab67d-cfbc-451a-881a-66ac6858ee4d | i. Certificate of Compliance
| note | 0863675d-ae65-4cef-bff4-d4aae5ad4c6f | ii. Completed ITP
| note | 7adef496-97e7-43ef-abe8-4f69e6b178f7 | iii. Weld Procedure Specifications
| note | 93b01f4d-218e-4392-abbe-63b16e513afc | iv. Weld Procedure Qualifications
| note | b4230ecc-ef9d-4253-bc97-4689ff370f14 | v. Welder Qualifications
| note | 343363b3-c881-4710-9d49-1c97f8ed6282 | vi. Material Certificates and traceability
| note | 61071fa8-4981-4e03-9676-a4cba5086aba | vii. Quality Assurance check sheets
| note | 7a375703-4911-4542-a009-d73bdf1e62f7 | viii. Welding Consumable batch certificates
| note | 3e73b3fb-c1c4-43d6-86de-f67357411178 | ix. Coating certificate(s)
| note | 45792b38-a808-4619-be9f-4f1ee8759522 | x. Non-destructive Testing (NDT) Reports
| note | c4998c9d-9b05-4868-b708-f0a564d3731b | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
| note | 7c74064d-c1fe-4002-897b-831fc5443f5d | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | e79ac34a-112b-45fa-b395-090b3003ae13 | METHOD: Document Review
| note | f081436d-b90d-4fe0-9bff-aa71359f9495 | FREQUENCY: Each component
| note | 94322b50-15be-44c8-abf2-229ded5be1d1 | CATEGORY: IP
| note | 11999c15-d8b0-4eb8-9ed0-c0dd05b60b0d | RESPONSIBILITY: PE/SE/SPE
| note | 83722d90-13b8-46dd-adee-d24e72cca6fd | VERIFYING DOCUMENTS: This ITP
| textbox | c05ca299-cd25-4e0e-b414-605cac3aff96 | Date Completed:
| checkpoint |  | 2.2 Base Plate Structural Grout or Mortar
| note | 800739c7-8505-4c22-b5e4-66f6a6532938 | REFERENCE: IFC Drawings
| note | 1622c23f-8248-4467-85af-a6e3a38144b1 | 610.33
| note | be98f0e0-3215-4941-8548-7128a408938c | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | 9a20ae19-7794-41db-941b-47a07d80064f | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
| note | 4efaec96-f831-4be9-84fe-4d3d5173eb5d | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
| note | bd4c9987-6efa-4603-994b-f78a3783b878 | iii. have a flowable consistency
| note | f64876f1-92a0-4b51-a5da-a8faf004bf71 | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
| note | 41e585e1-7f93-46ad-89ce-6d1c04b143bc | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
| textbox | d92e8546-7831-4d47-952c-9124e8c43e17 | Enter: Teambinder Material Approval number
| note | acc2531b-f22d-4b7a-ac92-7d3d097e1198 | METHOD: Document Review
| note | 24b45667-decc-42b8-8a18-56e41e55ea01 | FREQUENCY: Once, for each product, prior to placement of product
| note | ec230b39-e7fc-4e96-af80-b24eb1eb917c | CATEGORY: IP
| note | ed5297b5-6d24-4adc-9e0d-ff83b9ffaa8a | RESPONSIBILITY: Nominated Authority
| note | f0018154-4aaa-4a8f-bc19-e8d6071d5c84 | VERIFYING DOCUMENTS: This ITP
| textbox | e70e188f-7cb1-43f0-a8cf-b3720d2ae12e | Date Completed:
| checkpoint |  | 2.3 Base Plate Structural Grout or Mortar
| note | 0b24e46a-3464-4091-b3ae-4ed9a83b30b5 | REFERENCE: 610.23 (d)
| note | 328e7b46-124a-4cc9-82a0-771dc6926eb3 | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| note | 644ce439-165b-43d7-ae4e-4456027d518a | Note: This may be the same product used for the concrete curing
| textbox | 0a146950-359b-4ac7-bd09-a15f359a52e1 | Enter: Teambinder Material Approval number
| note | 9386da2a-713b-41fa-807f-ebfa1889d28c | METHOD: Document Review
| note | 639aff42-0c21-4c83-beaa-9b7bd27e9c38 | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | 19639b2e-c725-4882-8add-94963dde3b84 | CATEGORY: IP
| note | 59d67a58-35ee-4e93-9ff7-ef2fc971ed40 | RESPONSIBILITY: Nominated Authority
| note | 40176d5a-f81f-47f8-bc52-2ee897af4592 | VERIFYING DOCUMENTS: This ITP
| textbox | 29891c0f-4c6b-4752-8e77-7d586be5434c | Date Completed:
| section |  | Preliminaries - Procedures
| checkpoint |  | 3.1 Curing Methodology (for Grout and Mortar)
| note | 4824af60-4718-4816-9de9-9d58a11a0279 | REFERENCE: 610.23 (a)
| note | deb62aca-1864-4af5-970c-008cd3ee755e | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
| note | 2a577662-5aaf-495e-b200-233b35d984c1 | Note: This may be the same document used for the concrete curing.
| textbox | d56a4aa2-95b4-4efd-8125-31e5ed5e13a7 | Enter: Teambinder Approval number
| note | 26b3199a-747a-4b51-931f-209fac25dc84 | METHOD: Document Review
| note | f2af46db-8fcc-46d2-bb59-5375e54aa6a1 | FREQUENCY: Where applicable, once, 4 weeks prior to placement of product
| note | 7e2c7050-dba4-4e04-bdeb-70bf5c58f176 | CATEGORY: HP
| note | b2ae6cde-1cdd-45f0-a196-8dcea567872b | RESPONSIBILITY: Nominated Authority
| note | 2471093e-cacc-485f-a73c-4cfd602ffda2 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | dd46f5d7-2e63-4bd3-9c5f-2648f5da6ff9 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 4.1 IFC Drawings
| note | d9e53300-42c4-4ff4-a3d6-f012b04edcd9 | REFERENCE: MRPA Quality Management Plan
| note | 0c69a4a5-c1ae-4dba-b2df-12b904152f5a | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | b4e888bf-b771-478a-8c8a-b9f454d0cb8b | METHOD: Document Review
| note | 23ccb97f-cb36-415c-b9d3-cc8176ac6da0 | FREQUENCY: Prior to starting Works and at regular intervals
| note | b2eb69da-6638-471f-92b6-526b69c73efc | CATEGORY: HP*
| note | ea785b5a-b03c-425a-8421-a7188560150b | RESPONSIBILITY: All
| note | 5aa7bbd9-164d-469c-a393-bd9a74ff17b5 | VERIFYING DOCUMENTS: This ITP
| textbox | 52fb1ee7-9451-4045-9774-ebf5699ad9b4 | Date Completed:
| checkpoint |  | 4.2 Materials Inspection Checklist
| note | c24dc098-46a6-4aa7-9587-c0fc3042e36e | REFERENCE: IFC Drawings
| note | 82cdb75f-7f11-42e5-9cea-abbf56baec77 | 630.08
| note | 8c93d5f7-316c-4ed6-b309-de6a1e0e24ce | 630.09
| note | 16c5e450-f1d7-46ec-b6e2-1304adab5241 | 630.20 (a)
| note | dc68a1c3-d06d-4098-a1d6-47f74cac6f99 | 631.06
| note | 9e77baa2-548e-4c30-8827-05258b2fcf6c | AS4860 Clause 7
| note | a49f9bce-06a2-4693-b2b0-301de52064f0 | 631.11 (a)
| note | def1df43-8ffd-49fa-97d8-456512ed35f0 | AS2312 Clause 9.6.4 (i)
| note | 9597abbb-0c82-4cf7-a3a1-11c168b04f46 | AS4506 Clause 2.3
| note | e73d71d4-a161-4019-a568-8a39b0f3f07b | MRPA Quality Management Plan
| note | 384271b4-d65d-483e-90df-d3b2ef92bc04 | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
| note | bf504bf6-a12f-4c53-9629-9711e119489b | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
| note | 4a77ca20-50cf-4ffc-857f-c38bf88b1992 | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
| note | b6714980-944c-493a-8ae4-8a4b4784424c | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
| note | 230fbbe8-40f6-4fd9-8070-5db335fe6417 | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
| note | 2c1d5ce8-d121-475e-ba37-5f23e927917e | Complete: Materials Inspection Checklist in ConQA
| note | ebde7eed-e96e-48d2-a300-ffdf76459b1a | METHOD: Measure , Visual
| note | cdf5cbe4-80e7-43ee-a2b8-ef8e2c66423a | FREQUENCY: Each component
| note | 801e2559-8603-4a53-a794-dbcdb42e9e9b | CATEGORY: IP
| note | 77034ed6-fd46-4b00-8979-d6137fc43563 | RESPONSIBILITY: SE/PE/SPE
| note | 41d2b49b-5d7b-4bdd-b4b2-f083bb0f71f4 | VERIFYING DOCUMENTS: This ITP
| textbox | 91d3ddf7-2dce-4a8c-bb34-5d1a9f1d0802 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 5.1 Bearing / Mounting Surface Preparation
| note | f630eafa-9a35-405c-8e8e-575fc40c404e | REFERENCE: IFC Drawings
| note | 1c951e10-6cf2-4054-aef7-e63bc225cb5d | Product TDS
| note | 96b77534-7120-48b9-a054-839d1cdc4336 | ACCEPTANCE CRITERIA: Prepare the bearing surface in accordance with the Grout/Mortar Product TDS.
| note | 127720dc-28f2-475b-97db-232a6d1ed234 | As a minimum, ensuring that it is clean and free from loose particles and laitance.
| note | 88346354-bf86-4d73-8921-9c3080b34a7a | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
| note | 8d04e995-ba6f-49d7-b91f-70375fc6493c | METHOD: Measure , Visual
| note | 8d69d680-5a4c-4fbe-8c9b-8bfe2eb73639 | FREQUENCY: Each post location
| note | a27ed554-f825-4483-af4c-f4c2212af547 | CATEGORY: IP
| note | 3316fe84-d6d7-4d3c-8f2f-31da32833543 | RESPONSIBILITY: SE/PE/SPE
| note | 56aac7d8-a535-4b94-aa53-924b2bb12942 | VERIFYING DOCUMENTS: This ITP
| textbox | e4d49ce0-2b4b-4ef8-a4ab-3fbb996fab2b | Date Completed:
| checkpoint |  | 5.2 Structural Steel Handling
| note | 3e3b7ddf-706c-493e-a80b-7ae2945cec1b | REFERENCE: 630.09
| note | 52de7b2e-ef10-4117-b61d-ec8443676da8 | 631.14
| note | f333ae28-aa8e-42f0-ae39-4fb9eb39fd0e | AS4100 Clause 15.2.2 & 3
| note | 1d055495-3578-4835-9494-295a84a74500 | AS5131 Clause 11.5.6
| note | dfbf3047-68e3-4498-86b2-6a2e694493f5 | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
| note | 1ebffe96-d05c-48ce-8e16-483aa684f0d3 | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
| note | f6a65ab5-084f-4625-87dc-5880603e73ee | METHOD: Visual
| note | 95dadbd6-dc6c-4388-b3ec-eb14b3292ee7 | FREQUENCY: Each component
| note | f4c9c198-773e-4fc0-8ee8-a97f2eb815ab | CATEGORY: IP
| note | 9c1bf365-6f71-436f-aef0-de3f174d07e8 | RESPONSIBILITY: SE/PE/SPE
| note | 889b2503-a8c3-49e6-8934-e8ff4484e330 | VERIFYING DOCUMENTS: This ITP
| textbox | da2ad7f9-9473-4487-814e-272a9eaeb4b4 | Date Completed:
| checkpoint |  | 5.3 Structural Steel Erection
| note | 5802bffd-16c5-42f8-a4e9-bd5d52cbe55c | REFERENCE: AS4100 Clause 15.2.3
| note | c947c50a-93b0-475b-baa9-a20acc64caa7 | AS5131 Clause 11.5.7
| note | ef8398e3-8476-4987-b02c-5963c846e91a | 630.12
| note | dcffa110-7e9d-4551-aba2-b8df84ddf3a3 | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
| note | 5205e140-138b-4b77-beef-2efe33df6f82 | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
| note | 37ec64b7-decc-42a1-ac98-79bf2957bee4 | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
| note | 35561209-e919-4d18-965b-dbc40fb59478 | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
| note | c35fd37c-8e4d-408f-8d05-a5ff6b7c2f1d | Holes shall not exceed the greater of:
| note | 5da1173c-e050-4fbc-9cfa-e8555150dab2 | 1.25 x bolt dia. OR bolt dia. + 8mm
| note | 845190a1-7d53-459d-9428-d9c5526ce272 | Slots shall not exceed the greater of:
| note | 15f2ac21-ca48-4240-a611-937b856f979c | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
| note | 41fc4355-6435-44e7-aa0a-5e8441637bfa | METHOD: Measure , Visual
| note | 100320bb-1eb7-457e-968e-f21241b19ad5 | FREQUENCY: Each component
| note | b118b2e6-b85b-4dab-91c0-e2d1f489608f | CATEGORY: IP
| note | 73650c11-3733-43cf-9420-b8b43649d4e0 | RESPONSIBILITY: SE/PE/SPE
| note | a5f37da5-6baa-4328-8c9c-6918fc4b3525 | VERIFYING DOCUMENTS: This ITP
| textbox | bf8e5360-37a2-44ed-852b-d906b465eb01 | Date Completed:
| checkpoint |  | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
| note | a4588316-e7e7-4e0e-9758-f543cc46a5c7 | REFERENCE: IFC Drawings
| note | 58ec3b65-10de-4a65-b654-7f01056a3c97 | 630.20 (a) & (c)
| note | 71105a60-94bb-42fc-8992-18de0517ea52 | AS4100 Clause 14.3.5.2
| note | 38ce5ae0-25ea-4dc4-b242-2cb4bacca7a1 | AS5131 Clause 6.7.4
| note | 05901694-0af4-4c87-a9f6-24f59739f2f1 | AS4100 Clause 15.2.5.2 (a)
| note | ee546a5d-7392-4aa9-b6d8-203b7517d68e | AS5131 Clause 8.3
| note | 7bcec74d-4877-4adc-873e-9c4504ca3799 | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
| note | 00093cb6-f661-4aab-884a-945c2cc0d881 | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
| note | e7eaa6c1-ddde-4ec4-a60c-7c2814758ed0 | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
| note | db0e179f-8025-4f45-a614-7e36a10dd096 | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podgier spanner.
| note | e4b4f664-7620-4047-a5f9-72caf8684ea7 | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | 28075769-b146-4282-838f-e097930aea83 | METHOD: Measure , Visual
| note | fb3f4ae8-cb4a-419b-b198-84ab7fb35ee4 | FREQUENCY: Where applicable, each bolted connection
| note | 3eccfffa-a015-4276-8618-e639403468a6 | CATEGORY: IP
| note | 82269d07-b2a5-4fe3-b8e3-bbbd92e9bfb5 | RESPONSIBILITY: SE/PE/SPE
| note | 0f7dfe10-20d9-454c-aa71-cc9fcd1c5dbc | VERIFYING DOCUMENTS: This ITP
| textbox | 28523c9f-04a0-4ab3-bf11-76e9515e3315 | Date Completed:
| checkpoint |  | 5.6 Survey Conformance
| note | ffa152d3-b9dd-48bb-a555-c7d39b3f8631 | REFERENCE: IFC Drawings
| note | b06bb7bb-75a6-4c03-baa2-43f5ed472581 | AS4100 Clause 15.3.1 - 7
| note | e7570648-3f4a-41bb-897b-f69254b4eccf | AS5131 Appendix F, Table F3
| note | f8bc8dd0-d25e-4b72-902b-98be65287983 | ACCEPTANCE CRITERIA: Grouting of base plates shall not commence until verification that the Works meet level and location requirements within the tolerances below:
| note | f6f4c7d5-7ee4-476b-818e-ee6be1f9c8ee | Departure from RL = ±10mm
| note | ff67e23e-0635-450b-8add-f7df74215aab | Departure from plan position = ±6mm
| note | 179892fc-5558-47e9-b0fd-2ed35e1432b4 | Departure from alignment = ±6mm
| note | 33fdfd6c-6223-4161-bc39-6b697fa4e11e | Irregularities in alignment = 25mm in 30m
| note | 2b024547-c3a1-4b3a-9e57-c436449b4dcf | Projection of bolt = +25mm, 5mm
| note | c0b330ad-d5ea-4a75-99c4-333e29e710ab | Attach: Survey Report
| note | c9acbafb-867b-449d-8c61-f315bbfc9afa | METHOD: Measure , Visual
| note | 9abf329b-cb27-4625-a9eb-2d902e87cedc | FREQUENCY: Each element
| note | d839da26-eef9-403d-8e17-21d6f6359c66 | CATEGORY: HP*
| note | d6cd8f24-60f0-4a9f-9a3b-8d6d62cec3e8 | RESPONSIBILITY: All
| note | 27f83a43-60cf-43f0-9b1b-3338a493f5c8 | VERIFYING DOCUMENTS: This ITP
| textbox | 7773ac24-cacc-4077-b6d4-3f3ba236c826 | Date Completed:
| checkpoint |  | 5.7 Base Plate Formwork Construction & Placement
| note | 1f4f9cdd-1dd8-40fb-9630-e897a783e780 | REFERENCE: IFC Drawings
| note | 82c6807e-9d8f-4ff9-876f-e7d35262913d | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
| note | 9e1f53fb-556b-483b-b7a6-1f44e37668cd | Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
| note | 12e4ff12-656f-49ec-a8f8-42f24c614b58 | METHOD: Measure , Visual
| note | 974ee752-f834-4a20-974c-f8fc48ae8b1d | FREQUENCY: Each post location
| note | e6640c4b-2060-4213-90c0-e619c6c46258 | CATEGORY: IP
| note | 202c3e81-e6f2-412b-85be-a54f5ce79eed | RESPONSIBILITY: SE/PE/SPE
| note | d36cd19e-e7fe-4443-81b7-654d382a6589 | VERIFYING DOCUMENTS: This ITP
| textbox | 4a662266-3e4c-4472-ba33-41e2c2a0c588 | Date Completed:
| checkpoint |  | 5.8 Pre-soaking Concrete Surface
| note | 4fd0a6cd-9c4b-44d5-a6ab-38b74ed4de49 | REFERENCE: Product TDS
| note | 3a37830a-7ab6-4a36-bfc7-cc17a9325fb1 | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
| note | 26c3cd9a-e604-4edc-8468-ec88eeb5d99e | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
| note | 45ad4eaa-b26b-4474-a1c7-f94ce51c6471 | METHOD: Visual
| note | b20ef7aa-47f6-4a55-9d88-c2d21ad073c4 | FREQUENCY: Each post location
| note | 90666063-6e4c-459e-83cc-57d9d2cb2d83 | CATEGORY: IP
| note | 7248cc14-03b1-47e8-ab1a-c9b90c276a75 | RESPONSIBILITY: SE/PE/SPE
| note | d0e29884-329f-4281-a0a0-3ae4964fe48f | VERIFYING DOCUMENTS: This ITP
| textbox | 6c0ded39-49b2-4657-9cf1-e0b85b4a8da4 | Date Completed:
| checkpoint |  | 5.9 Weather Conditions
| note | 24398fef-113e-4d4b-bab6-6265b4b79107 | REFERENCE: 610.17
| note | e4d9dff4-e4dd-454c-982b-12cd1b888b2b | Table 610.171
| note | 60aeae9e-8fc8-475f-bb7a-bcfcc0023ff3 | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
| note | dada6e82-1ff1-4e14-97f2-8e9ba2248bde | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | 2c731c6e-8831-4666-bef9-6b6f7448c07b | Record: Required information on the Grout Pour Record.
| note | dee41597-2e09-4511-b62e-179d342cd8f1 | METHOD: Measure , Visual
| note | e2a0150a-275b-4b5f-a3c1-72a022a8c99c | FREQUENCY: Each lot
| note | d50bd689-2d3d-41d5-b49d-9e44a06bdcd5 | CATEGORY: IP
| note | 5ae14bbc-041e-412a-9a87-7b7eb9c12b1d | RESPONSIBILITY: Foreman SE/PE/SPE
| note | eadb2f6a-7a39-4f9a-b339-7d5ab5fadb95 | VERIFYING DOCUMENTS: This ITP
| textbox | fef6a832-c6ef-45dd-a745-b77b2c09fec0 | Date Completed:
| checkpoint |  | 5.10 Mixing Product
| note | ced613d0-5d6b-4792-8ede-bc6ee6ed3a99 | REFERENCE: Product TDS
| note | 0cc36bd5-c312-4324-8adc-31ee06933de0 | 610.28
| note | a315c873-325f-42eb-a7ad-ab0ff57ecf1b | ACCEPTANCE CRITERIA: Size of mixer should match the application.
| note | 99455467-c8c7-4819-bd49-157e184aa441 | Only whole bags to be mixed with potable water.
| note | 678adb58-7e14-4ff8-b5f2-be0191e6f6b9 | Volume of water matches the required amount for flowable consistency and accurately measured.
| note | f7089b05-dd6d-40b2-a7ec-bbefc313b0a9 | Product poured into the mixer slowly.
| note | fe5ef11c-844b-4017-baa2-0bf99f3b5f36 | Mixing time as per TDS so that a smooth, even consistency is obtained.
| textbox | 8ceefeec-032d-4b62-b361-279482cad88e | Enter: Required information on the Grout Pour Record.
| note | 43b62a04-0bc0-4e4a-ace6-85599cf6393e | METHOD: Measure , Visual
| note | b45070a2-ae1a-40b4-8fff-8367d83ca91b | FREQUENCY: Each batch
| note | 10d5e4e2-8a36-4c8d-a4d0-a76df762b9b0 | CATEGORY: IP
| note | a4c1b5e7-84a0-44ed-9971-3e720b57286e | RESPONSIBILITY: SE/PE/SPE
| note | c94b37c3-c9f8-4b9d-a6fc-f39e4d8ac28c | VERIFYING DOCUMENTS: This ITP
| textbox | 4b840c61-4619-4c98-93d1-2a6ad87fdee3 | Date Completed:
| checkpoint |  | 5.11 Product Testing - Compressive Strength Cubes
| note | 4e511810-6457-45ba-8985-cc268bbaba79 | REFERENCE: 610.28
| note | 5569b194-f28c-41bf-9547-75538f64043b | 610.33
| note | fc553a89-0129-49c2-b0d8-899229381157 | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
| note | 4c0ba25e-d119-4d1b-983d-229b577371a8 | Testing is be in accordance with the following frequencies:
| note | 203b88ef-5635-4e8c-8c49-3b59fb5e98ac | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| note | 4a10477a-a7c7-4746-b70f-a9d1c0a3080e | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| textbox | f17fca04-b912-4d83-957c-6125b31ddda4 | Enter: Required information on the Grout Pour Record.
| note | 51b1fe0d-e3db-4b5c-951f-553f58644e6f | METHOD: Test
| note | b77e8a2f-a805-4ddf-b84f-7ecff99362e7 | FREQUENCY: Each lot
| note | 190bd450-6dac-4d4c-8efd-fe7b61ebcfd8 | CATEGORY: IP
| note | bd8fbfd8-92fa-4a67-8f38-21b767c445e6 | RESPONSIBILITY: Tester , SE/PE/SPE
| note | 5810b942-1194-488c-90bd-d6bcfc55db4f | VERIFYING DOCUMENTS: This ITP
| textbox | 12e5620c-b051-4910-a6a8-4d89017f087a | Date Completed:
| checkpoint |  | 5.12 Placement & Compaction
| note | 83a61ec2-7250-4a3f-85c7-5e39e3d7383c | REFERENCE: Product TDS
| note | bcd8f00e-bdf8-4250-8e97-51dfd1f863a6 | ACCEPTANCE CRITERIA: All batches are traceable.
| note | 746cbc9c-0f22-4b3e-a9ad-6d78119037c8 | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
| note | 25bdfcf7-5b4b-4fb1-b5bd-bda9bc8729e7 | Product should flow to all areas and self consolidate.
| note | 57fe0e5b-6c1d-4186-9b1d-b767a8f86334 | Product that stiffens or is showing signs of stiffening shall not be used.
| textbox | 511b4317-11a7-4f25-95ec-6e6b38b99b05 | Enter: Required information on the Grout Pour Record
| note | f7b9e2da-5a9f-4e4a-9ea9-c85b87685152 | METHOD: Visual
| note | fc516a80-123b-48a6-8724-56e0dee0898a | FREQUENCY: Each post location
| note | 7dbe1ed0-29a8-4738-acae-5e52bac71610 | CATEGORY: IP
| note | fd90bad4-32f3-4dc7-9ccb-9537f3796204 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 8a65ad17-fc15-4d29-89b1-8559331248fa | VERIFYING DOCUMENTS: This ITP
| textbox | c81b2aff-e09b-4fc0-8887-8ac56c9f8e76 | Date Completed:
| checkpoint |  | 5.13 Surface Finishes & Protection of Works
| note | e54a5b9c-66e0-4f60-b58c-fad83bef383d | REFERENCE: IFC Drawings
| note | 96abad4c-0f48-49e3-8780-698a05d49cd4 | 610.17
| note | e5c78e79-6355-4e53-b196-56fab92129ef | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
| note | a0d6e886-76cc-4e3a-b114-45b31474eb03 | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | c1867d98-f70c-4d94-8671-a3e9682d1be8 | METHOD: Visual
| note | 6e27b76d-bc6a-4755-bfb1-a5ef4744c386 | FREQUENCY: Where applicable, each post location
| note | 35ea3131-7192-475e-9013-b0f53cd43545 | CATEGORY: IP
| note | cb7a028f-4936-43e0-883c-808c20bddea1 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 753fc37e-1e39-42ca-a07d-3b35049ba1a8 | VERIFYING DOCUMENTS: This ITP
| textbox | e992803c-ca76-4941-8fe4-8f35162f4965 | Date Completed:
| checkpoint |  | 5.14 Curing
| note | 1bfce4ed-b107-491f-a8e7-34d017c0507a | REFERENCE: Curing Methodology
| note | 7e1d9c01-6afc-4c23-98ef-ad57e6d6ff1a | 610.23
| note | 1f4255f5-a3e9-41fc-ad59-06eea9a4e7bb | Table 610.231
| note | 6749d7ca-5cab-4145-9ffe-19225e4e34e2 | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
| note | 7284c75e-493e-4406-8d9c-1a135bca05bc | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | e6e17fb5-35f0-424c-9ca0-fc693678895d | METHOD: Visual
| note | c4fe6458-28de-4fc8-8550-9af05c402b8e | FREQUENCY: Where applicable, each post location
| note | 7e7c5434-34dc-4af7-9bbf-fbd33143a376 | CATEGORY: IP
| note | 59f6a714-c4f2-4f38-8d67-72399cc0262f | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | a34018b1-fa10-4982-8c12-3bc721f59eb2 | VERIFYING DOCUMENTS: This ITP
| textbox | 937b123c-f8ab-44bd-8968-ac4a8a8f33ed | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 6.1 Inspection of Coating
| note | 213936e6-0a06-4c37-a922-bf67b0584600 | REFERENCE: IFC Drawings
| note | dbb05612-f41e-420a-9c29-14d068b3b520 | 631.15
| note | 2ed195c2-85dd-4181-9c4d-c9a7f25ee2b2 | AS4680 Clause 8.3 & 8.4
| note | 0b61ab8c-947b-4b5f-8ddd-31278834a927 | AS4506 Appendix E
| note | dccf4c7a-0e57-4e5f-8212-a7e6c550c064 | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
| note | 3d9c3138-8256-4309-966d-e6dba2e53d98 | Where damage exists, it shall be repaired using an approved repair procedure.
| note | 7b0b5179-bc34-4ea2-83fe-addf9df1b270 | METHOD: Visual
| note | 56c08ef7-c725-4937-b0d0-a8e994039bbf | FREQUENCY: Each component
| note | 9b7f9fe2-f4f7-4818-b3e0-1d78bebad5a3 | CATEGORY: IP
| note | 21cdc7e2-afb8-42c3-a205-0dc8bace87b4 | RESPONSIBILITY: SE/PE/SPE
| note | 173c857f-bbac-44a9-8805-12439d9e7a3c | VERIFYING DOCUMENTS: This ITP
| textbox | 47ed5d09-7f04-44b9-b1ac-1f9c2280b3d1 | Date Completed:
| checkpoint |  | 6.2 Compressive Strength Test Results
| note | 2ffdc8d3-77a7-4d54-ae0a-48bca07fe650 | REFERENCE: IFC Drawings
| note | f356efa1-0e66-497a-af05-a9a48c03286d | Product TDS
| note | 69a25348-97ab-431c-ae36-7ad1e39c8d93 | 610.28
| note | 7bfd29fc-ee77-4fc1-bf9e-669d68c35e83 | 610.33
| note | 9384f06a-5b52-44ad-bc75-dea7d5e59e58 | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
| note | 468e10a7-519e-47d2-80e3-092a650e8da8 | 28 day compressive strength per sample comply with the design strength.
| note | 2828f966-b019-41de-af43-c245e7b1fa2e | Attach: Compressive Strength Test Results
| note | e76d0715-8daf-4bbb-8e42-3c77062a385a | METHOD: Document Review
| note | 9cf66461-d2e9-470e-b2da-faa9f0b95513 | FREQUENCY: Each cube
| note | eefe7d4b-a2cf-427a-8b46-a4268af00bcf | CATEGORY: IP
| note | 09e4c91c-7f91-4cee-8201-69d1e565d4eb | RESPONSIBILITY: SE/PE/SPE
| note | 70276942-cf00-4341-a036-6e41656b6803 | VERIFYING DOCUMENTS: This ITP
| textbox | d9aff1a8-2731-4f05-9859-11b3201a9817 | Date Completed:
| checkpoint |  | 6.3 As-built Survey
| note | 16d61ab5-1eee-45d7-8b64-70e2143e14e8 | REFERENCE: IFC Drawings
| note | 3c4e3767-417d-43d2-a39c-2e0d999679e2 | AS5131 Appendix F, Table F3
| note | 76ae3ee5-1507-4cef-851c-da248bf6a001 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
| note | b2a3ae15-d70e-4ff0-8c94-b0d7018f28a1 | Departure from RL = ±10mm
| note | f7704619-9b6c-47fe-8d3b-07f73491669c | Departure from plan position = ±6mm
| note | 95992f92-7e5f-451b-9b5f-5e9669fef870 | Departure from alignment = ±6mm
| note | d198f458-39b9-4c9f-a4c3-ec79e5aaff75 | Irregularities in alignment = 25mm in 30m
| note | e3f98857-30ff-4004-a3fa-78cb87f2d89d | Projection of bolt = +25mm, 5mm
| note | 8eb091db-d7eb-4e6d-96ba-45a4751560b1 | Attach: Survey As-builts / Survey Report
| note | cd2aa57c-fb9c-4d2d-993e-f81a3250ee3f | METHOD: Document Review
| note | 45f57da0-0515-41e3-b8bf-722e3067dde2 | FREQUENCY: Each component
| note | d0f606e8-0d07-40dc-a30e-81e55e840150 | CATEGORY: IP
| note | 3a261aa1-4457-4925-90a9-ab0a944cca2c | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 977253a1-4e14-4c1c-adeb-4ebd4370e2c0 | VERIFYING DOCUMENTS: This ITP
| textbox | 549cd720-adc7-4dcc-b2b3-1abc59976a69 | Date Completed:
| checkpoint |  | 6.4 Non-conformance Report (NCR) Closure
| note | 00277e52-48c1-4d7e-99d2-2be2a4ec4095 | REFERENCE: MRPA Quality Management Plan
| note | a460d892-5a41-4740-a45f-ec672ea7d71d | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 3669a539-a89e-4409-b01c-865e82883a72 | METHOD: Document Review
| note | 978b7baa-34a8-4caa-806d-c99c8022fb85 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | f6edbb19-fa87-4ade-b048-953872bd205e | CATEGORY: HP*
| note | a72e06ce-f9e6-40e6-a95c-1ddf0c8a24fa | RESPONSIBILITY: SE/PE/SPE
| note | 2b100151-a54a-4a1c-8f84-d116c9406b64 | VERIFYING DOCUMENTS: This ITP
| textbox | c66ed83c-578d-4305-bb9b-6a3c624f80b8 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 9bfbfdda-eadf-45de-aa83-f3a470af1b7e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 8e436256-2dbc-4aab-9cce-f9f5617c020e | Name:
| textbox | b8ce35a2-aec9-4799-b00c-c239df110564 | Position:
| textbox | 578f4c00-786f-4520-8443-ae8a5f8bd9f1 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Landscaping - Planting Rev 0 |  | ITP-CIV-Landscaping - Planting Rev 0 | d772e3fd-2440-4481-a790-e8026482278a
| section |  | ITP-CIV-Landscaping - Planting Rev 0
| checkpoint |  | Lot Information
| dropdown | 39b9709d-a71c-549d-8c9f-e559fae49163 | Lot Status | Identified, Open, Ready for Close-out, Under Review, Reviewed with Comments, Closed out
| dropdown | 7068f2c3-09d4-5ca8-925f-495192539c7f | Responsible Engineer | Ben Kelly, Brigette Rizzario, Bunnarith By, Danniel Borrie, Danny Gannon, David Chai, Diana Delac, Jack Gascard, Jackson Nunan, Jadan Halket, Jon De Castro, Kia Menchin, Lachlan Summers, Luan Pham, Mazen Hamady, Mitchel Jacques, Plutarch Deliyannis, Ryan Dsouza, Sanjar Wasil, Scott Paterson, Sebastian Santalucia, Shane Voyer, Shayam Ajjarapu, Ty Qiu, Vince Argiro, Yokanth Ravichandrakumar
| textbox | c6e0cb65-7daf-5afd-a730-9e1ebb31e8dd | Design Package No (ex: CBR-0017, AUD-0011)
| dropdown | f522de08-96e1-5172-a665-dd25657f141c | WBS Area | Robinsons Road,Fitzgerald Road
| dropdown | 83344351-a1e2-5a6f-932a-4c762ab0ae7f | WBS Sub Area | Rail - Track, Rail - Structure, Rail - Facility, Rail - Signalling, Rail - ICT/OCS, Non-Rail - Road Authority, Non-Rail - Area Wide, Non-Rail - Council
| textbox | 29c77bab-ba43-5dd4-bced-b305d261e11b | Work Start Date (dd-mm-yyyy)
| textbox | f5796fd1-5511-5801-93cb-b646696844f5 | Estimated date of Lot Close-out (dd-mm-yyyy)
| textbox | 7c1e6adb-c289-5898-8ba0-1d748b906bc1 | Actual date of Lot Close-out (dd-mm-yyyy)
| textbox | 0e8012ca-989a-5fa4-bae1-d15c87ff87e0 | Comments
| checkpoint |  | Referenced Documentation
| note | 71f41283-d345-5dab-8acc-9c3ae8d2c4d3 | Document Title: ITP-CIV Landscaping - Planting
| note | 1e67ad71-6fa7-5493-88d4-222242cc1170 | ITP Description: Landscaping - Planting
| note | fb8e3950-e7d5-5f77-8d32-7fd17f133b5c | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 1bcec3a8-6bff-52b2-a78a-4c1596441578 | Revision Number: 0
| note | cc21794a-da8f-5907-b39a-eacc7544b690 | Revision Date: 24/11/21
| note | 682bcc50-6e26-5ed3-a4a8-d6e0056ce13e | ITP created by: Anthony Pearson
| note | 497b8221-4146-51e7-a8fb-ed890d275340 | ITP approved for use by: Josie Pavlou
| note | 804d0a81-9e58-5ed6-bf75-578fb3e15a43 | IFC Drawings
| note | 548d419f-3909-5114-8a6e-15cc679d4118 | Vic Roads Section 720 (Nov '18)
| section |  | Preliminaries
| checkpoint |  | 2.1 Check for correct documentation
| note | 709c7112-8ab4-52af-be8a-290b21430640 | REFERENCE: Drawings and Drawing Register
| note | bedf18e8-e0c0-57f2-95a2-e904fc1cbe58 | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using:
| note | b54d1fdf-0181-552b-a2d3-11c27718f208 | The correct and complete set of drawings
| note | 034fa1dc-3c13-582d-a7aa-daf716f1ae0f | All drawings are the latest revision
| note | 0bc7f5c2-6127-534a-889c-d60485dbcd9d | METHOD: Document Review
| note | 0ef73912-bd96-5b4b-9298-03d9d5219c40 | FREQUENCY: Prior to Commencing works
| note | e5ce9f35-a828-5c2d-8080-b3c84245e663 | CATEGORY: N/A
| note | 75a2efc2-0b9e-5df9-ad53-822a48dca19c | RESPONSIBILITY: SE
| note | 7b8607ad-2c40-5ae9-810e-9785d4827725 | VERIFYING DOCUMENTS: This ITP
| textbox | 6908bf08-6533-5d09-b64d-882901a8ad47 | Date Completed:
| checkpoint |  | 2.2 Submission and records
| note | 5dd08b38-3d84-52eb-b6be-646a0d4a4a58 | REFERENCE: VicRoads Spec.
| note | c3f0f62f-0cf0-5d56-b339-c298e00b386e | Cl.720.03
| note | 03caeb8a-c51a-59be-b4b5-6ccb37682527 | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
| note | 97d806d0-e8fc-56cd-8f57-5897a12358d5 | Following information shall be provided to the superintendent:
| note | 79acb458-c039-58ce-a6c1-88f420521604 | Inspections of plant stock for all plant species
| note | 73a9f011-9254-5a4e-917e-e09d6ab915ff | Records:
| note | b64b8908-d08a-5f87-b89c-46419626374c | Evidence of origin of indigenous provenance plant material
| note | 7aaf654b-13ab-5038-b5a2-87a9a4758359 | Analysis certificates for grass seed
| note | 072c66bb-16fe-5435-9209-007fbffb40d8 | Details of suppliers
| note | 58cc54c3-76bf-50f4-bda0-ebb11b9db6ba | Copies/Photos of fertiliser labels
| note | 2f89db19-13c5-59b2-afc9-2fa22d265c08 | METHOD: Document Review
| note | a3a474dc-8181-5897-accd-8c9cb8aa18e2 | FREQUENCY: Prior to Commencing works
| note | 8b037c4b-ee3b-51db-863f-c193c29bd461 | CATEGORY: HP
| note | 5a203460-dcbc-55c2-9d88-8cf94416a463 | RESPONSIBILITY: SE, Superintendent
| note | ba7365a7-a3b5-5884-a2c3-a57527c9dd19 | VERIFYING DOCUMENTS: This ITP , Attach Records to TeamBinder Approval Form
| textbox | 79ea086d-c581-5fb4-8e09-62409929f265 | Team Binder Approval Number
| textbox | 3129d31b-2f57-5c8c-a281-22becf351f50 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Supply of Plant Stock
| note | 6fb4b644-2fee-5ed0-9e39-d0efefd1b500 | REFERENCE: VicRoads Spec.
| note | 30f7df12-533f-5dfe-b426-4f556b051fcc | Cl.720.04
| note | ba262ae0-21e6-5b66-9255-07c78c3545d2 | Table 720.041
| note | d564ca86-ae4a-5868-bc90-7c9b0bd3da90 | ACCEPTANCE CRITERIA: All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
| note | 6a10b0c5-8f79-561e-b00a-32514cc4239c | Plants are to conform to the supply properties specified in Table 720.041
| note | a1ffd63b-750c-5f1d-97f9-d09e81de0c15 | METHOD: Verify
| note | 914bc422-5bc9-5f82-9974-4f343641b671 | FREQUENCY: Prior to Commencing works
| note | dd5477e9-d28d-596a-80da-07cb4570c14d | CATEGORY: N/A
| note | 74c656f4-e658-5b9d-ad75-1e53c28395da | RESPONSIBILITY: SE
| note | aab7a45e-26a7-5ee5-add0-240a356a8774 | VERIFYING DOCUMENTS: This ITP
| textbox | 4e91c2b5-b607-5502-af09-5452be4371e1 | Date Completed:
| checkpoint |  | 2.4 Supply of indigenous plant stock
| note | 910a6f37-b694-51ae-9a9d-26684ab9e612 | REFERENCE: VicRoads Spec.
| note | 9a05d24c-80c7-57bd-b13a-271f7df25825 | Cl.720.04
| note | cb93dd5b-fc73-5dd4-9239-29be303a8a1d | ACCEPTANCE CRITERIA: A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
| note | cb9db477-35b7-5dc7-b304-ebd1d309033a | The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
| note | 39799531-b7af-5d91-b2f6-463e7ccde913 | species name
| note | 2c9ccf90-af3a-538d-bebe-e3549aa68204 | storage code
| note | f9fc4465-643c-5ab0-95bc-34e9d33ac1b8 | collection locality - Latitude/longitude or AMG
| note | cf28fd87-eebd-5996-8d75-2cbff9bd09c8 | approximate number of parent plants sampled
| note | 6177ec4a-9382-56ce-888a-253dfc35e7ca | approximate number of plants in that local population
| note | c312e780-f1f0-5e7f-958b-db2526c82ced | METHOD: Verify
| note | 220c6c32-e547-55c4-a502-b4bd74906414 | FREQUENCY: Prior to Commencing works
| note | 55e39279-df50-5e88-9ef8-d9868c5391f2 | CATEGORY: N/A
| note | 1d9e1c43-df98-5ae0-8df8-5cb329b76c64 | RESPONSIBILITY: SE
| note | 2bac39d2-24c4-57f3-91b6-dd497ae318f7 | VERIFYING DOCUMENTS: This ITP
| textbox | 2e9947ef-ed15-51ea-b55e-567ab4c917e3 | Date Completed:
| checkpoint |  | 2.5 Supply of grass seed
| note | a4b4134a-99e1-5458-a4cd-b9d46918e603 | REFERENCE: VicRoads Spec.
| note | 11846b95-1465-5ee7-86f9-64fd669f0598 | Cl.720.04
| note | a96e62d0-b682-5220-a92e-ae51bd51780a | Table 720.045
| note | 3261149f-a5f4-5dd5-8bb2-4b47778ecd50 | ACCEPTANCE CRITERIA: Grass seed shall comply with Table 720.045
| note | 3bf392bd-14ac-5bb0-95a0-1099d43c3d42 | METHOD: Verify
| note | d0a8958d-997b-5984-8410-3d24b3b2ad93 | FREQUENCY: Prior to Commencing works
| note | dac6990d-a8ea-5e84-9cd8-3113355ecf45 | CATEGORY: N/A
| note | 29a121ed-8aeb-54c4-ac72-7a11499987ba | RESPONSIBILITY: SE
| note | 66f21c64-c4ac-53e8-a5f2-c9e09a92354d | VERIFYING DOCUMENTS: This ITP
| textbox | 06129efa-2fc2-56a5-a23e-2b8dc5ac2446 | Date Completed:
| checkpoint |  | 3.1 Planting Section Approval
| note | c726f9a8-5c53-585c-bb17-21f79c0745ba | REFERENCE: VicRoads Spec.
| note | 2dac354f-c394-5b60-84d1-27c015c84cc6 | Cl.720.06
| note | 1cdf9a6a-a55b-5edb-af12-168fc4db4168 | ECO-LANF-005
| note | 781e3334-aa88-5dfa-a93e-efce2d4a616d | ACCEPTANCE CRITERIA: Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
| note | 82e3fd0e-5f26-5df2-9b91-b44d5ea15e70 | METHOD: Verify
| note | e57aaf8d-ea42-51a1-a622-f1c07dcdb649 | FREQUENCY: Once
| note | b6917e06-2d75-5025-b7de-a3c77f1915f8 | CATEGORY: HP
| note | 04a0acf2-acdb-554f-a56e-9609f4cd32f3 | RESPONSIBILITY: SE
| note | 8b8364e2-53fb-5db0-8105-659a6bb486d5 | VERIFYING DOCUMENTS: This ITP
| textbox | 2701c50a-4ed8-5fef-8c08-34f87456d09f | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Pest and Weed Control
| note | 11970d72-7298-561e-b589-7d53e6fa1a07 | REFERENCE: Cl.720.05
| note | 02bfba0d-45e0-50a4-b2ec-ac94e8567836 | ACCEPTANCE CRITERIA: The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
| note | 92c28905-5f73-5101-b285-bcedb44c4468 | Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
| note | ecf3ac26-b94f-55c0-89b5-0eb5287245a5 | METHOD: Verify
| note | 36af1442-0860-588f-a000-f6491afac015 | FREQUENCY: Once
| note | 514d271b-bbdf-5758-bc51-a2de291b3426 | CATEGORY: HP*
| note | 27aca16e-f12c-5c33-b9d8-5bacb9045d07 | RESPONSIBILITY: SE
| note | d829c6c2-63fa-52e4-be47-7867cf385f5f | VERIFYING DOCUMENTS: This ITP
| textbox | bb239104-d815-5191-ab9d-8bb741ebd280 | Date Completed:
| checkpoint |  | 3.3 Setting out planting areas
| note | ecc28b26-6067-5b4f-a618-75246aad427a | REFERENCE: VicRoads Spec.
| note | 605a2e4a-64d3-54f9-a84e-d1da61562fb2 | Cl.720.06
| note | 6025a0d3-d58b-5c93-9fdc-1f89b84d56c8 | ACCEPTANCE CRITERIA: Planting areas are to be set out to the location and shape specified in the landscape drawings.
| note | 49b8666f-e5ca-58a2-bd6e-ebb92e7e8691 | Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
| note | 823ef491-998a-537b-af55-00682714ec9f | Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
| note | 4da29149-68cf-5ca9-8975-ce49d1c6fdc1 | METHOD: Verify
| note | d8d21314-9c6a-5d69-9579-06c778654aa7 | FREQUENCY: Each Applicable Lot
| note | e889a7ca-8f29-537b-a855-0b766ab2db10 | CATEGORY: N/A
| note | d2df7219-c692-5d7a-929a-86aec94b7d76 | RESPONSIBILITY: SE
| note | 484f03e6-33cb-5e05-86f9-2d3e626e2fb2 | VERIFYING DOCUMENTS: This ITP
| textbox | 3f94d056-6bee-5647-9eb4-7d85eafe84a2 | Date Completed:
| section |  | Construction
| checkpoint |  | 4.1 Planting
| note | d24c8036-e9b2-58ed-a5e1-fb02efdf3e5e | REFERENCE: VicRoads Spec.
| note | 142bb536-dde6-577e-bcbb-58395ecb2953 | Cl.720.09
| note | f6eeac29-9ce3-5bfe-83b5-a63ca00ce7e4 | ECO-LANF-005
| note | 24f01e23-f0d4-52b4-9b6d-d9d4eea1fc90 | ACCEPTANCE CRITERIA: All planting will be undertaken in accordance to Ecodynamics ITP ECO-LANF-005
| note | 34714c6e-0658-56d8-b5bf-0d59986d6d05 | METHOD: Verify
| note | d26d4fc0-e75a-5af6-8986-d44675e76744 | FREQUENCY: Each Applicable Lot
| note | eafc0bf5-5e52-5469-bae3-54a57a1124b6 | CATEGORY: NA
| note | af8f0ed8-dfa4-50c2-9605-ed78ddc20e54 | RESPONSIBILITY: SE,Foreman
| note | b1f4dbb0-1515-5f79-a542-422f326f8915 | VERIFYING DOCUMENTS: This ITP
| textbox | 57385cf1-5e3d-5bfa-91ed-552d8a995905 | Date Completed:
| section |  | Completion
| checkpoint |  | 5.1 Site Final Inspection
| note | 5c3cfb94-5b36-57d6-8ce5-0db124c0a8a9 | REFERENCE: ECO-LANF-5
| note | 3dd91835-3673-564b-ae1b-7e997619f4e4 | ACCEPTANCE CRITERIA: Ecodynamics ITP signed and completed
| note | b9c59ebd-b041-54ef-be84-eeb918828253 | METHOD: Document review & Site Inspection
| note | 4a65536b-aa70-5ed4-bf09-f4039c7dd71b | FREQUENCY: Following completion of planting works
| note | 8b56f663-34c3-56ee-a29c-b260e9356eb8 | CATEGORY: N/A
| note | 22c0a74b-b2f8-5323-98ef-e7516e370fcf | RESPONSIBILITY: SE
| note | 2f8e451f-df68-5799-b978-882897d444d3 | VERIFYING DOCUMENTS: Sub-Contractor ITP completed, signed and to be attached
| textbox | c72867cf-1927-523f-8c47-cb462fc6d680 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | d38a08bf-5f3e-5904-8782-7bbd2623ae1f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 103201dd-b417-545a-80ef-a4e032bd888a | Name:
| textbox | 91f41509-60a5-5edc-bbef-098a08e0d32e | Position:
| textbox | 472d39ad-861e-55d0-bb07-97fbf37fd80d | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-Rail-Formation (Supply and Install) Rev 0 | itp | ITP-Rail-Formation (Supply and Install) Rev 0 | d8e8946f-c1c0-44f7-a26f-7445c6318546
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 4bb50003-8198-4050-a9d7-7b2e173e6ac8 | Document Title: ITP-Rail-Formation (Supply and Install)
| note | ebc6c9be-e892-4fc5-8eb2-cce407bc218c | ITP Description: Formation (Supply and Install)
| note | 6e8adb59-646e-4645-a864-46b8b28e0631 | Discipline (e.g. CIV/STR/RAIL): Rail
| note | 9ae73503-69fd-48af-8ea8-aca0b6d925b1 | Revision Number: 0
| note | f1ff972d-9e72-4ea5-8dbf-c0fb8c4ded5d | Revision Date: 27/04/21
| note | 3d12059b-1a9a-4aa1-a741-772fbd2ea7a8 | ITP created by: Rayan Rahman
| note | 51734349-cca6-4203-9d87-d3d1f3341cae | ITP approved for use by: Romualdo Magpantay
| note | a4767607-a1b9-4b49-b752-cdcfd5120023 | 1.1 IFC Drawings
| note | baf771d4-78f4-4d0f-8c63-c30d3157e2d1 | NIST-2659 Rev 04
| section |  | Preliminaries/Material
| checkpoint |  | 2.1 General Fill Material
| note | 6588026d-525c-4c51-b5e2-cfedff254271 | REFERENCE: Nist 2569 Rev 04 - clause 5.7
| note | b8a6610e-8dec-4d5c-98de-9793aa598402 | ACCEPTANCE CRITERIA: General fill material is to be used to construct lower portion of embankment and compacted at 98% standard dry density ratio (RD) and have a soaked CBR ≥ 2% (95% standard compaction - 9kg surcharge) . It must be free of particles greater than 150mm in diameter.
| note | 5478e5f0-2c0f-4a32-a584-1cd8ee208b7a | METHOD: Visual Review Test
| note | d4ded004-80a3-4a92-8baa-d95128fb1541 | FREQUENCY: Each Lot
| note | a121d22d-1809-4b77-9434-85133907227c | CATEGORY: HP
| note | 27f6dbb5-b581-44e0-95c7-a85b34c46b67 | RESPONSIBILITY: SE/Nominated Authority
| note | 5b843b99-26c1-44a3-936e-8c1c62271848 | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
| textbox | ff63e6b7-14cb-47b3-96aa-62656af7bfa3 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Capping Material Supply
| note | f8325548-4289-42a4-86a5-f2f57024dc66 | REFERENCE: Nist 2569 Rev 04 - clause 5.10.1
| note | 27de8330-e871-40d1-a31e-abb23092cd29 | ACCEPTANCE CRITERIA: Capping material shall not contain any vegetation. Capping material shall comply to the below PSD:
| note | 75e5fb26-0435-4235-ac28-6eb7d006faf3 | Capping material shall have the following properties:
| note | 263a0777-3301-4d88-abfc-7171c48157e9 | 26.5mm 100%
| note | ec22a0d8-70e6-4343-ba48-1b7149a11209 | 19.0 mm-95-100%
| note | ebad0466-1e05-4b64-81a8-ecef965ab4d7 | 9.5mm-60-90%
| note | 23738de5-9b88-42ee-b9f1-c8a246b5e4dc | 4.75mm 40-70%
| note | 790b70c9-12b6-47c0-a105-5850da5f5f59 | 0.425mm 20-40%
| note | 0a495708-015f-497c-a9ae-7168753121ad | 0.075mm 5-10%
| note | d97d4a2f-bb65-478b-8902-0c1d27623255 | LL maximum 30(35 for arid areas)
| note | dd3bcd80-1ff1-494d-8a1f-580c303d6d65 | PI between 4 to 10(4-15 in arid areas)
| note | c82f5e3a-e41a-4a9b-8cc5-6cd1f21b5d4e | Maximum DD minimum 2.0 t/m3
| note | f8ea14ba-e916-4725-9eb5-b578afa6631d | CBR soaked(compacted to 95 % min std dry density)with a 9kg surcharge
| note | 5a35776f-2f1d-484b-a921-1fba23e94c1d | METHOD: Document Review
| note | 5d1765c3-3d7f-4ff7-8b26-34821c14295d | FREQUENCY: Once for each material type
| note | d10c1257-850e-42c2-a23c-7ec9c82c8b88 | CATEGORY: HP
| note | 2ce6c557-7757-4bc2-a385-0cd54b9e9635 | RESPONSIBILITY: SE/Nominated Authority
| note | 0bebc903-7f98-4d4c-84f3-cbc017115335 | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
| textbox | 80590228-f5e2-44d1-a946-5e9b4becc02c | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 Structural Fill Material Supply
| note | af748f06-6c09-4d3d-8cf1-8cea27b307a5 | REFERENCE: Nist 2569 Rev 04 - clause 5.7
| note | 3c98a153-65e4-47f8-ba2b-a52cf1a56bed | ACCEPTANCE CRITERIA: Structural fill material shall comply with the following properties/requirements:
| note | 8cdf99fd-6e3b-47f0-b7ed-eec6c4b35427 | 75.0 mm 100
| note | 3f9291f2-5862-4136-a3f7-214b68268a21 | 53.0 mm 80-100%
| note | f7cea811-71ff-4b67-be7a-fc2d042421d2 | 2.36mm-15-100%
| note | 0ce42572-afd6-4072-ae02-4bb490c5f89c | 0.425mm 5-70%
| note | 07c94aba-254d-45f5-a6b6-c778a8397ff2 | 0.075mm 0-30%
| note | 21994887-530f-4c02-b41d-a40099e1c77a | LL maximum 40
| note | d3bcc3af-e46a-411e-bdba-58d8787b441c | PI between maximum 20
| note | 34260d74-6ae2-4123-b66a-d6d299cb936d | Maximum DD minimum 1.8 t/m3
| note | 3db38acc-625b-4ca1-935b-6b75bfb83abe | CBR soaked(compacted to 95 % std dry density)with a 9kg surcharge
| note | 919bbde7-002b-472e-bc53-5334d3868e9f | METHOD: Review Test
| note | e18cdf7e-7b26-47b4-bd6f-07f369f4a4eb | FREQUENCY: Once for each material type
| note | 9e057513-8b29-46a2-bf0f-92fcbbdb4ec7 | CATEGORY: HP
| note | e01b3426-719c-4d4b-b25e-107e76d2af05 | RESPONSIBILITY: SE/Nominated Authority
| note | 41d1694d-98db-4f78-b588-7a3d54ec1a51 | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
| textbox | 6751a8fd-08ea-45fc-bfbc-c3565c7bd5e5 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Site Preparation
| checkpoint |  | 3.1 Survey set out
| note | a5558081-4d38-42b7-abec-53346a9072cc | REFERENCE: IFC Drawings
| note | efc24ca2-f0a3-491a-ad94-fbfee9593595 | Nist 2569 Rev 04 - clause 5.10.9
| note | ecddb907-eca9-4771-95a2-088c302dc6d1 | ACCEPTANCE CRITERIA: As per IFC drawings and within stated boundary requirements.
| note | 92fc638a-c493-4148-a38c-8f3e41b795af | METHOD: Visual and Measure
| note | 3bd1b58e-7009-4350-bc5a-f3443f93d124 | FREQUENCY: Prior to Commencement Each lot
| note | 1fcd7564-4c7b-45a9-8c44-c3c68226b1f8 | CATEGORY: IP/SP
| note | a9921db5-256f-4545-b25e-e0a90a155d9a | RESPONSIBILITY: Surveyor , SE
| note | 6085f120-c9d0-439f-9769-6c464d99e77b | VERIFYING DOCUMENTS: Sign ITP
| textbox | f36a9322-0e9b-4a76-b97e-99123d67cfa3 | Date Completed:
| checkpoint |  | 3.2 Clearing and Grubbing
| note | 5d2cabdb-ad85-4d4b-892b-1b11c2bfac01 | REFERENCE: Nist 2569 Rev 04 - clause 5.2.1
| note | 88fe7b68-9769-40ec-ad2e-f2710a3a4174 | ACCEPTANCE CRITERIA: Clearing and grubbing must be undertaken to the full width of the earthworks profile. Where an access road is to be constructed, clearing and grubbing shall extend to the extents of the access road and any ancillary earth formations required therefore
| note | 50e19272-e3cb-458c-bded-c014935a85aa | Clearing and grubbing includes removal and disposal of unsuitable material such as trees, stumps, timber, vegetation, rubbish, redundant materials and buildings
| note | 5857bc3a-246b-4bac-a99b-5da29077b491 | METHOD: Visual
| note | 9f5c3338-74af-4b79-92fc-0a41514d8433 | FREQUENCY: Each lot
| note | 71932ec8-9662-4691-b13d-0c6697947b3e | CATEGORY: IP
| note | 1c4e4af6-fbf2-460d-8385-a1b731fa8639 | RESPONSIBILITY: Site Engineer
| note | dc848f42-9e82-4388-95df-f00b844fed15 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 94946dae-aea0-4f9b-9cf6-0a4283e8b600 | Date Completed:
| checkpoint |  | 3.3 Topsoil removal
| note | 87d3f8e2-8247-4ed2-859a-9f143d499342 | REFERENCE: Nist 2569 Rev 04 - clause 5.2.2
| note | 9e1221a0-6b85-4d6d-956a-6a74252cc6cc | ACCEPTANCE CRITERIA: All topsoil shall be removed. Topsoil shall be placed in a stockpile clear of the work to enable its reuse in landscaping
| note | 24c4beec-6ac8-4b03-ac0a-a2c40c5c1e43 | METHOD: Visual
| note | a2bb35fd-997a-4414-914b-85d7d02c538f | FREQUENCY: Each lot
| note | 4b0deb7c-93ce-4b1e-b60d-8fcf331d108a | CATEGORY: IP
| note | 40693b96-7105-41fa-a3b9-0c61310e3e80 | RESPONSIBILITY: Site Engineer
| note | d64c28ed-fd68-428b-b040-5b4cc4dd31d9 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 6d86ddd4-b2a9-4961-b7d3-c225a867e8d4 | Date Completed:
| checkpoint |  | 3.4 Unsuitable Material Testing/removal
| note | eef6dfca-4b21-4c21-bb3c-8894a271e000 | REFERENCE: Nist 2569 Rev 04 - clause 5.8
| note | 4c8a85d2-78d9-4644-a07a-6a44dd8370e3 | ACCEPTANCE CRITERIA: Unsuitable materials must not be used as untreated subgrade or as fill. Unsuitable material includes:
| note | 4f9f7d0c-1b8c-4755-94d3-4929b60fc496 | Materials containing stumps, weeds, leaves and other organic materials
| note | f6b32514-b6d3-4672-9722-bfdf12df1a61 | Acid sulphate soils
| note | 47ec3732-47be-481e-ba93-95246b3d218c | Any material with CBR < 2%
| note | 5372c946-abfe-4111-a919-8018f6e62df9 | Dispersive material with unacceptable classification
| note | e6b73a74-3c92-4ed9-9648-832271c8805d | Material with a free swell index greater than 3%
| note | bc8ce20b-3555-4fb7-8327-0fba85a50f9d | METHOD: Review Test
| note | 7047ffcb-71d4-4d68-8767-979299274c23 | FREQUENCY: One test for work area
| note | 2e69b71a-9bb0-46e9-915a-7796a309f6c6 | CATEGORY: HP/TP
| note | 3a625011-83ea-487e-b836-4151c2e9028b | RESPONSIBILITY: SE/Nominated Authority
| note | 115055f1-f187-482e-95cb-41b742a87c3d | VERIFYING DOCUMENTS: Sign ITP
| textbox | e6299f10-33d5-46d6-8f48-d9aaea2a14f6 | Date Completed:
| section |  | Subgrade Preparation and Treatment
| checkpoint |  | 4.1 Subgrade Preparation
| note | 38337087-5e36-48f1-bf4c-213afbccfa39 | REFERENCE: Nist 2569 Rev 04 - clause 5.3.2
| note | 187d9b10-849f-46c4-b72d-b8042d741dff | ACCEPTANCE CRITERIA: The subgrade level shall be excavated to a minimum depth of 200mm below top of subgrade level and excavated material placed to the side
| note | 0afaef5c-49b8-45e2-8ae7-078f7449b9f6 | The exposed surface under the removed subgrade material shall be compacted and the compaction assessed by proof rolling
| note | f20b8710-e82d-497a-9e24-a339b082cb90 | The removed subgrade material shall be uniformly mixed, placed and compacted to 98% standard dry density (RD as per AS 1289 Appendix 3)
| note | 3e73fa7e-7f98-4a07-8946-9617307854be | An alternative option to remove, mix and replace subgrade material is to apply a rip and recompact method of 200mm depth
| note | 6b5b48c2-2c75-42f2-83ac-ace6e6d6e689 | Proof rolling shall be performed in accordance with proof rolling guideline requirement
| note | 37095632-66b8-414f-a38f-d522e16db4fe | METHOD: Review Test Proof Roll
| note | f0311127-17bc-421c-9f64-77da622ca239 | FREQUENCY: Each lot
| note | f571f7f7-ed55-4acd-a410-1c807072e000 | CATEGORY: HP
| note | e2ed3635-4c6e-4079-bb65-0c2a7e8efc98 | RESPONSIBILITY: SE/Nominated Authority
| note | 0bc57298-73f1-4d79-95b6-74bd593234e3 | VERIFYING DOCUMENTS: NATA Certificate , Sign off Proof Roll
| textbox | 64f50abe-6fbb-4139-950a-5938d839eb08 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.2 Subgrade Treatment/Ground Improvement (where subgrade has failed)
| note | 1863a105-64d0-4fb2-96ac-9d621abe74d8 | REFERENCE: Nist 2569 Rev 04 - clause 5.3.4
| note | a7f6b0c5-66f2-44ce-a517-719f3f4d6bd2 | ACCEPTANCE CRITERIA: The minimum treatment for unsuitable subgrade shall be as follows:
| note | 8a11306f-207b-46f3-af73-9fd8434a120c | Subgrade shall be scarified to a minimum depth of 200mm below top of subgrade level
| note | d126f8c1-2800-4047-876d-d220196ae401 | The exposed surface under the subgrade level shall be thoroughly compacted
| note | 118350fb-96f1-4712-a504-f59f09db7c3f | The removed subgrade material shall be either:
| note | f688f7a5-c4e9-466f-9130-ab46af07c8a1 | Uniformly mixed and blended with imported materials (graded materials, lime, cement etc)
| note | d5e83669-fcb8-4c77-ab2c-ad55c5db86a9 | Disposed and replaced with structural fill materials
| note | 5830c3fb-a701-42b7-b5f2-118be2472f92 | The treated material or engineered fill shall be placed and compacted to 98% standard dry density (RD as per AS 1289 Appendix 3)
| note | f34edc18-4b48-4888-aee1-d076352f5d19 | Proof rolling shall be performed in accordance with proof rolling guideline requirement
| note | e0fd4d84-37b3-4f08-a81c-a8628edb1efb | METHOD: Review Test Proof Roll
| note | 6692111a-7edb-4028-93f2-cf5b7ef62df8 | FREQUENCY: Each lot
| note | b917de24-37ec-499b-b7fa-2895e9a7e357 | CATEGORY: HP
| note | 36476b77-d798-4162-a173-284a48383d60 | RESPONSIBILITY: SE/Nominated Authority
| note | 7f1b0651-df20-4aa5-8892-9b19caf813e6 | VERIFYING DOCUMENTS: NATA Certificate , Sign off Proof Roll
| textbox | 7b607c16-54c8-4159-88d0-119786fa3351 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 4.3 Slopes and Slope Stability
| note | 13fd79d0-dea7-4c58-8254-15401e756ac2 | REFERENCE: Nist 2569 Rev 04 - clause 5.4
| note | 776fa10e-a27a-4355-bc04-3f875cc76c6b | ACCEPTANCE CRITERIA: When the depth of cutting is greater than 1m, geotechnical advise may be required
| note | 1f7ce94b-d748-4938-be3d-2b1122870853 | Guidelines for typical maximum batter slopes is shown below (vertical : horizontal):
| note | 1d3d8781-6f53-4bfb-8d59-28b2589781bb | METHOD: Visual
| note | 3a281f22-071c-437a-ae23-09c4a8a67a00 | FREQUENCY: Each lot
| note | 59477cbb-a70f-43dc-92e4-bb335ceb3546 | CATEGORY: WP
| note | 279fbefb-8434-4caa-a6ba-b11acf1902a5 | RESPONSIBILITY: Site Engineer
| note | ee854bd3-0fa7-4042-bd1c-a1ffc5c3ca91 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 2056dec6-d98a-4fa6-927c-cca883fc8650 | Date Completed:
| checkpoint |  | 4.4 Drainage Blankets
| note | 4e57f4d9-3a92-4d99-8f29-2bae9e842721 | REFERENCE: Nist 2569 Rev 04 - clause 5.6
| note | b9217679-b077-4d75-b6af-8cd864dc33c2 | ACCEPTANCE CRITERIA: Where a drainage blanket is to be provided at the base of an embankment, it will comprise of a geotextile laid along the base and around a layer of free draining filter material up to a 300mm depth with spall protection at the outlet.
| note | b4f426ea-8aac-48b8-8187-cf8ecfd3e8b9 | Free draining filter material will meet the below requirements:
| note | 87f4f52c-fae9-4ea2-b801-4bbddd8b70a2 | METHOD: Review Tests
| note | 04794c3d-d7d2-4d8a-83ea-02ad3003e9c6 | FREQUENCY: Each Lot if required
| note | 74c0af3f-9951-4251-a8f0-9116005dbe74 | CATEGORY: IP
| note | d8af75fc-8a41-4aea-85a9-476d8a0d4445 | RESPONSIBILITY: Site Engineer
| note | 0a90f55c-de0e-4f36-b7a6-88cf9fd29e96 | VERIFYING DOCUMENTS: Grading and material test results
| textbox | 1a4481c8-b368-44a0-a950-44c108088b6f | Date Completed:
| section |  | General/structural /capping fill Placement
| checkpoint |  | 5.1 General Fill Material Placement
| note | 39b31c47-cbb1-4060-b195-382c22b50be1 | REFERENCE: Nist 2569 Rev 04 - clause 5.7
| note | ec85b222-4ffe-404e-a8b5-74dd4f25f9f5 | ACCEPTANCE CRITERIA: General fill is to be placed in layers of uniform thickness, not exceeding 200mm loose. Each layer is to be proof rolled and Tested(see item 5.5 & 5.6)
| note | 3e87fac8-d547-407a-878e-b577258dbcb4 | METHOD: Visual, Review Test
| note | f407dacf-b775-4a34-804e-2831326fb71b | FREQUENCY: Each Lot
| note | 0388db88-212d-49d0-b19d-96146b3ac6c8 | CATEGORY: HP
| note | e07f4fd5-2ada-489d-9e1f-196530509498 | RESPONSIBILITY: SE/Nominated Authority
| note | d22b1bff-7746-4733-b35c-b97a84cfb74a | VERIFYING DOCUMENTS: Sign ITP
| textbox | cd501121-7f68-4882-a6a2-84b4aef3c735 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.2 Structural Fill Placement
| note | 51c997c1-22d4-40dc-8a51-03ac41c5dcae | REFERENCE: Nist 2569 Rev 04 - clause 5.7
| note | 4bdd2c9c-0262-4c5f-b814-93e175b6bdc3 | ACCEPTANCE CRITERIA: Structural fill is material used to construct the top 200mm to 1000mm of track formation, directly below capping layer. Structural fill will be placed in layers of uniform thickness, not exceeding 200mm loose. Each layer is to be proof rolled and Tested(see Item 5.5 & 5.6).
| note | a684da14-c78e-4b1c-9f48-f3783ef42964 | Depth of Structural Fill shall be as below
| note | 9a9e85ab-66e6-48d6-b35d-91e0dd3654ad | METHOD: Visual, Review Tests
| note | 98a08a44-2ae1-42c4-b028-36bb0a9e2c17 | FREQUENCY: Each Lot
| note | 0e19081b-17cd-42e3-ac8d-ce2f7b0b6ec7 | CATEGORY: HP, IP
| note | b23665d2-1722-43f5-b241-46141b4ad848 | RESPONSIBILITY: SE/Nominated Authority
| note | 45b4b61e-d868-496c-b5ae-861b496dff0b | VERIFYING DOCUMENTS: Sign ITP
| textbox | 3637fb47-4280-4db6-8d6f-142a253bd9e5 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.3 Capping Placement
| note | 6ba7c50a-9865-448e-ba04-8dc9d995284a | REFERENCE: Nist 2569 Rev 04 - clause 5.10.2
| note | d7c9fb2d-4912-4344-9889-03c4b484c6ee | ACCEPTANCE CRITERIA: Prior to placing capping layer, the structural fill material will be trimmed using a grader blade to the final profile and compacted by a minimum three passes of a smooth drum roller (10T minimum weight)
| note | 6aed48ce-f7d1-4a5c-9e72-780452b523d4 | Capping layer shall be constructed in one or several uniform layers to a total minimum compacted thickness of 150mm or as per design. No single layer shall be greater than 150mm and less than 100mm. Water shall be added as required for moisture conditioning and achieving optimum levels.
| note | 3a310fca-5e10-4d52-abcb-0481e9545fec | Capping layer will be proof rolled prior to placement of ballast and tested (see item 5.5 & 5.6)
| note | adebb7b7-5568-4d02-ae03-2b6b9c8f411a | METHOD: Visual , Review Test
| note | 20ab0af0-7b53-4f74-bbd7-4c35469365d3 | FREQUENCY: Each Lot
| note | 17cd41be-6a05-493e-a438-989d3b3c151e | CATEGORY: HP , IP , HP
| note | af60fe3d-35b8-4864-b580-6d7e4917e60f | RESPONSIBILITY: SE/Nominated Authority
| note | 9eb4993e-feea-4463-8f5c-21d6a9f5a5f0 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 8b739f81-092c-43ce-89f0-288b7ed2744c | Date Completed:
| checkpoint |  | 5.4 Earthworks Near Structures
| note | 5a87ae27-e6f5-42d6-a13b-4f850dce63a6 | REFERENCE: Nist 2569 Rev 04 - clause 5.12
| note | d0ce74fa-e6eb-411d-9b3e-9bbd29c03d16 | ACCEPTANCE CRITERIA: When constructing earthworks, within 5m of existing structures, additional care shall be taken as follows:
| note | 853816a0-c021-4add-a5a0-2709e43f369d | Non-vibratory equipment shall be used within this distance
| note | 176db7ac-d834-4b30-abf7-27d0cd834054 | Backfill material complying with NIST-2616 shall be used adjacent to structures. Where fill material below the capping layer has a CBR less than 8%, structural fill shall be used.
| note | dfabc3b5-f796-4ef2-b3f5-51fc9e46094c | METHOD: Visual
| note | b64a892e-c871-4711-9494-ef92f97cab76 | FREQUENCY: Each lot
| note | b9a91947-f835-4da4-a503-e7f4c70a3630 | CATEGORY: IP
| note | 03cb85b7-a968-45d4-b9ee-1ffdefd281ae | RESPONSIBILITY: SE
| note | 3724962d-de21-4413-bb2e-91957e9c3060 | VERIFYING DOCUMENTS: Sign ITP
| textbox | 56f25cc3-604b-42e7-8b89-fc22ffd87e81 | Date Completed:
| checkpoint |  | 5.5 Proof Roll (all Placement)
| note | cd701d8a-8815-4d09-a8cc-c5270c4a6f85 | REFERENCE: Nist 2569 Rev 04 - clause 5.9
| note | 07dd0b9a-b697-44fa-8385-826d88c07a07 | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
| note | 6de66370-278e-4852-9f7a-a071bffefe77 | METHOD: Visual
| note | cf629d50-8880-4f0d-a246-2d99ae4c93f4 | FREQUENCY: Each lot
| note | 8776db3b-26b3-48b7-8f66-3efea96f92c9 | CATEGORY: HP
| note | 36b02d20-333a-4845-8a02-6b2a086a1a9c | RESPONSIBILITY: SE
| note | 426b9219-1b01-4552-814d-8fd3c05fcb5b | VERIFYING DOCUMENTS: Sign ITP
| textbox | 6ee4cd15-7094-45c5-b322-dea1e000839a | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 5.6 Post Compaction Materials Testing(all placement layer)
| note | f3078b13-62e5-4194-99fe-51a08aa24b9e | REFERENCE: Nist 2569 Rev 04 - clause 5.9
| note | bf62ebd3-ecb0-404e-9ca8-c29d94a4c5f9 | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
| note | ddbb2b1b-aa60-4193-8a26-e86fefc2500c | General fill-Compacted & tested at 98% standard dry density ratio (RD) and have a soaked CBR ≥ 2% (95% standard compaction - 9kg surcharge) . It must be free of particles greater than 150mm in diameter.
| note | b94c75f5-6f85-4b2d-b3b0-4966b5bd0bd6 | Structural fill-It shall be compacted to a minimum 95% modified dry density ratio (RD). The product of the LL and % passing 425-micron sieve must not exceed 1800mm.
| note | c36bcdcf-9e80-453f-8bdf-9cafb613b276 | Capping shall be compacted to a 95% minimum standard dry density.
| note | d3e9583f-ad41-4b4c-9cd0-9ae430cfa28c | METHOD: Visual
| note | f3f7da36-d838-40b5-9158-e87b3ba6f506 | FREQUENCY: Each lot
| note | 3eee1a30-dd32-45fe-aae8-1c60e58115ae | CATEGORY: IP
| note | 8710e743-a5eb-4a77-9611-84ebeb3e9c33 | RESPONSIBILITY: SE/Site Supervisor, NA
| note | a8c125d1-4671-4a80-9118-2e5f1a50b39c | VERIFYING DOCUMENTS: NATA Certificate
| textbox | a03d0108-3b28-411f-b7a6-22a8fbf2c0ee | Date Completed:
| checkpoint |  | 5.7 Formation Reconstruction or Repair (permanent or temporary measure)
| note | ac0385d9-904f-4b4a-b04f-9a2cce400e57 | REFERENCE: Nist 2569 Rev 04 - clause 5.15.2
| note | 9853d784-d4af-4c72-8ea1-466083958d15 | ACCEPTANCE CRITERIA: During the May ROB-05 Occupation, there will be a requirement to reinstate capping material that is excavated/disturbed from piling activities. This capping material will be locally placed and compacted to achieve the compaction results as Section 4.7.
| note | abb0df81-6d28-4522-83ff-27a23712b19c | A proof roll may not be possible to conduct due to the small localised areas
| note | fb6226ae-853e-4cb7-ac20-39819d765e74 | METHOD: Visual Review Test
| note | 8a1df8cb-973d-4525-9ab5-ea7939e03231 | FREQUENCY: Each Lot
| note | 55fe3800-0472-4b39-b72b-b88dff2f57fb | CATEGORY: HP
| note | b1c14f75-f6ee-445b-886e-5d6b4780b3ee | RESPONSIBILITY: SE/Nominated Authority
| note | 425faab6-d3b1-4132-b246-091f0f2149aa | VERIFYING DOCUMENTS: Sign ITP
| textbox | b691ae7d-b405-4f3c-be18-52f1bd9fc186 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Post-Construction Activities
| checkpoint |  | 6.1 Finished Tolerance of Fill Materials
| note | f342dc35-d939-419b-aeac-72a48e2e7b13 | REFERENCE: Nist 2569 Rev 04 - clause 5.9
| note | 22096765-289f-452b-aa7d-9d700476541a | ACCEPTANCE CRITERIA: Finished layer surfaces for the interface between subgrade and formation and each distinct layer making up formation (both general and structural fill) shall be prepared and trimmed to the following tolerances:
| note | c62e79c6-9992-4701-99f9-c44ebc1baeb5 | Surface level of complete formation = +0mm to -50mm from design level
| note | 77ad73ce-6f62-401b-b802-acac752ff16b | variation in completed surface = +50mm to -0mm from 3m straight edge
| note | 406de6b2-c1cf-4d02-843c-149a9e703116 | Formation width = not less than design width
| note | 43bf373a-7415-429c-aaf9-b7da7ada9645 | Note: if the structural fill material will not be covered immediately with capping, or is expected to be heavily trafficked, the layer will be placed 30mm higher than design to allow future trimming prior to capping placement
| note | 15dcd1cc-3cac-4aab-8e8e-465dbeb71c9d | METHOD: Document Review
| note | b3a320d1-6068-4ff6-bea4-99d2ebfacf09 | FREQUENCY: Each Lot
| note | b32f997f-09a9-48cd-a7d6-ad4f2a84d03a | CATEGORY: IP
| note | a0b5d955-fd74-47f9-b7d4-c70c73f186a9 | RESPONSIBILITY: SE/Surveyor
| note | 83e72eb6-53f7-4310-ae9e-0105697017a7 | VERIFYING DOCUMENTS: Survey conformance report
| textbox | c658e8b0-0cf6-47fb-bbd6-732b01fc9d25 | Date Completed:
| checkpoint |  | 6.2 Finished Tolerance of Capping Layer
| note | 9ae4981a-2822-45e1-853a-c3c9ba0b5361 | REFERENCE: Nist 2569 Rev 04 - clause 5.10.2
| note | fe15880e-16cf-4e42-b698-c6e99f8c5c27 | ACCEPTANCE CRITERIA: Capping shoulders shall be a minimum 1000mm from toe of ballast to outer edge of capping, or as per design drawings.
| note | 67209e09-1f51-4086-bdcf-bf7dadafa0c3 | Capping layer shall be well distributed with course/fine particles to create an even surface free of segregation.
| note | 336d7d48-7ba6-42d2-81cf-ecfc4b06bfe7 | The Capping layer shall be such that:
| note | 0ab05631-ec11-4379-baab-4a6711648e66 | The finished surface is within 25mm, but not above, of the level shown on the drawings
| note | dcc4b4d4-2bb8-4e35-865e-eb8cd49bf2b0 | The difference of deviation from correct level for any two points 20 metres apart on the centreline shall not exceed 15mm
| note | 35d1d666-a73c-4603-90e1-5fffd622b5a0 | The deviation from a 3m straight edge laid on the surface parallel to the centreline shall not exceed 10mm
| note | d5adea03-02b9-4282-abd6-2d09af368f11 | When tested with a 3m straight edge laid perpendicular to the centre line the deviation shall not exceed 10mm concavity
| note | 5ba230a6-d4e8-4339-b95c-dfca81ae9f4c | METHOD: Document Review
| note | c83c49c2-3be9-42d1-b103-c51cd14e7fbd | FREQUENCY: Each Lot
| note | 63473518-182d-4eea-8ee2-3073caf1bd37 | CATEGORY: IP
| note | 4280ec6c-93bc-4bf8-96a1-f12f5d0ad09a | RESPONSIBILITY: SE/Surveyor
| note | ecad0967-42b9-4357-a6ba-f37f09f6523e | VERIFYING DOCUMENTS: Survey conformance report
| textbox | 816a3d3f-dffe-47c1-b7bc-00a3dcb8f6a2 | Date Completed:
| checkpoint |  | 6.3 Non-conformance Report (NCR) Closure
| note | 30035917-ba1d-45fd-a419-9544283dcdf5 | REFERENCE: MRPA Quality Management Plan
| note | c84145b9-b813-4489-88cc-aca5ebf7bd14 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | a11de415-3f42-4c4a-bf0b-3d15796baad6 | METHOD: Document Review
| note | d81afa1d-0727-4655-a699-edb4729241e9 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 4227f714-e363-4696-9d75-9293f1af86d1 | CATEGORY: HP*
| note | bcce0dfb-4810-4d98-b17a-a9668d53dada | RESPONSIBILITY: SE/PE/SPE
| note | 5994716d-70cf-4067-9f60-d08c5efee9ed | VERIFYING DOCUMENTS: This ITP
| textbox | ced64841-b888-491d-9eca-df44d28e290b | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 525b7bc7-4ede-4aa4-9014-c472623ceb6e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | cca3db86-9271-4386-88f1-94b984e4b3c9 | Name:
| textbox | 3938fd5e-c66c-459f-936e-0b4e1d2e65a4 | Position:
| textbox | a6ffce60-31e8-4dcf-b5a4-192153272d98 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-STR-Miscellaneous Structural Steel (Supply & Installation) Rev 0 | itp | ITP-STR-Miscellaneous Structural Steel (Supply & Installation) Rev 0 | d943c4a6-6ffb-415c-912a-acbfc3426bf9
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | c25c3f49-166f-439b-97fa-1d2ee4a0c37f | Document Title: ITP-STR-Miscellaneous Structural Steel (Supply & Installation)
| note | 93cd5325-e508-41f1-9255-849b5689ea75 | ITP Description: Miscellaneous Structural Steel (Supply & Installation)
| note | b108da0b-15d7-4251-abd0-384f8bf51045 | Discipline (e.g. CIV/STR/RAIL): STR
| note | f8444de8-c022-4dc4-a4ee-0c2e68469b25 | Revision Number: 0
| note | 4931b9c6-066e-4377-9248-1fa24cfc03ac | Revision Date: 4/05/2021
| note | f774fc56-18d3-4ae7-a895-cad26d116976 | ITP created by: Mike Freeman
| note | c1b57e1b-b118-4dec-b704-3bcfb1d6c1e7 | 1.1 VicRoads Section 610 November 2018
| note | 54de273d-2394-40a3-97e6-12b39f39f7cd | 1.2 VicRoads Section 610 March 2019
| note | ccb161fc-7d91-4d13-b353-02e99f646ac6 | 1.3 VicRoads Section 610 June 2019
| note | 625a542e-4364-4388-87f4-2db753a55ef2 | 1.4 VicRoads Section 630 October 2013
| note | 4ca683b3-f23e-4c06-8e3f-c04cbbc36ed9 | 1.5 VicRoads Section 631 February 2009
| note | adcdacc8-733b-4ff9-b06c-2ea9090916e6 | 1.6 AS4100-1998
| note | ac1d9a7d-e5c6-4617-b64b-2587886af1b4 | 1.7 AS5131-2016
| note | fde9727c-0350-44c5-a5b7-57e9ba736b53 | 1.8 AS4680-2006
| note | 571de948-7f7c-43d1-b451-ff58553e0b1e | 1.9 AS2312.1-2014
| note | f85c26ea-ec4f-4d8d-a658-16e0762062e4 | 1.10 AS4506-2005
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Structural Steel Components
| note | 3b4fff29-7637-47d7-bdfc-fda5c2717a95 | REFERENCE: IFC Drawings
| note | 6f0d585c-a3ef-4676-b35d-7624eb0a7031 | MRPA Quality Management Plan
| note | 7d7d45cc-6713-4859-8908-0e8e8accb17d | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
| note | 9db3b64c-7cf4-439c-a87f-981482d853cd | Typically this consists of but not limited to:
| note | fd2f5f5a-4b42-47fd-9f0c-f4a97b03d648 | i. Certificate of Compliance
| note | 0e0dca0e-3292-4b6b-a891-7ee3349d6627 | ii. Completed ITP
| note | 3989fc75-5fd7-429a-b9c9-11f96687779b | iii. Weld Procedure Specifications
| note | a4fd8777-27de-4c84-9388-ea34cf869059 | iv. Weld Procedure Qualifications
| note | 74797a3b-8c3f-4df4-949c-7de4c215694b | v. Welder Qualifications
| note | d9aa03fc-4db7-4f91-89bc-c545e03cdec2 | vi. Material Certificates and traceability
| note | dd34d510-b327-4b3d-9e6e-74a83aa2ff86 | vii. Quality Assurance check sheets
| note | 01c1b506-d25b-45e4-bada-e836fdfc49a5 | viii. Welding Consumable batch certificates
| note | 81308cfe-7728-42b9-9976-11a61b33779e | ix. Coating certificate(s)
| note | c1168043-152c-4f4b-88fd-0dd79e3ece8b | x. Non-destructive Testing (NDT) Reports
| note | 88a68d9c-2bc1-4c4f-a2a0-e8b427994850 | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
| note | 7889ee00-557c-4540-aa1d-6244070532fe | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | f117865a-d6aa-40ed-b94b-344d179be5ac | METHOD: Document Review
| note | 773c5058-aa85-47e5-94f8-ab37cea4cd9a | FREQUENCY: Each component
| note | 9e2d7e69-41d9-43fa-9ed1-9a93dd2d35e6 | CATEGORY: IP
| note | e5ffb90a-7565-4b94-8203-feb1bf8e9f5e | RESPONSIBILITY: PE/SE/SPE
| note | e6b012e1-fc6a-4307-9fcb-cb0f281d1f07 | VERIFYING DOCUMENTS: This ITP
| textbox | 15c7151f-cb42-4fbb-84bb-ccd26c8554c0 | Date Completed:
| checkpoint |  | 2.2 Base Plate Structural Grout or Mortar
| note | 28f69d78-b620-4d8b-93c6-0978cf3b8be5 | REFERENCE: IFC Drawings
| note | 08f02dc8-1193-4f4f-8bdb-bcfa93169825 | 610.33
| note | d7b302b9-c611-4025-bcd5-e1041aa0e857 | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
| note | ab80eaf2-d4c8-42e3-90d6-755c85a6ee6c | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
| note | 63d82404-3606-47ae-99fa-de42c29d4a30 | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
| note | ea8f984c-1144-4c4e-a258-83f37f37aeca | iii. have a flowable consistency
| note | 1758a85a-e8a2-41d2-8a03-ee0c82ccb518 | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
| note | d0ca6e11-aef9-484a-8059-79fbb5f691d6 | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
| textbox | 213926b9-7dce-40b3-a403-72dc448474aa | Enter: Teambinder Material Approval number
| note | 51609451-a43b-4c27-8fa0-c81ee685deba | METHOD: Document Review
| note | ed279f1e-b887-4023-8356-021625e7d7fa | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | ecfe2182-3cfb-4615-8557-d5c1f8aefc87 | CATEGORY: IP
| note | 46030d30-6006-452c-90cc-a99a746df8f6 | RESPONSIBILITY: Nominated Authority
| note | 5ac54356-7249-40ee-99a0-90c2ae289196 | VERIFYING DOCUMENTS: This ITP
| textbox | df516284-e521-4b55-a12b-4a408dfb1c3b | Date Completed:
| checkpoint |  | 2.3 Curing Compound
| note | 602abd8e-ee5d-4cc1-8e9f-bd34d39e124e | REFERENCE: 610.23 (d)
| note | 4475b65e-084b-4a35-8d60-c0c8885ed439 | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| note | 20546251-8018-4cf5-a721-b894ab2e5887 | Note: This may be the same product used for the concrete curing
| textbox | 85ec795c-e388-4d49-9053-b07f8bf47110 | Enter: Teambinder Material Approval number
| note | c9326581-e413-490f-a392-1473316f104e | METHOD: Document Review
| note | 21400609-af44-4350-b429-518a227d2bf4 | FREQUENCY: Where applicable, once, for each product, prior to placement of product
| note | 2c7062e0-a364-4909-817c-eb86b785cbfd | CATEGORY: IP
| note | dd6f9b56-bf85-4705-ba26-ddc724a19246 | RESPONSIBILITY: Nominated Authority
| note | a82cc1bd-5a91-4465-8162-357762ea614f | VERIFYING DOCUMENTS: This ITP
| textbox | 187e64f6-b6ae-4819-933f-40f3fba52d13 | Date Completed:
| section |  | Preliminaries - Procedures
| checkpoint |  | 3.1 Curing Methodology (for Grout and Mortar)
| note | 909b8d49-25d2-4646-a90c-06a0a6b308c7 | REFERENCE: 610.23 (a)
| note | 44234c52-c977-457a-a330-dd716cc79e73 | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
| note | 2ff5a7c7-db4c-4888-b40b-6a3146cd177e | Note: This may be the same document used for the concrete curing.
| textbox | 066cf4d1-8501-4ba4-898c-ca0430acb085 | Enter: Teambinder Approval number
| note | 4a25bdd0-896b-4750-8daa-7f12c916c47f | METHOD: Document Review
| note | b2382c58-64ea-409c-99fa-36ec2463e712 | FREQUENCY: Where applicable, once, 4 weeks prior to placement of product
| note | 97998c79-e7e5-459d-afd1-8cabef15537a | CATEGORY: HP
| note | 8549d64e-582a-47b1-9f0a-b6f050cd83eb | RESPONSIBILITY: Nominated Authority
| note | 6a3985e7-5948-4f49-97e1-3eeb0b88259d | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | b356f739-def9-467d-b094-507747d8c015 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Bolted Connections Using Direct Tension Indicators (DTIs)
| note | 12e9ec60-5a1c-4abb-abc7-53fa6af7456d | REFERENCE: 630.20 (e ) (ii)
| note | 42e7feea-9744-4bd4-beff-eac4205e9c53 | AS4100 Clause 15.2.5.3 (a)
| note | e55a8650-ce4d-4fee-92a8-58a19adf46fb | AS5131 Clause 8.5.7 (a)
| note | a9ff77ed-d7c4-49ea-8477-215fccfd5801 | ACCEPTANCE CRITERIA: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
| note | 49838752-509d-4623-8155-db3e07f722f3 | i. technical data sheet or information on the product
| note | b706a787-efe5-4825-b537-ed06759d32f2 | ii. 3 no. min. correlation tests between a calibrated torque wrench and a representative sample of each bolt diameter/length/grade combination to be used in the Works.
| note | 7d1481d4-0a6b-4319-b001-fe36626eff64 | iii. a valid calibration certificate of the torque wrench
| note | 047d18f6-a877-41dd-95cc-90e991aa4634 | Note: Daily records of use and correlation between a calibrated torque wrench are required, see 6.3 in Post-installation.
| textbox | 5263cf9c-3882-4808-b956-2108cc24fa5f | Enter: Teambinder Approval number
| note | 0646dcbd-84d9-44c9-9b01-504b23a91401 | METHOD: Document Review
| note | 6a5c4eeb-9220-4241-bc6b-a96d4f4be265 | FREQUENCY: Where applicable, once, 14 days prior to use of devices
| note | 5df7005e-455e-40dc-a9a0-7485b30f1606 | CATEGORY: HP
| note | e93e4273-777c-441e-aee2-9468f25e0bc7 | RESPONSIBILITY: Nominated Authority
| note | a7848124-79fc-46cb-aa57-d916702d2a3b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 67bab63f-fdb4-43a7-9024-00f2f8c0b712 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Pre-installation Activities
| checkpoint |  | 4.1 IFC Drawings
| note | 581e1dae-0ce0-4c4e-8fd1-8b92f5887c8f | REFERENCE: MRPA Quality Management Plan
| note | 5f7fa292-1f1d-4e4b-a53d-dcf3859a8959 | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | aa0e7acb-28fc-4321-8018-9953830adeea | METHOD: Document Review
| note | e813afdc-9c03-41d1-9eb7-3a278c9caef4 | FREQUENCY: Prior to starting Works and at regular intervals
| note | e4dc7cd9-3d1f-4fc1-97bb-709b96434a88 | CATEGORY: HP*
| note | ee49f113-463b-49a2-8682-373ef6aa1a42 | RESPONSIBILITY: All
| note | be4ead16-ec7d-4021-b4b3-86209d673c0b | VERIFYING DOCUMENTS: This ITP
| textbox | 415da6cf-0dc7-4bc7-9d3c-391059c7bfde | Date Completed:
| checkpoint |  | 4.2 Materials Inspection Checklist
| note | 311e71b3-2571-45e8-8bba-8a3c3eece92a | REFERENCE: IFC Drawings
| note | ecf605cd-ad26-4975-a8e6-46c7017fef18 | 630.08
| note | 4bce1b9f-85a0-4c49-8bba-5be2e3991f26 | 630.09
| note | 5632443c-259a-4157-934f-9e50253fbea0 | 630.20 (a)
| note | d730f6f9-f3d4-4bbe-a2ae-555344abf112 | 631.06
| note | a3383af8-e71a-4f74-bd50-c2f1e7832bf3 | AS4860 Clause 7
| note | 452b519b-5458-466d-908b-4e6fbfc4a92d | 631.11 (a)
| note | e7b6d9d1-295d-411a-997e-b7f3f3c928a4 | AS2312 Clause 9.6.4 (i)
| note | 863751fa-39ba-4dc2-9d25-bcaa043b24e1 | AS4506 Clause 2.3
| note | 7c4b1a41-d974-41f3-ac3c-ddd6d956efdb | MRPA Quality Management Plan
| note | 22f79d95-f02e-4182-a599-e734e4ef6bcc | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
| note | 02b13086-d04d-439d-bdac-082c2c2882c1 | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
| note | 7853f07a-03b8-422b-a6d3-7c1e9d721f72 | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
| note | e930a392-6eca-4d90-a727-584083e2ce2e | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
| note | 59a3d4ca-a78d-4275-a867-99c25220e99c | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
| note | 2b720a71-0492-4362-bfef-be0ee9e8d3b3 | Complete: Materials Inspection Checklist in ConQA
| note | 985c208d-49bb-4767-828c-8da0a1b71e6f | METHOD: Measure , Visual
| note | 64550164-b715-4ad8-a7a4-7336ccec9069 | FREQUENCY: Each component
| note | 0bab2c46-f66a-4ea4-8d23-7f6c20a78f43 | CATEGORY: IP
| note | afdff098-ee24-4cc1-ade8-3c71b5fc1ef9 | RESPONSIBILITY: SE/PE/SPE
| note | d0459782-d747-4ade-b11e-5de0286d376b | VERIFYING DOCUMENTS: This ITP
| textbox | 7fef3d77-7c06-46d8-b82c-1fe0a083fe79 | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 5.1 Bearing / Mounting Surface Preparation
| note | 3808180a-18a7-4a1d-b9bd-8df5000e56d0 | REFERENCE: IFC Drawings
| note | 9cbb73bf-0167-439d-9deb-2345d16b8f37 | Product TDS
| note | 15f7be2b-453f-45a1-82b4-3179bf553e0c | ACCEPTANCE CRITERIA: Prepare the bearing surface in accordance with the Grout/Mortar Product TDS.
| note | 1b629bb0-49d6-41c7-98a0-f7cd0acd3f38 | As a minimum, ensuring that it is clean and free from loose particles such as rust and laitance.
| note | be2c8389-f13d-4848-a297-d0b8bb8cd0ea | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
| note | e779d6ea-83b1-488d-b563-aa4dc464525b | METHOD: Measure , Visual
| note | 9af3cba5-1a1c-4d38-a12a-5b96e0421276 | FREQUENCY: Where applicable, each installation location
| note | dce53b92-a7be-4cb8-a168-6fe8c3df90f9 | CATEGORY: IP
| note | 2e0dc5de-f571-4aea-ac74-640847169c9a | RESPONSIBILITY: SE/PE/SPE
| note | e82c33fc-f4a5-4ef8-a12e-c7736f00c12e | VERIFYING DOCUMENTS: This ITP
| textbox | 843f8645-6bf3-4abe-9de1-af1e3f198ed9 | Date Completed:
| checkpoint |  | 5.2 Structural Steel Handling
| note | 42ad72a4-254b-421e-87c5-41354e6edf43 | REFERENCE: 630.09
| note | 7f6b9f00-60f3-4013-9e7b-3d8a0445c527 | 631.14
| note | 582e3723-7efc-484f-9e64-f93a742319d9 | AS4100 Clause 15.2.2 & 3
| note | fc60cf95-c660-4945-b244-aba422325144 | AS5131 Clause 11.5.6
| note | d8618d36-738e-4c28-a22e-b57ab5c3b905 | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
| note | 94bac920-ebbf-4fcc-a6aa-7981e88c4f51 | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
| note | e9a5116d-b29b-4504-a007-63b830bc6640 | METHOD: Visual
| note | c8ea75c8-5160-4a75-bdae-ae975fcff661 | FREQUENCY: Each component
| note | 442ae9bc-b405-43ad-a985-30877b6ff988 | CATEGORY: IP
| note | a02858e5-76ce-4da5-ac72-579932ac3f42 | RESPONSIBILITY: SE/PE/SPE
| note | abe1334e-7aea-4d17-bb3a-35033893bd44 | VERIFYING DOCUMENTS: This ITP
| textbox | 87cd91f3-1245-4ae4-a632-9a89db863bae | Date Completed:
| checkpoint |  | 5.3 Structural Steel Erection
| note | ce76e84b-2307-46c6-81d0-38274e23c8d4 | REFERENCE: AS4100 Clause 15.2.3
| note | 0c362376-540a-4daf-b533-9c80195a9dbb | AS5131 Clause 11.5.7
| note | 679adda8-53e5-4a27-a064-0e3c2ed6159b | 630.12
| note | bd50e908-3124-45cb-aa0d-ec579566ef7d | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
| note | 43f1909d-6136-40ad-a0e5-dfd54fe4a6a4 | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
| note | fca853fb-25e6-430a-94ec-9b5fecd588b7 | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
| note | 0bf7dc63-5a9a-485f-bcb1-29bee6d3e86f | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
| note | e3048d6b-e37e-4448-8df6-dd623214e021 | Holes shall not exceed the greater of:
| note | d7440328-9227-4df8-b99f-08ce971427b0 | 1.25 x bolt dia. OR bolt dia. + 8mm
| note | e64ac5c2-3fa5-498d-afab-d54b4c569444 | Slots shall not exceed the greater of:
| note | a71178fb-da4c-45de-b622-01b1e8a44d65 | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
| note | cbdc7459-a924-4a6a-97aa-5b7b52d04cbf | METHOD: Measure , Visual
| note | 81e4b34b-b738-45b7-a218-7723cf18b7a0 | FREQUENCY: Each component
| note | 1fa2df3c-6ad0-49e5-8f24-62ce676d3e77 | CATEGORY: IP
| note | 5fd6d943-2027-4065-84d6-5317beb2cd71 | RESPONSIBILITY: SE/PE/SPE
| note | e9c66b92-6e03-4cc7-9f6e-32e6bffb35f9 | VERIFYING DOCUMENTS: This ITP
| textbox | 6d67b88b-0490-4e63-96be-11328f402fb2 | Date Completed:
| checkpoint |  | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
| note | 1a4d03d9-d49c-4f1f-b565-be6aae4325af | REFERENCE: IFC Drawings
| note | 869c0d3c-c110-414d-b694-a08ebc1bdb00 | 630.20 (a) & (c)
| note | 27522a2e-95dd-4d06-a89e-75233b088092 | AS4100 Clause 14.3.5.2
| note | 4550cfa9-10f5-4262-ab7b-5a6bec647157 | AS5131 Clause 6.7.4
| note | c594520f-c03a-4f13-a298-45955db4cf50 | AS4100 Clause 15.2.5.2 (a)
| note | aadda739-6275-4523-8656-bfcdc0d88f00 | AS5131 Clause 8.3
| note | 9bddad2d-2445-4b65-8aa6-0f7a56a7c89b | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
| note | 2ad5e823-bc87-41cb-9e11-5e2cd8aa1426 | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
| note | 33196f15-036c-4f06-a529-a725a19b0147 | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
| note | 72099882-bc10-4643-a343-17f53b9e2aee | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
| note | 5f0461b4-e0a4-442f-851f-22064d114fb6 | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | b380ffac-63b4-4426-a05b-0cf0b9834e7f | METHOD: Measure , Visual
| note | 5e4f4967-c879-4560-b8c1-7d662cac85c5 | FREQUENCY: Where applicable, each bolted connection
| note | 43f473fe-0b96-4f01-916f-20cf9884050a | CATEGORY: IP
| note | 130f61a1-7601-451f-9a10-542b1f1f9937 | RESPONSIBILITY: SE/PE/SPE
| note | c91374a4-0c57-4ff1-882d-5b5c3006ae81 | VERIFYING DOCUMENTS: This ITP
| textbox | a588220f-6697-4ba3-8f54-9b3d44c27a8e | Date Completed:
| checkpoint |  | 5.5 Fastener Tightening - Tensioning Condition (8.8/TB & 8.8TF)
| note | a1082a95-f2b8-4d35-ab94-1c3c4686cd26 | REFERENCE: IFC Drawings
| note | 598c942e-4ec7-494a-b440-fd82739f63f8 | 630.20 (a) & (c )
| note | 9e3b8c2a-737a-402e-bb72-bcb661759337 | AS4100 Clause 14.3.5.2
| note | 8b96d7c1-9cc5-474b-bbfa-fdf2d54d49dd | AS5131 Clause 6.7.4
| note | ab338e41-ef9d-437c-b97d-c13f139adcb7 | AS4100 Clause 15.2.4
| note | 062a32a6-f4b5-4000-85e6-17596f3d918c | AS5131 Clause 8.5
| note | 711f7057-9b15-4184-99de-796e6bcdf3a4 | ACCEPTANCE CRITERIA: Nuts shall be either double faced or washer faced type.
| note | fe7c7315-1ef0-41e0-8376-8bf8d56d2bd5 | Place bolts, washers and nuts as detailed on the IFC Drawings with the high strength designation on the bolt and/or nut remaining visible at all times.
| note | 98ccdcc9-0f3a-40e4-b4ac-fbd30e5f4a59 | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
| note | 593ac2d8-c5f6-4c7d-96c7-0e78ba5d8781 | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
| note | cf5213b1-60ca-45c5-8ee5-6122577d305c | Tensioned fasteners shall begin with the snug tight condition.
| note | 1de9f12a-ae23-4e51-ad82-2d07cbc47dc4 | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
| note | 87a110c7-03f2-408c-88e7-a380d66e5db4 | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | af06f8b6-0a5c-4a0a-9540-cdcf7e63728b | Mark a datum point that crosses over the static part and the rotating part before tensioning via torque wrench, part turn method, stressing jack or direct tension indicators.
| note | c6298132-1b30-43f0-b07a-2bfeae21ce56 | METHOD: Measure , Visual
| note | e1a8f965-4f1a-4d63-be21-2f0010efba9f | FREQUENCY: Where applicable, each bolted connection
| note | 20af66f6-68da-4b3f-95a4-ba5b4ace0e53 | CATEGORY: IP
| note | 195752e0-2279-4f41-825d-9984e5519cc8 | RESPONSIBILITY: SE/PE/SPE
| note | b02e9824-441c-4b0b-9d82-a52063a3337a | VERIFYING DOCUMENTS: This ITP
| textbox | 8e5fa99e-b7a6-4b45-be27-10070144a5af | Date Completed:
| checkpoint |  | 5.6 Survey Conformance
| note | d3f78b56-1fd7-4926-af5b-e95c12f37c42 | REFERENCE: IFC Drawings
| note | c225bf58-4d56-4021-a041-15bf4e74f1da | AS4100 Clause 15.3.1 - 7
| note | 0244dbf2-15e7-4e05-ac7f-f99c30a13a19 | AS5131 Appendix F, Table F3
| note | 3a21713b-47ef-4a54-b7bd-8dd72eafe985 | ACCEPTANCE CRITERIA: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
| note | 2a3d9d13-b706-4ec4-b2a3-8a993d1884c6 | Departure from RL = ±10mm
| note | 9a1f3102-9bd0-4d33-91ae-bce2a6a509c0 | Departure from plan position = ±6mm
| note | c0fd9639-ce24-4ab5-a05b-417e4e35c3d7 | Departure from alignment = ±6mm
| note | 09ba30a2-3064-4159-88b9-ca4fe665094a | Irregularities in alignment = 25mm in 30m
| note | e70fd4ac-be3b-48b4-b565-d8cca54e20d9 | Projection of bolt = +25mm, 5mm
| note | 5df01675-4a29-4c61-af49-6548e994989b | Location of beam = ±3mm
| note | 26b99e2f-d77c-4513-ba09-c7d4e487bdf1 | Location of column = height/500, 10mm max.
| note | 60669d2a-2f9d-4d82-bc91-bcb5d795d288 | Attach: Survey Report
| note | cd43a0d0-89b6-4d3f-b871-a9785573339c | METHOD: Measure , Visual
| note | 5c93720c-00df-44a8-99c8-0853b43bad10 | FREQUENCY: Each element
| note | 87898743-6040-4a8d-b37d-a2b8e568cd57 | CATEGORY: HP*
| note | 19a5b8cc-da7d-49fc-853d-aef073c3e994 | RESPONSIBILITY: All
| note | 88ad6938-ed78-4285-bfab-8c13de7cb317 | VERIFYING DOCUMENTS: This ITP
| textbox | 3d2f9326-fe9d-4603-8c39-60807444d0f6 | Date Completed:
| checkpoint |  | 5.7 Base Plate Formwork Construction & Placement
| note | 1f2c8f6d-8734-4836-8590-deec12f71013 | REFERENCE: IFC Drawings
| note | 2f6b9c79-f29a-4cb3-9099-ca8cac2d24fd | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
| note | ba295afc-cf22-4401-adbc-426b9734e5cf | Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
| note | 59892eac-7f0c-4e18-b01d-91f5d28a5d23 | METHOD: Measure , Visual
| note | d552e37f-3af4-404f-9013-34f320b3393d | FREQUENCY: Where applicable, each bearing /mounting location
| note | ceeab0f9-e3e9-41d0-b760-888e54c819ae | CATEGORY: IP
| note | ae72dca9-c3dd-4b06-bdd8-63ac4ee19c6c | RESPONSIBILITY: SE/PE/SPE
| note | 2b397c39-9d42-4886-94ca-334baaf2c003 | VERIFYING DOCUMENTS: This ITP
| textbox | f082515c-b9c8-43a4-a410-9bd21d54552d | Date Completed:
| checkpoint |  | 5.8 Pre-soaking Concrete Surface
| note | f58f5545-ee9e-45b3-a97f-4ae5bafb1ca2 | REFERENCE: Product TDS
| note | c188b1f0-b583-409a-bc65-867a37bd4ba8 | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
| note | 81090973-aa3c-48a7-8c0f-caf2e39321a2 | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
| note | 0e270d30-ee5d-4984-b44a-db344fa4656c | METHOD: Visual
| note | ff2bbbdd-5828-41ea-9430-9c9358f4e777 | FREQUENCY: Where applicable, each bearing / mounting location
| note | 5d182fad-43c8-473b-b003-d0e4a7528753 | CATEGORY: IP
| note | 7c930c19-fd92-4ec4-b84d-4017c709cee0 | RESPONSIBILITY: SE/PE/SPE
| note | 57c5cc92-42b9-4cc9-a481-b8fd8acc2c58 | VERIFYING DOCUMENTS: This ITP
| textbox | 1a205ea4-4d0a-4b36-91b7-a36cbee44b85 | Date Completed:
| checkpoint |  | 5.9 Weather Conditions
| note | 5b530019-e5f5-4bb6-bf20-9a996557d596 | REFERENCE: 610.17
| note | 383a0ea7-47bf-44bb-860a-2be493e885c4 | Table 610.171
| note | ba9ce201-bc82-4d58-be17-15625c5c909e | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
| note | c0a5d365-b9da-4c9a-af20-fdeec31daf10 | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | ca63852e-a972-4da6-b32f-bbd52e556563 | Record: Required information on the Grout Pour Record.
| note | 2b176324-e5d7-4d2f-8512-358fd895247d | METHOD: Measure , Visual
| note | 98092497-b9fb-45d5-9853-1ced54605cce | FREQUENCY: Where applicable, each lot
| note | 8dc1df78-f907-4440-8a98-d7233213d654 | CATEGORY: IP
| note | b9719302-9b7f-4ad0-8e49-5762d753e7be | RESPONSIBILITY: Foreman SE/PE/SPE
| note | a8372df8-6b27-463c-b0be-d1502b930c0f | VERIFYING DOCUMENTS: This ITP
| textbox | 2645b627-bab5-4a38-bde1-cc2cfae5c797 | Date Completed:
| checkpoint |  | 5.10 Mixing Product
| note | f7a80305-dea2-44a7-936e-d16cea203b0e | REFERENCE: Product TDS
| note | 86a05a12-3405-4db9-8d08-c471688700ad | 610.28
| note | 956326c9-ddc5-452b-832f-de01d49ee141 | ACCEPTANCE CRITERIA: Size of mixer should match the application.
| note | 9130195f-be0e-4166-a9c4-b3ffdc93207b | Only whole bags to be mixed with potable water.
| note | 95f979ce-edf8-485c-84c2-6aa1d3a490e4 | Volume of water matches the required amount for flowable consistency and accurately measured.
| note | f5d59bf8-7799-4fb2-8188-accb15d38ff3 | Product poured into the mixer slowly.
| note | 6c25cc8c-fc30-457a-a11e-d1130c824d4d | Mixing time as per TDS so that a smooth, even consistency is obtained.
| textbox | c9c3296d-5a1e-4fc5-821f-2d539f0a4b68 | Enter: Required information on the Grout Pour Record.
| note | 3dd107f9-3bf3-427b-8247-dee2c5a21e15 | METHOD: Measure , Visual
| note | 21ae2cbd-b567-41d1-a1e4-9a6f9ef7ae9e | FREQUENCY: Where applicable, each batch
| note | 5edda109-1fe0-4208-8cb6-8138d4ff227d | CATEGORY: IP
| note | 2a051336-d5f9-425b-b841-915ef2d95439 | RESPONSIBILITY: SE/PE/SPE
| note | 4f130d71-5117-4d63-8224-daf974c63f53 | VERIFYING DOCUMENTS: This ITP
| textbox | 57032edb-cd5e-4685-b9c7-758244f8703d | Date Completed:
| checkpoint |  | 5.11 Product Testing - Compressive Strength Cubes
| note | f2ed5e9d-11d8-4256-a6c5-406c63991dce | REFERENCE: 610.28
| note | 1d40364e-c096-4f89-80ee-762744faffdd | 610.33
| note | e35b1d14-351d-419b-b701-42d2858da7fd | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
| note | f15b8caf-8cc6-41ae-b9ef-758c7e8d78bc | Testing is be in accordance with the following frequencies:
| note | ecd3a6c5-462b-45c6-b9b2-2e55258df11e | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| note | 4f84b609-0074-4aad-a362-b5f0713e536a | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
| textbox | e1877871-806c-4163-9763-ce97756bdd22 | Enter: Required information on the Grout Pour Record.
| note | 44b1f8d5-cb94-4938-9928-5fb4c6606de6 | METHOD: Test
| note | 58f7c55e-cc65-4149-8d80-74b7a4b5cfc5 | FREQUENCY: Where applicable, each lot
| note | 413785b8-2b03-452d-b37e-d712b3b288fc | CATEGORY: IP
| note | 5ee24395-b25b-4845-a7cd-9e15d314b0b6 | RESPONSIBILITY: Tester , SE/PE/SPE
| note | 22e8e6ea-509e-4fbe-bfc5-dafdc8102975 | VERIFYING DOCUMENTS: This ITP
| textbox | 0d6bcced-efa0-4d32-8b3b-981fda1ca68f | Date Completed:
| checkpoint |  | 5.12 Placement & Compaction
| note | 5efdf2a5-f257-4247-b352-c145afbe43e2 | REFERENCE: Product TDS
| note | d473bf00-19c8-4d65-af70-1c2d29c216b8 | ACCEPTANCE CRITERIA: All batches are traceable.
| note | 83cdf689-855c-4d47-93af-8261a36be9f3 | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
| note | 5ffad3a1-9083-42bb-8452-66732fa2cb8b | Product should flow to all areas and self consolidate.
| note | 3a65b1a3-eeca-4691-96e0-51e38f586c24 | Product that stiffens or is showing signs of stiffening shall not be used.
| textbox | 2b34fae6-a285-42cc-acaf-05fde9c45be0 | Enter: Required information on the Grout Pour Record
| note | e6e9cf34-7368-42c8-8864-26d2e2106183 | METHOD: Visual
| note | bd2ed9ad-b78a-4c82-98dc-794000ba39f1 | FREQUENCY: Where applicable, each bearing / mounting location
| note | 591f21fd-28fc-4d08-890b-290cd03059ca | CATEGORY: IP
| note | aac0f7b0-7ce3-4f1c-8931-62ec52774755 | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | a08d1e5b-1d76-48bb-a07b-d12d5eb70c2d | VERIFYING DOCUMENTS: This ITP
| textbox | 2c010ffe-ddfa-4e1f-89c4-b53cc18909e6 | Date Completed:
| checkpoint |  | 5.13 Surface Finishes & Protection of Works
| note | d0276e3a-9f0c-4ba1-854d-6b4a474ad0b9 | REFERENCE: IFC Drawings
| note | 6649348c-44a8-47c7-88e2-ba923190c155 | 610.17
| note | f275ee7f-eb8d-48d1-b0f7-c036cc936ae2 | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
| note | 75bd23bf-3bc1-4318-aa3d-b6c2ad788ef2 | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
| note | 4f476e9b-58aa-44c4-8cf9-9315d47c6907 | METHOD: Visual
| note | bbdf9c93-8a15-4741-a365-ddafd4ce4ebe | FREQUENCY: Where applicable, each bearing / mounting location
| note | 307cf3e7-006b-482e-9703-653960bc5561 | CATEGORY: IP
| note | 6b704b58-367f-4e1c-98fe-ec805c33f52b | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | d20847fb-4dde-4273-89a1-a3dcbc14b2ea | VERIFYING DOCUMENTS: This ITP
| textbox | 346fe335-daab-49f7-a80b-c39489b16c66 | Date Completed:
| checkpoint |  | 5.14 Curing
| note | d9d9361a-990d-4575-a75d-631cb1292cbd | REFERENCE: Curing Methodology
| note | 81b6e0e3-40d1-43e9-bdc7-53eab83cd184 | 610.23
| note | fceaa769-48e7-49bd-a19e-41a1d648ac32 | Table 610.231
| note | 3d284d99-4739-477d-af65-6372a4d3ff5d | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
| note | f77a7439-ca3e-4e43-8557-25e0bcd1fe38 | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
| note | c5c0c5cc-1fff-435e-abe0-b71918c926e2 | METHOD: Visual
| note | 6360da12-6616-4b4f-b384-51417d3a810e | FREQUENCY: Where applicable, each bearing / mounting location
| note | 36582c6b-c4c6-4798-af93-12473d758d6c | CATEGORY: IP
| note | 5686f897-d856-4d89-9d6b-59142455f72c | RESPONSIBILITY: Foreman , SE/PE/SPE
| note | 08ad49cd-671d-4495-bcef-b7a910f4920c | VERIFYING DOCUMENTS: This ITP
| textbox | ec33e771-77c7-4eb7-b3d4-551678d9f25d | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 6.1 Inspection of Coating
| note | 2a815ae9-ccc7-4ddb-af65-2730749af199 | REFERENCE: IFC Drawings
| note | e4120a2b-d862-486c-b743-727c9b4b0ec0 | 631.15
| note | 1ec479d7-3837-41c4-afeb-8779ebd14a81 | AS4680 Clause 8.3 & 8.4
| note | 837c475c-4950-4500-aa06-763162e8215a | AS4506 Appendix E
| note | a23ba831-4568-4c5c-9cb0-31278eaac045 | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
| note | 592fc17f-bc70-462e-ad80-4aca27a31624 | Where damage exists, it shall be repaired using an approved repair procedure.
| note | 88d7e518-8e15-49e2-934e-f32339f1dc52 | METHOD: Visual
| note | 032e4274-becf-4e69-8a33-e439be8e5b4b | FREQUENCY: Each component
| note | 52c827e9-dc25-46b1-acdd-6fe34c9155f1 | CATEGORY: IP
| note | 2990748a-7da6-4152-af96-4bd3f352dbad | RESPONSIBILITY: SE/PE/SPE
| note | 0157ba57-9106-45ff-bd72-67f3e939c11a | VERIFYING DOCUMENTS: This ITP
| textbox | f6116a2a-12b6-439d-bef9-74a5b61db5cc | Date Completed:
| checkpoint |  | 6.2 Compressive Strength Test Results
| note | 6919b41f-ef3f-408a-b5bc-2dd7631af1d6 | REFERENCE: IFC Drawings
| note | 0c7a91d5-f271-427c-969d-ed6b6034e3e8 | Product TDS
| note | a0ffad05-8438-4648-8dd1-bf7c6a873cff | 610.28
| note | 533857d1-d6c0-4b71-bb94-af8d1a469511 | 610.33
| note | db0c511d-fb8a-427b-b6cf-d87a7f74eaa2 | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
| note | eb58b437-8c2b-44db-81a8-d38444a58612 | 28 day compressive strength per sample comply with the design strength.
| note | 1c067763-de94-48fd-bfd4-2a28c8ca217f | Attach: Compressive Strength Test Results
| note | ef2518b2-cdbe-4960-9e3e-dfa808146d43 | METHOD: Document Review
| note | 30c9101b-d4e8-4d57-b262-3b562c55a8a0 | FREQUENCY: Where applicable, each cube
| note | 5e37e0d0-1ac9-45b3-88d9-46fc369dcb4b | CATEGORY: IP
| note | 9b87c536-87bc-485c-9aff-2721970ea761 | RESPONSIBILITY: SE/PE/SPE
| note | 3e0830ea-3e1e-46ca-8b7a-31ad2ba695cb | VERIFYING DOCUMENTS: This ITP
| textbox | b6373208-ebe6-430b-bfaf-90df709c4253 | Date Completed:
| checkpoint |  | 6.3 Direct Tension Indicator Daily Records
| note | 30d660e7-0a3f-47d7-9988-80a9ce5184da | REFERENCE: 630.20 (e ) (ii)
| note | 690137ed-c8d6-4f0f-9935-24d4781c4504 | ACCEPTANCE CRITERIA: Provide correlation between a calibrated torque wrench and direct tension indicators (DTIs) per bolt diameter.
| note | e96a2fd1-714d-4530-bc68-7a965be4f922 | Attach: Daily Record(s) of Correlation Between Torque Wrench & DTIs
| note | fc8cb42a-059f-468d-9ab8-17ed9aee7167 | METHOD: Document Review
| note | f2ef6f60-9605-4745-b31d-a0303381a079 | FREQUENCY: Where applicable, for each day that DTIs were used
| note | 11ad34ce-3ab9-4c6e-b6ec-9780e402dd7f | CATEGORY: IP
| note | fc8a3571-e93b-416c-9ca1-261b105f0747 | RESPONSIBILITY: SE/PE/SPE
| note | dfae3a49-1a4e-4b7f-b1af-3a56fbfa49a0 | VERIFYING DOCUMENTS: This ITP
| textbox | f4dba9b9-0fab-45ba-9925-8c48c63d1ea3 | Date Completed:
| checkpoint |  | 6.4 As-built Survey
| note | cc56364e-4139-4450-a6bc-ac00d2ca0035 | REFERENCE: IFC Drawings
| note | f17f2dfb-8f7d-49ff-95b6-1fe2d54fe96f | AS5131 Appendix F, Table F3
| note | 142a85e5-a30d-463d-8fa5-01827187ff75 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
| note | 91febc03-3fc1-47c1-831e-2b4ba5efefe5 | Departure from RL = ±10mm
| note | d086c7eb-a9c4-403b-babc-56e4a55d0e68 | Departure from plan position = ±6mm
| note | 67c9aa09-12bc-49af-ad45-fcc5ec403cd2 | Departure from alignment = ±6mm
| note | 2c918c54-f4ca-4dba-9b20-a3ed51f582a1 | Irregularities in alignment = 25mm in 30m
| note | d5292736-35e7-4db2-b1a1-42da8269a69d | Projection of bolt = +25mm, 5mm
| note | c5144215-a990-4b92-b79a-e2e2ac2f8307 | Location of beam = ±3mm
| note | 909b0b0b-7b1a-424b-b851-886ffc762aac | Location of column = height/500, 10mm max.
| note | 2e118106-9f41-4ace-b304-6b396187eb97 | Attach: Survey As-builts / Survey Report
| note | 4d69d334-e298-4233-8a50-59c8d5f9530c | METHOD: Document Review
| note | c7529fb8-644c-4970-ba7d-135e31325a89 | FREQUENCY: Each element
| note | a1068cd4-e19d-4f40-8d83-2a4e70e92509 | CATEGORY: IP
| note | d6c651a7-9f87-4d63-a3f5-4b29e4eb3105 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 82e5e0c1-2ccc-4f0e-8b59-e618375b7fa7 | VERIFYING DOCUMENTS: This ITP
| textbox | bf7b888a-ba16-4a4b-a2ea-852d6bbb43af | Date Completed:
| checkpoint |  | 6.5 Non-conformance Report (NCR) Closure
| note | a8ad49f0-1f83-4d7f-b27c-cf2b96a17f6d | REFERENCE: MRPA Quality Management Plan
| note | 8990526b-27af-4e91-9cb3-78cfbc82c32d | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 2e7b59fe-8759-473e-9c88-401bb6dcd1b7 | METHOD: Document Review
| note | 11e404bb-7ef0-4aac-bc67-8346d89fc026 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 0bafc7a9-63b9-4c2a-8f9c-ee77074f405f | CATEGORY: HP*
| note | df054180-fcf2-471b-9e47-556e6dfc8180 | RESPONSIBILITY: SE/PE/SPE
| note | e48c5f29-dad3-4c98-b429-597bcc92ed0d | VERIFYING DOCUMENTS: This ITP
| textbox | 0602302e-c7a1-4b01-a230-3fc553b19dd6 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 2259d6a7-99cd-480c-af5f-2a0d05f57414 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | e1edc905-e914-4521-ba11-dc44b8a66120 | Name:
| textbox | 343fd0c6-af61-438d-9507-cca0ed8da24b | Position:
| textbox | 54dd1e38-9387-46cd-9433-f9168697485e | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Tactile Indicators (Supply and Install) Rev 0 | itp | ITP-CIV-Tactile Indicators (Supply and Install) Rev 0 | dc48f9a5-60ee-4215-91bc-c31b67fdc5c8
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 7154f392-52ee-4403-a5b4-be65b5d9d3e7 | Document Title: ITP-CIV-Tactile Indicators (Supply and Install)
| note | ce679802-bc30-4bc6-85cb-e2108756f192 | ITP Description: Tactile Indicators (Supply and Install)
| note | 46bb0df8-c1ac-4235-b437-a66707ab04ea | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 2e8e6f9c-0c30-463c-83d3-9067350a3f23 | Revision Number: 0
| note | b30febc3-5286-4b6c-ad9c-a71c4229ff74 | Revision Date: 04/06/21
| note | be8ae3fd-34fd-4290-9ca8-6bb24a323aca | ITP created by: Romualdo Magpantay
| note | 66867dc6-26c1-4ce2-9fa1-503cbff63fe1 | ITP approved for use by: Romualdo Magpantay
| note | f8854f2e-afea-407c-94ce-bcc2b40c0383 | 1.1 AS1428.4.1
| section |  | Preliminaries
| checkpoint |  | 2.1 Material Conformance
| note | 02bce366-35da-43b2-a565-dde6e6050bab | REFERENCE: AS1428.4.1 Section 2.2 & 2.3.1
| note | 00f866da-0e2d-47eb-b913-4bbf8e1c959b | ACCEPTANCE CRITERIA: Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1
| note | a4ebab38-18e4-4d18-a4b5-2b214e80f1c6 | METHOD: Document Review
| note | 2540577f-2c61-4254-9bec-319cc7d9cf0c | FREQUENCY: Once
| note | 663c5f5d-8ba8-4733-8f30-fae1a72a15d6 | CATEGORY: HP
| note | 6dbd86db-d043-46e9-b1ce-b4aaf4dd0382 | RESPONSIBILITY: Nominated Authority
| note | 5ca87f3c-dde8-497f-9a52-35b07ae8526d | VERIFYING DOCUMENTS: ConQA Hold Compliance Certificate
| textbox | 72c6d152-b3e5-4dc8-b6aa-7f2feb8192c5 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Delivery and Storage of Tactile Indicators
| note | 78d53667-929b-4cff-b5f1-53772a62e03e | REFERENCE: QMP/IFC drawing
| note | 500e4863-2d27-448d-bee9-7ccc751132a5 | ACCEPTANCE CRITERIA: Check delivery of tactile indicators on the delivery docket for compliance with the specification and project design requirements
| note | c9c6874d-b8f1-4a29-99e1-7197aead999b | Check tactile indicators are in manufacturer’s original packaging
| note | 46a70fa7-5951-4602-a91f-38c642133649 | Check tactile indicators are free of damage and defects
| note | 58a25c8a-623d-4c16-9f7a-589420860ed5 | Store materials and accessories so as not be affected by site and environmental conditions
| note | bf9d765f-ce9f-4dcc-937e-0c6cc5995aba | METHOD: Visual /Site Inspection & Document Review
| note | 301d0a26-a37d-4d44-8ad3-9563c0e283a1 | FREQUENCY: Per Lot
| note | 0fa04690-0ea6-4675-8a93-ab93a8bb3c5e | CATEGORY: IP
| note | ee016076-744e-4c8c-bc37-1afcc4645af2 | RESPONSIBILITY: SE/PE/SPE
| note | 74bd7b31-07fa-471c-b56e-b0ca2fc448f8 | VERIFYING DOCUMENTS: This ITP Delivery dockets
| textbox | 7fc32dfd-76de-4bc9-ba0e-c0f73cedba84 | Date Completed:
| section |  | Application
| checkpoint |  | 3.1 Installation
| note | 709f66de-b3e3-484b-9e73-55f7cbaea228 | REFERENCE: AS1428.4.1 Section 2.3.3
| note | 9b49544d-7f28-4c7c-9a4f-2c56f0fe5e8d | IFC Drawings
| note | 18e00ffd-fca0-457c-b253-3e3cede10074 | ACCEPTANCE CRITERIA: Notify Nominated Authority prior to installation works
| note | be98541c-940f-4cab-b45c-c6f8c10325ff | Warning indicators shall be installed as follows:
| note | ee965034-fd65-4ce4-801b-0526d85fb2aa | (a) For the full width of the path of travel.
| note | 823acb6c-54bf-49dc-b85b-fa8ab320c5db | (b) Perpendicular to the direction of travel when approaching the hazard.
| note | 5e8dd2b0-be1b-40fb-bb5b-d5859998283c | (c) Set back 300 +/-10 mm from the edge of the hazard except at railway platforms and wharves.
| note | c85b7b94-842d-4f0a-b3af-405eae9ecc76 | (d) Where integrated warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below, over a minimum depth of 600 mm to 800 mm from the direction of approach.
| note | e84ad953-0631-4b22-ad51-3ae1510808a3 | (e) Where discrete warning TGSIs are used over a depth of 300 mm to 400 mm, the arrangement shall be as shown in Figure 2.1 below with a minimum of 6 discrete truncated cones in the direction of travel.
| note | 2d45bd60-fba3-42f5-b92c-af5d2addfc44 | (f) Where discrete warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below with a minimum of 12 discrete truncated cones in the direction of travel. Where required on a path of travel, warning indicators shall be located at both the top and bottom of stairways, ramps, escalators and moving walks
| note | 79402f2a-17a5-416d-ad60-dda52f4632ff | METHOD: Visual /Site Inspection & Document Review
| note | 545246d5-fe4c-4c37-ba4f-cac6045bd028 | FREQUENCY: Per Lot
| note | 35800d99-d4bb-4ab3-b215-08f0198d3d71 | CATEGORY: HP
| note | e12514f2-d8a3-4f17-9f27-365b98237767 | RESPONSIBILITY: Nominated Authority
| note | 421b868a-a793-4c0d-b080-fdd546e74c57 | VERIFYING DOCUMENTS: ConQA Hold
| textbox | ef2a580b-01de-4908-bc4f-7bc3315c29cc | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Laboratory and On-site Measurement of Luminance Contrast
| note | 2a73cb48-52ca-4d0f-8949-dce21c2b49a6 | REFERENCE: AS1428.4.1 Appendix E
| note | 08fd5adf-07c3-4074-98db-6e9763a3b865 | ACCEPTANCE CRITERIA: Submit Test report to AS1428.4.1 E5.4:
| note | c060993f-9e13-43bd-a817-9d2d5fd507d8 | The following shall be reported:
| note | 23c814d7-9789-41b9-9e8b-5394fecdbd06 | (a) Full description of the surfaces tested with product details where known.
| note | 3d7e701c-23c2-4709-a4e6-64e7c75a080f | (b) The instrument being a luminance meter with a 1° measurement area corrected to approximate the CIE 1931 Standard Observer.
| note | bf67a281-9dcb-437c-a8fd-b395114d8b13 | (c) The location of the sample, if on-site.
| note | 46570319-edf3-497e-b6a5-f4a3d50fee11 | (d) The location of the sample of the measurements on the TGSI.
| note | 59d25b8d-7efc-436d-a61b-ea58eaac42ff | (e) A description of the light source(s) illuminating the sample, including type, [e.g. fluorescent tube, incandescent, high pressure sodium discharge, metal halide, and colour (in general terms)].
| note | 9f1c3a5d-32ba-40ba-85e9-fdd76af40fcf | (f) The mean luminous reflectance of the adjacent surrounds to the tactile indicator under the conditions set out in Paragraph E5.3
| note | f4092a36-47c2-4ed5-a12a-909037a464a9 | (g) The mean luminous reflectance of the tactile indicator under the conditions set out in Paragraph E5.3
| note | 08143a88-4dc3-428c-a365-764c148b6938 | (h) The luminance contrast with the surrounds on both sides of the tactile indicator.
| note | 1dda97de-a21a-4193-96fd-4b2b33769935 | (i) A reference to this test method, i.e., AS/NZS 1428.4, Paragraph E5, Appendix E.
| note | d08705c9-b92b-4011-ba77-869da73f6e2a | METHOD: Visual /Site Inspection & Document Review
| note | 103f7d0b-ac09-4c9d-868f-cd22e690bd83 | FREQUENCY: Per Lot
| note | 6e9e5fce-234b-416c-8ffa-620e1f3442d9 | CATEGORY: IP
| note | fe1860bc-6e45-48f2-b93c-908ae09030b2 | RESPONSIBILITY: SE/PE/SPE
| note | c728a597-c56a-4b4d-b0f3-79424f4a01db | VERIFYING DOCUMENTS: This ITP Laboratory Report
| textbox | f7876285-0fde-4c70-8917-d3937c0cb6d3 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.1 As-built Survey /Drawing/Photos(if applicable)
| note | d044c8ee-1202-46e7-9b41-89888b363159 | REFERENCE: IFC Drawings
| note | 5d93e0ad-d97b-4f22-8d9b-dc6282cddb67 | Vic roads 160.A9
| note | 276a1333-cae7-4e4b-8257-b7ca25f95761 | ACCEPTANCE CRITERIA: As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format
| note | 6c09fe64-6298-4aa5-92db-ab3be26679ce | Attach: Survey As-built / Survey Report
| note | a17ac3cf-c3e0-4066-a2b9-38d621c16299 | METHOD: Document Review
| note | bf0227b0-1776-4daf-b3dd-926a3918f305 | FREQUENCY: Each element
| note | 2c3b7122-c14d-4d2e-bed3-3732fee8111d | CATEGORY: HP*
| note | ac6e71f8-22d6-43c9-b53e-39d949fd34e2 | RESPONSIBILITY: Nominated Authority
| note | 8a492267-b0e5-4e10-93e0-a55668740b35 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 23e1d1ec-663a-44e8-8ecc-20833e91077d | Date Completed:
| checkpoint |  | 4.2 Non-conformance Report (NCR) Closure
| note | d815122f-8969-4796-9e62-25ad122ccba4 | REFERENCE: MRPA Quality Management Plan
| note | 6e32cc2c-6216-4e15-b012-3af4baf57776 | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | b46f99c7-5ca9-454e-9366-05c11b47d7e3 | METHOD: Document Review
| note | ded6fcb1-5455-4dd3-a1b6-f9e9067733a6 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 63693f80-5d27-4fcb-b86d-4d93231516c4 | CATEGORY: HP*
| note | 4438fe0d-c35f-4ff6-b954-671497eb3c21 | RESPONSIBILITY: SE/PE/SPE
| note | 9e001bcf-9c9d-436a-9838-9b953811fda0 | VERIFYING DOCUMENTS: This ITP
| textbox | b222a934-3fbc-46c2-af07-71be4f2b3599 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 5125fee7-1003-4e57-9273-0180708045c2 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | c318aa63-9b3f-40a0-82ab-16935f239877 | Name:
| textbox | 8175d384-fc7c-41e9-af7d-f40329a91a61 | Position:
| textbox | da4581ca-5d66-4fd7-a5b8-6c85fabf78db | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-General Concrete Rev 1 | itp | ITP-CIV-General Concrete Rev 1 | dc7718c6-97f1-4cc9-9265-1e2985eb98df
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 236057f7-78b9-48d5-8a0e-0ba3fd308043 | Document Title: ITP-CIV-General Concrete
| note | 923c9a7c-70bc-4727-9ec1-bdf20437fd76 | ITP Description: General Concrete
| note | fc97af16-e905-48ca-8a9f-4abdb030fc43 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 998352df-0b6b-40df-8453-9c2234446c1d | Discipline (e.g. CIV/STR/RAIL): CIV
| note | cf78fdcc-8dc7-4e4f-a2d4-d720f44acca0 | Revision Number: 1
| note | 57f7e590-1646-40b5-8382-f05e9bf92a5f | Revision Date: 27/08/2020
| note | ab8c7edb-247a-408e-a0ba-441ae0734567 | ITP created by: Mike Freeman
| note | cf2639d0-5835-40a3-9707-63c262ae2b59 | ITP approved for use by: Mike Freeman
| note | c2492f58-549c-4238-bcf6-2f15c6dfeb17 | 1.1 VicRoads Section 703 June 2018
| note | fa40065f-826b-4b20-921b-86fc88032b07 | 1.2 VicRoads Section 812 July 2016
| note | 3c58c4d0-3f80-497b-a034-d81ef6343662 | 1.3 AS1379-2007
| note | c4983e60-8d41-473e-9f1c-118d611f413e | 1.4 AS3610-2018
| note | 4252e416-8496-495a-b1d6-457ceb0f3d0e | 1.5 AS4671-2019
| section |  | Preliminaries - Materials
| checkpoint |  | 2.1 Bedding Material / Base Layer
| note | 0a0b9b9d-8e58-4602-855e-5c415160fd63 | REFERENCE: IFC Drawings
| note | 661b97a7-dca4-4086-be87-de4dcbe41b20 | 703.21
| note | 20ec4e99-e366-4fcd-9212-2913568812be | 812.04
| note | 7e0090b0-956a-4948-8942-1d0ac541da8a | ACCEPTANCE CRITERIA: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
| note | 4552748f-1a4c-4086-b1c0-baa0b4009bb8 | Material is registered with VicRoads in accordance with Code of Practice RC500.02.
| textbox | ae98c1fd-a593-47a3-9746-480b749ee6a8 | Enter: Teambinder Material Approval number
| note | db02aa02-2883-4790-a939-a1154014dda9 | METHOD: Document Review
| note | b5f05a1f-21d4-45f5-af15-a369ab19257c | FREQUENCY: Once, for each mix design, prior to placement of material
| note | 2bb5a963-de15-4708-9aa0-a8a8e6cb2526 | CATEGORY: HP
| note | a5f5a2ff-f456-43c0-95f7-ce0edace3c58 | RESPONSIBILITY: Nominated Authority
| note | 49e16f1e-8240-43ff-bb5a-26a1a37a349b | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 860127f3-0b06-4352-b26d-fcb764750ebe | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Concrete Mix
| note | 2188672a-813e-41a4-9a78-ef9e86466958 | REFERENCE: IFC Drawings
| note | 60fa596e-8862-4649-be53-8d32d917a81e | 703.05 (a)
| note | 28047f72-33de-41b6-ab8f-eca7ae957b11 | 703.07
| note | 83d86be5-cc90-4430-aa0a-b429c9af0745 | MRPA Quality Management Plan
| note | ec1be236-302f-4712-8a1a-c5c62394bd46 | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
| note | 4ef1d0bb-5626-4961-94ea-ee82e7be4c3e | Paving concrete mix conforms to AS1379.
| note | 5792d91a-921c-4731-9735-3b178d766c9a | SUP concrete mix is registered with VicRoads.
| note | 55a2bd03-c416-4105-96a5-a7788ef4f2f7 | No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
| textbox | 0642c9cf-ebce-43a0-bb4b-c023f42428a8 | Enter: Teambinder Material Approval number
| note | fa4a723a-5f77-4406-8123-f747e8681341 | METHOD: Document Review
| note | 11e996e3-8d1e-421d-a2b3-3d2af450af6b | FREQUENCY: Once, for each mix design, prior to placement of concrete
| note | eb71c380-3960-4079-9721-b9c609c0c9c3 | CATEGORY: IP
| note | e5afd62b-f556-497f-897d-5eb232bc7693 | RESPONSIBILITY: Nominated Authority
| note | 59999453-7d4d-426b-836a-32737bec3d83 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 8d118270-35db-4320-b6c2-3b5548933a23 | Date Completed:
| checkpoint |  | 2.3 Reinforcement Certification (or ACRS Certification)
| note | 93385016-7cae-4911-9972-3381c038eaed | REFERENCE: 703.13
| note | 47d67e99-6fc8-4d37-aa49-c03767a798d9 | MRPA Quality Management Plan
| note | 48e632bf-30c0-4485-9271-9ba529d71ea4 | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
| note | fff3e681-5a58-409e-a05f-3e785632d45e | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
| note | ea91f5b2-3d30-4da6-bc0d-083b35e541ad | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
| textbox | dfee8fb8-3baf-4233-a712-8683d0cc8016 | Enter: Teambinder Material Approval number
| note | cc43ba74-a31a-4e75-b02a-816fe8c9d354 | METHOD: Document Review
| note | f3b59e78-9f2c-405b-b700-500da2d0c3f5 | FREQUENCY: Once for each supplier, prior to placement of order
| note | 85419bec-932e-4d45-b9bb-aedb5fafe737 | CATEGORY: IP
| note | 435fed6e-9784-43ae-a3fd-6e6aad781888 | RESPONSIBILITY: Nominated Authority
| note | dca41e06-03d9-433b-bc4b-7858a41bad93 | VERIFYING DOCUMENTS: This ITP
| textbox | 81508367-972b-45f5-9720-36a873545ae3 | Date Completed:
| checkpoint |  | 2.4 Evaporative Retardant
| note | 8a5618af-aad5-4452-b6d3-38b34d30cb81 | REFERENCE: 703.09
| note | 24e9f6a5-15eb-4ab2-9f67-317f39b48bf2 | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
| textbox | 4b64c320-e365-4a3d-805c-7a02d3c65335 | Enter: Teambinder Material Approval number
| note | 207678d3-0240-4d98-8307-57b4ad36c7fc | METHOD: Document Review
| note | 987da46e-905c-438e-b4a9-34c09818df5c | FREQUENCY: Once, for each product, prior to placement of concrete
| note | 60360bd1-e8b0-4a55-b04f-328c0417361a | CATEGORY: WP
| note | a06e51e2-936b-424c-af5c-c184139b765c | RESPONSIBILITY: Nominated Authority
| note | ff7c5b12-6465-4fe9-aafd-cacbd5f131eb | VERIFYING DOCUMENTS: This ITP
| textbox | 9b02e033-f87e-4f56-9aee-1167cdf0ba1c | Date Completed:
| checkpoint |  | 2.5 Curing Compound
| note | 00fa6bcd-66e4-4bfb-8a80-5ae2a67294d7 | REFERENCE: 703.10 (a)
| note | 349f5e6a-42d5-457d-a8ec-860803e9f3fd | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
| textbox | cfff6db4-1224-4af8-b84d-570cb9a99899 | Enter: Teambinder Material Approval number
| note | e18d1a13-9bd3-4893-aa27-f27dfa3ddd80 | METHOD: Document Review
| note | 9b23e603-9910-4932-8682-5ba16082d9e8 | FREQUENCY: Once, for each product, prior to placement of concrete
| note | dd10bfa1-084c-44ee-ab8c-39eda2014c32 | CATEGORY: IP
| note | b953b83c-e893-4883-8e7f-25a92dfa07b4 | RESPONSIBILITY: Nominated Authority
| note | d1f488aa-a57b-4626-9148-f06b439fe5f7 | VERIFYING DOCUMENTS: This ITP
| textbox | 633608b4-026f-4f17-8767-f2aa3f82679b | Date Completed:
| section |  | Pre-construction Activities
| checkpoint |  | 3.1 IFC Drawings
| note | e5900af1-9ec5-4c43-a9dc-27648cd59fc6 | REFERENCE: MRPA Quality Management Plan
| note | 9fd1f4eb-00eb-4a10-8260-f64a0631d4fb | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
| note | 151f49f9-1cde-4f26-a491-1b5ddce9a9f2 | METHOD: Document Review
| note | c7d61c57-d4e1-40d3-a9f6-3f0c36b2b358 | FREQUENCY: Prior to starting Works and at regular intervals
| note | d9e37283-914e-4a21-903f-f08a604cf015 | CATEGORY: HP*
| note | 8886c57b-c04b-4822-8062-d74f62740d39 | RESPONSIBILITY: All
| note | e763f38d-a6f5-44da-8f3a-971af90cd8b3 | VERIFYING DOCUMENTS: This ITP
| textbox | faf32203-df43-43d5-87f7-1b31f2fb561c | Date Completed:
| checkpoint |  | 3.2 Survey Set-out
| note | a7838c25-6c0d-4114-ab37-cf722f3fea54 | REFERENCE: IFC Drawings
| note | 09b35e83-dec6-410f-a73a-6a6c022fe057 | 703.17
| note | c4a9f68a-a585-4674-b624-d7f416979a29 | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
| note | b78a9c25-56e5-4fad-8766-df1068a7210c | The Nominated Authority will review and confirm the set out.
| note | 4e5ae1a3-9d95-40d0-a260-1e620414fd2f | Attach: Survey Report
| note | 03719059-4101-48ff-9bc5-1182f1a58cf1 | METHOD: Document Review, Measure, Visual
| note | a4eb4665-4acb-4ce8-a76b-162d3691d740 | FREQUENCY: Where applicable, each lot
| note | 03244323-0854-400d-be82-4c356740530e | CATEGORY: HP
| note | 025b6ca0-545d-4da9-98d4-a769673e1d79 | RESPONSIBILITY: Nominated Authority
| note | 01f8ab2f-8b70-4db0-9d33-964836c455fe | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 4214e0f8-d7c4-4e6d-b78e-faaa5aef23df | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction Activities
| checkpoint |  | 4.1 Excavation
| note | 142b42e8-b381-4d48-b5f9-aeaf588547e5 | REFERENCE: 703.20
| note | 56147b04-b92a-4d03-8bd8-d4b287a798c0 | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
| note | e223968d-d742-4fa5-b262-66e8ebd2ffbe | Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
| note | 764ec928-c6a7-4f55-9706-c450a13f4ec4 | Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
| note | 40badd41-4399-4e5c-82e0-6c20894e59cf | METHOD: Visual, Measure
| note | 958d5f42-2d0d-4dd6-92a5-dd5e234785c8 | FREQUENCY: Where applicable, each lot
| note | 2de75dcc-e024-4830-b70e-febd227c618a | CATEGORY: IP
| note | 49b3f3c3-d3bb-4fef-93ad-ceff81c2cef9 | RESPONSIBILITY: SE/PE/SPE
| note | 2bceef36-d99c-4e4f-b31c-fa4f304c2e3c | VERIFYING DOCUMENTS: This ITP
| textbox | 718034fc-9425-4757-9883-aa52bbf78bb3 | Date Completed:
| checkpoint |  | 4.2 Bedding Material Placement & Compaction
| note | bc7a9204-8cfb-4908-a782-6b400a0607b8 | REFERENCE: 703.21
| note | ae6eb902-e6d5-4017-8aef-e148609ac4ba | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings).
| note | 457cd01c-b9cf-41f7-92f3-8b5308d519ea | Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
| note | d91b9d9c-e093-43d2-bec1-52bd0f05c18c | The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
| note | f1f3bff4-0e3a-4eb1-ad36-dc67a136aa53 | All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
| note | 3c1675b0-d476-4b65-afe1-ecf85608c80d | Attach: Bedding Material Delivery Dockets
| note | 73a47b3f-0100-4281-bed0-90df68d48511 | METHOD: Visual, Measure
| note | 72248299-c7ed-4750-ba0b-7d2f2923080c | FREQUENCY: Where applicable, each lot
| note | 4daa3b7a-5a3f-4752-807a-e70d2e4c2240 | CATEGORY: IP
| note | 6bb98be8-74e9-4a17-b744-90d58011a9de | RESPONSIBILITY: SE/PE/SPE
| note | d40b1af2-6c14-4d47-8821-b1a49624a9b3 | VERIFYING DOCUMENTS: This ITP
| textbox | 0db89b33-f857-4df1-b59f-ad835fa18dea | Date Completed:
| checkpoint |  | 4.3 Formwork Construction & Placement
| note | c0da65d1-22be-44da-8ff0-2afa26e08ce4 | REFERENCE: IFC Drawings, 703.12
| note | f38f9eb2-5be7-4249-b33e-f946a48412b1 | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
| note | e1dc3451-ff00-444b-8271-adf7d99a1db7 | Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
| note | 94053d09-488c-4e9c-a501-5a0e2c71972c | Joints in formwork shall be constructed such that loss of mortar is prevented.
| note | 89f5c656-9477-4a0e-972c-28dd5defeeec | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
| note | 08990272-ab54-4f95-9f78-270a905e1dcb | METHOD: Visual, Measure
| note | a454c1a6-e164-4564-ac1b-c63461135b99 | FREQUENCY: Each lot
| note | eb0abea3-d652-4079-aa23-221966aa0681 | CATEGORY: IP
| note | 09d02a1d-71cd-4672-a152-38103b7038d7 | RESPONSIBILITY: SE/PE/SPE
| note | 5a80dde6-9a62-410a-b7a9-967a9fb8dd3a | VERIFYING DOCUMENTS: This ITP
| textbox | 488f295a-649b-44c3-a865-76306b8b0dca | Date Completed:
| checkpoint |  | 4.4 Construction Joints & Matching Existing Surfaces
| note | 303a56f9-eb25-4da0-bc75-7f92895960fa | REFERENCE: IFC Drawings
| note | 1be4c3bd-56bf-4008-8c72-b439346aa564 | 703.24
| note | 94d1dace-2b72-4ce5-b6e7-d86a0e3ee816 | Relevant Council Standard Drawings
| note | 94f1d077-7694-4694-a6fa-d63960ab4099 | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
| note | d021fc90-295e-45e2-96f9-70bea3d12ea3 | Consult the relevant Council Standard drawings for the joint detail, these may require:
| note | 54b11ebc-f254-49c8-8ace-b7a2bbcb45c3 | i. Concrete cutting of a shear-key
| note | 98a117d7-e30c-45a7-92d2-c81c10e9d45b | ii. Surface roughening
| note | df2e6e26-f9bd-4ccd-affe-434c8e5db5d3 | iii. Drilling and insertion of dowel bars (may also be galvanised)
| note | 001ad01b-14b2-4545-b720-fc7cef57a45c | iv. Cutting a groove for sealant
| note | 152de112-e74c-4283-9b8b-82eda802de5f | Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
| note | 8c4fd5ce-dff3-4f22-b5c6-381662d3abd9 | Transitions between different profiles shall be made in accordance with the drawings.
| note | 9f78dec5-4ba6-4320-8c07-fe96a2ff8e66 | Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
| note | 17c8bc9b-5f68-4d23-a3cc-02ccf463cedc | METHOD: Visual, Measure
| note | 230f0890-f3b8-4b80-8d43-9479d66b579e | FREQUENCY: Where applicable, each lot
| note | 6c412799-4c5b-4a56-91eb-0461d71bee12 | CATEGORY: IP
| note | f983ae79-70c3-47ce-a998-50484baa226b | RESPONSIBILITY: SE/PE/SPE
| note | 8a7dfedb-96d1-4a79-9c58-c18e22c43649 | VERIFYING DOCUMENTS: This ITP
| textbox | 92397bbd-83c6-476a-9218-296159b4e70f | Date Completed:
| checkpoint |  | 4.5 Isolation Joints
| note | 7f918859-f4eb-4837-9a12-84d5de548fc1 | REFERENCE: IFC Drawings
| note | 55dcf850-5b29-4722-aea1-122eb5494ede | 703.26 (c)
| note | 96beb1de-8d52-436c-b269-752bc740a2e8 | Relevant Council Standard Drawings
| note | 67038975-b927-4fc4-895f-f56fc952f9e8 | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
| note | b440fe90-e517-4343-b361-abc937bfcf76 | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
| note | 50c83f32-d753-4285-b35b-e94eee30a534 | ii. at any location marked on the drawings
| note | 8c9522d2-b14e-4b5f-b6fe-22cb6cabf25b | The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
| note | 50bd0db4-1493-4846-934a-d2630a9f3149 | METHOD: Visual, Measure
| note | 1067e70a-718e-448b-aeb6-3d7a30affc81 | FREQUENCY: Where applicable, each lot
| note | 9ae558a7-ba20-4a27-a643-5ba71f8359ef | CATEGORY: IP
| note | 03074616-c18d-4ff4-a8d5-12468d30b918 | RESPONSIBILITY: SE/PE/SPE
| note | e4e72195-af24-4565-a16c-e5e3e25abf29 | VERIFYING DOCUMENTS: This ITP
| textbox | 06115ccc-3103-41c9-b595-247c3a648bf3 | Date Completed:
| checkpoint |  | 4.6 Reinforcement Placement
| note | a59e409d-0594-4dbc-a7be-1d67dce6cad9 | REFERENCE: IFC Drawings
| note | 9cf582d5-d1f2-4afa-96c8-53a1f75817ec | 703.13
| note | a5f1ce24-2fbf-4ac9-a133-4026269ed1ab | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
| note | b39a0c49-71a1-49e5-ba4a-e5df5c8569ab | Any splice lengths achieve the minimum length and are in contact for this length.
| note | b03c507a-aedc-4abc-82ef-cab3ce182e7f | The reinforcement surface condition is free from dirt, debris and damage.
| note | 221001da-0f32-4be1-a382-dc8cb6d0599f | The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
| note | fa6116f9-b255-40eb-b599-131ba6835c2f | Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
| note | a80ef737-ed02-48f5-8c68-86fb2b5dcb7a | Minimum cover of 50mm at edges has been achieved (including tie wire locations).
| note | 66accac7-285d-4695-95cb-947c0d0e8301 | METHOD: Measure, Visual
| note | 5192121f-82ad-4b1a-9dbe-e1fad1d43119 | FREQUENCY: Each element
| note | 30e6767c-a1ac-4ac9-8089-bf979ff0fc08 | CATEGORY: IP
| note | ecebbfcb-6f8b-4b0f-97da-c1c7c69cfde5 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | bdfd63a4-ae5f-4b47-a008-06895e0a02a1 | VERIFYING DOCUMENTS: This ITP
| textbox | afc5cfe7-4d69-4b21-b185-de0a3ea85cf6 | Date Completed:
| checkpoint |  | 4.7 Pre-pour Inspection
| note | 26edddfa-c2aa-4a3a-b461-348ca22e3f20 | REFERENCE: IFC Drawings
| note | 5780def2-0f21-40d7-98ed-49bb516a072b | 703.15
| note | ed3e4965-d975-40d9-93a8-a0cb58efe45b | 703.21
| note | 1347af33-52a5-4361-9279-be26ba5f2373 | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
| note | e3ea64c6-0fd5-4ea8-b1ba-966594ae0bc5 | METHOD: Measure, Visual
| note | 913df962-5adb-42f8-a967-4c9675e5601a | FREQUENCY: Each LOT
| note | 2c440574-bb3f-4c6c-8262-918ee577890e | CATEGORY: IP
| note | 916473fd-cc98-44c4-90d1-53a8e62a9a9e | RESPONSIBILITY: SE/PE/SPE
| note | ec11d88c-9b10-46d5-833a-fdf5459d662a | VERIFYING DOCUMENTS: This ITP
| textbox | 86aac8e7-f520-41a3-b9a5-d80e84f80233 | Date Completed:
| checkpoint |  | 4.8 Weather Conditions & Evaporation Limits
| note | 995f4cb6-e4d8-4889-810a-09efe9cfcda7 | REFERENCE: 703.09
| note | 6bce248f-6b0e-4918-8219-3aa6b66f3a6b | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
| note | 09b04a62-41eb-4550-8f67-4d26f6091694 | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | 496c4311-ddcf-4ace-8524-5db5ef4cfb86 | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
| note | 379d2758-8d19-48dd-a404-a726c0d492f9 | When the evaporation rate exceeds 0.50 kg/m˛/hr apply evaporation retardant at the rates specified on the manufacturers TDS.
| note | c9b9f98a-a0f0-4105-baac-af307b6b1985 | Record: Required information on the Concrete Pour Record.
| note | 29622ef7-76e0-4f7e-9ef0-e782988d03f4 | METHOD: Measure, Visual
| note | 6661cc9a-8ff1-43ab-9ab4-ceadbffc450b | FREQUENCY: Each LOT
| note | d7f62ce8-fec1-49c3-ab1d-d48aef02d05f | CATEGORY: IP
| note | be7f8173-7e72-47a4-a6d9-52a6bdc9ab1f | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 64186e49-d058-48a8-86d0-5f05b55683a3 | VERIFYING DOCUMENTS: This ITP
| textbox | 9b9a68ce-7e11-4d5c-a2a9-ff5631a4a911 | Date Completed:
| checkpoint |  | 4.9 Concrete Testing - Sampling Frequencies
| note | bf038c02-cd08-4bb9-a172-1de4650d47d9 | REFERENCE: 703.11
| note | 7a8a12a4-93fc-487b-90b2-87d7ee094376 | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
| note | c8b89f65-6107-44ab-bbae-54f127cf0bef | 0mł to 50mł = 1 sample
| note | c0bfe94a-b65b-4b02-9cfa-b0d356f280b6 | Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
| note | 5de94cd1-1911-4da9-b8f6-ea7907601f11 | Compressive strength cylinders = 2 no. 28 day strength.
| note | 2a490486-f576-4fd2-ac4c-87b5f9d53b86 | Record: Required information on the Concrete Pour Record.
| note | 70ed3ba0-89dd-454e-8abb-439bf12e9c99 | METHOD: Test
| note | c6bf53a0-5f79-48e5-ba7e-782633a0b68b | FREQUENCY: Each lot
| note | 1d2e57a4-9c8f-4174-9959-dde83c5cbe54 | CATEGORY: IP
| note | 8a18bee0-8152-4568-a93d-8c5a34fe3279 | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
| note | 5c58a97a-4440-447f-8a92-5c5cf3f42643 | VERIFYING DOCUMENTS: This ITP
| textbox | 1e2bcc33-4327-431c-b339-90a1ff6324e5 | Date Completed:
| checkpoint |  | 4.10 Concrete Testing - Slump
| note | c6f6948a-cf32-4f28-8836-c1436c1a6da1 | REFERENCE: 703.11
| note | 0e48c4b3-08fd-43e9-bcd4-5e838d333fa4 | 610.16 (c)
| note | 17745ac2-4b59-4e95-a906-6788da696466 | ACCEPTANCE CRITERIA: Slump testing tolerances =
| note | 90e12499-fd62-4678-8a9c-be13ea322f08 | <60mm = ą10mm
| note | 148020b5-db17-49c0-b401-f008150528d6 | e60mm to d80mm = ą15mm
| note | f91baeb4-910c-4ae3-b9a8-167eba6ebb00 | >80mm to d110mm = ą20mm
| note | 1db1f62c-ea63-4b83-8ef4-cde80785b798 | >110mm to d150mm = ą30mm
| note | 5a007382-7ddf-4a12-9420-67865aa5bd1e | >150mm = ą40mm
| note | d842e9f1-cddd-4e21-a011-f2708191691f | Record: Required information on the Concrete Pour Record.
| note | 10560cf5-310a-4300-8dc6-e70af86078a1 | METHOD: Test
| note | bd2d5865-7104-4ca7-99ef-3c713d3fdce9 | FREQUENCY: Each sample
| note | 92d03f77-ac5e-4a4a-8007-91f7ddf7651c | CATEGORY: IP
| note | 153d8a1b-9b6f-4d66-b079-e18e94d271d9 | RESPONSIBILITY: Concrete Tester
| note | 79b87962-c62f-4dde-b920-419d5fcf5fc0 | VERIFYING DOCUMENTS: This ITP
| textbox | 4458bedd-12b7-48d3-9576-59ccdd1770b0 | Date Completed:
| checkpoint |  | 4.11 Concrete Testing - Compressive Strength Cylinders
| note | c930d419-bffb-41cd-96cf-26a181674b3e | REFERENCE: 703.11
| note | 4a5ae845-a2c5-4bd6-a1a8-08e8cc082b3e | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
| note | a949b6d2-86d2-4467-8d5b-752b378c3246 | Record: Required information on the Concrete Pour Record.
| note | d3a96772-469d-49a0-9b4f-effeb9adae69 | METHOD: Test
| note | d8c0f504-0580-4d83-a5c7-887e02c65d8f | FREQUENCY: Each sample
| note | 88af0125-1dff-4c52-b4db-a0813242af2a | CATEGORY: IP
| note | a4135241-86bc-4b23-884b-52f74473ffa6 | RESPONSIBILITY: Concrete Tester
| note | 958f1565-1e65-4909-b127-dd49c0b75968 | VERIFYING DOCUMENTS: This ITP
| textbox | 0546dfbe-a0a5-4269-96b6-d27eccf467e9 | Date Completed:
| checkpoint |  | 4.12 Supply & Discharge Rates
| note | c24f4f3e-8ee2-4e11-9d38-ea131799860f | REFERENCE: 703.08
| note | d13d0320-7465-4516-8aa2-9a4b86b4be34 | AS1379 Clause 4.4.1
| note | da70c1a8-232c-4675-8c29-1c02853ea225 | AS1379 Clause 4.2.3
| note | f1523113-bdab-443c-9a36-1bfaae119fb0 | AS1379 Clause 4.2.5
| note | 55684a67-b94b-4f8a-9b77-b97036899271 | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
| note | b82c21ff-5df3-4638-b991-2ad5bbbca93d | Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
| note | 9f34c6b0-c212-4960-8e68-5250e93a08c8 | Concrete that stiffens or is showing signs of stiffening shall not be used.
| note | f7b7a674-9fa9-4a08-b3a1-52d2ee80dc46 | If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
| note | bcf81ce0-bcdc-40a3-89dd-d384f503484e | Record: Required information on the Concrete Pour Record.
| note | a2743538-bbe3-44a2-a360-207dd8ceb8e3 | METHOD: Measure, Visual
| note | 7f12b089-2e42-4d45-a5e2-99ed804f082d | FREQUENCY: Each load
| note | ba288490-551e-43be-8d0d-b03997e6ed16 | CATEGORY: IP
| note | 4c7d5fef-a709-4ee6-b464-3bc46c706631 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | e96a0c83-b2bf-4027-ae03-dd36be4b4b53 | VERIFYING DOCUMENTS: This ITP
| textbox | 83be8063-f35f-42f0-97ae-4ae64d7c6046 | Date Completed:
| checkpoint |  | 4.13 Placement & Compaction
| note | 686e0b3b-2654-4888-b6bf-f77d66ff8eab | REFERENCE: 703.08
| note | da043dd6-8b16-42b3-a8b4-04f7e2624183 | ACCEPTANCE CRITERIA: All concrete batches are traceable.
| note | c3cf066a-aa59-44a7-87ce-ace31820a177 | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
| note | fd57d912-a84e-436c-a3b1-5d9e793e32f5 | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
| note | 92b08960-ac68-457c-8cbb-bab999e4ed26 | Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
| note | 83824815-dfe8-4c65-bf14-3139a7304f67 | Vibration continued at each point until air bubbles cease to emerge from the concrete.
| note | 7ccdb67d-f293-4ba8-b696-7b41c26b1f1b | Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
| note | 1b986a6e-cbe0-4904-b362-7072010393b6 | Record: Required information on the Concrete Pour Record.
| note | f548db4e-33fd-4408-b429-3c872a212c34 | Attach: Concrete Pour Record
| note | 618c3191-52a1-4dcf-87a8-5004a897dbe4 | Attach: Concrete Dockets
| note | 054d4dac-ace2-4797-b3d5-3e29b1b92ede | METHOD: Visual
| note | 6a5d8f39-c702-4ede-bb5b-0ecb29ed81de | FREQUENCY: Each load
| note | bc871f77-8da9-4e97-874f-ebf9408e0325 | CATEGORY: SP
| note | 5c7e8fe4-338f-4b18-8ea0-42bb4cfd75f9 | RESPONSIBILITY: Foreman, SE/PE/SPE
| textbox | 13e5ba35-15a4-4d69-872d-aa313b5dc1bb | Date Completed:
| checkpoint |  | 4.14 Surface Finishes
| note | 02e731d2-fa00-4f58-b4c7-bb2c8270d417 | REFERENCE: IFC Drawings
| note | 22b4bc1c-f718-4c56-8039-6e2ea477dd8f | Relevant Council Drawings
| note | 66ab382c-087f-478d-ac3c-bb6d05483c34 | 703.25
| note | 5bb651f2-a1c7-4fa9-a2e1-b3fded488cfd | ACCEPTANCE CRITERIA: Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
| note | 45e034df-23c1-4e74-beb1-cf720d533217 | All outside edges of slabs and all joints shall be finished with a suitable edging tool.
| note | b4f2cbd6-9aa5-4d11-9a23-17a896145e3a | METHOD: Visual
| note | e8f4fc70-6cf9-405b-846c-11857e53bc13 | FREQUENCY: Each lot
| note | 76c87c6e-ea81-437c-897c-078c3aa1e119 | CATEGORY: IP
| note | 11310d72-63f2-4292-8618-8eda0d9df821 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | d143bbdf-7318-4f28-99f1-d470d165b6f5 | VERIFYING DOCUMENTS: This ITP
| textbox | 7d8fc359-2d6a-41a2-a8e6-4ce1dae08bf0 | Date Completed:
| checkpoint |  | 4.15 Marking of Conduit Locations
| note | d3eaeb62-de60-420b-8f25-1c5ce9938947 | REFERENCE: IFC Drawings
| note | 56cf9e2f-695b-4406-9a55-de279ca92b1e | Relevant Council Drawings
| note | 63e3de5e-c57c-46b2-93ee-abf0dc4ed4e5 | 703.28
| note | 47177bff-040c-4fb0-a25c-1af0187d56bf | ACCEPTANCE CRITERIA: The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
| note | 3d7d9cf1-45a9-419c-b6e2-e939dfebfe04 | METHOD: Visual
| note | 7f821acc-2ceb-4159-a757-50bfd43c41f7 | FREQUENCY: Each lot
| note | 8cb1d564-55a4-4079-bab4-ded6e547f9c2 | CATEGORY: IP
| note | c5561e2e-19c2-46dc-a044-3240ab0c172d | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | e663a2cd-55fa-4540-9a33-eba87ce314ac | VERIFYING DOCUMENTS: This ITP
| textbox | 20cc596e-1f1e-4330-846d-2924e48e3cba | Date Completed:
| checkpoint |  | 4.16 - Crack-control Joints / Weaken Plane Joints
| note | 3e69a23a-4462-4bc8-a8ae-97e49c8efc3e | REFERENCE: IFC Drawings
| note | 7542eca8-64d3-420b-ba51-d5af8f7ce79c | Relevant Council Drawings
| note | ad0fa10c-feca-4c5b-b8b3-d9bebd329e93 | 703.26 (b) (ii)
| note | f16f992f-fbf6-4d25-86bd-77c299cab644 | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
| note | 6b594f57-a7cb-4871-952e-69fb22a1a2ab | METHOD: Visual
| note | 5a805a79-6bea-4dd3-9e9a-b3ae70471861 | FREQUENCY: Where applicable, each lot
| note | ea76be95-2d11-45cc-a706-550ee79cc49e | CATEGORY: IP
| note | 837aaddb-4d5e-483f-b3b1-3fa707a11427 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | b56b2e74-620d-46e6-a6b1-b803fd254bc0 | VERIFYING DOCUMENTS: This ITP
| textbox | 1c318a2e-a900-4d32-b524-eae5982e0f1e | Date Completed:
| checkpoint |  | 4.17 Curing
| note | f664f196-4304-401b-9a6d-cf4fc8338579 | REFERENCE: 703.10
| note | 5a87490e-7108-4a75-9545-e62f6883b188 | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
| note | e981229b-cca7-4861-bbde-1c02a035fe03 | Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
| note | d86970d2-fc99-4369-bb7b-8134639fbcb8 | The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
| note | d977bcd0-771e-4efe-8c1d-3eabb96e8a1f | Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
| note | 8156d31b-254a-42cd-899e-41f865210288 | Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
| note | 3b550acd-e903-4f42-8bdb-226db3b68602 | METHOD: Visual
| note | 10768512-6081-43fd-9149-9491bfb233b9 | FREQUENCY: Each lot
| note | b100188f-81cd-4da8-be55-2a319c2c6a78 | CATEGORY: IP
| note | 815d3ddc-a5d2-47e2-80cd-d279b662de48 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | e73e6247-ae6f-4f65-b83c-27cdfe195adf | VERIFYING DOCUMENTS: This ITP
| textbox | 6a734ce5-4f32-459d-8db7-436470ac469c | Date Completed:
| section |  | Post-construction Activities
| checkpoint |  | 5.1 Protection of Newly Poured Concrete
| note | 9ffdc576-6b3e-4350-9111-d2d1255e221e | REFERENCE: 703.27
| note | 39dc6114-0062-4354-8212-1f764eb3d1c6 | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
| note | 4962ddbf-821d-4186-9527-627e2201df59 | Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
| note | ed43468f-b681-4972-ad37-de75b00c199a | METHOD: Visual
| note | 78e244a4-b093-40fe-ba09-bdac71f0f516 | FREQUENCY: Where applicable, each lot
| note | b11e04e6-199a-4be3-b6b9-597e2ed867e2 | CATEGORY: IP
| note | d1d10943-0387-49a1-b352-65419d2af103 | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | d4528f44-671f-489c-8542-f34e572b196b | VERIFYING DOCUMENTS: This ITP
| textbox | 15734b90-e18d-4351-b89b-7e1168ac0ecc | Date Completed:
| checkpoint |  | 5.2 Stripping Formwork
| note | 4a21cc65-d331-4040-a4af-acadc82bd328 | REFERENCE: 703.12
| note | f3c2317f-3937-4761-8591-fc8d4339c58c | AS3610 Table C2
| note | ddf320f1-9a20-436b-97d1-fcaa134e5785 | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
| note | 92d864ca-f83e-4a02-8a03-5179ec4c023d | i. 2 days for vertical formwork on external surfaces; and
| note | 511ba437-5e8c-4c70-a900-abb30c9d166d | ii. 1 day for vertical forms on permanently hidden surfaces
| note | 921a52db-5acc-4e48-a053-84d3b1078807 | METHOD: Visual
| note | fa6206e5-600a-4abe-8e61-2633380a0610 | FREQUENCY: Each lot
| note | 2a0ee069-f83d-4e4a-9173-4683af7880c1 | CATEGORY: IP
| note | 30ff9760-4be0-4040-93c0-bd05ca956d7a | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | 1a018ecf-c4f1-4d55-a56b-9835bd1ebda4 | VERIFYING DOCUMENTS: This ITP
| textbox | ff69ed61-854f-45b0-aa6c-41f030e8f838 | Date Completed:
| checkpoint |  | 5.3 Backfilling & Pavement Restoration
| note | 6f9c0f46-b316-44a3-bd97-439f67bf7fad | REFERENCE: 703.29
| note | 37504a29-09e0-475b-86e5-04dd86785576 | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
| note | 793d5008-af04-4f05-a9fa-2f41899dc450 | METHOD: Visual, Measure
| note | 63e0cd06-04bf-46b3-a609-fe66ae567391 | FREQUENCY: Each lot
| note | 2d68a0e2-a0df-4640-99bb-1a9a8e7fcad1 | CATEGORY: IP
| note | f9144373-373c-4531-8369-70e48c41e78e | RESPONSIBILITY: Foreman, SE/PE/SPE
| note | b938333a-16d0-4287-abab-30fc81d037dc | VERIFYING DOCUMENTS: This ITP
| textbox | 48d13244-8320-458e-9aff-3bd0b663e374 | Date Completed:
| checkpoint |  | 5.4 Surface Inspection - Cracks
| note | 1008cad6-4e9d-45a3-a05e-6365835ab4b4 | REFERENCE: 703.3
| note | 0a71989a-54a0-40dd-bbdc-f75bb577dc86 | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
| note | 1de9da6d-8ade-40d2-a2a6-81008247d6ef | If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
| note | 4b2714ec-6c81-447f-bbc1-e1f382264135 | METHOD: Visual, Measure
| note | ed645c06-705a-4716-a850-78ec151e9b3d | FREQUENCY: Where applicable, each lot
| note | 1f9a495b-7411-42a1-9685-8acd3b1cf84b | CATEGORY: IP
| note | 0cb62020-fb40-4b95-833e-f3168d51d46c | RESPONSIBILITY: SE/PE/SPE
| note | 42a19ecb-4c0f-40a9-bc8a-796c37a0b2a5 | VERIFYING DOCUMENTS: This ITP
| textbox | 5198e088-5deb-409b-b46a-f04689bb2ab1 | Date Completed:
| checkpoint |  | 5.5 Surface Inspection - Surface Finish
| note | c8caf445-e998-4b83-a0d4-b608bb59a78e | REFERENCE: IFC Drawings
| note | 895f9fb1-60b8-4988-a03c-35295529b9e3 | Relevant Council Drawings
| note | 4db0ad57-8b07-4b0a-9b33-7a68660202d9 | 703.25
| note | 878ac47e-f942-4ae3-81cc-7eea0b3e9b66 | 703.10 (a)
| note | 99ccf68a-3bcc-47d2-9c79-fd2a9903591d | AS3610 Clause 3.2
| note | 920db7c3-9db7-43dd-844b-39a3d25ba842 | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
| note | 55ce3ad3-9cba-4fac-b9e2-abf64b9a752f | All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. Class of finish:
| note | 13d6790e-7b7b-4b92-ae41-b045aa4bb775 | Permanently hidden surfaces = Class 4
| note | 53b90c30-ca8c-4842-a428-e74c774c5c65 | All other surfaces = Class 3
| note | 9fea2619-3d77-4d30-b0de-e96f241d51b3 | At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
| note | 05d9f868-85a4-46e7-a816-01de26bdaf4d | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
| note | ba508032-afb3-49e3-b3bd-a6ca9fe3f903 | METHOD: Visual
| note | 4170468c-df20-476d-94b0-f1b2a13dcf5f | FREQUENCY: Each lot
| note | 30a6384c-7dbc-488c-b31f-95012cb90661 | CATEGORY: IP
| note | b065f2d9-a74d-4ed2-bfbd-99557b7ca5a0 | RESPONSIBILITY: SE/PE/SPE
| note | 4d04266f-03d2-4a75-80fa-189d2c0ffc08 | VERIFYING DOCUMENTS: This ITP
| textbox | 6eb454d8-abaa-49a7-a19c-2a2cab22750e | Date Completed:
| checkpoint |  | 5.6 Compressive Strength Test Results
| note | 3e962578-a5e7-420b-8af0-686d38fb86f8 | REFERENCE: IFC Drawings
| note | 1baeedff-e090-4751-8c13-bf870702bbc9 | Relevant Council Drawings
| note | 2f91f96a-a1b5-4209-8bbf-9c99dd44dfeb | 703.11
| note | 09b331dd-af45-418a-90a3-b1b21d6ec48d | Table 703.111
| note | d11da278-ff70-4426-bc51-2b7ace7a4745 | ACCEPTANCE CRITERIA: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
| note | 598f5524-f9e7-4a96-b087-5bcd58e3af3b | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
| note | 185b4fa6-6441-45ea-b73e-ec2056740f1b | Attach: Compressive Strength Test Results
| note | f25efa24-f2fa-4a23-9f39-05f26677087f | METHOD: Document Review
| note | a6805ae1-706c-42b6-b2d7-c79a27797f6e | FREQUENCY: Each cylinder
| note | aae93d42-8792-4125-96d2-dbc4020c8e8b | CATEGORY: IP
| note | 18b0173c-27d7-44cd-96bc-2329450ae517 | RESPONSIBILITY: SE/PE/SPE
| note | 12bc6167-ddd7-492e-a032-fc707160bbce | VERIFYING DOCUMENTS: This ITP
| textbox | 20ea4801-d8f6-47c4-9ae6-448a5b6eb68a | Date Completed:
| checkpoint |  | 5.7 As-built Survey
| note | e8afef9d-bcd2-4b32-acd7-e13d05ba78fd | REFERENCE: IFC Drawings
| note | bdd483aa-a8aa-4cdc-a34a-5b7a5d3bd893 | 703.15
| note | 19efa59e-fdd2-4a50-a2e3-e575a5c4d29d | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
| note | 44ebe256-f5ea-4acb-aef3-3732fcdf1fc9 | Departure from RL = ą10mm
| note | 2a9609a5-c502-43b8-a322-5ef1bd4dbba4 | Departure from alignment = ą10mm
| note | a6a295c8-b9d5-41a5-b684-fff3228d49c1 | Rate of change of deviation from RL or alignment = 10mm in 10m
| note | 29916bd3-e8bc-4389-a161-358632eb5309 | Irregularities in alignment = 5mm in 3m
| note | a746f96a-91b8-4103-baf3-ea38879561c2 | Section dimensions = ą5mm
| note | f6059265-6188-4ce9-a872-69683eacc038 | Section dimensions (less than 25mm) = ą3mm
| note | 2c7a8d57-94d8-4fca-bd94-781fa355e29b | Width of pavement = -5mm, +15mm
| note | ee7f4a51-0aa0-47c7-9d4c-d4817730dcc1 | Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
| note | 68afdbfb-b1f8-4220-9831-1c6cb74a3429 | Attach: Survey As-builts / Survey Report
| note | 3365698e-35da-4582-904c-e281ed79d792 | METHOD: Document Review
| note | c4869b62-f854-41d0-8cc4-ee02c488f071 | FREQUENCY: Where applicable, each lot
| note | d4ce7545-4f5c-45f1-91b9-74a1c220e2dc | CATEGORY: IP
| note | c05a36d2-b8dd-4ed7-a449-b6fa6e330d91 | RESPONSIBILITY: Surveyor, SE/PE/SPE
| note | 392864dd-ef46-4b72-bc17-b0f2642cc616 | VERIFYING DOCUMENTS: This ITP
| textbox | d989132b-7c3c-4202-86cb-97176b3ce1bd | Date Completed:
| checkpoint |  | 5.8 Non-conformance Report (NCR) Closure
| note | edcf176f-5c84-419f-85bc-0a0b5b76c530 | REFERENCE: MRPA Quality Management Plan
| note | bccbca5e-8477-4f68-b7cb-a2c8dbf289de | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | f06c0393-ea11-4247-918c-c9bfe3ab5aa9 | METHOD: Document Review
| note | 195a2d1e-cf15-4215-ab5c-77324e4fca7f | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | e4f423de-62b0-47b7-83bc-21d2158b3b08 | CATEGORY: HP*
| note | fa076dc2-095e-41ec-976d-f224923aa600 | RESPONSIBILITY: SE/PE/SPE
| note | f870407a-d71c-4af1-9429-67dddbf9a70f | VERIFYING DOCUMENTS: This ITP
| textbox | 4e37935c-603c-4609-856c-2561a9a50bd5 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 13a724da-26b8-4bce-ad3d-7469b6ea2834 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 4d035ed5-cce6-4db7-b878-be8fed9b83ca | Name:
| textbox | ae5deb4f-bca1-4540-b743-514bc1b2a5e9 | Position:
| textbox | f866a540-8f33-4a4f-b9ab-22e262c99f2e | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Sign Posting Rev 0 | itp | ITP-CIV-Sign Posting Rev 0 | df5c0028-89f3-4c32-817f-d370de1f51ef
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 775bdde7-293c-4a0b-9d8d-59ccaa9cef25 | Document Title: ITP-CIV-Sign Posting
| note | 06cf4ef1-7eaa-4515-8d03-aee044004759 | ITP Description: Sign Posting
| note | 5e84d432-6e72-409e-a423-cc86cffeb97b | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
| note | 833485b5-1ff8-440f-9a4e-2563774f362f | Discipline (e.g. CIV/STR/RAIL0 CIV:
| note | e3116b41-fe7a-438b-8d97-c13d72333632 | Revision Number: 0
| note | 18dfa063-04c8-4920-87e1-d1a93f5032b7 | Revision Date: 24/09/20
| note | 09317b41-4647-4af7-8518-e6b2e0ac172e | ITP created by: Romualdo Magpantay
| note | 92cc1e30-fa1d-4e8f-8906-711c4be6535e | ITP approved for use by: Romualdo Magpantay
| note | 69e8dfa6-c444-40d3-9307-158e504d6120 | 1.1 VicRoads Section 714 December 2018
| note | 7776acfe-e510-4af8-8c2a-1e0d3c0731c4 | 1.2 AS 1743
| section |  | Preliminary
| checkpoint |  | 2.1 Obtain approval to supply bolts, nuts and washers from Independent Certifier (IC) including steel post other support systems.
| note | f6351727-d694-4a36-83f3-9bd04ca24481 | REFERENCE: Vicroad 714
| note | 3eaf9227-c66a-4d52-aa4f-50727d44a196 | IFC Drawing
| note | 7bd58e37-15be-43c9-8fe9-2c89f288ea53 | AS/NZS 1252
| note | 527c905a-a741-4e02-8739-21d7cec5693f | ACCEPTANCE CRITERIA: ● Submit to the Independent Verifier that ISO9001 certificate of the supplier, Certificate of conformance, details of the supplier, lot identifications and relevant test result
| note | 8b649d63-77f8-4ba8-91c6-86aeadf29659 | ● Steel posts shall be manufactured from steel complying with AS/NZS 1163, AS 1397 or AS 1450, and having a minimum yield strength of 250 MPa.
| note | 0762ab14-21c1-4f56-a600-9525e412cacb | METHOD: Review
| note | 276b2271-c3b4-464f-a783-258e6e91c484 | FREQUENCY: Per Supplier
| note | b0349fc6-0c70-4fb6-96f0-a16feff6e23f | CATEGORY: HP
| note | cd20eb4e-356f-4e10-8e8f-046d6067ce05 | RESPONSIBILITY: Nominated Authority
| note | b8104abf-960d-49b4-a687-11bf3a614ce5 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 69fb85c7-726d-425a-b1ba-b2c78c4c4326 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Obtain approval for commencement of sign manufacture
| note | f8af54f6-e311-4d32-b950-d4d7dfe42f1a | REFERENCE: Vicroad 714
| note | defdea74-cc1e-4174-bff1-a732d39b4022 | IFC Drawing
| note | d94bc7b7-d7fc-42bc-995c-10968bf1cad4 | ACCEPTANCE CRITERIA: Submit prior to commencement of manufacture, a statement advising the brand(s) of retroreflective sheeting and details of the non-reflective background and legend material, to be used in the sign manufacture.
| note | 5a1b7f4c-4f8e-4049-b9d2-c8b67bda6952 | METHOD: Review
| note | fc58916d-9562-4be0-912d-b6ae2271e249 | FREQUENCY: Per Supplier
| note | 874facc7-e3d6-4556-b0fa-3e7d81a79e23 | CATEGORY: HP
| note | a889b8d2-032c-4768-8689-42ad8af21dd5 | RESPONSIBILITY: Nominated Authority
| note | 46cbe48b-87be-4f73-a35a-88cf7c6909f9 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 1025ab4c-893e-4c91-a64b-71317108b792 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.3 To inspect the manufactured signs prior to delivery & submit a conformance certification statement.
| note | 81f180d5-fa2c-4da1-b1d8-c14eaa8d64c2 | REFERENCE: Vicroad 714
| note | 08518d22-b1b7-4743-bbfe-432427bdca52 | IFC Drawing
| note | 92760c57-4dee-4c40-bb83-0ee24a9b606b | ACCEPTANCE CRITERIA: Submit to inspect the signs prior to delivery:
| note | 03de618f-c6d7-4df1-966a-feb1582b2edb | ● Statement certifying that the signs comply with the requirements of Vic roads and IFC drawings
| note | 55013572-88ed-4f58-88f7-d9188d0e54c2 | METHOD: Review
| note | 33b0e748-629a-426f-bb9d-d25b54772173 | FREQUENCY: Per Delivery
| note | 1f9cd7c3-17ba-4b5d-bc7d-cdea71cee457 | CATEGORY: HP
| note | a3115155-b8b7-4e50-9aaa-5e7944e52be7 | RESPONSIBILITY: Nominated Authority
| note | 853e571f-aef4-467f-915c-7ec815a5bad3 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 51636cd8-f1b9-412f-b324-34df30ca00f0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Installation Activities
| checkpoint |  | 3.1 Set out the works to ensure all signs and support structures are located in accordance with the design drawings
| note | eea57669-34f8-41a3-8c59-f49e8f4fb86e | REFERENCE: Vicroad 714.06
| note | b088e45c-6826-45fd-bf84-33d3ea4304a3 | IFC Drawing
| note | 15ee2762-80a8-4abb-ad7f-d2e79d410b29 | ACCEPTANCE CRITERIA: Submit a Hold Point to inspect the proposed arrangement and alignment of each sign support structure, upon completion of setting out
| note | b6616461-d38f-4b54-8239-06dc1e870e38 | METHOD: Visual Dimensional
| note | 9861ebda-9e0d-41be-ac49-8a5d21387b64 | FREQUENCY: Per lot
| note | ce899dbb-ae14-4c6a-909c-4807bf263d73 | CATEGORY: HP
| note | e23bc662-fbc6-44e9-937b-d478d021f40d | RESPONSIBILITY: Nominated Authority
| note | 91f997da-0b5a-4521-8cf6-315a6a4cac49 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 28d6e200-de45-4304-ba6f-a3d5839ac4d5 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.2 Clear the areas around the sign support structures
| note | 19630d08-2554-4e1e-b41a-2917fa98ae18 | REFERENCE: Vicroad 714
| note | 3ad3c3cd-b335-4995-ad2f-32f1362c9902 | IFC Drawing
| note | b58c1c6b-180a-4e3a-8368-87323eafff12 | ACCEPTANCE CRITERIA: Submit a Hold Point for the intention to clear any trees & undergrowth within 3 metres of the sign support structure & along a motorist’s line of sights to the front of the sign are cleared and removed.
| note | 4cbd1b00-3b14-40ec-8afc-54627b421e96 | METHOD: Visual Dimensional
| note | e2463e88-2f61-4d99-ac6f-fb52ebbfb77a | FREQUENCY: Per lot
| note | b4ec2e16-caa9-4e85-82f5-32ec45580070 | CATEGORY: HP
| note | dd0623ce-a73d-4ae9-8907-7036be3190f3 | RESPONSIBILITY: Nominated Authority
| note | 51d1b72b-12e3-42d8-bd13-67da5001c74e | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 952410d2-52cd-4e9b-be21-632384628bd0 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.3 Excavation of the foundations for signs
| note | ebf30004-07dd-46b0-b046-d9fd30817a9d | REFERENCE: Vicroad 714
| note | 681f4608-93b0-4e6e-b2e7-a9393217acc0 | IFC Drawing
| note | 97705aae-b944-4c24-915e-f1c0ea62d551 | ACCEPTANCE CRITERIA: All posts shall be set in concrete foundations to the depths shown in the Sign and Post Schedule & Concrete used in foundations shall be 20 MPa complying with the requirements of Section 703
| note | 8e7229fa-58dd-47d9-a24d-60527af7d440 | METHOD: Visual Dimensional
| note | aa3325dc-48d3-49c0-8dc1-82cee06753d8 | FREQUENCY: Per lot/ Signage
| note | 5e102c3f-f665-42dd-b102-6427f71fb3e0 | CATEGORY: IP
| note | 419d0e35-fc19-4a87-8517-3da4f22e1698 | RESPONSIBILITY: Project /site Engineer
| note | 5b0e1646-f857-429a-95d2-234c9927866f | VERIFYING DOCUMENTS: This ITP
| textbox | 4a031863-1f00-4736-8c23-40508a97740b | Date Completed:
| checkpoint |  | 3.4 Placement of Concrete
| note | 3a3aa619-374d-47f8-a9c1-9b8026b35753 | REFERENCE: Vic road 610
| note | 841d391e-d02d-4d59-bebc-52c146a645aa | ACCEPTANCE CRITERIA: Notify NA prior to intended time of commencing the placement of concrete, when fixing of formworks and reinforcements in position (if applicable) will be completed and when concrete will be placed for pre-pour inspection
| note | ba110456-82d1-4531-a64b-61a1c5a74876 | METHOD: Visual Dimensional
| note | daccf76b-bf00-4f0b-9dc8-d879eebfb8c4 | FREQUENCY: Per lot/ Signage Structure
| note | 64e51421-6a1f-48e5-8743-319b0ef2186b | CATEGORY: HP
| note | 366ca4f7-bb94-4ffb-8f14-b144c668b471 | RESPONSIBILITY: Nominated Authority
| note | 2f477f5e-6667-4ee6-803e-6fed5e4c4ee8 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | 669c6aa5-c0aa-4ecc-a279-d780ab045227 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 3.5 Erect posts for signs in according to design drawings
| note | 83d77347-c78c-4dea-ad5a-5ae7ea9122c2 | REFERENCE: Vicroad 714
| note | 6e958ee1-6505-49a4-a769-b45edddf423f | IFC Drawing
| note | 1048b595-84be-496f-8db8-60502430e012 | ACCEPTANCE CRITERIA: ● Where posts are to be mounted in sockets, the post shall be securely fixed into the socket by an approved vandal-proof method.
| note | 5d3c16d0-af60-4d8d-ac90-e20a49b029cf | ● Signs to be mounted on two or more posts shall have posts positioned such that the sign face is rotated away from the approaching traffic to avoid direct reflection. Posts shall be positioned such that the sign is rotated away from the cross section by an amount equal to one tenth of the width of the sign (approximately 5º).
| note | a453a7d1-c411-464b-9adb-d0d0a347a426 | METHOD: Visual Dimensional
| note | 40ec3115-8bca-4281-a6a3-9cc02b6c00c2 | FREQUENCY: Per Sign Structure
| note | b80bf8d3-cb39-4270-8544-708463293a04 | CATEGORY: IP
| note | 0455592f-1719-4a1e-b155-3261691417c3 | RESPONSIBILITY: Project /site Engineer
| note | 9ddd4389-c4b4-4082-9276-d89fbfbf8f19 | VERIFYING DOCUMENTS: This ITP
| textbox | eb159db3-2e5a-4d21-a6b2-435563666a73 | Date Completed:
| checkpoint |  | 3.6 Attach sign panels to the supporting structures if fabricate on site
| note | 86ee53e2-2854-4239-8a59-8276bceb9559 | REFERENCE: Vicroad 714
| note | f2fe42b6-1754-4a1f-a98b-bf6855d6fbe3 | IFC Drawing
| note | 33bf579f-b6f7-4fd2-a7bb-16ae11c6c247 | ACCEPTANCE CRITERIA: Installation of signs shall be in accordance with the Sign and Post Schedule(Vic roads 714.07).
| checkpoint |  | 3.7 Masking of signs
| note | 3eb7b1aa-dc7b-4e19-bfd8-0d0aadee97a1 | REFERENCE: Vicroad 714
| note | 59a74363-a479-4841-a998-49a65e5259fb | IFC Drawing
| note | f1cbe0d5-fc0b-4a2e-b81d-aaae2fd6753b | ACCEPTANCE CRITERIA: Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign.
| note | 46bcde76-72c4-42fc-8ef3-85079ceb560a | Adhesive material shall only be applied to the masking material and not be applied to either the front or rear
| note | 1b95616f-9e3a-449b-acaa-5d4ad9858aa6 | METHOD: Visual
| note | 7f1139ff-dd88-4525-82ac-93d98ac15367 | FREQUENCY: Per lot
| note | 7aa2a2e5-5c8e-4118-b8be-fe3f9e59ee5b | CATEGORY: IP
| note | be97074d-08f8-43d2-9af9-5b62358cbc33 | RESPONSIBILITY: Project /site Engineer
| note | 6ad783da-08ab-4ec5-8ee4-506bfdd6546c | VERIFYING DOCUMENTS: This ITP
| textbox | afc7f034-ca11-4e67-8400-525c63ebabf2 | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 4.1 Inspect and repair the installed signs for any surface damage (i.e. scratches)
| note | 75be9540-c032-41b3-b775-f60056f2782a | REFERENCE: Vicroad 714
| note | 92f8ee43-95ce-4788-986a-61a1a6e85d5f | IFC Drawing
| note | 2e32243a-baff-42c9-8a35-fb50c4fd009f | ACCEPTANCE CRITERIA: ● Damaged galvanized coatings renovated with zinc-rich paint to at least equal to thickness specified by galvanized layer.
| note | f265b72f-669a-4d06-b2e3-1ac6f231d375 | ● Any structure with a total damaged coating areas exceeding 2500 mm² have been regalvanised by the manufacturer.
| note | a2357a8e-75fe-41f8-8c5e-6ec4456650fa | METHOD: Visual Dimensional
| note | 6eccf965-3e9d-40b7-92de-6c33cccab99c | FREQUENCY: Per sign structure
| note | fe8876bc-ef85-449e-84ab-482fbe0ee0f4 | CATEGORY: IP
| note | 5cd9fbf2-dd0c-4870-91c6-b1689aa21366 | RESPONSIBILITY: Project /site Engineer
| note | 67515c97-8197-4d63-ba41-6e60be8ed075 | VERIFYING DOCUMENTS: This ITP
| textbox | 2dd91391-e356-4a55-99af-518f460ccd8d | Date Completed:
| checkpoint |  | 4.2 As-built Survey /Asset Identification
| note | 34fb7faf-d2cb-4bfe-a164-bea85fe886e5 | REFERENCE: As built Drawings
| note | e39e5c96-ac4e-4176-be24-b7da94d78a3c | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
| note | 1de7202a-5054-41d7-a5cc-fd6432d090bb | METHOD: Document Review
| note | 3a3eccb5-9bf3-44a5-ac97-99bcf2f8ec58 | FREQUENCY: Once
| note | f0141d5f-eecb-4529-8b45-978ccbcc44e0 | CATEGORY: IP
| note | 78ee979d-5f01-4c7e-95db-2e0904a73a3c | RESPONSIBILITY: Surveyor Site Engineer
| note | f916a184-25da-4b8d-8185-c99310e1844c | VERIFYING DOCUMENTS: This ITP
| textbox | 223a62d7-e29a-40a1-aa90-ccc28701daae | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | d3272c96-fb58-4afc-8a1f-540f0943d01e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 94a34d7a-722a-412e-ba1e-bb08e3c7034b | Name:
| textbox | cccf7d31-2bf2-403b-aa5a-842cc39aec97 | Position:
| textbox | 0b8b7a08-af55-4fe4-8e9e-7e9b55e6ecdb | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Robinsons Rd installation of NFC Drainage Blanket Rev 0 | itp | ITP-CIV-Robinsons Rd installation of NFC Drainage Blanket Rev 0 | ecd2d389-3721-4090-9c94-5acfebfe78f3
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | e948140e-6db4-4079-8720-63a915b50fb3 | ITP Description: Robinsons Rd installation of NFC Drainage Blanket
| note | 8f65c260-ecbf-4d90-bfd1-7e0916eeaa0f | Discipline (e.g. CIV/STR/RAIL): CIV
| note | b436afdf-acb1-476a-8cd0-a6bdfbbd144b | Revision Number: 0
| note | 1efa7bc9-f303-44f4-94ad-eb0fa1e4d3d6 | Revision Date: 15/12/2021
| note | 757dc9de-4bbe-4f7a-8d47-21e330dba461 | ITP created by: Isaac El Zayat
| note | 6e7b4f8e-7412-4acd-aea6-f07ddbef8f57 | ITP approved for use by: Victor Mira
| note | cb05f4bb-9cf2-4196-96ae-27909f7d9a1b | 1.1 VicRoads Section 702 (May 2019)
| note | c7a9df5e-30c9-43b8-bc63-acf2204ef899 | 1.2 VicRoads Section 204 (Dec 2015)
| note | d571c5d0-4257-47d0-8689-8402abe83ad7 | 1.3 IFC Drawings
| section |  | Preliminaries
| checkpoint |  | 2.1 Granular fill (NFC)
| note | 6a20812a-5848-4562-8e30-a2128e60e4cf | REFERENCE: IFC Drawings
| note | 7ecf92a7-9232-4b3c-8e5f-9ffaf0c921ef | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | 6374bdff-1a7f-4c04-bb3f-cb969e155d18 | 702.05
| note | a13d6b44-9e19-4e9d-92a2-ebb2bea16740 | ACCEPTANCE CRITERIA: No fines concrete shall consist of Type GP cement, water and coarse aggregate. The quantity of cement used shall be 4.0% by volume. Grading limits shall be as specified in Table 702.051 for B4 granular filter material.
| note | 23a3b055-2179-4189-9a85-3fa7084cc4c4 | Achieve 28 days UCS of 5Mpa
| textbox | 03e1a4ef-31bc-49a4-aff0-22f595b57ae9 | Enter Teambinder Material Approval Number:
| note | c15fe6a7-dfb8-4faf-8fdf-a68ced525f7e | METHOD: Prior to Commencement
| note | 281aba22-3844-4522-8b65-f53425c8b300 | CATEGORY: HP
| note | 049c1165-95eb-4630-8653-b769f159eda0 | RESPONSIBILITY: Nominated Authority
| note | 085781e8-6537-4218-814e-527689301b15 | VERIFYING DOCUMENTS: ConQA Hold Point Release
| textbox | e6630f51-9d10-4c15-9948-47b2922b98f1 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Methodology
| note | da3e873d-83be-4cd0-be51-cdf063949069 | REFERENCE: IFC Drawings
| note | 7448baa2-0e10-4a9f-ba5f-d61f8bba070e | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | 05a83ba4-12ab-4c18-a60a-42920a276de6 | ACCEPTANCE CRITERIA: To submit Placement methodology to the designer for approval
| textbox | daf221c5-dee5-4112-b32e-8c29a7aba84e | Enter Teambinder Approval Number:
| note | 093af0f3-74d6-4bd4-8e9e-d14900f0bfb3 | METHOD: 7 Days prior to commencement
| note | f6496aeb-1faa-4950-8fe9-a109e6c68897 | CATEGORY: HP*
| note | 05d6227b-c4f5-41b1-95a7-b5e8eac4ab43 | RESPONSIBILITY: SPE/PE
| note | 07f37949-b71c-49f7-8ac1-31b080ba97fc | VERIFYING DOCUMENTS: Teambinder approval This ITP
| textbox | ab43f074-7036-49c6-9abe-d6a2fb1e79ab | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out
| note | fc01799d-91a3-4f4f-aff6-18d9a1ec8590 | REFERENCE: Section 702.3
| note | c926d176-b428-485a-9d57-051403d31d38 | IFC drawings
| note | 3fede1c9-9a61-4b8c-bbf6-a4fa3acd5947 | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
| note | 416eed29-e461-44ca-9cda-a0340167f0c1 | METHOD: Measure , Visual
| note | da8b9dc4-4873-40c3-a459-16477c02906e | FREQUENCY: Each element
| note | f4d228da-e64e-4264-a88f-7b5628543fae | CATEGORY: IP
| note | 5c7306f2-a07f-4543-ba16-c34c3ad76b3c | RESPONSIBILITY: SE/Site Supervisor
| note | d14cdda0-2145-4d70-a631-10c96ef76875 | VERIFYING DOCUMENTS: Sign ITP
| textbox | ad70153c-c30b-4f5c-a303-78e013de5f50 | Date Completed:
| checkpoint |  | 3.2 Cut Floor Level
| note | 05bc7723-d97c-4f06-a824-c53bb5215086 | REFERENCE: 204.03
| note | dd1a3441-1c98-4137-8fb4-d6c568b1082d | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the relevant drawings within the following limits:
| note | 62ab126c-0a56-4a60-aa14-b5f8235214a1 | Mean value range: +15mm to -30mm
| note | 68840df5-cba2-4da3-94e5-25578447a562 | METHOD: Measure
| note | d1d0723d-74f5-4d05-a16f-b4035ffe4791 | FREQUENCY: Each lot
| note | 5e23d72a-dba2-4ce6-9ff4-8769ecdbef52 | CATEGORY: IP
| note | ea02d945-71b1-473a-b3f5-34ac04f7cfc5 | RESPONSIBILITY: Surveyor/SE/Site Supervisor
| note | 5142deb2-0487-406b-bf14-2c4dda9d09cc | VERIFYING DOCUMENTS: Sign ITP , Survey Pick Up Report
| textbox | d30e828c-a3e7-4901-8e4a-6820c5911b0c | Date Completed:
| checkpoint |  | 3.3 Test Rolling
| note | 3b26a783-8caf-436d-ad09-cc0557214c6b | REFERENCE: Section 173.03
| note | 684df550-3564-4765-bf4a-74408dfffb02 | Section 204.12
| note | 51387279-31d5-4544-9d46-66914137b77c | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. The Contractor’s quality plans and procedures shall include test rolling as a hold point
| note | 97cc71dc-acaa-49c6-b603-91613ef5728d | METHOD: Visual
| note | 0eebf474-b751-413b-881e-8b0fae0f8f3c | FREQUENCY: Each layer
| note | c4096683-6d35-4e9e-9b7a-40d1a388ef06 | CATEGORY: HP
| note | 5c392daf-74a2-430e-9b31-9e1b0fc23a10 | RESPONSIBILITY: Nominated Authority
| note | afa7cca4-6ae3-43fe-ba21-45d97499ccda | VERIFYING DOCUMENTS: Sign ITP
| textbox | 2fd45205-313a-47f1-99d0-7339c39b6f04 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Cut floor preparation
| note | 7278f98a-64b5-4ba7-b54a-0345a703a638 | REFERENCE: IFC Drawings
| note | 1592fb53-8204-4915-a33f-7b7083498bae | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | 6e3e32d1-3e57-432a-9e94-3b82ebde025f | ACCEPTANCE CRITERIA: The regulation course of low strength (20Mpa) concrete shall be used to smooth out any imperfections of the cut floor in order to provide a drainable surface that eliminates the possibility of ponding
| note | 9038e917-a5ba-431a-abff-a128dc8c4658 | METHOD: Visual
| note | e57dee54-ef99-4568-9d9b-2a7226449fe7 | FREQUENCY: Each Lot
| note | 40757e40-513f-4751-a7a6-4219f2d236b1 | CATEGORY: IP
| note | 79054932-c908-4d94-8eb4-d5c32fe19705 | RESPONSIBILITY: PE/SPE
| note | 8c0b2508-12f7-4ff5-a804-0def4407cf60 | VERIFYING DOCUMENTS: Signed ITP
| textbox | 47b46515-fe68-44f0-a602-e9afb8b51ce3 | Date Completed:
| checkpoint |  | 4.2 Cut Floor Inspection
| note | 32afa258-1ab9-4cfa-9176-2bd5acfd2efd | REFERENCE: IFC Drawings
| note | 156b4563-241c-43aa-94ce-0d32181403b7 | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | c7bd7d25-d49e-42d2-b17e-e90a81fb9717 | ACCEPTANCE CRITERIA: Surface to be inspected by Geotechnical Engineer for permeable cracks prior to placement of the NFC layer the rock subgrade is classified as slightly weathered, medium to very high strength Basalt
| note | 9aac229b-26a3-4ca5-8ff1-1ac3c2e3b7e0 | Required bearing capacities are to be confirmed on site by the design geotechnical engineer prior to the placement NFC
| note | ff21ff26-956f-4f7b-9706-7f101c31b509 | Visual, Measure
| note | 72340760-b482-4620-bc45-9d193bea2781 | FREQUENCY: Each lot
| note | 13272121-3f9f-4ef5-942a-1630c1086cd5 | CATEGORY: IP
| note | 484e6523-2529-4a2f-81d6-de4780279d37 | RESPONSIBILITY: PE/SP, Design Geotechnical Engineer
| note | bfd3fea7-f231-4d0a-9923-44d9b130a31e | VERIFYING DOCUMENTS: Signed ITP , Record Bearing Capacity
| textbox | b6e1be4e-998b-434d-849a-8a2685df4164 | Date Completed:
| checkpoint |  | 4.3 Placement of NFC
| note | 02d8638f-7e70-4d34-b978-8c2db25d9a54 | REFERENCE: IFC Drawings
| note | cdee782d-4b9c-46ef-99fc-3664f811688c | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | 39c97102-9a25-4d38-8c12-40dbfcafe650 | ACCEPTANCE CRITERIA: Spread and level off the layer of NFC Material = 150mm thickness to underside of base course.
| note | 749747c5-19ab-43e1-838f-dbab94f0ffa9 | METHOD: Visual
| note | b5ec32d2-e256-4516-870d-f1c78cb91847 | FREQUENCY: Each layer
| note | 72061c36-9d9f-4a3f-86bb-171dbf9747aa | CATEGORY: IP
| note | 612c667f-379a-448c-b47b-fe7ecf74e998 | RESPONSIBILITY: SE/Site Supervisor
| note | c08ec78b-99bf-4c8f-bfac-54654ae9f7f3 | VERIFYING DOCUMENTS: Sign ITP
| textbox | acb5680f-5478-4b10-9195-63d31e66288f | Date Completed:
| checkpoint |  | 4.4 UCS
| note | 48182961-719c-45d6-938c-4ed8a7c804c1 | REFERENCE: IFC Drawings
| note | 2ebceb38-d315-48f8-920f-adce02dd3e5a | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | 3cb4b44a-1b17-4ea0-b7a4-d9f904e2ee2f | ACCEPTANCE CRITERIA: NFC Drainage blanket shall cure using Polyethylene sheeting for a minimum of 5 days or until a UCS of 4 MPA is reached
| note | 23ce5ba9-5d4e-4faf-b1eb-496e80baea46 | METHOD: Document Review
| note | 2a8624af-699a-48e9-9a10-4a8a98c77034 | FREQUENCY: Where Applicable
| note | a854bae3-443a-4233-840a-d81e420dd6e0 | CATEGORY: IP
| note | 835d030c-2b0b-4e32-ad11-20dae4de76ad | RESPONSIBILITY: PE/SPE
| note | 05ce5181-8e1c-461c-9a6f-c271373f87d3 | VERIFYING DOCUMENTS: This ITP , UCS Test results
| textbox | 98c9aaa3-2611-4d01-ab74-30b7a2e6204d | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 Construction traffic
| note | f0497ea3-28c3-48be-9e4e-6969c23ccdbf | REFERENCE: IFC Drawings
| note | 58461fad-2af0-4e03-9fbd-448870beccf7 | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | fd6f1cd3-14db-49ec-bca7-cd7629f0c138 | ACCEPTANCE CRITERIA: NFC Drainage blanket should achieve a UCS of 4 Mpa prior to construction traffic
| note | 76bee285-8163-4905-b1b9-5dce7caba984 | METHOD: Document Review
| note | 99c33580-aa26-4ddc-8681-59c738a1b484 | FREQUENCY: Where Applicable
| note | c4a4e222-980d-4cff-9522-4856c5da2746 | CATEGORY: IP
| note | d383db00-1d9d-4b14-886f-1e5110209b4b | RESPONSIBILITY: PE/SPE
| note | a21dc09b-4c9b-42a6-8d61-2c4dfea49ab6 | VERIFYING DOCUMENTS: This ITP , UCS Test results
| textbox | abf642d8-7eef-4edc-b866-9aa6c7a6c904 | Date Completed:
| checkpoint |  | 5.2 UCS
| note | b5a0b324-5772-4b48-9c2e-5d8492c1d7a3 | REFERENCE: IFC Drawings
| note | 52aa3244-37e0-4e13-bac5-fc55f94c5638 | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | e709f25f-e242-4c57-8aef-31fada2ca839 | ACCEPTANCE CRITERIA: NFC Drainage blanket shall achieve 28 days UCS of 5Mpa
| note | d5fcddae-d14b-4a4d-808d-d695fa5e80ed | METHOD: Document Review
| note | 94316260-9af7-49e3-86d3-bc5bb212ad5e | FREQUENCY: Where Applicable
| note | 1340af73-c3a3-459f-a5c0-cff83314ed57 | CATEGORY: IP
| note | 7bc22492-ca59-439d-9199-14ec33c1c12a | RESPONSIBILITY: PE/SPE
| note | 0cba9fdb-f0d3-452a-8a41-73847ad55011 | VERIFYING DOCUMENTS: This ITP , 28d UCS Test results
| textbox | 06183283-6671-4394-8758-b8a5f74be09f | Date Completed:
| checkpoint |  | 5.3 Permeability
| note | d3921926-ec11-4252-b61c-eeac084b681b | REFERENCE: IFC Drawings
| note | ab80fb19-666a-4524-a071-b2d981bc9fe2 | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | 55baad32-4932-470b-85b3-caa25b9ebf71 | ACCEPTANCE CRITERIA: NFC Drainage blanket shall have permeability of not less than 0.015 m/s when tested in accordance with TfNSW T377
| note | 35a8e04c-7282-4435-a728-e2f61d02da06 | METHOD: Document Review
| note | 6b281a92-64a1-4301-842f-aa4f726c5497 | FREQUENCY: Where Applicable
| note | 489f235c-e001-4c0c-864d-f0c3f9fa9454 | CATEGORY: IP
| note | 7dda5569-9608-4124-abee-e11bc9e5760a | RESPONSIBILITY: PE/SPE
| note | 6d972b84-970e-4ca0-9d7d-22acd897a3ee | VERIFYING DOCUMENTS: This ITP , Permeability test results
| textbox | 6993c8c4-10e4-41c8-a751-984aea5e4ed4 | Date Completed:
| checkpoint |  | 5.4 As-built Survey
| note | 53a27463-c606-406d-a878-e19863301f01 | REFERENCE: IFC Drawings
| note | b5cb2806-b8d7-45e1-9ecd-86448f474b11 | MRP-072-C-AUR-DRG-11-DPK-CPT-0102
| note | 78620b9c-870c-417e-8bd1-9ffe781ac1db | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
| note | cb8e5d78-a8bf-4808-af68-750e0296c3f3 | Attach: Survey As-builts / Survey Report
| note | 64da4d51-0586-4ee0-bacd-0029bfd0cc8d | METHOD: Document Review
| note | 60339c2e-074c-4165-aaf2-de4428920c6c | FREQUENCY: Each element
| note | 626cf7bb-6261-4748-b4d6-de4a953fa256 | CATEGORY: IP
| note | e1d115f8-4384-4c2e-8b3e-a47e85601f61 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 1fe20e99-6c81-4f3c-a751-df3e5492ab9a | VERIFYING DOCUMENTS: This ITP
| textbox | 0a6a9288-326c-4dac-ae43-dc7e2249f131 | Date Completed:
| checkpoint |  | 5.5 Non-conformance Report (NCR) Closure
| note | b9248666-83b7-484d-b16f-8193f8ae3892 | REFERENCE: MRPA Quality Management Plan
| note | 12b2c9c2-1d49-4b33-b6f6-f2d9f8d9cdae | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
| note | 64a4cbb9-59ab-4141-8c17-2b62a61f765b | METHOD: Document Review
| note | 1128ad96-bb0d-487f-b210-a6191d732b7a | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 1b49fdfa-ef61-40ef-9a4a-523067982c92 | CATEGORY: HP*
| note | 9e550eb5-47c6-49c5-9edf-0eb5ca079c81 | RESPONSIBILITY: SE/PE/SPE
| note | 81d4652b-3adb-4b08-8cd3-d028672e4be9 | VERIFYING DOCUMENTS: This ITP
| textbox | fa8f9605-0527-4ce3-9aa1-10cef2f35a24 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 2a70002d-9c2c-432d-8d4b-5b79ea442801 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | d4a2706b-7a79-4682-ba43-b574737c7389 | Name:
| textbox | 8ef3dc0e-fbc8-4b47-9821-03155ac66bee | Position:
| textbox | aa21c3eb-7f75-4261-ac5e-8efedf4e8600 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-RSS Wall - Fill and Strap Installation Rev 0 | itp | ITP-CIV-RSS Wall - Fill and Strap Installation Rev 0 | f01604e4-68d3-4658-b5f1-d5519731376e
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | faadf2a0-7b8b-423d-b0ed-2ef271a4013d | Document Title: ITP-CIV RSS Wall - Fill and Strap Installation
| note | bfebcd69-ca2b-4b1c-a826-4762711fc432 | ITP Description: RSS Wall - Fill and Strap Installation
| note | b1629b35-eca9-4bf5-9781-e80b7a76a8f5 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 7cf26c49-fcc7-4c8d-b39a-380d0c43165c | Revision Number: 0
| note | 027806bf-9aa8-4a8b-a052-2966b134671a | Revision Date: 26/11/20
| note | cacdc734-ef79-4392-ae7f-170befc30806 | ITP created by: Matthew Brown
| note | 3d89dc3c-de4e-4266-bb4f-5accde0d5394 | ITP approved for use by: Josie Pavlou
| note | e142269d-46c0-481e-badb-e8b906aca839 | 1.1 Reference Documents:
| note | fba15faf-e3ca-4529-8ac7-4642a86554ff | VicRoads Standard Section 204 (December 2015)
| note | f6efff82-8925-44a8-b26f-bbe7e2471be8 | VicRoads Standard Section 682 (November 2018)
| note | 7e72c60f-a5d4-4bda-8474-a0c98b1ec45a | Vista Wall Installation Guide
| note | 3cd81e4e-1412-4ea9-8f29-020343434b8c | IFC Design Drawings
| section |  | Fill Placement
| checkpoint |  | 2.1 Surface Prior to Fill
| note | e721f67f-20b8-4e32-88f4-d9af9afde01c | REFERENCE: VicRoads Specification 204.10 (b)
| note | ea25baa6-2ddc-4242-9bae-497449422edf | VicRoads Specification 204.11 (b)
| note | 476ec450-4ffb-4422-bd7f-6c08d2b54ade | IFC drawing
| note | c0dab32e-19a1-4ca9-9b5d-a60775e41ff5 | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed: No fill to be placed until the area has been reviewed and approved by nominated Authority.
| note | 4497b850-a58a-466e-9f30-7b6f3d851727 | Note: Applicable where time since completion of previous layer (since Nominated Authority sign off for proof roll on previous layer) is more than 2 days or where there has been a significant rain event, otherwise N/A.
| note | 188284d9-4164-4b0f-b5e4-412817f64c50 | METHOD: Visual Inspection
| note | 426cb1bc-2dc7-420f-b2e9-b611e387e683 | FREQUENCY: Prior to commencement of fill works
| note | 61e092f1-9f0b-401e-bc67-5c25ba7de304 | CATEGORY: HP
| note | a14dd9a4-e159-4fbc-a86f-099d0f7786f2 | RESPONSIBILITY: SE
| note | 853988b2-46c9-4440-9a77-4412e62ae314 | VERIFYING DOCUMENTS: This ITP
| textbox | bb61bc9b-6fbc-49a1-b9f2-37f4944485c5 | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.2 Placement of Fill
| note | 7d70bd97-77fa-4691-b8d0-d24dfb140528 | REFERENCE: Section 204.10
| note | 5b1b3b70-2287-4ea2-a8ad-59a4aaf273ae | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
| note | 18a63d9c-0ec2-44c9-908b-721dc8df4732 | All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
| note | e7941999-cc56-41c2-840a-f099597f0e3f | METHOD: Monitor
| note | d19f3ce9-fcf9-4e56-8c51-1985c040cd14 | FREQUENCY: Each layer
| note | 39664245-7bc4-4f7a-a747-09086d8964ca | CATEGORY: IP
| note | 5abad9a7-2a64-46d4-9143-0c0c157169e6 | RESPONSIBILITY: SE
| note | 65c266e8-0851-4edd-8e41-7e98995cc5eb | VERIFYING DOCUMENTS: This ITP
| textbox | cacc7f14-bf5e-4106-a97f-75e4d437f3d7 | Date Completed:
| checkpoint |  | 2.3 Care of Reinforcing Straps - Compaction Plant Activities
| note | ed237cdd-04bf-420a-93ea-69c4b2b38569 | REFERENCE: VicRoads Specification 682.16
| note | 12bb6e99-caf4-4efb-ad20-4233286124e6 | VicRoads Specification 204.11
| note | c425a14f-92dd-43c3-af59-892fa59d2405 | VicRoads Specification 204.11, Table 204.111
| note | a1adf542-b1a7-4329-b1b3-77bae1d79651 | IFC Drawings
| note | a5f20a7b-ef33-41fe-89fb-6a00cfcb975a | ACCEPTANCE CRITERIA: Filling and compaction shall be conducted with care in order to avoid damage to or displacement of reinforcing straps and facing panels.
| note | f3966613-1e30-4390-b502-10243bb15206 | Tracked machines or vehicles shall not be allowed to traffic over or work on reinforcing straps until the reinforcement is protected by a minimum 150mm layer of fill material.
| note | bed4907e-7997-4285-8ccb-15d70fa89647 | Pad foot rollers shall not be used for compaction of fill material.
| note | 49c30a41-cb0e-4c5f-8bf0-7a2a4318fe38 | Construction and compaction plant shall not be operated within 1.5m from back of wall and comply with minimum distances shown in table 204.111.
| note | d0d512af-1e70-4a4c-a10f-d0c761f0a32f | Only hand compaction allowed within 1.5m from back of wall. Material is placed in layers that ensures required compaction is achieved.
| note | f00e0556-0373-44b8-aa31-3c5c1fa849a2 | METHOD: Monitor
| note | f3358f8c-b850-46f0-9017-554cf83581c8 | FREQUENCY: Each strap layer
| note | 740a4518-02e5-47b6-9eb8-476aeacc36a7 | CATEGORY: IP
| note | 88608287-83b1-4c26-9877-bba7ac4faf3c | RESPONSIBILITY: SE
| note | 55c3e03c-ed41-44ea-8fc6-2a0bf0425767 | VERIFYING DOCUMENTS: This ITP
| textbox | cd759f4a-fee0-43a5-a9bd-0fa97a29d03d | Date Completed:
| checkpoint |  | 2.4 Construction Loading RSS Wall/Abutments
| note | c2cab275-6246-4c20-a076-45104db422f1 | REFERENCE: IFC Drawing no.: MRP-045-C-RFLD-DRG-33-DNG-CSW-0001
| note | 05a94d6f-b1ee-480e-ac2a-de0d378e9c70 | Project Specific Notes #9
| note | a3b6a06e-d60f-4977-b517-1823db24559b | ACCEPTANCE CRITERIA: Maximum construction loading based on 35t Franna Crane with 10t load. Cranes are not permitted within 3m of installed wall panels
| note | f092cfa0-66cd-4006-8416-0691d1306f95 | METHOD: Doc. Review
| note | 9a626ec7-c309-4de6-9e38-849a7837e5d7 | FREQUENCY: Each layer
| note | 9762e2c7-9444-4b4c-adba-e4a00c928d10 | CATEGORY: IP
| note | cdafc329-0da7-4cb1-8c73-9498c7c4cb2b | RESPONSIBILITY: SE
| note | cfb95630-3d6a-49fd-8d30-111be87c3d52 | VERIFYING DOCUMENTS: This ITP
| textbox | 940b57da-c286-47d5-86ec-4ca27a0893a3 | Date Completed:
| checkpoint |  | 2.5 Testing Rolling
| note | 4658969e-dd8a-4162-9eef-4510079078de | REFERENCE: Section 204.12, 173.03
| note | c80301a4-6458-4416-be9f-ee76c80819b3 | ACCEPTANCE CRITERIA: All layers of fill and cut floor level to be test rolled in accordance with section 173.
| note | 4d5a78d4-c77e-40f3-895a-8ef690d859da | METHOD: Measure
| note | 816d88e3-dbae-434b-bfa2-8f9a546564d3 | FREQUENCY: Each layer
| note | bc2ddcee-3f0a-4203-a497-6e42f1dc214c | CATEGORY: HP
| note | 7f1389c5-cb3f-482f-b48d-62bd9bf58ca7 | RESPONSIBILITY: SE and Nominated Authority
| note | 6ad07585-bbea-4db9-a179-e126ec69123b | VERIFYING DOCUMENTS: Sign ITP
| textbox | 87fc6ca8-3ee7-45a4-99a5-0aaf298a528e | Date Completed:
| signoff |  | NOMINATED AUTHORITY HOLDPOINT
| checkpoint |  | 2.6 Post Compaction - Compaction and Moisture
| note | af906793-bbbb-4fba-8563-c85db45e50df | REFERENCE: IFC Drawings
| note | 35dbdf26-7173-4f92-8878-3e0a07f18ebb | VicRoads Specification 204.04
| note | 72bf8cf4-3c4f-4185-8c4b-b43c8dd23632 | VicRoads Specification 204.131
| note | 4a8d6a3d-3e78-4276-8366-3946d1afbecc | VicRoads Specification 204.14
| note | df933d41-33cb-4b76-b41c-3b97e5e1e19d | VicRoads Specification 682.16
| note | 6d1fa8b8-7c38-4c3f-b4bf-a26890b54a45 | ACCEPTANCE CRITERIA: Tested for compliance in accordance with Table 204.041 & 2014.131 (Scale B) & Table 204.141 in addition to the requirements below:
| note | d104dc9a-feff-4314-97d1-5c0bf3e41ba4 | RSS Fill:
| note | ec3e427c-7094-4fa2-86b4-21b37140c468 | Compacted to 98% Standard Proctor Density
| note | a5a9f64c-31a7-4ba9-bf59-9e21bd5879d4 | Moisture content to be 0%-2% of the optimum moisture content
| note | 837f2b57-bc78-40d0-9af2-c4da5ca2fcec | METHOD: Doc. Review
| note | ad8d9847-2f24-4073-a961-8f2636776c57 | FREQUENCY: Each Layer
| note | ce90fec3-c93d-44fa-a0b7-c55eca719f6c | CATEGORY: IP
| note | 04034abe-cb9d-4112-9d16-58c273309ec1 | RESPONSIBILITY: SE
| note | 4a3fec62-50b3-4f8e-8275-68518b7757ef | VERIFYING DOCUMENTS: Sign ITP Material Test Report
| textbox | 5345dfa1-f893-4a9c-9db9-eb2b19d8228a | Date Completed:
| checkpoint |  | 2.7 Post Compaction Material Property Testing
| note | 7015a114-4c63-445a-b97b-9515b2dd38ea | REFERENCE: IFC Drawings
| note | 59cafe53-c019-44b7-bb5a-29d8764389cc | Table 204041
| note | 867d1fa3-c7aa-4977-a814-c49ad35306ce | Table 204.141
| note | 46eb9bdc-6410-4000-8b47-ff519849a946 | ACCEPTANCE CRITERIA: Post Compaction Material Properties:
| note | 0734601a-ff17-4552-bf83-95fb2dcb586d | Liquid Limit: ≤ 30%
| note | f2638e7c-be12-41de-86ba-5aed2b7ad856 | Plasticity Index: ≤12%
| note | d493a4d0-6d09-4e32-b4d1-b4c21c8cf05e | Grading:
| note | d15c833b-f09e-4c27-abe8-37e2be188db5 | 150mm AS Sieve: 100% Passing
| note | e48da940-6098-4eb7-8706-2fbedc609c62 | 37.5mm AS Sieve: 60-100% Passing
| note | 4ce32090-3255-42ef-b157-099b8ee94e5d | 9.5mm AS Sieve: 25-100% Passing
| note | ed2bf84f-48e4-4ef0-9e56-b7d3d2c73e9a | 2.36mm AS Sieve: 15-100% Passing
| note | f83fa4d4-9192-4a77-a304-f7d23d136e49 | 0.6mm AS Sieve: 10-100% Passing
| note | 667dd3f9-a0e1-410a-90f4-b0a8d6e3ab63 | 0.075mm AS Sieve: 0-15% Passing
| note | f2b2e213-8cac-45fd-8047-af987baacac1 | CBR ≥ 6%, Swell ≤ 1.5%
| note | 6a33b637-e7c7-437f-91c9-edc6a5e53f4e | Scale B:
| note | 14f313a2-1cc2-466d-9eac-1749739cafdd | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm
| note | 45a75c4a-4089-4104-a319-a11208cba99e | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
| note | 8b41688f-9582-4f8a-9371-ce54e21d94fa | METHOD: Review Document
| note | d2df9ded-5a19-4f42-b91c-9cff088d1420 | FREQUENCY: Scale B: 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
| note | 9f2e5f67-e3ad-4e24-8df4-f3b2beba4781 | CATEGORY: IP
| note | 7d7d3629-c232-4383-842a-334a50f404d5 | RESPONSIBILITY: SE/Site Supervisor
| note | baff6aeb-30db-4054-a758-0babdeedd113 | VERIFYING DOCUMENTS: This ITP Attach Material Property Test Report
| textbox | 0ed6d511-b487-4460-81d6-92c44a712b76 | Date Completed:
| checkpoint |  | 2.8 Material Property Testing At Quarry
| note | 2bf080ac-28d5-471c-8059-36c00793f855 | REFERENCE: Fulton Hogan Tynong Quarry: South Gippsland Highway Dandenong South Project – RSS Wall Select
| note | dabb0fad-33e3-41b7-b9fd-0053b0785a82 | Backfill ITP
| note | 7836e304-7522-4d68-92c9-be17f3a12c86 | ACCEPTANCE CRITERIA: Material Properties:
| note | 51c6dab4-d987-4ee8-b374-c6c2840b5dc6 | Internal Friction Angle = 36°
| note | ff793a38-1e8a-419b-b076-0c14bf3b50ec | Liquid Limit: ≤ 30%
| note | c55264bf-0741-4323-acb2-9355486f2bea | Plasticity Index: ≤12%
| note | 0465fb9a-925e-4032-b301-6e69fbd142c2 | Coefficient of Uniformity: ≥5
| note | 15b94307-c210-4117-89fd-80c862389b52 | pH: 5-10
| note | b0c85b10-fcf5-403b-9fc8-7ebfa2f00bbf | Resistivity: > 1000 ohm-cm
| note | 2a9fd360-9b0d-4244-b2ac-57cba74b4ead | Chlorides: <200 mg/kg
| note | 55eb1d44-c979-4b2e-82f7-fb91ae402c1f | Sulphates: <200 mg/kg
| note | ca52a297-46ce-407f-9adb-33dc21d6eb7c | Organic Content: 0%
| note | 6b12afed-3cab-4475-bb72-d85deca9e577 | Grading:
| note | faf8aa45-e0aa-4b66-aec8-a039505411d9 | 150mm AS Sieve: 100% Passing
| note | 06e83e80-64ce-4104-810a-d43b4ae2d3e6 | 37.5mm AS Sieve: 60-100% Passing
| note | 0263f67c-d717-4664-90dc-300616fb7660 | 9.5mm AS Sieve: 25-100% Passing
| note | fb854604-2e1a-43d0-b615-b785ce1534af | 2.36mm AS Sieve: 15-100% Passing
| note | 4468b47f-1992-40e7-93f2-49a696867a17 | 0.6mm AS Sieve: 10-100% Passing
| note | d28176b1-b1b6-498e-b371-9618c257a126 | 0.075mm AS Sieve: 0-15% Passing
| note | 16c699ab-b4f4-46d6-aa88-fb91c49c69ef | METHOD: Review Document
| note | 6f84f7ef-0932-4442-be68-fd22c5911389 | FREQUENCY: As Per Quarry ITP
| note | 8b718733-0a7b-4f9a-a20c-3943ee9aeb59 | CATEGORY: IP
| note | 126046e7-ee56-4e7b-88c9-1baa9f6c3f2f | RESPONSIBILITY: SE/Site Supervisor
| note | 2a1750d5-ec09-4774-af2f-0118579f17dd | VERIFYING DOCUMENTS: This ITP Attach Material Property Test Report
| textbox | 52bb7170-46f7-4455-b404-c4c79cf13416 | Date Completed:
| section |  | Strap Installation
| checkpoint |  | 3.1 Galvanised Coating
| note | a8c1386b-a667-4b7d-9782-8b861c62e1b6 | REFERENCE: Vista wall Installation Manual
| note | afd70668-0f1d-44a7-ad5c-a1ce7bbf770a | ACCEPTANCE CRITERIA: Visual check that galvanised coating is not damaged prior to use.
| note | cbca6939-32f8-45bc-9575-f78d887193be | Refer to design advise from RSS strap supplier.
| note | dbbbb0db-7994-4276-8328-fe62015f3a65 | METHOD: Monitor
| note | 6e5b06b0-65df-4766-b1e9-da89a652a8a8 | FREQUENCY: Each strap layer
| note | a3a61826-74a4-4268-bd6a-377593f707e8 | CATEGORY: HP*
| note | 788b96a6-85d7-4d31-8018-bbfc7e2066a7 | RESPONSIBILITY: SE
| note | 43912292-f7af-4363-883d-2a2ae2798b6d | VERIFYING DOCUMENTS: This ITP
| textbox | c549dec1-946f-435e-8ce4-fcf691d41937 | Date Completed:
| checkpoint |  | 3.2 Strap Installation
| note | 49f7b1d8-d8b7-4dbd-a940-e4afa25e59c3 | REFERENCE: IFC Drawings
| note | ba0a5301-abc2-4a79-856d-30298e4f4421 | Section 682.17
| note | 6c70b838-e0f1-4cd4-90d8-862ddd23fde9 | ACCEPTANCE CRITERIA: Reinforcing elements shall be placed at the required level and position directly on top of the compacted fill material and connected to the wall panels in accordance with the design. Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
| note | 756cafbe-c6a7-4aef-8547-23b965ac0178 | METHOD: Monitor
| note | 72538d33-8769-47fb-8a78-d95c83243554 | FREQUENCY: Each strap layer
| note | 8aa97e46-c461-48f5-8987-8b9146d2a528 | CATEGORY: IP
| note | 9288efbf-eec9-4062-85fe-e3f06b602cef | RESPONSIBILITY: SE
| note | 52244243-db2b-429d-8224-b8e50fe9aada | VERIFYING DOCUMENTS: This ITP
| textbox | 83939072-f8fc-4a8b-8509-fa078a1440c4 | Date Completed:
| checkpoint |  | 3.3 Strap Location
| note | a037a231-500a-42a2-9b2e-6eb182ff5008 | REFERENCE: IFC no. MRP-045-C-RFLD-DRG-33-DNG-CSW-0111 to 0113 and
| note | bad781ae-755e-4e9d-b3ec-cad840ee76ba | MRP-045-C-RFLD-DRG-33-DNG-CSW-0131 to 0151
| note | 7fdc31b1-26a3-4eea-bab5-ee0f305da701 | ACCEPTANCE CRITERIA: Mark-up panels clearly after installation for construction teams to indicate design location of straps.
| note | 0ff55785-9314-4d2a-b04d-508ac869da54 | Note: multiple connections are cast into panels to create a "standard" panel during fabrication and should not be used as the actual strap quantity.
| note | 3f47468d-a80f-4963-82f3-26bb7e72c1b3 | Design drawings show strap location and arrangement for each panel.
| note | e6574ccd-4cf9-47f2-b714-817b91762f16 | METHOD: Doc. Review, Visual
| note | 972f2cb2-13a4-49e7-9780-d7be673c8eb0 | FREQUENCY: N/A
| note | 04447b67-5109-4f3d-8ef0-de8ab7435ce1 | CATEGORY: IP
| note | 6be0991e-f8f4-4237-a0a4-5d625b550e84 | RESPONSIBILITY: SE
| note | b4618c2c-c9db-4260-b29e-4859c01ac489 | VERIFYING DOCUMENTS: This ITP
| textbox | a446f65d-6407-40f3-b2a7-cffbd8b963ec | Date Completed:
| checkpoint |  | 3.4 Strap Length
| note | abf56361-8a25-49df-b1a1-b31d9dfd364d | REFERENCE: IFC No. MRP-045-C-RFLD-DRG-33-DNG-CSW-0000
| note | af63311b-6f67-4cbe-a0a4-be47257990bb | ACCEPTANCE CRITERIA: Ensure correct strap length is installed.
| note | d9b7726b-a09b-472b-9aca-f154d60c921f | Refer to grid strip schedules on IFC design drawings
| note | 9aeb7f32-ad0a-45e8-b629-eec4dc6deb45 | METHOD: Monitor
| note | e354f38e-7671-4349-8d15-08a522b8a7c3 | FREQUENCY: Each strap layer
| note | 1ed364ce-4c86-4791-bebe-6f974317f343 | CATEGORY: IP
| note | 45e9ea2a-ba17-4fbb-9b44-5b456f7ed118 | RESPONSIBILITY: SE
| note | 861adc65-162a-454e-9d65-f1ea51122ba0 | VERIFYING DOCUMENTS: This ITP
| textbox | 0437a634-20b8-4baf-a502-2621f51c5282 | Date Completed:
| checkpoint |  | 3.5 Strap Connection
| note | 60bc8ee3-e20b-49fe-8478-6aaeaa30e017 | REFERENCE: Section 204.10
| note | a9c59694-07e3-49de-b1b5-e08a16fe2c52 | ACCEPTANCE CRITERIA: Ensure straps connected as per design detail and Vista Wall construction guidelines
| note | 7c071457-1a6d-40aa-bb59-9cd1d23b31a7 | METHOD: Monitor
| note | beac2bcc-dd6f-4bf4-9145-cd8808605aab | FREQUENCY: Each layer
| note | ed632a76-3258-40da-bf3b-0a74609a95a6 | CATEGORY: IP
| note | 0043e0a4-b59f-45bb-8b90-616a94930f5e | RESPONSIBILITY: SE
| note | 34d3b4bc-b89e-46ee-b184-d9cd3a913509 | VERIFYING DOCUMENTS: This ITP
| textbox | 28427652-15a1-4e64-8087-c4e583fb6dd7 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 4.1 Survey Conformance As Built (Top Layer)
| note | a8ab0f0c-e31c-477d-a95f-4cdd6e605ad7 | REFERENCE: Section 204.03 (d, g & h), 206.16
| note | ea0554f8-5b28-448b-9132-1057bdd5aa4a | ACCEPTANCE CRITERIA: Scale B:
| note | c7965ea6-209f-4e11-82ef-a16f7e46213b | Min. No. of Measurements Per Lot: 40
| note | 2127e71d-bc7d-4a98-9c81-538eebad6bf5 | Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
| note | 099c5261-fd18-4896-8675-b3cc9025b638 | METHOD: Review
| note | 2454c83a-f52f-465b-aa7a-6318f99593d8 | FREQUENCY: Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
| note | 6c724bc7-f9a1-464d-bf17-4b0168f2eb42 | CATEGORY: IP
| note | 3c41fde5-fa10-40f7-a3e2-c70b9b754bce | RESPONSIBILITY: SE
| note | 4cb4a705-adb8-493f-a67a-00aeebf970b7 | VERIFYING DOCUMENTS: This ITP Attach: Survey Conformance As Built
| textbox | a382e118-97e4-464b-a8ab-798dc2ae07c1 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | e8289ec2-8c9d-4b17-809a-6a41118b943f | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | c19632a3-2fe4-4be9-99e7-7f23f9287601 | Name:
| textbox | 4683ba86-1a59-409f-bc4c-980af543403e | Position:
| textbox | e43463cc-dbde-4a25-b112-12c67363340f | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | itp | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | f2d3b61b-dc7e-4044-9a73-4df1a0425a88
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | bf5a93e6-cadd-4272-b52b-8e7ecc334f33 | ITP Description: Kerb and Channel (Supply and Install)
| note | 98857f7e-6df7-48a3-a044-641ef9c346e7 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 26eec72a-2017-4d78-b820-285a225e54f7 | Revision Number: 1
| note | 38cda143-a2e0-48de-95a5-eba7bb5111a7 | Revision Date: 28/08/20
| note | 75f0b9bb-91eb-4cb0-bd06-668e7cb35af1 | ITP created by: Saaf EL-ZUBAIDI, Isaac & Velcek
| note | 0be47783-5fef-4626-89da-8b1b29c853d6 | ITP approved for use by: Josie Pavlou
| note | 5eded922-9431-41c5-950b-55eae8281b92 | VicRoads Section 703
| note | 4d93d8a7-f34c-4d35-b260-77ed3af47377 | VR SD2001
| note | e10ffc6b-b9fc-4bc4-83cf-bb9708485032 | VR SD2102
| note | 7fe7a274-dab4-4ec1-92eb-3ad7254cbc54 | AS 2876
| note | 32a2ad43-255c-4037-92c4-a22e2c1bd82b | AS1379
| section |  | Preliminary Works
| checkpoint |  | 2.1 Check for correct documentation
| note | 9d638470-95ad-4633-9f67-eb338bfd0f7a | REFERENCE: Drawing and Drawing Register
| note | 120054e9-a8e1-4e18-8ce0-04e6ab4eec65 | ---------------------------------
| note | 8265ba6c-7b47-414f-8682-37bbeea16f54 | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are : -Using the correct and complete set of drawings .- All drawings are the latest version
| note | 2a7d9217-01b0-432d-a036-1b005111d77b | ---------------------------------
| note | 57ae00d7-0b5c-4314-9de0-06c341913e50 | METHOD: Visual inspection
| note | 510862d9-d1b2-482d-bbd7-5dd875e7869e | ---------------------------------
| note | 80148902-7b6e-4e75-9a1f-3a1641e2f368 | FREQUENCY: Prior to commencing any activity
| note | b542eb42-0041-4ad7-84c3-0f26254dc2c5 | ---------------------------------
| note | a56f5a10-3a38-4e24-9fd2-33cafdde2013 | CATEGORY: HP*
| note | 65a87046-b0bb-4c9a-a573-c2ac37e31187 | ---------------------------------
| note | 7fbe9c32-5987-4c15-aba1-8ad731f1b83b | RESPONSIBILITY: Site Engineer/Site Foreman
| note | b97520a3-22c9-4dfb-8eb2-f4ab8f5ac959 | ---------------------------------
| note | 87902cfe-d9a8-49e4-8a59-8d1e0a9bfeeb | VERIFYING DOCUMENTS: ITP Signed
| textbox | 70ec4a33-1bd2-4e3e-9375-e32929f05f8c | Date Completed:
| checkpoint |  | 2.2 Mix design
| note | 4b10fa2d-d4ae-4fa5-a55d-b0a28b6b1633 | REFERENCE: SD2001
| note | b7150b4d-ed9b-4ab7-9cd9-bdc84dc1d496 | AS1379
| note | 26682514-6d94-4c0b-a3a0-3abf8130c77b | Section 703.05, 703.06, 703.07
| note | 172d2923-dc98-471b-808a-7d7fe2622d34 | ---------------------------------
| note | 0c1dc611-53a9-49ec-9ef4-5269f7d142b4 | ACCEPTANCE CRITERIA: Approved VR mix design to be used.
| note | fd1b708e-b4aa-4837-aae1-7e085716fc13 | Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
| note | 0258e9ae-587f-46d3-9753-ca7cc9a0c5e2 | Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
| note | 696f5743-c6b1-44ac-84f6-5fc7dd116980 | ---------------------------------
| note | 2ab42684-9adf-49d3-b905-ef6f8d1ce16f | METHOD: Verify
| note | dda0525c-b256-4931-99b0-9522ee75d905 | ---------------------------------
| note | b683c04d-e82e-4f71-b5fd-765e65f8b041 | FREQUENCY: Prior to commencing any activity
| note | 2142595e-2dfe-434f-a985-fa7fd065b984 | ---------------------------------
| note | 53ce5c2e-5069-4386-9b05-299b7fd5688a | CATEGORY: HP*
| note | a02538da-785a-4fb9-978c-f69d5d23b171 | ---------------------------------
| note | 7d855273-a41f-4f98-bef5-58e95dc85ba2 | RESPONSIBILITY: Site Engineer
| note | 2b05bc01-e22d-4173-b681-062766a0594f | ---------------------------------
| note | e7ab4b9c-b091-4a55-9933-338ca166f9bd | VERIFYING DOCUMENTS: ITP signed/Mix Design Certificate
| textbox | 6ad46e19-e045-48f4-8e18-95487b5c6286 | Date Completed:
| checkpoint |  | 2.3 Bedding Material
| note | bacb202b-76ff-47bc-9cf6-dfbf6ddfc9c2 | REFERENCE: Section 703.21
| note | b7404390-3d0e-46ec-92ff-941050f0eacf | IFC Drawings
| note | d12b9e8d-c2b7-4700-94e9-e27e08b7529a | ---------------------------------
| note | 30bd4ef1-d344-4156-95fb-74e49a42fe37 | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
| note | 841d288e-bbee-41e4-a0c0-3a7209f6ec91 | Beaconsfield Car Park: Bedding shall be size 20 mm Class 2 Crushed Rock in accordance with IFC drawing detail
| note | 47f4a578-3ac6-43a4-866e-c5cc2f44f8a3 | ---------------------------------
| note | f41f1efd-913b-4db7-9d8f-9678b5475f89 | METHOD: Verify
| note | a652f067-d0c4-4563-9e46-ae34dc001b87 | ---------------------------------
| note | 3400c1b0-e02e-46d5-9e14-2ea2f42785f3 | FREQUENCY: Prior to commencing any activity
| note | 8f40b1b3-dc29-465d-848a-7d220218cea8 | ---------------------------------
| note | 78a5e66e-778e-423d-90dc-5198d9716588 | CATEGORY: HP*
| note | 2234daf8-1672-4b71-b490-f1340cb40e41 | ---------------------------------
| note | c460d00d-8154-4766-9fd7-15b1809c6f10 | RESPONSIBILITY: Site Engineer
| note | 36d965be-f111-4430-9e2d-f01896a14476 | ---------------------------------
| note | 95bad6a8-0bf4-4bbb-b454-a3e45c7675db | VERIFYING DOCUMENTS: Material Conformance Certificate
| textbox | 6b1ad9f8-3604-4e63-9e52-428c1fca0008 | Date Completed:
| checkpoint |  | 2.4 Curing Compound
| note | d6daabaf-2c55-4661-9a5f-62e942876db6 | REFERENCE: Section 703.10
| note | 07feb4b0-aef3-4caa-bb0f-6136cc92f1f1 | ---------------------------------
| note | a2130682-1a51-4e95-a224-4d326e4f78a3 | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
| note | afa1cd49-b001-466b-ae49-aeed50f06933 | ---------------------------------
| note | 15dbfc03-b731-418d-9b09-69c623659549 | METHOD: Verify
| note | f9027386-5d3e-42b4-a994-c516e44e5f75 | ---------------------------------
| note | 626e5472-d136-4751-9daa-c979e1f24762 | FREQUENCY: Prior to commencing any activity
| note | a36fe187-90bf-4784-ad66-f3b1549e02b2 | ---------------------------------
| note | 9b2a9a0a-241d-4c19-829f-ff4b5fb02976 | CATEGORY: HP*
| note | 12545bfe-b5e8-460d-9d40-a585d751622b | ---------------------------------
| note | bb82bef6-3dc2-4047-ad16-bcc725bde5b7 | RESPONSIBILITY: Site Engineer
| note | 6226469f-5e3c-46a1-bfbd-68915bbbbfe1 | ---------------------------------
| note | cfefda3d-50ed-4094-914b-6ef2caf7b5a9 | VERIFYING DOCUMENTS: Material Conformance Certificate
| textbox | f2d470ec-ab83-4333-afac-6d13820d5ad5 | Date Completed:
| section |  | Pre-construction / Pre-installation Activities
| checkpoint |  | 3.1 Setting out
| note | 67914f92-4a6c-4205-bb22-a6b4e15e3a40 | REFERENCE: Section 703.17
| note | ca916733-2a36-4b59-af96-833b0aa6cc4b | ---------------------------------
| note | 218faa95-0a77-4e3c-b955-148faa2bfedc | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
| note | e11c9a45-7959-4007-9ef6-8fc3b45b48b0 | The superintendent will review and confirm set out.
| note | 177b5f88-92c1-47ab-a992-fa9d04ffa1ae | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
| note | 7b00a84c-727c-4366-a4d9-c11e546ab7a9 | ---------------------------------
| note | 89e04158-93c3-402e-8ad3-0ed95e83c578 | METHOD: Verify
| note | b70e6dc1-355d-42ad-b564-4db20d891bed | ---------------------------------
| note | 713b132d-6c80-4978-aeb4-b0f6c05883ed | FREQUENCY: Prior to start
| note | cbcdf8f2-dc19-4a46-a704-fb23a982bfc6 | ---------------------------------
| note | 445076e0-6bbb-4b01-b272-702ade21dce5 | CATEGORY: HP
| note | 12e00563-7248-40b3-a824-8ac87a4176f3 | ---------------------------------
| note | fef95a2f-bc26-49d1-b025-e91652b90e02 | RESPONSIBILITY: Site Engineer / Superintendent
| note | db41496b-e282-4b44-afa9-6058f9baa9aa | ---------------------------------
| note | 147330fb-8d51-43ad-8c25-ec96be68e2aa | VERIFYING DOCUMENTS: ITP signed
| textbox | a53e875f-d718-4b28-b60a-2590b67c90b9 | Date Completed:
| checkpoint |  | 3.2 Temporary drainage provisions
| note | 45140ec2-5b81-4d01-83cf-6e1f9d00ca78 | REFERENCE: Section 703.18
| note | 6ea6f12c-832e-4c4f-8acd-cacf7d90bca2 | ---------------------------------
| note | 15af68c2-bfd2-4a92-b304-7764e9065b52 | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels ,temporary diversion of discharge of drainage and storm water to be in place.
| note | dd8216f4-1be6-44d9-a5fd-5bf7bf1d513e | Need to obtain prior written approval from the relevant waterway authority prior to diversion.
| note | eaa8ea62-620c-4bc2-9b2c-3fd272faea7e | ---------------------------------
| note | bfe138a1-226b-43ff-aade-a4a530ee1836 | METHOD: Visual inspection
| note | f84113b6-25ef-4dcc-b376-2a72ccc7b787 | ---------------------------------
| note | 4f204bda-3a0f-495d-8502-76f7ecd64822 | FREQUENCY: If required
| note | 7e7775b9-a819-4870-a11a-59ffe9518850 | ---------------------------------
| note | dbd23a75-6eb2-45a9-bdae-19823489ba53 | CATEGORY: WP
| note | ef545baa-223e-44b5-a8da-3b269c265c56 | ---------------------------------
| note | 73146624-4001-4bc8-a8c0-7acbde7edca7 | RESPONSIBILITY: Site Engineer/Site Foreman
| note | 2a70e3c3-7ca5-45f7-aaa0-aec83cc36e4b | ---------------------------------
| note | 55f39d03-b297-439b-b7c7-5acbcc472b8a | VERIFYING DOCUMENTS: ITP signed
| textbox | e0691150-2187-40ed-a76c-d7190eff6a59 | Date Completed:
| section |  | Construction / Installation Activities
| checkpoint |  | 4.1 Bedding
| note | 96eb17f3-c0af-4313-bae4-822d5c38b29b | REFERENCE: Section 703.21
| note | bb6b9818-d5c4-4ab8-8f49-3aa9e6fcd188 | ---------------------------------
| note | e292be18-90f8-4c51-8a5d-cd9765f352a7 | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm .
| note | 6d1bd515-1b2b-417c-822c-2385ffae53c3 | Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
| note | 004795c2-d4e0-4e5c-a9cd-784d0a6c1eb1 | ---------------------------------
| note | 62a4e36a-4408-4015-a844-5c3f05eafe70 | METHOD: Visual inspection
| note | b6c91791-31e8-470d-9324-ad016688c10a | ---------------------------------
| note | 31c42783-1bff-4bf4-bc71-a425c4e06e78 | FREQUENCY: Each lot
| note | 49602ade-3234-4912-bb17-71f956c2867a | ---------------------------------
| note | 095ad1c9-b1ca-45e3-aa33-3396c00b429f | CATEGORY: WP
| note | 776063c8-c4a8-4387-8b7a-bc3fcd5ef753 | ---------------------------------
| note | 279a388e-df2d-40d6-91df-ad477ce18844 | RESPONSIBILITY: Site Engineer/Site engineer
| note | 31ba0045-e51b-442f-9508-5fe3fdbe1579 | ---------------------------------
| note | cacaa18d-42b5-4f92-8fc4-17f177fc9464 | VERIFYING DOCUMENTS: ITP signed
| textbox | a29f16c4-eae3-48d1-b0d9-b7a572f27d02 | Date Completed:
| checkpoint |  | 4.2 Formwork
| note | 61a3bdae-0c7c-4811-87ad-a2d210910c1c | REFERENCE: Section 703.12
| note | 27a8da9a-1ccb-4b61-8894-d2928e610033 | AS3610
| note | edc428b5-4a93-4b42-bca9-c66416190b68 | ---------------------------------
| note | 5e49d5d7-ec85-451c-8526-ff7639f53141 | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
| note | 19fc9973-6712-459e-b48c-a864f34b180d | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
| note | d2582c5f-f238-4ec4-a674-4d60d0970ea0 | ---------------------------------
| note | 10ab4a17-1fa6-4cc3-88ce-5addcfbf3ad8 | METHOD: Visual inspection
| note | 0f72291c-0871-4f79-b6f1-fb8fe14583ab | ---------------------------------
| note | a9e6e9d1-5df5-4004-b114-a581921aac47 | FREQUENCY: Each lot
| note | 85a272b0-4352-42fc-8757-755a9723602b | ---------------------------------
| note | 129d389d-c729-4f3a-ac8a-e4bae88a4a35 | CATEGORY: WP
| note | e1453f53-9a1e-4b97-b11a-ce1a7e0a005e | ---------------------------------
| note | a4d34782-dd35-40b6-aba2-18bd6930f124 | RESPONSIBILITY: Site Engineer/Site engineer
| note | f33a6738-26e2-4153-921b-a155ada92950 | ---------------------------------
| note | 50a870bb-1ea7-49d6-a111-cd2704824848 | VERIFYING DOCUMENTS: ITP signed
| textbox | 5a0722ed-18d1-44d0-a212-4404007f9455 | Date Completed:
| checkpoint |  | 4.3 Pre Pour Check
| note | 3276bb7d-2e5e-43d2-a6ad-50a2bf4a9e7f | REFERENCE: Section 703.09
| note | 411459a5-828c-4e5a-b8b4-e3ee1e27012f | Section 703.21 Section 610.17a), b) & c)
| note | 58c478a0-778c-4d5b-a8e4-52f249c8f683 | ---------------------------------
| note | d14a273b-e08f-4400-a115-8dd28c09bee9 | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface .
| note | 4a2bcd7f-e93d-4f14-9ae5-bdeb1c55c71a | Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
| note | 348675b2-f81f-4e62-ab0f-f54de9468107 | ---------------------------------
| note | 9b75065e-37ae-47d2-81d5-8c0cc4e6264a | METHOD: Verify
| note | d2759aac-f015-4ec7-9daa-5b8fca94c590 | ---------------------------------
| note | db26fcc9-ced9-4ab3-8b75-10dc29246be7 | FREQUENCY: Each lot
| note | 53570945-5f8c-474e-9a76-a9867cdc11b4 | ---------------------------------
| note | 464f404b-3003-482f-9fac-4fc7271421f8 | CATEGORY: HP*/WP
| note | 5a0cad26-ce7e-4e07-8c27-6d9c7c8625c1 | ---------------------------------
| note | 0ddcaa6b-cb71-4f6b-bb03-4fd94f5814cc | RESPONSIBILITY: Site Engineer/Site superintendent
| note | 6f6eb98e-5722-4e54-8868-4df8d4d6ff1d | ---------------------------------
| note | 1050dce2-5eb1-4089-9487-c1a989518687 | VERIFYING DOCUMENTS: ITP signed
| textbox | 6bb37c2a-c78f-4721-8d49-7c3b0dd0b071 | Ambient temperature-----°C
| textbox | 28f05bd7-e021-4f05-b5e1-f2a516c97f29 | Date Completed:
| checkpoint |  | 4.4 Concrete placement
| note | 187f34bc-00db-48a1-bd44-7b1f4f30d28b | REFERENCE: Section 703.08
| note | 5f79ab2a-6037-4d3b-b8a6-b925f6e14212 | Section 703.23
| note | 361fd2c4-60ac-4892-b97d-2debe19b5779 | ---------------------------------
| note | 6045751d-c54b-45d2-9b2f-6915cf0a8c95 | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
| note | 0face41c-787b-4dd0-b843-d2d106bd58a0 | Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
| note | f3405dff-c1e0-4a34-8f79-dd22a536efed | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
| note | 55cf84cd-4daf-4fbf-a4ac-5d2fa533a13c | Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
| note | 354f8337-1e74-42ea-84df-d09195142ecf | ---------------------------------
| note | 0269acf1-c2fc-4ce5-8305-de4eff77411d | METHOD: Site inspection
| note | e64698cf-f9e6-4511-922d-fa054dd0dcda | ---------------------------------
| note | c368cc84-2b7b-4111-a3dd-fc9995c6b033 | FREQUENCY: Each lot
| note | 3bcf9795-f310-46fc-b756-b27c8ac48f54 | ---------------------------------
| note | 64900613-c52f-4b07-ae0d-4e6a0ee5597e | CATEGORY: IP
| note | c8c331e5-a9df-46ab-ab57-ffe9b1fd4a20 | ---------------------------------
| note | d92a7b50-2803-4be4-8d3e-948745dcdcdf | RESPONSIBILITY: Site engineer
| note | 25386be5-0f63-49e9-aa0a-d97bd3462d22 | ---------------------------------
| note | 87abe954-24f4-4482-8fa4-e29fcde1c30f | VERIFYING DOCUMENTS: ITP signed
| textbox | 506a0020-cf71-4410-8c77-16cdf20d1bb6 | Concrete Temperature ---°C
| textbox | 33aa5360-08d1-43fc-8034-9fd668e8f06e | Date Completed:
| checkpoint |  | 4.5 Transitions
| note | 294a5edb-f356-436e-a598-1b836c357d29 | REFERENCE: Section 703.24
| note | 48f6bf51-9a0a-4f53-af4d-142aa2ac96e4 | ---------------------------------
| note | 77131749-36a8-4db1-8a4d-92365fd94349 | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
| note | 25344015-e174-4c0b-9bf2-ae5081488163 | ---------------------------------
| note | 36c82d9a-17c0-4e4b-b42b-3efde50f8dcd | METHOD: Site inspection
| note | 8ba9027f-3258-48ed-b5d4-890e39454487 | ---------------------------------
| note | bb93c69c-6852-4293-9855-ba0f7425c63d | FREQUENCY: Each lot
| note | 76953d2c-59fd-4ca3-a264-ea07701c67fc | ---------------------------------
| note | 501ee5bb-3912-4a18-a06d-efa2a03e7afb | CATEGORY: IP
| note | 955dce00-0da0-4c50-a381-1702e2e5e35f | ---------------------------------
| note | 90a1eb27-3914-46a2-bf82-e9ceb2f3ec1f | RESPONSIBILITY: Site engineer
| note | 27c80209-ce39-4b6e-a40a-5d3464a197d1 | ---------------------------------
| note | ac4851f7-b045-4863-8f48-4c0e2ccdb221 | VERIFYING DOCUMENTS: ITP Signed
| textbox | a33f93f4-c93c-4c66-a3e3-fbd3fd17f0b6 | Date Completed:
| checkpoint |  | 4.6 Surface Finish
| note | acf13f34-56bf-4001-9935-e5c08539f0c6 | REFERENCE: Section 703.25
| note | 836fa0d5-2707-4c77-9586-2e282250fa53 | ---------------------------------
| note | 35cfc003-d310-4065-a400-c1cad9d1a70b | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
| note | 76421c20-fa80-4c93-a205-a6d9e142d151 | Renderings shall be applied within 30 minutes of extrusion.
| note | 55f72db4-694e-449b-8ce4-0731099bc918 | Concrete to have a neat appearance and uniform colour.
| note | 09b824a5-7a5d-4809-bce1-56d1461a0488 | Class 3 finish required for external surfaces.
| note | 4e212f96-0ba4-4d23-9580-cd504638d968 | Class 4 finish required for permanently hidden surfaces.
| note | f6cbde3b-8e4f-4b18-a7e3-de8099ed8399 | ---------------------------------
| note | dfa87634-e515-4bf7-887a-b4e7696a5d33 | METHOD: Visual inspection
| note | 3d43df9b-ba68-4271-8fae-28bc6e09480b | ---------------------------------
| note | 3fc50a29-b7aa-4f59-84a6-1eb6ee0b9be5 | FREQUENCY: Each lot
| note | 635b6187-7124-4fdb-909a-ded4fb35fc43 | ---------------------------------
| note | 0eaa9343-2b61-469a-999a-dbb44c0c8d71 | CATEGORY: IP
| note | dc52cb76-134c-4275-b875-7a4df3c32ae5 | ---------------------------------
| note | 499d8844-9b43-4139-aec3-cbb59b86d77e | RESPONSIBILITY: Site Engineer/ Site Forman
| note | e66ba90d-0edb-4829-ae2b-2325912b6a0f | ---------------------------------
| note | ce2881b9-5e9c-456f-9afc-d654584533e5 | VERIFYING DOCUMENTS: ITP signed
| textbox | f8e3e4b0-f7e9-43a6-a358-dca18161a102 | Date Completed:
| checkpoint |  | 4.7 Formwork Stripping
| note | 3bc7012f-4e09-4a52-8455-a757b7a22ff9 | REFERENCE: Section 703.12
| note | 2468ce29-d94f-4f59-9b87-9eb014b731cf | AS3610
| note | 7a616254-3fcb-4206-8e7f-d2c73bdfef77 | ---------------------------------
| note | 60811f2b-c1d9-4038-be13-c27513fa50db | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
| note | a793f4dd-1e6a-4b42-bf64-1602eaa77a62 | - External faces 2 days
| note | 09069ece-baa0-42b0-b483-9456834be347 | - Permanently hidden faces 1 day
| note | 8aff8926-3380-4308-8e8f-e9de16ff3aea | ---------------------------------
| note | f1e43a4c-da68-4f6e-9791-702ba766cb96 | METHOD: Visual inspection
| note | 8f4389a5-0f81-4136-9e6e-9c9ba34f98b6 | ---------------------------------
| note | ba48537c-9b50-4632-b2a7-e1f08d9ea3a0 | FREQUENCY: Each lot
| note | 895f9592-cb09-4f7f-af9d-fc9af4ef7fc2 | ---------------------------------
| note | 77137f80-7d56-4e01-b9e2-eec523aa2181 | CATEGORY: IP
| note | 8320b9db-e799-48e7-9714-b64bd8eb926d | ---------------------------------
| note | 71760cb0-22cd-4f1c-b59f-2c0cb62a5dd4 | RESPONSIBILITY: Site Engineer/ Site Forman
| note | 915a71d7-6467-4455-9228-ca1b2147ec12 | ---------------------------------
| note | 617eb238-f048-4bd8-8eb8-c4685054615f | VERIFYING DOCUMENTS: ITP signed
| textbox | 676197db-020c-499d-a4cd-f104d52f88ee | Date Completed:
| checkpoint |  | 4.8 Tolerance
| note | 10483a69-30d7-474d-aedf-0432730abe64 | REFERENCE: Section 703.15
| note | ec3cd9b7-fe6a-4ba3-bbda-cd3b6381603c | ---------------------------------
| note | a6c94436-f221-46d3-b92b-40e139f72801 | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
| note | aed74b95-eb49-4883-9819-0c92b35b4ed2 | Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
| note | 58014450-c905-4f3e-9297-3731e2f27f86 | Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
| note | 71cb8f20-7950-4287-992a-e0f73c85e2c8 | ---------------------------------
| note | 58444205-d56b-4b0c-9d78-ce758108cbe0 | METHOD: Verify
| note | 6a0695bd-5a68-44fc-810a-4d2573847cb6 | ---------------------------------
| note | fc4d14a3-6c4d-469a-bd85-6fd9549779cb | FREQUENCY: Each lot
| note | 0f76ff60-8c24-4ed2-bcf0-8bcc2efc78f7 | ---------------------------------
| note | 2989cbc7-5d97-4cda-b6cb-b469a33ca57c | CATEGORY: IP
| note | 236f0f36-1d95-4438-a5ca-1f27ce9893dc | ---------------------------------
| note | 1ba453f9-33fd-414a-889d-122b246c550b | RESPONSIBILITY: SITE Engineer/surveyor
| note | 6a3afb3a-822a-47e9-a374-f17f8dddc6d5 | ---------------------------------
| note | db7feb10-d0a5-4eff-baf4-fff4d46c519c | VERIFYING DOCUMENTS: ITP signed
| textbox | fe653558-af92-4cf0-a096-4321e0657fe3 | Date Completed:
| checkpoint |  | 4.9 Curing
| note | 33fa5db4-d641-4fa7-9c97-517dbead20ab | REFERENCE: Section 703.10
| note | 401843bf-904d-41bf-909a-81d49fa75889 | ---------------------------------
| note | 9f9d0c30-44b9-4d0c-a545-1765e9b8240f | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
| note | e3d3eabc-ab2b-4abe-827d-30e15be2342c | Concrete edgings shall be cured for a period of not less than three days after placing the concrete
| note | 7d13dd18-cbf9-4f01-bbbd-a0f367b98fc0 | ---------------------------------
| note | 24629265-f682-4ebd-844d-d50a479820c1 | METHOD: Visual inspection
| note | 5ea9c3f1-8b1f-4492-b8dc-0bc0cb42d93c | ---------------------------------
| note | f52807f6-6525-4e6a-8a40-8d4c69bd00a2 | FREQUENCY: Each lot
| note | 6878a34d-20cf-4701-a7e5-3f262767afa5 | ---------------------------------
| note | 65fa024e-1a7b-4ea5-b7ef-a5b73fcf43cd | CATEGORY: IP
| note | edde0d1e-ba70-4fac-8acf-dbf3d46f6400 | ---------------------------------
| note | 4ea4dd0a-a70e-413d-a0d5-f851cd541975 | RESPONSIBILITY: Site Engineer/Site Foreman
| note | 920c7206-598f-44e3-9464-ec6874e2bf98 | ---------------------------------
| note | 6ac6d633-d83c-4bde-8b53-2be4be522707 | VERIFYING DOCUMENTS: ITP signed
| textbox | 9a3c33db-6500-4ff5-8bf5-c67755b6b750 | Date Completed:
| checkpoint |  | 4.10 Joints
| note | f1a88e2e-5d90-4ede-b241-e8105b598091 | REFERENCE: Section 703.26
| note | 5c203828-df31-4ea5-a02e-112f623b1af7 | ---------------------------------
| note | 6ff53700-f464-4068-a8a3-7e64f579e985 | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
| note | 52d8c776-59f3-4ba8-a9e6-c950447e1282 | Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
| note | 60e27595-0306-4de2-bef8-2d0c2736e81c | Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
| note | 10ea7cf2-0917-4aa4-974c-475541175b76 | ---------------------------------
| note | a3ef9c82-3bec-4b9e-9acb-b7e54ae0a90d | METHOD: Verify
| note | bbb7a8c0-c9be-4f02-a461-39c047ecfec7 | ---------------------------------
| note | def98fa5-d2e0-4a7d-8b9a-010489b80966 | FREQUENCY: Each joint
| note | a677dedb-ff96-4824-ab37-0bf8466110c9 | ---------------------------------
| note | b039298f-00c0-4dbf-bebb-b9488408a8b6 | CATEGORY: IP
| note | 4d7bebba-13db-48d1-b3ab-3b9fe53bd9a4 | ---------------------------------
| note | 9de09ccb-aa32-47ef-9261-896a60d8b660 | RESPONSIBILITY: Site Engineer / Site Forman
| note | 56dd2893-9e57-4c18-9492-1d8b6cad0992 | ---------------------------------
| note | 2954cdc0-d056-4987-94f8-ae708965cc52 | VERIFYING DOCUMENTS: ITP signed
| textbox | 60dd5eaf-046a-4e6e-aaa8-8a755d9b7066 | Date Completed:
| checkpoint |  | 4.11 Backfilling
| note | bff9b761-f3bb-4378-abd0-3a4e2d7cbe55 | REFERENCE: Vic Road spec 703.29
| note | 9025a465-5066-4fbe-9a21-e50158f6d30b | ---------------------------------
| note | c1e16a0d-6f58-4bcc-9402-e8b18afb4202 | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
| note | 41f5f817-1a8a-41c7-ad15-bf6547d163a6 | ---------------------------------
| note | d839831b-2ed7-4574-8e7b-0341fe1bf826 | METHOD: Verify
| note | ae43d840-e2aa-4923-b9cb-5b0ad9e23192 | ---------------------------------
| note | af369e95-23a6-4ceb-b972-71e846c113c7 | FREQUENCY: Each lot
| note | aedb7fed-1cf7-48a9-9ff8-cfc5e2a90d7f | ---------------------------------
| note | 6e35fa3f-3957-42c9-b89e-a50d0a95ca67 | CATEGORY: IP
| note | 2b426fd5-adb1-4356-a491-54e861ab8e5f | ---------------------------------
| note | fa7af1cf-3542-49f5-a85c-3f0954666cb9 | RESPONSIBILITY: Site Engineer
| note | c0fe6f53-37b2-4814-bef2-7762c5080cf4 | ---------------------------------
| note | 105ed75f-8d79-49e5-aaf0-561d62b2f207 | VERIFYING DOCUMENTS: ITP signed
| textbox | 783d9cbe-5314-4396-a93d-6bb0235d6802 | Date Completed:
| checkpoint |  | 4.12 Protection of Concrete
| note | bae73c58-f6b1-449e-8bdc-f7450e015b87 | REFERENCE: Section 703.27
| note | 160b1b33-6230-4a9f-ba2d-1290d6a6fc88 | ---------------------------------
| note | b0b9d7e8-b423-462a-9cd6-65cf2cd9610b | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
| note | fb1ac42c-4b0a-40c7-bd29-81d26659acc1 | ---------------------------------
| note | 15e8fb83-24de-400e-8d9c-6e01b68dee72 | METHOD: Visual inspection
| note | 4d141166-37b5-4125-aeac-2dccf5b7b434 | ---------------------------------
| note | b19305ae-f078-4df4-aa7b-826e01838e3e | FREQUENCY: Each lot
| note | 6fc2582f-ce4a-4be9-a828-ac8f79fd2c38 | ---------------------------------
| note | 13f08bec-25de-42b2-8f63-4a2d2f7b865c | CATEGORY: IP
| note | 71dfbbc1-555c-4857-8cbc-80430ffee44a | ---------------------------------
| note | 50ad4193-bbd2-4336-bd90-94bd25a018b8 | RESPONSIBILITY: Site Engineer
| note | 8270f74e-ca01-460b-94bb-ac2bd8365cf4 | ---------------------------------
| note | 0cfa6882-228e-40ca-8123-64fedd272b29 | VERIFYING DOCUMENTS: ITP signed
| textbox | 4c9db5d5-e7bf-4813-8c1e-811daf959bb6 | Date Completed:
| checkpoint |  | 4.13 Cracking of Concrete
| note | 0db6b613-150a-4647-8ee0-0aefb50dd232 | REFERENCE: Section 703.30
| note | 369af505-99fb-48e9-986d-93697cdca5db | ---------------------------------
| note | 6a525384-0456-438f-929f-5956a991bc1f | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
| note | a43c61c5-fc63-49a0-82ea-3bb497cbf98b | Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
| note | d99aed9e-777c-442a-8763-31d1acff6d05 | ---------------------------------
| note | 5f8b0e06-4d2b-419b-b035-3f2f1e5595b1 | METHOD: Visual inspection
| note | ee12ba93-e7e4-4279-b4d5-11a579e12c3b | ---------------------------------
| note | 8c533cc3-7be5-4111-bfb1-263595a9afec | FREQUENCY: Each lot
| note | ff1bd543-f86c-4d05-b503-60529a29dec5 | ---------------------------------
| note | 992c06c8-4486-4704-8c0e-f0bdee254533 | CATEGORY: IP
| note | 45ad04da-c556-4b68-a09a-0f9b43d7fdb4 | ---------------------------------
| note | a78d7597-6ae1-4efc-b25b-82f8921c7a27 | RESPONSIBILITY: Site Engineer
| note | 90b10943-e121-40c5-8d6f-9c1e64b4cd89 | ---------------------------------
| note | 6b26369c-91b4-4b17-828c-3df40633b449 | VERIFYING DOCUMENTS: ITP signed
| textbox | 0059a5a9-0dd0-4a8e-b7c6-94634935b22d | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 5.1 Survey Conformance
| note | 12800a65-90d3-4ee3-a0f5-aa228b7ea7cd | REFERENCE: Section 703.15
| note | 8ad736ba-24d6-4446-8238-77fc944ab478 | ---------------------------------
| note | ea367f90-df4e-44e0-ba44-f8d4c549ddba | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
| note | 1d736a1c-013f-4c7b-b213-2cf660ca6866 | ---------------------------------
| note | 9658a37e-c4d2-4f33-91f5-0187bd710f96 | METHOD: Document Review
| note | e8b6bdbf-32ea-4620-b41a-4cea5725077b | ---------------------------------
| note | e0fd0375-c815-41cd-934a-812cf3af3b0f | FREQUENCY: Completion of each lot
| note | aa2d3a6a-8838-46b0-a1e3-e5bb8e6f543a | ---------------------------------
| note | f1134825-cb51-46c0-9af1-28b56238cd45 | CATEGORY: WP
| note | 5d5eac72-a6f4-4819-9dcc-2195afce0e53 | ---------------------------------
| note | a55953ba-fad3-44f5-97f3-18124f317384 | RESPONSIBILITY: Project Engineer/ Surveyor
| note | 2d7b1986-ba6b-40d6-a172-850d178a85ae | ---------------------------------
| note | c605936b-d00c-4796-a79e-573f935482ba | VERIFYING DOCUMENTS: As-built survey records
| textbox | cbb8c697-e319-47bd-a57d-dbcd653a0813 | Date Completed:
| checkpoint |  | 5.2 Non-conformance Report (NCR) Closure
| note | 0c030b74-1a80-46aa-85ef-5c5d924cdbb9 | REFERENCE: MRPA Quality Management Plan
| note | 21e182c8-a67a-4811-bdb9-eb96e5a64de6 | ---------------------------------
| note | 0a17ed1a-39e3-4363-b869-fe32ce4cf22e | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 46cdfdb9-9e78-421b-9e4e-b90107e51c8b | ---------------------------------
| note | a74a380e-306c-4a80-bad5-dae1d0223711 | METHOD: Document Review
| note | 85c2ce3e-c732-4cfa-b5fd-3f55d69269b0 | ---------------------------------
| note | 8e710f23-e004-40d0-80dd-cbb0e3fd09a8 | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 3d4a247b-f9ea-40f0-a469-077fa1cfdd5e | ---------------------------------
| note | 63d79b1d-7be0-4d18-b67b-cd4007ea9207 | CATEGORY: HP*
| note | 91bdf50d-0d1d-4505-a04f-46d533808b37 | ---------------------------------
| note | 711f6d9e-289e-4d03-9ca6-86a310479dd5 | RESPONSIBILITY: SE/PE/SPE
| note | 7591efc4-24d1-4bdf-8880-afb47cc3eb3a | ---------------------------------
| note | eb04787b-20fe-4190-9846-27944976f77e | VERIFYING DOCUMENTS: This ITP
| textbox | b98a3d32-8bc2-4d54-a4bd-4cc8e9461ceb | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 4ea403e6-91e1-459a-95a0-2f25350a849e | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 73ea5f9a-1dba-4c87-82db-25032fef3c8c | Name:
| textbox | 36d9e745-022d-4e6e-ae7f-e9daeec0e66b | Position:
| textbox | be0bb1c5-ece1-456a-8c39-844d6b1ef5b3 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-RSS Wall - Levelling Pad and Strip Footing Rev 2 | itp | ITP-CIV-RSS Wall - Levelling Pad and Strip Footing Rev 2 | f323c935-ca63-4cd6-b137-19aa3b270d56
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 626dfb6a-639a-497b-895d-6956fdf2f7c8 | Document Title: ITP-CIV-RSS Wall - Levelling Pad and Strip Footing
| note | ac1cd5d7-699e-4ddc-9290-efc461ec1beb | ITP Description: RSS Wall - Levelling Pad and Strip Footing
| note | 7c87af4e-43bc-439c-aab7-e594f168fbf7 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | c24eadad-44b8-4a9d-bbc1-e408d4f98ae6 | Revision Number: 2
| note | 08acc17a-948b-448b-bd55-683dd3d20772 | Revision Date: 44132
| note | 30c586a6-9507-4851-ba0d-612db2e931b9 | ITP created by: Khalid Kamel
| note | ba19dd92-803c-4e99-8314-b367f1d9b781 | ITP approved for use by: Josie Pavlou
| note | 72b12eb8-e464-4688-9ffc-902ca71ba5f5 | Referenced Documentation
| note | ffd070fe-7268-401b-a68d-3246a027c708 | 1.1 VicRoads Section 682 Nov 18
| note | 96f700ee-204d-494d-86fe-255dd36bc346 | 1.2 VicRoads Section 620 May 09
| note | 7474c1c7-0290-4845-8e10-779e7fcc106f | 1.3 IFC Drawings
| note | 01e95912-5734-42a2-9974-b0a76fb1cdc8 | 1.4 Temp Works IFC Drawings
| section |  | RSS Wall - Levelling Pad (Panels)
| checkpoint |  | 2.1 Survey Set-out
| note | edf9703a-a973-425e-a046-eba189e94c62 | REFERENCE: IFC Drawings
| note | eb294078-5ab8-4d13-960b-fbd80624fcad | ACCEPTANCE CRITERIA: Survey Set out points of the levelling pad. Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
| note | 88041bf8-3ac0-4bdf-bb42-09dd7a6788dc | METHOD: Measure Visual
| note | df621e6f-5de2-4764-802f-f306d88cf40b | FREQUENCY: Each Lot
| note | 31e7cb0a-7758-4ab7-bdd7-786c21785303 | CATEGORY: IP
| note | e9abc0a7-7e66-4529-a178-36d45115add3 | RESPONSIBILITY: SE/PE
| note | b3f2168e-a739-4f86-8d84-8af969298537 | VERIFYING DOCUMENTS: This ITP
| textbox | 58110037-3a67-45e2-8eb4-86c2c1084afb | Date Completed:
| checkpoint |  | 2.2 Box Out Levelling Pad
| note | 4891086a-ba5b-46c6-8adb-1dfc37ecf0b8 | REFERENCE: IFC Drawings
| note | dc5bec78-c521-4517-9535-06cb4fb977ad | ACCEPTANCE CRITERIA: Box out levelling pad as per deign level and survey set out
| note | 2c14ec77-b423-4fbe-9a87-9dfd972bed96 | METHOD: Measure Visual
| note | 4d7442d6-38ae-4b59-be8d-95337fe2b14f | FREQUENCY: Each Lot
| note | 706688d1-af1a-4d6a-bfb9-a8ab39c7e23d | CATEGORY: IP
| note | 62e6a215-ef46-4c34-b892-8a714c42651a | RESPONSIBILITY: SE/PE
| note | e8e5cc33-b830-4efd-a844-6984ae39c473 | VERIFYING DOCUMENTS: This ITP
| textbox | 89f822e9-d992-430b-8e78-5b813b1cfc46 | Date Completed:
| checkpoint |  | 2.3 Form Levelling pad
| note | 09ffddcf-b35e-4971-b532-6de906bfbae9 | REFERENCE: IFC Drawings
| note | 4a643675-f43b-4d45-85aa-7cf9bc166ea8 | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
| note | 7a16e512-6399-484e-a4bd-045dfe340921 | METHOD: Measure Visual
| note | 137bd623-abb4-4b18-b039-d8b68638f7ef | FREQUENCY: Each Lot
| note | 79fe9aa8-87aa-4923-9329-01c42fa34226 | CATEGORY: IP
| note | 1f8eabc4-3af0-41ba-a015-2a07215ed37b | RESPONSIBILITY: SE/PE
| note | 5c484a27-6c89-43f9-b62f-4608f7f16156 | VERIFYING DOCUMENTS: This ITP
| textbox | d2b5f808-442c-4246-af13-99a3eb350b9d | Date Completed:
| checkpoint |  | 2.4 Concrete Pour
| note | 05b883e6-caf7-41f9-bbab-7aeaf508be70 | REFERENCE: IFC Drawings
| note | 7e45adfe-53c4-4ea1-8ac2-fe5b6408d35a | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
| note | c0b75f97-b649-47e9-bba7-b42f3c9a4fbb | METHOD: Visual
| note | dafb7246-239a-4c8f-a0df-dc97f2f71a67 | FREQUENCY: Each Lot
| note | 1eb0d844-9691-40fb-b8b3-dabd4ab11235 | CATEGORY: IP
| note | 440ca879-befa-4b21-914e-9d0a19d2b615 | RESPONSIBILITY: SE/PE
| note | d7207e06-ec35-44f8-9c97-684c2296a353 | VERIFYING DOCUMENTS: This ITP
| textbox | ccea1070-aefe-444d-824e-8c63ba2abd1c | Date Completed:
| checkpoint |  | 2.5 Concrete Testing
| note | 338ac75d-11f6-484c-bffc-3ceee826acf0 | REFERENCE: IFC Drawings
| note | fe8a1824-84e8-4c97-b2a6-af11c6187280 | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
| note | 28563c1b-b974-4977-8075-4e415cc71091 | METHOD: Document Review
| note | 36b577d5-09cd-4520-a3a0-6fbad5129859 | FREQUENCY: Each Lot
| note | 97b81a20-6c90-4ddb-8250-97e9bf584459 | CATEGORY: IP
| note | 3c3b84e1-275a-44c1-98bc-81413e288116 | RESPONSIBILITY: SE
| note | 914fcc28-fc98-4fa4-a502-944206ced6d1 | VERIFYING DOCUMENTS: Attach Concrete Strength Test Report
| textbox | 755a3e89-132a-4d9d-abd7-9b2c63bd74ca | Date Completed:
| checkpoint |  | 2.6 Concrete Curing
| note | d8ce57f7-4aa2-4f1c-95bf-eb695799c8f7 | REFERENCE: IFC Drawings
| note | 9d886a85-4b38-4ae9-83b9-3f1a83b97efd | ACCEPTANCE CRITERIA: Curing Compound shall be applied post pour
| note | 1b0faf76-f02a-4539-8730-02cdc5b5ba4f | METHOD: Visual
| note | 243b5c78-c94b-4696-9d11-ca09d1e84152 | FREQUENCY: Each Lot
| note | 1b15d033-02d7-4226-83b3-3ea7e4d755dd | CATEGORY: IP
| note | 807e3d5d-a2af-4f23-8e83-00c3418ba2dd | RESPONSIBILITY: SE/Site Supervisor
| note | 3ccde066-8d6e-402e-a393-96726b355f87 | VERIFYING DOCUMENTS: This ITP
| textbox | 4b1f854e-846d-4fcc-bd60-6fcffc22e727 | Date Completed:
| section |  | RSS Wall - Strip Footing (Propping)
| checkpoint |  | 3.1 Verify Ground Pressures
| note | 7fc4f471-d1df-4b9a-9a5c-a962556ab7f9 | REFERENCE: Temp Works IFC Drawings
| note | ab5e1c79-a631-42cd-85f2-e78fee346d7d | ACCEPTANCE CRITERIA: Bearing Capacity Requirement under Strip Footing shall be a minimum of 50 Kpa
| note | 8209a6ab-723e-4e7c-9b6c-9a2495a24918 | METHOD: Document Review
| note | e370718f-590c-4c2e-b9ed-f8e28a34389e | FREQUENCY: Once, prior to the commencement of works
| note | 9ff9c819-e584-48f5-ae2e-a83934e89d1e | CATEGORY: HP*
| note | 6e70ed64-881c-48fa-a096-70b25f866370 | RESPONSIBILITY: PE
| note | 354e5134-7aa0-48bb-96cf-582a3cbf5051 | VERIFYING DOCUMENTS: Attach Geotech Report
| textbox | 2f3bd318-c02a-471a-a30d-720c12220057 | Date Completed:
| checkpoint |  | 3.2 Survey Set out point
| note | 57c84038-ab3e-4081-a3b9-486354ff46d1 | REFERENCE: Temp Works IFC Drawings
| note | 0e8ed8b5-28ba-4870-a0c7-d14324b72625 | ACCEPTANCE CRITERIA: Survey Set out points of the Strip Footing. Strip Footing is a 800mm wide by 300mm thick unreinforced concrete footing
| note | 51add799-9ad2-4f73-ab63-7989618c1d80 | METHOD: Measure Visual
| note | 89a87606-3bd7-4ca5-8b50-9809eefc75e4 | FREQUENCY: Each Lot
| note | e39c9afa-bf5a-4435-9a9a-f600ca514da6 | CATEGORY: IP
| note | 452cbc2b-e686-45e2-a5f6-14447c2ab190 | RESPONSIBILITY: SE/PE
| note | f5711467-cf87-4027-bc8e-ff91a4a8f544 | VERIFYING DOCUMENTS: This ITP
| textbox | b79ddaa1-15ef-45ae-8b35-d01c442a3429 | Date Completed:
| checkpoint |  | 3.3 Box Out Strip Footing
| note | 4ea244c3-a24d-4c6c-b38c-02a663de191a | REFERENCE: Temp Works IFC Drawings
| note | c9b60d71-5a9b-4ee8-8201-cb696cda3f23 | ACCEPTANCE CRITERIA: Box out Strip Footing as per deign level and survey set out
| note | 722f695a-6250-4303-a62a-add40ce1a572 | METHOD: Measure Visual
| note | 6a472535-f136-48a1-a4eb-5a99d59c6a59 | FREQUENCY: Each Lot
| note | 7a9e5482-5329-46b0-b19b-1fcc0f3ccbc6 | CATEGORY: IP
| note | e54048d6-feaa-4ab5-90ab-86a094a6c40d | RESPONSIBILITY: SE/Site Supervisor
| note | 47fc7593-f601-42b9-aafe-03e1424f874f | VERIFYING DOCUMENTS: Signed ITP
| textbox | 7c6666e5-567a-4d7f-9773-659f35b9f254 | Date Completed:
| checkpoint |  | 3.4 Concrete Pour
| note | 6c92a2ab-c7b6-4294-b6e0-f8309128fe75 | REFERENCE: Temp Works IFC Drawings
| note | f764b58f-3149-4738-9fbc-83688326f0e4 | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
| note | b1fdd9c8-c737-4b22-b769-c11c4dabf064 | METHOD: Visual
| note | 0ae4194b-7f0f-4def-a375-bce02ce50813 | FREQUENCY: Each Lot
| note | b2e5abee-20c3-48f9-a770-747dc842f2dd | CATEGORY: IP
| note | 18e22a2d-3240-42c4-a845-457eeb88f4c7 | RESPONSIBILITY: SE/Site Supervisor
| note | e39e6e78-bd57-4ce2-a28b-9741df7d9818 | VERIFYING DOCUMENTS: This ITP
| textbox | 24c5b6f2-c57e-4a6d-a35f-23a4df0e1c25 | Date Completed:
| checkpoint |  | 3.5 Concrete Testing
| note | dc9c4825-5aa9-4ba3-be2e-8d611b48ed21 | REFERENCE: Temp Works IFC Drawings
| note | e1e485ca-6e81-441c-926a-4698e2c8ac82 | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16(b)
| note | bc84a65c-aee3-4f48-b62f-95c5cd00554b | METHOD: Document Review
| note | 64a3380d-ba9e-4cf7-809e-80c2faeda2f9 | FREQUENCY: Each Lot
| note | 3db565f9-7c66-4498-ad6a-57486ca4619c | CATEGORY: IP
| note | a7ce02e7-a464-4146-8123-474df77261f8 | RESPONSIBILITY: SE
| note | f0cdf9ae-b345-4977-a63a-5a704811fd1a | VERIFYING DOCUMENTS: Attach Concrete Strength Test Report
| textbox | 315bddc4-f118-4a45-ab14-979c124dda20 | Date Completed:
| checkpoint |  | 3.6 Concrete Curing
| note | 4e9dae25-5864-4a5a-9977-35922d7de8d6 | REFERENCE: Temp Works IFC Drawings
| note | 895e4ecd-6027-469e-97fa-e77a7ba027d0 | ACCEPTANCE CRITERIA: Curing Compound shall be applied post pour
| note | 4f012b66-6f64-4954-87ad-0e7162e8fd2b | METHOD: Visual
| note | 2f0f5736-90e7-464e-9531-662bdec0b601 | FREQUENCY: Each Lot
| note | e2138376-1d60-490f-bfd2-3b6065c9856c | CATEGORY: IP
| note | 4e14d88d-f43e-4a59-ac5c-f89af14aba2b | RESPONSIBILITY: SE/Site Supervisor
| note | 4d46f915-6a4f-4775-980b-2eed47f1f1f4 | VERIFYING DOCUMENTS: This ITP
| textbox | 1b74ca38-ab52-4c8f-81ed-68657a416e21 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 643d25ad-54fd-4ad4-ae43-b4a36aa4ecb2 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 81e78995-bdea-4abc-aebf-9606b8073e6b | Name:
| textbox | a6b8aa60-c027-49f2-892e-bab854d9ca2e | Position:
| textbox | abd694b8-043c-44f8-bfb1-eda3bd89d1d8 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-RSS Wall - Preliminaries Rev 2 | itp | ITP-CIV-RSS Wall - Preliminaries Rev 2 | f4d5a7a9-e549-42f7-937b-a6c65f16897c
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | f78fcbca-459d-4d43-8cd6-3f7ee44d8cfb | Document Title: ITP-CIV-RSS Wall - Preliminaries
| note | 0b8a5054-c100-456d-b772-29ed58965d79 | ITP Description: RSS Wall - Preliminaries
| note | f919dccf-5e41-443f-8cc2-da108b43fbc0 | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 94dda7aa-fa59-48ed-bc29-e2d65ab5f322 | Revision Number: 2
| note | 0203b26a-edaa-43ef-b301-9726143260a7 | Revision Date: 10/11/20
| note | 093f3716-7891-4963-b2d2-b0e35a7a873a | ITP created by: Khalid Kamel
| note | aeea6196-8c68-4fc4-8f58-bb6b55180a91 | ITP approved for use by: Josie Pavlou
| note | 280f79b1-07ec-4f77-9581-b61be6680ce5 | 1.1 VicRoads Section 682 Nov 18
| note | d9b736b6-02f2-429e-b7ed-cebf6f874536 | 1.2 VicRoads Section 204 Dec 15
| note | bdad7ed6-be8c-419a-b964-1db174c90b5c | 1.3 VicRoads Section 620 May 09
| note | 19adc325-69d7-44c2-9bf2-5495da09e2e1 | 1.4 Vic Roads Section 210 Nov 18
| section |  | Preliminaries
| checkpoint |  | 2.1 Supply - Select Fill
| note | 2e4518c2-c4ed-4bd9-8519-b595eb3ec27b | REFERENCE: IFC Drawings
| note | 1d490a14-d234-4b4f-9898-ef86da1fbd70 | Section 682.14
| note | 29c24ece-4276-4df1-b90e-e661ebc0a124 | RMS R57
| note | 1a8a32c1-39c9-4edf-b25e-39ca01056a9f | ACCEPTANCE CRITERIA: Must be a granular material, free from organic matter and other deleterious material.
| note | aaf48221-9058-4ee3-a872-37f4b27c18b6 | Unit Weight: 20-24 kN/m3
| note | 3ff1ec1c-8abf-4f41-a996-f92e4644bcb7 | Internal Friction Angle = 36°
| note | e776efd9-ef6c-4fe4-a963-31b7013bd761 | Cohesion = 0kPa
| note | eaac5001-7a58-48bc-af99-c9b6605553f1 | Liquid Limit: ≤ 30%
| note | 33952ed6-74c1-4455-b43d-aa5ee01a2c20 | Plasticity Index: ≤12%
| note | 4c7261fa-cdd7-4ca8-b9a9-31b4d99b318b | Coefficient of Uniformity: ≥5
| note | 6d129053-bb21-423e-8ba3-7688e7dd7c35 | pH: 5-10
| note | 1ac9958c-a2ec-44e3-99ca-3b63dd9c23bd | Resistivity: > 1000 ohm-cm
| note | aa120e6f-f44a-4409-9bbb-04a8833d598a | Chlorides: <200 mg/kg
| note | 8611ef67-a07d-4075-b795-a0393e4bfbb6 | Sulphates: <200 mg/kg
| note | 60171dae-f04d-455e-bf3a-74b2d9cfffc8 | Organic Content: 0%
| note | b157910d-7f86-460d-991e-5297e8f75eb3 | Grading:
| note | 01468386-58cc-4087-ada1-8a3391e73d6f | 150mm AS Sieve: 100% Passing
| note | 7cec9506-793a-4129-83d4-6efe46728bc7 | 37.5mm AS Sieve: 60-100% Passing
| note | 6b0108f3-27da-4f96-b4b1-e76e347f15ba | 9.5mm AS Sieve: 25-100% Passing
| note | f48f6ccb-6b37-437a-bf9b-6e7a5593a8dd | 2.36mm AS Sieve: 15-100% Passing
| note | e23d9f54-31eb-4f08-9afd-b1c71fcad228 | 0.6mm AS Sieve: 10-100% Passing
| note | de266135-11bf-42bf-885c-5ba3797f9e03 | 0.075mm AS Sieve: 0-15% Passing
| note | 2ad1b50c-e07d-486c-bf88-8bc154a7234d | METHOD: Document Review
| note | 497b60b2-9afb-40fb-99a7-f35156b5c476 | FREQUENCY: Once, prior to the commencement of works
| note | 6834a89c-6e14-4d32-9c75-ff212aefb093 | CATEGORY: HP*
| note | 40847fc2-5052-411b-b3c6-4b9f2fccf2d7 | RESPONSIBILITY: PE
| note | cfeb545e-4f86-45ab-8cb5-1be96b28eff7 | VERIFYING DOCUMENTS: This ITP
| textbox | 961b4fd3-920c-4f3e-95cf-9e800f32a927 | Date Completed:
| checkpoint |  | 2.2 Supply - Concrete
| note | 1853bb57-85ad-4400-b638-42c115017532 | REFERENCE: IFC Drawings
| note | 69d42090-38ca-4ebb-a3db-3dbac31bf1e7 | ACCEPTANCE CRITERIA: Concrete for the Levelling Pad and Strip Footing shall be 25 MPa VR
| note | 52416b7e-0aff-49c8-ae80-c7e4d80d00a7 | Insert TeamBinder material approval No.
| note | bf6f4eb9-78ef-4a19-bcf3-bfa71423869c | METHOD: Document Review
| note | aee32c17-9b64-45e0-b85d-2ce477fd8f3f | FREQUENCY: Once, prior to the commencement of works
| note | 93791fb5-b882-4487-bb14-6833c81e57cf | CATEGORY: HP*
| note | 0fda5a96-f0e5-4f05-b635-314d45c5049f | RESPONSIBILITY: PE
| note | 9964fc2a-869b-43f1-939f-aa252de5531c | VERIFYING DOCUMENTS: This ITP
| textbox | e9623495-e235-4fb6-89ff-4b3a0c8aa7f9 | Date Completed:
| checkpoint |  | 2.3 Supply & Storage - Precast Panel
| note | 14db29b7-5310-484b-8387-e864570aa325 | REFERENCE: IFC Drawings
| note | 20845609-c527-4643-a683-3de879aef41d | Section 682.13
| note | 990af00a-15aa-47eb-b3a7-b969a6595f74 | Section 620.08
| note | 2e4d8a93-751a-4fc0-acfe-6ebf5445e733 | ACCEPTANCE CRITERIA: Precast panels are as per drawings. Have not been damaged during transport and/or unloading on site. Have achieved the 28 day strength and is more than 7 days after casting. Panels must be stored in a location that prevents damage or discolouration and supported on firm blocks. Panels to be stored as per manufactures guidelines and section 620.
| note | 2867b2f5-18b7-43d9-bb70-f0d89c21cc3c | Insert Teambinder Approval Number
| note | bc2bd0aa-dbfd-49f7-a9f8-725c1d475e3b | METHOD: Document Review
| note | 3df262cb-93e0-41c4-9aab-fcdde69c0eba | FREQUENCY: Each Delivery
| note | 5ffcb8df-dd33-4fa2-bac6-20fc11d1537e | CATEGORY: IP
| note | 53154d05-7150-4016-827f-26e76ecff1fc | RESPONSIBILITY: SE
| note | c7fd6a06-9b10-4869-a70f-f005ad8d1dc6 | VERIFYING DOCUMENTS: Attach Delivery Dockets. Manufacturer's Documentation to be uploaded to TeamBinder
| textbox | 622778b6-0b96-4cec-94e7-8bc2e18738aa | Date Completed:
| checkpoint |  | 2.4 Supply - Joints Fillers (if applicable), Geotextile, Connections & Straps
| note | ea0956c4-8ce9-4a33-9886-4406d81221fc | REFERENCE: IFC Drawings
| note | baf99ee2-3bef-4f74-ab0b-c0a207f1d3c0 | Section 682.08
| note | bb3bf9f6-cce9-4206-9ee8-b4097c506c23 | Section 682.12
| note | 77906e7d-b69d-4b32-af99-11cc6ed45b92 | Section 210.02
| note | cb61d30d-9501-4234-b45f-7b6cd2ea2806 | ACCEPTANCE CRITERIA: Steel straps shall have a thickness of 5 mm.
| note | d0b62083-ef27-48e6-bdf7-1b911f63903f | All steel components including couplers shall be galvanized in accordance with the Australian Standard for Hot-dip galvanized (zinc) coatings and material certificate to be submitted.
| note | d83c9bec-e54b-40e2-9bc2-34c1c0eb85bc | Geotextile to be WLPNWGEO1W530N. Geotextiles are kept clean and undamaged and stored away from direct sunlight until covered.
| note | 995dcd56-4d8a-4d47-a4f4-cf919a2a0b85 | METHOD: Document Review
| note | 99e323ad-c497-45f9-9bae-47d497ff36b7 | FREQUENCY: Each Delivery
| note | cf72ce82-188c-41b5-9240-96f27b0f5364 | CATEGORY: IP
| note | 646342a4-72c2-473c-8038-47f941191a97 | RESPONSIBILITY: SE
| note | 15a92a54-294e-410d-a462-bc9445447716 | VERIFYING DOCUMENTS: Attach Delivery Dockets. Manufacturer's Documentation to be uploaded to TeamBinder
| textbox | 7f7b3beb-dba0-4ba1-ba2d-fdd3298d3b01 | Date Completed:
| checkpoint |  | 2.5 Geotechnical Investigation
| note | 58180316-13ef-490f-9201-ea0bb9a138ee | REFERENCE: IFC Drawings
| note | 08777b4d-f9fa-4695-8c29-2b0151b8d694 | ACCEPTANCE CRITERIA: The founding material beneath the reinforced fill zone shall be inspected on site by a qualified geotechnical engineer to ensure that the soil conditions meet the assumed material properties.
| note | 7344f9a3-38c7-48e6-9983-67a97a6c5f87 | Assumed material Properties:
| note | 402a0d01-c85e-442b-8690-43e3106dbb44 | Stiff Clay or better.
| note | cb30e0e8-7e07-471b-a0fe-2832c0011881 | Unit Weight = 18kN/m3
| note | 8b35d672-2e78-4c97-8c13-fe3ed8ea40f5 | Effective Friction Angle = 28°
| note | 5b7a45ab-e135-462a-8284-d010df8c9cbf | Effective Cohesion = 10kPA
| note | 48b2be7c-7e68-4b5c-be0f-48667e5b258a | Wall Height 0 - 7.5m: Undrained Cohesion = 80kPa
| note | c4996b35-002f-4a42-9d7c-93f51deb0be2 | Wall Height 7.5m - 9m: Undrained Cohesion = 100kPa
| note | ad76f523-6c70-4c36-8528-f689455d979e | METHOD: Document Review
| note | 2520791b-deed-412f-adf5-40162dbe7f79 | FREQUENCY: Once, prior to the commencement of works
| note | 56aacdb1-db84-458f-9d56-ff0100e79f35 | CATEGORY: HP*
| note | 3586aae1-5e0e-4250-bc04-82d3d9c07838 | RESPONSIBILITY: PE
| note | 0d56c609-46f2-481d-84e3-2517c6ebdcf6 | VERIFYING DOCUMENTS: Attach Geotech Report
| textbox | 956f9113-6698-4e08-a3c5-8c1487d606fb | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | a5c676a3-d7f8-4d0a-a238-79836ec71979 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 14530fde-c4a1-4c76-a66e-71a7e28730ca | Name:
| textbox | 7940fa02-1c00-4770-9275-234f888dd68e | Position:
| textbox | 01076f03-7e54-4368-8c78-3b259927af7d | Date Completed:
| signoff |  | Sign ITP
| checklist |  | ITP-CIV-Traffic Signals - Commission (Supply and Install) Rev 1 | itp | ITP-CIV-Traffic Signals - Commission (Supply and Install) Rev 0 | f8c9357e-a029-446b-9082-9b89280aeddd
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 0214f3d4-2827-5bcf-af2a-2ea891809da9 | Document Title: ITP-CIV Traffic Signals - Commission (Supply and Install)
| note | ac93a5ae-7458-5533-ab74-f9b4f167054b | ITP Description: Traffic Signals - Commission (Supply and Install)
| note | 09d28090-177f-5582-8c23-a7485cb0c0ee | Discipline (e.g. CIV/STR/RAIL): CIV
| note | 920b08cb-7dac-56b3-93da-bd9f215e766c | Revision Number: 1
| note | 657d0f39-4468-5d0e-99b0-02fd7c9272bd | Revision Date: 15/02/22
| note | 235725d1-a9a5-5997-a8d8-fee45fe58413 | ITP created by: Saaf El-Zubaidi
| note | f7bd6ba5-b19b-59d9-897d-d338596b237c | ITP approved for use by: Josie Pavlou
| note | f1ee3272-9779-59ae-b1a8-5985f3db131c | 1.1 VicRoads Section 730 October 2013
| note | 59496921-442c-54bc-95a4-50c9280c05f7 | 1.2 AS3000
| section |  | Signalling Electrical System
| checkpoint |  | 2.1 Point of Supply
| note | aafe9d58-a62c-520c-a53d-7bea7564348a | REFERENCE: Section 730.14 (a)
| note | 3762c98c-2693-586e-aca4-3d2bbb9a7d0a | SD TC-1207
| note | d60aeac0-d3ef-5905-ad44-d99ace0ce27c | ACCEPTANCE CRITERIA: The Contractor shall arrange for the installation of the point of supply with the local power distribution company, at the location approved at the pre-installation meeting
| note | 8bc5c25a-eb6f-5725-b92f-dfc83ccdafd2 | The point of supply shall be installed in accordance with SD TC-1206 and arranged with the local power distribution company to meet the specific requirements.
| note | a13b59b1-4815-56db-bed9-3dfe25b3f01c | METHOD: Review
| note | d4a1f2d6-c3a4-50e8-8abc-aaf683ce76c0 | FREQUENCY: Per item
| note | cfcb11a5-9700-5c47-97fd-06a37231d87b | CATEGORY: IP
| note | ae5ff647-8aa6-59a9-a9e2-d3b33d384326 | RESPONSIBILITY: SE/Supervisor
| note | 834fcc8c-8eb7-5a83-9a77-1bd6cdffda18 | VERIFYING DOCUMENTS: This ITP
| textbox | ef39ff33-9f26-59d9-a0ad-9658d6469f58 | Date Completed:
| checkpoint |  | 2.2 Communications Line
| note | 6788ec04-92f9-5cf9-973d-37e985f69fbb | REFERENCE: Section 730.14 (b)
| note | bf642180-38b8-5ab3-b207-ea75614f6f8e | SD TC-1207
| note | d11c048e-823c-530c-ab15-9d1f78fb018d | ACCEPTANCE CRITERIA: A communications conduit along with a two pair telecommunications cable is to be installed from the signal controller to the nearest suitable communication supplier's pit as per SD TC-1207
| note | 4db1d7cf-c7ae-5db4-b0e3-bdd367c4f6e8 | METHOD: Visual
| note | 0dcd85de-8c45-5c47-b0fe-b360a92d88d2 | FREQUENCY: Per item
| note | 866412f0-94ef-59fd-83bc-4d6fe4373914 | CATEGORY: IP
| note | 623505d7-b7b9-5532-96e8-2016e861bb65 | RESPONSIBILITY: SE/Supervisor
| note | 756bbb85-7cdc-5c80-ad71-e579010e880c | VERIFYING DOCUMENTS: This ITP
| textbox | df88fd56-e3f2-56f5-9095-9027263e0531 | Date Completed:
| checkpoint |  | 2.3 Cable Installation
| note | f5baff6d-abb1-5dfa-81d7-73ceddb2cb77 | REFERENCE: Section 730.14 (c)
| note | 4d5423ca-1431-525c-8551-14321576b214 | ACCEPTANCE CRITERIA: Site cabling is to be completed in accordance with Section 730.14 (c), ensuring all cables are installed with no damage to sheathing and insulation, restrained at the point of termination (top of pedestal and MA/JUP access points) to ensure minimal stress on terminations, as well as sufficient cable provided to reach 1.5m above the signal controller base
| note | e51d22c1-c825-543b-98cb-ad00ac41e6e2 | METHOD: Visual
| note | 10318ae4-170a-5a8e-8f40-bb9f5c0b4ef8 | FREQUENCY: Per cable
| note | d5a99e9b-dc80-5d99-bb50-d93aa1f2a905 | CATEGORY: IP
| note | 1567d0de-5a5e-5b58-b3a0-0b11a128caf7 | RESPONSIBILITY: SE/Supervisor
| note | ba903a0d-19d2-56bc-98d4-58cbe8202ca8 | VERIFYING DOCUMENTS: This ITP
| textbox | 9a8797c9-395d-56ab-9961-ee007529f735 | Date Completed:
| checkpoint |  | 2.4 Cable Sizes and Wiring
| note | 25ad3d6f-8741-5e93-88a2-137a6198d8e0 | REFERENCE: Section 730.14 (d)
| note | 5bdb8f94-1975-5dc6-9667-c1ef30a84e2a | ACCEPTANCE CRITERIA: 51 core cable is to be used at intersection traffic signals and its sequential assemblies. 29 (dual carriageway) or 19 (single carriageway) core cable is to be used at pedestrian operated signals and its sequential assemblies
| note | 560e233b-c23d-5b98-ad00-9a764564edff | METHOD: Visual
| note | 6a667c62-85ea-5244-b095-b51f0b5e9910 | FREQUENCY: Per cable
| note | a7cd74ff-fa6f-50f1-965f-e9837414e14c | CATEGORY: IP
| note | bab0d5ec-6fb9-576d-8d31-fc74cef34ba0 | RESPONSIBILITY: SE/Supervisor
| note | 82fc68a3-7845-5955-b140-a91a304cce56 | VERIFYING DOCUMENTS: This ITP
| textbox | 664532d5-a91a-5e8d-b929-e79e8a0ab34c | Date Completed:
| checkpoint |  | 2.5 Pedestrian push button terminations
| note | 99829811-d082-5870-8fc8-d9af1a06224c | REFERENCE: Section 730.14 (e)
| note | 9fff3a0f-17e6-53a4-a25e-c705f3d5227c | Table 730.141
| note | 2d1609be-2722-5f4d-aea7-c9c4efd9eafb | ACCEPTANCE CRITERIA: Pedestrian push button detectors are to be connected by 5 core cable and terminated at the required locations.
| note | 3699c264-cb06-5a55-9091-b60c58ac70e3 | METHOD: Visual
| note | 04c04f8b-0626-599d-bec1-791b2af387f2 | FREQUENCY: Per cable
| note | b6a9baf2-ad89-5394-acb7-b1a83e4aba4b | CATEGORY: IP
| note | 64787072-d01e-56c5-9a6d-6d12a3fa0f33 | RESPONSIBILITY: SE/Supervisor
| note | 3dd5b3af-0c7f-54a8-ae81-a5f2b97af47e | VERIFYING DOCUMENTS: This ITP
| textbox | db95eff0-ab58-51e7-93a4-3c5522517c35 | Date Completed:
| checkpoint |  | 2.6 Connecting of traffic signal controller
| note | 5a0a5762-fdf6-58e9-b02e-f7686b513ac4 | REFERENCE: Section 730.14 (f)
| note | 469804fb-eecb-5eb6-8e6c-bb46e6b9e421 | ACCEPTANCE CRITERIA: Contractor shall install a 3 core supply cable in a 50mm conduit between the supply point and signal controller base. 1.5m of supply cable shall be coiled in the pit closest to the controller base.
| note | 1cebfdd7-70a1-5335-9a19-2c8b2b082026 | METHOD: Visual
| note | 4f09263f-3152-5921-89ab-b571e5b6e581 | FREQUENCY: Per cable
| note | d7971505-3ba8-5099-a95a-62181c9c305c | CATEGORY: IP
| note | 0918cd46-5c5e-5232-9d81-37ca09f7f14b | RESPONSIBILITY: SE/Supervisor
| note | 7525191d-cdb1-5892-9b8d-74620ae802af | VERIFYING DOCUMENTS: This ITP
| textbox | 770284a9-6296-5b95-a2e6-9208d1cca8bd | Date Completed:
| checkpoint |  | 2.7 Testing of Electrical Works
| note | e626ed36-63f2-5a3c-bfd4-61a6129c0e48 | REFERENCE: Section 730.14 (l)
| note | be4cad1b-2b73-5f03-afff-f2bf5c763b2e | AS3000 Cl 8.3.3
| note | aa58ae99-852f-5b42-bd93-08d4bc524830 | ACCEPTANCE CRITERIA: The following tests are to be carried out prior to the installation of lanterns and hardware:
| note | 8f337051-b509-5395-abb7-673213c2f862 | continuity of all active, neutral and ELV conductors as well as earthing system.
| note | 2772ece8-19d9-567f-9def-cab35f617d3d | Attach: Electrical Test Report
| note | f058d0fb-8eac-5444-b4b2-ccc8345223f7 | Following the installation of all lanterns and hardware, the Contractor shall carry out a flash test.
| note | d8970d8a-72fd-5290-bca3-c408815665b9 | METHOD: Records
| note | 3315135b-03a3-5d7f-b53b-4a08c9cd7751 | FREQUENCY: Per installation
| note | 4438d811-28b6-5826-b881-b8dc9006b290 | CATEGORY: HP*
| note | a783cd67-09bf-526e-a854-1fcfd227910b | RESPONSIBILITY: SE/Supervisor
| note | ee915c51-2ea8-5885-be9b-64f2eb2625dc | VERIFYING DOCUMENTS: Electrical Test Report
| textbox | e13b1977-69d3-5158-a34a-ff1c0666eef1 | Date Completed:
| checkpoint |  | 3.1 Cutting of detector loops
| note | 6df0929e-cc24-5d86-a421-863045f41c6a | REFERENCE: Section 730.14 (j)
| note | cd56cb40-1719-5d22-8459-8f9e345f1385 | VicRoads TCS 054
| note | e5520e98-1784-547e-9de4-eb2d7b86cdfa | ACCEPTANCE CRITERIA: Detector loops are to be cut as per the locations shown on the design drawings to the TCS 054 specification.
| note | 71c15f45-7c31-53ac-b150-58bbf1c4cfa8 | METHOD: Visual
| note | cf3f8a63-3e7f-5c05-9c16-95e64d8fae51 | FREQUENCY: Per loop
| note | 99805bd2-2a38-5322-b1b8-227cdeeef449 | CATEGORY: IP
| note | c93aa88a-4c91-5aa3-9bf2-806c405da270 | RESPONSIBILITY: SE/Supervisor
| note | 1fb0b59a-89ed-5dba-ab36-a882ef9a3477 | VERIFYING DOCUMENTS: This ITP
| textbox | 8554d6e8-31fc-503b-975c-bb05e2fb9375 | Date Completed:
| checkpoint |  | 3.2 Installation of detector feeder cables
| note | ea50bfc0-bb14-5a0e-b40f-e7f510767074 | REFERENCE: Section 730.14 (g)
| note | 36e2f44b-fc55-52b3-8c1b-bd609a5692eb | SD TC-1300
| note | a2d13af8-0aec-58a4-88e8-f688d7e2b15c | ACCEPTANCE CRITERIA: Detector feeder cables are to be installed to connect detector loops to the traffic signal controller. Installation is as follows:
| note | 6af2a354-142f-5d5e-a97b-e68f66b6a51c | Install 1 cable per loop and each cable pair shall be clearly and durably marked at both ends to enable positive identification
| note | ee790f6d-75e1-5115-a2ed-18154f8d77db | Connection of the detector loop cables to the detector feeder cables by soldering
| note | 6f566a73-febc-5bec-9cee-70c5c0264cee | 4 wires for each loop (as per SD TC-1300) shall be tied together in a knot close to the conduit end
| note | c382dd07-fe97-5d52-8c14-2c63ba6ac5e1 | Terminations (joined or unjoined) shall be separately insulated and sealed against the ingress of moisture with heat shrink
| note | d54bca1b-be49-581e-af7f-15edf07343e5 | Detector cables to have sufficient length to allow 1.5m to be coiled in the pit and 1.5m to reach the top of the controller base
| note | 1ffd0e0b-bce3-5fe0-9dfc-d985120a7a4a | Cable diagram shall be provided once complete and visible to the controller installation contractor detailing the loop cable/feeder cable connections.
| note | 8b09e863-64c6-555a-a8c2-3332e5db301f | METHOD: Visual
| note | 4388bd16-b06f-5f07-a034-9f33a0d01dd2 | FREQUENCY: Per loop
| note | 9a58f6dc-6055-56e9-8879-48fbb139e8df | CATEGORY: IP
| note | f4a512cf-aee5-579d-8add-754c4bcadc47 | RESPONSIBILITY: SE/Supervisor
| note | 159697af-b646-595a-8293-5b72573dd61b | VERIFYING DOCUMENTS: Sign ITP
| textbox | fc4aafaa-700f-5ca1-a0ee-ffff3eb7b6f2 | Date Completed:
| checkpoint |  | 3.3 Cabling of Large Sites
| note | 3d21f261-2147-5b9a-bb5d-a93fcc2bfbe7 | REFERENCE: Section 730.14 (i)
| note | 171fdd3f-4a62-5a99-b851-b5d5ac3f3f59 | ACCEPTANCE CRITERIA: For large signal installations where the standard allocation of cores as specified in SD TC-1204 cannot readily be adopted, MRPA shall draw up a proposed cabling scheme for approval.
| note | 43b8a963-98fd-5633-955d-a42e0f42b6e3 | Attach: Proposed Cabling Scheme Checklist
| note | 399ad5c1-56d9-5c93-8d3e-45c04c9d65e7 | METHOD: Records
| note | e52e6715-e6dc-5420-8ca4-61f1e2c58f0b | FREQUENCY: Per installation
| note | 0f41e5db-e08a-5ebd-9fef-4cd0b6a966f4 | CATEGORY: HP*
| note | de3ee58c-fb64-51b4-a8e5-8a61d75d05b9 | RESPONSIBILITY: SE/PE, NA
| note | 0a6cb0a1-ba14-5fcf-b84c-e14c1df06202 | VERIFYING DOCUMENTS: Attach Proposed Cabling Scheme Checklist
| textbox | 454cda13-1c05-5f1a-88a2-971c624f5096 | Date Completed:
| section |  | Pre-Commissioning
| checkpoint |  | 4.1 Pre-Commissioning Site Inspection
| note | 7a7a8ceb-f429-5fc3-9c45-2bd8954ce00c | REFERENCE: Section 730.16 (a)
| note | 8ae7ff9b-3c35-53ac-8f19-9d74af7bb4a2 | ACCEPTANCE CRITERIA: Inspection to be carried out between the relevant parties upon completion of the installation works.
| note | 7d34fb61-228d-5947-9543-1e4f35a11055 | The Contractor is to notify NA and VR of the inspection.
| note | 98f50623-e38c-52c2-b06d-928605d7d7b1 | METHOD: Records
| note | 2e8d1380-14d4-5a6e-8596-af8656debd34 | FREQUENCY: Per installation
| note | 76ec9506-964b-5b38-8d40-dfe0f25bbeb8 | CATEGORY: IP
| note | 003e68c1-17bf-5d33-8eeb-d47dd60ed55f | RESPONSIBILITY: P/E, NA, Supervisor, VR
| note | 61372d45-d35c-5da8-ac0c-034253c1148e | VERIFYING DOCUMENTS: Attach Pre-Commissioning Installation Report
| textbox | a749917a-1574-5415-918d-e62131cb8e97 | Date Completed:
| checkpoint |  | 4.2 Provision of power
| note | baebe56f-198a-59c2-af9a-582980bea38f | REFERENCE: Section 730.16 (b)
| note | b4c99bde-9814-5fb5-ad44-5523956511ac | ACCEPTANCE CRITERIA: Obtain connection of mains supply by submitting all necessary paperwork and payment of fees.
| note | 7cb62d4d-2515-579c-a28a-8c717d048374 | METHOD: Records
| note | ff13bb42-0b31-5c10-af23-b04d9af754c2 | FREQUENCY: Per installation
| note | 57639f09-66b2-5dea-9b80-f8bbc4d235fb | CATEGORY: IP
| note | 22af9a67-3be4-536f-b07f-050a595fdeaa | RESPONSIBILITY: PE, Supervisor
| note | 71785543-f16b-51fd-9ab9-5ee0a84bc4fc | VERIFYING DOCUMENTS: Sign ITP
| textbox | 19cfbbb9-0846-58a5-8901-bc3c2958caa6 | Date Completed:
| checkpoint |  | 4.3 Traffic Controller Installation
| note | 610a457e-1a69-5200-ba43-584fb358b425 | REFERENCE: Section 730.16 (c)
| note | 39f7df4f-57a2-5dc6-8f9b-f82714fa0c4e | ACCEPTANCE CRITERIA: Contractor to notify VR when the site is completed, tested and ready for the traffic signal controller to be installed.
| note | c69b0c99-5aa3-5be3-a079-1734350a959e | Traffic signal controller to be installed by controller supplier or authorised representative.
| note | 1c6ae6f8-8ccb-5f70-8a36-9e68633a0203 | Contractor shall arrange issuing the Certificate of Electrical Safety and the necessary paperwork to obtain connection.
| note | e939d728-ef4c-5ee6-8956-bc807d48792b | METHOD: Records
| note | d6971001-6575-5064-8b69-d13e820b316d | FREQUENCY: Per installation
| note | 51b9c423-b25a-59d0-a63f-fdc0bbcc4070 | CATEGORY: IP
| note | bc286cf2-cf8e-5780-b632-999bc1e38747 | RESPONSIBILITY: PE, Supervisor
| note | 6a09f44f-5350-577b-adbe-accc00a47a0b | VERIFYING DOCUMENTS: Attached Certificate of Electrical Safety
| textbox | f1d41df3-061b-540f-bf9d-8d0f60141e3a | Date Completed:
| section |  | Completion of Site Works and Commissioning
| checkpoint |  | 5.1 Switch-On
| note | 64124499-6e47-59ed-8e47-8a1b3507d229 | REFERENCE: Section 730.17 (a)
| note | 35cebf58-7b1c-576a-814b-cf8b4d75af34 | ACCEPTANCE CRITERIA: Prior to switching the signals on, a 'flash test' of the installation shall be carried out to ensure that each lantern is connected to the correct cable core. The flash test shall be witnessed by the Nominated Authority and VR and confirmed as acceptable.
| note | 8827d29a-6f1a-512f-b99e-2ecaa7af0ee0 | The controller supplier is to record the relevant details required for the Electrical Test Report.
| note | 7a3e8802-0d18-5b97-b9e5-616b546aa472 | METHOD: Review
| note | 7f789882-cbd9-5275-b578-e47fe26a7936 | FREQUENCY: Per lantern
| note | 120882b4-c8aa-52b9-96f1-73d6be475204 | CATEGORY: HP*
| note | 2c641a35-c0a0-5fd4-91fa-53702ebd83ac | RESPONSIBILITY: PE, NA, VR, Supervisor
| note | 2ddfaec7-f701-5eb6-83e3-d19cfee31334 | VERIFYING DOCUMENTS: Attach Electrical Test Report
| textbox | 11d2d2b7-3718-5bf9-a1e7-0e69de606bb6 | Date Completed:
| checkpoint |  | 5.2 Removal of redundant hardware
| note | 3b4e93db-4446-55ec-9374-d0ca1f2e6797 | REFERENCE: Section 730.17 (b)
| note | f224a6f3-acc4-5ab8-8226-9ab41262ff07 | ACCEPTANCE CRITERIA: All redundant components of hardware and equipment shall be removed unless specified on the design drawings.
| note | c5b412b9-901b-5a77-91b8-ad6c3b352515 | METHOD: Visual
| note | 6c26db0a-5ece-58dc-b149-5873de054b58 | FREQUENCY: Per installation
| note | 2fa95afe-75eb-54cd-a082-b9ef6a9eb510 | CATEGORY: IP
| note | 5ae7f1b2-d57a-5aec-bd24-cbc024da2c1c | RESPONSIBILITY: SE/Supervisor
| textbox | 4fdc4fc6-4da0-5aa0-bd48-af1915848c25 | Date Completed:
| section |  | Post-construction / Post-installation Activities
| checkpoint |  | 6.1 Survey as-built
| note | eae91481-480e-5610-888f-49df5755e715 | REFERENCE: IFC Drawings
| note | ae2cfa8c-19d2-55ba-99f4-9b7efa8a34ad | ACCEPTANCE CRITERIA: Survey to As Built Traffic Signalling works.
| note | c66e5086-daec-5c59-98ff-dc9f866f8aa7 | As Constructed Traffic Signal plan to be submitted to Vic Roads.
| note | d5d237f2-e74b-5df2-9ee3-7e22fbb3005f | METHOD: Document Review
| note | 7f7efa2f-9524-5ef3-b6a1-4625beb9bf6d | FREQUENCY: Each element
| note | 700fa354-b308-5d29-a638-94cec2e4f09b | CATEGORY: IP
| note | 140ef2f9-683e-5d83-b8fa-34ecf7bea3d6 | RESPONSIBILITY: SE/Surveyor
| note | cbf9aea9-1ad0-535b-9985-5f7fb3353338 | VERIFYING DOCUMENTS: Attach As Constructed Traffic Signal plan
| textbox | 1ae8cd39-86cc-5ea6-8e48-1d2b4ae1d0a3 | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | 970c35c7-5f63-5b28-a292-ccb6b28b2967 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 96c13f39-ba52-57d2-852d-56944473a9db | Name:
| textbox | ac541449-3ef1-5bb3-b9ed-91aeec838ba0 | Position:
| textbox | a75d14a9-c148-5dfd-90a1-0883763e3cb4 | Date Completed:
| signoff |  | Sign ITP
| checklist |  | Stormwater - Pit Installation Rev0.0 | itp | Stormwater - Pit Installation Rev0.0 | fde6eeb4-81cd-4a2a-9bdb-59958e107277
| checkpoint-no-value |  | Document Reference
| note | 4f8b36f1-28cc-4d8d-9ae5-8b35896477e9 | VicRoads Standard Section 701 (April 2019)
| note | 13be4730-78f2-483d-bb02-0e753d67b7f3 | VicRoads Standard Section 705 (October 2018)
| note | a4966234-94ca-468a-9d21-724dd142a498 | Revision of ITP template: Stormwater Drainage_00
| note | d09919b6-f06b-43a1-ad21-a375a617704e | ITP template approved by: Michelle Edgar, October 2019
| checkpoint-no-value |  | 2.1 - Pit Details
| dropdown | 60cc15e3-e920-4d98-8826-f9b240f419c1 | Design detail: | Modify existing pit,New Pit and Line,New pit on existing line
| dropdown | 273ed96d-a274-4f41-a7c3-0c665efa5472 | Pit Supplier: | Aus Pits,Cast in Place
DataPoint is missing 'select' values | dropdown | 66759763-96ae-4e7e-90cf-5a7582111971 | Pit Lid Type:
DataPoint is missing 'select' values | dropdown | dd726015-e7aa-4dfe-94bc-4d897718833f | Pit Lid Class:
| dropdown | 6884a8f3-1161-4466-bcd3-891e57a1b7d9 | Pit Type: | Headwall,Junction Pit,Side Entry Pit
| textbox | 9c68e6ce-eec0-4507-b230-f66aff13e47d | Product ID
| note | 9ef132ac-f9fc-41fb-a82a-6570ea7ed07b | Record Line Number from IFC Draiwngs (suggest to use in Lot title)
| note | d284829a-7a1e-4ed0-a195-68d5c57db067 | - - - - - - - - -
| note | f172cc56-3301-44cb-9e5d-35fdd2f5b23a | References - 705.05, 705.09
| checkpoint |  | 2.2 - Excavation
| note | 77294ba3-00cb-41a4-894e-0e1247b0d4a2 | Excavation to design depth. Foundation is satisfactory.
| note | 333d5675-e1e9-42e3-820d-d334076faa2f | For precast pits clearance provided to each face of excavation is not less than 400mm
| note | 13b78715-daa8-4179-bab0-9a1a171e38f1 | Bedding for precast pits meet requirements of 701 and compacted to refusal. 80mm for clay and 150mm for rock foundation.
| note | 4512bec1-8946-4a41-bc8c-b3463f037448 | - - - - - - - - -
| note | 9a92a88f-09dc-4f4e-b027-80c55bdf4752 | References - 705.05
| note | 93949e53-6838-4310-a1df-8ab6de8975e6 | - - - - - - - - -
| note | ea8c838a-4ba8-464d-be5f-c07f2dcf6e0f | Verification Record - This signed ITP
| checkpoint |  | 2.3 - Placement of Pit
| note | a06565d8-8f64-46e4-8ef5-66e7916b376d | Survey pick-up to verify
| note | 4bcf84f3-03cb-4565-9cff-0a72ac9de9de | Offset pits to kerb +/- 20mm
| note | 3112fcac-e758-488b-a0ec-43b9996e445c | Plan location pits not adjacent to kerb +/- 100mm
| note | e0c91bc9-0e98-46f7-907a-ce273cce3251 | - - - - - - - - -
| note | 39e92d6b-fb32-4fa8-bb22-2829f19d176a | References - IFC Design, 701.09
| note | 246a0386-4f8e-4bf1-881a-ac9687baaa6a | - - - - - - - - -
| note | 3fcca405-e3bb-424b-9002-3a32a6d0e18c | Verification Record - Survey data included in CAD master file
| checkpoint |  | 2.4 - Pipe drainage connections and jointing
| note | dc9d7bea-ed31-4680-ba62-8c4c024c7fa2 | All stormwater connections to be neatly made. Where nessary, trim ends of drains and finish with cementitious mortar
| note | 42604336-90dc-40e1-97ed-b0a70fe79cd4 | Openings to be neatly saw cut to required size, not to exceed pipe diameter by 50mm
| note | 82cf33bc-443b-45bb-ba0f-5f081b0b029b | Reinforcement exposed by the cutting of holes shall be coated with epoxy.
| note | af49cf77-c93d-44d6-b48b-27d78e01fe1c | - - - - - - - - -
| note | e592e6fa-56de-4e60-806a-f666371fc818 | References - 705.1
| note | 98346a30-3a76-4336-870d-d92527b70fcf | - - - - - - - - -
| note | 02ec631a-fcea-430b-a885-ac4aeeb1612d | Verification Record - This signed ITP
| checkpoint |  | 2.5 - Shape pit floor
| note | aa633ba8-f16c-40bf-86a6-979967d899cd | Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
| note | 246561b1-7704-4ed1-8b2d-a7a99847e458 | - - - - - - - - -
| note | a562fcf8-6dda-4c09-8d55-935e88c4593f | References - 705.12 VR standard drawings
| note | d486994c-ee2e-4201-9f99-6efc52bd91cc | - - - - - - - - -
| note | fe20caa0-7641-41a2-92c9-032f8c61abd5 | Verification Record - Ths signed ITP
| checkpoint |  | 2.6 - Step Irons
| note | ededd44d-955a-4e3f-b0a0-25f24c9c810a | Requirement TBC.
| note | a5a557eb-ef82-49ae-8791-89fff34a37a7 | - - - - - - - - -
| note | fa7fcbda-16b0-463e-abd8-6ec96de8ab5f | References - 705.11 OR Advise from VicRoads operations team
| checkpoint |  | 2.7 - Fitting of covers
| note | 251f6faa-7520-49cf-8ea1-8482953b8e68 | Cast into top of pit or beddded on fresh mortar 5mm thick. 2 parts sand, one part cement and sufficient water.
| note | a972d80d-57e0-45d4-8b5f-5090393281ff | - - - - - - - - -
| note | d4145075-5370-4936-8bc0-77a4bbb47e48 | References - 705.16
| note | 46ac57f5-0a94-4d78-91cd-4172b7aa6a95 | - - - - - - - - -
| note | 28e4ed55-ab01-46f8-a90a-648edebfb483 | Verification Record - This Signed ITP
| checkpoint |  | 2.8 - Backfilling around drainage pits
| note | a01ba5d0-2c56-4a6f-8b6a-356510016a3d | Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment
| note | a5d200d8-87fb-49b6-ba03-1178b7120332 | - - - - - - - - -
| note | e24f8309-1d3d-4a9f-adf0-cd54d4efb987 | References - 705.17
| note | 598f7940-a861-4788-bf8b-91b3116b0508 | - - - - - - - - -
| note | 77c988b4-2ef9-4421-9143-b1f01d0fed30 | Verification Record - This signed ITP
| checklist |  | ITP-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation) Rev 1 | itp | ITP-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation) Rev 1 | ff8373f9-60e7-4553-b8f0-df5d8cf21823
| section |  | Referenced Documentation
| checkpoint-no-value |  | Referenced Documentation
| note | 8ede6b47-ffd8-4441-80e2-152b5650e782 | Document Title: ITP-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation)
| note | 87473659-9c5e-4384-a0b1-ed81c267404b | ITP Description: Precast Barriers, Parapets & Kerbs (Supply & Installation)
| note | 7fe17885-137b-4086-8a9e-36384d72a755 | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
| note | 9addf9f7-67eb-49eb-aa28-a63771b4a200 | Discipline (e.g. CIV/STR/RAIL: STR
| note | 0b9aead4-4496-466e-8baf-755b40b64d59 | Revision Number: 1
| note | eaf6be81-76d4-44fe-892e-db0b8015a56a | Revision Date: 44244
| note | a5cea546-35a9-41ac-990f-931f74aff013 | ITP created by: Mike Freeman
| note | 457d89f9-0c06-4544-9af5-726615f1c761 | ITP approved for use by: Mike Freeman
| note | 25beb783-335d-413b-97ff-15311742055d | 1.1 VicRoads Section 610 November 2018
| note | 56280ccb-7d4b-441b-af80-8263c7fc3af8 | 1.2 VicRoads Section 610 June 2019
| note | 30d05fa4-b47a-43d7-bddc-6367bd17c5af | 1.3 VicRoads Section 620 May 2009
| note | a329697f-fb9c-4558-be48-a5b3ea2c329d | 1.4 VicRoads Section 630 October 2013
| note | 7a1932bc-e218-4b5a-9d7f-bd59075f3a6c | 1.5 VicRoads Section 671 October 2013
| section |  | Preliminaries
| checkpoint |  | 2.1 Precast Elements
| note | fb487248-950e-493e-a9fa-1cd74e554cd4 | REFERENCE: IFC Drawings
| note | 05ffc3a8-0a3a-41cd-819d-ca3457c9bd4c | 610.46 (a), Table 610.463 (November 2018)
| note | a524b044-c51c-4d95-9dad-0521e7d9ae48 | 610.47 (a) Table 610.473, (March/June 2019)
| note | 6c7db008-b96d-4058-bf00-d426a343edc4 | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
| note | 8c34195d-17e4-4eff-b815-757395ac0c33 | i. Certificate of Compliance / Birth Certificate
| note | 1f971707-6515-4539-9c33-c796b535ef6d | ii. Compressive strength test results
| note | 2683f76b-d537-480f-8076-a20697d0f191 | iii. Precast Lifting Design
| note | 33783c4a-053e-44d8-bf97-e3b51e7a3907 | iv. Pre-pour check sheet / ITP
| note | 3eb68920-c5a9-4ec4-944d-e19dc0641a2d | v. Post-pour check sheet / ITP
| note | 6aecfa78-ab7e-49d9-8da8-7bad01be8a67 | vi. Covermeter check record
| note | ac8c560f-bc97-4255-9cc4-0d72f76d0de9 | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
| note | 29344d33-ad3a-44d4-8486-82842007c56c | Note: Different revisions of 610 have different clause numbers
| note | 4fcb6394-a40b-48c5-8580-2cabff7baf54 | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
| note | eff8f0e7-c171-4f5c-b753-7792d1af20c4 | METHOD: Document Review
| note | 328cd4a2-ed03-49b6-85b1-168f0efe98ee | FREQUENCY: Each element
| note | e65ce6f6-ecfb-47cf-b5ba-4bd6e5f08551 | CATEGORY: IP
| note | 990f99b1-3a49-4ab6-9666-718dd9454899 | RESPONSIBILITY: PE/SE/SPE
| note | 4b00e388-10b8-464b-97ab-59641e953d75 | VERIFYING DOCUMENTS: This ITP
| textbox | c12bb393-9946-4ac5-ad5d-7eb348c48281 | Date Completed:
| checkpoint |  | 2.2 Epoxy Adhesive
| note | c2c132d8-1f02-4360-8d44-922cdd7010c8 | REFERENCE: MRPA Quality Management Plan
| note | 90421646-8b4c-4b7c-b7b1-c9f10254dbe4 | ACCEPTANCE CRITERIA: Details of epoxy adhesive used to install steel bearings to bridge deck/foundation to be submitted for review to the Nominated Authority.
| textbox | 52f846a8-c746-438b-bd8b-59d5ed0a36a7 | Enter: Teambinder Material Approval number
| note | 8c1d0a6a-11a8-4de9-a27d-10c1bdc52329 | METHOD: Document Review
| note | 3e59daad-8c17-4339-ba5a-eb6963d0094e | FREQUENCY: Once, for each product
| note | c73c114a-9623-4c3f-afb9-486e84050646 | CATEGORY: IP
| note | 1eb19b9b-a947-4b5a-b743-4fb53bc8a3b7 | RESPONSIBILITY: Nominated Authority
| note | 10b1e8d9-18ea-4476-9610-abf5de894cda | VERIFYING DOCUMENTS: This ITP
| textbox | 1367eea9-981d-4599-9272-3bb53eac12d0 | Date Completed:
| checkpoint |  | 2.3 Joint Sealant
| note | 8156cbb9-c3b7-408a-bf06-e0ec12c37c96 | REFERENCE: MRPA Quality Management Plan
| note | d6f5be35-af67-4149-8d5e-38a4a90e3ce4 | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
| textbox | f2cb8bd6-5b12-4266-8520-3d549072d1fe | Enter: Teambinder Material Approval number
| note | 0fbcda0c-f25b-418f-8f86-782089fe292f | METHOD: Document Review
| note | 97f00367-72aa-4a3c-94c9-4ccd336c222b | FREQUENCY: Once, for each product
| note | 50e0608e-4ece-4be5-b777-cb7dda9683d0 | CATEGORY: IP
| note | 801391a7-1c68-40f4-85b4-e4e3fcfcc972 | RESPONSIBILITY: Nominated Authority
| note | 02e2f839-884c-4d6b-a6d2-8a08aca4572b | VERIFYING DOCUMENTS: This ITP
| textbox | 5db579a3-833e-4f5b-b98c-5d9370c61974 | Date Completed:
| checkpoint |  | 2.4 Bridge Deck / Foundation Compressive Strength
| note | 1758131e-eea1-484e-87ff-fd758b9b0df8 | REFERENCE: 671.03
| note | cd0b80db-736f-47d7-ae4a-92673f9ffb0f | ACCEPTANCE CRITERIA: Check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
| note | b71adb75-7c8c-42f7-9861-aca85782b406 | METHOD: Document Review
| note | bfb68e06-88e5-48e5-ba01-a0df845d72c8 | FREQUENCY: Each installation location
| note | 43c3db53-07fb-45e5-bcea-ad00cabd705f | CATEGORY: IP
| note | 4f9da36d-9f31-471c-8d18-5ea166ba7ed9 | RESPONSIBILITY: SE/PE/SPE
| note | 2dd18357-7481-464e-acea-b34fff96ce1f | VERIFYING DOCUMENTS: This ITP
| textbox | e02445cb-3f25-4d5e-9588-45b05b8830d0 | Date Completed:
| section |  | Pre-installation Activities
| checkpoint |  | 3.1 Survey Set-out of Precast Elements
| note | 84ecbcaf-d225-472a-b917-d781a6a9fcb8 | REFERENCE: IFC Drawings
| note | a6a62b89-961e-4815-b8cf-a907faa015fd | 610.46 (a), Table 610.462(November 2018)
| note | f815d1b7-bd3c-415e-b4ab-7c79183a581b | 610.47 (a), Table 610.472 (March/June 2019)
| note | fddf2862-4bb2-4618-9120-aeb0fa1dba61 | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
| note | fc9f177e-18ca-4cb1-ab9a-b1b5bacfc9e5 | Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
| note | 4af29c6a-ec4e-48c1-87a1-6c4832f22e0f | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
| note | 3049b3e1-5551-442e-b2d0-575e5ae4333e | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
| note | 5ff1a3d1-eae1-45ca-8e78-d3a65b9c3594 | METHOD: Measure , Visual
| note | 5712bb11-181e-402a-86a5-e39288f77ced | FREQUENCY: Each element
| note | d71e7e35-ec48-48c1-b71f-dc7a1a60fb95 | CATEGORY: IP
| note | 41f93565-518a-4abf-856f-027e64e8c2d7 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | f39c7137-313e-4456-a824-53a3b9bada1e | VERIFYING DOCUMENTS: This ITP
| textbox | 095f2235-f077-4ccf-b2c7-0bdb563667a4 | Date Completed:
| checkpoint |  | 3.2 Hold-down Bracket Levelling Bolt Bearing Plate Placement
| note | 4f0944e9-84ef-4205-8b89-d7357dc6d814 | REFERENCE: IFC Drawings
| note | 3eee0aeb-7c5c-4397-a437-25fb9063d8c7 | Product TDS
| note | 35751ca0-29f3-4547-8422-cfef454f6a72 | ACCEPTANCE CRITERIA: Mix the epoxy adhesive in accordance with the product TDS and apply to the back face of the steel bearing plates.
| note | b53e9b3b-9964-4f90-b51e-6175e4daaee2 | Place the epoxied plates onto the survey marks and ensure that the area level.
| note | 3650b979-b1c5-4792-ad1d-e42455a6e6cb | METHOD: Measure , Visual
| note | 36e7a25e-c10c-4d74-8802-46c672e4d852 | FREQUENCY: Where applicable, each installation location
| note | f64392f7-d12d-4109-be72-59c935c7a391 | CATEGORY: IP
| note | e8efb6de-72e1-40dc-8d8f-7652c745f58b | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | f1eb5fe8-4208-45ee-be58-571c79f8133a | VERIFYING DOCUMENTS: This ITP
| textbox | 1803a694-a1ca-46c5-97e4-e016424b2fa8 | Date Completed:
| checkpoint |  | 3.3 Bearing Shims or Bearing Strip Placement
| note | 7d0f2618-eb38-477a-a70c-b5152f5fe2a1 | REFERENCE: IFC Drawings
| note | 9c64d658-c7ae-491e-9ee6-f51c7deb0503 | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
| note | 947b3248-5742-46cf-8447-c37122cd0f34 | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
| note | fafa3b78-e0ff-42f9-8a86-f4bc7001a4bc | METHOD: Measure , Visual
| note | b6629526-2df7-4648-874e-941ae354eb41 | FREQUENCY: Where applicable, each installation location
| note | 6e110be3-a02b-4ca6-b344-b9c92934a77d | CATEGORY: IP
| note | bd58ae68-7c31-404f-9825-64efb81dbbcf | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | f0bc8a44-568e-4ee9-ac3e-6ff35aad6c9a | VERIFYING DOCUMENTS: This ITP
| textbox | 43b31f0e-56dd-4dfd-9e50-05a8944e80b3 | Date Completed:
| checkpoint |  | 3.4 Sealing Strips, Backing Rod & Bitumen Board
| note | b39207e6-a1c5-41d4-b8c7-7984e9bef4e8 | REFERENCE: IFC Drawings
| note | f67b11ca-0740-4632-863d-da1c98b4a6f5 | ACCEPTANCE CRITERIA: Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits).
| note | a635cb26-8f55-4c48-8795-36749758e9c3 | Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities.
| note | 32d08adb-16e5-49ae-ba55-45aefc2643c7 | METHOD: Measure , Visual
| note | 26d7701e-b4e0-40da-b94b-30f921c27961 | FREQUENCY: Where applicable, each installation location
| note | 877b79ac-ba52-41d3-95a3-51e686e232e8 | CATEGORY: IP
| note | c9c169ed-fa3f-4cd5-abd3-66661f0dde9c | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 9a701397-c81b-4b58-84c7-edc0ee66ad1a | VERIFYING DOCUMENTS: This ITP
| textbox | 99e0181c-5312-4791-a682-bf1e42332b2b | Date Completed:
| checkpoint |  | 3.5 Materials Inspection Checklist
| note | ac7f746a-0caf-4307-ac0f-e53398c7953b | REFERENCE: 620.06
| note | 3cb519a2-c8c5-47d7-bff9-c252dce60261 | 620.07
| note | 617914fc-2df3-4de6-9f61-0aeac0dd4f6f | MRPA Quality Management Plan
| note | d7fdfb92-c3b7-490b-87f1-e202c318b9f5 | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
| note | 526f0351-1402-462b-8589-b0c14811ed89 | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
| note | 8c256ca9-ef69-4a28-a408-d9df691ae23f | Elements shall have unique identification and orientation marked (if applicable).
| note | b7b89cad-3c65-48f6-a71e-48fcf7419c32 | Complete: Materials Inspection Checklist in ConQA
| note | a6253fc1-be10-4e83-b0b4-94897db80be3 | METHOD: Measure , Visual
| note | 35f03387-418e-4124-86cd-27d61b8bb175 | FREQUENCY: Each element
| note | 13ff1a42-8d07-4549-a1ad-d4c0b7188112 | CATEGORY: IP
| note | c8402afb-6910-48ee-a362-82a720db22e6 | RESPONSIBILITY: SE/PE/SPE
| note | 9a17ffb2-23dc-4aba-b74f-a47ae05f3e5c | VERIFYING DOCUMENTS: This ITP
| textbox | c47325e9-66f0-4af0-9f41-f0ee22f2225c | Date Completed:
| section |  | Installation Activities
| checkpoint |  | 4.1 Precast Handling
| note | 56c8f5d1-cd94-4a57-97ab-ba57fc08fb98 | REFERENCE: 620.07
| note | da173067-6807-4e0e-abf0-0db1eee34f70 | Crane Lift Study
| note | 6bcda74a-6dbd-4d89-9d38-1e45a2b54d2b | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
| note | 6d03c8ef-9780-44d7-b280-f6caca67b7b3 | METHOD: Visual
| note | 0366f45d-9b76-485b-90d9-f29ab424bb6e | FREQUENCY: Each element
| note | e2b5a8b2-6d64-42a6-913b-59cd9ee05ea8 | CATEGORY: IP
| note | 6b2af405-2aba-4b09-813e-629ab92eca03 | RESPONSIBILITY: SE/PE/SPE
| note | be93eb31-b639-4d8e-bd50-80c2784eceee | VERIFYING DOCUMENTS: This ITP
| textbox | cf2e0213-1ad9-4966-b233-2f336fe34759 | Date Completed:
| checkpoint |  | 4.2 Precast Placement
| note | 747cc2d4-c560-4062-b272-20310383e4eb | REFERENCE: IFC Drawings
| note | 323bbbf7-9f9e-4649-a817-3bac7fc5f742 | 610.27
| note | 5247a269-0149-4767-9509-1c6a6c6ecd7e | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
| note | af96cc99-8708-4d07-a238-3cde337c4cab | Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance.
| note | 18d42539-3739-43ae-99c9-8ec976eb58bb | The nominal gap between elements is as per the IFC Drawings.
| note | c674c4d3-da87-45db-ac3e-186ca8ce3b90 | METHOD: Measure , Visual
| note | 5531af84-af6f-4019-be9f-0ebe924bf8da | FREQUENCY: Each element
| note | 4fb7b035-c41f-4720-bff1-9532768bd903 | CATEGORY: IP
| note | 4b9944f7-1805-4514-96ec-20f80b8a091a | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 31e28146-e2a8-4300-b759-709aeca77f17 | VERIFYING DOCUMENTS: This ITP
| textbox | 900e4ff2-9b9e-4847-b1eb-80b95c57fcdb | Date Completed:
| checkpoint |  | 4.3 Draw-string in Service Ducts
| note | 8c9ced96-d36f-4149-a45c-b59b6a2f41fc | REFERENCE: IFC Drawings
| note | 679b566f-36eb-49be-ad9b-f21c6ce83dd7 | 671.03
| note | 83a54270-83b9-428f-99ad-b07c93204b34 | ACCEPTANCE CRITERIA: Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes.
| note | 9a10f9c6-3801-467c-9d8b-af6be0524953 | METHOD: Visual
| note | e3d9d176-61b0-4418-9a69-bbf2c4a2ec65 | FREQUENCY: Where applicable, each element
| note | 40dc8e7f-16c9-4a83-9d75-2fd9128e2db2 | CATEGORY: IP
| note | 7c40b37c-f5cf-4f05-bd16-a36458743ecf | RESPONSIBILITY: SE/PE/SPE
| note | aa2f3d8a-b1fa-4146-b0e7-a8ab0b0e2c6e | VERIFYING DOCUMENTS: This ITP
| textbox | 3e574b6f-8fd5-4a2b-8904-88aec70f4808 | Date Completed:
| checkpoint |  | 4.4 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
| note | 20dec3f3-d260-4cd4-a856-8972aaf48ab4 | REFERENCE: IFC Drawings
| note | 9301d110-9b05-463c-a24a-6ded0be3d4e4 | 630.20 (a) & (c)
| note | 387d4c33-3b28-4d0c-afd6-d714b3606e35 | AS5131 Clause 8.3
| note | 0411ce98-7f70-46db-b6cc-7c1af1c36f4e | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
| note | f7bc39f6-bfe2-4b65-8f03-959c4396982a | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
| note | 493e14be-22ee-4621-8bd8-fbf86a90dde6 | Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
| note | b43e297a-d048-4a62-aeae-46b51879c4ba | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
| note | 563580d1-6916-4daf-961a-c9d29680045e | METHOD: Visual
| note | 56d754d4-cded-4886-b1ca-674f2bf1c1cb | FREQUENCY: Where applicable, each bolted connection
| note | ee7a9caf-cd7e-4453-bc65-70cfd18cbbb4 | CATEGORY: IP
| note | 301bc668-7388-409a-9c31-57d07859bc85 | RESPONSIBILITY: SE/PE/SPE
| note | de184c96-9ecc-4f67-b32b-9a5159bc6dc9 | VERIFYING DOCUMENTS: This ITP
| textbox | c7db1f55-d9c9-495b-9dab-0ce42523e47e | Date Completed:
| checkpoint |  | 4.5 Precast Traceability
| note | 98d73917-b9ac-417f-a63c-f4fe8a05f98d | REFERENCE: 620.09
| note | 4ddb9e59-4a57-4ebb-a549-2d301787d668 | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
| note | a06ed561-0429-4e7a-9238-72d316e83af5 | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
| note | c79c18e2-fac2-4d1a-af76-74650138ae57 | METHOD: Visual
| note | 9cdc74d7-05be-4d4f-ac1f-0dde6a2ec2e4 | FREQUENCY: Each element
| note | 8a358b29-6722-4d07-a88b-091baa9f0999 | CATEGORY: IP
| note | 22005b90-63d4-430e-b345-a77c7e38481e | RESPONSIBILITY: SE/PE/SPE
| note | 697606ad-f554-4f5b-81c9-cbee63913f73 | VERIFYING DOCUMENTS: This ITP
| textbox | 08ec3846-469e-45b9-8080-4b53951ab682 | Date Completed:
| section |  | Post-installation Activities
| checkpoint |  | 5.1 Joint Sealant Application
| note | 6ee6c5bf-d30d-4ff1-8426-696ad1102143 | REFERENCE: IFC Drawings
| note | bf57ff79-e2d7-44c8-b8ba-9a022962e501 | ACCEPTANCE CRITERIA: The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
| note | a56988ba-96c5-4da7-a3de-cd5de53fc6da | METHOD: Visual
| note | 14d0b5b3-ffdf-4aed-af90-b242fffc752a | FREQUENCY: Where applicable
| note | 881f2894-e916-48f3-be09-14c89526f3a2 | CATEGORY: IP
| note | b69e06a5-e06d-4254-813f-4d1608ecfffa | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | d9f54d4c-09ca-4d3a-86de-4636ff9bcab4 | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
| textbox | 5cfc5f11-c697-4052-9586-3b9bd6e69d4a | Date Completed:
| checkpoint |  | 5.2 Flowable Grout Pour
| note | bf1417cd-9140-4060-8713-e46cd2c15c6d | REFERENCE: IFC Drawings
| note | b2f931d3-41c6-4a41-80c9-4591e75b7ebc | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
| note | 5e78ff50-8842-4d6f-8571-bebf8b699c3f | Complete: Grout Pedestals & Bearings ITP
| note | dc99047c-d464-45e0-940c-3592bb47b3bb | METHOD: Visual
| note | acf5ea63-49ee-4529-b1c0-0dbac3e90cd6 | FREQUENCY: Where applicable
| note | 75a6342f-1559-47bf-b4f2-54088754e26c | CATEGORY: IP
| note | 65d3b85a-20a0-407b-97c4-b7a768748a31 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 8fef52fe-684c-44e6-8dcc-d802e03bc49a | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
| textbox | 6443ae18-3250-4637-9dfa-5e9b8246f2bf | Date Completed:
| checkpoint |  | 5.3 Barrier Railing
| note | 8f84ccd5-b2f8-443d-a345-be2545f422e9 | REFERENCE: IFC Drawings
| note | 04bbf3c1-5820-4857-a5b9-e28a06e680b6 | ACCEPTANCE CRITERIA: Where applicable.
| note | 561c0ace-cafd-458a-b9fc-a65d0b7b8702 | Complete: Structural Steel Barrier Rail (Supply & Installation) ITP.
| note | fff1ab4f-7079-4f99-a600-969199f81957 | METHOD: Document Review
| note | c1105d87-70c7-478c-9bef-a463940950cd | FREQUENCY: Where applicable
| note | d0f6ecef-6373-4322-a1ac-358232f97d72 | CATEGORY: IP
| note | 637377a7-0733-4138-8394-d881bce7d867 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 3e8e769b-b4f0-47a1-9d60-d6619c04a1fd | VERIFYING DOCUMENTS: Structural Steel Barrier Rail (Supply & Installation) ITP
| textbox | 75e8ee38-b8c2-4eb7-8b3f-f790004c4af1 | Date Completed:
| checkpoint |  | 5.4 As-built Survey
| note | ebc5ddaa-aa6a-40f9-abb8-8992cb675c95 | REFERENCE: IFC Drawings
| note | e373c5ce-581f-4326-bdbc-dc522c1381a7 | 610.46 (a), Table 610.462 (November 2018)
| note | 81649270-ecbc-4e36-ad3f-afaa1773d0b9 | 610.47 (a), Table 610.472 (March/June 2019)
| note | 43816a6f-e4af-4746-934d-cf9549542fc9 | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
| note | 3ad97e17-3cf3-42e5-b803-fd00af5808f7 | Attach: Survey As-builts / Survey Report
| note | b99055e3-262a-4c74-9ac1-8b424c5c575d | METHOD: Document Review
| note | 542c0365-c4cf-4b4c-ac8f-b413f1a589ac | FREQUENCY: Each element
| note | 050dfd73-3238-4a1c-be5b-0fd7398b3b45 | CATEGORY: IP
| note | c1766aa5-c537-4c71-9f84-1be15cf99c55 | RESPONSIBILITY: Surveyor , SE/PE/SPE
| note | 71563986-729b-4c39-a982-8f7e7b464b29 | VERIFYING DOCUMENTS: This ITP
| textbox | 823beb11-1bd0-45b4-8c7f-547bf7151b42 | Date Completed:
| checkpoint |  | 5.5 Non-conformance Report (NCR) Closure
| note | 7b53ffff-bd7c-440e-adfe-e04b7420cec8 | REFERENCE: MRPA Quality Management Plan
| note | c9887733-40cb-4192-8c87-c542d318d30a | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
| note | 8bbb91fc-2ff5-4aff-b1aa-8fc7b0c0dd0b | METHOD: Document Review
| note | 159ab3b8-a08c-415c-a9f2-435a62960f0b | FREQUENCY: Once, prior to closure of this lot / element / Work area
| note | 9f3d4c30-8050-4105-83bc-38cbf3f0661b | CATEGORY: HP*
| note | dfd583fd-6d56-4ba1-bdfc-3ce80c64a735 | RESPONSIBILITY: SE/PE/SPE
| note | 9fc42244-0c3a-49ef-a8f6-d9fee92e91eb | VERIFYING DOCUMENTS: This ITP
| textbox | 8774619f-19a0-4b7e-89b6-f4f665a8effa | Date Completed:
| checkpoint |  | Metropolitan Roads Program Alliance Final Inspection
| note | d953a48a-f236-45af-8101-8611f8bfce23 | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
| textbox | 4380f54d-4728-4a6d-9599-5e3f596bc2b8 | Name:
| textbox | fa7f3d04-783e-45f2-950e-0d2a5e2783eb | Position:
| textbox | 94d046bf-3783-4df8-a5d4-aa5ff30b977a | Date Completed:
| signoff |  | Sign ITP