## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-CIV Delineation Fence | itp |  |  |  |  | ITP-CIV Delineation Fence Rev 2
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-CIV Delineation Fence
label | ITP Description: Delineation Fence
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 2
label | Revision Date: 27/05/2024
label | Referenced Documentation
label | 1.1 Non Dependent
label | REFERENCE: IFC Drawings
label | 1.2 Non Dependent
label | REFERENCE: AS1657
section | Materials
checkpoint | 2.1 Concrete
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: 25 MPa concrete to be used as per IFC drawings.
label | METHOD: Document Review
label | FREQUENCY: Each Mix
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Site Supervisor
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Steel components including posts, mesh and fittings
label | REFERENCE: IFC Drawings AS1657
label | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | ○ Steel posts to be CHS with a grade of C250
label | ○ Black PVC finish
label | METHOD: Document review, Visual and Measure
label | FREQUENCY: All elements
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, and fence start and end points.
label | ○ Offset checked against the running edge prior to installation of posts.
label | METHOD: Visual and Measure
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Excavation works
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Excavation completed by auger outside of service working limits.
label | ○ Follow asset owners guidelines for work around their service.
label | METHOD: Visual
label | FREQUENCY: Each fence footing
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Ground Conditions
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | METHOD: Visual
label | FREQUENCY: Each post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Fence Footing
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Footing dimensions 600mm deep x 300mm diameter. Every second footing to have dimensions 1200mm deep x 300mm diameter.
label | ○ 25 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per VicRoads Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample.
label | METHOD: Measure
label | FREQUENCY: Each footing
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP, Concrete Dockets
date | Date Completed:
checkpoint | 4.4 Fence Post Installation - Non-sleeved
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover.
label | METHOD: Measure
label | FREQUENCY: Each post
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.5 Chain Wire Mesh Installation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Chain-wire mesh 1200x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications.
label | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 5.1 As-Built Survey
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure spacings do not exceed standards.
label | METHOD: Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
holdpoint | Sign ITP