## Resources
Warnings | Type | Id | Name | Values | Prompting Name | Resource Id
| checklist |  | QA - Torch On to Plywood Checklist |  | Torch On to Plywood Checklist | 002398c5-77c1-4fa8-bdb1-9e05ed5cf4b4
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Plywood Substrate
| checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
| checkpoint |  | No Screws/nails/fixings popping up
| checkpoint |  | Joints flush and even
| section |  | Prime of Substrate
| checkpoint |  | Substrate clean and free from debris
| checkpoint |  | Primer installed
| section |  | Base Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Check all welds at the end of the day
| section |  | Cap Sheet
| checkpoint |  | Install low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
| checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
| checkpoint |  | Membrane dressed into drains/outlets
| checkpoint |  | Install clamps/rings/baskets
| checkpoint |  | Flood/ILD test
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Metal Cladding Install Checklist |  | Metal Cladding Install Checklist | 02a60f1c-4e9c-476e-bdb4-8232c7782ace
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Install
| checkpoint |  | Bottom flashing installed straight/level all the way around
| checkpoint |  | Building wrap installed
| checkpoint |  | Flashing tape installed (check plans)
| checkpoint |  | Soaker flashings installed
| checkpoint |  | Cladding installed plumb and straight
| checkpoint |  | Screw pattern according to plan/spec/best practice
| checkpoint-no-value |  | Flashings installed as per specification
| checkpoint |  | Closure foams installed
| checkpoint |  | Fixings installed correctly
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Fibertite Overlay Install Checklist |  | Fibertite Overlay Install Checklist | 040c1b75-e3f6-4a8a-b80a-24b5d2c50238
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Substrate
| checkpoint |  | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
| checkpoint |  | Cut back existing roof edge at gutter
| checkpoint |  | Remove ridge as we go
| section |  | VCL-Vapour Control Layer
| checkpoint |  | Surface/Substrate is dry, clean and free from sharp edges
| checkpoint |  | All areas covered and lapped a minimum of 50mm
| checkpoint |  | All holes/penetrations patched and made watertight
| section |  | Roof Pan Infills
| checkpoint |  | Surface is dry before installing Poly
| checkpoint |  | Infills to be a minimum 5mm above ridges on roof
| checkpoint |  | Every pan has been infilled
| section |  | Roofboard
| checkpoint |  | Substrate/surface dry & clean prior to being installed
| checkpoint |  | Installed in brick pattern
| checkpoint |  | Correct screws with load washer
| checkpoint |  | Installed as per wind uplift fixing plan
| checkpoint |  | Install 70mm X 100mm zincalume flashing at gutter edge for strength
| section |  | Fibertite
| checkpoint |  | Correct Glue being used for substrate
| checkpoint |  | Fibertite fully glued to substrate
| checkpoint |  | Broom/rolling of fibertite
| checkpoint |  | Wipe/clean laps with acetone prior to welding
| checkpoint |  | All laps, details, penetrations fully welded/closed and QA'd with hook
| checkpoint |  | Clamps / rings / baskets installed
| checkpoint |  | Flooded / ILD checked
| section |  | Fiberclad Flashings
| checkpoint |  | Installed correctly
| checkpoint |  | Fixed down according to specification
| checkpoint |  | Cleaned down with acetone prior to welding
| checkpoint |  | Fibertite fully welded to flashing and QA'd with hook
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | Weather Monitoring |  | Weather Monitoring | 07eb1ba3-8dd4-4850-a104-a46eef91be1b
| section |  | Current Weather
| checkpoint |  | Wind / weather conditions
| checkpoint |  | Record any delays
| checkpoint |  | area / gridlines
| checkpoint |  | Comments / issues / observations
| section |  | Weather Forecast
| checkpoint |  | What is the weather forecast this week
| checkpoint |  | Record any delays
| checkpoint |  | area / gridlines
| checkpoint |  | Comments / issues / observations
| checklist |  | QA - Fibertite Warm Roof Over Concrete Checklist |  | Fibertite Warm Roof Over Concrete Checklist | 101230d6-7989-49e9-b9dc-d582ea6108c3
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Concrete Substrate
| checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
| checkpoint |  | All lumps and sharp concrete bits ground/hammered down
| checkpoint |  | Large holes filled with grout
| section |  | Vapor Control Layer
| checkpoint |  | Substrate clean, dry, and free of debris
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapor control layer has been checked and no damage
| checkpoint |  | Insulation boards installed
| checkpoint |  | Joints flush (no gaps between boards)
| checkpoint |  | Correct length of fixing with load washer if no Securock
| section |  | Securock
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Installed in brick pattern
| checkpoint |  | Correct length of fixing with load washer
| section |  | Fibertite
| checkpoint |  | Adhesive installed to substrate
| checkpoint |  | Laying of membrane into adhesive
| checkpoint |  | Broom/rolling of membrane
| checkpoint |  | Wipe and clean laps prior to welding
| checkpoint |  | Test weld with the welding machines
| checkpoint |  | Probe of seam with QA hook
| checkpoint |  | Membrane dressed into drains/outlets
| checkpoint |  | Claps/rings/baskets installed
| checkpoint |  | Flood/ILD tested
| section |  | Fiberclad Flashings
| checkpoint |  | Installed correctly according to specifications (right way around)
| checkpoint |  | Fixings and welding done according to specifications and details
| checkpoint |  | Probe of weld with QA hook
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | New Files |  | New Files | 1208f41d-17f6-4182-9ed6-915e22e5c60a
| checkpoint |  | Upload Files
| checklist |  | QA - MSR Checklist |  | MSR Checklist | 1f4d62ad-95fe-42a9-91e9-1662e8a78f4c
| section |  | Prestart
| checkpoint |  | Area Accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Metal Deck
| checkpoint |  | Timber to have separation barrier
| checkpoint |  | Base deck screwed down and secure
| section |  | Vapour Control Layer
| checkpoint |  | Is the substrate clean, dry and clear of swarf
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Acoustic Board
| checkpoint |  | Is the surface dry
| checkpoint |  | Installed with no gaps
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapour control layer has been checked for no damage
| checkpoint |  | Insulation board installed
| checkpoint |  | Joints flush (no gaps between boards on ends)
| section |  | Topdeck Install
| checkpoint |  | Covertek Installed with 150mm overlap
| checkpoint |  | Drip edge installed
| checkpoint |  | Lay sheet with minimum 75mm gutter overhang
| checkpoint |  | Top end of sheet turned up
| checkpoint |  | Fixing back into purlin
| checkpoint |  | Closure foam to gutter end
| checkpoint |  | Profile Washers over 12m
| checkpoint |  | Sheets straight & perpendicular to gutter
| checkpoint |  | Screw pattern as per fixing plan
| section |  | Roof flashings
| checkpoint |  | Installed correctly according to specification & drawings
| checkpoint |  | Fixings done according to specifications and details
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | Add Flood Testing Checklist |  | Flood Test Area: | 22c95d72-dcc0-49a3-bdef-bdae9af4b94e
| checkpoint |  | Is area fully finished, QA’d and ready to be tested
| checkpoint-no-value |  | Flood test details
| textbox | dc968f8f-9cf1-485a-a65f-e4087427ee32 | Date:
| textbox | b0fb2bc4-3c3c-47bb-93fe-add4a651804d | Area tested:
| textbox | befd486d-6456-4e39-ba95-1395566ebfda | Duration:
| button | 3fff6840-5866-4f4c-96c8-494f7e9efd79 | Have you checked regularly for leaks | Yes, No, N/A
| button | 050fef10-15f2-4590-ba62-2a0b1b1b0a29 | Is there rain in the forecast | Yes, No, N/A
| button | b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 | Have all leaks been repaired | Yes, No, N/A
| checkpoint |  | Flood test complete
| button | 5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 | Have the plugs been removed from the drains | Yes, No, N/A
| button | b74c91b9-0371-4641-ad5b-1c9d76ee0c77 | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
| signoff |  | Sign Off
| checklist |  | QA - Fiberglass System Checklist |  | Fiberglass System Checklist | 2c08dbad-6330-4798-a61d-92f957abf563
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Surface Prep
| checkpoint |  | Concrete free of contaminants
| checkpoint |  | Concrete flat and smooth
| checkpoint |  | Bug holes in plinths filled and smooth
| section |  | Membrane install
| checkpoint |  | Install sealant angle fillets to all wall floor junctions
| checkpoint |  | Prime surfaces with Epistixx
| checkpoint |  | 2nd body coat
| checkpoint |  | 3rd body coat
| checkpoint |  | Traxx 2000 wear coat.
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | Add Variation Checklist |  | Variation Details - | 2f98d637-56db-4061-a132-fbf29ad70936
| checkpoint |  | Variation Details Approved
| textbox | 28d26279-c304-4689-8317-1deb797dc8fe | Reference/Drawing/Instruction Number
| textbox | 2247155b-6de8-434c-a1e1-058d724a6a62 | Variation Area
| textbox | ae7fc046-dca9-4fab-98f8-374caeb044ec | Materials & labour breakdown
Invalid dependant | signoff |  | Request Variation Acknowledgement
| checkpoint |  | Variation Completed
Invalid dependant | signoff |  | Request Variation Signoff
| checklist |  | Add Delay Checklist |  | Delay Checklist | 4d9f8c84-10f3-41e6-a006-6cbdf64fe63e
| checkpoint-no-value |  | Delay details.
| textbox | ae5b692f-ee75-4a3d-90e7-43a6b2bca49e | Date:
| textbox | 8e11a44b-51f7-4a8f-9494-ec9e467452ec | Description:
| textbox | 22cd20b8-86af-49a9-97d4-39d5b860ca1a | Area/Grids:
| textbox | e5ab19af-90b5-4328-9a8b-ee0707087643 | Wind/Weather Conditions:
| checklist |  | QA - Soffit Checklist |  | Soffit Checklist | 65819cc6-ba9b-4938-b578-b76aec39bfd5
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Substrate ready (check plans) with proper purlin spacing
| checkpoint |  | Design/Spec/Approvals complete
| section |  | Install
| checkpoint |  | Flashings installed according to plans
| checkpoint |  | All sealant work complete
| checkpoint |  | Install soffit lining according to plans/spec/best practice
| checkpoint |  | Screw pattern according to plans/spec/best practice
| checkpoint |  | Finish flashings complete
| section |  | Sign Off
| checkpoint |  | Cladding Install Complete
| signoff |  | Request Sign Off
| checklist |  | Add Daily Cassette Log |  | Daily Cassette Log - | 6b092a41-a3e9-4020-8470-8dbda3e5e629
| checkpoint-no-value |  | Date:
| textbox | e5ab19af-90b5-4328-9a8b-ee0707087643
| checkpoint-no-value |  | Cassette Number:
| textbox | 8e11a44b-51f7-4a8f-9494-ec9e467452ec
| checkpoint-no-value |  | Record any delays:
| textbox | 22cd20b8-86af-49a9-97d4-39d5b860ca1a
| checkpoint-no-value |  | Wind/Weather Conditions:
| textbox | 5114a122-dcf7-44a7-be38-8623182196af
| checkpoint-no-value |  | Comments/Issues/Observations:
| textbox | a6aebd36-6433-4aca-b8f4-ef6216c059cf
| checklist |  | Xtreme FibreTite Checklist |  | FiberTite Checklist - Area: | 6c249880-08bb-4f25-9a62-60a2a0693ade
| section |  | Pre Start
| checkpoint |  | Area Accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP (metal/concrete/ply)
| checkpoint |  | Perimeter support installed installed if metal deck substrate
| section |  | Metal Deck
| checkpoint |  | Timber to have separation barrier
| checkpoint |  | Base deck screwed down in every pan
| section |  | Vapour Control Layer
| checkpoint |  | Is the substrate clean, dry and clear of swarf
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Acoustic Board
| checkpoint |  | Is the surface dry
| checkpoint |  | Installed in brick pattern
| checkpoint |  | correct length screw with recessed flat plates
| checkpoint |  | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapour control layer has been checked for no damage
| checkpoint |  | Insulation board installed in a brick pattern
| checkpoint |  | Joints flush (no gaps between boards on ends)
| checkpoint |  | Fixings at correct spacing according to spec if no Securock in system.
| section |  | HDP Roofboard
| checkpoint |  | Is the surface dry
| checkpoint |  | Installed in brick pattern
| checkpoint |  | correct length screw with recessed flat plates
| checkpoint |  | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
| section |  | FiberTite
| checkpoint |  | Test weld with welding machine
| checkpoint |  | Adhesive installed to substrate
| checkpoint |  | Laying of membrane into the adhesive
| checkpoint |  | Broom/rolling of membrane
| checkpoint |  | Wipe and clean of laps prior to welding
| checkpoint |  | Probe of seams with QA hook
| checkpoint |  | Clamp and weld of outlets and overflows
| checkpoint |  | Flood test of outlets
| section |  | Fiberclad flashings
| checkpoint |  | Installed correctly according to specifications (Right way around)
| checkpoint |  | Fixings and welding done according to specifications and details
| checkpoint |  | Probe of weld with QA hook
| checkpoint |  | Area Complete (Request MC Signoff)
| checklist |  | Add Dayworks Checklist |  | Dayworks - | 6d49d944-95f0-475f-8bb1-b020c6397987
| checkpoint |  | Day Work Details
| textbox | d27d8079-cce6-47f2-bc8f-5447bd0b63c3 | NTSC / SI #:
| textbox | d63889f7-ee5a-4b1a-8284-614d5f938189 | Labours (HR)
| textbox | 926bb36c-59db-4b70-828c-6bc1bf2ce049 | Work Description:
| textbox | 693bbb1a-ade5-4140-a549-223cae16f4cb | Materials:
| textbox | 6d1abe7d-16c2-45ff-b354-7f74775359b8 | SWP Representative. Prepared By:
| textbox | 7e548609-67fa-4b3f-91fa-027d546e556f | Client Representative. Confirmed By:
| signoff |  | Request Signature Signoff
| checklist |  | QA - Fibertite to Plywood Checklist |  | Fibertite to Plywood Checklist | 744bc8e1-64bc-4e19-99bf-196c7e53c566
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Plywood Substrate
| checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
| checkpoint |  | No Screws/nails/fixings popping up
| checkpoint |  | Joints flush and even
| section |  | Fibertite Membrane
| checkpoint |  | Correct Glue used per spec
| checkpoint |  | Fibertite fully glued to plywood
| checkpoint |  | Broom / roll fibertite into glue
| checkpoint |  | All laps, details, penetrations fully closed & QA'd with hook
| checkpoint |  | Membrane dressed into drains/outlets
| checkpoint |  | Clamps / rings / baskets installed
| checkpoint |  | Flooded / ILD checked
| section |  | Fiberclad Flashings
| checkpoint |  | Installed correctly according to specifications (right way around)
| checkpoint |  | Fixings and welding done according to details
| checkpoint |  | Welding of Fibertite to flashings fully finished and QA'd with hook
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Metal Flashing Install Checklist |  | Metal Flashing Install Checklist | 765a6200-f86f-4a0e-8868-9eb8defe8b73
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Metal Flashing Install
| checkpoint |  | Installed with a minimum upstand of 150mm or according to drawings
| checkpoint |  | Expansion joint installed if needed (i.e. with runs longer than 12m for coloursteel or 8m for Ali.)
| checkpoint |  | Fixings according to Code as a minimum (or plans if more are required) in a straight line
| checkpoint |  | Laid in a straight and tidy manner
| checkpoint |  | All laps and junctions sealed properly and facing away from waterflow
| checkpoint |  | All visible ends & junctions cut and folded straight and tidy
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Carpark MMA Checklist |  | Carpark MMA Checklist | 7727a854-4d78-44b5-a7c8-c1070dc2693f
| section |  | Pre Start
| checkpoint |  | SSSP onsite
| checkpoint |  | Fencing demarcation installed
| checkpoint |  | Site signage installed
| checkpoint |  | Area Accessible
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Surface Prep
| checkpoint |  | Removal of coatings
| checkpoint |  | Grind of substrate
| checkpoint |  | Shotblast of substrate to achieve suitable profile
| section |  | Pre-start of membrane install
| checkpoint |  | Substrate dry
| section |  | Membrane install
| checkpoint |  | Prime of substrate
| checkpoint |  | Stripe out cracks
| checkpoint |  | Map out areas based on coverage rates for install
| checkpoint |  | Membrane layer installed
| checkpoint |  | Wear layer installed and broadcast
| checkpoint |  | Excess broadcast swept and removed
| checkpoint |  | 1st Top coat
| checkpoint |  | 2nd top coat
| checkpoint |  | Site cleared and broken down
| checkpoint |  | Site cleared and broken down
| checklist |  | Add Final Inspection Checklist |  | Final inspection | 83d215c7-5b19-4400-856c-5f11de59eec5
| checkpoint |  | Final inspection
| textbox | 5c48b2f9-7155-5010-a625-9c61273b1f4a | Date
| textbox | cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 | Area/elevation/grids
| textbox | f185db39-ef5a-566f-a627-b84ed061402b | Description
| note | bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 | Attach Photos
| signoff |  | Request Signature Signoff
| checklist |  | MSR checklist |  | MSR checklist | 8f509152-385d-4008-af1f-288db5c56026
| section |  | Pre start
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Purlins installed and QA / handover received from main contractor
| checkpoint |  | visual inspection by SWP
| section |  | Liner deck
| checkpoint |  | Liner deck fixed down in every purlin and every pan
| checkpoint |  | Correct fixing installed
| section |  | Vapor control layer
| checkpoint |  | Substrate clean, dry, free of debris
| checkpoint |  | Z flashing installed
| checkpoint |  | VCL installed and covered all surface
| checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
| section |  | Acoustic board install
| checkpoint |  | VCL clean, no ponding water, free of debris prior to install
| checkpoint |  | VCL has been cheeked for damages
| checkpoint |  | All holes/penetrations patched
| section |  | Insulation
| checkpoint |  | Boards tightly butted all areas covered
| checkpoint |  | Correct insulation installed as per spec
| section |  | Underlay installed
| checkpoint |  | Correct underlay installed as per specifications
| checkpoint |  | Overlapped a minimum 150mm side laps and 200mm end laps
| checkpoint |  | All areas covered
| checkpoint |  | Underlay installed as per specifications
| checkpoint |  | Joints taped together as per drawings and specifications
| section |  | Metal roof installation
| checkpoint |  | Drip edge installed as per drawings and specifications
| checkpoint |  | Laid straight and perpendicular to gutter/purlins
| checkpoint |  | Gutter overhang as per drawings and specifications
| checkpoint |  | Top end turned up
| checkpoint |  | Bottom ends turned down
| checkpoint |  | Closure foam installed
| checkpoint |  | Screw pattern according to plan/specs/fixing plan
| section |  | Flashing install
| checkpoint |  | Sealant installed with 2 continues beads
| checkpoint |  | Clean excess sealant
| checkpoint |  | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
| checkpoint |  | Flashings installed as per drawings and specifications and facing away from waterflow
| checkpoint |  | Fixings installed as per drawings and specifications
| section |  | Review and sign off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work completed, checked and reviewed as per specifications
| signoff |  | Client/main contractor sign off
| checklist |  | Supplier Site Visit |  | Site Visit date: | 9c7920d9-243c-4974-a587-6cd8a9b647b0
| checkpoint-no-value |  | Site Details
| textbox | 6d41fa6a-4e1a-577e-a624-6bd736f97876 | Job Name
| textbox | 22044acf-ec81-5b86-a826-c71cabe41273 | Who is in attendance
| textbox | 1235194d-88da-53a0-854a-ce85145c2b1e | Area/Gridlines/Detail
| checkpoint |  | Photos
| textbox | e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 | Inspection Notes
| signoff |  | Signoff Required
| checklist |  | Add Defect Checklist |  | Defect - | a25b18f6-8629-4d86-b7cb-c2bc53a45867
| checkpoint |  | Defect details recorded
| textbox | 9b18e909-7530-4d08-ad54-acb417409980 | Explanation of defect:
| textbox | 3af60290-922d-4e09-aeb9-b795186cbbd5 | Area:
| textbox | da7b5fcc-182d-4ccf-ade5-02dfaae6dedb | Party responsible for damages:
| textbox | f37cdc9e-47d2-43c7-b8ce-36034d624bbc | Efforts required for repair:
| textbox | 16d78d9b-0a7d-4e07-bb38-68e664e6d30e | Man hours required for repair:
| signoff |  | Request Approval from Main Contractor
| checkpoint |  | Defect Fixed
| signoff |  | Request Defect signoff
| checklist |  | QA - Fibertherm Checklist |  | Fibertherm Checklist | a3f7b109-61a3-4212-9d4f-a08941bc2109
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Metal Deck
| checkpoint |  | Timber to have separation
| checkpoint |  | End openings to have closure foam installed
| checkpoint |  | Base deck screwed down in every pan
| checkpoint |  | VCL tape to be installed to all sheet laps
| checkpoint |  | VCL tape to all upstands
| section |  | Post and Rail install
| checkpoint |  | Post installed at correct fixing centers
| checkpoint |  | Thermal break pad under post foot
| checkpoint |  | Rail installed to posts
| section |  | Insulation install
| checkpoint |  | Specified Insulation installed
| checkpoint |  | No Gaps
| section |  | Top Deck install
| checkpoint |  | Lay sheets straight
| checkpoint |  | Hang over into gutter min 75mm
| checkpoint |  | Top end of sheets turned up
| checkpoint |  | Bottom end of sheets turned down
| checkpoint |  | Fixing back to rail
| checkpoint |  | Profile washers
| checkpoint |  | Screwed off as per fixing plan
| section |  | Flashing install
| checkpoint |  | Fixings according to specs & details
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | FiberTite warm roof to CLT mechanically fixed and adhered checklist |  | FiberTite warm roof to CLT mechanically fixed and adhered checklist | b7f4e3f2-27dc-4ee0-be04-b383fbe4bc51
| section |  | Pre start
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Visual inspection of substrate ready for SWP
| checkpoint |  | QA document received from previous trade from main contractor
| section |  | CLT Substrate
| checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
| checkpoint |  | Installation of SA primer
| section |  | Vapor control layer
| checkpoint |  | Substrate clean, dry, free of debris
| checkpoint |  | Z flashing installed
| checkpoint |  | Install VCL over primer
| checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
| checkpoint |  | Installation of SA primer
| section |  | Insulation
| checkpoint |  | VCL clean, dry, free of debris prior to install
| checkpoint |  | VCL has been checked for damages and repaired
| checkpoint |  | Closure flashings installed correctly
| checkpoint |  | Install board adhesive in specified pattern
| checkpoint |  | Boards tightly butted
| section |  | Tapered EPS
| checkpoint |  | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
| checkpoint |  | Install board adhesive in specified pattern
| checkpoint |  | EPS board installed into adhesive
| section |  | ILD system installed
| checkpoint |  | ILD System installed as per specs
| checkpoint |  | ILD test plate installed
| section |  | HDP board
| checkpoint |  | PIR clean, dry, free of debris prior to install
| checkpoint |  | Install board adhesive in specified pattern
| checkpoint |  | HDP board installed in brick pattern where possible
| section |  | FiberTite
| checkpoint |  | Prime substrate where required
| checkpoint |  | Adhesive installed to substrate
| checkpoint |  | Laying of membrane into adhesive
| checkpoint |  | Broom/rolling of membrane
| checkpoint |  | Wipe and clean laps prior to welding
| checkpoint |  | Test weld with welding machine
| checkpoint |  | Probe of seam with QA hook
| section |  | Sumps
| checkpoint |  | Sealant installed to dropper flange under membrane
| checkpoint |  | Membrane dressed in to outlets
| checkpoint |  | Clamp/rings/basket installed
| checkpoint |  | Flood test
| section |  | ILD report
| checkpoint |  | ILD report
| section |  | Fiberclad flashing
| checkpoint |  | Installed correctly according to specifications ( right way around )
| checkpoint |  | Fixing and welding done according to specifications and details
| checkpoint |  | Probe of seam with QA hook
| section |  | Pressure bar installed
| checkpoint |  | Installed correctly according to specifications ( right way around )
| checkpoint |  | Fixings done according to specifications and details
| checkpoint |  | Prime of Substrate where required
| checkpoint |  | Sealant installed
| section |  | Over flashings
| checkpoint |  | Over flashings has a separation barrier
| checkpoint |  | Fixings done according to specifications and details
| checkpoint |  | Primer of Substrate
| checkpoint |  | Sealant installed
| section |  | Review and sign off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work completed, checked and reviewed as per specifications
| checkpoint |  | Client/main contractor sign off
| checklist |  | QA - Torch On to Concrete Checklist |  | Torch On to Concrete Checklist | c0d3b3fa-01ee-495d-9904-471a5222cd2e
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Concrete Substrate
| checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
| checkpoint |  | All lumps and sharp concrete bits ground/hammered down
| checkpoint |  | Large holes filled with grout
| section |  | Prime of Substrate
| checkpoint |  | Substrate clean and free from debris
| checkpoint |  | Primer installed
| section |  | Base Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Check all welds at the end of the day
| section |  | Cap Sheet
| checkpoint |  | Install low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
| checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
| checkpoint |  | Membrane dressed into drains/outlets
| checkpoint |  | Install clamps/rings/baskets
| checkpoint |  | Flood/ILD test
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Fibertite to Concrete Checklist |  | Fibertite to Concrete Checklist | c80b1971-9c49-4a7b-963d-b73c4850a4d4
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Concrete Substrate
| checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
| checkpoint |  | All lumps and sharp concrete bits ground/hammered down
| checkpoint |  | Large holes filled with grout
| section |  | Fibertite
| checkpoint |  | Adhesive installed to substrate
| checkpoint |  | Laying of membrane into adhesive
| checkpoint |  | Broom/rolling of membrane
| checkpoint |  | Wipe and clean laps prior to welding
| checkpoint |  | Test weld with the welding machines
| checkpoint |  | Probe of seam with QA hook
| checkpoint |  | Membrane dressed into drains/outlets
| checkpoint |  | Claps/rings/baskets installed
| checkpoint |  | Flood/ILD tested
| section |  | Fiberclad Flashings
| checkpoint |  | Installed correctly according to specifications (right way around)
| checkpoint |  | Fixing and welding done according to specifications and details
| checkpoint |  | Probe of weld with QA hook
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Sheet Tanking System Checklist |  | Sheet Tanking System Checklist | cd1a8acb-c088-4484-8a9f-75f4e691845e
| section |  | Pre Start
| checkpoint |  | Area Accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Primer
| checkpoint |  | Applied as per specification on dry substrate at 5m2 per litre
| section |  | Membrane
| checkpoint |  | Temperature must be over 4 degrees for membrane install
| checkpoint |  | Is the substrate clean, dry and clear
| checkpoint |  | Membrane applied with min 50mm overlap
| checkpoint |  | Overlap is to pressure applied or rolled for seal
| section |  | Protection
| checkpoint |  | Works to be protected by main contractor
| checklist |  | QA - Torch On Warmroof to Concrete Checklist |  | Torch On Warmroof to Concrete Checklist | cde62c22-24c1-40a2-b5f6-f2586e6b0c60
| section |  | Pre Start
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Concrete
| checkpoint |  | Concrete clean and dry. Free from dirt/debris and ready for priming
| checkpoint |  | All lumps and sharp concrete bits ground down/hammered down
| checkpoint |  | Large holes filled with grout
| section |  | Vapour Control Layer
| checkpoint |  | Is the substrate clean, dry and clear of swarf
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapour control layer has been checked for no damage
| checkpoint |  | Insulation board installed
| checkpoint |  | Joints flush (no gaps between boards on ends)
| section |  | Securock
| checkpoint |  | Is the surface dry
| checkpoint |  | Installed in brick pattern
| checkpoint |  | Correct length screw with load washer
| checkpoint |  | Prime of Securrock
| checkpoint |  | Installed as per wind uplift fixing plan
| section |  | Base Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Check of all welds at the end of the day
| section |  | Cap Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
| checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
| checkpoint |  | Clamps / rings / baskets press into overflows and outlets
| checkpoint |  | Flood test / ELD tested
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Torch on Warmroof Over Plywood Checklist |  | Torch on Warmroof Over Plywood Checklist | d0d825ce-0bd4-41e7-aa8c-91be07c4a8ab
| section |  | Pre Start
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Plywood
| checkpoint |  | Plywood clean and dry. Free from dirt/debris and and ready for priming
| checkpoint |  | No screws/nails/fixings popping up
| checkpoint |  | Plywood joints flush and even
| section |  | Vapour Control Layer
| checkpoint |  | Is the substrate clean, dry and clear of swarf
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapour control layer has been checked for no damage
| checkpoint |  | Insulation board installed
| checkpoint |  | Joints flush (no gaps between boards on ends)
| section |  | Securock
| checkpoint |  | Is the surface dry
| checkpoint |  | Installed in brick pattern
| checkpoint |  | Correct length screw with recessed flat plates
| checkpoint |  | Prime of Securrock
| checkpoint |  | Installed as per wind uplift fixing plan
| section |  | Base Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Check of all welds at the end of the day
| section |  | Cap Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
| checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
| checkpoint |  | Clamps / rings / baskets installed and press into overflows and outlets
| checkpoint |  | Flood test / ILD checked
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Metal Gutter Install Checklist |  | Metal Gutter Install Checklist | d14cd2e4-71ef-46a9-9fc5-25db335bb94e
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Install
| checkpoint |  | Brackets installed according to plans/spec/best practice
| checkpoint |  | Gutter lapped and sealed correctly according to best practice
| checkpoint |  | All terminations and ends folded/sealed properly
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Fibertite Warm Roof Over Metal Deck Checklist |  | Fibertite Warm Roof Over Metal Deck Checklist | d73dda22-05eb-4b9b-8651-5e3302f983c1
| section |  | Pre Start
| checkpoint |  | Area Accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Metal Deck
| checkpoint |  | Timber to have separation barrier
| checkpoint |  | Base deck screwed down in every pan
| checkpoint |  | Sheet edges stiched together at 300mm centres
| section |  | Vapour Control Layer
| checkpoint |  | Is the substrate clean, dry and clear of swarf
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapour control layer has been checked for no damage
| checkpoint |  | Insulation board installed in a brick pattern
| checkpoint |  | Joints flush (no gaps between boards on ends)
| checkpoint |  | Fixings at correct spacing according to spec if no Securock in system.
| section |  | Securock
| checkpoint |  | Is the surface dry
| checkpoint |  | Installed in brick pattern
| checkpoint |  | Correct length screw with load washer
| checkpoint |  | Installed as per wind uplift fixing plan
| section |  | FiberTite
| checkpoint |  | Adhesive installed to substrate
| checkpoint |  | Laying of membrane into the adhesive
| checkpoint |  | Broom/rolling of membrane
| checkpoint |  | Wipe and clean of laps prior to welding
| checkpoint |  | Test weld with welding machine
| checkpoint |  | Membrane dressed into drains/outlets
| checkpoint |  | Clamps / rings / baskets installed
| checkpoint |  | Flooded / ILD checked
| section |  | Fiberclad flashings
| checkpoint |  | Installed correctly according to specifications (Right way around)
| checkpoint |  | Fixings and welding done according to specifications and details
| checkpoint |  | Probe of weld with QA hook
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Torch on Warmroof Over Metal Deck Checklist |  | Torch on Warmroof Over Metal Deck Checklist | df0c1abc-57ef-4e0c-bb0a-ce0854afbb0c
| section |  | Pre Start
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Metal Deck
| checkpoint |  | Timber to have separation barrier
| checkpoint |  | Base deck screwed down in every pan
| checkpoint |  | Sheet edges stitched together at 300mm centres
| checkpoint |  | No sharp edges protruding
| section |  | Vapour Control Layer
| checkpoint |  | Is the substrate clean, dry and clear of swarf
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapour control layer has been checked for no damage
| checkpoint |  | Insulation board installed
| checkpoint |  | Joints flush (no gaps between boards on ends)
| section |  | Securock
| checkpoint |  | Is the surface dry
| checkpoint |  | Installed in brick pattern
| checkpoint |  | Correct length screw with recessed flat plates
| checkpoint |  | Installed as per wind uplift fixing plan
| checkpoint |  | Prime of Securrock
| section |  | Base Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Bleed of bitumen on overlap should be up to 10mm
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Check of all welds at the end of the day
| section |  | Cap Sheet
| checkpoint |  | Install from low to high
| checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
| checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
| checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
| checkpoint |  | Clamps / rings / baskets installed and press into overflows and outlets
| checkpoint |  | Flood test / ILD tested
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Fibertite Warm Roof Over Plywood Checklist |  | Fibertite Warm Roof Over Plywood Checklist | dfd6451f-0f90-4a41-90ce-1c765e8f8380
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Plywood Substrate
| checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
| checkpoint |  | No Screws/nails/fixings poping up
| checkpoint |  | Plywood joints flush and even
| section |  | Vapor Control Layer
| checkpoint |  | Substrate clean, dry, and free of debris
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes/penetrations patched and water tight
| section |  | Insulation
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Vapor control layer has been checked and no damage
| checkpoint |  | Insulation boards installed
| checkpoint |  | Joints flush (no gaps between boards)
| checkpoint |  | Correct length of fixing with load washer if no Securock
| section |  | Securock
| checkpoint |  | Surface is dry prior to install
| checkpoint |  | Installed in brick pattern
| checkpoint |  | Correct length of fixing with load washer
| section |  | Fibertite
| checkpoint |  | Adhesive installed to substrate
| checkpoint |  | Laying of membrane into adhesive
| checkpoint |  | Broom/rolling of membrane
| checkpoint |  | Wipe and clean laps prior to welding
| checkpoint |  | Test weld with the welding machines
| checkpoint |  | Probe of seam with QA hook
| checkpoint |  | Membrane dressed into drains/outlets
| checkpoint |  | Claps/rings/baskets installed
| checkpoint |  | Flood/ILD tested
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - MSR Cladding Checklist |  | MSR Cladding Checklist | e0bfff07-557d-404d-9ae7-3ffe48999d66
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Vapour Control Layer
| checkpoint |  | Substrate clean and ready
| checkpoint |  | All areas covered and sheets lapped 50mm
| checkpoint |  | All holes / penetrations patched and watertight
| section |  | Brackets and Rails
| checkpoint |  | Z brackets installed to fixing plan
| checkpoint |  | Rhom rail installed to fixing plan
| section |  | Insulation
| checkpoint |  | VCL no damage
| checkpoint |  | Insulation installed with no gaps
| section |  | Cladding
| checkpoint |  | Covertek installed with 150mm laps
| checkpoint |  | Starter flashings installed
| checkpoint |  | Soaker flashings installed
| checkpoint |  | Sheets laid straight
| checkpoint |  | Closure foam installed
| checkpoint |  | Correct screw pattern / fixings used
| section |  | Flashings
| checkpoint |  | Installed correctly according to spec and drawings
| checkpoint |  | Fixings according to spec and details
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off
| checklist |  | QA - Metal Roof Installation Checklist |  | Metal Roof Installation Checklist | f033c5ac-4348-4795-8516-5f36666efd32
| section |  | Prestart
| checkpoint |  | Area accessible
| checkpoint |  | Edge protection and safety installed
| checkpoint |  | Substrate complete and ready for SWP
| section |  | Safety Mesh Installation
| checkpoint |  | Laid perpindicular to the purlins.
| checkpoint |  | Fully secured to Purlins/Timber.
| checkpoint |  | No protruding bits or loose ends.
| section |  | Covertek Roofing Paper Installation
| checkpoint |  | Laid either perpindicular or parallel with purlins.
| checkpoint |  | Overlapped a minimum 150mm
| checkpoint |  | All areas completely covered.
| checkpoint |  | Laid tight to timeber/purlins.
| checkpoint |  | Secured so it will not blow away if roof not being installed immediately.
| section |  | Metal Roof Installation
| checkpoint |  | Drip edge installed
| checkpoint |  | Laid straight & perpindicular to gutter/purlins
| checkpoint |  | Gutter overhang 75mm minimum
| checkpoint |  | Top ends of sheets turned up.
| checkpoint |  | Fixings back into purlins and laid in a straight line as per Code of Practice.
| checkpoint |  | Closure foam to gutter ends.
| section |  | Roof Flashings
| checkpoint |  | Installed correctly according to drawings and to the Code of Practice.
| checkpoint |  | All fixings in place and done according to code of practice.
| checkpoint |  | All laps and junctions sealed properly.
| section |  | Review and Sign Off
| checkpoint |  | Area left clean and tidy
| checkpoint |  | All installation work complete, checked and reviewed as per specification
| checkpoint |  | Client / Main Contractor sign off