## Resources
Type | Id | Name | Values | Prompting Name | Resource Id
checklist |  | QA - Sheet Tanking System Checklist |  | Sheet Tanking System Checklist | 14bf945b-4c94-47bb-aafa-a8e9c0ad81f3
section |  | Pre Start
checkpoint |  | Area Accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Primer
checkpoint |  | Applied as per specification on dry substrate at 5m2 per litre
section |  | Membrane
checkpoint |  | Temperature must be over 4 degrees for membrane install
checkpoint |  | Is the substrate clean, dry and clear
checkpoint |  | Membrane applied with min 50mm overlap
checkpoint |  | Overlap is to pressure applied or rolled for seal
section |  | Protection
checkpoint |  | Works to be protected by main contractor
checklist |  | Add Defect Checklist |  | Defect - | 73554810-7587-4136-ab90-0915e9e1dbe2
checkpoint |  | Defect details recorded
textbox | 9b18e909-7530-4d08-ad54-acb417409980 | Explanation of defect:
textbox | 3af60290-922d-4e09-aeb9-b795186cbbd5 | Area:
textbox | da7b5fcc-182d-4ccf-ade5-02dfaae6dedb | Party responsible for damages:
textbox | f37cdc9e-47d2-43c7-b8ce-36034d624bbc | Efforts required for repair:
textbox | 16d78d9b-0a7d-4e07-bb38-68e664e6d30e | Man hours required for repair:
signoff |  | Request Approval from Main Contractor
checkpoint |  | Defect Fixed
signoff |  | Request Defect signoff
checklist |  | FiberTite warm roof to concrete fully adhered checklist |  | FiberTite warm roof to concrete fully adhered checklist | c3cece43-f97a-4ff0-935b-71210a5f8e1c
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Visual inspection of substrate ready for SWP
checkpoint |  | QA document received from previous trade from main contractor
checkpoint |  | Large holes filled with grout by others
checkpoint |  | All lumps and sharp concrete bits ground/hammered down
section |  | Concrete Substrate
checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
checkpoint |  | installation of SA primer
section |  | Vapor control layer
checkpoint |  | Substrate clean, dry, free of debris
checkpoint |  | Z flashing installed
checkpoint |  | Install VCL over primer
checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
checkpoint |  | Installation of SA primer
section |  | Insulation
checkpoint |  | VCL clean, dry, free of debris prior to install
checkpoint |  | VCL has been checked for damages and repaired
checkpoint |  | Closure flashings installed correctly
checkpoint |  | Install board adhesive in specified pattern
checkpoint |  | Specified insulation board installed
checkpoint |  | Boards tightly butted
section |  | ILD system installed
checkpoint |  | ILD System installed as per specs
checkpoint |  | ILD test plate installed
section |  | HDP board
checkpoint |  | PIR clean, dry, free of debris prior to install
checkpoint |  | install board adhesive in specified pattern
checkpoint |  | HDP board installed in brick pattern where possible
section |  | FiberTite
checkpoint |  | Prime substrate where required
checkpoint |  | Adhesive installed to substrate
checkpoint |  | Laying of membrane into adhesive
checkpoint |  | Broom/rolling of membrane
checkpoint |  | Wipe and clean laps prior to welding
checkpoint |  | Test weld with welding machine
checkpoint |  | Probe of seam with QA hook
section |  | Sumps
checkpoint |  | Sealant installed to dropper flange under membrane
checkpoint |  | Membrane dressed in to outlets
checkpoint |  | Clamp/rings/basket installed
checkpoint |  | Flood test
section |  | ILD report
checkpoint |  | ILD report
section |  | Fiberclad flashing
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixing and welding done according to specifications and details
checkpoint |  | Probe of seam with QA hook
section |  | Pressure bar installed
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Over flashings
checkpoint |  | Over flashings has a separation barrier
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Primer of Substrate
checkpoint |  | Sealant installed
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | QA - Torch On Warmroof to Concrete Checklist |  | Torch On Warmroof to Concrete Checklist | 492437f4-cf0e-4a8f-abf1-c7d41c429464
section |  | Pre Start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Concrete
checkpoint |  | Concrete clean and dry. Free from dirt/debris and ready for priming
checkpoint |  | All lumps and sharp concrete bits ground down/hammered down
checkpoint |  | Large holes filled with grout
section |  | Vapour Control Layer
checkpoint |  | Is the substrate clean, dry and clear of swarf
checkpoint |  | All areas covered and sheets lapped 50mm
checkpoint |  | All holes/penetrations patched and water tight
section |  | Insulation
checkpoint |  | Surface is dry prior to install
checkpoint |  | Vapour control layer has been checked for no damage
checkpoint |  | Insulation board installed
checkpoint |  | Joints flush (no gaps between boards on ends)
section |  | Securock
checkpoint |  | Is the surface dry
checkpoint |  | Installed in brick pattern
checkpoint |  | Correct length screw with load washer
checkpoint |  | Prime of Securrock
checkpoint |  | Installed as per wind uplift fixing plan
section |  | Base Sheet
checkpoint |  | Install from low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Check of all welds at the end of the day
section |  | Cap Sheet
checkpoint |  | Install from low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint |  | Clamps / rings / baskets press into overflows and outlets
checkpoint |  | Flood test / ELD tested
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | Metal cladding checklist |  | Metal cladding checklist | ed67e18b-803a-4d65-8934-39976618467d
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Building wrap installed check plans and specifications and QA / handover received from main contactor
checkpoint |  | Battens installed with the correct spacings check plans and specifications QA / handover received from previous trade from main contactor
checkpoint |  | visual inspection by SWP
section |  | Rohm rails Install
checkpoint |  | flashing tape installed check plans and specifications
checkpoint |  | Rohm rails installed with the correct spacings check plans and specifications
checkpoint |  | Rohm rails installed to fixing plan
section |  | Cladding install
checkpoint |  | Cladding installed plump and straight
checkpoint |  | Screw pattern according to plan/specs/best practice
checkpoint |  | Closure foam installed
checkpoint |  | Top end turned up
section |  | Flashing install
checkpoint |  | Sealant installed with 2 continues beads
checkpoint |  | Clean excess sealant
checkpoint |  | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint |  | Flashings installed as per drawings and specifications
checkpoint |  | Fixings installed as per drawings and specifications
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | FiberTite to plywood checklist |  | FiberTite to plywood checklist | d225c5b4-d44f-4e4c-b8e6-3cbe25c1874f
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Visual inspection of substrate ready for SWP
checkpoint |  | QA document received from previous trade from main contractor
checkpoint |  | Visual check no screws/nails/fixings popping up
checkpoint |  | Visual check that joints are flush and even
section |  | Plywood Substrate
checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
section |  | ILD Mesh System installed
checkpoint |  | ILD System installed as per specification
checkpoint |  | ILD test plate installed
section |  | FiberTite
checkpoint |  | Prime substrate where required
checkpoint |  | Adhesive installed to substrate
checkpoint |  | Laying of membrane into adhesive
checkpoint |  | Broom/rolling of membrane
checkpoint |  | Wipe and clean laps prior to welding
checkpoint |  | Test weld with welding machine
checkpoint |  | Probe of seam with QA hook
section |  | Sumps
checkpoint |  | Sealant installed to dropper flange under membrane
checkpoint |  | Membrane dressed into outlets
checkpoint |  | Clamp/rings/basket installed
checkpoint |  | Flood test
section |  | ILD report
checkpoint |  | ILD report
section |  | Fibre clad flashing
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixing and welding done according to specifications and details
checkpoint |  | Probe of seam with QA hook
section |  | Pressure bar installed
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Over flashings
checkpoint |  | Over flashings has a separation barrier
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | QA - Torch on Warmroof Over Plywood Checklist |  | Torch on Warmroof Over Plywood Checklist | b20ca4b3-8468-45f4-b2cd-b483096c3bff
section |  | Pre Start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Plywood
checkpoint |  | Plywood clean and dry. Free from dirt/debris and and ready for priming
checkpoint |  | No screws/nails/fixings popping up
checkpoint |  | Plywood joints flush and even
section |  | Vapour Control Layer
checkpoint |  | Is the substrate clean, dry and clear of swarf
checkpoint |  | All areas covered and sheets lapped 50mm
checkpoint |  | All holes/penetrations patched and water tight
section |  | Insulation
checkpoint |  | Surface is dry prior to install
checkpoint |  | Vapour control layer has been checked for no damage
checkpoint |  | Insulation board installed
checkpoint |  | Joints flush (no gaps between boards on ends)
section |  | Securock
checkpoint |  | Is the surface dry
checkpoint |  | Installed in brick pattern
checkpoint |  | Correct length screw with recessed flat plates
checkpoint |  | Prime of Securrock
checkpoint |  | Installed as per wind uplift fixing plan
section |  | Base Sheet
checkpoint |  | Install from low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Check of all welds at the end of the day
section |  | Cap Sheet
checkpoint |  | Install from low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint |  | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint |  | Flood test / ILD checked
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | Add Final Inspection Checklist |  | Final inspection | 13645b74-c2b0-47f7-bc5b-6d794583dfba
checkpoint |  | Final inspection
textbox | 5c48b2f9-7155-5010-a625-9c61273b1f4a | Date
textbox | cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 | Area/elevation/grids
textbox | f185db39-ef5a-566f-a627-b84ed061402b | Description
note | bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 | Attach Photos
signoff |  | Request Signature Signoff
checklist |  | SYS - PT - Job Details |  | Job Details | aa7e11f7-0e09-4648-9c2b-efe9f8215a7b
checkpoint |  | Site Info
textbox | 4e739149-fe6d-425d-b45e-4a4ff63e7c1e | Site Address
textbox | e326d577-6e3a-40b7-870a-8e178eda7195 | Main Contractor Details
textbox | 6c1ef37c-4d31-4405-b668-f398c4ad1275 | Project Managers Details
textbox | 351c3436-2ae9-42ae-9ee9-1146e81bffa2 | Site Manager Details
checkpoint |  | Latest Drawings
checkpoint |  | Scope of Works Attached
checkpoint |  | Additional Pre Start Docs
checkpoint |  | Fixing Plan Attached
checklist |  | Add Daily Cassette Log |  | Daily Cassette Log - | d887a7ec-32a8-4460-8fd9-2b88cb25d057
checkpoint-no-value |  | Date:
textbox | e5ab19af-90b5-4328-9a8b-ee0707087643
checkpoint-no-value |  | Cassette Number:
textbox | 8e11a44b-51f7-4a8f-9494-ec9e467452ec
checkpoint-no-value |  | Record any delays:
textbox | 22cd20b8-86af-49a9-97d4-39d5b860ca1a
checkpoint-no-value |  | Wind/Weather Conditions:
textbox | 5114a122-dcf7-44a7-be38-8623182196af
checkpoint-no-value |  | Comments/Issues/Observations:
textbox | a6aebd36-6433-4aca-b8f4-ef6216c059cf
checklist |  | Add Variation Checklist |  | Variation Details - | 975c6e74-f00e-4b22-a81f-1bd8fe0954ec
checkpoint |  | Variation Details Approved
textbox | 28d26279-c304-4689-8317-1deb797dc8fe | Reference/Drawing/Instruction Number
textbox | 2247155b-6de8-434c-a1e1-058d724a6a62 | Variation Area
textbox | ae7fc046-dca9-4fab-98f8-374caeb044ec | Materials & labour breakdown
signoff |  | Request Variation Acknowledgement
checkpoint |  | Variation Completed
signoff |  | Request Variation Signoff
checklist |  | MSR checklist |  | MSR checklist | 2266e747-eb08-49d0-82df-b39ada68937b
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Purlins installed and QA / handover received from main contractor
checkpoint |  | visual inspection by SWP
section |  | Liner deck
checkpoint |  | Liner deck fixed down in every purlin and every pan
checkpoint |  | Correct fixing installed
section |  | Vapor control layer
checkpoint |  | Substrate clean, dry, free of debris
checkpoint |  | Z flashing installed
checkpoint |  | VCL installed and covered all surface
checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
section |  | Acoustic board install
checkpoint |  | VCL clean, no ponding water, free of debris prior to install
checkpoint |  | VCL has been cheeked for damages
checkpoint |  | All holes/penetrations patched
section |  | Insulation
checkpoint |  | Boards tightly butted all areas covered
checkpoint |  | Correct insulation installed as per spec
section |  | Underlay installed
checkpoint |  | Correct underlay installed as per specifications
checkpoint |  | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint |  | All areas covered
checkpoint |  | Underlay installed as per specifications
checkpoint |  | Joints taped together as per drawings and specifications
section |  | Metal roof installation
checkpoint |  | Drip edge installed as per drawings and specifications
checkpoint |  | Laid straight and perpendicular to gutter/purlins
checkpoint |  | Gutter overhang as per drawings and specifications
checkpoint |  | Top end turned up
checkpoint |  | Bottom ends turned down
checkpoint |  | Closure foam installed
checkpoint |  | Screw pattern according to plan/specs/fixing plan
section |  | Flashing install
checkpoint |  | Sealant installed with 2 continues beads
checkpoint |  | Clean excess sealant
checkpoint |  | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint |  | Flashings installed as per drawings and specifications and facing away from waterflow
checkpoint |  | Fixings installed as per drawings and specifications
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | Add Dayworks Checklist |  | Dayworks - | 494df41c-3b67-49a7-854f-43800155fade
checkpoint |  | Day Work Details
textbox | d27d8079-cce6-47f2-bc8f-5447bd0b63c3 | NTSC / SI #:
textbox | d63889f7-ee5a-4b1a-8284-614d5f938189 | Labours (HR)
textbox | 926bb36c-59db-4b70-828c-6bc1bf2ce049 | Work Description:
textbox | 693bbb1a-ade5-4140-a549-223cae16f4cb | Materials:
textbox | 6d1abe7d-16c2-45ff-b354-7f74775359b8 | SWP Representative. Prepared By:
textbox | 7e548609-67fa-4b3f-91fa-027d546e556f | Client Representative. Confirmed By:
signoff |  | Request Signature Signoff
checklist |  | QA - Torch On to Concrete Checklist |  | Torch On to Concrete Checklist | f52bcb99-7095-4199-9648-040b808ea31f
section |  | Prestart
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Concrete Substrate
checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint |  | All lumps and sharp concrete bits ground/hammered down
checkpoint |  | Large holes filled with grout
section |  | Prime of Substrate
checkpoint |  | Substrate clean and free from debris
checkpoint |  | Primer installed
section |  | Base Sheet
checkpoint |  | Install from low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Check all welds at the end of the day
section |  | Cap Sheet
checkpoint |  | Install low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint |  | Membrane dressed into drains/outlets
checkpoint |  | Install clamps/rings/baskets
checkpoint |  | Flood/ILD test
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | FiberTite to concrete checklist |  | FiberTite to concrete checklist | e6fc5bbf-349d-49a8-8a58-b398f7032c9b
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Visual inspection of substrate ready for SWP
checkpoint |  | QA document received from previous trade from main contractor
checkpoint |  | Large holes filled with grout by others
checkpoint |  | All lumps and sharp concrete bits ground/hammered down
section |  | Concrete substrate
checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
section |  | FiberTite
checkpoint |  | Prime substrate where required
checkpoint |  | Adhesive installed to substrate
checkpoint |  | Laying of membrane into adhesive
checkpoint |  | Broom/rolling of membrane
checkpoint |  | Wipe and clean laps prior to welding
checkpoint |  | Test weld with welding machine
checkpoint |  | Probe of seam with QA hook
section |  | Sumps
checkpoint |  | Sealant installed to dropper flange under membrane
checkpoint |  | Membrane dressed in to outlets
checkpoint |  | Clamp/rings/basket installed
checkpoint |  | Flood test
section |  | ILD report
checkpoint |  | ILD report
section |  | Fiberclad flashing
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixing and welding done according to specifications and details
checkpoint |  | Probe of seam with QA hook
section |  | Pressure bar installed
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Over flashings
checkpoint |  | Over flashings has a separation barrier
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Primer of Substrate
checkpoint |  | Sealant installed
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | FiberTite warm roof to CLT mechanically fixed and adhered checklist |  | FiberTite warm roof to CLT mechanically fixed and adhered checklist | b7f4e3f2-27dc-4ee0-be04-b383fbe4bc51
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Visual inspection of substrate ready for SWP
checkpoint |  | QA document received from previous trade from main contractor
section |  | CLT Substrate
checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
checkpoint |  | Installation of SA primer
section |  | Vapor control layer
checkpoint |  | Substrate clean, dry, free of debris
checkpoint |  | Z flashing installed
checkpoint |  | Install VCL over primer
checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
checkpoint |  | Installation of SA primer
section |  | Insulation
checkpoint |  | VCL clean, dry, free of debris prior to install
checkpoint |  | VCL has been checked for damages and repaired
checkpoint |  | Closure flashings installed correctly
checkpoint |  | Install board adhesive in specified pattern
checkpoint |  | Boards tightly butted
section |  | Tapered EPS
checkpoint |  | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
checkpoint |  | Install board adhesive in specified pattern
checkpoint |  | EPS board installed into adhesive
section |  | ILD system installed
checkpoint |  | ILD System installed as per specs
checkpoint |  | ILD test plate installed
section |  | HDP board
checkpoint |  | PIR clean, dry, free of debris prior to install
checkpoint |  | Install board adhesive in specified pattern
checkpoint |  | HDP board installed in brick pattern where possible
section |  | FiberTite
checkpoint |  | Prime substrate where required
checkpoint |  | Adhesive installed to substrate
checkpoint |  | Laying of membrane into adhesive
checkpoint |  | Broom/rolling of membrane
checkpoint |  | Wipe and clean laps prior to welding
checkpoint |  | Test weld with welding machine
checkpoint |  | Probe of seam with QA hook
section |  | Sumps
checkpoint |  | Sealant installed to dropper flange under membrane
checkpoint |  | Membrane dressed in to outlets
checkpoint |  | Clamp/rings/basket installed
checkpoint |  | Flood test
section |  | ILD report
checkpoint |  | ILD report
section |  | Fiberclad flashing
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixing and welding done according to specifications and details
checkpoint |  | Probe of seam with QA hook
section |  | Pressure bar installed
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Over flashings
checkpoint |  | Over flashings has a separation barrier
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Primer of Substrate
checkpoint |  | Sealant installed
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
checkpoint |  | Client/main contractor sign off
checklist |  | MSR cladding checklist |  | MSR cladding checklist | 762a81a6-836e-42dc-9144-178bd7decbfa
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Purlins installed and QA / handover received from previous trade from main contractor
checkpoint |  | visual inspection by SWP
section |  | Vapor control layer
checkpoint |  | Substrate clean, dry, free of debris
checkpoint |  | VCL installed and covered all surface
checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
section |  | Rohm rails Install
checkpoint |  | C channel flashings installed
checkpoint |  | flashing tape installed check plans and specifications
checkpoint |  | Rohm rails installed with the correct spacings check plans and specifications
checkpoint |  | Rohm rails installed to fixing plan
section |  | Insulation
checkpoint |  | Boards tightly butted all areas covered
checkpoint |  | Correct PIR installed as per spec
section |  | Underlay installed
checkpoint |  | Correct underlay installed as per specifications
checkpoint |  | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint |  | All areas covered
checkpoint |  | Underlay installed as per specifications
checkpoint |  | Joints taped together as per drawings and specifications
section |  | Cladding installation
checkpoint |  | Starter flashings installed
checkpoint |  | Laid straight and perpendicular to gutter/purlins
checkpoint |  | Top end turned up
checkpoint |  | Closure foam installed
checkpoint |  | Screw pattern according to plan/specs/fixing plan
section |  | Flashing install
checkpoint |  | Sealant installed with 2 continues beads
checkpoint |  | Clean excess sealant
checkpoint |  | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint |  | Flashings installed as per drawings and specifications
checkpoint |  | Fixings installed as per drawings and specifications
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | Xtreme FibreTite Checklist |  | FiberTite Checklist - Area: | 6c249880-08bb-4f25-9a62-60a2a0693ade
section |  | Pre Start
checkpoint |  | Area Accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP (metal/concrete/ply)
checkpoint |  | Perimeter support installed installed if metal deck substrate
section |  | Metal Deck
checkpoint |  | Timber to have separation barrier
checkpoint |  | Base deck screwed down in every pan
section |  | Vapour Control Layer
checkpoint |  | Is the substrate clean, dry and clear of swarf
checkpoint |  | All areas covered and sheets lapped 50mm
checkpoint |  | All holes/penetrations patched and water tight
section |  | Acoustic Board
checkpoint |  | Is the surface dry
checkpoint |  | Installed in brick pattern
checkpoint |  | correct length screw with recessed flat plates
checkpoint |  | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
section |  | Insulation
checkpoint |  | Surface is dry prior to install
checkpoint |  | Vapour control layer has been checked for no damage
checkpoint |  | Insulation board installed in a brick pattern
checkpoint |  | Joints flush (no gaps between boards on ends)
checkpoint |  | Fixings at correct spacing according to spec if no Securock in system.
section |  | HDP Roofboard
checkpoint |  | Is the surface dry
checkpoint |  | Installed in brick pattern
checkpoint |  | correct length screw with recessed flat plates
checkpoint |  | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
section |  | FiberTite
checkpoint |  | Test weld with welding machine
checkpoint |  | Adhesive installed to substrate
checkpoint |  | Laying of membrane into the adhesive
checkpoint |  | Broom/rolling of membrane
checkpoint |  | Wipe and clean of laps prior to welding
checkpoint |  | Probe of seams with QA hook
checkpoint |  | Clamp and weld of outlets and overflows
checkpoint |  | Flood test of outlets
section |  | Fiberclad flashings
checkpoint |  | Installed correctly according to specifications (Right way around)
checkpoint |  | Fixings and welding done according to specifications and details
checkpoint |  | Probe of weld with QA hook
checkpoint |  | Area Complete (Request MC Signoff)
checklist |  | Supplier Site Visit |  | Site Visit date: | 4325987c-5633-429b-b27a-077e0c587ca4
checkpoint-no-value |  | Site Details
textbox | 6d41fa6a-4e1a-577e-a624-6bd736f97876 | Job Name
textbox | 22044acf-ec81-5b86-a826-c71cabe41273 | Who is in attendance
textbox | 1235194d-88da-53a0-854a-ce85145c2b1e | Area/Gridlines/Detail
checkpoint |  | Photos
textbox | e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 | Inspection Notes
signoff |  | Signoff Required
checklist |  | Weather Monitoring |  | Weather Monitoring | 07eb1ba3-8dd4-4850-a104-a46eef91be1b
section |  | Current Weather
checkpoint |  | Wind / weather conditions
checkpoint |  | Record any delays
checkpoint |  | area / gridlines
checkpoint |  | Comments / issues / observations
section |  | Weather Forecast
checkpoint |  | What is the weather forecast this week
checkpoint |  | Record any delays
checkpoint |  | area / gridlines
checkpoint |  | Comments / issues / observations
checklist |  | Metal Roof checklist |  | Metal Roof checklist | 322dd718-0082-4d2d-ac73-00eb7cab9e0e
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Purlins installed and QA / handover received from previous trade from main contractor
checkpoint |  | visual inspection by SWP
section |  | Safety Mesh install
checkpoint |  | Laid and secured perpendicular to the purlins
checkpoint |  | Lap side joins by min 1 grid section
section |  | Underlay installed
checkpoint |  | Correct underlay installed as per specifications
checkpoint |  | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint |  | All areas covered
checkpoint |  | Underlay installed as per specifications
checkpoint |  | Joints taped together as per drawings and specifications
section |  | Metal roof installation
checkpoint |  | Drip edge installed as per drawings and specifications
checkpoint |  | Laid straight and perpendicular to gutter/purlins
checkpoint |  | Gutter overhang as per drawings and specifications
checkpoint |  | Top end turned up
checkpoint |  | Bottom ends turned down
checkpoint |  | Closure foam installed
checkpoint |  | Sheets fixed in to the purlins
checkpoint |  | Screw pattern according to plan/specs/best practice
section |  | Flashing install
checkpoint |  | Sealant installed with 2 continues beads
checkpoint |  | Clean excess sealant
checkpoint |  | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint |  | Flashings installed as per drawings and specifications
checkpoint |  | Fixings installed as per drawings and specifications
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | QA - Carpark MMA Checklist |  | Carpark MMA Checklist | 7727a854-4d78-44b5-a7c8-c1070dc2693f
section |  | Pre Start
checkpoint |  | SSSP onsite
checkpoint |  | Fencing demarcation installed
checkpoint |  | Site signage installed
checkpoint |  | Area Accessible
checkpoint |  | Substrate complete and ready for SWP
section |  | Surface Prep
checkpoint |  | Removal of coatings
checkpoint |  | Grind of substrate
checkpoint |  | Shotblast of substrate to achieve suitable profile
section |  | Pre-start of membrane install
checkpoint |  | Substrate dry
section |  | Membrane install
checkpoint |  | Prime of substrate
checkpoint |  | Stripe out cracks
checkpoint |  | Map out areas based on coverage rates for install
checkpoint |  | Membrane layer installed
checkpoint |  | Wear layer installed and broadcast
checkpoint |  | Excess broadcast swept and removed
checkpoint |  | 1st Top coat
checkpoint |  | 2nd top coat
checkpoint |  | Site cleared and broken down
checkpoint |  | Site cleared and broken down
checklist |  | New Files |  | New Files | 1208f41d-17f6-4182-9ed6-915e22e5c60a
section |  | Details
checkpoint |  | Upload Files
checklist |  | Metal gutter and downpipe checklist |  | Metal gutter and downpipe checklist | 6e0ac8e1-46d4-4b0c-91e8-0496f6cf367a
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Visual inspection of substrate ready for SWP
checkpoint |  | QA document received from previous trade from main contractor
section |  | Gutter install
checkpoint |  | Brackets installed according to drawings and specifications
checkpoint |  | Gutter lapped and sealed correctly according drawings and specifications
checkpoint |  | All terminations and ends folded and sealed
checkpoint |  | Expansion joints installed
checkpoint |  | Expansion joints roof flashings installed
section |  | Downpipe install
checkpoint |  | Correct size dropper installed, riveted and sealed
checkpoint |  | Correct downpipe brackets installed with the correct spacings
checkpoint |  | Down pipe installed plumb and straight
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | SWP - QA - Fibertite Overlay Install Checklist |  | SWP - QA - Fibertite Overlay Install Checklist | aeb13fe5-2eb4-48e2-87c6-8355dd03eb92
section |  | Prestart
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Substrate
checkpoint |  | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
checkpoint |  | Cut back existing roof edge at gutter
checkpoint |  | Remove ridge as we go
section |  | VCL-Vapour Control Layer
checkpoint |  | Surface/Substrate is dry, clean and free from sharp edges
checkpoint |  | All areas covered and lapped a minimum of 50mm
checkpoint |  | All holes/penetrations patched and made watertight
section |  | Roof Pan Infills
checkpoint |  | Surface is dry before installing Poly
checkpoint |  | Infills to be a minimum 5mm above ridges on roof
checkpoint |  | Every pan has been infilled
section |  | Roofboard
checkpoint |  | Substrate/surface dry & clean prior to being installed
checkpoint |  | Installed in brick pattern
checkpoint |  | Correct screws with load washer
checkpoint |  | Installed as per wind uplift fixing plan
checkpoint |  | Install 70mm X 100mm zincalume flashing at gutter edge for strength
section |  | Fibertite
checkpoint |  | Correct Glue being used for substrate
checkpoint |  | Fibertite fully glued to substrate
checkpoint |  | Broom/rolling of fibertite
checkpoint |  | Wipe/clean laps with acetone prior to welding
checkpoint |  | All laps, details, penetrations fully welded/closed and QA'd with hook
checkpoint |  | Clamps / rings / baskets installed
checkpoint |  | Flooded / ILD checked
section |  | Fiberclad Flashings
checkpoint |  | Installed correctly
checkpoint |  | Fixed down according to specification
checkpoint |  | Cleaned down with acetone prior to welding
checkpoint |  | Fibertite fully welded to flashing and QA'd with hook
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | QA - Fiberglass System Checklist |  | Fiberglass System Checklist | 2c08dbad-6330-4798-a61d-92f957abf563
section |  | Prestart
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Surface Prep
checkpoint |  | Concrete free of contaminants
checkpoint |  | Concrete flat and smooth
checkpoint |  | Bug holes in plinths filled and smooth
section |  | Membrane install
checkpoint |  | Install sealant angle fillets to all wall floor junctions
checkpoint |  | Prime surfaces with Epistixx
checkpoint |  | 2nd body coat
checkpoint |  | 3rd body coat
checkpoint |  | Traxx 2000 wear coat.
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | FiberTite to plywood warm roof checklist |  | FiberTite to plywood warm roof checklist | a64d85a0-a6e4-418a-b3ba-2e591de2411a
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Visual inspection of substrate ready for SWP
checkpoint |  | QA document received from previous trade from main contractor
checkpoint |  | Visual check no screws/nails/fixings popping up
checkpoint |  | Visual check that joints are flush and even
section |  | Plywood Substrate
checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for VCL
section |  | Vapor control layer
checkpoint |  | Substrate clean, dry, free of debris
checkpoint |  | Z flashing installed
checkpoint |  | VCL installed and covered all surface
checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
section |  | Insulation
checkpoint |  | VCL clean, dry, free of debris prior to install
checkpoint |  | VCL has been checked for damages and repaired
checkpoint |  | Closure flashings installed correctly
checkpoint |  | Specified insulation board installed
checkpoint |  | Boards tightly butted
checkpoint |  | Fixing plan attached
checkpoint |  | Installed as per fixing plan if no HDP board
section |  | ILD system installed
checkpoint |  | ILD System installed as per specs
checkpoint |  | ILD test plate installed
section |  | HDP board
checkpoint |  | PIR clean, dry, free of debris prior to install
checkpoint |  | Fixing plan attached
checkpoint |  | HDP installed tightly butted in brick pattern
checkpoint |  | Installed as per fixing plan
section |  | FiberTite
checkpoint |  | Prime substrate where required
checkpoint |  | Adhesive installed to substrate
checkpoint |  | Laying of membrane into adhesive
checkpoint |  | Broom/rolling of membrane
checkpoint |  | Wipe and clean laps prior to welding
checkpoint |  | Test weld with welding machine
checkpoint |  | Probe of seam with QA hook
section |  | Sumps
checkpoint |  | Sealant installed to dropper flange under membrane
checkpoint |  | Membrane dressed in to outlets
checkpoint |  | Clamp/rings/basket installed
checkpoint |  | Flood test
section |  | ILD report
checkpoint |  | ILD report
section |  | Fibre clad flashing
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixing and welding done according to specifications and details
checkpoint |  | Probe of seam with QA hook
section |  | Pressure bar installed
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Over flashings
checkpoint |  | Over flashings has a separation barrier
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | Add Delay Checklist |  | Delay Checklist | eaa64fc6-20cd-46d6-8fde-e41383a77674
checkpoint-no-value |  | Delay details.
textbox | ae5b692f-ee75-4a3d-90e7-43a6b2bca49e | Date:
textbox | 8e11a44b-51f7-4a8f-9494-ec9e467452ec | Description:
textbox | 22cd20b8-86af-49a9-97d4-39d5b860ca1a | Area/Grids:
textbox | e5ab19af-90b5-4328-9a8b-ee0707087643 | Wind/Weather Conditions:
checklist |  | QA - Fibertherm Checklist |  | Fibertherm Checklist | a3f7b109-61a3-4212-9d4f-a08941bc2109
section |  | Prestart
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Metal Deck
checkpoint |  | Timber to have separation
checkpoint |  | End openings to have closure foam installed
checkpoint |  | Base deck screwed down in every pan
checkpoint |  | VCL tape to be installed to all sheet laps
checkpoint |  | VCL tape to all upstands
section |  | Post and Rail install
checkpoint |  | Post installed at correct fixing centers
checkpoint |  | Thermal break pad under post foot
checkpoint |  | Rail installed to posts
section |  | Insulation install
checkpoint |  | Specified Insulation installed
checkpoint |  | No Gaps
section |  | Top Deck install
checkpoint |  | Lay sheets straight
checkpoint |  | Hang over into gutter min 75mm
checkpoint |  | Top end of sheets turned up
checkpoint |  | Bottom end of sheets turned down
checkpoint |  | Fixing back to rail
checkpoint |  | Profile washers
checkpoint |  | Screwed off as per fixing plan
section |  | Flashing install
checkpoint |  | Fixings according to specs & details
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | Add Flood Testing Checklist |  | Flood Test Area: | 22c95d72-dcc0-49a3-bdef-bdae9af4b94e
checkpoint |  | Is area fully finished, QA’d and ready to be tested
checkpoint-no-value |  | Flood test details
textbox | dc968f8f-9cf1-485a-a65f-e4087427ee32 | Date:
textbox | b0fb2bc4-3c3c-47bb-93fe-add4a651804d | Area tested:
textbox | befd486d-6456-4e39-ba95-1395566ebfda | Duration:
button | 3fff6840-5866-4f4c-96c8-494f7e9efd79 | Have you checked regularly for leaks | Yes, No, N/A
button | 050fef10-15f2-4590-ba62-2a0b1b1b0a29 | Is there rain in the forecast | Yes, No, N/A
button | b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 | Have all leaks been repaired | Yes, No, N/A
checkpoint |  | Flood test complete
button | 5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 | Have the plugs been removed from the drains | Yes, No, N/A
button | b74c91b9-0371-4641-ad5b-1c9d76ee0c77 | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
signoff |  | Sign Off
checklist |  | FiberTite warm roof to Base deck checklist |  | FiberTite warm roof to Base deck checklist | 5d1ba509-f72f-4af1-ad57-d66bbdb4a955
section |  | Pre start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Visual inspection of substrate ready for SWP
checkpoint |  | QA document received from previous trade from main contractor
section |  | Metal deck
checkpoint |  | Base deck screwed down in every pan and every purlin
checkpoint |  | Base deck laps stitched together at 300mm centres
checkpoint |  | Correct fixing
section |  | Vapor control layer
checkpoint |  | Substrate clean, dry, free of debris
checkpoint |  | Z flashing installed
checkpoint |  | VCL installed and covered all surface
checkpoint |  | VCL lapped with a minimum of 100mm side and end laps
section |  | Insulation
checkpoint |  | VCL clean, dry, free of debris prior to install
checkpoint |  | VCL has been cheeked for damages and repaired
checkpoint |  | Closure flashings installed correctly
checkpoint |  | Specified insulation board installed
checkpoint |  | Boards tightly butted
checkpoint |  | Fixing plan attached
checkpoint |  | Installed as per fixing plan if no HDP board
section |  | ILD system installed
checkpoint |  | ILD System installed as per specs
checkpoint |  | ILD test plate installed
section |  | HDP board
checkpoint |  | PIR clean, dry, free of debris prior to install
checkpoint |  | Fixing plan attached
checkpoint |  | HDP installed tightly butted in brick pattern
checkpoint |  | Installed as per fixing plan
section |  | FiberTite
checkpoint |  | Prime substrate where required
checkpoint |  | Adhesive installed to substrate
checkpoint |  | Laying of membrane into adhesive
checkpoint |  | Broom/rolling of membrane
checkpoint |  | Wipe and clean laps prior to welding
checkpoint |  | Test weld with welding machine
checkpoint |  | Probe of seam with QA hook
section |  | Sumps
checkpoint |  | Sealant installed to dropper flange under membrane
checkpoint |  | Membrane dressed in to outlets
checkpoint |  | Clamp/rings/basket installed
checkpoint |  | Flood test
section |  | ILD report
checkpoint |  | ILD report
section |  | Fibre clad flashing
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixing and welding done according to specifications and details
checkpoint |  | Probe of seam with QA hook
section |  | Pressure bar installed
checkpoint |  | Installed correctly according to specifications ( right way around )
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Over flashings
checkpoint |  | Over flashings has a separation barrier
checkpoint |  | Fixings done according to specifications and details
checkpoint |  | Prime of Substrate where required
checkpoint |  | Sealant installed
section |  | Review and sign off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work completed, checked and reviewed as per specifications
checkpoint |  | Client/main contractor sign off
checkpoint |  | All installation work completed, checked and reviewed as per specifications
signoff |  | Client/main contractor sign off
checklist |  | QA - Fibertite Overlay Install Checklist |  | Fibertite Overlay Install Checklist | f0229a61-4649-41e8-9da5-660770c422df
section |  | Prestart
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Substrate
checkpoint |  | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
checkpoint |  | Cut back existing roof edge at gutter
checkpoint |  | Remove ridge as we go
section |  | VCL-Vapour Control Layer
checkpoint |  | Surface/Substrate is dry, clean and free from sharp edges
checkpoint |  | All areas covered and lapped a minimum of 50mm
checkpoint |  | All holes/penetrations patched and made watertight
section |  | Roof Pan Infills
checkpoint |  | Surface is dry before installing Poly
checkpoint |  | Infills to be a minimum 5mm above ridges on roof
checkpoint |  | Every pan has been infilled
section |  | Roofboard
checkpoint |  | Substrate/surface dry & clean prior to being installed
checkpoint |  | Installed in brick pattern
checkpoint |  | Correct screws with load washer
checkpoint |  | Installed as per wind uplift fixing plan
checkpoint |  | Install 70mm X 100mm zincalume flashing at gutter edge for strength
section |  | Fibertite
checkpoint |  | Correct Glue being used for substrate
checkpoint |  | Fibertite fully glued to substrate
checkpoint |  | Broom/rolling of fibertite
checkpoint |  | Wipe/clean laps with acetone prior to welding
checkpoint |  | All laps, details, penetrations fully welded/closed and QA'd with hook
checkpoint |  | Clamps / rings / baskets installed
checkpoint |  | Flooded / ILD checked
section |  | Fiberclad Flashings
checkpoint |  | Installed correctly
checkpoint |  | Fixed down according to specification
checkpoint |  | Cleaned down with acetone prior to welding
checkpoint |  | Fibertite fully welded to flashing and QA'd with hook
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | QA - Torch on Warmroof Over Metal Deck Checklist |  | Torch on Warmroof Over Metal Deck Checklist | 61392c15-0325-414d-a6c6-107fb38367b2
section |  | Pre Start
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Metal Deck
checkpoint |  | Timber to have separation barrier
checkpoint |  | Base deck screwed down in every pan
checkpoint |  | Sheet edges stitched together at 300mm centres
checkpoint |  | No sharp edges protruding
section |  | Vapour Control Layer
checkpoint |  | Is the substrate clean, dry and clear of swarf
checkpoint |  | All areas covered and sheets lapped 50mm
checkpoint |  | All holes/penetrations patched and water tight
section |  | Insulation
checkpoint |  | Surface is dry prior to install
checkpoint |  | Vapour control layer has been checked for no damage
checkpoint |  | Insulation board installed
checkpoint |  | Joints flush (no gaps between boards on ends)
section |  | Securock
checkpoint |  | Is the surface dry
checkpoint |  | Installed in brick pattern
checkpoint |  | Correct length screw with recessed flat plates
checkpoint |  | Installed as per wind uplift fixing plan
checkpoint |  | Prime of Securrock
section |  | Base Sheet
checkpoint |  | Install from low to high
checkpoint |  | Bleed of bitumen on overlap should be up to 10mm
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Check of all welds at the end of the day
section |  | Cap Sheet
checkpoint |  | Install from low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint |  | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint |  | Flood test / ILD tested
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off
checklist |  | QA - Torch On to Plywood Checklist |  | Torch On to Plywood Checklist | 2f860b6f-9d6b-4b87-8014-05ef3307bb5a
section |  | Prestart
checkpoint |  | Area accessible
checkpoint |  | Edge protection and safety installed
checkpoint |  | Substrate complete and ready for SWP
section |  | Plywood Substrate
checkpoint |  | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint |  | No Screws/nails/fixings popping up
checkpoint |  | Joints flush and even
section |  | Prime of Substrate
checkpoint |  | Substrate clean and free from debris
checkpoint |  | Primer installed
section |  | Base Sheet
checkpoint |  | Install from low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Check all welds at the end of the day
section |  | Cap Sheet
checkpoint |  | Install low to high
checkpoint |  | Side laps a minimum of 80mm and end laps 150mm
checkpoint |  | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint |  | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint |  | Membrane dressed into drains/outlets
checkpoint |  | Install clamps/rings/baskets
checkpoint |  | Flood/ILD test
section |  | Review and Sign Off
checkpoint |  | Area left clean and tidy
checkpoint |  | All installation work complete, checked and reviewed as per specification
checkpoint |  | Client / Main Contractor sign off