## Resources
Type | Id | Name | Values | Prompting Name | Resource Id
checklist |  | Tiling ITP |  | Tiling ITP | 7291579c-a02b-4384-9614-e2f46b21106b
section |  | 1. Check Drawing
checkpoint |  | Confirm Drawing, specification and revision #
note | 771fc7c6-0533-5961-8aab-5f30ea7af078 | Inspection: admin
dropdown | 708d54f9-7e7d-58dc-a948-ba39b5b8959d | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 2. Substrate Prep - Wall
checkpoint |  | Inspect for wall quality to accept tiles and ensure that substrate free from debris
note | 3e04e220-7381-59db-a8bb-ee315341237b | Inspection: visual
dropdown | 28163313-12a9-53f7-bb7f-5a9e21d6f356 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Clean and dry
note | 867a744f-89fb-5344-b051-a7b624bf8ce6 | Inspection: visual
dropdown | 651bb41a-dfa2-5a77-9d57-38046c98385c | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Joints Sealed
note | 28ecc26a-42ec-5f85-8dd5-c6d52a2928bb | Inspection: visual
dropdown | 8418f01f-3d4a-59cd-9629-e291963f6fa6 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 3. Substrate Prep - Floor
checkpoint |  | Inspect concrete substrate free from debris Cracks >0.2mm to be filled with Polyurethane
note | 2a192dec-27eb-5c8c-9132-c8fe70a34be3 | Inspection: visual
dropdown | 71fe2ba5-0f3c-589a-8141-06b03b1ee4c3 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Clean and dry
note | 45867f06-16cf-5329-aab2-9b013c5ab1dd | Inspection: visual
dropdown | de2f9c30-c4d1-59e3-a6f1-a58b93f94590 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 4. Tile Termination Points
checkpoint |  | Locate termination points and set for Angle location at door entry.
note | 20536554-c674-5bae-a156-b4e1b154b6a2 | Inspection: visual / setout / laser
dropdown | f974d1e8-b072-50cc-93e5-9a42650fe874 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Set angle / termination points under door leaf
note | ec4b83c5-8f47-509b-a4a3-f9b472a26e50 | Inspection: visual / setout / laser
dropdown | a15327ea-fd7b-50ba-a8cb-4e82393cbf3e | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Correct RL as per architectural drawings
note | a580c396-3e80-56ee-80a7-23385c33e00f | Inspection: visual / setout / laser
dropdown | 4e351354-120f-54ec-9813-ddcfe1d015fe | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 5. HOLD POINT
checkpoint |  | Waterproofing membrane inspected by Toga and approved to receive screed beds. Check with waterproofer for go ahead
note | 7062d763-f98c-51be-9c74-31523b6bdd84 | Inspection: site foreman / waterproofing contractor
dropdown | 7136c814-ede8-51cc-9963-b5a3dceddc61 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
signoff |  | HOLD POINT
section |  | 6. Sand and Cement Bedding
checkpoint |  | Screed mixed by machine ratio1:4
note | 880e11fd-36f7-5cff-b8d0-48cb8582989a | Inspection: 100L stand mixer
dropdown | 493dce4b-a74d-54fe-a77e-c028e64aa2e8 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Floorwastes protected to prevent debris entering into drains with compressible sponges
note | 7b54c8f2-3fde-53b0-88e3-47bc73e98dbd | Inspection: visual
dropdown | e2c5c680-10e3-58fd-a833-6a96e6bca1ba | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Clearout pipework to finish at screed bed level
dropdown | 25b49733-df46-56fc-86e0-5f0542a6332d | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 7. HOLD POINT
checkpoint |  | Setout and starting point verified with Builder and Drawings
note | d1f74977-6ba4-558c-8bad-7ab77b71bafd | Inspection: laser / visual / chalk line
dropdown | 9bce1a4d-21a7-5140-b053-62560e3c52a3 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
signoff |  | HOLD POINT
checkpoint |  | Ensure standard sceed thickness minimum of 15mm.
note | 5c58317b-b512-5050-8a7b-7ecda328a464 | Inspection: visual / guage
dropdown | ffcb9118-1610-5811-bce5-634bf7ee8c42 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
signoff |  | HOLD POINT
checkpoint |  | Screed areas lower than 15mm to minimum 10mm to recieve engineered binder (Keracem ECO in replacement of Grey cement)
note | 25998d9e-a45f-5a3b-8d5d-d8c4489d64a8 | Inspection: visual / guage / markup
dropdown | c7d0c411-bb4e-5d53-89d0-f4eeec5d41a0 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
signoff |  | HOLD POINT
checkpoint |  | Where screed beds lower than 10mm use Keralevel LR with Universal Primer
note | fb53584d-7dad-595d-964a-b5f03be72d0f | Inspection: visual / guage / markup
dropdown | 9cf2a9d9-0b39-52fc-9e65-45335eece19b | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
signoff |  | HOLD POINT
checkpoint |  | 24hrs curing minimum
note | 1a780cfe-8dae-5e23-97a3-1cd7af689403 | Inspection: visual / guage / markup
dropdown | 1f3d6f04-b78e-52b1-b0fc-e7a3c2a05695 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
signoff |  | HOLD POINT
section |  | 8. Acoustic
checkpoint |  | Ensure substrate free from loose material to maximise bond to acoustic mat / screed bed
note | 4177a373-8c45-51c6-9e01-601cc1e50b67 | Inspection: visual
dropdown | aa6ee990-dcf1-5380-b0b8-a072a912bf49 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 4mm notch trowel / bioflex grey adhesive
note | bff15328-3de2-599f-ac14-052d98ee91fa | Inspection: visual
dropdown | 5423eea7-ad2c-5dc6-8a8d-a6f56fe828c4 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Ensure acoustic matting has no gaps / weighted roller
note | d66784d8-dd94-535e-81f4-92c66d63b119 | Inspection: visual
dropdown | f9be7214-07c5-58ee-9541-67e5a0fe4b3f | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Any gaps to be filled with Polyurethane and finished flush
note | 9dadb359-edc0-5474-97fe-61be2095b9d7 | Inspection: visual
dropdown | 9467e419-69e4-5a9a-b368-1a01e7aadeeb | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 9. Inspect Tile Laying
checkpoint |  | Quality (Set-out, tile cuts, even joints & flatness)
note | aab8532d-4b2a-56ea-b3a0-6538aca4cad8 | Inspection: visual / straightedge
dropdown | 2483f1a3-d336-53cf-bcf7-61daff02d6f6 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Set-out as per drawing
note | 8fd77c76-0e82-5597-9513-a6f9eb4ef778 | Inspection: visual
dropdown | 402c4119-d2d4-5846-832a-f9be58aca75d | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Verify strip drain size and position of waste outlet
note | 87723885-705b-5fa9-9dff-5de99ff57bf6 | Inspection: visual
dropdown | 1e96b90d-34b7-5c2e-84f6-f579cf6feac9 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Falls to waste as per drawing / isolate falls to waste
note | 62545cfc-8d7c-5e10-9662-1902ce4de10b | Inspection: visual
dropdown | 6c47179d-8f8c-551d-8b4a-0d290a2a7843 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | No lipping tiles exceeding A.S tolerances 1.5mm
note | 3afad3cf-4548-58ac-b2d9-b61c27b5c57b | Inspection: visual
dropdown | d3545ece-eab1-50a5-ab8d-0410816415b9 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 10. Preseal
checkpoint |  | General sweep clean of terrazzo floors
note | 3309f117-4908-55c6-b1f5-449ee8936d60 | Inspection: visual
dropdown | fee66047-5b0b-5682-8132-ed1a3a0721dd | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Wet wipe excess dust off tile surface
note | 7b49d7dc-f0e4-5300-aac3-17c42796f99c | Inspection: visual
dropdown | b6fd3da3-d95a-5297-8c7b-11fc157c9dd3 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Lambs wool application of presealer to terrazzo floor surface prior to grouting - 1 coat
note | b5d94f0c-98e0-5457-824a-a79254c644db | Inspection: visual
dropdown | f5bc534c-e9ff-5e60-9891-f1e6cf141324 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Allow preseal to cure minimum 8 hours before grouting. Area to be baricaded off from entering.
note | ec84285b-c4d7-5010-9c8c-f2787dc98261 | Inspection: visual
dropdown | 42fc9028-5a85-582b-b7c7-ba8ad10744db | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 11. Grouting
checkpoint |  | Grout mixed by machine
note | 8eefe2f8-c703-5593-ae0f-b69a0652244a | Inspection: visual
dropdown | f332ff09-da0a-5988-a38c-49a95df250e1 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Joints free from debris / spacers
note | 5ac36d27-72b5-5445-9605-08d90f9bbcf5 | Inspection: visual
dropdown | 7cbe8798-b0f0-5baf-9575-26245048d01a | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Surface is uniform and clean / no grout build up / internal corners free of grout
note | df5bb407-c65e-50d0-83c6-d6c1404d00e8 | Inspection: visual
dropdown | 3d146264-f327-5567-a8ec-0c5fcd28717b | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 12. Protection
checkpoint |  | Corflute taped down (no black corflute) cover entire tiled surface
note | e1dbcf2b-b24b-5c80-ac59-1b913dc204ed | Inspection: visual
dropdown | f4d2d48f-9795-5beb-889e-c02b8619f35d | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | Make allowance for toilet pans, partitions / glass installation
note | 45f82cfb-38e8-54a2-a0c6-1077f57a2782 | Inspection: visual
dropdown | 9d0f249d-d8ef-520e-a9da-497007ed4fbd | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section |  | 13. Repair Any
checkpoint-no-value |  | Repair Any
section |  | 14. Final Inspection
checkpoint-no-value |  | Final Inspection
textbox | 7b0fb972-c0f9-5334-b9bd-01bbd0ec6ac5 | Position:
date | 27888008-0d64-57a9-9d5c-18387395c5ab | Date:
signoff |  | Prepared By:
checklist |  | Waterproofing ITP |  | Waterproofing ITP | 7e2f745e-19a2-4457-a483-48d4ada29313
section |  | Details
checkpoint |  | 1. Waterproofer to inspect substrate to confirm acceptability. Ensure clean, dry, devoid of contamination and excess dust removed and vacuumed.
note | 9bdf6290-8d7b-5159-abea-7411c74c4d02 | Inspection: visual
dropdown | 0e8ea806-4589-58a5-b398-69fcb61fdc65 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 2. Fillet bond breaker using Aquastop 70 tape and Nanosil to improve adhesion. Ensure all tape is bonded to the substrate.
note | e0da82ac-5aa3-55ac-b18d-30ee6c8c9965 | Inspection: visual
dropdown | c370b75e-14fb-5e5c-87f1-3808071a089a | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 3. Polyurethane fillet to internal vertical corners in shower, at junction of concrete with puddleflange, clearout, pipework
note | e44b8ba1-950a-585c-bf7c-298671727745 | Inspection: visual
dropdown | 2c7e41f2-01e2-5172-a71c-4f2919cdeb50 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 4. Primer A Eco to be applied to porous substrate (Data Sheet attached) All concrete and wall linings
note | 566d87d0-f07e-532f-96a5-dd178e9baaf1 | Inspection: visual
dropdown | 840dd0d9-5330-5fb0-9547-16891ff84732 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 5. Prime Keragrip Eco for non porous primer (Data sheet attached) Angles, puddlefalnges, threaded pipework
note | 765f12c5-f1a0-5c0e-ac57-f252e7ea980d | Inspection: visual
dropdown | b1ddf47f-fb74-5f7e-a85c-c034faa3c637 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 6. 1st Coat Kera Trade WPM (Data Sheet attached) Applied to floor, 150mm high including perimeter banding and 200mm above shower rose and extending 200mm past shower screen location. Extend to vanity 150mm min. surround to side and above vanity shelf. Extend 150mm below level of vanity.
note | ced7c6d1-587e-5b12-8f25-5130c34e6425 | Inspection: visual
dropdown | 0c64e9be-81a5-5655-8e38-5d6e3c3ab940 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 7. 24hr Curing (Typical*) *curing time are typical, refer to manufacturer spec for product curing times
note | b3f85187-ab13-57e3-a814-5b2926d560a5 | *curing time are typical, refer to manufacturer spec for product curing times
note | f39fdbb5-c41a-5480-a5b1-cb985bbe6082 | Inspection: visual and touch
dropdown | 457cebc4-3a7a-5c39-822b-a8e74c6a6a46 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 8. 2nd Coat Keratrade WPM applied
note | ccd984b9-4190-5aee-88b9-fca4cb71bffa | Inspection: visual and touch
dropdown | 7b160cd5-bf99-50e9-b393-82b2ff31e49b | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 9. 48hr Curing (Typical*)
note | 2ad89966-0978-508b-9791-6beb167e2f5c | *curing time are typical, refer to manufacturer spec for product curing times
note | f45d3cd0-7369-50d1-861c-fbda48b52a88 | Inspection: visual and touch
dropdown | 25b9702b-8839-5f52-be19-dff94964069b | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 10. Dry Film Thickness (DFT) Test completed min 1.13mm
note | 9a94ca08-23d1-5b99-9238-e748891ca09a | Inspection: electronic testing
dropdown | c732c0c5-4d4d-5901-81e4-615931c5deaa | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 11. 24hr Water Test
note | 365778d1-ae72-5890-83eb-5703e1a4bb30 | Inspection: visual and marker
dropdown | 69aace4b-9ea0-52ec-8775-9fdcf9e10838 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 12. Final Water Test Measure Completed - AS3740-2010
note | 1cffe44d-85e4-5b37-aa30-299f2f2cddf7 | Inspection: visual
dropdown | dbd87837-0d66-5053-bb8d-2bbb7c13bcee | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint |  | 13. Drain Down by waterproof installer
note | 762a48d1-3237-51d6-bd3d-f12d8c4d9d1b | Inspection: visual
dropdown | 6cd87419-ae69-5f81-8562-86e1274f5c70 | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
signoff |  | 14. Waterproof installer to check / provide go ahead
section |  | 15. RECTIFICATION ITEMS
checkpoint |  | RECTIFICATION ITEMS
checkpoint |  | 16. Area Handover to Tiler
signoff |  | Verify with Tiler
section |  | 18. Quality Assurance from Builder
checkpoint |  | Quality Assurance from Builder
section |  | 19. Final Inspection
checkpoint |  | Final Inspection (1)
textbox | 1edad775-33be-5322-90aa-69d710a4ba23 | Position:
date | 2a740eae-0a90-5bea-aafd-a08705a22266 | Date:
signoff |  | Prepared By:
checkpoint |  | Final Inspection (2)
textbox | c4f50682-cbed-5c75-9f72-b1e48a745922 | Position:
signoff |  | Approved By:
checklist |  | Add Time Sheet |  | Time Sheet | 99f2569f-42bf-4ae8-a149-7abdba16a78d
section |  | Time Sheet
checkpoint-no-value |  | Details
date | 94e47690-8b1c-58ca-b139-ef69a8b4a3d3 | DATE:
textbox | dcf6be24-6f16-5941-923a-f0f8f6fab18e | CLIENT:
textbox | 3dc1a08d-45b6-50ce-a2be-18e20db89e7a | SITE:
textbox | ec67f581-1cb5-5c42-a028-ffa5f227853c | SITE INST. NO:
checkpoint-no-value |  | DETAILS OF WORKS
textbox | f2b4650e-05ce-54c3-82b8-3c7870b3440f | Description of works carried out:
textbox | 27c1fb72-ea0e-5239-a7ac-49212cd89858 | Reasons for works that have been carried out:
textbox | 009ade48-ec88-5b35-a525-349460bdb6b0 | Areas where works have been carried out:
checkpoint-no-value |  | Photo of area before works carried out
checkpoint-no-value |  | Photo of area after works carried out
checkpoint-no-value |  | LABOUR
textbox | 998972e4-ec92-57e6-aa81-0555f8d8f885 | (1) Dates:
number | a14a2e6b-5963-5b97-91e8-9aaf09ff60a2 | (1) HOURS
textbox | 5e7415de-0232-5378-93f2-3ceab4720597 | (2) Dates:
number | abe30f6b-0724-5df1-a964-42648b81a75a | (2) HOURS
textbox | 56b6b6c2-7a8a-50ce-a2cd-2eb710568d51 | (3) Dates:
number | 88cf6357-edc1-5527-9013-b3c92fa2257f | (3) HOURS
textbox | e6cc7f55-5577-57b6-a15c-f2bb29166a93 | (4) Dates:
number | a5d206d8-585a-55fe-9ad2-721ae11a88e3 | (4) HOURS
textbox | 5b1c5cde-f0e7-5db8-8208-a9965d469406 | (5) Dates:
number | 9b650f26-7b97-5c98-a833-86fde6db2ba9 | (5) HOURS
textbox | 6408649b-32b3-5236-a8bc-b992c0c4028c | (6) Dates:
number | 40c17368-75f0-5cc5-b06b-27a3db6a7c6d | (6) HOURS
checkpoint-no-value |  | MATERIALS
textbox | 1803dece-bf56-5d6f-9ab3-a26dadc35f73 | (1) MATERIAL USED
number | d91b9c8f-aa1f-5650-bf43-7586a661fe3c | (1) QTY
textbox | 07476e4f-45c0-53c2-9d39-9b38edcd3331 | (2) MATERIAL USED
number | 46042b3d-4435-5c9d-9a4f-981b8056ea35 | (2) QTY
textbox | 7e21d221-fc8c-579f-aad9-6cc858430f15 | (3) MATERIAL USED
number | 72e215e9-094a-54a9-bbe5-c490b4bd27e3 | (3) QTY
textbox | 17ecff9d-2859-5ec5-8184-0e6cec315bc1 | (4) MATERIAL USED
number | 6171903d-cef5-51f2-9a8b-d65cc957e4a5 | (4) QTY
textbox | 700534f8-9ca2-57b5-986f-786d7b8d9e12 | (5) MATERIAL USED
number | 3e6c1b0e-f99b-5888-862c-7131238903f4 | (5) QTY
textbox | 870e9171-5d72-5c78-bd73-f12b9fa3e54b | (6) MATERIAL USED
number | 603010f2-5545-557e-8432-525ca243d2f7 | (6) QTY
checkpoint-no-value |  | ACCEPTANCE
note | 998972e4-ec92-57e6-aa81-0555f8d8f885 | Teammembers Project P/L
textbox | a14a2e6b-5963-5b97-91e8-9aaf09ff60a2 | NAME
signoff |  | SIGNATURE