## ITP Cover Page
Acoustic Improvements - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 015 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | 015
Project Number: |  |  | DN1210 - SP2 |  |  |  |  | ITP Status: |  |  | Approved - Issued for Construction
ITP Description: |  |  | Acoustic Improvements |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | LTO Agreements (763, 765, 767, 769, 773, 1064 SH29)
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract spec
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Approved | 2024-11-27 |  | Cordelia Girdler-Brown |  | Draft for Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [5 empty] | Downer PM |  | Nick Adams
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 28/01/2025 | Downer QM |  | Cordelia Girdler-Brown
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body_BC
Acoustic Improvements - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 015 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | PRE-CONDITION SURVEYS
| Pre- Construction Surveys | Photographic record and inspection of existing property conditions prior to the commencement of works. | Building Report | PS 2.9 | Building Report | Prior to commencement of works | ENG | HP
3.2 | MATERIAL - WINDOW & DOOR FIT-OUT
| Omega Windows & Doors | Product specifications to meet the requirements of WSP's acoustic survey of each property. | Engineer's Approval | Signed LTOs & Acoustic Property Surveys | Manufacturer's data sheet and Engineers approval | Prior to commencement of works | ENG | HP
3.3 | MATERIAL - DOUBLE GLAZING
| Kiwi Double Glazing | Product specifications to meet the requirements of WSP's acoustic survey of each property. | Engineer's Approval | Signed LTOs & Acoustic Property Surveys | Manufacturer's data sheet and Engineers approval | Prior to commencement of works | ENG | HP
3.4 | MATERIAL - VENTILATION
| DVS Ventilation | Product specifications to meet the requirements of WSP's acoustic survey of each property. | Engineer's Approval | Signed LTOs & Acoustic Property Surveys | Manufacturer's data sheet and Engineers approval | Prior to commencement of works | ENG | HP
SECTION 4 – POST CONSTRUCTION (HANDOVER)
| QA Check list | QA checklist covering the extents of all the work including the openings of windows & doors, new doors & windows, double glazing installation, ventilation system, installation & painting. | All the scope of works stated in the signed LTO's of each residential property will be visually inspected. | Signed LTOs & Acoustic Property Surveys | QA checklist Visual Inspection | Pre-construction During construction Post- construction | WP | SE