## ITP Cover Page
Wetlands 02 Earthworks - Inspection and Test Plan
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - SP2 - 019-REV0 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project SP2 |  |  |  |  | ITP Number: |  |  | SP2 - 019-REV0
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Approved - IFC
ITP Description: |  |  | Wetland 02 Earthworks |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STW, 23273502-WSP-DR-GEO, 2-32735.02-WSP-DR-UDL
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specification
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-12-12 |  | Cordelia Girdler-Brown & Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved - IFC | 20/01/2025 |  | Cordelia Girdler-Brown & Nick Adams and WSP |  | As per NTC-0398 - ITP item no 2.1.4 - Full grading requirements to be listed. ITP item no 3.2 - material testing items to be added to ITP item no 4.1 - Insitu testing missing from ITP ITP Item no 4.1.2 - minimum requirement should be 3 blows not 4/100mm ITP item no 6 - update title of section |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 28/01/2025 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Wetlands 02 Earthworks - Inspection and Test Plan
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - SP2 - 019-REV0 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
1.1 | GENERAL
1.1.1 | Earthworks Methodology | The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to Earthworks | HP | ENG
1.1.2 | Ecology Sign Off | Confirmation from Ecology that earthworks can proceed | Email | Internal Hold Point | Email from Ecology NZ | Prior to Earthworks | H | SE
1.1.3 | Erosion & Sedimentation Controls | Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding | As-built Completed | Internal Hold Point | ESC As-built | Prior to Earthworks | H | SE
1.2 | DESIGN
1.2.1 | Design | Ensure that Design is approved and Drawings are of the latest revision | Visual inspection by Engineer | Internal hold point | Check Drawing Register | Prior to Earthworks | C | SE
|  | Site check for service features, any required design amendments to be resolved on site | Visual inspection by Engineer | Internal hold point | Engineer notified of design amendments to be resolved | Prior to Earthworks | C | SE
SECTION 2 | IMPORTED MATERIAL TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
2.1 | RIP RAP ROCK TESTING
2.1.1 | Weathering Index of Coarse Aggregate | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA to CA | NZS4407:2015 Test 3.11 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
2.1.2 | Crushing Resistance of Course Aggregate | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | > 150kN | NZS4407.3.10 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
2.1.3 | Solid Density of Aggregate | NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles | ≥ 2.65 tonnes per m3 | NZS4407.3.7.1 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
2.1.4 | Grading | NZS4407:2015, Test 3.8.2 - Grading of Aggregates by method of dry sieving. | Sieve Size % Passing 230.0mm 85% passing 150.0mm 50% passing 95.0mm 15% passing | NZS4407.3.8.2 PS 21.5.14 | IANZ Accredited Report | Percentage Passing %50 | HP | ENG
2.1.5 | Point Load Strength | ASTM-D5731: 2017, Standard Test Method for Determination of the Point Load Strength Index of Rock and Application to Rock Strength Classifications | >1.5 MPa | ASTM D5731 PS 21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
2.1.6 | UCS Rock | AS4133.4.2.1: 2022, Method 4.2.1: Rock strength tests – Determination of uniaxial compressive strength | >30 Mpa | AS4133.4.2.1 PS21.7.4 | IANZ Accredited Report | 1 per 1000m3 | HP | ENG
2.2 | TCC-AP65-2 SOURCE MATERIAL TESTING
2.2.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of 100kN | NZS4407:2015 Test 3.10 TCC-IDC-IT-4.3.1-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.2.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | ≥60% | NZS4402 Test 3.15 TCC-IDC-IT-4.3.1-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.2.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, CA or CB | NZS4407 Test 3.11 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.3 | TCC-AP65-2 PRODUCTION MATERIAL TESTING
2.3.1 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 63.0mm 100% passing 37.5mm 68-90% passing 19.0mm 42-76% passing 9.5mm 26-58% passing 4.75mm 16-44% passing 2.36mm 10-33% passing 1.18mm 6-24% passing 0.425mm 3-14% passing 0.075mm 1-6% passing | NZS4407 Test 3.8.1 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
2.3.2 | Shape Control | Tolerance allowed from approved grading curve (%) | Sieve Size % Tolerance 37.5 – 9.5 34-50% 19.0 – 4.75 18-40% 9.5 – 2.36 12-32% 4.75 – 1.18 6-24% 2.36 – 0.6 2-20% 1.18 – 0.3 0-15% 0.6 – 0.15 0-12% | TCC-IDC IT-4.7.2 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
2.3.3 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4407 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.3.4 | The Solid Density | NZS 4407:1991 Test | Report Value Only | NZS4407 TNZ B/02:2005 7.5 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.3.5 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | ≤ 8 | NZS4407:2015 Test 3.4 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.3.6 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent Washing method | ≥25 | NZS4407 Test 3.6 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
2.7 | Geotextile
2.7.1 | Geotextile | The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. Class D | Engineers Approval | PS 16.5.7 Appendix V | Delivery Docket/Material certificate | Results to Engineer for Approval | HP | ENG
SECTION 3 | Imported/Site Won Material Testing - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.1 | SITE TOPSOIL
3.1.1 | Laboratory Testing for Soil Suitability | Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse Soil Reaction Electrical Conductivity Mechanical Analysis (texture) Stone Content Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium Organic Matter Content Check for Toxic or Hazardous substances | Engineers Approval | NZTA P39:2013 3.1 | Laboratories Test Report | 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling | I | SE
3.2 | SITE WON MATERIAL (TYPE A2 NON-GRANULAR)
3.2.3 | Maximum dry density optimum water content air voids and shear vane strength (su) with range of mositure contents | NZS4402:1986 test 4.1.2 heavy compaction test | Results from test | Appendix XVIII | Report | 1 set (3 tests) per material type and source | HP | ENG
3.2.7 | Organic content | Visual observation | Fill shall be free from organic, calcareous or other deleterious materials | Appendix XVIII | ConQA | Fill shall be free from organic, calcareous or other deleterious materials | HP | ENG
3.2.8 | Soil Permability | maximum soil permeability | 10-7 m/s | PS:16.5.5 Appendix XVIII | Report | 1 Test Per Source | HP | ENG
3.2.9 | Liquid limit | liquid limit | less than 65% (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.10 | Moisture content | maximum moisture content | 6 % above (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.11 | Prohibitied materials | deleterious materials | Not containing allophane, organics or other deleterious materials. (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
SECTION 4 | ACCESS TRACK
4.1 | SUBGRADE
4.1.1 | Subgrade Level Confirmation | Confirm subgrade is 400mm from finished height | String lines - or equivalent are 400mm +0mm/-30mm Tolerances width -20mm +100mm | PS 20.14.5 | Survey as-builts | Every 20m chainage | I | SE
4.1.2 | Subgrade CBR Testing | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | CBR >7 Min 3 blows / 100mm | PS 27.4.2 Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE
4.1.3 | Subgrade CBR Testing | "NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level" Hand auger hole is required | "Average Minimum SU: > 60kPa Single Test Min SU: >50kPa 2-3m deep " | PS 27.4.2 Appendix XVIII | Shear Vane Report | 4 test per 400M2 | I | SE
4.1.4 | Proof Roll | Visual Inspection of Proof Roll | Displacement <15mm | Appendix XVIII | Visual Observation | Across stripped area | I | SE
4.2 | SUBGRADE LIFT
4.2.1 | Subgrade CBR Testing | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | Min 2 blows / 100mm | Appendix XVIII | Scala Report | 4 test per 400M2 | HP | ENG
4.2.2 | Subgrade CBR Testing | "NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level" Hand auger hole is required | Average minimum Su > 80kpa Single test minimum Su > 60 | Appendix XVIII | Shear Vane Report | 1 set (5 test) per 500m3 of fill placed per area worked per day per lift | HP | ENG
4.2.3 | Bulk desnity, Dry density, Air voids | NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density | Results from test | Appendix XVIII | Report | 1 Test performed for every 10 NDM | HP | ENG
4.2.4 | Water content | NZS4402:1986 - Test 2.1 water content | Results from test | Appendix XVIII | Report | 1 set (5 test) per 200m3 of fill placed per area worked per day per lift | HP | ENG
4.2.5 | Insitu density insitu compacted dry density insitu water content | NZS4407:2015 – test 4.3 nuclear moisture density gauge (ndm), direct transmission mode | Average maximum air voids < 8% Single test maximum air voids < 10% | Appendix XVIII | Report | 1 Set (5 Test) per200m3 | HP | ENG
4.2 | HOLD POINT
4.2.1 | QA Submission | Submit all Subgrade QA before proceeding with next pavement layer | Engineers Approval | Appendix V | Conqa Siggnoff | Once | HP | ENG
4.3 | GEOTEXTILE FABRIC
4.3.1 | Placement of Geotextile Fabric | Place Geotextile Fabric Strength Class D across pavement area, with 500mm overlaps | Visual inspection | 232735.02-WSP-DR-STW 0302 | Visual Inspection and photos | During construction | WP | ENG
4.4 | SUBBASE (TCC AP65-2)
4.4.1 | 3m Straight Edge | Formation check to ensure surface is smooth | +/- 15mm | PS 27.4.1 | Check Sheet | Every 20m Centres 1 each lane | I | SE
4.4.2 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | String lines - or equivalent are 150mm +5mm/-25mm | TNZ B/02:2005 5.1 232735.02-WSP-DR-STW 0302 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.4.3 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | TNZ B/02:2005 7.5 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
4.5 | HOLD POINT
4.5.1 | QA Submission | Submit all Subbase QA before proceeding with next pavement layer | Engineers Approval | Appendix V | All test reports Material Test Results Laboratory MDD NDM results | Once | HP | ENG
4.6 | Finish (TCC AP65-2)
4.6.1 | 3m Straight Edge | Formation check to ensure surface is smooth | +/- 15mm | PS 27.4.1 | Check Sheet | Every 20m Centres 1 each lane | I | SE
4.6.2 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | String lines - or equivalent are 150mm +15mm/-5mm | TNZ B/02:2005 5.1 232735.02-WSP-DR-STW 0302 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.6.3 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >98% of MDD Min >95% of MDD | TNZ B/02:2005 7.5 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
4.7 | HOLD POINT
4.7.1 | QA Submission | Submit all Subbase QA before proceeding with next pavement layer | Engineers Approval | Appendix V | All test reports Material Test Results Laboratory MDD NDM results | Once | HP | ENG
SECTION 5 | EARTHWORKS
5.1 | EXCAVATION
5.1.1 | Subgrade Level Confirmation | Confirm subgrade is 300mm below from finished height | String lines - or equivalent are 300mm +0mm/-30mm Tolerances width -20mm +100mm | PS 20.14.5 | Survey as-builts | Every 20m chainage on all major contours | I | SV
SECTION 6 | FOREBAY
6.1 | TOPSOIL LAYER
6.1.1 | Checking of levels | Confirm that the thickness of the riprap is 300m | String lines - or equivalent Tolerances width -20mm +100mm | TNZ B/02:2005 5.1 | Survey as-builts | Every 20m chainage on all major contours | I | SV
6.2 | ROCKLINED FOREBAY
6.2.1 | Placement of Geotextile Fabric | Place Geotextile Fabric Strength Class D across pavement area, with 500mm overlaps | Visual inspection | PS: 21.5.15 | Visual Inspection and photos | During construction | W | ENG
6.2.2 | Checking of levels | Confirm that the thickness of the riprap is 300m | String lines - or equivalent Tolerances width -20mm +100mm | TNZ B/02:2005 | Survey as-builts | Every 20m chainage on all major contours | I | SV
SECTION 7 – AS-BUILTS
7.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. |  | PS 16.7.6 | Survey Records/ Redpen markups | Post Earthworks | D | SV
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mention the specification item here not internal hold point
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure why this is a hold point for a Quality Manager to Quality Engineer - this should be for the Environmentalist to sign off
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as above
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where are the testing requirements specifies for Rip Rap rock?
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: please note the items I added to item 2.1.1 and 2.1.2 there needs to be those details here,
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: where is this section from? if its the standard/specification please add it to the next column
Note on B69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As above: is AP40 required?
Note on B81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check also the requirements of PS 16.6.4f)