## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-015 ITP Acoustic Improvements | itp |  |  |  |  | DN1210-SP2-015 ITP Acoustic Improvements Rev 0
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | Pre-Construction Surveys
label | Detail - Photographic record and inspection of existing property conditions prior to the commencement of works.
label | Acceptance / Conformance Criteria - Building Report
label | Standard / Specification - PS 2.9
label | Verifying Document - Building Report
label | Testing Quantity Required (based from schedule qtys) - Prior to commencement of works
label | Verification Activity: Activity - ENG
label | Verification Activity: By - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Omega Windows & Doors
label | Detail - Product specifications to meet the requirements of WSP's acoustic survey of each property.
label | Acceptance / Conformance Criteria - Engineer's Approval
label | Standard / Specification - Signed LTOs & Acoustic Property Surveys
label | Verifying Document - Manufacturer's data sheet and Engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to commencement of works
label | Verification Activity: Activity - ENG
label | Verification Activity: By - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Kiwi Double Glazing
label | Detail - Product specifications to meet the requirements of WSP's acoustic survey of each property.
label | Acceptance / Conformance Criteria - Engineer's Approval
label | Standard / Specification - Signed LTOs & Acoustic Property Surveys
label | Verifying Document - Manufacturer's data sheet and Engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to commencement of works
label | Verification Activity: Activity - ENG
label | Verification Activity: By - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | DVS Ventilation
label | Detail - Product specifications to meet the requirements of WSP's acoustic survey of each property.
label | Acceptance / Conformance Criteria - Engineer's Approval
label | Standard / Specification - Signed LTOs & Acoustic Property Surveys
label | Verifying Document - Manufacturer's data sheet and Engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to commencement of works
label | Verification Activity: Activity - ENG
label | Verification Activity: By - HP
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – POST CONSTRUCTION (HANDOVER)
checkpoint | QA Check list
label | Detail - QA checklist covering the extents of all the work including the openings of windows & doors, new doors & windows, double glazing installation, ventilation system, installation & painting.
label | Acceptance / Conformance Criteria - All the scope of works stated in the signed LTO's of each residential property will be visually inspected.
label | Standard / Specification - Signed LTOs & Acoustic Property Surveys
label | Verifying Document - QA checklist, Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Pre-construction, During construction, Post- construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP2-019 ITP Wetlands 02 Earthworks | itp |  |  |  |  | DN1210-SP2-019 ITP Wetlands 02 Earthworks Rev 1
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - Earthworks Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Ecology Sign Off
label | Detail - Confirmation from Ecology that earthworks can proceed
label | Acceptance / Conformance Criteria - Email
label | Standard / Specification - Internal Hold Point
label | Verifying Document - Email from Ecology NZ
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 1.1.3 - Erosion & Sedimentation Controls
label | Detail - Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 1.2.1 - Design
label | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | Acceptance / Conformance Criteria - Visual inspection by Engineer
label | Standard / Specification - Internal hold point
label | Verifying Document - Check Drawing Register
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 1.2.1 - Design
label | Detail - Site check for service features, any required design amendments to be resolved on site
label | Acceptance / Conformance Criteria - Visual inspection by Engineer
label | Standard / Specification - Internal hold point
label | Verifying Document - Engineer notified of design amendments to be resolved
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
section | SECTION 2 – IMPORTED MATERIAL TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
checkpoint | 2.1.1 - Weathering Index of Coarse Aggregate
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - NZS4407:2015 Test 3.11 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.2 - Crushing Resistance of Course Aggregate
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - > 150kN
label | Standard / Specification - NZS4407.3.10 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.3 - Solid Density of Aggregate
label | Detail - NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles
label | Acceptance / Conformance Criteria - ≥ 2.65 tonnes per m3
label | Standard / Specification - NZS4407.3.7.1 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.4 - Grading
label | Detail - NZS4407:2015, Test 3.8.2 - Grading of Aggregates by method of dry sieving.
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 230.0mm ¦¦ 85% passing
label | 150.0mm ¦¦ 50% passing
label | 95.0mm ¦¦ 15% passing
label | Standard / Specification - NZS4407.3.8.2, PS 21.5.14
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Percentage Passing %50
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.5 - Point Load Strength
label | Detail - ASTM-D5731: 2017, Standard Test Method for Determination of the Point Load Strength Index of Rock and Application to Rock Strength Classifications
label | Acceptance / Conformance Criteria - >1.5 MPa
label | Standard / Specification - ASTM D5731 PS 21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.6 - UCS Rock
label | Detail - AS4133.4.2.1: 2022, Method 4.2.1: Rock strength tests – Determination of uniaxial compressive strength
label | Acceptance / Conformance Criteria - >30 Mpa
label | Standard / Specification - AS4133.4.2.1 PS21.7.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 100kN
label | Standard / Specification - NZS4407:2015, Test 3.10, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥60%
label | Standard / Specification - NZS4402, Test 3.15, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, CA or CB
label | Standard / Specification - NZS4407, Test 3.11, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407, Test 3.8.1, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.3 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.4 - The Solid Density
label | Detail - NZS 4407:1991 Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407, TNZ B/02:2005 7.5, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.5 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - ≤ 8
label | Standard / Specification - NZS4407:2015, Test 3.4, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.6 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent Washing method
label | Acceptance / Conformance Criteria - ≥25
label | Standard / Specification - NZS4407, Test 3.6, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7.1 - Geotextile
label | Detail - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. Class D
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7 Appendix V
label | Verifying Document - Delivery Docket/Material certificate
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 3 – Imported/Site Won Material Testing - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
checkpoint | 3.1.1 - Laboratory Testing for Soil Suitability
label | Detail - Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse
label | ○ Soil Reaction
label | ○ Electrical Conductivity
label | ○ Mechanical Analysis (texture)
label | ○ Stone Content
label | ○ Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium
label | ○ Organic Matter Content
label | ○ Check for Toxic or Hazardous substances
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - NZTA P39:2013 3.1
label | Verifying Document - Laboratories Test Report
label | Testing Quantity Required (based from schedule qtys) - 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.3 - Maximum dry density optimum water content air voids and shear vane strength (su) with range of mositure contents
label | Detail - NZS4402:1986 test 4.1.2 heavy compaction test
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (3 tests) per material type and source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Organic content
label | Detail - Visual observation
label | Acceptance / Conformance Criteria - Fill shall be free from organic, calcareous or other deleterious materials
label | Standard / Specification - Appendix XVIII
label | Verifying Document - ConQA
label | Testing Quantity Required (based from schedule qtys) - Fill shall be free from organic, calcareous or other deleterious materials
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.8 - Soil Permability
label | Detail - maximum soil permeability
label | Acceptance / Conformance Criteria - 10-7 m/s
label | Standard / Specification - PS:16.5.5 Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.9 - Liquid limit
label | Detail - liquid limit
label | Acceptance / Conformance Criteria - less than 65% (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.10 - Moisture content
label | Detail - maximum moisture content
label | Acceptance / Conformance Criteria - 6 % above (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.11 - Prohibitied materials
label | Detail - deleterious materials
label | Acceptance / Conformance Criteria - Not containing allophane, organics or other deleterious materials. (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – ACCESS TRACK
checkpoint | 4.1.1 - Subgrade Level Confirmation
label | Detail - Confirm subgrade is 400mm from finished height
label | Acceptance / Conformance Criteria - String lines - or equivalent are 400mm +0mm/-30mm
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - PS 20.14.5
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Subgrade CBR Testing
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - CBR >7
label | ○ Min 3 blows / 100mm
label | Standard / Specification - PS 27.4.2 Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Subgrade CBR Testing
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | ○ Hand auger hole is required
label | Acceptance / Conformance Criteria - Average Minimum SU:
label | ○ > 60kPa
label | Single Test Min SU:
label | ○ >50kPa
label | ○ 2-3m deep
label | Standard / Specification - PS 27.4.2 Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Proof Roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Displacement <15mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Subgrade CBR Testing
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - Min 2 blows / 100mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.2 - Subgrade CBR Testing
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | ○ Hand auger hole is required
label | Acceptance / Conformance Criteria - Average minimum Su > 80kpa
label | ○ Single test minimum Su > 60
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 test) per 500m3 of fill placed per area worked per day per lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.3 - Bulk desnity, Dry density, Air voids
label | Detail - NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test performed for every 10 NDM
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.4 - Water content
label | Detail - NZS4402:1986 - Test 2.1 water content
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 test) per 200m3 of fill placed per area worked per day per lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.5 - Insitu density insitu compacted dry density insitu water content
label | Detail - NZS4407:2015 – test 4.3 nuclear moisture density gauge (ndm), direct transmission mode
label | Acceptance / Conformance Criteria - Average maximum air voids < 8%
label | ○ Single test maximum air voids < 10%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Set (5 Test) per200m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.1 - QA Submission
label | Detail - Submit all Subgrade QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Conqa Siggnoff
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.1 - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class D across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - 232735.02-WSP-DR-STW 0302
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 4.4.1 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 15mm
label | Standard / Specification - PS 27.4.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.2 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - String lines - or equivalent are 150mm +5mm/-25mm
label | Standard / Specification - TNZ B/02:2005 5.1 232735.02-WSP-DR-STW 0302
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.3 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - TNZ B/02:2005 7.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5.1 - QA Submission
label | Detail - Submit all Subbase QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - All test reports, Material Test Results, Laboratory MDD, NDM results
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.1 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 15mm
label | Standard / Specification - PS 27.4.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.6.2 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - String lines - or equivalent are 150mm +15mm/-5mm
label | Standard / Specification - TNZ B/02:2005 5.1 232735.02-WSP-DR-STW 0302
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.6.3 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >98% of MDD
label | ○ Min >95% of MDD
label | Standard / Specification - TNZ B/02:2005 7.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.7.1 - QA Submission
label | Detail - Submit all Subbase QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - All test reports, Material Test Results, Laboratory MDD, NDM results
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – EARTHWORKS
checkpoint | 5.1.1 - Subgrade Level Confirmation
label | Detail - Confirm subgrade is 300mm below from finished height
label | Acceptance / Conformance Criteria - String lines - or equivalent are 300mm +0mm/-30mm
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - PS 20.14.5
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage on all major contours
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
section | SECTION 6 – FOREBAY
checkpoint | 6.1.1 - Checking of levels
label | Detail - Confirm that the thickness of the riprap is 300m
label | Acceptance / Conformance Criteria - String lines - or equivalent
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - TNZ B/02:2005 5.1
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage on all major contours
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 6.2.1 - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class D across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - PS: 21.5.15
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 6.2.2 - Checking of levels
label | Detail - Confirm that the thickness of the riprap is 300m
label | Acceptance / Conformance Criteria - String lines - or equivalent
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - TNZ B/02:2005
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage on all major contours
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
section | SECTION 7 – AS-BUILTS
checkpoint | 7.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records/ Redpen markups
label | Testing Quantity Required (based from schedule qtys) - Post Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature