## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
4e42662c-0246-50cf-9247-900e66f49620 | checklist | Approved Design Report |  | Approved Design Report
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b34ac1ea-d920-54d9-9cd9-6c1faf4fa917 | checkpoint | Approved Design Report
a71d059d-9c7d-5222-852c-85cdde0b9d72 | checklist | Approved JMF |  | Approved JMF
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4a55af90-a9e7-5799-bd27-12753cdd6d7b | checkpoint | Approved JMF
af676baa-217b-5fa8-b3ed-139f819d6b53 | checklist | Chipseal ITP | itp | Chipseal ITP
d04147a8-3cd0-5cdc-acfb-a50a5713f5bb | section | 1.0 Pre-Works (Off Site)
12cb7714-09d2-51ee-8cd2-eeff3cbc58d2 | checkpoint | Binder Penetration Grade
6ada9a68-cd62-55d7-90b0-62a7484914c7 | note | Type - T
43283828-8a11-549c-8eed-5f343b660603 | note | Reference or Specification - NZTA M1
684fe87e-7414-5d97-a2ff-995db4a68fa4 | note | Method/Test Required - Property Test, NZTA M01
b295356c-7a5c-5df9-aa57-9e14b0e8caa9 | note | How Often? - 1 test certificate per bulk shipment
2f5fa047-49f6-5054-9f97-19c12131ed14 | note | Records Required - Test Report
321adfdb-3319-5984-b004-fbb85372c971 | note | Responsibility - Bitumen Supplier / Project Manager
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
bd3d71ef-c3bc-583b-83d6-74723da2118e | note | Type - I
f9773ce5-6ccf-5503-a2fc-a16c4627954f | note | Reference or Specification - NZTA P/17, M06
920b33dc-051b-5235-8f1a-21d93e9984b9 | note | Method/Test Required - Sample Test - Cleaness Value, NZTA P/17, M06
61c02b17-b93e-5b4d-9b5f-b3d76db8c04d | note | How Often? - Each Stockpile
93a192b1-5ed8-57b4-bf26-768ccb40174b | note | Records Required - Test Report
3980ed84-1e4d-577b-ae2c-2f172c789fdf | note | Responsibility - Project Manager / Renewals Manager
d510b888-7ac4-5a5a-9001-107c5a01424d | checkpoint | Stakeholder Management Requirements met
126b76ea-e90b-55eb-8c76-95fb8014be7f | note | Type - H
9c1dcff6-80dc-533d-b118-cc86a258b856 | note | Reference or Specification - CSCMP
ebab0faf-858a-5828-b7b7-e9b752d19790 | note | Method/Test Required - Confirm requirements followed
d0d91543-e6e5-5b5d-8087-a252b351a916 | note | How Often? - Each site
d83d6cdd-a8c1-59b6-8208-747eae056440 | note | Records Required - Test Report
f732a913-daf0-53f1-b4bd-0141d9782f52 | note | Responsibility - Project Manager / Renewals Manager
cb8f9138-18e8-518b-9cfb-c3084f87e9ca | signoff | HOLD POINT
0348475e-2ecb-4b52-a0e1-8549bd3f9a67 | checkpoint | Stakeholder Management Requirements met
48a43283-f617-5ea5-a54c-9e134eba2cb2 | note | Type - H
702b39a9-e49e-54ba-866e-6080d5636c29 | note | Reference or Specification - CSCMP
b0ddc931-1575-59fb-b1c5-3067abd826da | note | Method/Test Required - Confirm requirements followed
672b6015-6e02-5810-860d-f68810b42ff0 | note | How Often? - Each site
55d319fa-43ac-5bfe-bf4b-e33176fe4f30 | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
f38e328c-faf6-5d87-a762-0429c4fd1fb8 | note | Responsibility - Project Manager / Renewals Manager
43607efe-fcd0-5bde-b80e-5ab360a32ff7 | signoff | HOLD POINT
20a2f0eb-8a85-4bb2-bcb3-ec0347a34441 | checkpoint | Stakeholder Management Requirements met
488457fb-bac4-5e7e-b883-beea6640cd65 | note | Type - H
93ffe116-d48a-560a-92a1-a62cd767c498 | note | Reference or Specification - CSCMP
ea0c4bbe-a5e1-5562-b09c-c2bd76715b83 | note | Method/Test Required - Confirm requirements followed
4607899f-35d9-5609-ad2b-2d6390a0b494 | note | How Often? - Each site
4de551fe-d8e1-51d1-ad1e-a8ee02f20fb9 | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
38fd9906-4ab1-5b4a-bb7b-9a9af0f552a9 | note | Responsibility - Project Manager / Renewals Manager
ee4c2813-4a94-59d0-bced-ab325be99d78 | signoff | HOLD POINT
4e7da939-9cca-5c1d-84ce-e9e823e26a7a | checkpoint | Confirm if any environmental protection is required
ba69855c-e1af-50a6-a37c-7a84a312cb32 | note | Type - I
490b5c99-5ea8-5879-af43-0bef34848e47 | note | Reference or Specification - ESMP
f02e79be-80bc-5fcb-98ba-30e5298e1666 | note | Method/Test Required - Record decision
a1fcf265-7d19-5e7c-a8c8-617815d62bfc | note | How Often? - Each site
c544dffa-f627-5489-a975-ee2ffc211b88 | note | Records Required - Pre-seal Inspection Form
7b30a37e-5fb3-56ec-9a39-a5d65ec70789 | note | Responsibility - Project Manager
68c679e2-0df7-514d-b7e6-5ba6b03dca52 | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
c435b3e2-2592-5230-bd95-6a70a3cd2e5b | note | Type - H
7c25c85f-af37-5615-a396-3de5e104c3b3 | note | Reference or Specification - QMP
9da6338e-48bb-5116-8a1b-6b8a681de71a | note | Method/Test Required - Brief all team members on day’s work plan
6164a820-cc18-5ab4-b900-d08820c9a50d | note | How Often? - Each site
e214cf45-f04a-5aa1-a5c7-d05f90cd27e0 | note | Records Required - Pre-seal Inspection Form
5236ee3b-df2b-5887-85c5-f22963ff4a3a | note | Responsibility - Project Manager
3dbdf597-75a7-5f4c-b3b0-be881617e898 | signoff | HOLD POINT
7e43cd03-2461-5d0b-be20-b98dbed56896 | section | 2.0 Pre-Construction (On Site)
6f355f2c-df11-59ed-bd97-25b614509738 | checkpoint | Job start, identify risks and controls, communicated to team
4b4d90ee-cb36-52d9-a3e0-2731acec4901 | note | Type - H
cd3cf8c0-7f3f-59b8-bb02-ec8d360ca393 | note | Reference or Specification - HSMP
4b7532a3-e908-510f-bb71-9899d1a4ad85 | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
122386ca-71d6-5c8e-96eb-c4c5f5061ae0 | note | How Often? - Each site
dc9c94c8-7fac-506e-b062-8f05b0c7b165 | note | Records Required - Hazard ID form
e5bf5c66-add4-5e95-b72f-0379d5d62c67 | note | Responsibility - Site Foreperson
1343757c-7bab-5f16-9893-71c8c675b1b0 | signoff | HOLD POINT
39b3ac28-bb99-5723-a25d-70f5fe36ee0f | checkpoint | Establish traffic management to plan
07971abd-88df-50ba-b6d2-f081eb4c8cb2 | note | Type - H
8dfc76b4-7458-5df8-88e9-95f8d3ba5267 | note | Reference or Specification - TMP
c1e505c5-3141-517a-8478-ac5e76a6635a | note | Method/Test Required - Site audit post set up
9fb16562-b14d-56bf-846d-4468f1de5ebf | note | How Often? - Each site
55bed5f6-f304-524b-86ca-bbff99b5dd3f | note | Records Required - TTM Diary
333c41d2-62ec-57a5-a4e2-c03daa7c1e3b | note | Responsibility - STMS
38c57964-067f-571d-b082-eaaefae973fb | signoff | HOLD POINT
10f90953-b533-5814-b439-c82c6371befa | checkpoint | Confirm site is on approved programme
cf5b7b43-fc16-5a44-8bad-11d6bb7bd96f | note | Type - H
cfacd089-2b99-561b-96bb-42e92b7ff2be | note | Reference or Specification - Approved Programme
7c99e3a5-f04c-54bb-9a44-46f5767007ed | note | Method/Test Required - Record as-built site dimensions
58dea1e3-8cd8-527a-8c0a-f9fd517ce280 | note | How Often? - Each Site
4f695334-1413-5638-bfd2-b5b702a6cde5 | note | Records Required - Pre-seal Inspection Form
6fe0ceaa-320f-5ba2-8783-13ccfbd3bfd3 | note | Responsibility - Site Foreperson
04fe20a7-45bf-5a6e-b3c3-4c7affb1c531 | signoff | HOLD POINT
35073b60-6504-591b-a727-aa666a6293ce | checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
cdff5c5f-9fd5-59af-a2d4-54122b29b152 | note | Type - H
6401f005-dd45-5d0b-a794-52d0edea6179 | note | Reference or Specification - Approved Programme
8100df10-f5c7-5892-a4b8-a98086f97ec1 | note | Method/Test Required - Record as-built site dimensions
ceb15530-f1c1-57e5-a19e-273a706c8125 | note | How Often? - Each Site
f8b6e84b-df83-5ade-99f3-7c3f1c80d6f3 | note | Records Required - Pre-seal Inspection Form
d82da7c1-b263-5344-a7ca-493b23e9c3c2 | note | Responsibility - Site Foreperson / Site QA
2058fd33-e7e9-5d68-8176-bdfaeb18defe | signoff | HOLD POINT
b54d216a-ba1a-59c0-bb34-1e8bd557fb6c | checkpoint | Stockpiled sealing chip is clean and suitable for sealing
ce8d1750-2208-5a00-aa4c-02f64a6ad528 | note | Type - H
f8e29351-b074-5051-85d5-136c112c390e | note | Reference or Specification - QMP
179820b6-3d22-5225-904f-c3469c214859 | note | Method/Test Required - Acceptable/Unacceptable
5a392190-2d92-5786-a3d1-2d0534dddf64 | note | How Often? - Each Stockpile
46703324-d4e5-5d7b-b35b-043ac16c0b0f | note | Records Required - Pre-seal Inspection Form & Photograph
f1c6a000-23cf-5923-b8f7-4abc76c16559 | note | Responsibility - Site Foreperson / Site QA
b8eae8b5-10a9-5d73-9061-39c58dcdaa0a | signoff | HOLD POINT
9828576b-31a1-5461-840d-ad39228d9afc | checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
ce62ee55-6ed3-50be-8786-e9e64a3c7f7d | note | Type - H
1acb56ca-43a5-54ad-ae19-4bfd3f2e9dfe | note | Reference or Specification - QMP
c09018c4-f279-537b-8345-6df1106c2323 | note | Method/Test Required - Acceptable/Unacceptable
5743e528-0873-5316-9659-ffd4f449dbe6 | note | How Often? - Each Stockpile
63545db3-17af-5ae6-aae7-5bcfa721612f | note | Records Required - Pre-seal Inspection Form
ca6a4d1e-158c-5980-a37e-58ab1e3b3577 | note | Responsibility - Site Foreperson / Site QA
c67c73a6-7d36-5f8b-9040-5c9e771cd702 | signoff | HOLD POINT
1c841a6d-fc29-56e9-95b3-246f43cbb01d | checkpoint | Record & photograph environmental protection measures installed
ec380566-0cd2-5714-9fd1-8946bf01bc03 | note | Type - I
8462ea6f-0876-50ff-ba63-d7282033e112 | note | Reference or Specification - ESMP
8e052287-6eca-5087-85d0-7bbf10d4a5c9 | note | Method/Test Required - Record temporary measures
f4abb034-66cc-55a9-a169-83bf20e07802 | note | How Often? - Each site
d328af19-c594-52da-a234-fd4cf0b5e838 | note | Records Required - Pre-seal Inspection Form & Photograph
14f9c03c-57e7-549a-94c3-0bf47bdc70d1 | note | Responsibility - Site Foreperson / Site QA
f70db8e6-421d-5131-bcbc-8063acb80ebf | checkpoint | Binder application rate
aa54ca0a-6440-5868-9a25-1e5737978321 | note | Type - T
ff5cb513-3ac4-5e49-a60c-832e2c7a1ece | note | Reference or Specification - Seal Design / Spraying Insructions
aec3c1f1-d7bb-5678-aa92-acc97ca62210 | note | Method/Test Required - Confirm seal design requirements from programme
6ba9d6d5-ee46-568e-b2c4-1566e4a6ee92 | note | How Often? - Per site
fdef347d-5464-5b8c-969f-942c899872a8 | note | Records Required - Spray Sheet
e68a0b5b-bcac-58a2-a0d1-5bf36703627b | note | Responsibility - Site Foreperson / Site QA
16168148-ed93-5376-b0b2-0496c84e6649 | checkpoint | Pre-Sealing surface condition
8145b914-b30a-5817-84e1-82736206be62 | note | Type - I
147021d7-1efe-5509-a4ce-3e9db78d0dbf | note | Reference or Specification - QMP
23629807-4e6d-533a-b045-a5eb4a9bfdba | note | Method/Test Required - Acceptable/Unacceptable
1bd6ded7-ee03-5dc3-897c-a28ee6767bb8 | note | How Often? - Per Site
b59abe95-f2c4-5188-9f84-2b78f00cc259 | note | Records Required - Pre-seal Inspection Form & Photograph
20566797-ac2a-5d61-9f67-cd1e2cafcf6e | note | Responsibility - Site Foreperson / Site QA
59026fbf-8bf0-561d-b8fa-b9d1d14b1af3 | section | 3.0 Construction
a5c298e0-f827-57b8-af21-551c58c5500e | checkpoint | Start spraying Temp >10°C
9ce0e83c-950f-5688-b0e9-ade54eee8ead | note | Type - T
8f32a86c-1ecb-5d07-a3da-583eca0188fd | note | Reference or Specification - NZTA P/17
a0d9842c-3ac5-5c1c-97fa-72a100a3fb63 | note | Method/Test Required - Start >10°C
23ad09b4-50e8-5712-af76-5b6ff476a7da | note | How Often? - Per site
a54846ae-f54a-5872-a550-140b289a9549 | note | Records Required - Spray Sheet
a69acf50-a904-5037-a4c5-e27557114790 | note | Responsibility - Site Foreperson / Site QA
8fb925e5-cccf-53af-b469-f8a5b5e02830 | checkpoint | Binder application variation
41396e9e-486a-598f-8d6b-7bfc32169995 | note | Type - T
b0a49af3-c2a7-5514-9574-f9985da40f92 | note | Reference or Specification - NZTA P/17
7bf66f0b-5afb-5d64-8c5d-7bb39083b2d9 | note | Method/Test Required - +/- 4% (spray rate)
50593310-6212-5b55-a34a-5fbd1eb39480 | note | ○ +/- 50l (tank dip)
4cf1de33-0956-582a-931e-f63b7c8b9f36 | note | How Often? - Per site
e7b8a9c1-42c5-582d-b621-e3f566f83839 | note | Records Required - Spray Sheet
b7e8706c-c22d-501b-bf38-21eb62d39deb | note | Responsibility - Site Foreperson / Site QA
caa733b6-3591-5558-96ab-e053ff0b3924 | checkpoint | Sealing chip application
f847689b-d226-5f0c-89a7-4fa16e334e17 | note | Type - I
f5587512-bc01-5666-bd07-788b6cfe056c | note | Reference or Specification - NZTA P/17
e877f5ca-b934-53a5-8867-9a607686ecbc | note | Method/Test Required - Full and even coverage of sprayed area
6f48a3a5-9495-560b-8e7e-f3c72fcbf125 | note | How Often? - Per site
eb2205b4-d2e7-52b9-878d-c1462c54e6e8 | note | Records Required - Post-seal Inspection Form
ddc2439d-473d-5dc6-8ce3-09aa1bde38f7 | note | Responsibility - Site Foreperson / Site QA
c1972697-70e0-5da8-8c51-1f976797e889 | checkpoint | PTR Rolling pattern
de709e7a-ffc4-5549-b3e5-a59059a5451e | note | Type - I
97138fbb-7a12-51c6-a737-4fd1b434985c | note | Reference or Specification - NZTA P/17
43c7a34b-ff3d-58e4-ad8f-5e272adf6ad2 | note | Method/Test Required - Initial rolling completed along with traffic- rolling under controlled TTM
370f4e3d-96a9-5b6c-a047-3e35b43a5326 | note | How Often? - Per Site
97000c60-184a-5148-a746-295abfa5e605 | note | Records Required - Post-seal Inspection Form
b0dfc191-1670-56e3-87a5-377c6a583dda | note | Responsibility - Site Foreperson
f114a9a5-6d3a-590b-90c9-8576a9d77b4c | checkpoint | Traffickating
2ce63054-e437-5a24-bbba-24bad7671541 | note | Type - I
7a503f4a-8a97-55a3-9bfc-90565bd6a94a | note | Reference or Specification - Chapter 11 - Chipsealing in NZ
6888a3ba-73df-5dbe-901a-cd6169aecf40 | note | Method/Test Required - Initial rolling completed along with traffic- rolling under controlled TTM
64604757-55ba-57d6-a74a-aad3e15f4665 | note | How Often? - Per Site
76aa1134-d120-5fa9-bfa0-ed5b8a19c573 | note | Records Required - Post-seal Inspection Form
bbb2a0ef-5151-594f-99e6-ce5cbe1a564b | note | Responsibility - Site Foreperson / STMS
46ae9207-177b-4759-849d-d0278eafc582 | checkpoint | Traffickating
38cc7ff8-ea37-572f-9ca1-b331859f20ba | note | Type - I
ca2752d8-6891-5ea1-a623-da89e39d2c21 | note | Reference or Specification -
764b499b-be4a-5d0c-95cf-81efd087cf46 | note | Method/Test Required - Positive Traffic Control is to remain in place for at least 6 hours after the last chip run is complete, the positive TC is to move the traffic across the full width of the road to ensure full chip imbedment
7b3aa640-71a6-580e-ad90-07ce045a413a | note | How Often? - Per Site
37ac953c-2e04-5ce5-9908-83d8bc200091 | note | Records Required - Post-seal Inspection Form
2f791a7f-5cee-5a68-8396-c008810ee410 | note | Responsibility - Site Foreperson / STMS
b23f8b7f-71a2-5c83-9d73-6bdb9524b41d | checkpoint | Tagging for line marking
b1a1d143-16eb-5999-9f13-d11727c7a25b | note | Type - I
1fbd02b3-29cd-54f4-a98f-99df2e178085 | note | Reference or Specification - Chapter 11 - Chipsealing in NZ
3cdb774f-d39d-54c0-93bf-cd205e9bffcc | note | Method/Test Required - Pre-seal Visual check
8a16df8c-7220-571c-bba7-ab8a78d4b9f9 | note | How Often? - Per site
69d66546-cb40-54f9-863c-e570427f6d56 | note | Records Required - Post-seal Inspection Form
0b69bcc9-a450-5b0b-9cd3-37f30a590093 | note | Responsibility - Site Foreperson
e4d0a871-a7da-5e96-9e88-9ec6465111d6 | checkpoint | Post-Sealing Surfacing Condition
66866640-c807-5500-8fc3-8363dd38aee1 | note | Type - I
8f965fe9-29d9-5f68-b04a-cbd8de4a761c | note | Reference or Specification - QMP
81dfb045-5b98-59a9-a520-18f465a69ecd | note | Method/Test Required - Visual check
62174d4d-2b9a-5246-86bb-75a819a34588 | note | How Often? - Per site
8e9fd821-89a3-5367-b4e2-4b11d8237f5c | note | Records Required - Post-seal Inspection Form & Photograph
c0c3eb77-a375-5204-99cc-1ebeb4e6b051 | note | Responsibility - Site Foreperson
041895cb-bf17-548c-813a-80c54acc65fe | section | 4.0 Post-Construction
33b84639-aa8b-5019-b6fb-c520effb3f69 | checkpoint | Linemarking and RRPM Reinstated: Matches previous linemarking - within 48 hours of sealing
ecc99839-17c3-52f3-83e3-fa325cceef69 | note | Type - H
6955d83b-7ac0-50ad-bdfa-7d67745f3231 | note | Reference or Specification - MOTSAM
78dcd705-26f1-5565-bd53-2b7cd158d96f | note | Method/Test Required - Visual check
590f37dd-cb8f-53b5-ab6b-f3bed10b2c2f | note | How Often? - Per site
a6204fd0-4349-5d91-9bb5-a10d6e8496f2 | note | Records Required - Photograph
b985aae0-184e-5b6e-bbaa-fc4395c1f2fc | note | Responsibility - Project Manager
eb787fc6-bb44-514e-996c-505eef1b238a | signoff | HOLD POINT
33e806a9-191e-5eb0-b4e2-08b194d00d21 | checkpoint | Spray Sheet/s Checked & Supplied for Claiming
a7afb8dd-8d5c-512f-be9f-bbf5fa8cdd49 | note | Type - H
a5321786-1100-52bb-b1f5-a448c5fcbda8 | note | Reference or Specification - QMP
a5fcbb1b-7116-58a7-92d4-cabeca67df0b | note | Method/Test Required - Spray sheet data verified against design/programme
f9ca1326-1018-5edd-92d1-7af34ebb17ef | note | How Often? - Per site
e8c49fc5-4307-5955-b047-64a3fd4efa4e | note | Records Required - Spray Sheet/s
c4c21f45-fe5c-5bc8-a056-5f8b0ce218d9 | note | Responsibility - Project Manager
fb1154c2-1642-5760-b614-848abe796d6c | signoff | HOLD POINT
c1b63417-4e8f-5678-8d80-db4ef1de7e20 | checkpoint | Collect & Upload RAMM data
142d9e90-e9b5-5341-a13c-0cf1fef9e3b6 | note | Type - H
ce323526-c0e3-5d8e-bd68-3fab85366bd2 | note | Reference or Specification - Comply with Waka Kotahi format
1644933e-ca31-5808-a82c-cc53c4cbd9bf | note | Method/Test Required - Correct data supplied
4a91688f-3a6a-5b67-827e-63b9e7bc6b00 | note | How Often? - Per site
b2c32ffe-8aac-5faf-91fe-351e1d8c6c60 | note | Records Required - Spary Sheet/s & Photographs
588f7894-fc1b-5ecd-8a32-a27683d7c5d6 | note | Responsibility - Renewals Manager
f0742716-4a16-5135-93b9-76341616685b | signoff | HOLD POINT
b9c83b9e-13c0-5d06-b178-9f23237abb7f | section | 5.0 Out Of Season Sealing
40235823-5a4c-5575-9e93-16eafa87d306 | checkpoint | Out of Season Sealing
7ea23f76-9dab-5e53-9af4-655ead0c8832 | note | Type - H
0f27b004-8ca6-59a3-bf46-96f3fecb417a | note | Reference or Specification - Winter Surfacing Site Note
145ceb2a-05ce-5d64-a4ec-dc094350bc81 | note | Method/Test Required - Waka Kotahi Approval
123455f9-cfe0-5fae-b04e-5d1e96a03b18 | note | How Often? - Per Applicable Site
3c9553ae-9458-5f5a-a5ba-60b54094d549 | note | Records Required - Copy of Waka Kotahi Approval on- site
48625dca-45e5-50c1-a664-f61eaa20cf49 | note | Responsibility - Project Manager / Renewals Manager
159c744e-3320-5eb3-925b-681ea72394c2 | signoff | HOLD POINT
f7060e2d-d700-5b94-8045-203e59e5ae52 | checklist | ITP - Pavement Rehab - SH 02 - Apanui Road East |  | ITP - Pavement Rehab - SH 02 - Apanui Road East
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
09dfa698-6b7f-519e-b940-013fd716a19e | checkpoint | Design - Geometric Design
a4972593-7418-5488-a12b-71ec42b5ba8d | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
219c8ad2-7a91-5b33-a715-82c5d3087570 | note | Acceptance Criteria - Principal Approval
c3dbf441-54c0-595a-8c72-d93b68fa691f | note | Method - Contractor and Principal peer review
76612ce4-6b60-5856-87be-9547a9935d82 | note | Frequency - per design revision
698ac8e7-bc3c-573b-a76c-30a0069855db | note | Conduct - C or S
81ecf535-083e-5530-82c6-2a236195b375 | note | Produce Record - C
b853c828-d5a7-5e4e-83c9-a50675855d76 | note | Approval - E
34a44c2d-db4e-5cb6-96dd-bb79bff0fe67 | note | Hold Point Y/N - Y
734b8921-df80-5868-90e2-320abcb6aec9 | signoff | HOLD POINT
fc457da0-71e7-5429-a676-cfa9f8ad8762 | checkpoint | Design - Pavement Treatment Design
842a56dd-9abd-5139-804c-b162e0978965 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
38aa067d-758e-573b-9d41-854a86b3a9ad | note | Acceptance Criteria - Principal Approval
5fe04562-7803-533d-8e6c-7e209436ceac | note | Method - Contractor and Principal peer review
7d97a569-3d4a-5836-b469-4ea5a2a6d894 | note | Frequency - per design
5115e985-c2fa-53c9-80b7-240778999f71 | note | Verifying Document - Pavement Rehabilitation Design Report
e0aa86dc-2be0-59ab-89a6-c3b04f0668c9 | note | Conduct - C or S
7248badb-6fe3-51cb-92f2-accabf113364 | note | Produce Record - C
ec54e177-4d07-5aa7-a121-80fbc598cccb | note | Approval - E
bc2f23fd-f81d-5bc6-9e84-d6263cb1e387 | note | Hold Point Y/N - Y
f7622f1f-ef56-5ab3-b6af-8b3b9e5d5f72 | signoff | HOLD POINT
36362436-b1e4-5e95-af81-437ff9bbd938 | checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
72e10f1e-86fd-51a1-9a6e-16d44fcb9056 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
55fd2e66-a5ae-5755-8e0c-27918bca9b39 | note | Verifying Document - Sampling Worksheet
68150f9d-4eb3-5214-9ba4-7bb36ee6a43e | note | Conduct - C or S
1cea0e99-b39b-56f6-8f56-0ee6203ce180 | note | Approval - S
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
eee6de1f-f43b-5674-a5b0-62871dce59c8 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
da2ce39f-da98-5c65-93fa-e5c4267a48ea | note | Acceptance Criteria - Soaked CBR ≥ 40
a3c09993-e6a0-5484-8167-c4fc32786a76 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
d56bd3df-dc59-5848-acf4-22bda6809864 | note | Responsible Person - Supervisor
3e3dffdd-b76c-5c4c-8819-1229d39faf00 | note | Verifying Document - Test Report
d0cc3a50-b387-574b-882c-8668e21deebb | note | Conduct - Sp or C or S
04408c7a-993c-5f6e-85bc-96dfe41b58ee | note | Produce Record - Sp or S
b96c7ec2-5cf6-5eaf-a4f9-affefa7da466 | note | Approval - E
bca8627f-7500-54f6-8c4f-414dfc2bf4df | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
ae7e2d83-e996-5777-8251-1ac263229947 | checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
3d73a674-5395-5f28-9bc5-33d2198d27aa | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
f80f63a9-59a2-538e-b996-08df515c9dd5 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
cdb09127-17a6-58e2-8b40-8a9431472dd0 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
33acad26-51bc-5783-ad7d-7c0e95c99f8f | note | Responsible Person - Supervisor
581e2b71-acdd-5aed-bc12-594663610b51 | note | Verifying Document - Test Report
9cad8e49-47ef-530d-8a38-5200250bfda1 | note | Conduct - Sp or C or S
920a61a9-9a88-5170-9219-ba0fbd0d537c | note | Produce Record - Sp or S
a0b5f8f5-7381-51bb-8cfe-41e170238da8 | note | Approval - E
5031db99-4e31-5322-9ace-a283ba83d66c | note | Hold Point Y/N - Y
59b9d644-63f9-5af7-bf31-75c1a6bf1a10 | signoff | HOLD POINT
282d13fa-6a2e-5570-b955-78f6c0062fd3 | checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
b630f031-17ef-54aa-92cd-41c250dffd8c | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
92f129e6-501a-5a06-bf99-07a0a2dfd0c9 | note | Verifying Document - Sampling Worksheet
19b6d86b-bdd4-5d23-8c3b-38570c4103e5 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
20f46294-a40e-5eea-b139-133605910406 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
a260b83a-016a-57dc-9b02-691e1c0e0928 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
6ae60ab9-941d-5259-9288-14b913e7d6dd | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
5182f5c1-959a-5fcc-ae38-2385b0982c64 | note | Frequency - One test for every 10,000m³ of source material
a91e7ca8-ead8-5f23-ac24-7d745289b557 | note | Responsible Person - Quality Controller
51362051-8cbd-58c3-8edd-a595932b6adc | note | Verifying Document - Test Report
cd64a77e-ac11-5332-a1e5-80a743febe2f | note | Conduct - Sp or C or S
d832ecdb-866a-5b01-9492-c9a532c575cd | note | Produce Record - Sp or S
e200dc98-c7b1-5353-a60a-4099e1baeaf5 | note | Approval - E
e2400b52-522d-553c-81cb-e2ee99d2b399 | note | Hold Point Y/N - Y
2bce147b-57e0-5df2-aa19-d3114e0f900e | signoff | HOLD POINT
771bbcd5-e52e-5af5-9fc3-2a5ff6956b1d | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
4e982646-63a3-5bd4-84b5-6b2ed30b5ece | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
e7fd7e81-ef6d-5d2c-8258-d131b5d7ed7b | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
b6ea1241-b7a5-5375-81b6-3af5bcae9396 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
22d8dc52-ddb7-58bc-9b33-ac31a0c1ace4 | note | Frequency - One test for every 10,000m³ of source material
16511ad1-dd6d-5255-af9f-b71856531432 | note | Responsible Person - Quality Controller
0ea53995-a287-527a-9b8c-5b3b52df442d | note | Verifying Document - Test Report
4c479ecb-66e6-55e5-af6d-53539bc96582 | note | Conduct - Sp or C or S
47392b26-dfea-51f0-b214-4ee62ff886bb | note | Produce Record - Sp or S
d4f7bc6f-7cd7-5158-991a-4a8ef54a881c | note | Approval - E
775280fd-0bb5-5e5e-b857-78e05a42e9a3 | note | Hold Point Y/N - Y
5de343b7-b3e0-59f2-8f5e-085d4a8c0fdc | signoff | HOLD POINT
113f3833-1e06-55b9-9978-c5d36d530658 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
acc41205-f78c-5ffe-9813-5c49ce38fcb9 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
d8d0aa27-27f6-5f4f-adad-26df33232c2e | note | Acceptance Criteria - Soaked CBR ≥ 80%
4bfc13b0-aa32-581c-9695-8f07e0b1c19d | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
14d73bc6-a1fe-5512-8dcb-04fa6815b3a9 | note | Frequency - One test for every 10,000m³ of source material
37f65b56-8c0b-5a0e-9fda-8eb9dc42725c | note | Responsible Person - Quality Controller
1be30b28-7407-5a77-b27b-8c627edb0ecb | note | Verifying Document - Test Report
3cfeb9e4-818c-5f9a-95ef-bb8b3cc69d27 | note | Conduct - Sp or C or S
eee2e5b0-d803-5485-92b6-28acd24ed397 | note | Produce Record - Sp or S
1cdc1875-95cc-5313-95dd-de517a15983a | note | Approval - E
2534db5e-58be-5e0a-b40a-c70af25185c7 | note | Hold Point Y/N - Y
40c2302f-cce5-5c54-87be-1069cdfc7929 | signoff | HOLD POINT
976c9ab2-336e-5bd7-8941-60563e8cfc82 | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
797cbd21-67b9-511a-91ea-c459b73e8223 | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
b2542ae7-79da-5ccb-a0ed-0b67950bcb23 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
daac5e24-d830-55c1-90df-4289fb525876 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
005a9c81-b923-5de6-91c6-8d8f04195868 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
a798c52d-d43f-5e9a-9fec-7a4e7128f1da | note | Responsible Person - Quality Controller
737daca7-6e89-59fa-9202-61f926eb6617 | note | Verifying Document - Test Report
07d2e62e-6e5d-5f8d-98be-3119d3e51f1b | note | Conduct - Sp or C or S
60bfc139-3054-5d49-a00f-d417f0e0af1b | note | Produce Record - Sp or S
1f4d4192-5ac9-5d79-aef9-22d806eec893 | note | Approval - E
22bc9915-bd34-5b2f-a51f-cc55849d02b6 | note | Hold Point Y/N - Y
8c291f12-658c-5f73-81d4-ac64eaf7be26 | signoff | HOLD POINT
21f389de-1666-5508-9d06-5a4f024a4cbe | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
1457bfe5-6072-5e2a-9df7-64d4439556b5 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
bf4a24b5-a474-5d3f-aefb-b4a22b0fbcd0 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
f27000af-229a-5cbc-9ff8-8d2dba1d1b05 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
faffda64-7b72-5210-ad2b-33fa402a82f0 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
674f2abf-a1f0-50c8-a60a-9658ddbd7c81 | note | Responsible Person - Quality Controller
b3d910b2-0828-5a51-9d74-29e62ee4b424 | note | Verifying Document - Test Report
1ff185f2-debb-5d3e-8b0c-9a25c4874891 | note | Conduct - Sp or C or S
b2e7298a-2764-5ab6-a654-c2a3154fe68f | note | Produce Record - Sp or S
e8beb355-4be6-55e1-af29-afb05b8905a8 | note | Approval - E
f9b7f882-b4d9-5ce9-b0c9-83e42c9613ee | note | Hold Point Y/N - Y
f50c0087-ac9f-533c-9dad-f1906513e000 | signoff | HOLD POINT
66a6116e-307f-5697-aa3e-d266fb4bd96f | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
c116c1a8-b1f1-58af-84b6-8b821e537ad7 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
04c7ccfb-1d6d-5025-9cdb-7b28badf6cfb | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
ea5f387f-bd3f-52ea-8648-5a832a695026 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
f409e6f9-ad35-5dbc-aea3-90fb79d8269e | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
c8d78fca-986b-508e-a0f2-485990397ac5 | note | Responsible Person - Quality Controller
ed6464c6-e9a1-5fdc-9d1e-550e11f48960 | note | Verifying Document - Test Report
83952595-5467-53c1-bb3e-60e3c43d8a1d | note | Conduct - Sp or C or S
ddc0e9fc-b809-59f2-b0af-f8978b7fa5dc | note | Produce Record - Sp or S
4579b6a3-ebcc-590f-bee9-da7aa219a084 | note | Approval - E
25e17ace-5085-5351-9d43-5143632e407b | note | Hold Point Y/N - Y
7ecc9215-ad8b-5530-b3e7-13982b2273e0 | signoff | HOLD POINT
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
1e8bbc3c-b3df-5fcc-bf46-273a2aadca25 | note | Controlling Documents - TNZ F7 Specification
c654435f-6afb-578d-a369-2de54a379627 | note | Acceptance Criteria - Details on Docket
f1f92833-7e34-5372-9e5e-93e064712626 | note | Method - Visual inspection
3726d4f3-0a2d-5815-9f04-95e5bd766e45 | note | Frequency - Per Delivery
b7488286-e33c-5be2-9f4c-970bd0e4e21c | note | Responsible Person - Quality Controller
ac6de84d-b698-5eec-a945-8ac2084a8b26 | note | Verifying Document - MDS
148e32ba-c038-58c5-a7a7-a94fb0eb9e14 | note | Conduct - Sp or S
68ad2235-413b-52e0-8e62-4dc9fe1b9ae4 | note | Produce Record - Sp or S
4bf93bd1-9ae4-55ee-af2b-f5dd8f56821d | note | Approval - C
50c9e728-5c68-5903-a395-b7f87c250cf6 | note | Witness Point Y/N - Y
f2243fec-ad92-567d-bb3c-12058747fa66 | checkpoint | Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent
c759b501-9100-56f4-8677-3e78feb163b8 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
7f117d62-f7a3-52fa-af80-d8454c7bed8b | note | Acceptance Criteria - Details on Docket
9838db72-f145-5d7a-8612-28550431f6ec | note | Method - Visual inspection
68fc695a-f458-53f9-a5fa-5aa1979c0a75 | note | Frequency - Per Delivery
0818d5c5-532a-590a-ae2f-a33064da54ca | note | Responsible Person - Quality Controller
dfbefdb2-c0cb-5cf2-858a-faa69607de5d | note | Verifying Document - MDS
994d81e4-9d4b-5fba-aaf5-a17bcc8eb957 | note | Conduct - Sp or S
a5057382-0c1c-54bc-aecc-89a791fa1a3b | note | Produce Record - Sp or S
5a218af4-92a6-5a79-926f-0e0bb05b8419 | note | Approval - C
02a951f3-4abf-507e-bfaa-3773de960b26 | note | Witness Point Y/N - Y
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
c4a29282-2caa-5321-ad93-8263f48ee01e | checkpoint | Production Testing of basecourse material - OMC/MDD
9a9c53aa-4372-5b59-bf22-fa17a4cb1740 | note | Controlling Documents - TNZ B/2 section 7.5
26e47511-e127-5362-9b7a-b43f087b0c8b | note | Acceptance Criteria - To obtain OMC & MDD
292294b4-c2d8-5b93-a66e-12d14b061e80 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
467c06a3-83bb-52f5-9edd-c36366c2cad4 | note | Frequency - Once on commencement and then each layer at one test per 5000m2
f446cbcf-bf9f-5422-baff-994d28a1ff9d | note | Responsible Person - Quality Controller
d61ab9b8-11a4-5256-97bc-6c73abd82c94 | note | Verifying Document - Test report
3e67754f-9857-517d-9668-d059c8f326f3 | note | Conduct - S or C
493119b8-cb9a-57ad-bd66-955effd889b9 | note | Witness - C
9f1986b4-d9a3-5292-8e97-c5ef2cad5d6c | note | Produce Record - S or C
7c1e554f-c30d-562c-9f09-2fd81e574189 | note | Witness Point Y/N - Y
5d30f265-1634-5cae-a3ef-c61dc9b88c38 | checkpoint | Production Testing of basecourse material - Solid Density
b9696d5c-2658-56e5-82eb-0eb2edb77145 | note | Controlling Documents - TNZ B/2 section 7.5
cf0f0f9e-5c5a-5d32-aa3e-c915ea2c93c1 | note | Acceptance Criteria - For info. and use in MDD calculation
1f111013-6f6a-52a0-8c51-8183998605ce | note | Method - NZS 4407; test 3.7.1
b1f2a57c-fa80-59ea-805d-054fbf19dfd7 | note | Frequency - Once on commencement and if any materials change
c51a123f-a0e9-5a37-a831-7c43a78b48ce | note | Responsible Person - Quality Controller
3c276bb0-16d2-5ba3-b4a1-11e48f639a2f | note | Verifying Document - Test report
8478cdba-436a-51c4-8496-1a704f50dee7 | note | Conduct - S or C
8f4c7047-7422-5e06-a29c-ec22a030c51f | note | Witness - C
8f6b68d3-f08c-5e29-9930-b707d69c968a | note | Produce Record - S or C
c316ccfe-53a3-5379-8e52-88ea9e13deca | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
1c38c3c1-489b-5bf4-ac95-751946d38fe4 | note | Controlling Documents - Reference from Project Drawings
ab192240-e2d4-5c4c-bda7-ccb60b34ff6b | note | Method - Survey/Mobile Roads, Marks with Dazzle
1e88b743-3109-5931-848e-d785964a9039 | note | Frequency - Chainages for every different pavement sections
10360f1e-8fdb-5e27-833c-6e46f31833a3 | note | Responsible Person - Subcontractor/ Engineer
abd73e71-50bd-53dd-af81-23e1e5b66406 | note | Verifying Document - Construction drawings
06c3aeb9-b0cb-5edf-ac81-b0372ecd839d | note | Conduct - S or C
0ce64507-ad28-5cb3-adb6-2630dd8b1087 | note | Witness - C
69c85866-338a-5ae8-bf5e-ea301172e6a0 | note | Produce Record - S or C
00415ac7-204f-58ae-987b-4bdf1a77e0ba | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
3d88a4e2-c6e4-599a-bb79-2905300a8311 | note | Controlling Documents - Site specifics to be confirmed
45f0433a-0a21-5bff-aead-766ee1b7d22f | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
ec66c147-8911-559e-bc5a-d8b904ab18c3 | note | Method - Scala Penetrometer on Excavation Floor
6332467d-2788-5fac-9c7b-71422b9554e6 | note | Frequency - As required
e95546c4-97db-53bb-a6eb-2e4bf4df8a1d | note | Responsible Person - Quality Controller
e384c5ed-278e-5f65-a651-001e77988784 | note | Verifying Document - Agreed treatment plan
7653c31a-2f4c-50f1-a6ec-cdebc3f33837 | note | Conduct - S
12079753-ab5b-5d43-a59b-b2ece5367b0e | note | Witness - C
208429d7-6c01-5cda-8d90-9484b1c9bab2 | note | Produce Record - S
7d4dea14-e2a0-59e6-807e-3943f634e3b0 | note | Approval - E
a0bacc2b-9a12-5f16-bfca-7633fa9c3601 | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
6ea48867-c296-5c7f-a6a0-851b1c27a72b | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
b21f6292-825e-51ff-a100-c24bab680bfa | note | Acceptance Criteria - 250mm deep unless specified
bab47471-0a77-56ca-8f62-05e21b20fbdc | note | Method - Visual inspection
bc67f966-9fb3-50e4-bacd-d9b44517bfc2 | note | Frequency - As required
5ed4223a-7a4d-5802-951f-6e52215b7a9c | note | Responsible Person - Quality Controller
1589d42f-0f43-5356-99f4-b09690fd0363 | note | Verifying Document - Dig out site records/ Asbuilt
9b06c7c7-045f-5704-823a-d52f8e85a201 | note | Conduct - S
36546ba0-e3f6-53da-af17-097fe2d4a079 | note | Witness - C
6ad29d63-9be0-5be3-b8d6-155868e44b75 | note | Produce Record - S
a1590c87-10d8-5350-999e-4ddf5d64a9b3 | note | Approval - C
bde7a904-a880-589a-8cf6-dd3e1c0527fb | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
2ddecfba-7f67-5937-92ab-60101a07e9cc | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
8f54e9d4-e613-5537-bb04-a145f8c95a6b | note | Acceptance Criteria - Scala > 3 blows per 100mm
a9a61efc-7da5-57a2-ab09-5c0ae5f71f30 | note | Method - Scala Penetrometer test on base of digout
b697810d-b562-56c4-92dd-bcccd3877fcd | note | Frequency - As required depending on size of digout
ab70aa17-cf87-5f79-84e9-375e58652e39 | note | Responsible Person - Quality Controller
40dd9c05-cbd2-5338-a02d-437bae257435 | note | Verifying Document - Test report
159f8e5f-a406-5e74-8894-9ffd51731dec | note | Conduct - S/C
039dc7fb-2c6e-5676-a8f8-57f92fb38a82 | note | Witness - C
969796c1-e908-50cd-8994-bf89864e303d | note | Produce Record - S/C
51a0539f-12ea-561d-8d8e-3ba388648de3 | note | Approval - E
5ef8c7dd-15f3-5409-9715-b5b8d0af4201 | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
bd1aa235-7939-5e0c-8d6a-30c4410445cb | note | Controlling Documents - TNZ F7 Specification
623ae227-393d-5c0c-a7d8-e20a27af2f9f | note | Acceptance Criteria - Meet TNZ F7 Spec.
e15de3a4-0b57-592d-9236-3971c5441a6e | note | Method - Visual inspection
b6b24524-5eb4-5eb8-af80-9f95a640c1eb | note | Frequency - Per Delivery
257f3684-083e-5af7-88df-215e73706a51 | note | Responsible Person - Quality Controller
7f249e69-c4c8-5eab-8a8a-be08ca869ccd | note | Verifying Document - Certificate of conformance
6f32d529-4b74-5606-a426-5d54043719b8 | note | Conduct - Sp or S
aef40724-c389-50a2-b97a-0ba69a4caee4 | note | Produce Record - C
069a5233-1851-56ae-a75a-4a56bb3386a0 | note | Approval - C
fd6d2a93-4289-512e-a471-f37062480487 | note | Witness Point Y/N - Y
33fd8fbe-9408-576a-8bf7-891431ad9e70 | checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer (if rqd)
5a63dc1b-13dd-59b9-bec7-5b3d3d15deb4 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
4b78a90b-6c00-5ca7-9cb1-eba84cb81f5c | note | Acceptance Criteria - On the list of approved materials/suppliers
7741609c-7598-536c-8e4c-3ef59951545e | note | Method - Visual inspection
45ca3ebf-5b6d-5aad-bdb5-ae11c7197903 | note | Frequency - Per Delivery
70d447ff-e44d-521f-b0b6-b36138eca67e | note | Responsible Person - Quality Controller
aaa53a3d-c64f-5f3b-a95d-ea50a2d44afd | note | Verifying Document - Certificate of conformance
db1a8d2b-6bca-5595-9f66-ad11f258f0ec | note | Conduct - Sp or S
0b19f6bb-6827-5cbb-b0d2-d6f05729d347 | note | Produce Record - C
d8fe067f-28ff-542e-be1f-cca894422e2b | note | Approval - C
9efede8f-a188-5181-b9fb-d9569970b597 | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
91fe0120-7e40-5cce-83b4-c45abe6b44ce | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
e9cb4a5b-6406-50ce-b3e9-def2178b7d3f | note | Acceptance Criteria - Clegg value > 45
44970a15-a484-57e4-a406-1a6ecd67dbdf | note | Method - Clegg Test
d4052e74-dbd2-5566-a4c7-8292d0ced0d8 | note | Frequency - Min. 2 per digout
d0229476-5570-5767-b32d-fb4bef9f1ec9 | note | Responsible Person - Quality Controller
e185a86e-93c7-55c6-ac1b-314f318c657f | note | Verifying Document - Test report
c9d195fc-d316-5c41-ab5e-b9286758b378 | note | Conduct - S/C
9554ceac-90ce-5d3a-8feb-139ff4a8ba43 | note | Witness - C
575eb5cb-90f1-50e3-8a47-f19d9df4d581 | note | Produce Record - S/C
483d71f0-8c51-59be-bc74-6cd83afdede2 | note | Approval - E
9af38c20-c6f1-598a-91df-94416612e5f9 | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
eeb50d65-64ce-572e-8456-9dd1f3e00c42 | checkpoint | Place M/4 AP40 Basecourse Material
b043dabd-2bb8-55bc-94e6-dfdd1ab6536a | note | Controlling Documents - TNZ B/2 (section 7.2)
dde89276-5d15-5cb6-9fb2-a2da58f7d73c | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
fadbccdd-3673-580a-b1fa-d9bfd70a63f8 | note | Method - Visual Inspection
b76b5e44-b3c6-510a-9a62-b9413e691b21 | note | Frequency - On completion of placement
d63aa1b9-6197-5ed7-8111-4093b6d59751 | note | Responsible Person - Quality Controller
657a6869-246b-57f7-a500-5ccc4798c5b4 | note | Verifying Document - Photographs and Daily Site Record
f12e3354-e69c-55a0-85d0-d12e0716a946 | note | Conduct - S or C
b9891b04-6c46-551e-985e-7606ec3ca3c5 | note | Produce Record - S or C
2d2c8e70-5236-5023-ad63-1bea93769647 | note | Approval - C
8eaff9e2-87e1-5a3e-b2e5-0734cf6d9e2b | note | Witness Point Y/N - Y
b2669c88-ac51-56ca-b8c1-ca203b10eac4 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
a9c53394-41df-5b5a-b6b9-79ee7c960fbe | note | Controlling Documents - TNZ B/2 (section 7.5)
044330c0-f942-549a-a736-207ba88e453e | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
1a5bcbf5-99de-5544-8275-17b7a439e7de | note | Method - Plateau Density Testing
d0d85266-f236-5703-bae7-87711f82cca6 | note | Frequency - 1 time, or additional tests when material changes visually
c2b14418-c054-5b8e-aec6-7f5cd2549607 | note | Responsible Person - Supervisor
32cdefd7-3f92-51bf-a83c-e8a053aa2dd3 | note | Verifying Document - Test record
da9bc055-cb70-5987-9cc9-73fb007e0b8c | note | Conduct - S or C
0b172b1d-c2e4-517a-ba58-73ebfa9c9cdb | note | Produce Record - S or C
5d97c286-002d-50de-a22b-240f94b8a49e | note | Approval - C
82d8705f-e682-51f0-b302-63423b94d399 | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
56ea7d6a-b7ad-5a14-9421-460f30bdde1b | note | Controlling Documents - TNZ B/2 (section 7.5)
e024ffb1-3466-5e3e-b1d8-0e62036fa133 | note | Acceptance Criteria - To provide MDD for NDM testing
eaaf7d7e-2262-5069-b3d8-3c8833a01c3d | note | Method - Plateau Density Testing
96a6091e-ab3c-5508-a1ca-b52327fb4319 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
d31c47ff-c797-5bf5-af7c-27fce442eeec | note | Responsible Person - Quality Controller
d49bd3db-c6f7-5908-9e69-6b9c0a8e5473 | note | Verifying Document - Test Record
e6e38fdf-435b-5850-bb13-863d89262521 | note | Conduct - S or C
a64afca0-be56-51ef-95d1-7bdd03d4466a | note | Produce Record - S or C
65c31542-3a2a-59ba-8bdc-31bb7bbe3b2d | note | Approval - E
c200b7b5-9822-59a3-b982-15b98984c7fc | note | Witness Point Y/N - Y
1b96c1cd-dc03-50d2-9eeb-7acf490a611e | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
59423977-1c27-51d9-987d-22a6747ce48b | note | Controlling Documents - TNZ B/2 (section 7.6)
226ef402-af5f-5c69-8296-cc9b76e33929 | note | Acceptance Criteria - To provide MDD for NDM testing
940b050b-0aae-533e-b0d3-4377efd1dca7 | note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
c7df6423-e005-5589-899d-53f0a6372829 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
724e7068-11e6-5cf8-a264-9a86d420dfdb | note | Responsible Person - Quality Controller
437a7484-8d5d-5378-a40a-35a16970ea50 | note | Verifying Document - Test Record
7b465805-5668-5145-ad07-ee93cce2e9f7 | note | Conduct - S or C
1a15f201-0f30-5071-a820-3254b99e5d00 | note | Produce Record - S or C
a10851d7-24e6-5c91-8012-2186d954bfb9 | note | Approval - C
f5009eba-9970-5371-8819-dfd7919cfa26 | note | Witness Point Y/N - Y
9b641378-7dcd-5a3d-807c-a31562803710 | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
52cd3060-ea9a-5916-bacd-1ee379ef7373 | note | Controlling Documents - TNZ B/2 (section 7.6)
2bf963fb-8034-5e06-9f41-0378a2039f6c | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
f318e30c-35f9-5619-9e8e-caaf2924efcf | note | Method - Plateau Density Testing, Lab. MDD
3d929918-7485-5176-b748-26f225d4661d | note | Frequency - At commencement of construction and whenever materials change
e440f684-aa6d-53eb-bcef-e83945c2d4e6 | note | Responsible Person - Quality Controller, Engineer
8f71634b-5deb-55d9-b296-d2008aca9c44 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
b3f2a51f-b4e3-5a52-8073-98bfb1502ba0 | note | Conduct - S or C
afe0592e-0db0-541f-a58b-eb4e6ce61ced | note | Produce Record - S or C
7419b494-cd83-59e0-967f-e28a3309f1ee | note | Approval - E
32f3db5c-b6c5-5e8b-903f-4774fb2e8d66 | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
330d49ad-8b7f-52cb-a1a7-0b91643320bf | note | Controlling Documents - TNZ B/2 (section 7.6)
b11fc7a8-ea5f-5db9-ad5b-97679ba03793 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
95f2de13-a5d8-54d2-b69f-f4770c3da2a8 | note | Method - Nuclear Densometer Testing
90154219-c8da-5a15-bce4-001e25564f01 | note | Frequency - ≥ 5 tests per 1000m² lot
a1024a92-7374-564d-9ae7-c6dcd3bec6b7 | note | Responsible Person - Quality Controller
27dc068f-0c12-53ff-8ab7-e5dd352c4696 | note | Verifying Document - NDM Record
01d7de57-c7e9-55cb-830f-4ef8b60059a0 | note | Conduct - S or C
e5ff4953-74ac-5b3d-b83c-208124a6a680 | note | Produce Record - S or C
4ae51385-a350-5280-88dc-4671b98cca8f | note | Approval - E
c89d0fae-7c01-5a20-9c07-be4279cd5727 | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
af8b704b-8f32-5b45-a4e7-54e95af16d0f | note | Controlling Documents - TNZ B/2 (section 7.7)
928d4a10-fe49-580f-b591-efc51ce90cfd | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
28840a26-5f41-5633-b3b6-e98d110a0a23 | note | Method - 3m Straight Edge
1d508d54-9412-536c-ad80-63949794e4ed | note | Frequency - during construction and prior to seal
14686e18-39f1-5e8c-9d4c-4d758cdbb242 | note | Responsible Person - Supervisor
fd42abb6-423a-510b-a24f-7c24e98ed9ba | note | Verifying Document - Photographs
0d48bfa7-90ab-5f66-9ec4-f54317ceca6c | note | Conduct - S or C
9881dec4-84e4-505c-bedb-bbdba9b1b57a | note | Witness - C and E
ab1221f4-e38e-5b31-aa20-b0f42effe6ff | note | Produce Record - S or C
59110fcc-321e-5ed1-92d9-5c341f6f1b0c | note | Approval - E
43c78411-a042-5df0-94e9-23277c08519b | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
eb37e1b5-cde0-5f4a-a57f-1fb1ba23b4d2 | note | Controlling Documents - TNZ B/2 (section 5.1)
158fb82c-540c-5126-84f4-5508ff4ef0e5 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
a71b5598-59c5-5ca4-af49-1547d56d7e59 | note | Method - 3m straight edge or Survey Asbuilt
38c754e2-b08f-5106-8f4f-f272dbe047b9 | note | Frequency - during construction and prior to seal
c98fa6ca-ace3-53f1-81f2-05f8ba2fa0a9 | note | Responsible Person - Supervisor
5b9e082f-ae0c-512a-89b0-786192978e00 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
27e1b0df-e313-5df1-9641-976efad749af | note | Conduct - S or C
f71563b5-ef60-5ad2-a31d-06b00df045a3 | note | Witness - C and E
22d368c8-b077-5c5a-92de-453dcc09b177 | note | Produce Record - S or C
355b0f81-61a0-533b-93bd-1ff20bbb0213 | note | Approval - E
cacde381-3a00-5d61-bbb6-da3b2f02a075 | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
fcadc16e-1c1a-541f-9990-6fd6455a63c9 | note | Controlling Documents - TNZ B/2 (section 7.8)
9c1c80fc-2891-5d35-8ac7-c86430e274e3 | note | Acceptance Criteria - Tightly bound matrix post sweep
e210a0e8-ec2e-5fba-b813-1d6b0b3685c6 | note | Method - Visual inpsection
90e2322e-e095-5e9a-9216-d3b7d3459bcf | note | Frequency - prior to seal
94cd0d4b-1bf8-58eb-9024-9353e4afb429 | note | Responsible Person - Supervisor
5ce6376e-08bd-59c1-9401-ad6022359124 | note | Verifying Document - Pre-seal inspection sheet
d4f1933e-861e-56af-be3f-e297c9bfcfe8 | note | Conduct - S or C
622fb9e7-8686-5fce-9ab8-b5fe897d02c7 | note | Witness - C and E
2f945187-6df1-5327-93fd-64be13a2f35c | note | Produce Record - S or C
dfcf4ad4-c9a9-5a5e-9e6b-6de89e360c16 | note | Approval - E
36602a06-c596-5045-9db6-474115d66884 | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
b06a9b51-e668-5403-a6c8-b6ab73748942 | note | Controlling Documents - TNZ B/2 (section 12)
d7d543bf-e6e5-5075-b073-fdd3153f5d4d | note | Acceptance Criteria - ≤80%, however 65% is ideal
5f84c2c5-c426-5080-8d61-81b389d18b61 | note | Method - Nuclear Densometer Testing
8e55bae1-0f3c-5052-a430-71f6bad7e92f | note | Frequency - ≥5 tests per 1000m² lot
7b4305d7-0f17-5c82-afb8-28c2d68647dd | note | Responsible Person - Quality Controller
e1f9b8d1-11ab-5b9c-934a-51ff5cb5d0d0 | note | Verifying Document - NDM Record
f56dcb72-8406-51c4-aba1-77d20c960d00 | note | Conduct - S or C
f2e9c004-a6fd-5434-b17d-16a5fb24fee0 | note | Witness - C and E
e06e0af1-e87b-5394-9239-edfea845b919 | note | Produce Record - S or C
deb7e211-ddb7-529b-811c-fc61b6822b7b | note | Approval - E
4be631de-1585-5ed6-8270-90a8c2945473 | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
246f479b-be73-532b-b845-4aa2abdc73ec | note | Controlling Documents - TNZ B/2 (section 7.7) NZTA Maintainence specification section 6.1.2
ec0a1cee-7d3b-5a1b-b6a9-77e547083143 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
7477e3e4-d5a2-5410-87f7-ce36e57fd22d | note | Method - NZTA Maintainence specification section 6.1.2
a57cb043-1258-503b-a410-e061353e266b | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
4f459d6e-2857-53cd-895b-a250017adcfc | note | Responsible Person - Quality Controller
ff13585a-3502-529c-ab7f-0affedbff4f4 | note | Verifying Document - Test Records
4c7fdeaf-1539-5f02-b263-1cae6abaf97c | note | Conduct - S or C
cd100b38-9039-53b0-b4b3-e06c8285a173 | note | Witness - C and E
cec873ea-fb3c-5236-bf8a-1b99e2f2f4a8 | note | Produce Record - S or C
d0729714-9d20-5e9e-bb83-edf97806dc93 | note | Approval - E
8f333617-298a-5196-ac46-3124ed5981b6 | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
f6ac91d4-5c0b-53d1-9e4e-00bc03939ff3 | section | 5. Chip Sealing - 5.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
1adf23f6-59a2-5364-ab91-15aad3e890c9 | note | Controlling Documents - TNZ M/1
5c3f53e8-ec8b-51d3-b535-ae1d12756ece | note | Acceptance Criteria - Table 1
50bc75f2-b599-504d-9a4f-79f096af8459 | note | Method - Property Test
15e31419-9ea0-5121-82e6-8dae4030c659 | note | Frequency - Annual
8e2eb36c-6c76-5eaa-a89b-52f17e4fef48 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
7a1e15e5-8711-5624-ad88-7a388e402412 | note | Verifying Document - IANZ Report's
fe6606c5-1f4f-5337-88a2-dbc6da77b4d9 | note | Conduct - C
2fb4284d-52a0-58f6-921c-3fe798f6a769 | note | Produce Record - C
5ddd5044-2532-53c1-903f-4f31c01183c3 | note | Approval - C
4b4a82e2-df90-595d-8d21-dd9399d30030 | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
21227ec1-135f-5e82-a56e-b9f88e36e31c | note | Controlling Documents - Higgins Internal Specification
41a1232b-2573-5291-a8e1-fff571fe4270 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
ecf6ea04-29ce-521e-8d3e-9c0f6b49f91c | note | Method - Property Test
fec8e4ca-7162-50ad-999f-9b46a031191a | note | Frequency - 1/100,000 litres supplied
179b4f4f-5ad4-51da-8c01-76d94a2123b5 | note | Verifying Document - IANZ Report's
ebc87558-56d9-505e-bdb1-d0ba4c28a887 | note | Conduct - C
6c02281b-1f79-5446-84df-4316fe13fd04 | note | Produce Record - C
48b77828-19aa-5ba4-a78f-cd67c8ad3fdd | note | Approval - C
5035b9be-5fe5-5d61-9b42-be8ffce1a36b | note | Witness Point Y/N - Y
51a1a52c-eff3-55cf-8c7e-6c107ae62708 | checkpoint | Source Property - Coarse Aggregate - Weathering Resistance (1)
2b9e513b-1526-525c-a06e-8e7d24af767d | note | Controlling Documents - TNZ M6, RNZ 9805:2009
fc128cb4-d6a9-5a62-a45d-c9c0a8fb777f | note | Acceptance Criteria - <10% fines under 230kN minimum
3f16373e-5a12-5a43-a4c5-b8a002c5e975 | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
7d59f86f-04e0-5976-bb60-1c53643e343c | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
ed6c9101-1ff7-5df5-8e2e-595c792fd2f8 | note | Responsible Person - Surfacing Project Manager
385f9a27-e600-5e3a-9ffd-4835f45fecea | note | Verifying Document - IANZ Report's
c2b29fcc-8732-5b25-8b9d-342ca55b97c1 | note | Conduct - C
7cf03318-33d4-5e06-b6c1-a713d5093da4 | note | Produce Record - C
d64ce3a6-723e-55e5-8905-ca9743e444bb | note | Approval - E
68374467-20d3-583f-8fb6-bf84d949ed82 | note | Hold Point Y/N - Y
01e1698d-0877-5529-a332-ad90ecd7e9c4 | signoff | HOLD POINT
7b5914e5-b261-5e79-8d1d-bc109846daf5 | checkpoint | Source Property - Coarse Aggregate - Weathering Resistance (2)
1058fe2a-437c-599a-815f-7e41b76b52ca | note | Controlling Documents - TNZ M6, RNZ 9805:2009
6e7db834-18b0-59fd-bb88-197fdda1c952 | note | Acceptance Criteria - AA or BA
f2cc9233-7b69-58e9-8ac9-c0ccda443bf2 | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
41c95273-3fea-5bca-8efb-edf4a8bc8ecb | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
d7c3976f-cdfd-52e6-8676-6bb690d7637a | note | Responsible Person - Surfacing Project Manager
c8e8433b-0573-5aa5-ad24-bd3f9c4ece0a | note | Verifying Document - IANZ Report's
d09d8261-e76e-55c6-82a2-da57e1163765 | note | Conduct - C
c98136e7-8a75-5660-9015-7caffde32135 | note | Produce Record - C
9298cc03-2de8-5d4b-b940-746e186b6392 | note | Approval - E
7439888c-9733-5ead-93e1-fa429e7db2e4 | note | Hold Point Y/N - Y
1152f04d-0b26-5fed-8594-9c9550aee864 | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
ccc6dee3-3837-5d67-bc9f-cf43c8f357ac | note | Controlling Documents - NZTA T/10
f2550e94-21d8-58cf-aa3a-754cf7de2d8d | note | Acceptance Criteria - Meet Skid performance Requirement
05cdc2ab-a474-5c2c-bc11-33aee26e6136 | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
e36fa3b5-c92e-5ad5-8630-8a17d5f7061d | note | Frequency - Each Site
ac51aec8-8fd7-50be-89d2-c6675fb400a1 | note | Responsible Person - Surfacing Project Manager
47220790-9484-506b-a86a-4079017eb9bf | note | Verifying Document - IANZ Report's
865fd960-057b-54f4-b6b8-365479907d9c | note | Conduct - C
66e1add0-8fad-515f-9de9-a3357b2cc9d9 | note | Produce Record - C
c23417be-e02e-5c95-9620-dfd5eef62073 | note | Approval - E
5bc18520-ce30-5416-a453-22b72f1cc86d | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
c1d08e1b-e52e-56f5-9af4-c91349bf8ce5 | note | Controlling Documents - NZTA P/17, M/6
f14aa18d-6d4d-5920-813b-9c342418fae5 | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
b667fc3a-0e3a-5eed-8ed6-9c97165ba604 | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
22bf8371-f3d4-52d7-aa0d-2a113db58b2d | note | Frequency - Per Stockpile
c8379ac7-3fef-53ed-8f2a-bed7d63a6fb4 | note | ○ <100m3 - 1 Sample
140214c4-7069-5cd2-aa2f-4180916f37e3 | note | ○ 100-500m3 - 2 Samples
850bb90f-7797-5063-9b43-fc635adc0f29 | note | ○ >500m3 - 3 Samples
ed94d0b2-c112-540a-98b2-b41bedad0009 | note | Responsible Person - Surfacing Project Manager
5e9b5f09-6a84-5100-bc66-8eae4f70013b | note | Verifying Document - IANZ Report's
d63c5236-2148-5b0f-b721-04b4a800cd6a | note | Conduct - C
f9885a82-02bc-5f23-abfe-8b6f47fcba71 | note | Produce Record - C
912e3bf4-bd85-582f-b9d4-769447b4a080 | note | Approval - E
35a507ee-4839-5de1-9ea5-dfcd5d327e51 | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
b83953f2-6371-53c7-8c97-aaa56bd47e66 | note | Controlling Documents - NZTA P/17, M/6
16d14825-6d55-5d61-ba96-66aa9fc37af4 | note | Acceptance Criteria - As per Table 3 NZTA M/6
2807f6e5-06f6-51d6-baf3-439e0e18f429 | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
f9a16178-d603-54dd-b25f-bcad30ad2edf | note | Frequency - Per Stockpile
e316eef9-fc81-5721-9d30-1fef373336e8 | note | ○ <100m3 - 1 Sample
c56b5132-451c-57bc-b0f3-efdc6066df84 | note | ○ 100-500m3 - 2 Samples
b9a26283-bafc-51b4-8849-786d0a952c14 | note | ○ >500m3 - 3 Samples
9af7841d-ef15-5e3a-91d3-831c82a3e2c6 | note | Responsible Person - Surfacing Project Manager
18c49007-90cf-52e8-afd7-e4ed84c81c4d | note | Verifying Document - IANZ Report's
16a4a1a4-c8ac-5ac9-bcb3-e101522d537f | note | Conduct - C
44c4b7f2-2f96-50eb-8a1e-c880a7e34c7f | note | Produce Record - C
3a546aeb-d670-5141-969c-91e4c8bdff5e | note | Approval - E
e4c2cc37-6a61-5ade-a0e1-502321239103 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
3e93ff78-0612-51c5-8b20-565e93dd44b6 | note | Controlling Documents - NZTA P/17, M/6
ae713c0a-ece3-5cb4-8a03-e35887a209ba | note | Acceptance Criteria - Min. 98%
a08ff6c3-a2e0-5f48-a810-b7eae78300a3 | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
742bb2b4-89f0-56d9-9867-065db350fd95 | note | Frequency - Per Stockpile
80ccdaea-5d5c-54f0-a0f6-702fdb384967 | note | ○ <100m3 - 1 Sample
b242fb0d-a28e-5f19-98e1-5d5ae481dc16 | note | ○ 100-500m3 - 2 Samples
1eef10c6-73eb-5cf0-b229-24a3d950384e | note | ○ >500m3 - 3 Samples
ee37d49d-788c-5d23-b94f-10a49571a248 | note | Responsible Person - Surfacing Project Manager
f2acf9dd-5aa3-5540-98be-b0630ed6fb4d | note | Verifying Document - IANZ Report's
7a0a4482-322d-5e43-a237-cf1aee3c8732 | note | Conduct - C
b8f6ece5-ec45-51ad-89f9-083d681daac8 | note | Produce Record - C
b1ac9393-7fa2-5665-b1c9-547f257ee3ad | note | Approval - E
9acf315b-b715-54b2-aa44-48085712350a | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
98cbe5f4-fe89-5716-ac9b-713b68d3843d | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
2198db8f-6562-56dd-843d-ac85e448a3bf | note | Acceptance Criteria - Client Approval
29b58ce6-5d97-5707-a5b9-05975f4b7514 | note | Method - Review
bb866431-4b6c-5491-9304-f7d2ba198462 | note | Frequency - Annual
5c5b8591-a6f9-5bb8-9edd-95f2f64482d5 | note | Responsible Person - Surfacing Project Manager
815149d6-a055-5fb3-a8af-e16516e2ffa3 | note | Verifying Document - EBOP NOC Design Report Acceptance
207458d3-32f1-53d5-8709-b610ef3fed24 | note | Conduct - C
9e75f401-5f74-51e9-9676-5a6349a02044 | note | Produce Record - C
33cbe14f-b67a-5dc1-a3f3-15217bbc485f | note | Approval - E
52670e62-6adb-5ac8-9bfc-18035b28ab54 | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
2d90825f-40a1-55cc-9369-13e616f644fc | section | 5. Chip Sealing - 5.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
bac00f7e-dad7-5fd9-80df-0fc91b1eac04 | note | Controlling Documents - EBOP NOC Design Report
dec3f07b-e536-55fe-bb93-4bb4bc3ba856 | note | Acceptance Criteria - Visual Inspection
b510565c-3083-5fa8-963e-77c261de2d1b | note | Method - Visual
187530f3-2e52-5db2-82eb-14fa8fdf18d9 | note | Frequency - Prior to start sealing each site
82d3f85e-be33-5cf5-b5b1-2558adcb813c | note | Responsible Person - Surfacing Supervisor
cb250130-e036-525b-92b7-8a5f9ecc9aba | note | Verifying Document - Chip Sealing Quality and Site Record
99cc5342-ac92-5273-bb09-2b54fbab70eb | note | Conduct - C
efe51894-8cc2-59b4-b512-18747a1acd8c | note | Produce Record - C
d417b078-1380-5ade-9188-22ef06d65b2f | note | Approval - C
6cc86c48-bec5-5211-b9cf-2438712a0032 | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
cc5447c5-c40e-5578-951a-f9e97297f0bb | note | Controlling Documents - P/17
bc48778c-4567-5578-afd4-6832e25f43a2 | note | Acceptance Criteria - Visual Inspection
fe495c31-4279-52f7-ab39-e312907d2b39 | note | Method - Visual
390b5140-8a13-58e4-ab6e-1daf5d7213b4 | note | Frequency - Each site, prior to start of sealing
43af5515-108b-53d0-98a2-b1b88275eb0a | note | Responsible Person - Surfacing Supervisor
b77b9fa2-39af-545c-9ffc-83c090bee372 | note | Verifying Document - Chip Sealing Quality and Site Record
cafce6e6-6f31-54a8-8a09-646eecb08bad | note | Conduct - C
2f1d64b9-8cc6-5902-ba54-cc233279d17e | note | Produce Record - C
31012d71-8440-588d-b74f-423a6a8a02b0 | note | Approval - C
857358df-9c29-5a2d-a10f-6ffee269cf57 | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
be26165d-036a-57d6-bba3-8c127a2a4cb6 | note | Controlling Documents - N/A
d9937254-0e64-5daf-ba4d-4f313b3b1e52 | note | Acceptance Criteria - Visual Inspection
9144c1b5-ca24-5a0d-b2e3-181b123f0e7b | note | Method - Visual
3ced55de-2e27-5ac0-a9df-1148793de581 | note | Frequency - Each site, prior to start of sealing
dcd17861-9adf-5d8a-bf47-a9542507e7c9 | note | Responsible Person - Surfacing Supervisor
3dcb77d6-9b52-5aff-b268-10a458551093 | note | Verifying Document - Chip Sealing Quality and Site Record
a059e604-5da5-5dd9-91cf-445edef9c601 | note | Conduct - C
466a7133-ad2d-518d-ac29-6ceb61b9f435 | note | Produce Record - C
0239515d-4473-571e-8830-f817b2ee1e62 | note | Approval - C
be288bdd-3917-5272-ae05-bc2fb24e7d44 | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
8dab8c58-e0b6-591f-9101-821fc83374bc | note | Controlling Documents - EBOP NOC Design Report
940b06f7-faa8-55be-8e39-07dbf21719eb | note | Acceptance Criteria - Details/chip correct
d66de705-cf2a-574d-ba13-6787bbb1267e | note | Method - Visual
125a8bf2-9f22-513d-ad72-9a1dcfa51dcc | note | Frequency - Each Site
5477ce9e-600d-57ff-9c2f-c7a71271a8e6 | note | Responsible Person - Surfacing Supervisor
2dd0d2fb-ebb0-5f91-83e4-46090ea91ac1 | note | Verifying Document - Chip Sealing Quality and Site Record
a2cca1c7-481b-547d-97b8-32981c444d8c | note | Conduct - C
2f7fde14-4f71-5e0d-80d5-7820087cfd3c | note | Produce Record - C
1f9f82c7-b65d-5991-bf54-1dab857ac16b | note | Approval - C
94617302-c9e7-5725-b848-2d3e2ad65fe6 | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
7cbd7e91-97fd-50d5-a0a3-c62ce86b57e5 | note | Controlling Documents - RNZ 9803_0513
267bdd65-c419-59af-acc2-aff2f82895cc | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
c7c3b433-269d-572b-bb9e-69e563fd51ec | note | Method - Sample and test
8efb8914-4292-5c9b-b290-c0e72c356195 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
0da4d25f-7284-5327-9e27-b84897600a01 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
36242789-5ed9-5d1d-a134-b58fb82f562c | note | Verifying Document - IANZ Report's
0ce1a900-78fa-5b9b-ab49-fa18f9724e34 | note | Conduct - C
8e9ce13b-667b-5033-ad18-bfb21edb3c66 | note | Produce Record - C
5d85bafc-c504-5da6-801a-03f3c2b0ed78 | note | Approval - C
7957a21b-1c26-591a-9558-16d0847f8528 | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
747b7e2e-1844-5b11-87a1-477b2fc69820 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
c51eca56-1f71-5363-8776-d30873aaa37a | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
b30c5d4e-b5dc-5204-9410-daed6f788857 | note | Method - Test, Review
8291d9e8-56a4-563b-b68b-2d23b828f19c | note | Frequency - Per Sprayer, Per Site
135f3ac0-d846-50f0-a5a6-f16f55b2aaa5 | note | Responsible Person - Surfacing Supervisor
75455cad-2d9d-5744-bb3f-99990a3b8661 | note | Verifying Document - E/2 Certificate. Spray Sheets
54a019fc-ba3a-5c16-9d2d-03177db2a970 | note | Conduct - C
b1dba1e9-f655-57c1-b189-69e90e697b09 | note | Produce Record - C
5e8bfdb1-0283-56b9-b943-2d5841fd1fc6 | note | Approval - C
d5c0aff6-3f0e-543a-8162-e7a9d87563bd | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
3ec2c9aa-1e7b-572a-9dd2-074c0ded0ac7 | note | Controlling Documents - Chipsealing in NewZealand
5ae712f1-7795-5c4e-a6a4-872485465794 | note | Acceptance Criteria - As per Chipping Guide
da717217-50b6-5c6b-9cff-c57e122ef9a1 | note | Method - Visual
d1ec2303-a47a-582a-9f92-f3f4ce8af01b | note | Frequency - Each Site
f83f9e65-f247-5d84-8ad0-431b7a92e40a | note | Responsible Person - Surfacing Supervisor
f0813372-94d3-54e8-881e-94cd390b8d90 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
db5e288a-f9cf-5df8-abcc-c2b95c315587 | note | Conduct - C
ba78f370-516d-59bf-a552-bb8185152a2e | note | Produce Record - C
0a372e49-90e1-5e2c-94da-b601c2793db7 | note | Approval - C
670da1de-9626-56f2-8d28-56f358fc5602 | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
fb00e6db-f908-520c-ae03-6809986ff2f7 | note | Controlling Documents - Chipsealing in NewZealand
71dd1699-97d5-5ef0-ae89-af121af49419 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
d2d82206-c1cf-5684-8e00-6d5cbc4dc190 | note | Method - Visual
bc0d0593-0960-5c97-afc0-af5d2c84b9ea | note | Frequency - Each Site
b5e72a55-6312-5fa5-a6cf-6cd13ac28da1 | note | Responsible Person - Surfacing Supervisor
eb0fb13d-ed17-52f1-b3ef-d7f9dcfbc84a | note | Verifying Document - Chip Sealing Quality and Site Record
719f0049-d4c7-507a-bf10-6328d3212c6f | note | Conduct - C
6d2aaba4-532f-5094-9ef4-2a0f22e9ee9b | note | Produce Record - C
20098e20-b6e4-5b77-b70d-356acf3a499d | note | Approval - C
728cf912-7799-570a-845c-fbeac512166e | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
0a1e64b5-edce-5333-a9d6-6410c44dd808 | note | Controlling Documents - Chipsealing in NewZealand
b378789c-39b1-54d9-8cda-3be16333e985 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
a2e290d6-c1bc-5868-8e9a-73840dcc744c | note | Method - Visual
b70c22ca-3447-58af-9d90-ea783d5306a5 | note | Frequency - Each Site
b5a0331c-9793-5075-b92e-ee2411bb7fa3 | note | Responsible Person - Surfacing Supervisor
8f86da46-a2f2-546c-90ad-9214c6416710 | note | Verifying Document - Chip Sealing Quality and Site Record
2beca2ac-1f31-54bf-9b33-e2a23e8c985d | note | Conduct - C
f44c542a-72ea-597f-9678-794850f4a57f | note | Produce Record - C
34da8fb3-0bb4-5dab-ba4b-74c95b9e3eb6 | note | Approval - C
987b83f6-9a31-5381-88be-73126ff5ce03 | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
b3d94830-f192-53b5-b95b-e2a385cef8ec | note | Controlling Documents - Chipsealing in NewZealand
fcdbbb27-4b0b-56c8-911b-4ab2ca295199 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
1def7461-3f99-5e08-8efa-7b8ab6eae84a | note | Method - Visual
c249d022-ff89-501d-8d39-3f4b6a77323c | note | Frequency - Each Site
c486b396-5752-572e-8715-6e19bf33b9f6 | note | Responsible Person - Surfacing Supervisor
465372b8-f134-5997-81ae-5889f81b684e | note | Verifying Document - Site Record
133a621f-ca80-5b2f-a6ca-3b07f94e89c5 | note | Conduct - C
c624a242-55f2-59bd-9c7c-62d9c2e96706 | note | Produce Record - C
de2a9d4d-00f7-5bfb-a169-93aa1f58b0c7 | note | Approval - C
f4bd0fc6-f7a2-5811-a90e-c0199a81e9b0 | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
36a75c46-3092-5e62-b623-5d75e64678a7 | note | Controlling Documents - MOTSAM
d7a72734-7c08-50bf-b89a-09cc12a116b8 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
0b659f3b-85b2-5335-810b-9c0f214dbcaa | note | Method - Visual
acaada8b-8756-5a0c-bc12-49017b9917d5 | note | Frequency - Each Site
ca90ba35-0cf6-5828-ba70-d0673af55649 | note | Responsible Person - Surfacing Supervisor
25b7afe2-a524-52dd-9329-95ee82bd1a6e | note | Verifying Document - Site Record
cca8e7d1-b783-51d3-9331-6a2a7487d19e | note | Conduct - C
2cb8c0ef-edfb-5806-a899-9792147b94c5 | note | Produce Record - C
b78e6d69-8532-5d2f-aa65-b4d1cef2ffaa | note | Approval - C
795a8469-0380-5fe1-949c-24fae9c2942b | note | Witness Point Y/N - Y
2fa24de8-fb07-5d57-947e-3eea20cf5b9a | section | 5. Chip Sealing - 5.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
35a15772-048f-5866-bc20-20d666162d08 | note | Acceptance Criteria - Formal Agreement
5b061734-df8a-56f7-9bb2-45321ca3023f | note | Method - Visual Inspection
1d8fedff-ff61-5dcc-a52f-d2e99e9ee08a | note | Frequency - Post seal sweep
e02526f7-faed-51fa-a49e-2705556a812b | note | Responsible Person - Quality Controller, Supervisor and Engineer
2151417d-9f01-5e5c-a1ab-fa9c8b1d61dd | note | Verifying Document - Meeting Minutes
a9b3eb84-52dc-5bee-b5fd-ed25eaaa787c | note | Conduct - C
e05a1451-4ab4-53cc-87a1-90ce3219a789 | note | Witness - C, S and E
eeff3bac-b328-5c35-a122-68c670734ec4 | note | Produce Record - C
6d661991-db51-51aa-b0e4-97dad6809f96 | note | Approval - E
4ab51750-fc49-5768-b510-8378a32701af | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
aef1750c-b540-5c64-852b-9f5a2c30f76e | note | Controlling Documents - NOC; MS 6.1.3
1c233291-fa10-5cfe-92a2-7b0253b35383 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
54727146-5005-544c-ae0b-9fa10dc1ac55 | note | Method - Record
43b08050-3e60-5d8f-a298-05b64edf836a | note | Frequency - Within 2 months of completing the annual resurfacing programme
612f6eea-79d8-51c8-aefb-5dd79ce183c6 | note | Responsible Person - Surfacing Manager
a258ed4a-6784-5baf-bd69-b7fa99480932 | note | Verifying Document - Construction Completion Report
8f8c0eed-3cc4-5f65-b5ac-b93818df0c3a | note | Conduct - C
69085b4b-ce4a-5fdb-9189-5ef0454ab03c | note | Produce Record - C
aaabec55-7e2e-5854-ae2e-7897446623a8 | note | Approval - C
95011652-a96a-500b-a71f-d8e8852c1d0e | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
9e1c790a-af46-5e5f-9442-b60d12f91fb4 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
666a209e-1dd3-5386-bc10-da41a7524fa2 | note | Acceptance Criteria - Engineer Approval
5af7703a-6025-5095-9b8e-4b97155110e2 | note | Method - Visual Inspection
5d8bc002-e6fa-5d51-bccf-3c6f0ada98f2 | note | Frequency - ≤2 months of 1st Coat Seal
1092e98a-5310-5c83-be38-f00262ddd43c | note | Responsible Person - Quality Controller/ Contract Manager
f135a18a-df94-5863-9fd6-e21bb5fb9e54 | note | Verifying Document - Signed Report
e81987b8-e329-5eef-bf95-7a9b96974369 | note | Conduct - C
6087059f-b261-5be3-9b42-8997f62f3b93 | note | Witness - C, S and E
4b4c0af3-7cd0-5760-bd84-8e42866dffb2 | note | Produce Record - C
c6b7a511-84a5-559a-aab0-96c0d0cbab9c | note | Approval - E
2342948e-f4ea-5ad2-a4a0-41881c427a32 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
dcbb2414-cb7d-5900-b089-bafc6d3b1bdb | checklist | ITP - Pavement Rehab - SH 02 - Gas Pipe Line | itp | ITP - Pavement Rehab - SH 02 - Gas Pipe Line
5056f7bc-9e2e-5279-8805-b3dfbdedd24a | section | 1. Procurement - Materials: Cement
a401f515-06eb-5d99-bbc6-048113aafb9a | checkpoint | Stabilising Agent Selection
bc76d9df-250c-530c-aeaa-18211fe87d07 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
d1f9061e-6857-5cbd-859a-cf22d2b19808 | note | Acceptance Criteria - GP
1625f521-0f6e-55aa-9124-08fe95bdb8fb | note | Method - Visual inspection of supplier docket
682b04ef-95aa-5929-808b-1736efbdb17e | note | Frequency - Per truck load
6ff58026-c8d1-5ff6-852a-fd17f66681ae | note | Responsible Person - Quality Controller
5439edf0-7542-58f4-9026-b0f6c8b7ba71 | note | Verifying Document - Supplier Docket, Supplier Cert
7fc2b539-2aa1-55cc-beb5-a2c87224661a | note | Conduct - Sp or S
6cbac185-b5af-5349-a7f2-3dacc87395fb | note | Produce Record - Sp or S
ff223444-2c30-5b4a-b2d2-a6ad6dbb64fe | note | Approval - C
31fd4a24-9529-5dd8-a3d8-fa74c853ce07 | note | Witness Point Y/N - Y
f2cdf32d-b044-53e6-a60c-8d8eb6f61e14 | section | 1. Procurement - Materials: Water
433d7cdd-68bf-5ea7-a572-5dbee45308ec | checkpoint | Water draw for stabilising
53179220-0cb0-5889-a370-4deec57cecb4 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
4b1f088c-b88d-5a36-8659-3d20fa7c8902 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
e2a70e7c-cd5a-55bc-aed3-fa176c654116 | note | Method - Visual inspection of hydrant use form
29034830-a244-515a-aef0-6261ceac5b83 | note | Frequency - Per truck load
d68f1cd6-9e35-567d-9bed-58a1cb4ce72b | note | Responsible Person - Quality Controller
1d1466a6-8815-5520-8ae1-00e99ffd0287 | note | Verifying Document - Hydrant use form
7c272279-bc84-5f41-bb43-6f212a8c9797 | note | Conduct - Sp or S
648972bf-02ff-5986-bd17-fb50efa1b129 | note | Produce Record - Sp or S
dca222f7-7583-5321-909f-929adad80971 | note | Approval - C
8aaa21cf-3f65-5b92-bc63-a6118dd2ad99 | note | Witness Point Y/N - Y
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
3cbcad33-916c-583b-8548-b5e09634e85a | checkpoint | Production Testing of stabilised material - OMC/MDD
47cde7bc-3dca-5ef6-a4f1-36d61e2c78c7 | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
52e58884-a654-5577-910c-d8cdc57a6c7f | note | Acceptance Criteria - To obtain OMC & MDD
bde1180d-bc84-5453-94ea-7127485f185f | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
4decf31f-3975-57fb-a12f-5b16bfaef38e | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
c9a8ecf3-4fec-52e2-bec5-ad724a360acf | note | Responsible Person - Quality Controller
66e1ae2e-d678-5b84-b92d-bf73f4e1f594 | note | Verifying Document - Test report
ca4cbf53-bf45-5464-a267-fb465a915762 | note | Conduct - C
b7536f57-e625-5340-bcce-69c9666079ca | note | Witness - C
229d7b37-d402-5d80-9007-306cfdae2f59 | note | Produce Record - C
a86985ee-0b63-549c-bcac-f1d03784cfd9 | note | Witness Point Y/N - Y
db166df1-f07e-5e98-a6bd-e46d84f52c3e | checkpoint | Production Testing of stabilised material - Solid Density
34fae511-7e95-5a06-8bec-ac28379461fc | note | Controlling Documents - TNZ B/5 section 7.7
20e1cdb3-5b1d-57c5-af81-17ccd4402755 | note | Acceptance Criteria - For info. and use in MDD calculation
49ffb785-231b-5d49-b2f8-2d7ca12f7864 | note | Method - NZS 4407; test 3.7.1
d1d33634-eba9-58ab-8d68-161bc0fd63dc | note | Frequency - Once on commencement and if any materials chage
d3e5ea2a-bae2-565c-be50-5dd8be802d82 | note | Responsible Person - Quality Controller
458949f7-4a9f-5f88-aaf9-c37ccbcd22d8 | note | Verifying Document - Test report
2f6ce5f9-b658-5ae7-b351-58180c7fc8f1 | note | Conduct - C
1813b7be-34ea-5efa-b14b-24f68bcd2fe7 | note | Witness - C
fa2e3be2-420d-5854-8780-4fac90162295 | note | Produce Record - C
01d91a17-5c8d-5b0b-aa58-ee77082ad07b | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
20121a8b-14f6-577e-a7b7-203efb53d83e | note | Controlling Documents - Reference from Project Drawings
3ea8754a-4a64-5da4-9820-e5e26f828d02 | note | Method - Survey/Mobile Roads, Marks with Dazzle
7522771f-74ca-56bc-b414-3323827b4bb3 | note | Frequency - Chainages for every different pavement sections
ae2f1235-db67-5ff0-b666-cad79f482919 | note | Responsible Person - Subcontractor/ Engineer
039204e0-a724-5d04-a329-9404fe6c51d6 | note | Verifying Document - Construction drawings
1a23c649-bed4-517b-b737-f0381313727d | note | Conduct - C
60447742-27a1-5092-a814-66dbe214a1fd | note | Produce Record - C
bb925ecb-c994-5b3a-b31e-c9ad42a66a57 | note | Witness Point Y/N - Y
a35b0113-7e10-5d0b-9744-96661b84f602 | section | 3. Construction - Hoeing and In-situ Cement Stabilization
27c96781-3034-5bd6-8be1-9136ce336cf1 | checkpoint | Spreading of Cement
47c43259-0f6c-54d9-b215-440b4c83b0c4 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
5f50630f-903d-59b8-a2fc-cc77b7840704 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
44eb6767-018e-5abe-8ffc-e9a445adacdb | note | Method - Mat test (1m² canvas) and Average Usage Test
147bcaf8-39f3-5458-9e85-1fc6bcb665e7 | note | Frequency - per 400m² and upon emptying the spreader
c0a4f6a5-89bb-55ed-ac0f-eb70a975c542 | note | Responsible Person - Quality Controller
63fd8b42-2b55-5508-9494-da5d4417d23e | note | Verifying Document - Mat Test Form and truck dockets
75bac049-ed33-5d7e-a57a-e0e472db0da2 | note | Conduct - S or Sp
432db1ad-6180-5796-9991-f434d5f873fe | note | Produce Record - S
8aca7ed1-caab-53c7-80d6-582ccc72917c | note | Approval - E
a30a319f-3105-50ce-866f-b955bde269c5 | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
b70fce16-6717-5149-a52a-1db58ac81772 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
29356b28-15e6-5f5e-808a-7f2bc6013adb | note | Acceptance Criteria - 90-100% OWC
8d000523-65e8-59f6-8a2b-f9f5031cc346 | note | Method - Nuclear Densometer Testing prior to Stabilisation
4e8611c9-3ea9-52ac-aedd-cbb5ff2ee9be | note | Frequency - ≥1 per 1000m² lot
ce075717-2abb-5591-9ca9-86d38488a412 | note | Responsible Person - Quality Controller
8ab85bc5-e0cb-5da0-82a9-24116b0fc86f | note | Verifying Document - NDM Record
66397266-caad-56f3-898e-a87fe92b160c | note | Conduct - S
3cb30e47-6595-54ee-a189-62f6b8655ec0 | note | Produce Record - S
a2ef28b4-946e-504d-ba24-84dfcdbcfbbf | note | Approval - C
7b8b0c3c-21e7-56d8-9b8d-330ef37a367d | note | Witness Point Y/N - Y
3aae6428-5972-5b13-a661-272c4bed881e | checkpoint | Cut Depth
30f7ba2e-96b4-53c1-96f7-d95820354a9d | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
ab4fb71a-78ec-52ee-a846-fe53de5563a0 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
df9ef84c-bffc-52bb-b829-6fdcaf24c3f7 | note | Method - Physical Measure and Visual Record
c4e2fc32-4815-534b-b0b6-fc294e6340dd | note | Frequency - ≥1 per 200m of cut length
410a12dd-bd59-51ed-bdff-d7e1387ed4c5 | note | Responsible Person - Quality Controller
beca68a2-a4e8-5bf9-b4c2-749eb4ecce8a | note | Verifying Document - Photographs and Daily Site Record
013b0d29-fde0-54b4-bafe-9b9bcb44be25 | note | Conduct - S
401dbe28-ef2e-5ab7-a393-06ce981fbc1f | note | Produce Record - S
b87513f2-737a-54f2-9b6b-e7adf03ab357 | note | Approval - C
1019d693-758d-529a-ba35-6981de5d0afc | note | Witness Point Y/N - Y
b4e8c8c0-519c-5ea3-a63c-d6e4e3e61d57 | checkpoint | Longitudinal Joints
e01cf752-cc82-56fb-aae5-eec327d766a3 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
f7a56f07-c330-5a21-b012-e6e1bef93601 | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
200c1a1a-5c6e-5fb0-a857-69c165e64d24 | note | Method - Visual Record
3c8046d1-2d10-5fcc-96b2-c00ab57d0a8a | note | Frequency - Per sucessive cut
cb91a565-6b73-560b-9d72-9b58b7a7355f | note | Responsible Person - Quality Controller
4ce96f17-69ab-57d3-99e0-57facb4c83b8 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
75c034c1-4aa0-5025-9923-0bb6134b4cc4 | note | Conduct - S
4f9ce1ab-ca59-58b7-81ad-8adedbeea058 | note | Produce Record - S
24a9aa7c-b322-5e13-bb13-841f1a5ea023 | note | Approval - C
3e7b9b60-0ba9-509c-aefb-f36021dabeb8 | note | Witness Point Y/N - Y
4adf91a5-413d-56e8-8c6a-9cb5dbaf546e | checkpoint | Continuity of Layer
4be95a31-a353-5d18-9105-8bed68773889 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
895292fe-9663-5a9a-8f8f-45a14437cbf5 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
f79dd426-f25b-519e-8dd5-b31021903bb4 | note | Method - Visual Record
d43df30e-e574-587f-b1bc-8a47bc69857e | note | Frequency - Per sucessive cut
4cf51790-cf3f-5457-8753-05860231d7d3 | note | Responsible Person - Quality Controller
996f540d-4d4a-53da-b61f-eb5a101e0e9d | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
9559bb3f-e8fd-5763-9cbe-d839a0c404e0 | note | Conduct - S
d0a8562a-db0f-5de6-b683-a716b3307037 | note | Produce Record - S
266ec5c4-7c5c-5a37-b4e7-22094ceeb916 | note | Approval - C
5c465a63-6080-5b77-af8f-55eb5a3eeddf | note | Witness Point Y/N - Y
b2669c88-ac51-56ca-b8c1-ca203b10eac4 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
03cb8cd2-c514-586b-92da-90dfc5c2ef1c | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
48184242-6e28-5de3-8c97-c88bd3cef74f | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
fb7208ee-0737-57ba-835d-58d02f238515 | note | Method - Plateau Density Testing
42eac297-3880-538e-91f9-701e0419da83 | note | Frequency - 1 time, or additional tests when material changes visually
27644623-ef4c-5fde-b6b1-5de7b2adfcbe | note | Responsible Person - Supervisor
0f2bacd6-eab5-53b8-8548-9dce41086d99 | note | Verifying Document - Test record
cf3d6837-29e2-5dd9-8016-73a48db440d2 | note | Conduct - C
5e19cabf-29ef-5b6e-8ef0-26ab858944ad | note | Produce Record - C
c397dd40-241f-544e-9e52-30ba087ddbd4 | note | Approval - C
dbbfdabb-21ec-50a5-ba51-17d9afdf4e1a | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
9e983bdf-65c5-582d-8a3d-fa3defeb18b8 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
5ba37dae-f79a-5bf9-9b63-b27aa705e0b4 | note | Acceptance Criteria - To provide MDD for NDM testing
564229c4-b7f8-59f8-af64-971ed2e3073a | note | Method - Plateau Density Testing
a5f5195a-acf6-58fc-9158-ec4e47376b66 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
9398415c-2ed6-5543-9f4b-3b2cfc6fd40a | note | Responsible Person - Quality Controller
0b50cce4-38b2-5458-bf23-ccf29f44359a | note | Verifying Document - Test Record
0df93eb0-002e-5c21-bc79-0208dd0faeb7 | note | Conduct - C
101818b7-9fd0-5268-9bf3-99d7e4f1205f | note | Produce Record - C
4953f85d-18fa-5bcd-9358-30be35d4c4ac | note | Approval - E
d16fbfdc-cff5-5746-a2d2-776f939523bf | note | Witness Point Y/N - Y
989ea8cb-93ca-594c-9179-b120567afd14 | checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (1)
e8bb7226-3bae-567a-b391-d4a371cb2803 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
8a13ddb5-d9b0-5679-a6e3-c932362210a1 | note | Acceptance Criteria - To provide MDD for NDM testing
1a341b26-337e-5905-adfd-b8cfa3f61834 | note | Method - Laboratory MDD at OMC NZS 4402 test 4.1.3.
a70b5989-3f42-5da2-89b8-bb967deffc61 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
746509a5-bca4-5b21-96b6-df4347e30907 | note | Responsible Person - Quality Controller
d5304820-1468-5994-be6f-8e25370a708c | note | Verifying Document - Test Record
47abeddc-323d-5bf5-9b48-1bdc59d72883 | note | Conduct - C
933e056e-965a-5f0a-a514-e448180d9c4a | note | Produce Record - C
58425621-8004-50ad-a18d-eb932b96336f | note | Approval - C
546cd4ff-7c70-534f-bb8d-0b8269ac38d7 | note | Witness Point Y/N - Y
805ca79e-8cfe-5253-a5f6-0212dd309f45 | checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (2)
5f144f1e-997a-5405-963b-91d0b4e97d8c | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
46c85c09-95c9-5c5c-922f-0af7b38e11b4 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
9d1e40d9-09c2-58fe-9b6c-f8fa604d5306 | note | Method - Plateau Density Testing Lab. MDD
f29eeb64-f818-5e6a-ad2e-cf6dd8dbbfa5 | note | Frequency - At commencement of construction and whenever materials change
2f31282a-2c3a-5032-a905-51d102a739d9 | note | Responsible Person - Quality Controller Engineer
3287b9d6-8ae4-5a8c-ac9b-dedf602933e1 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
b0a7bc5b-2579-5053-9b05-7adc4954b883 | note | Conduct - C
b25f5b1b-1d57-5e59-b914-0c00aefef21c | note | Produce Record - C
47edfeb4-e22c-58ea-b719-54d248ef2b49 | note | Approval - E
5d8e1c75-f810-524e-8c46-b55ceef54fd5 | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
36ce997d-ed62-506d-aae5-557e6e3e5cb4 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
c554c81b-5149-5345-8baf-f19ad9d44c3e | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
8020fe10-fa5c-5a49-8617-4f942c21ddff | note | Method - Nuclear Densometer Testing
a52d07f9-39a3-5dbb-b6c4-9a313c5b8305 | note | Frequency - ≥ 5 tests per 1000m² lot
330291ed-e0f1-531d-8bf2-21fea8f74d55 | note | Responsible Person - Quality Controller
12837899-97c6-54f9-8f22-b308185cfe92 | note | Verifying Document - NDM Record
64031f9a-c884-5c99-be20-e1538f37d704 | note | Conduct - S or C
e732a1d0-0d42-5a95-b746-86cfa20a8401 | note | Produce Record - S or C
2613a377-9cf5-59f2-a148-659962d1dfc0 | note | Approval - C
b8739275-ddc8-5c87-b5de-a22267b44ce9 | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
63ac480a-f8b5-58f9-bbf7-a763b61d12c2 | checkpoint | Surface Smoothness
06d2f169-857f-598a-ba66-c004d151c8a5 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
57fd63a5-e2a7-5cb9-8503-cc1ac3749851 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge
c958b681-8b7e-541a-96e2-7264d43f4a2a | note | ○ No water ponding
abcff95d-890c-5b31-aae3-95de9027f368 | note | Method - 3m Straight Edge
e49be42b-19dd-57bb-8cf1-d833d013cb4d | note | Frequency - during construction and prior to seal
0966857c-87e5-5c54-98ab-2437ded93cea | note | Responsible Person - Supervisor
edb0974c-fa44-5f97-855e-bbb15ed2d657 | note | Verifying Document - Photographs
2efbce71-09a8-50fc-ab1d-5de0b4473a11 | note | Conduct - S
263ad085-a0fc-5b6d-88da-4b159f68505d | note | Produce Record - S
788cfd46-3e44-5a63-bbe9-cd3f018da4e7 | note | Approval - E
dcf20f21-50f6-56ee-b8c2-ef8002655d03 | note | Witness Point Y/N - Y
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
1f6e52a1-c88d-558b-8b46-b4487c5620e6 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
1b04521a-034c-5cfa-b605-cefdcf1b63d7 | note | Acceptance Criteria - Between -5mm and +15mm
d42d499e-9609-5548-a054-6702ea24b666 | note | Method - String lines or Survey Asbuilt
691dbd40-a32a-5cdf-af70-b564aaf6e101 | note | Frequency - during construction and prior to seal
aff0fd63-4015-56b4-a1f3-e232f040272f | note | Responsible Person - Supervisor
972b4562-db03-57cf-bdfb-5db481ebb797 | note | Verifying Document - String Sheet/Survey Asbuilts
b68f9033-b648-52f7-9abb-ce357f9beab5 | note | Conduct - S
b0d98c9f-9f95-586c-a9ce-a90862ed98e3 | note | Produce Record - S
dc2c1155-a418-523c-90f5-61c296745eb1 | note | Approval - E
c3497d1f-3dac-5fbc-8c34-2c20e4a9ceeb | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
18c2480a-0828-530e-a1e2-bf2625b0dfcb | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
19f39249-ada9-572f-9a65-241b67501189 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
0ead94f5-934b-56aa-a5dc-2607c2c204c7 | note | Method - 3m straight edge or Survey Asbuilt
ebbb6f14-2f9b-512d-9c14-3e29c8b271d2 | note | Frequency - during construction and prior to seal
820acbf0-e8e7-527a-b5fc-1c003d11fef0 | note | Responsible Person - Supervisor
971c24cd-e9b0-5758-baa1-87a89d6be552 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
109d4716-f14b-5b87-b78a-b6c78eccde79 | note | Conduct - S
305a0829-648f-595c-bbe2-46c4fdbc62fa | note | Witness - C
5c93c9d1-03dc-599f-960a-40656a252cbb | note | Produce Record - S
3c5af168-ef13-58fb-83bb-77fe79856aa7 | note | Approval - E
fa74b928-ba0b-5b64-885f-37dbeaee8a9e | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
41bd56e0-119a-590c-bc3f-865bdf3fcb1d | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
9a00a9ef-6a14-5b2e-8ba3-ff75b7658fcb | note | Acceptance Criteria - Tightly bound matrix post sweep
d3f0c5c9-c527-5203-9258-2d61c2018978 | note | Method - Visual inpsection
fb9c19e7-dc5c-572f-9e46-0ebcd98dbe79 | note | Frequency - prior to seal
acff4ee4-bb9c-5cac-8fd8-091563e8e7c8 | note | Responsible Person - Supervisor
06dd6802-b89c-59b5-9d65-cc93da0a3f91 | note | Verifying Document - Pre-seal inspection sheet
1a581fe8-a59b-5d94-b105-11629edb267a | note | Conduct - C
67fd2d07-e2f8-568d-b5a9-048d50682306 | note | Witness - C and E
e51c64cf-f3aa-5103-a583-12bdafb098c1 | note | Produce Record - C or S
595702bb-eebe-55d3-aa0d-653d9c4d2ccf | note | Approval - E
522075a8-e36c-5160-907a-45a6b5a3be4b | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
460074f4-d46c-5626-8967-b968d5250680 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
375ebfe4-4421-50b1-ba26-8b3023578bde | note | Acceptance Criteria - ≤80%, however 65% is ideal
8aa993e9-7ad6-5a79-b95a-d5195ec115ec | note | Method - Nuclear Densometer Testing
d534ae6c-6403-5a16-91e9-5f011d57d2d5 | note | Frequency - ≥5 tests per 1000m² lot
42fb44ff-5c5c-5662-876a-6d4f0cb52bc7 | note | Responsible Person - Quality Controller
fb2c06e8-b48f-5665-b306-ce8c5aaa61f2 | note | Verifying Document - NDM Record
05b8a5d7-3aea-56c0-a803-8c2d17a273d8 | note | Conduct - C
549fd33e-eb3b-558d-bac5-573e2640c8ac | note | Witness - E
b54afb95-fb2b-5fb9-a462-dd37d4c53aaa | note | Produce Record - S
964c3c76-b64b-551a-bd18-78ba6f8eb5d2 | note | Approval - E
c389a605-190c-5307-bdc9-79aa7daa6677 | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
559dea9b-245e-53b5-9949-dd1b43eb58ab | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
d43e4f5f-6f68-54d6-9eee-d7b0fe46669b | note | Acceptance Criteria - For chipseal or non structural AC surfacing;
0d8546ae-93b1-5bac-8e6a-7c4e7c2ac27d | note | ○ No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
58718949-c431-5eae-99b6-1ee46d403362 | note | Method - NZTA Maintainence specification section 6.1.2
c5ab43df-8251-5e16-bd48-d5333510901c | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
cc28df5f-1a53-5789-9538-09020ea1d097 | note | Responsible Person - Quality Controller
b5a70250-93ae-5ce2-a0fd-40d4257d28ba | note | Verifying Document - Test Records
fb3a9ddf-e517-5275-83e6-4d5233fc9cee | note | Conduct - C
25c57d95-776d-5608-a74e-9841e2e4097c | note | Witness - E
5cf1cbf7-79e2-5129-99ab-cb28aebd78b5 | note | Produce Record - S
cdaec704-c4d6-5838-8c7b-654bb98f4985 | note | Approval - E
8693ff54-c2dd-5465-a320-ed2b084d4c42 | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
e474f2d8-47f5-5d50-98fc-f63f6e5b67cf | section | 4. Chip Sealing - 4.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
d8e417c7-93bd-56c3-aaa9-44b25b3b8c36 | note | Controlling Documents - TNZ M/1
9cf7dfb4-5ae0-54f4-bea3-df99cef5d25f | note | Acceptance Criteria - Table 1
2eb91e30-1a2d-5b6c-85a9-9128d01237b1 | note | Method - Property Test
b2b06d2d-19dd-5d1c-9b55-043cb3a35dab | note | Frequency - Annual
2a8259db-9d80-538d-bfa7-3742db249122 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
1d8ca4c3-ecac-5b93-ae96-2de0fbaf3b2d | note | Verifying Document - IANZ Report's
a60efada-3d83-51ee-8a0e-b47b00411b5b | note | Conduct - C
75a35704-2d3a-541d-9f75-a6ac9009952b | note | Produce Record - C
2c6a1a42-f1a6-5763-80e0-9aa5659357ab | note | Approval - N
f4da1adc-2299-565b-afec-a9c06787eea2 | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
b9ef1f89-5679-589c-bc0a-bea5910dc43b | note | Controlling Documents - Higgins Internal Specification
ebc583e7-f498-585e-99da-eb9a2182e243 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
962ace67-49cb-5deb-85ac-e3e923c6530c | note | Method - Property Test
02c56880-48df-5962-8a27-16573d8b6470 | note | Frequency - 1/100,000 litres supplied
4de8d547-1971-555c-a051-0c2c3000e0de | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
e3f2d783-bcd5-5ba7-8bfe-873803576f2e | note | Verifying Document - IANZ Report's
2ee42af5-b218-579e-8427-7e366a8ea5e5 | note | Conduct - C
118d20d3-7e1e-51d6-b0a5-11f88987a29a | note | Produce Record - C
3a599b23-b572-5015-80d3-668dd114bfdc | note | Approval - N
78a4ab07-4901-58e7-920b-a2bcbc9b1b18 | note | Witness Point Y/N - Y
271433f5-90db-5716-947f-66b53e064a88 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
86734254-8727-5ed6-a6d9-420dfc22d315 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
2b075c87-ff4c-5aa7-ac90-7ef574e592ce | note | Acceptance Criteria - <10% fines under 230kN minimum
6fc90323-f6e1-5ad4-ab6d-af96398ba14e | note | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
4f3df896-2067-5966-8ddc-209daaa0db3d | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
bd814a83-d0e9-5866-bd72-ef35c7d8859a | note | Responsible Person - Surfacing Project Manager
69bf3488-2c94-5673-9c5c-1f3da9d72512 | note | Verifying Document - IANZ Report's
450c5a52-9e37-58ab-9af0-6cbe7096068e | note | Conduct - C
6a59277c-0815-5426-b435-1db708f39933 | note | Produce Record - C
1afeac39-dd16-576e-9787-ba40d222d883 | note | Approval - N
fba53de4-c6f0-5096-9385-6564ea491f1c | note | Hold Point Y/N - Y
6001235b-048c-5705-ab46-316e6fddaf77 | signoff | HOLD POINT
b5105286-fa50-5f37-8ad8-ff00dc521109 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
8b0fee10-6f1a-5fac-8291-c423f33c35dd | note | Controlling Documents - TNZ M6, RNZ 9805:2009
dbea8ae2-df00-52c2-a297-cc7d34d2b848 | note | Acceptance Criteria - AA or BA
3c096184-33bd-5199-8096-ca2e320d2194 | note | Method - Weathering Quality Index NZS 4407 Test 3.10
8c899276-d86d-5111-825e-3a198106cc2e | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
c0e44374-ed5f-5e10-945c-3546077642fc | note | Responsible Person - Surfacing Project Manager
ec46c966-49de-50f8-8973-f0ceb8dae3e6 | note | Verifying Document - IANZ Report's
c640b430-d46b-5b15-99c5-06fd563faf85 | note | Conduct - C
1e353f15-8378-51a1-aac1-7457d768f500 | note | Produce Record - C
2daf90bd-c21e-561b-a289-2e39761e6a0c | note | Approval - N
4a24c2e1-8395-52ae-b63e-72b4c861e2b8 | note | Hold Point Y/N - Y
d36fb53c-673d-5ad9-bcd6-d21d23c23bfc | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
eb52e712-49a5-5cf6-a7da-bc33af8d9a54 | note | Controlling Documents - NZTA T/10
1c000715-c07d-5049-8cd7-8f3951cb8faa | note | Acceptance Criteria - Meet Skid performance Requirement
c7038591-d0e7-565f-8898-b00d826bc620 | note | Method - Aggregate Perfomance Method TNZ T/10 section 12.3
84c1206c-91f1-5357-a231-f67f973fa659 | note | Frequency - Each Site
f79879e1-36ed-5c98-a4c0-5c188af0a1e5 | note | Responsible Person - Surfacing Project Manager
1e1dc95d-274a-5a39-bf43-76be0a579789 | note | Verifying Document - IANZ Report's
3db106e0-c1ed-5304-a4f7-90e750b04972 | note | Conduct - C
3634c1d4-4139-5e73-857e-3ee103ed915d | note | Produce Record - C
20624166-5d76-5b99-943d-830bc5d7527a | note | Approval - N
24612a71-04fc-5372-aadb-fc1746dc45dd | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
15f0f957-f3c6-5489-9856-54901a51f6d2 | note | Controlling Documents - NZTA P/17, M/6
2d2c74fa-e6de-5012-ac78-12314d64f843 | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
6882d3e3-5079-5bad-9df8-163e1e7a60b9 | note | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
53b7b940-6db2-51dc-9f2f-acda0191f462 | note | Frequency - Per Stockpile
7f80b8d8-f145-51fd-b780-42a0178a9f63 | note | ○ <100m3 - 1 Sample
fbe8ffb6-020a-53fe-844f-ef438263a622 | note | ○ 100-500m3 - 2 Samples
7c6673e5-3169-518d-9766-eda0f947cc5c | note | ○ >500m3 - 3 Samples
06d856fb-53c4-53b0-97e6-03d76424ea7c | note | Responsible Person - Surfacing Project Manager
d8705049-09ea-5789-8e06-5ae623a7a7f6 | note | Verifying Document - IANZ Report's
8d4de111-b9ca-53a2-960e-1f0df4ba704b | note | Conduct - C
695d8308-5c59-5d7a-bd4b-909c6ab08dcd | note | Produce Record - C
2413b513-bf62-5f11-8110-8e7c8bb7a4ba | note | Approval - N
e21f2b44-7cb1-5a80-b2c0-21114834ed2f | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
b5005132-c832-537b-9085-226bf954bf30 | note | Controlling Documents - NZTA P/17, M/6
855e0350-85f5-5105-a5b4-cad9d873ac2e | note | Acceptance Criteria - As per Table 3 NZTA M/6
1a9b5841-6fff-5cc2-92b8-8ff924a6f2be | note | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
704082dc-d0fa-5e75-9f66-56853027c1d5 | note | Frequency - Per Stockpile
cf387e03-91b7-5d52-bb9f-d44a6d196542 | note | ○ <100m3 - 1 Sample
b87e0d97-ee58-5950-b493-8691b04dd016 | note | ○ 100-500m3 - 2 Samples
19bfff5f-089b-5275-b430-9754dbe77be1 | note | ○ >500m3 - 3 Samples
84fde6e3-bcfb-5a07-8aad-c26cfc10a319 | note | Responsible Person - Surfacing Project Manager
56f0d4d1-6bc7-58ae-a44f-25d9fa5e0dbe | note | Verifying Document - IANZ Report's
6dfcd8ea-532a-5b76-ab2e-5c58fe5bd158 | note | Conduct - C
8dc2f274-bcf1-500a-86f4-0e8801be87d7 | note | Produce Record - C
d868d0bf-899d-5d05-9a46-8a9a18479262 | note | Approval - N
61020613-953c-5d1e-92b6-4efc0ec4f533 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
fe3385da-2a9d-5595-9a19-879ebdfdd446 | note | Controlling Documents - NZTA P/17, M/6
c5b1fc04-b21f-5214-ba9d-2fef0cfd9c2f | note | Acceptance Criteria - Min. 98%
e1d9f6ce-a57a-58b1-b9b4-9377bb280889 | note | Method - Sample Test - Broken Faces NZS 4407 Test 3.14
386f296a-a6cb-5166-bd67-2ee4adbb6e24 | note | Frequency - Per Stockpile
0a9f643f-dd19-5365-bb1d-eb2a4439c15e | note | ○ <100m3 - 1 Sample
be738548-bd1c-5f03-be72-81562ea6f438 | note | ○ 100-500m3 - 2 Samples
40b98861-3a8f-5021-a013-56326ccf7731 | note | ○ >500m3 - 3 Samples
88e31d05-f1e1-5bcd-baf4-31234b55273b | note | Responsible Person - Surfacing Project Manager
34f2f2af-5ae9-59de-8270-13776ea814ff | note | Verifying Document - IANZ Report's
7498b327-93c9-55db-ae82-85d8c9487e68 | note | Conduct - C
80951682-ac17-5806-ba39-59dde4bbc652 | note | Produce Record - C
3becfbc3-035c-5837-aae0-54266180236e | note | Approval - N
e50c5e32-6715-5b65-b8f1-bb40355657b6 | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
c965692b-394f-5484-baf4-020db740a04d | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
65390f31-fa4c-5f6f-b335-3913c963be51 | note | Acceptance Criteria - Client Approval
94334e9b-a17d-5914-8a6a-0a3d9dfb40c8 | note | Method - Review
a66db1a5-ecca-5ab1-b21e-ccfdf1b955a5 | note | Frequency - Annual
41199f82-ee4c-51b0-bc0a-629314e7073e | note | Responsible Person - Surfacing Project Manager
b3d7dbfa-b7a6-5d28-83ad-b1afae2b6074 | note | Verifying Document - EBOP NOC Design Report Acceptance
d708f5b3-0db7-50d5-a5f6-d5ac7d9a023e | note | Conduct - C
ba7fd5f6-94b2-5dca-96c9-78363878f116 | note | Produce Record - C
ff30572c-7d25-5e5d-909c-5f598140ccd6 | note | Approval - N
37b9534e-7cd7-5c0d-9ad6-87aa7733a78d | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
ad1da6e3-fe6e-5b5e-b09b-144bb42ed8ce | section | 4. Chip Sealing - 4.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
9768fb20-a7fd-50ca-a101-15413961e316 | note | Controlling Documents - EBOP NOC Design Report
c480b0a7-66f3-51a3-a27e-07cf2c5cad98 | note | Acceptance Criteria - Visual Inspection
eacc6c44-560f-5a22-b859-1d4f42edfe2a | note | Method - Visual
d0ecaf70-2301-5b8d-8b99-2c9a0e23d307 | note | Frequency - Prior to start sealing each site
936d5184-b971-5a01-9354-18b5d555a2b3 | note | Responsible Person - Surfacing Supervisor
a840cc50-d37e-5e51-aa08-895af28e73ad | note | Verifying Document - Chip Sealing Quality and Site Record
e6d276f6-daf1-5780-a12c-ba4056d24581 | note | Conduct - C
36b428d9-c43a-5e6b-8d20-3cf8e007ce85 | note | Produce Record - C
b582b7d7-7736-530c-891b-5efc15ce6d3d | note | Approval - C
07dc5a9b-c52c-5213-bfb6-f891635d0cf5 | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
0c0f2983-3889-5d91-b56b-6f76a3545e50 | note | Controlling Documents - P/17
2386b960-0c8e-54b8-be23-6781816bf5ce | note | Acceptance Criteria - Visual Inspection
fb94fcbb-4d59-53e5-a85f-757e892d079f | note | Method - Visual
fee9fabb-8764-5a3f-9af0-9a4c66ca3950 | note | Frequency - Each site, prior to start of sealing
61c5b7e9-d110-5604-bfc1-57e5fb8aa891 | note | Responsible Person - Surfacing Supervisor
07add028-0dc6-5f22-ad71-a53cc5a2edc7 | note | Verifying Document - Chip Sealing Quality and Site Record
17342240-401a-5bb8-86ee-fb35bd5c7e4c | note | Conduct - C
7a880a13-07e7-53bf-b63b-da766e178202 | note | Produce Record - C
495e2765-08d1-5b88-b6f8-2f771f31b61b | note | Approval - C
598aae50-4352-5f25-8e6c-9c21df2a7fee | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
3d0e888b-c5aa-5349-b4a0-abdd822c8250 | note | Controlling Documents - N/A
9aac35f8-7521-5d24-8357-288f2636d9a4 | note | Acceptance Criteria - Visual Inspection
f4afaf15-9d5e-58cf-ab9c-3bde2782dba3 | note | Method - Visual
fed335f2-e4ab-552e-b3ef-8a6f9c23e541 | note | Frequency - Each site, prior to start of sealing
214b01e6-443d-5173-8886-b2bd278f5ef0 | note | Responsible Person - Surfacing Supervisor
a788fbf2-fe41-5668-94fa-c0bbb32b5abb | note | Verifying Document - Chip Sealing Quality and Site Record
6f51bf6e-38a3-50a9-8286-9051cc703bb0 | note | Conduct - C
aea3b434-6379-525d-aa00-72f57a7610c3 | note | Produce Record - C
2d2c973d-91dc-5437-b324-a8bb8198bc40 | note | Approval - C
68a3285f-ce2b-5b1f-a598-2f8cca6e6bcd | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
699e59e4-e9c9-5c1d-adee-5f5da4deef01 | note | Controlling Documents - EBOP NOC Design Report
b97e4954-696e-51c6-b919-cbf8c87e2671 | note | Acceptance Criteria - Details/chip correct
f1798d77-982a-51b8-a4af-e370294c90ba | note | Method - Visual
b097adab-5559-585e-b81f-b71285025001 | note | Frequency - Each Site
381cbb01-d8a7-5ad4-a74e-ce6a1e6e7211 | note | Responsible Person - Surfacing Supervisor
2db3a573-ca1c-59ca-8719-9bc0391cb4ca | note | Verifying Document - Chip Sealing Quality and Site Record
53373869-f722-53fe-a8a0-3a6b316b4b4f | note | Conduct - C
8b0a557b-cd59-5dfc-8bb3-0fd3e2229756 | note | Produce Record - C
a499251c-82ca-5e4d-90cd-0427ea3a7b21 | note | Approval - C
e3da9b70-7f26-549b-a856-bb636469c449 | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
598f8d05-260f-5ca6-9ba6-a4be1fab71fb | note | Controlling Documents - RNZ 9803_0513
088bb7d3-1fda-5b2d-b98d-1171702ec4f0 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
a49beae7-40d4-570e-b32f-73798e605fa3 | note | Method - Sample and test
68abf7b0-d2ef-5505-932b-29d7a30de3cd | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
4ea0ad88-d96d-5653-8c07-d77bdf487139 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
22a32490-d87c-5ac2-8e9a-2653826581bf | note | Verifying Document - IANZ Report's
4cb19777-eff5-5949-b85a-4586c12850b8 | note | Conduct - C
e404769a-b27d-5784-ac0f-caed627a802c | note | Produce Record - C
ac3370e6-a77c-5ffd-b209-037545ef7d17 | note | Approval - C
d836146c-2f39-5164-be5c-26217c4bc6b1 | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
0fa7bb77-9245-58a9-87b1-9914f89df592 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
da45b4f7-fdb5-50ee-9de8-9219370c1060 | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
dd1aeb9d-416d-5805-baeb-c1a1c720969b | note | Method - Test, Review
f1ddf702-3549-526c-b6ef-e30fe3ac6b66 | note | Frequency - Per Sprayer, Per Site
c67eb7ab-ab4b-5264-8f63-59b67da5eea6 | note | Responsible Person - Surfacing Supervisor
5585266b-3c84-5c1d-ace9-4d1617b1636d | note | Verifying Document - E/2 Certificate. Spray Sheets
b50c3499-99e3-5b7d-8eaa-e69c81034548 | note | Conduct - C
94aa4af3-2c6f-5eb5-b8ec-a2fc4049de29 | note | Produce Record - C
ed64325d-9530-50f6-871f-6b63be7fd24e | note | Approval - C
552f7318-b798-5daa-b5f4-403e48d2fd3d | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
414ffe68-9bb6-58f0-b2f4-039c67f157d6 | note | Controlling Documents - Chipsealing in NewZealand
6173183d-0eb0-55cc-bfcf-c2386af57bea | note | Acceptance Criteria - As per Chipping Guide
c8a21634-2724-5fb1-b4e8-1a666fb786a3 | note | Method - Visual
a3d4cd18-77b1-5579-b3c3-11fd0ba0a818 | note | Frequency - Each Site
f07b3161-0d9c-572a-8ef3-a27f4dca443a | note | Responsible Person - Surfacing Supervisor
1e6ece2e-5f4d-597b-8841-ff1db254d57c | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
42128b7e-f80d-5d7b-931d-8b312bf0f014 | note | Conduct - C
1ceae8e1-216b-57b3-89e6-ea23e6b3c931 | note | Produce Record - C
02c71231-0d48-558b-8e2c-8a53c509b290 | note | Approval - C
41a0f17d-e93d-578a-9701-f538bfc2b363 | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
74d39f58-428f-55c0-abf6-204e967a1107 | note | Controlling Documents - Chipsealing in NewZealand
97bb8b93-58cd-55b5-a820-d9b8a1427deb | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
ccd1e65d-d237-562c-b649-8df5f9a1f808 | note | Method - Visual
c7fe88fd-f827-54d4-8b7d-5145741349d8 | note | Frequency - Each Site
c484f8bf-5f96-55f9-a840-f33d79399fb5 | note | Responsible Person - Surfacing Supervisor
cf8623b0-c8bb-50e1-9cb6-c4af967b1833 | note | Verifying Document - Chip Sealing Quality and Site Record
5ccea7b8-3ee4-54a0-b13a-b4ad057eba9a | note | Conduct - C
274a1409-d82a-5f83-a62f-652d1f464bc7 | note | Produce Record - C
9b64b377-b49b-5db8-a3b7-166c1b384807 | note | Approval - C
b9423ab2-d7e8-523e-b308-ffc0f80e1265 | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
d37579d5-5c33-5791-9300-047263d8f512 | note | Controlling Documents - Chipsealing in NewZealand
f6877094-17bd-5ff5-99dd-959d223ee987 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
54500165-86f5-5fb7-b063-47ac791f618c | note | Method - Visual
f3eaa2e2-384a-5cc6-961b-9ab43d4440f4 | note | Frequency - Each Site
1c215086-6b01-5491-913c-4650ccd95c32 | note | Responsible Person - Surfacing Supervisor
eb9b5917-e603-59b0-bdea-25d07824ea54 | note | Verifying Document - Chip Sealing Quality and Site Record
3f375295-b343-58d8-97cc-f14f9ab01bb6 | note | Conduct - C
fb718ac5-f689-58d4-857d-688d806a5c3d | note | Produce Record - C
a2cba819-edd5-50fb-8002-998c78a886d6 | note | Approval - C
3c74cdb0-afce-58f8-9ce1-38c1b4e9491f | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
c799f3ce-6812-5e69-a03a-f8e786913d61 | note | Controlling Documents - Chipsealing in NewZealand
57b9acdd-06b6-55dd-a54b-cb6bb32c93a8 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
7a313514-e612-5df2-b8bd-e0570698b4b9 | note | Method - Visual
28f8189a-09b2-59e8-9e22-e8fe2c812de1 | note | Frequency - Each Site
c4280342-fb98-5e8f-9bf3-826ba82b7543 | note | Responsible Person - Surfacing Supervisor
a99f7dd6-150d-5421-a208-ac1fb51e3da3 | note | Verifying Document - Site Record
a7bd2f31-eab5-504a-93d4-351e0891f8bc | note | Conduct - C
a9dda60e-1492-5063-9276-034919934554 | note | Produce Record - C
efb12b9d-16ca-5559-a7b9-a2956063c753 | note | Approval - C
b1650407-7cba-5a6c-a586-4361e3e4c609 | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
9da4158d-4934-5aca-afab-74e10ddd5c45 | note | Controlling Documents - MOTSAM
fec5ae4f-eb4d-5119-beda-d7708e8f6082 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
71d9c448-ff9c-5b08-84c0-e6ce74387049 | note | Method - Visual
62c51062-6a96-5d51-afd4-adc226175675 | note | Frequency - Each Site
c0a089a8-1dc3-516f-b615-67067ed91db1 | note | Responsible Person - Surfacing Supervisor
0b15bba0-a841-5a72-9bf1-f24d2f8c8d3a | note | Verifying Document - Site Record
b558a381-20c0-5df4-aa4e-c5a9cdffefa2 | note | Conduct - C
2fd83b8b-a2ab-56fd-abb1-f30e5904475f | note | Produce Record - C
f7f66605-35e9-539b-acfe-1ef0739e917f | note | Approval - C
afe770f3-d55b-5592-bbba-3787825540e5 | note | Witness Point Y/N - Y
4f1135f1-33a8-5ccf-87e2-4ab44989b7ec | section | 4. Chip Sealing - 4.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
8c726c12-2d9d-5524-bee2-9e7c664fcd77 | note | Acceptance Criteria - Formal Agreement
f6e2bf57-7110-5bfa-b8f0-7c5c4fe45019 | note | Method - Visual Inspection
dba7bd4c-6bb2-54a4-ac60-494d665e7572 | note | Frequency - Post seal sweep
f6d75c50-9505-58fb-9bc1-7f4005716f73 | note | Responsible Person - Quality Controller, Supervisor and Engineer
43f721a4-9f2d-5536-8fc6-1ed085d2eaaa | note | Verifying Document - Meeting Minutes
3668014f-b6d4-5d6a-9176-0b93b12ddcf2 | note | Conduct - C
d878fb04-a16d-5762-baf3-6ce60258befb | note | Witness - C, S and E
ef7752f2-acff-59f9-8e9f-1fd32eb993d7 | note | Produce Record - C
ff7a2f08-c877-5ffd-8b8b-f90bead61f3c | note | Approval - E
08a564ba-0499-5a71-b6a6-397be0ab8783 | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
8534892e-729d-57f9-a81e-109aea656b5a | note | Controlling Documents - NOC; MS 6.1.3
21b07152-0379-59cb-a892-1ab7309dbb25 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
e1988a2c-ad9e-5daa-b6a4-bf7710ec6305 | note | Method - Record
1b46ff72-df8e-5df1-a9b2-4cac26e5be98 | note | Frequency - Within 2 months of completing the annual resurfacing programme
b3a42740-7be7-5cd2-b494-a682c94e1146 | note | Responsible Person - Surfacing Manager
8f1f8136-9067-5430-b999-5fb52f8d65bc | note | Verifying Document - Construction Completion Report
de3ed758-bf28-5898-9e99-b694e0b79e3c | note | Conduct - C
2d7e9966-0e0d-5fcc-bc5f-c8e55b407fc1 | note | Produce Record - C
26f70d32-ad12-5e50-b6d5-7887c3b13ba6 | note | Approval - C
37375258-aae9-507c-8f5b-65c36147a578 | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
5e6456de-ae93-5eef-804b-e3fe90d2e144 | section | 5. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
66e0e989-a548-5c0d-a92e-dfc5b99985f7 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
130c5cda-2635-5117-987c-6385d4c807e1 | note | Acceptance Criteria - Engineer Approval
abc0c4c3-a4b2-5fde-a357-434e9637fe52 | note | Method - Visual Inspection
eab41298-557c-590a-866f-73f6be262f2c | note | Frequency - ≤2 months of 1st Coat Seal
92d4c73a-46dc-5294-bbc9-cacdfad410af | note | Responsible Person - Quality Controller/ Contract Manager
3aed72ba-7bea-5878-ab8a-5ef2f3102a4d | note | Verifying Document - Signed Report
1168663d-8f16-5828-9a79-93789932c41d | note | Conduct - C
31ed2053-3c86-5016-a383-0c30f599f1ab | note | Witness - C, S and E
cabdc166-1116-5d77-8f46-79e4e1d3002c | note | Produce Record - C
0c23a7fb-82a2-5886-8bdf-c142f90263c5 | note | Approval - E
46534750-ebb4-56aa-85ae-052b587fe6f4 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
7546f041-e4b6-5fbc-b34b-a8b652973dc8 | checklist | ITP - Pavement Rehab - SH 02 - Waiotahi Valley Road | itp | ITP - Pavement Rehab - SH 02 - Waiotahi Valley Road
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
09dfa698-6b7f-519e-b940-013fd716a19e | checkpoint | Design - Geometric Design
93f379ec-5a76-5a57-82c2-d5d911944cca | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
69c6c965-7605-5380-ab3e-d4e595a5ec8e | note | Acceptance Criteria - Principal Approval
de5cc030-5876-55b1-8f8c-ac9b259497b5 | note | Method - Contractor and Principal peer review
44856f54-1102-5c24-bbd9-e615237b11c7 | note | Frequency - per design revision
9707ebec-56d4-57b4-b39a-1dfa848a98ba | note | Conduct - C or S
9e356456-3b20-5133-90a2-0c0f4bce5b05 | note | Produce Record - C
ece21ca5-05d6-5788-b43a-f0d80f957098 | note | Approval - E
c2b5d660-77e8-546e-8015-8dc6a4549c41 | note | Hold Point Y/N - Y
734b8921-df80-5868-90e2-320abcb6aec9 | signoff | HOLD POINT
fc457da0-71e7-5429-a676-cfa9f8ad8762 | checkpoint | Design - Pavement Treatment Design
fef820ab-16d1-5e65-95b9-0a0de0496611 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
f1e0b623-37cf-50fc-87dc-4b238c4cbec6 | note | Acceptance Criteria - Principal Approval
f0a69056-690c-5463-91db-900b26fefc68 | note | Method - Contractor and Principal peer review
604aa294-7a6e-5dc7-9a52-7432805be655 | note | Frequency - per design
c0c4e32e-219b-5d6b-958a-2485ab52b835 | note | Verifying Document - Pavement Rehabilitation Design Report
1b59fcbc-6ab7-5ad2-a9b6-4995715e631d | note | Conduct - C or S
b8992621-c38a-5349-b101-93ab028b46df | note | Produce Record - C
8dfa7993-f0f4-5a41-9152-2024e283e870 | note | Approval - E
703a3b61-8318-53ce-96a1-60cfa215cd05 | note | Hold Point Y/N - Y
f7622f1f-ef56-5ab3-b6af-8b3b9e5d5f72 | signoff | HOLD POINT
36362436-b1e4-5e95-af81-437ff9bbd938 | checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
e6ff7371-c568-5d5f-a474-9c55dee4d4e6 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
b6fb45df-f8bf-5db2-85f2-6546a2f90e1c | note | Verifying Document - Sampling Worksheet
7e328f0d-a03a-5806-889b-c6fccf5d9bec | note | Conduct - C or S
785531d2-3a54-598c-8d02-79b86dc7e960 | note | Approval - S
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
492a42bc-d4c3-5258-ae81-19d0b4c4269f | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
3cb6f558-642e-5865-ba61-af2f1e5d5ab1 | note | Acceptance Criteria - Soaked CBR ≥ 40
7f8912fe-1f4d-5661-b19f-2f321d3a6839 | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
671c71ce-37e8-5f09-98ce-dd6d4fa6b68b | note | Responsible Person - Supervisor
4a097548-c821-53ca-ba23-d4ce36190f9f | note | Verifying Document - Test Report
3cd07b69-dc35-594a-bdff-f4044707e5c3 | note | Conduct - Sp or C or S
e3aff20e-f95f-5e53-bd24-2294f9f72b2a | note | Produce Record - Sp or S
6c3b398d-574e-5615-868d-fd4242b6e6e8 | note | Approval - E
084ab794-ca17-566a-be0e-20b1a519a22a | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
ae7e2d83-e996-5777-8251-1ac263229947 | checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
a5f97ba2-de2f-5390-973a-5e15811dc4d6 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
999d730c-e3a5-5107-81bd-071a8bc4490c | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
b0e271da-7b99-5c63-9e30-daae68f15db9 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
0427e10d-97c7-50d9-b086-0adfa1e15b7f | note | Responsible Person - Supervisor
a04beac1-49dd-532b-9813-3f1cbf37a0b2 | note | Verifying Document - Test Report
3901a464-79ab-5c5d-9829-364fa9632365 | note | Conduct - Sp or C or S
34e3b0c8-8e71-5446-bc30-4e718d3050ef | note | Produce Record - Sp or S
bb1df76d-564d-5cb0-8f38-60385d54260b | note | Approval - E
e01668f1-8ebd-5839-b915-f2d55e689935 | note | Hold Point Y/N - Y
59b9d644-63f9-5af7-bf31-75c1a6bf1a10 | signoff | HOLD POINT
282d13fa-6a2e-5570-b955-78f6c0062fd3 | checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
97daea82-3933-586a-aaad-eef4648e1106 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
43af55c8-4252-5c11-bdcf-a7964c94d438 | note | Verifying Document - Sampling Worksheet
19b6d86b-bdd4-5d23-8c3b-38570c4103e5 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
a574de35-3e2d-5797-9f67-5899724fb4d6 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
fe48357f-8da2-51b6-9917-9eaff2089e8f | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
dd246dca-a8dc-5b42-a6fe-39aba73c622e | note | Method - Crushing Resistance Test (NZS 4407:1991, Test 3.10)
4640ab3b-a914-5928-8f33-a832dcdca336 | note | Frequency - One test for every 10,000m³ of source material
6e5c2e57-d1ec-53b9-875f-5907ac4770b7 | note | Responsible Person - Quality Controller
bc9a862a-ae54-52ce-bd2b-d13b7d4491b7 | note | Verifying Document - Test Report
9ac52143-505e-5eea-9fb4-3afb80f7d6db | note | Conduct - Sp or C or S
f948addf-f72d-5702-83f7-0a22eacbe703 | note | Produce Record - Sp or S
cba877c7-e0c1-5672-a0fe-d1cef66b180c | note | Approval - E
df461267-d09e-53a3-826f-73b7a73cc468 | note | Hold Point Y/N - Y
2bce147b-57e0-5df2-aa19-d3114e0f900e | signoff | HOLD POINT
771bbcd5-e52e-5af5-9fc3-2a5ff6956b1d | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
0dafde7f-9f8a-5812-8b71-3ac4084a2782 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
4583c0ef-8842-5484-8599-55d3a72b0fb9 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
078564ea-6c85-5152-b1aa-633ab9f7040b | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
6dac58d7-3e2c-52f0-bd44-6efd0347a2f7 | note | Frequency - One test for every 10,000m³ of source material
4e1e61b5-602b-5534-bf60-3817267336ac | note | Responsible Person - Quality Controller
6184dfe1-716c-5084-a455-23c6d78f2769 | note | Verifying Document - Test Report
1a8933f4-ad81-516d-bd1c-70c8600e96fa | note | Conduct - Sp or C or S
0445dffd-dca2-5458-b632-890d4da7f148 | note | Produce Record - Sp or S
b6d1c850-f037-51fe-a660-df70eb42c85b | note | Approval - E
0e06d4d2-f02c-5c70-a6ea-32b0ea525be5 | note | Hold Point Y/N - Y
5de343b7-b3e0-59f2-8f5e-085d4a8c0fdc | signoff | HOLD POINT
113f3833-1e06-55b9-9978-c5d36d530658 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
105475b1-4d15-5c23-84d6-ca9cb8ccadca | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
f0a9e98f-29ca-5067-a779-84e79b128ac6 | note | Acceptance Criteria - Soaked CBR ≥ 80%
a1fdb781-271e-56f2-885b-ebec296ba5a6 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
004aafb8-a8f0-50e3-a41c-64af2e3dee3b | note | Frequency - One test for every 10,000m³ of source material
54518a95-c48c-5cc6-9630-77020f4fb6d4 | note | Responsible Person - Quality Controller
98d8f9bb-bfca-58d5-83c1-51a9d194fcdc | note | Verifying Document - Test Report
028241be-8cc5-5c7c-a473-ea8a33d335fa | note | Conduct - Sp or C or S
514b40af-d3f5-5fb6-a336-a12c6581a38f | note | Produce Record - Sp or S
2ff9049e-5c10-525a-8203-03b9acbb710d | note | Approval - E
64e4c581-efa3-5d19-82fd-97ab0b83e3c9 | note | Hold Point Y/N - Y
40c2302f-cce5-5c54-87be-1069cdfc7929 | signoff | HOLD POINT
976c9ab2-336e-5bd7-8941-60563e8cfc82 | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
8033ac96-4261-5266-9fdc-3059b2ed4976 | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
e0b45140-5023-51d7-97b6-e7efd23b0076 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
cae988e9-6a59-55f5-a2d2-dff66f774f6a | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
fd976a5b-387a-5b0c-95a2-a223be71c584 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
46f62571-c036-5ff1-84d4-3ca0404b2062 | note | Responsible Person - Quality Controller
d6be2185-d2fa-5d3f-b46c-00218b13078a | note | Verifying Document - Test Report
b5071349-5a7e-53f2-9df5-a3737ac549a9 | note | Conduct - Sp or C or S
5c022f1d-819d-5972-9570-ecbbcac5e350 | note | Produce Record - Sp or S
ca210dd3-8e23-559c-bd0b-17cddb252737 | note | Approval - E
00bef305-f90a-5a8e-b559-5223e3b877c0 | note | Hold Point Y/N - Y
8c291f12-658c-5f73-81d4-ac64eaf7be26 | signoff | HOLD POINT
21f389de-1666-5508-9d06-5a4f024a4cbe | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
c9d058f9-ea28-50bc-9211-6ea4efe416e9 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
05a90f6e-c12a-5a13-84c3-6c6d781736b1 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
f771883d-368f-5fb6-b0ad-0cd1ff17920b | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
82178f47-7613-5225-a472-c8afc24baae6 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
60ee3f7b-bfcc-529a-843d-bac96fa2752a | note | Responsible Person - Quality Controller
5d3831c3-35cb-5ed3-80cd-ac5132212677 | note | Verifying Document - Test Report
66d0a02d-f34d-51ed-a980-104f72fbf47b | note | Conduct - Sp or C or S
08555e1a-2ce1-530a-bd5c-fe74fcbed5bb | note | Produce Record - Sp or S
39eedea1-41a8-5737-a02e-96ddf2c2209b | note | Approval - E
eed1c5cb-b914-5428-a345-f4116331f29d | note | Hold Point Y/N - Y
f50c0087-ac9f-533c-9dad-f1906513e000 | signoff | HOLD POINT
66a6116e-307f-5697-aa3e-d266fb4bd96f | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
469bc0e0-232d-5457-b133-3531c1cc96f3 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
70447507-1b6a-5920-aef6-e48383562d22 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
3cf6e5a4-df2c-5e8e-9c58-9d710218b149 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
c6b6f7de-8992-549d-8cb4-6021fb093e2e | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
7881e1e1-bf41-5335-badc-4dcc02134f75 | note | Responsible Person - Quality Controller
43a19383-36bb-5bb2-8190-6fce16804808 | note | Verifying Document - Test Report
6c9a335d-9069-5464-aa7c-85cf23ae3914 | note | Conduct - Sp or C or S
8b3fbcdd-0b14-576c-a687-0e207a5fca5b | note | Produce Record - Sp or S
1870ee5f-d224-5e28-a988-4f4078ff7863 | note | Approval - E
2e3f6363-15e2-542a-907b-89f1d9f36c06 | note | Hold Point Y/N - Y
7ecc9215-ad8b-5530-b3e7-13982b2273e0 | signoff | HOLD POINT
288f3247-2eba-55d4-ae79-89580bc4bef3 | checkpoint | Materials: Cement - Stabilising Agent Selection
36bc8e12-f275-5b65-8101-d36b4f75a950 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
d587ed48-7b0d-5372-93bc-23c5d74414b2 | note | Acceptance Criteria - GP
dbf961fe-d423-5bc0-a24a-1314d76abd23 | note | Method - Visual inspection of supplier docket
f7c6b1d9-4f05-5141-a072-e8dfc76dcb5e | note | Frequency - per truck load
c1a2233f-56bc-51e7-ab7e-f38938bbb74a | note | Responsible Person - Quality Controller
64b9ee9b-5960-57e4-808d-ffd570113f3e | note | Verifying Document - Supplier Docket, Supplier Cert
69d63524-7fe7-5f2e-8e6b-f5818054e77d | note | Conduct - Sp or S
fa448b27-41c9-5ef6-a3d5-918c9f24c88d | note | Produce Record - Sp or S
8ac9be4f-6f68-535b-b347-9e416cc8dbb4 | note | Approval - C
6411bc57-fdf0-5277-a39a-12e7bf009d84 | note | Hold Point Y/N - Y
4c5e2924-c37c-5329-8e7e-217f3be76a22 | signoff | HOLD POINT
5fe70724-8f32-50a2-8961-1dac348f79c6 | checkpoint | Materials: Water - Water draw for stabilising
ecf6d9d9-45b0-5794-b0ca-8f271a85f2a9 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
c65321df-4671-5115-abde-1dd4b10ea2e7 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
8f744c97-f2c9-509b-8114-9c861a2c126d | note | Method - Visual inspection
8b11e954-49f0-5086-8713-e197e3d03438 | note | Frequency - per truck load
d0d4b16b-4bb4-5522-a690-91d116393019 | note | Responsible Person - Quality Controller
c535c376-141e-591a-adb4-21c83f391fe2 | note | Verifying Document - Hydrant use form
ce9f7742-dbba-5f1a-ab87-e0dfe55fb827 | note | Conduct - Sp or S
02e3376c-1176-551a-95cf-1863b1a089ce | note | Produce Record - Sp or S
4164720b-f667-56d6-9a82-4baeced0504c | note | Approval - C
50b540e0-0b6f-58f3-a453-647654166724 | note | Hold Point Y/N - Y
20a1edd9-bdbe-56ed-9252-c68d03654979 | signoff | HOLD POINT
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
c2da3199-f696-55c8-b737-922301e5d486 | note | Controlling Documents - TNZ F7 Specification
40c49783-c870-590f-b03c-e265d77890bc | note | Acceptance Criteria - Details on Docket
e0b7a7c9-e266-5b27-93be-a87495dd18f4 | note | Method - Visual inspection
d58c843c-a87c-5fb3-a032-f3ed97b7003c | note | Frequency - Per Delivery
20ef4adc-7f17-5e61-810a-a43d336c09ac | note | Responsible Person - Quality Controller
f13f9c6b-b3eb-5ec8-8c54-9c2f32e9bdd2 | note | Verifying Document - MDS
a2499dcb-6545-579d-b92b-c41524dd1a0f | note | Conduct - Sp or S
0936b60b-74bf-5588-9c1a-64d8a449ddcb | note | Produce Record - Sp or S
b284ea08-8f73-54e7-9f2d-93ff25f358c0 | note | Approval - C
e0e5a13b-5716-5f6a-b67f-8a531a8e1f28 | note | Hold Point Y/N - Y
e7ab7dcb-bdc9-555a-a417-f0efe57b5add | signoff | HOLD POINT
f2243fec-ad92-567d-bb3c-12058747fa66 | checkpoint | Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent
e3913ceb-29ab-5f65-a224-36ee4eb82347 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
486f969e-269d-595e-b4f2-812bd4054352 | note | Acceptance Criteria - Details on Docket
a6b11492-b886-53ae-9c67-b537adc4a01c | note | Method - Visual inspection
dcee9d24-5006-5f44-936b-21202620f394 | note | Frequency - Per Delivery
4473b692-07ef-5be0-a22f-5f0ba87d2e03 | note | Responsible Person - Quality Controller
1cb8dc53-0a38-5ccf-806e-46be8de47ed5 | note | Verifying Document - MDS
517188fa-9be7-58a6-bf62-e958bbcee8c8 | note | Conduct - Sp or S
cac8f736-a209-5714-b6b5-07e5081880f0 | note | Produce Record - Sp or S
b2237a32-4e36-5602-94ac-991cffa58e78 | note | Approval - C
214da58e-7cb8-5781-9ab9-711346746dbe | note | Hold Point Y/N - Y
45d02961-1ba6-529c-a3b0-26c5698a727d | signoff | HOLD POINT
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
3cbcad33-916c-583b-8548-b5e09634e85a | checkpoint | Production Testing of stabilised material - OMC/MDD
755f62f2-502b-53c8-93d7-cb34ff8eb97d | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
e43be72a-72b4-569e-b65b-47fd5b5b4ad9 | note | Acceptance Criteria - To obtain OMC & MDD
e6ea4edd-619e-5c20-874b-6bb29ad517e6 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
64000b70-d6fd-5f52-b12e-9ef3cd8062ca | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
6b491b2d-280e-5277-afa1-7ab19dc06057 | note | Responsible Person - Quality Controller
d608b23f-8cc7-5337-8640-d8b005c25ed2 | note | Verifying Document - Test report
301d06f8-a792-5c26-8925-64cd7d29b101 | note | Conduct - C
2f8e32ab-7a37-511c-8bda-36f69ec37dd4 | note | Witness - C
4b6e46b2-d8cf-5014-be04-ca34dc967b91 | note | Produce Record - C
2abe47f2-a38d-5397-ae93-787b783ff6e3 | note | Witness Point Y/N - Y
db166df1-f07e-5e98-a6bd-e46d84f52c3e | checkpoint | Production Testing of stabilised material - Solid Density
0082c9f8-2cfc-585c-bc0c-bbc4bd6a8015 | note | Controlling Documents - TNZ B/5 section 7.7
973a04a5-01a0-5518-bf29-12fd7d0105d9 | note | Acceptance Criteria - For info. and use in MDD calculation
a53f48b4-883c-5374-bdf9-6c3d50e91c57 | note | Method - NZS 4407; test 3.7.1
859da73c-5487-51ba-8729-3e45f5204d93 | note | Frequency - Once on commencement and if any materials change
4c700793-2980-5425-8730-be4f1e44aafe | note | Responsible Person - Quality Controller
abff892e-5f12-5f4c-bbdb-6395cffe4e8c | note | Verifying Document - Test report
5e5d06cb-0614-57c1-ac67-6cd6fd9f8341 | note | Conduct - C
47665114-d7d7-5a89-afe6-1e8e7d036577 | note | Witness - C
fc695814-510b-5358-9b88-e2c2890e49c4 | note | Produce Record - C
2f595270-7696-5252-b8a3-fbdfb3d884ff | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
2fc8289a-903b-54f0-be2b-08b7c9e035d1 | note | Controlling Documents - Reference from Project Drawings
8e16c6ba-db42-58c4-bb34-caea58e17968 | note | Method - Survey/Mobile Roads, Marks with Dazzle
24ea987d-b23f-5a88-97fe-16a696a91ed4 | note | Frequency - Chainages for every different pavement sections
1c791c74-19e1-5425-b903-5a6d2373dbdc | note | Responsible Person - Subcontractor/ Engineer
3eddeb66-f889-5758-8d10-74038664d6c9 | note | Verifying Document - Construction drawings
c83b273d-9c3b-5c8d-a511-28a0508cd191 | note | Conduct - C
a4e6b269-3269-5dca-82a9-a3ff551f51bd | note | Produce Record - C
20978bb9-fed6-5a9d-94ce-ba0aae1ab93b | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
7e5a71c7-c096-53ce-8ace-b8eaaedc94d2 | note | Controlling Documents - Site specifics to be confirmed
d5a9b7e4-48fc-5ae1-8d20-87bf7fb04e1b | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
1c2f5536-bbdd-57c9-9a05-76339b079b5f | note | Method - Scala Penetrometer on Excavation Floor
8a4f111e-337b-5203-a880-d41c8b133f46 | note | Frequency - As required
b25913ec-16a3-596a-b16d-223452df4106 | note | Responsible Person - Quality Controller
a73abac0-ff88-5b6d-84dd-7316d4d29ccd | note | Verifying Document - Agreed treatment plan
2c670634-d33c-57d9-814d-d9ce0bf16b83 | note | Conduct - S
307c422d-8114-5c6a-a0cc-deb5bd88d0dd | note | Witness - C
0f85ef17-bdd8-5c11-9319-20cc7651c66e | note | Produce Record - S
fd80d1b6-099f-523f-b4b5-a760c13cb5df | note | Approval - E
eb0b5e08-b956-522a-9209-8f3bea29b968 | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
2daa9b76-5adb-5649-b4dc-cb58be59a34c | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
19e6ece9-0a6b-5d89-82c4-dd95a3666a29 | note | Acceptance Criteria - 250mm deep unless specified
98c9e89b-fb5b-57eb-8461-37bb4e83a658 | note | Method - Visual inspection
19bdd6b0-c9c0-52f5-8bb4-41aba12a435e | note | Frequency - As required
51d7360d-56a9-5d5e-8a0c-3ca18dc2e571 | note | Responsible Person - Quality Controller
7b587c96-71c4-5c36-a78a-9daada27c135 | note | Verifying Document - Dig out site records/ Asbuilt
5e50604d-f956-59a7-a1f4-aeac67145cf4 | note | Conduct - S
b8aff06c-7a18-5f75-a296-77d3e91e9fcd | note | Witness - C
702d962d-e797-55a0-8198-5d8001f47c7f | note | Produce Record - S
265df6ab-bffa-5d1f-945b-7b70644c20a7 | note | Approval - C
5c6e5e4a-f7c4-5c4a-bf50-6055032defc8 | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
24b2d625-f848-5285-a59d-4269904a56cb | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
1e187e4b-a9f4-59c6-982a-2834f74e26c2 | note | Acceptance Criteria - Scala > 3 blows per 100mm
a3f7fc1f-876b-5576-8c1e-4836f6e68870 | note | Method - Scala Penetrometer test on base of digout
e21ee84f-5113-5d53-b2a4-e793a66b3400 | note | Frequency - As required depending on size of digout
fea25306-2b57-5707-b93a-6731ddafdae3 | note | Responsible Person - Quality Controller
fb72febf-a773-5fab-a73f-1ae145939555 | note | Verifying Document - Test report
bd955477-312b-5c51-bd29-3bb1eabb7fb3 | note | Conduct - S/C
d1c2611e-b6b5-568d-a455-0d09255adac9 | note | Witness - C
497084ad-460e-5f6a-8f16-d76f2d44b892 | note | Produce Record - S/C
1befe3ba-e6ba-5178-a16f-873f025d5ab8 | note | Approval - E
d8eace0e-0d0b-5dd8-b77c-c51a7f443c9a | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
10743bf6-606d-531c-a8ca-b0096b230d91 | note | Controlling Documents - TNZ F7 Specification
4c3a6ee2-b02a-57fa-a49b-1d9fe4376ade | note | Acceptance Criteria - Meet TNZ F7 Spec.
7802c211-3838-5bc0-a6e0-0d0ecdb9a05b | note | Method - Visual inspection
a7fee22a-8497-5e0b-a94e-82b9b08b80da | note | Frequency - Per Delivery
ee61cf5e-8563-5742-91b2-83dd9f14ef52 | note | Responsible Person - Quality Controller
2e51ed46-956e-5b49-b4c2-69af8d01e69b | note | Verifying Document - Certificate of conformance
88c8ed12-22e4-585d-b3fc-6d08d46ec25b | note | Conduct - Sp or S
311b5866-945e-56d2-83a0-2f6b08887cff | note | Produce Record - C
3868c425-0877-581a-9d40-7882e377cc5a | note | Approval - C
7a5a979f-61e6-50f6-9620-67b74088ddaa | note | Witness Point Y/N - Y
33fd8fbe-9408-576a-8bf7-891431ad9e70 | checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer (if rqd)
2d1d5a5e-7791-5f81-bd5e-c6382a83b569 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
59e9e5d5-1105-5784-8e7e-ca2602a68a1f | note | Acceptance Criteria - On the list of approved materials/suppliers
329e0ace-72c7-5fbf-9e1f-aa63ab0dfb99 | note | Method - Visual inspection
1275c4db-9753-5dd5-b94a-1e04ccfa849f | note | Frequency - Per Delivery
d07536a6-562c-5656-86e7-d69f81374d99 | note | Responsible Person - Quality Controller
3096150f-e82e-5341-9883-659bba7c03ea | note | Verifying Document - Certificate of conformance
3ebc05b6-b8f0-5b19-ac6e-effa3ea4fa33 | note | Conduct - Sp or S
acfea8ef-cbcd-5bb8-b6f7-c9dfb8b1cc48 | note | Produce Record - C
5b7ac24c-0733-5031-ae29-ddc6decbb2e5 | note | Approval - C
f2cdc5c6-4bae-5da7-80d8-b2aa202b7479 | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
9cc1acbc-9e62-5cc8-be69-3342663d269a | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
65e03f18-199e-5f22-9835-e4bfc7716ea1 | note | Acceptance Criteria - Clegg value > 45
d3a365b3-93d1-5ef8-b240-4686d4aaba15 | note | Method - Clegg Test
ea2eea3a-0924-5476-9055-5192f1840214 | note | Frequency - Min. 2 per digout
230ea7f7-8b1a-53f2-a97a-a30f47d5c727 | note | Responsible Person - Quality Controller
7f9a0569-642c-5bd8-b034-f8e572aa882b | note | Verifying Document - Test report
b71e30f0-e374-56ba-8d86-0e18753d468c | note | Conduct - S/C
aa8642dc-d0b8-5136-bffc-9e28ab57042a | note | Witness - C
8a9254fa-fe73-5495-afe7-15d49479c7d6 | note | Produce Record - S/C
bc46449b-b06b-5bc5-b3c8-5aa48bd31090 | note | Approval - E
bac87d01-3cb7-5936-9620-083212331f53 | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
eeb50d65-64ce-572e-8456-9dd1f3e00c42 | checkpoint | Place M/4 AP40 Basecourse Material
4202b31d-e76c-580e-bf5d-a20b7cb9a69d | note | Controlling Documents - TNZ B/5 (section 7)
519ad91f-faa1-5beb-9669-90fe14a3d3be | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
83d18e0f-7f75-5758-b6e9-ea09b2ee6e29 | note | Method - Visual Inspection
d22b7403-c0b9-5ff8-92f9-85c04dd8c250 | note | Frequency - On completion of placement
f0059473-cd09-5bc3-afeb-7ec7b6d693fa | note | Responsible Person - Quality Controller
0c62ac4c-5a25-5ce8-a034-f94ec8826172 | note | Verifying Document - Photographs and Daily Site Record
8551aa0b-d8ff-5d1b-b7c2-0170bb3e9c83 | note | Conduct - S or C
f7822b72-e704-5740-88d5-e62e5612364d | note | Produce Record - S or C
f20dedb5-0efb-5368-8cab-4e55ee840202 | note | Approval - C
27d19872-937a-56a9-bad5-5f63c3560623 | note | Witness Point Y/N - Y
27c96781-3034-5bd6-8be1-9136ce336cf1 | checkpoint | Spreading of Cement
aa625469-df39-5020-9203-cdd9fa78fe58 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
f967d2e2-d2a1-55d2-85d8-56c2446b3100 | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
83dd0578-5a2f-5ea8-9674-aafe624e0cd4 | note | Method - Mat test (1m² canvas) and Average Usage Test
eab741fb-e806-5eeb-81be-205152a8c7e3 | note | Frequency - per 400m² and upon emptying the spreader
3aa81423-05f5-5ce5-a44a-e43e4ceeb07e | note | Responsible Person - Quality Controller
8d09c3d0-752d-5917-a610-bae8195ed785 | note | Verifying Document - Mat Test Form and truck dockets
a3175baf-8851-51ce-9192-3c3946d38309 | note | Conduct - S or Sp
80f98a10-8cdc-5046-a226-bc634cddad83 | note | Witness - C
5bf47c80-4a36-54f0-866e-c6214bcab38a | note | Produce Record - S
0e8aa34e-8ecd-5541-9ea2-7290eff88293 | note | Approval - E
4254155f-d564-58fe-a2db-b38b0ada9116 | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
21391891-0a0a-5357-b467-e343bfa24c38 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
24b52c66-f2b1-5455-bdb0-b8d73a18ba3f | note | Acceptance Criteria - 90-100% OWC
3bcf2005-13a5-591a-8afa-11bd69e55498 | note | Method - Nuclear Densometer Testing prior to Stabilisation
4d71bf2f-9a99-584e-9dd6-16f5d93d29af | note | Frequency - ≥1 per 1000m² lot
5092b8ff-b194-57db-9c10-a91aadbda9d6 | note | Responsible Person - Quality Controller
67eb8339-e83b-5ecc-939d-779de6be8b78 | note | Verifying Document - NDM Record
efbe8c8d-d6e7-5800-967e-888baedf6f02 | note | Conduct - S
39e5437a-cc20-5b80-8d32-9cc72604c5e7 | note | Produce Record - S
aff81f05-f129-5184-8cdb-cfd288be24a9 | note | Approval - C
f377b144-5a1f-5a1f-bac2-a80c4e8de96d | note | Witness Point Y/N - Y
3aae6428-5972-5b13-a661-272c4bed881e | checkpoint | Cut Depth
aedbf701-b396-595d-a73a-02cc06c6f16b | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
7692189e-cec3-5b7e-9da3-efe2d9b1d3ea | note | Acceptance Criteria - -5mm and +15mm of design stab depth
9ff96de5-cc1e-57bc-9a15-4e3ff09d6d3d | note | Method - Physical Measure and Visual Record
9e71b7bc-3e30-5007-a988-0364ab1c9e48 | note | Frequency - ≥1 per 200m of cut length
3cfb49d1-a446-5826-a3d4-3355d60f60af | note | Responsible Person - Quality Controller
e5206788-eb89-5d54-85e9-525fa384591e | note | Verifying Document - Photographs and Daily Site Record
b5c4deb0-d5ad-586c-86ad-918f6713d7b5 | note | Conduct - S
33461dad-6134-5fa1-8712-ef511615d2f1 | note | Produce Record - S
c55274e8-c45f-59bb-9c15-615d4797bfc9 | note | Approval - C
2f30625a-81a7-5840-9642-446dfcde31ee | note | Witness Point Y/N - Y
b4e8c8c0-519c-5ea3-a63c-d6e4e3e61d57 | checkpoint | Longitudinal Joints
cac21e68-f4d7-5c96-80cb-5d5533334e23 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
b9b6f3dd-2b2c-5377-ab9b-cf42b65415d2 | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
cdf1916a-62cf-5a48-ae6b-4d2a93affd18 | note | Method - Visual Record
f709c877-f8a1-5824-b75a-5a79e0a9ecd4 | note | Frequency - per sucessive cut
cb8a9bbc-7deb-5799-9976-6dba1194413b | note | Responsible Person - Quality Controller
33e92816-57a9-58d5-b92e-15766d95ed13 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
8da0f76f-acf6-5955-9a95-b96ac0b8cf74 | note | Conduct - S
d32c5e43-aa9e-5831-92ea-bfa311fd4d34 | note | Produce Record - S
3a3b65a0-14f3-5c36-9c52-162e30a75fc7 | note | Approval - C
6eb72378-f895-565c-8640-58e193da944e | note | Witness Point Y/N - Y
4adf91a5-413d-56e8-8c6a-9cb5dbaf546e | checkpoint | Continuity of Layer
b5694b05-8c15-5bfe-989c-34fe455a64ab | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
1a7b32c0-f77b-54bf-bfbe-a32ceed029c9 | note | Acceptance Criteria - Longitudinal overlap, 1m for cement, 5m for bituminous stabilising agents
33f777ca-9137-5ca9-bf8e-cc8cfc391cee | note | Method - Visual Record
a40bdb08-5f74-5c98-962a-1907d203585a | note | Frequency - per sucessive cut
a1c4cd29-a2fb-5247-b7ee-a7138318a7d5 | note | Responsible Person - Quality Controller
502d20b1-211a-5f6c-a401-59548a06de02 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
64099724-a3f6-5cce-931e-b0035beb9a26 | note | Conduct - S
ad2ec1a6-02a6-58a0-8d55-f72e22e06ea4 | note | Produce Record - S
97ddc69c-cbe9-5c5c-b81f-32b73ac0b10a | note | Approval - C
8f09d0ee-368f-561e-8139-66764be485db | note | Witness Point Y/N - Y
a3e7c399-2e95-59d2-b1ad-e3d1d43952bc | checkpoint | Stabilised Material Particle Size
866a4d45-b933-558f-9945-5aedde95b0dc | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
96b0e5f3-2b10-58af-b557-81c7f1c99839 | note | Acceptance Criteria - No excessive breakdown of stabilised material
51eb71ec-6ebc-53c2-8ee7-70ee133710e0 | note | Method - Visual Record
d463a247-f514-5ec8-ab6a-2e28fca5cbe0 | note | Frequency - within 20m of each section and then regularly based on material variability
ce56de42-981f-5c61-90eb-d8fe0763d32d | note | Responsible Person - Quality Controller
b689ed47-a2cf-567e-886e-c112d8e8f899 | note | Verifying Document - Photographs
827869e3-5375-5efe-939b-3d90d2406996 | note | Conduct - S or C
90fa719b-847c-5c54-a453-d31f0dfc17aa | note | Produce Record - S or C
bb770ec8-a7b8-51cd-8b81-2c30eeb732c5 | note | Approval - C
c35f9d62-5303-56aa-ad33-43c8ba676608 | note | Witness Point Y/N - Y
b2669c88-ac51-56ca-b8c1-ca203b10eac4 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
bce7e2f1-9195-56c1-9cd1-ff067332ff26 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
171a48ba-ed94-5549-b58f-e0c02f2edb59 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
f7cf98e8-3e51-544c-bc59-05888c87ad8e | note | Method - Plateau Density Testing
c844de21-5480-5080-93f0-19701907b719 | note | Frequency - 1 time, or additional tests when material changes visually
97b7e226-be8e-5253-ad0c-97436a19a6ec | note | Responsible Person - Supervisor
20d1d98f-cce5-5303-938c-e577cba638e7 | note | Verifying Document - Test record
3e5b36d7-c12d-509b-812d-480e2b0f036d | note | Conduct - S or C
bfe4dd47-ca71-5507-ab28-bf98511f830a | note | Produce Record - S or C
feeac871-5afb-5029-a72e-0f0fc2910043 | note | Approval - C
83be6f7f-f597-5e41-99d3-5e31caf4e623 | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
3850eafe-ed12-5930-bec6-552ef49d86df | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
2ecfc1e1-bc39-55fe-8430-fc8096b69325 | note | Acceptance Criteria - To provide MDD for NDM testing
ef49f97a-51c5-5e2a-b374-6341d74ea87a | note | Method - Plateau Density Testing
3be97028-4c74-50aa-9885-413006a53ecd | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
4c159592-26b6-55cd-bbfa-f940adb8c81a | note | Responsible Person - Quality Controller
dd051631-0ea6-5b0c-8677-65d516f9df4d | note | Verifying Document - Test Record
da55fef8-71fc-5527-8c7a-b2e6ddf06ed1 | note | Conduct - S or C
0d275c9e-8203-5289-bb28-1c4bd3c1e69a | note | Produce Record - S or C
f495f98a-7c09-5d55-b7f1-b655a60d1f47 | note | Approval - E
00ac72b4-488d-5809-98c9-6a171b012f54 | note | Witness Point Y/N - Y
1b96c1cd-dc03-50d2-9eeb-7acf490a611e | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
4a7d5509-44ef-5f2a-8d32-34a0bec68a76 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
c308cfed-7f50-587e-bcdd-87e3f68623eb | note | Acceptance Criteria - To provide MDD for NDM testing
f11fed88-b8b4-5c48-b6a1-85dcaa7c82dc | note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
e0f081b1-726e-594d-ac34-e888e8a2650e | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
0779d057-5387-5af4-9598-0889bb76e653 | note | Responsible Person - Quality Controller
6df8d42b-3eb6-552d-b96b-bb41a278dccb | note | Verifying Document - Test Record
b93172c6-e612-532f-8572-e067cb7393bb | note | Conduct - S or C
a47a1780-502d-546c-a908-57f862bf4d6d | note | Produce Record - S or C
0e8b1e02-80c4-5aa6-887a-6141c4ee51fe | note | Approval - C
f9102eea-7484-5c9f-944a-16ca2d7492c2 | note | Witness Point Y/N - Y
9b641378-7dcd-5a3d-807c-a31562803710 | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
38acb9d0-ce36-5732-bde3-8faaf0a50408 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
53fdfaf5-0d5a-57cf-a511-c19708144bcf | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
5e437a2b-3df9-5610-bbd7-b0d084671d6e | note | Method - Plateau Density Testing, Lab. MDD
4fa49551-0802-592d-962d-5e552585f2c8 | note | Frequency - At commencement of construction and whenever materials change
0f27a27a-d5bb-589b-9a3d-a96488363d77 | note | Responsible Person - Quality Controller, Engineer
6085846e-63e9-50d9-a2fb-4ec3bcd1aec9 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
7347a681-bf1e-5c08-8bb0-ec1c16fc70b6 | note | Conduct - S or C
85533cc8-9681-5f83-9c7c-8854e50af3d8 | note | Produce Record - S or C
cd9a6001-fd25-580b-b2b9-fbac2101eec9 | note | Approval - E
2fc732e0-7ba0-5060-9551-dc92c9c2240f | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
73b648ad-5df2-5e8f-8272-5aa4ac8ebd88 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
013b43cc-0de9-5fc6-89d9-05fb2c011605 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
43bb2475-a161-5299-a9fc-be476a50445c | note | Method - Nuclear Densometer Testing
4438eb1a-3a41-5de7-9a01-c32e46f07a47 | note | Frequency - ≥ 5 tests per 1000m² lot
0cf8212b-fbe3-56e5-b489-ff9aad54f343 | note | Responsible Person - Quality Controller
a0654bf7-dbe0-5295-82bf-3d81b1afaaa8 | note | Verifying Document - NDM Record
f5af2008-7ab2-5d7b-b941-eb951c0840ef | note | Conduct - S or C
8cf0a067-9eeb-5416-bcb2-793045563b98 | note | Produce Record - S or C
428714fe-f4ab-592c-885e-943ed132eee9 | note | Approval - E
dca96636-bf81-5831-bdf2-3b18961b9e93 | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
cd6daa60-e401-5df4-9c23-bd98b0efaa94 | checkpoint | Control Testing (if required)
30f0d87f-e7d9-5fc9-a0e0-623b8b85a203 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
267efe07-7d59-514f-b3ac-17da4abfebe7 | note | Acceptance Criteria - Nil
6c267add-e42f-51aa-9f6e-e09515ba0d3b | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
b2c5cdab-7806-5de9-99ee-8c6d43c0f0d5 | note | Frequency - when agreed with the Engineer
c109892f-e58f-576c-be66-02560e89d7ca | note | Responsible Person - Quality Controller
c9e9b0cc-5f43-5b36-bf00-017af860cafd | note | Verifying Document - Test Report
cd3693eb-d6fe-50ae-8a94-abfe80a2c1d0 | note | Conduct - S or C
fa59f68c-0086-5b0f-87c4-a27bf4d4c316 | note | Produce Record - S or C
48ed3bd4-8576-5efa-83a8-72d381ca86af | note | Approval - E
82f9aebf-08d6-578a-9244-e7ea1b3e1962 | note | Witness Point Y/N - Y
63ac480a-f8b5-58f9-bbf7-a763b61d12c2 | checkpoint | Surface Smoothness
829555a2-245b-5119-be33-f1e9a03d32f7 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
f7a6a99e-77e3-546e-a808-663b1b93b2e0 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
193231b9-9b06-5baa-9cf8-e21261db880a | note | Method - 3m Straight Edge
c86ea5f3-1446-5bf9-9d93-50497b8f8e11 | note | Frequency - during construction and prior to seal
e74df7e5-6eab-5e25-9872-297a21c4beb9 | note | Responsible Person - Supervisor
1d7ce457-de07-5cbd-b555-5f3ec3a239e8 | note | Verifying Document - Photographs
5fb1d7b8-16ea-55b2-b063-1f10150e02a8 | note | Conduct - S or C
a20b09fb-2e0b-57c6-adc7-ed01270df749 | note | Witness - C and E
0ec99de4-f279-56d7-9067-0eb5cd2af94e | note | Produce Record - S or C
8260b939-95f6-5f84-932e-3183372455e8 | note | Approval - E
d33f8bd0-0121-5125-a48c-806a4fbc06b7 | note | Witness Point Y/N - Y
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
c318c47e-09c0-5c4e-ac75-409f48e6b4a9 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
c9da252e-eec9-547f-8eeb-1131e0a03ac0 | note | Acceptance Criteria - Between -5mm and +15mm
c4b8d6fc-b361-5820-ad10-0be178d8a984 | note | Method - String lines or Survey Asbuilt
0690af5e-70c6-5e7f-b3c0-d263ad06101b | note | Frequency - during construction and prior to seal
a44b7b2d-4990-5b55-b0e8-bd34c797fcd4 | note | Responsible Person - Supervisor
74b8afb2-0bce-5e46-b20f-002f391ed11f | note | Verifying Document - String Sheet/Survey Asbuilts
c72bce69-ce2d-5692-beb9-f90f9dd43de9 | note | Conduct - S or C
d0aa4c7f-b548-5887-baec-fe50462f9853 | note | Witness - C and E
d80c50b8-32c5-553c-9934-5467de988ded | note | Produce Record - S or C
b482e0fb-2b5a-563f-85eb-bf948b851514 | note | Approval - E
5886c2c7-dd67-5c0f-92bf-2d90dec4f092 | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
328b91db-a709-5430-a49b-fc303a603053 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
a2995b0c-eeec-5aa4-8db7-3d9ee95505f9 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
3be9b917-9e14-5116-9b87-d9a32b6d7b79 | note | Method - 3m straight edge or Survey Asbuilt
941f0e1d-fb8a-5d56-a2a2-bfd5182fd184 | note | Frequency - during construction and prior to seal
0d9f6b64-de8f-56c7-a9b6-6c160c2503c8 | note | Responsible Person - Supervisor
2bbddeb6-a333-557d-9717-d9d606eae483 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
8af07165-555f-596e-b682-f9edfe4e9685 | note | Conduct - S or C
b6c16346-c38f-5dd7-8147-4ec5bd1b335c | note | Witness - C and E
45f0e330-e925-5a6c-8099-4e93952b6b28 | note | Produce Record - S or C
b325ce39-ed77-5a23-a720-a27252df01d0 | note | Approval - E
96d154f0-0f1b-5cb6-b58b-313341294864 | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
cf5f65bf-7ecf-5276-b18c-5367b748ccac | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
31402dcd-042b-574b-884a-2fdf086043c8 | note | Acceptance Criteria - Tightly bound matrix post sweep
684d3bdf-226f-5dbf-8c71-b3f710291855 | note | Method - Visual inpsection
2ceeffdb-b6a3-5421-8f73-cb66f5a01a70 | note | Frequency - prior to seal
abce1cd6-7e8e-5572-a57d-8e0fe7da186c | note | Responsible Person - Supervisor
a55f544d-3bcf-5c6c-a0bb-195f196830c3 | note | Verifying Document - Pre-seal inspection sheet
0639b01e-6ade-54cc-8fca-dd5bb1233075 | note | Conduct - S or C
f298c2e8-78fe-57c2-9124-6a28a84d5210 | note | Witness - C and E
73ffb4f7-dd45-58e4-9a47-c91723235b1e | note | Produce Record - S or C
9c28de49-6287-57d0-a02d-fbe299680324 | note | Approval - E
a1942584-1121-524c-bfab-d23fc5bcd3be | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
c89a4dcd-b5d6-5635-9a54-54091600b092 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
97753172-0b7b-5a1e-a98e-71bb64762bc8 | note | Acceptance Criteria - ≤80%, however 65% is ideal
c43c5666-2b56-5122-9697-32ac4e44d889 | note | Method - Nuclear Densometer Testing
6f43fb1b-a1e5-5742-aa0a-ed4613afba2d | note | Frequency - ≥5 tests per 1000m² lot
599316fe-9859-5f01-8d3a-c687d04915a5 | note | Responsible Person - Quality Controller
512ceaf0-c08a-50a3-960f-d5becff1cf16 | note | Verifying Document - NDM Record
4da75469-16b1-5954-9cd4-58b9b0ef35df | note | Conduct - S or C
62ffe649-511c-5171-9a19-421596854f58 | note | Witness - C and E
11d374f4-fb7e-5487-b3b3-9be80f8bc046 | note | Produce Record - S or C
3c76aa20-1e07-5e20-8fb1-687e559ca365 | note | Approval - E
efcd515f-6076-5162-a809-c6de783d68f8 | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
7a3091e7-cb01-5804-a5c8-2ad04c962756 | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
57b27e66-4ca8-51a5-9cb2-00797ca7e640 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
e2fa5709-5bbf-5c0b-93d2-9e2869f5f6e2 | note | Method - NZTA Maintainence specification section 6.1.2
b0602ec2-6e43-5521-9cc6-0fa2913d68fa | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
37546e53-f921-50ac-b26d-d7310931234f | note | Responsible Person - Quality Controller
f89958f7-08af-53d6-ba66-5c3e697c4442 | note | Verifying Document - Test Records
e1155985-19a0-5797-ac12-e020becf51be | note | Conduct - S or C
ac4b9517-5d7a-58c7-95fd-b4690e12b860 | note | Witness - C and E
a63093c0-9e57-5076-a769-1109536fe3e1 | note | Produce Record - S or C
d9d2f82f-585b-54e1-b51d-b1f9c967a4f5 | note | Approval - E
3b729b4f-b77b-50c0-ac8c-e332288fcd7a | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
f6ac91d4-5c0b-53d1-9e4e-00bc03939ff3 | section | 5. Chip Sealing - 5.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
3bd18625-056e-5382-9517-36cce8c84ec5 | note | Controlling Documents - TNZ M/1
b6ed4449-c3cb-560a-b60b-9f962021ad28 | note | Acceptance Criteria - Table 1
9033a895-66dc-5889-ae6e-8b1e0be14779 | note | Method - Property Test
0bfb918d-5df8-5534-afd1-f13e432070fe | note | Frequency - Annual
bf43154d-9a55-53f1-b62e-9958c19faa23 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
fcf233b7-86aa-57f4-9b17-43b01fed6ca9 | note | Verifying Document - IANZ Report's
a74cc211-3c25-5f1b-a777-4383a0ef5daf | note | Conduct - C
d8a2cf39-b95b-5c90-830f-9360f76e9795 | note | Produce Record - C
9d339dd9-8c9b-5a0f-b8ca-0c75a3f0c25f | note | Approval - N
f25bbcaa-89f1-5c10-9a74-d9669fdd9f83 | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
338c3815-f591-5899-8074-fcdeebfea5a9 | note | Controlling Documents - Higgins Internal Specification
d07d2a1f-ea84-5ee5-a3cd-32e336f9a548 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
1dff6a7b-9642-505f-886c-feb1bf240538 | note | Method - Property Test
be1a51ed-b18d-50ef-9b3b-fb0563fbcca8 | note | Frequency - 1/100,000 litres supplied
a990bfbf-d922-5f35-913f-ac29e3f975d9 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
27c6fcc7-8806-5847-b536-3f8f422cd3ba | note | Verifying Document - IANZ Report's
831fa28a-16c4-50f2-bfe4-b26cdd3b2a7a | note | Conduct - C
2b9bb950-8288-5fbf-9b52-48a4d334b925 | note | Produce Record - C
f317ef19-3be0-548c-bc17-6359989f2e79 | note | Approval - N
0c51515a-ee1b-56cd-a129-5f50f83e7c97 | note | Witness Point Y/N - Y
271433f5-90db-5716-947f-66b53e064a88 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
c1ded6e3-21d3-5c2c-8897-707887ae6e19 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
d60693c0-4ae5-5bd8-b17c-19e779453987 | note | Acceptance Criteria - <10% fines under 230kN minimum
12c8505e-8038-5f90-a68d-176d76f01296 | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
4d5950cc-41e1-5198-912f-ae71fb61b916 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
d21bc354-8bc4-5235-8a84-72d8049ae979 | note | Responsible Person - Surfacing Project Manager
24450c3b-3b5d-5860-b7b1-3049e5e1c3b0 | note | Verifying Document - IANZ Report's
2b6f5c45-30b4-539f-a191-3db24fb75a88 | note | Conduct - C
e735a081-b912-5bc9-b359-e713b8ccfb81 | note | Produce Record - C
5c8e7640-665a-5a89-85aa-2f1fd40be639 | note | Approval - N
264963ba-ee62-5d16-ab10-47a4def63d81 | note | Hold Point Y/N - Y
6001235b-048c-5705-ab46-316e6fddaf77 | signoff | HOLD POINT
b5105286-fa50-5f37-8ad8-ff00dc521109 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
7fdc82e8-da9e-53da-baa4-c27f9630f342 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
0b26e57d-5a4e-5b91-bc42-5490e80f5bc6 | note | Acceptance Criteria - AA or BA
802c3728-9210-56ad-aa56-18039a6bce83 | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
6679aeea-2c18-5af3-a847-17287cd9c310 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
6ddb2c54-85bc-56c7-a7b0-6099d3fb9517 | note | Responsible Person - Surfacing Project Manager
9f950a58-ac73-5095-9b1a-4227c0f9b1c9 | note | Verifying Document - IANZ Report's
fa6b8f11-6411-57b2-84bb-508ba138073c | note | Conduct - C
cf50a6f1-36c0-516e-9a36-e8537b2e87ef | note | Produce Record - C
8714438a-03fe-509e-bfd8-6b1e9c10e347 | note | Approval - N
d55413ee-4da0-5346-9b6f-9a88ca6b873d | note | Hold Point Y/N - Y
d36fb53c-673d-5ad9-bcd6-d21d23c23bfc | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
7bb247bd-43a8-5946-b321-c424f9b43c7c | note | Controlling Documents - NZTA T/10
e10c815e-4d29-5219-a127-e726d9b611db | note | Acceptance Criteria - Meet Skid performance Requirement
4e34326e-dfaa-550f-b963-4bf3c5685fb5 | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
bf26756a-0c50-5bd3-b8c1-4e89f29d7885 | note | Frequency - Each Site
db481dfd-0ace-5f68-990a-7054dba7df93 | note | Responsible Person - Surfacing Project Manager
29561f61-0646-5f5a-b886-77a82666a404 | note | Verifying Document - IANZ Report's
fcc644e9-943f-5cf7-9854-c7c70c85cdf0 | note | Conduct - C
c99c5d29-6bd2-5c6e-9820-76f695fd3102 | note | Produce Record - C
10909287-03bf-57a6-815b-aa82b004c59e | note | Approval - N
11048cc9-5a55-5da1-937c-95304c8b6750 | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
5a8f8c14-4013-56b7-8e3a-7e70861c12ac | note | Controlling Documents - NZTA P/17, M/6
8dc1ae1a-55e8-5293-99e9-97f9ef458872 | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
99e9f80b-59da-5e8e-af64-c88ff04f4370 | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
52a7ef58-7ba9-507e-887a-9241e3f8d7f7 | note | Frequency - Per Stockpile
404c1e08-cece-5332-8ab0-7374b0243325 | note | ○ <100m3 - 1 Sample
83eafc8f-dfa9-55af-a313-79064ec5647b | note | ○ 100-500m3 - 2 Samples
cb9d209f-6978-592f-9d08-5b6090e44eba | note | ○ >500m3 - 3 Samples
c269312c-b6a2-58c8-a948-dac4c2e7ab25 | note | Responsible Person - Surfacing Project Manager
269783c2-b25f-5f8a-8ac2-e78c02e518ef | note | Verifying Document - IANZ Report's
0f721df3-eba4-5083-829b-0d4c9f334c03 | note | Conduct - C
8996b97a-0c4a-5ed4-9720-708ba67f86e8 | note | Produce Record - C
f7dfd040-30b7-51ed-affc-ce70968f8184 | note | Approval - N
2fa7e8f8-c87b-5cd0-9d6c-05b64c41c852 | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
d7c188fd-b33c-5a89-b9ab-3de29dfc21e0 | note | Controlling Documents - NZTA P/17, M/6
31798489-d180-5350-980a-e915fed379b7 | note | Acceptance Criteria - As per Table 3 NZTA M/6
b1ac196f-bd20-5147-a76c-5aff0117a265 | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
e2ba18b2-581a-595e-9267-47d2ca1c05ac | note | Frequency - Per Stockpile
566df73d-9768-52e6-a63a-a349e3cf21b4 | note | ○ <100m3 - 1 Sample
120b391a-a2b4-52de-b549-e0aec956199b | note | ○ 100-500m3 - 2 Samples
6400cc8f-5099-5cac-9d63-209bc8bfd62e | note | ○ >500m3 - 3 Samples
697b993c-3e84-58dd-820e-cedc63522a63 | note | Responsible Person - Surfacing Project Manager
2c299cbc-bb34-5091-acba-4861043334af | note | Verifying Document - IANZ Report's
b7cf70e0-db09-526a-b880-4208239a64f8 | note | Conduct - C
a04a1694-a1e4-513b-8757-b8e3676dec7a | note | Produce Record - C
9eab3059-1718-5401-8726-ad45a807124b | note | Approval - N
e59d36b5-ac9a-58df-af37-21f381a24123 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
608d7a4e-bb4c-5dcf-8878-a99bbd832886 | note | Controlling Documents - NZTA P/17, M/6
97bcc069-6cee-58a6-b7f6-c1c3648ec8b0 | note | Acceptance Criteria - Min. 98%
e006ef12-5509-5865-a220-6f40aec0040d | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
4acc71a5-89f7-5580-917a-795735201371 | note | Frequency - Per Stockpile
52fdaa3c-910f-538f-af38-bd94d328e94f | note | ○ <100m3 - 1 Sample
04c59584-1769-5676-bc4a-22bc36cd2b55 | note | ○ 100-500m3 - 2 Samples
f3b4dff2-df93-51ba-9421-2b53b0c4de81 | note | ○ >500m3 - 3 Samples
2d520109-9b40-5263-9100-dcacf57b182b | note | Responsible Person - Surfacing Project Manager
0cbeaa66-e7d6-58ff-a9dd-4315b79472b3 | note | Verifying Document - IANZ Report's
89154a7d-ba54-51ce-b84f-605a6c197ae0 | note | Conduct - C
99a5d79c-ab4d-5b5f-8f40-5608265dea07 | note | Produce Record - C
82045bfd-24b1-5a0d-9915-dc4e81b53c8e | note | Approval - N
85c9135c-eb57-51fb-9f56-df2d49d6c23c | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
cd1a49e7-aaee-590b-afd0-45ada2558ccf | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
f99231a9-4f0c-5fa2-b8a1-209c625df892 | note | Acceptance Criteria - Client Approval
ba304941-1d30-54c8-81f5-5db6733e7605 | note | Method - Review
587491e4-7b90-5326-b43a-c47cfaa0afbc | note | Frequency - Annual
12fec213-59a4-5286-9e32-a55c9a12e13b | note | Responsible Person - Surfacing Project Manager
b50cf8ce-74b4-5bd5-ae35-3ba0bba7d18f | note | Verifying Document - EBOP NOC Design Report Acceptance
04e69591-71f3-588b-9cc1-56fb2a3d60e6 | note | Conduct - C
4431b323-3ba1-5970-8827-926dc67a3e66 | note | Produce Record - C
a398c931-e5cf-5b71-8395-c140a5d58891 | note | Approval - N
196d98ef-9784-5185-bfb4-989156e97092 | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
2d90825f-40a1-55cc-9369-13e616f644fc | section | 5. Chip Sealing - 5.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
4a1d88b5-99d5-580c-9ffd-7b0622e52509 | note | Controlling Documents - EBOP NOC Design Report
ae1ff51b-c97a-5a7d-b839-3c7be38c2669 | note | Acceptance Criteria - Visual Inspection
45ec98d3-5021-5943-b62e-25febd3de753 | note | Method - Visual
d0cc1923-8770-59fc-a836-855baee242df | note | Frequency - Prior to start sealing each site
06f38bd1-be91-5b59-b779-f84f50a12a70 | note | Responsible Person - Surfacing Supervisor
6e447b4c-a4eb-5733-a0d4-b66052da2532 | note | Verifying Document - Chip Sealing Quality and Site Record
8b71ddcf-afc6-5860-b556-1e796f54dcd7 | note | Conduct - C
ae31d374-162c-5d04-84fe-9e896cac27b7 | note | Produce Record - C
b3f9a298-cccb-5fab-ad4e-084f1714f1db | note | Approval - C
1b2ff781-95d0-5b32-a07c-dd0401c4fdb2 | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
8fe48c84-afe5-5092-9612-c2b1ddf71a8f | note | Controlling Documents - P/17
a23f3d4c-300a-5e60-bb18-4bb354372a4e | note | Acceptance Criteria - Visual Inspection
0cfd8b61-b360-54f7-ae3f-6fc182ae868c | note | Method - Visual
b1ab55d5-5ba0-5058-a396-54ae58a344ec | note | Frequency - Each site, prior to start of sealing
6ad07731-df2c-5c40-abb4-e2629e2dd74b | note | Responsible Person - Surfacing Supervisor
2fa813c3-1d9a-5c47-b3b3-5bce4a97edb6 | note | Verifying Document - Chip Sealing Quality and Site Record
1a32b05f-80f1-548a-bddf-d62a2d25d1ae | note | Conduct - C
7ded64d3-b94e-53d4-a40a-c09786093c13 | note | Produce Record - C
b71e0abe-a3e6-5edb-9c6b-8a82ad91f01b | note | Approval - C
8e19e31c-2adf-594a-a8a7-19349b52da84 | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
365d9aa5-b182-5844-83da-e03719388b22 | note | Controlling Documents - N/A
e69d8c0c-b93c-5085-a3b3-714c80289bb1 | note | Acceptance Criteria - Visual Inspection
d43b2a03-7034-5001-ac44-578082c587e0 | note | Method - Visual
86437c72-ef3f-5cb2-9b57-3a84c7513ebc | note | Frequency - Each site, prior to start of sealing
71f12616-f522-5158-a8db-e8c56f5551e0 | note | Responsible Person - Surfacing Supervisor
a81cb5fb-6144-53b6-b8d9-fd9d4835d6a0 | note | Verifying Document - Chip Sealing Quality and Site Record
4063ab2a-a4b2-5fa3-ba39-548e7264b3ef | note | Conduct - C
b2125c78-2ff7-50a1-a74d-c6d3db8adab9 | note | Produce Record - C
f041acfb-ec4d-5d00-ba32-f73390a54460 | note | Approval - C
cd6a9565-0500-5531-a982-5a1ce51fbb2b | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
275f7731-48d0-5540-94e2-48145a026b18 | note | Controlling Documents - EBOP NOC Design Report
cbd538b8-f2cb-5e20-bd08-6261805a9bd1 | note | Acceptance Criteria - Details/chip correct
00fc3824-c648-55fd-9a9b-856e6b91967f | note | Method - Visual
b9b4b109-21c8-5bb3-99f5-5f565a0250d8 | note | Frequency - Each Site
487f3d91-a543-59f1-8182-022e55b1a459 | note | Responsible Person - Surfacing Supervisor
8d98f661-5dc5-5395-9294-f732f20338a1 | note | Verifying Document - Chip Sealing Quality and Site Record
deab67ed-f457-5474-b669-8b75396d6939 | note | Conduct - C
7c1639fe-774b-57ac-bbf0-3a2f20c450a1 | note | Produce Record - C
93b0e65a-18f7-53df-bcec-61bb8cfdadde | note | Approval - C
e6b5d454-85a4-5914-9efc-7ea5424277ca | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
bef7929f-a665-5d8b-9956-a4c3221b49e1 | note | Controlling Documents - RNZ 9803_0513
dc5cb967-d69f-5d59-86e3-613bfcdb9bd3 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
5c7c8567-e0d8-514f-acae-c5ee74947123 | note | Method - Sample and test
97b7012c-206a-522b-9b25-5e6f23ac48c7 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
912c3cfe-7dcb-5d1d-ad30-4ec0a79abf59 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
565ea23c-ed99-54d1-a6c7-7d1a51ad6de0 | note | Verifying Document - IANZ Report's
1d6089c4-2fb1-5772-ad26-2f6b8ad00908 | note | Conduct - C
769957bb-d398-59f1-be6b-77936795bfad | note | Produce Record - C
7e206e27-0924-5964-a9f6-ddc5ab6d5038 | note | Approval - C
09a19464-965c-53d7-8f72-960e7a0a3482 | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
3d59aa6b-da9e-5879-a224-f35b5c1adc4b | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
03b8e358-446e-597c-b020-e55b1e43dc19 | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
c2c9032f-6aeb-571a-9cd4-7e23bfb36f55 | note | Method - Test, Review
0050db81-3425-539a-a9fa-0735012b20eb | note | Frequency - Per Sprayer, Per Site
99e510ca-f94a-5d2d-b4c0-d082f9e9bce8 | note | Responsible Person - Surfacing Supervisor
c5095636-36e2-5838-84bb-a35ec0d9fb0e | note | Verifying Document - E/2 Certificate. Spray Sheets
263a5a89-e068-5e54-8813-05fe3609a720 | note | Conduct - C
8edd7096-5958-5b36-96dc-60bc250017a9 | note | Produce Record - C
ca84ff41-48f4-5db0-845d-283d8d5de184 | note | Approval - C
88cbfdd5-696e-5ce5-bea4-88c64f897231 | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
bfff3d15-ad51-5c43-b70c-6d3bc69bd93e | note | Controlling Documents - Chipsealing in NewZealand
76199d10-c035-5030-a2ae-e285b1b72a67 | note | Acceptance Criteria - As per Chipping Guide
12c47a01-fb43-5971-ab8f-f9c9e289cb52 | note | Method - Visual
20f5215f-296a-51cb-9028-7c220a50b9ca | note | Frequency - Each Site
0f0b3d93-e026-5d67-bf27-9b0387f6f60e | note | Responsible Person - Surfacing Supervisor
c755d9ee-b75f-58c4-adf2-ee1dc696981b | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
688fb9b7-b8e2-5f92-b234-2269e17635c4 | note | Conduct - C
04857c1a-de5f-560b-89a6-9a3fd5723411 | note | Produce Record - C
341d6c66-46aa-57d0-92c7-e4d1459cfd15 | note | Approval - C
2c4142c8-4c54-5345-919b-5608d07f5ae0 | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
99abc667-451d-5c7f-935e-c25562a9053e | note | Controlling Documents - Chipsealing in NewZealand
01358a33-4b97-5c7c-89d1-7dfa9cce5f35 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
8687b8a9-69e5-5a58-b69b-24771f57e1f8 | note | Method - Visual
82a28129-538a-5555-bab0-192d30663d05 | note | Frequency - Each Site
44b5d210-14bc-5ae3-8f78-336c386f65cf | note | Responsible Person - Surfacing Supervisor
1e5d75f8-ac2c-5095-98c2-9b2136ac8f76 | note | Verifying Document - Chip Sealing Quality and Site Record
492703fd-5514-5e2c-ae05-f43cc10e562a | note | Conduct - C
57226010-9307-5b95-86ae-fffc3e009d6b | note | Produce Record - C
b225efec-8116-5e0b-b34e-8d8e8fe9a852 | note | Approval - C
75abf5e6-9e9d-5732-b0b0-7cfdb22a8be9 | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
da5adf69-6ed4-54ce-9381-085a7dfe3d64 | note | Controlling Documents - Chipsealing in NewZealand
220249e1-ae66-54e8-8f9a-bb11e69dda4e | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
083f583e-7066-5245-9696-1974a00d6f4b | note | Method - Visual
f0f11d89-35f3-5d50-84c9-c6c17e8e8529 | note | Frequency - Each Site
2cb6d25d-2e2f-5532-b061-fa39834c1597 | note | Responsible Person - Surfacing Supervisor
ea30ca6f-aeb9-5f15-8533-6b4c3d3b97c3 | note | Verifying Document - Chip Sealing Quality and Site Record
549ca0db-7454-594c-866d-46814d025ecd | note | Conduct - C
fe99c485-0daa-5c8f-bcfc-fb229747913a | note | Produce Record - C
56b55c4c-eede-5ced-9221-52166cbdbf7f | note | Approval - C
a85a84eb-2c57-5d69-9eb3-7c3bd9944d42 | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
7c2b5379-7baa-5847-b154-586b4d8eca98 | note | Controlling Documents - Chipsealing in NewZealand
f1adf686-98b9-5f6f-82e3-a4c6af49d861 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
f53a06cd-6814-5899-9192-b3d1df1d6302 | note | Method - Visual
c7d8f9b3-90ab-5668-85eb-11ef64549ffb | note | Frequency - Each Site
a85c2cd6-66ae-5888-8867-d2c4bda5c944 | note | Responsible Person - Surfacing Supervisor
2d5ef2ea-9660-568e-bbe3-d9efef9d5afb | note | Verifying Document - Site Record
25e0481e-315e-5f6f-9839-0b9ef5b7eb30 | note | Conduct - C
ca40678c-09a5-5e5c-934e-60cf10a78dfa | note | Produce Record - C
99f85b1d-7bcf-5419-a9dc-c01c35d5688e | note | Approval - C
e9468846-f28f-5bb6-9a48-fa375b410b1f | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
f382c45b-b8a9-5b69-9f18-93957f99cbc3 | note | Controlling Documents - MOTSAM
2824eb90-2dc7-5571-b937-1be7d9a3d8a0 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
a9a19634-329a-597d-aa09-3586610fc774 | note | Method - Visual
832a3301-17d4-52e6-8a30-901f9671f32a | note | Frequency - Each Site
97a71474-031e-5d91-991b-da420ab020e4 | note | Responsible Person - Surfacing Supervisor
d32f5caa-e747-5838-b578-b39d6910c42f | note | Verifying Document - Site Record
3736f96d-d0cc-514f-a310-bd044065d2f6 | note | Conduct - C
e1360a66-f022-52d6-8d97-11ddae5ed561 | note | Produce Record - C
bd441fbb-b05c-516b-b4ad-e8a565dedcbd | note | Approval - C
015b9461-f38a-54ca-82e3-9f2916b5f51c | note | Witness Point Y/N - Y
2fa24de8-fb07-5d57-947e-3eea20cf5b9a | section | 5. Chip Sealing - 5.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
7e9175f8-8700-5b39-a177-1b6ade51ea03 | note | Acceptance Criteria - Formal Agreement
87aead4b-679c-5e98-8a94-91ea6043f038 | note | Method - Visual Inspection
9e26cae9-4c8f-50de-845d-8bf90757ad17 | note | Frequency - Post seal sweep
5d6fed12-6a04-5609-aafc-e1121e3539ec | note | Responsible Person - Quality Controller, Supervisor and Engineer
b024ea6c-83cc-56e1-a63e-e0420935252b | note | Verifying Document - Meeting Minutes
088620ec-d121-5a8e-92af-360a01080d7a | note | Conduct - C
6b6bd57c-6f54-599e-a7f4-239f16acb980 | note | Witness - C, S and E
f7cc5467-6484-51e4-90b9-7f7815c7972f | note | Produce Record - C
e0d9f03f-ba95-5cea-8b8b-9ac5a3025182 | note | Approval - E
8c0b1099-b869-5e0a-ba83-0fc3e21ac17a | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
b4b1eb1e-ca88-5df2-b5c4-1199e04c48ac | note | Controlling Documents - NOC; MS 6.1.3
0de94e75-1999-52f5-8a49-b859757aa63f | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
f48c9bdf-7e56-5a90-8346-d2fa8b47fcc5 | note | Method - Record
c436cc7a-7d3d-55c5-ae01-cfff09c89f67 | note | Frequency - Within 2 months of completing the annual resurfacing programme
5d6e223f-ecee-52aa-8758-c889e67a054b | note | Responsible Person - Surfacing Manager
ef60f7ed-e656-5d88-bc20-c03491fff072 | note | Verifying Document - Construction Completion Report
60c5f7b5-ced1-50c1-9ff4-10a667b23671 | note | Conduct - C
bed1cee3-94b1-5cfb-a7ca-f13a5d160ac7 | note | Produce Record - C
ff2d8714-dbaa-5275-b6c4-d90838d5f54a | note | Approval - C
50f39c44-e755-5767-adee-bda3e69be8ac | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
8dbbc8c3-eb79-53b1-a141-9591518ae160 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
f1ab9cb1-9dae-5478-af5a-e78d0287d6be | note | Acceptance Criteria - Engineer Approval
2da6ac45-a970-5d02-931e-f7caa1e0d1b5 | note | Method - Visual Inspection
c5ae373a-4a7a-5798-b465-f53c8fc79131 | note | Frequency - ≤2 months of 1st Coat Seal
c8dd9b95-e773-57dc-9f8a-78eb87676e10 | note | Responsible Person - Quality Controller/ Contract Manager
29ee5dbe-d71e-5ba6-b015-f868ae6457cc | note | Verifying Document - Signed Report
5595b065-9424-58c5-9936-a2d1ad0e8f01 | note | Conduct - C
beaad7b8-6cc1-5b35-b9d8-7301a4d01c7d | note | Witness - C, S and E
cae67242-1b34-5c1d-9fb2-592728e9b8c8 | note | Produce Record - C
8e4f6654-9353-5686-aec5-8a5d6a18bb9f | note | Approval - E
3bb5fb10-1853-5164-9b54-f0fa374b8860 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
29725530-b052-565a-8bf3-21ad7a85e3d2 | checklist | ITP - Pavement Rehab - SH 05 - Boundary Road South | itp | ITP - Pavement Rehab - SH 05 - Boundary Road South
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
09dfa698-6b7f-519e-b940-013fd716a19e | checkpoint | Design - Geometric Design
68423ce5-735a-563e-a7f0-e3420fdfd32a | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
70c5442d-6ab1-5ad3-9248-c8055bb735c5 | note | Acceptance Criteria - Principal Approval
f824db68-73dd-5f20-a45b-f033c175cdea | note | Method - Contractor and Principal peer review
f671c897-a9e3-5f6f-8dd4-12c27c143b9b | note | Frequency - per design revision
6d63af3b-1f60-5f1e-a15d-836395cbd432 | note | Conduct - C or S
d2ee0128-def5-5f52-80bb-3dc665c70e79 | note | Produce Record - C
f7ae235b-5623-5bb0-995c-d0d3c32b8af0 | note | Approval - E
6f02eaf5-6162-5b37-99e9-39fb914f9dd4 | note | Hold Point Y/N - Y
734b8921-df80-5868-90e2-320abcb6aec9 | signoff | HOLD POINT
fc457da0-71e7-5429-a676-cfa9f8ad8762 | checkpoint | Design - Pavement Treatment Design
d8b4e70c-9167-5b7d-83ac-d1005ce874c9 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
047f1367-d511-5e77-9afe-e2847e1d8f73 | note | Acceptance Criteria - Principal Approval
44b8362f-c4eb-5615-97c4-17ae6a38d70d | note | Method - Contractor and Principal peer review
616d5841-c3ac-5fc5-aa7f-dcf6f3370c41 | note | Frequency - per design
aac0e670-a565-5798-9023-361c9a048993 | note | Verifying Document - Pavement Rehabilitation Design Report
66845e96-5bf6-5e72-bf6c-39ab96ab51a0 | note | Conduct - C or S
5440ab7b-4196-5522-9a9a-17b6cfe2dcde | note | Produce Record - C
5c27b7c9-1bfb-557e-a540-315e1450553b | note | Approval - E
9d2308df-5e1c-53c2-bc63-6e2f7a01d38e | note | Hold Point Y/N - Y
f7622f1f-ef56-5ab3-b6af-8b3b9e5d5f72 | signoff | HOLD POINT
36362436-b1e4-5e95-af81-437ff9bbd938 | checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
6194ac1b-dfd1-5d10-8713-21966b37f5c3 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
efee79a0-fac9-54d5-aefe-10bb6cdb6f8c | note | Verifying Document - Sampling Worksheet
2ef92523-2dc4-546e-9f6f-a99f5391a094 | note | Conduct - C or S
2fa736f0-2fc9-544c-b547-7469a676c021 | note | Approval - S
a7155c78-0c62-597b-b7b0-dd8b72581861 | note | Hold Point Y/N - Y
a9333c6b-9961-5161-9914-ca21c6664667 | signoff | HOLD POINT
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
8f706956-01d6-5660-9f84-d02b7274fce3 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
2bafa74b-44a2-545e-a6d1-0c54f9bb569c | note | Acceptance Criteria - Soaked CBR ≥ 40
639c2bb4-fde0-506e-8545-3387c4101baa | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
12d4fd14-4911-5ade-bf34-8a858b7bdc2a | note | Responsible Person - Supervisor
19335cc3-51f2-50b9-9e93-5bc9dcfd6f26 | note | Verifying Document - Test Report
f715a1e3-319d-5e65-852b-aa3a85809bdd | note | Conduct - Sp or C or S
6cb5c79c-bf2c-5673-9bda-c0d4047ea9a5 | note | Produce Record - Sp or S
83bc2aed-e26b-5889-a7c1-28fc0bd4ac1a | note | Approval - E
4abdfaad-d856-5939-a46f-8373bfc1ce9b | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
ae7e2d83-e996-5777-8251-1ac263229947 | checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
cf8affbc-9dff-51aa-b364-df242a9d012a | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
1ea057a3-59a7-5eec-a215-4f0926bb0538 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
89026ef2-601a-5e02-845d-9991b3ca26dc | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
9a8793a6-fed6-5bd2-af73-20dda2ce2e5a | note | Responsible Person - Supervisor
0f44216c-376b-55ac-b7dc-5b81e707e6ba | note | Verifying Document - Test Report
99e89de0-87cb-5ee3-8560-315771218746 | note | Conduct - Sp or C or S
2ff80d71-06d7-5c4b-9a31-c6b85c049a8b | note | Produce Record - Sp or S
d05e34cf-bece-59c4-80e0-5c0433198bd8 | note | Approval - E
834d7948-b731-503c-9806-efa078fd0cf5 | note | Hold Point Y/N - Y
59b9d644-63f9-5af7-bf31-75c1a6bf1a10 | signoff | HOLD POINT
282d13fa-6a2e-5570-b955-78f6c0062fd3 | checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
ecabb8ca-be7d-5d9c-9fa9-03938e1568e9 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
38785bdb-da7f-5229-8c4d-492418a23eff | note | Verifying Document - Sampling Worksheet
19b6d86b-bdd4-5d23-8c3b-38570c4103e5 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
c3173046-1fcc-5077-9f65-89722324ffa1 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
207a3d14-ac6b-5033-91a6-322f1bf8e3a7 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
065dd30e-63cd-523b-b861-32953564d26a | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
e48f5339-0c8a-507b-b711-4549c1a18f31 | note | Frequency - One test for every 10,000m³ of source material
257c394e-efa0-52cf-a00b-ea8451a1acbb | note | Responsible Person - Quality Controller
b8ab547d-0547-510b-beaa-6b331390688e | note | Verifying Document - Test Report
759d776a-7a6d-5a99-88a1-2d99c7066082 | note | Conduct - Sp or C or S
14bacf53-9bcb-564e-8e10-cc5254c39235 | note | Produce Record - Sp or S
5f925a6d-61d6-5695-91b4-3fc2f196d2d1 | note | Approval - E
da76f773-cf30-54f4-8b89-0deec2a4c7dc | note | Hold Point Y/N - Y
2bce147b-57e0-5df2-aa19-d3114e0f900e | signoff | HOLD POINT
771bbcd5-e52e-5af5-9fc3-2a5ff6956b1d | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
58a48681-9110-5b44-8c76-1f3da607b0d6 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
21ba48b4-5247-5df4-aa39-9a1c18f9285e | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
6a7066a0-daac-5d26-8715-e843d29e88e6 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
0797a43c-d487-5718-990e-b70b72ae8e8c | note | Frequency - One test for every 10,000m³ of source material
6f06c1e7-219b-525b-bf05-07fd55714312 | note | Responsible Person - Quality Controller
4a58f0d4-7d0d-5039-bb30-14dd3cce1721 | note | Verifying Document - Test Report
742d039d-528b-5610-94f0-325865371f21 | note | Conduct - Sp or C or S
5e70788f-3705-5ae7-a7af-b5920ef84a8d | note | Produce Record - Sp or S
93b6116e-fb16-5897-97f9-b21a3644cdaf | note | Approval - E
3e83f79d-1318-5b9e-a65f-292393efae94 | note | Hold Point Y/N - Y
5de343b7-b3e0-59f2-8f5e-085d4a8c0fdc | signoff | HOLD POINT
113f3833-1e06-55b9-9978-c5d36d530658 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
e2007c9e-da7e-5470-8d46-a5c72268d3c7 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
f9b15cdd-3020-5ddd-a068-f211d186bd1c | note | Acceptance Criteria - Soaked CBR ≥ 80%
dc92b0da-8890-581d-b1cf-e49af5e00d2f | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
ecf08606-2590-502f-9cbb-6d037f6c5f2f | note | Frequency - One test for every 10,000m³ of source material
98662be6-b0fa-5979-b278-9c3bcd230210 | note | Responsible Person - Quality Controller
52525420-0484-550c-a99c-6ac4081505c3 | note | Verifying Document - Test Report
72e46180-e440-53c0-99b8-e79972740fb3 | note | Conduct - Sp or C or S
8b35a4f0-354d-5d9a-ac3d-fcee5d17cc08 | note | Produce Record - Sp or S
71c35870-03f5-5295-87c3-5588dce5129a | note | Approval - E
c053d567-bfcb-5caa-bf9e-dbb3ba880771 | note | Hold Point Y/N - Y
976c9ab2-336e-5bd7-8941-60563e8cfc82 | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
a1c30cf4-6a7c-5878-81ca-81471192ea7f | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
82bcc410-3802-5cf5-bb2f-af72b55213c9 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
602a218e-2bf6-5935-8f86-926182b18062 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
445e5159-6958-5159-829d-99a491d661e5 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
77a048c0-fad6-50a1-b819-07c7314da7be | note | Responsible Person - Quality Controller
61f57c24-bdf3-52b3-bcc3-ed523282fb07 | note | Verifying Document - Test Report
717dc5d6-3a8a-5e68-b9ca-5f2624a88d7c | note | Conduct - Sp or C or S
c3718ded-676f-56c5-a3c9-9f7da3631350 | note | Produce Record - Sp or S
b037ffcb-779b-525f-890f-c0ebd7455394 | note | Approval - E
d95267a5-cc24-520a-aa05-459d3b2797e7 | note | Hold Point Y/N - Y
8c291f12-658c-5f73-81d4-ac64eaf7be26 | signoff | HOLD POINT
21f389de-1666-5508-9d06-5a4f024a4cbe | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
b5584f41-2c6b-5b56-a30a-4fbe7b46e03a | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
a25979a1-fd0e-5be1-afef-cfe382aa0871 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
999b4046-0484-577c-b1df-fa01a668d5d1 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
3fbb570e-e354-5fb6-834c-f6bbc99b37eb | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
94f98659-e1da-5c82-9748-f3afc82f411d | note | Responsible Person - Quality Controller
99724843-c6b1-5aa5-93b4-2bc409037c1b | note | Verifying Document - Test Report
4fe3d5f2-27d1-5184-8426-df456e1c98cb | note | Conduct - Sp or C or S
0ea1908e-02c4-5934-8c08-3fbce1978e3d | note | Produce Record - Sp or S
e4a12ba7-d65c-5f69-9c28-80a8b7f72d32 | note | Approval - E
badd05dc-e36e-5774-ba47-2ac6d6a01b35 | note | Hold Point Y/N - Y
f50c0087-ac9f-533c-9dad-f1906513e000 | signoff | HOLD POINT
66a6116e-307f-5697-aa3e-d266fb4bd96f | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
d68b4360-be7f-5ec3-9f1e-5fc26931ed95 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
0b790218-bad2-5a83-88fe-5c48d5211178 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
9a941cb7-fb3e-5eca-9726-cc90ab801a00 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
a4cb6289-a8d9-55df-ac0a-5848af4579d2 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
84894325-4426-5803-a862-191061355b5a | note | Responsible Person - Quality Controller
89c9203f-cc85-5b5c-92be-311daabe0932 | note | Verifying Document - Test Report
9c72cefe-633c-5b4c-881a-fdd7247601d4 | note | Conduct - Sp or C or S
a85a751d-2845-5620-b935-edfd2760e622 | note | Produce Record - Sp or S
0dc317a7-0b4f-5b9c-a0ae-fe27a38035ae | note | Approval - E
5a145bb9-877c-5be6-87cd-01ce7208f009 | note | Hold Point Y/N - Y
7ecc9215-ad8b-5530-b3e7-13982b2273e0 | signoff | HOLD POINT
288f3247-2eba-55d4-ae79-89580bc4bef3 | checkpoint | Materials: Cement - Stabilising Agent Selection
fc2c1c56-15f6-5cb3-9637-a8bc08ee2358 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
7f1040a4-1bce-5bf9-8422-0d59c819f847 | note | Acceptance Criteria - GP
50d1caf7-aa44-5285-82eb-276b7492d423 | note | Method - Visual inspection of supplier docket
66ec5cd1-eb48-58db-9cc1-cf48cf213bbc | note | Frequency - per truck load
514c227f-ab20-5c0b-9a1f-42ca214dff5a | note | Responsible Person - Quality Controller
f4c24bc7-30e4-5c65-a9c6-313067583743 | note | Verifying Document - Supplier Docket, Supplier Cert
2d5e140f-7eab-5d21-ba8b-cdef52850bd9 | note | Conduct - Sp or S
440b078b-910d-5a9a-b269-07e051d9a32c | note | Produce Record - Sp or S
d7adb740-9f92-5437-b50f-a5a1dbd26fd5 | note | Approval - C
eee5ba1d-16b8-5073-8855-32af07b6e962 | note | Hold Point Y/N - Y
4c5e2924-c37c-5329-8e7e-217f3be76a22 | signoff | HOLD POINT
5fe70724-8f32-50a2-8961-1dac348f79c6 | checkpoint | Materials: Water - Water draw for stabilising
aa078cdc-bdf9-59da-9939-1234df082cf5 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
ba1422a2-e040-53ee-a2d2-347d788a99c3 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
862160cf-679d-59ca-8b2d-219f58ca80d0 | note | Method - Visual inspection
b233fd53-79a8-59c8-b4f8-ee5f42540548 | note | Frequency - per truck load
6feca4d4-0e45-5395-adea-19766834a8c2 | note | Responsible Person - Quality Controller
2f9b0764-c2e9-5146-9f5c-90e66b029491 | note | Verifying Document - Hydrant use form
433f64c4-dd02-5aa4-bdea-db89933bed26 | note | Conduct - Sp or S
e2c584d0-8569-58cd-8bf3-cdc761c60969 | note | Produce Record - Sp or S
3c3df39d-f11c-5bcf-a8c0-7b312c02ce4a | note | Approval - C
610172b2-0319-5c80-a48a-2201f4ffcda4 | note | Hold Point Y/N - Y
20a1edd9-bdbe-56ed-9252-c68d03654979 | signoff | HOLD POINT
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
12f81c0c-db5d-5bd6-841e-2839e3c1c2be | note | Controlling Documents - TNZ F7 Specification
8a8fc460-062a-5023-982e-65bc063e736f | note | Acceptance Criteria - Details on Docket
ebb9792a-2ff2-59b7-bc02-8f0d65c49903 | note | Method - Visual inspection
554390a3-fcd9-5012-bd4d-41f023d6006e | note | Frequency - Per Delivery
bfe616e1-582e-5e8a-a937-ba22d9a12ba3 | note | Responsible Person - Quality Controller
c605f4a1-9fdd-58d9-b074-d6747a3fcbfc | note | Verifying Document - MDS
e2b14aab-6ccc-5b26-8740-f1090af0bff7 | note | Conduct - Sp or S
428698c7-b995-5e07-b6cb-956e4f588480 | note | Produce Record - Sp or S
239764e8-7723-5eed-8f52-d67d10c329e9 | note | Approval - C
0d09940e-8b9d-573d-b9eb-34f2e2c6ce0d | note | Hold Point Y/N - Y
e7ab7dcb-bdc9-555a-a417-f0efe57b5add | signoff | HOLD POINT
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
3cbcad33-916c-583b-8548-b5e09634e85a | checkpoint | Production Testing of stabilised material - OMC/MDD
5bcbb87e-9163-569f-97e3-4eb72951837f | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
a861ce85-5561-55fc-be3f-49175b510e14 | note | Acceptance Criteria - To obtain OMC & MDD
0d47a205-6a9a-59bb-8130-dcfbfa827f7e | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
f8f18cad-0fcd-524a-a6a3-e571c13b0cfa | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
c951793c-1532-5295-a9bc-5067a3175e86 | note | Responsible Person - Quality Controller
32fdf909-a79e-5ab4-ba54-ba33e3e82e1e | note | Verifying Document - Test report
1d6859bb-f4e6-5668-8e7a-0f3277ce5d42 | note | Conduct - C
c138692d-04d9-569d-ac63-54e060c634d1 | note | Witness - C
41fb8b74-fbc1-5705-965b-56432256c6da | note | Produce Record - C
daa42bf6-f107-50e0-b02f-6db624318850 | note | Witness Point Y/N - Y
db166df1-f07e-5e98-a6bd-e46d84f52c3e | checkpoint | Production Testing of stabilised material - Solid Density
52a9a133-0b2e-5e2d-8e9b-81db1d3669e6 | note | Controlling Documents - TNZ B/5 section 7.7
0df21620-57ef-5610-9797-865eb2fc1142 | note | Acceptance Criteria - For info. and use in MDD calculation
6ce7f857-c5af-5881-ad44-94513e6d8fdd | note | Method - NZS 4407; test 3.7.1
1d4affb1-6ab4-5f07-832c-6511ea2df79e | note | Frequency - Once on commencement and if any materials change
589dc5b1-ebd9-5fef-a150-20bd19ba0fd0 | note | Responsible Person - Quality Controller
c44eaa50-7c73-5f4e-adb8-259d1eab021f | note | Verifying Document - Test report
25bda42c-0426-5505-b233-829d7a0e3419 | note | Conduct - C
a82cd583-ab23-553f-9d5b-84ab0ad0c922 | note | Witness - C
8d5d0278-2b5c-5de6-bdb4-0d8888c0afa5 | note | Produce Record - C
ce5e6eff-38b1-51ae-8c9c-df050912f1cd | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
93e8e117-b338-579d-a345-c154c2b6cf4e | note | Controlling Documents - Reference from Project Drawings
269a2ae2-623f-5eaf-a292-cab59b004ec2 | note | Method - Survey/Mobile Roads, Marks with Dazzle
03c0ecfa-3bb4-5bed-87ee-43b51c898e96 | note | Frequency - Chainages for every different pavement sections
5e19793e-1840-53b2-9a8a-57392918ff29 | note | Responsible Person - Subcontractor/ Engineer
7383cc56-2e7b-598b-a15d-423a2fdbbea4 | note | Verifying Document - Construction drawings
d8c0cf0c-ec1f-5560-95a3-cf3b88e2fd07 | note | Conduct - C
3a1a3928-0a2c-50b6-921e-7d7b98a7adb0 | note | Produce Record - C
35e1fb2b-d3c2-593e-8089-9c2c672cee4d | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
5e93a0c5-e681-52a4-bd6d-2d266a9f63b4 | note | Controlling Documents - Site specifics to be confirmed
3c92ac5c-36a8-51b5-acb5-5498428a5bfc | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
52636f60-2e2e-50f6-994c-bdb5c22e4fe7 | note | Method - Scala Penetrometer on Excavation Floor
9b208a06-37e2-527b-bb74-c868859c7a32 | note | Frequency - As required
2f8f7b72-7ce4-51d3-8086-9ce2fbb9d0f2 | note | Responsible Person - Quality Controller
1cdc4dff-a0c5-5b39-821e-6a8c614144be | note | Verifying Document - Agreed treatment plan
b4d25060-dcfa-5528-985e-2c9cd460170c | note | Conduct - S
b5c16b25-1f4e-54ca-9df8-2a1c1662b442 | note | Witness - C
0fb35849-a626-578b-acde-1a095b27a46b | note | Produce Record - S
09ddf3e4-7bd7-5c67-b802-b1980716ac94 | note | Approval - E
dbb1d090-08aa-5643-a56b-aeea224c10dd | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
b2596429-b487-509f-a936-f010f7a21e77 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
6d2436a5-cb4b-529a-b74e-0bb23e3b4a52 | note | Acceptance Criteria - 250mm deep unless specified
ad536714-9168-55da-8ac0-09fa500ecb53 | note | Method - Visual inspection
822d3817-9be0-5b1e-8a26-35100fa699fd | note | Frequency - As required
af910eb5-9f3b-51dc-9df2-89e746d6b620 | note | Responsible Person - Quality Controller
80e29439-77ab-5b51-a694-355b4dd6b9f0 | note | Verifying Document - Dig out site records/ Asbuilt
f103a798-1706-5d65-99ee-e55e691574a5 | note | Conduct - S
2e80b82d-e4ab-50a7-9dfd-3662092a53e8 | note | Witness - C
bf6f5795-8b1d-5e7d-8246-63cbcc06e749 | note | Produce Record - S
eea12972-dd3c-599c-8490-9a3996092df6 | note | Approval - C
785bf457-2265-585b-8612-6b0805dc7e0c | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
bd50840b-ed42-5388-a2ed-fe0b633dce43 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
d5a3d4c6-65e8-5295-9535-4e6592ccb10c | note | Acceptance Criteria - Scala > 3 blows per 100mm
66a5a25d-dd21-54f7-8f35-05096156bebf | note | Method - Scala Penetrometer test on base of digout
064706f5-d405-58ab-a085-08505ad5d995 | note | Frequency - As required depending on size of digout
b8266e2c-c073-5cf7-913c-b65592803504 | note | Responsible Person - Quality Controller
2de2ee37-650f-5305-bc57-aca4af8629f0 | note | Verifying Document - Test report
53e289d1-74ff-5f52-baaa-119b276d35d7 | note | Conduct - S/C
73fc48c6-e031-5c49-baf7-8d61fffacbb6 | note | Witness - C
e5a28030-d003-5c97-98eb-35ab60dffe7e | note | Produce Record - S/C
da07635f-b330-5ba6-812a-2b75a7bdbf9a | note | Approval - E
7c0c793c-3596-5708-a6a5-7a05e3dfb4d7 | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
6bf390f4-64c0-553e-9ce4-2bad137af13d | note | Controlling Documents - TNZ F7 Specification
4d5f671e-000a-5d53-80d1-e795c1dd8e11 | note | Acceptance Criteria - Meet TNZ F7 Spec.
f4ee18c7-b0a3-52bd-8634-c34211a9baca | note | Method - Visual inspection
234340bb-a2da-5641-a9b0-e95e219e7dae | note | Frequency - Per Delivery
7888a073-a41d-51a7-b5ba-7ff3f2f1f26b | note | Responsible Person - Quality Controller
edae2de3-420b-56ce-944f-27f16680df71 | note | Verifying Document - Certificate of conformance
fa2397ba-a32d-5c3c-b39f-bc97589a1ff5 | note | Conduct - Sp or S
0e3a0c61-b407-58d4-9500-40ca9339351d | note | Produce Record - C
f6c61015-4d44-5074-be2b-8536e84e9adf | note | Approval - C
8b46710b-6969-5520-bc7d-0a3768f17f04 | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
a5bfc23f-37d1-53d7-9b98-ddf7f7002f0b | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
5c2836db-92ba-5f5e-abcb-7fe0115a1e3a | note | Acceptance Criteria - Clegg value > 45
bc8cb729-d70d-5680-9926-7f1e69a247a4 | note | Method - Clegg Test
db11178d-a3c4-5fbe-9a24-1dd1acc6f484 | note | Frequency - Min. 2 per digout
f9d74d5f-8ff8-5974-97e6-5da18a27ca31 | note | Responsible Person - Quality Controller
732f7f83-2160-5a8e-be12-623098a3de5d | note | Verifying Document - Test report
eb85919b-c5c7-505d-9cf0-1f1619f55796 | note | Conduct - S/C
0952f42d-b173-5769-b574-3197673d298f | note | Witness - C
035162f0-89ec-5241-9dbf-5b101f3d3eeb | note | Produce Record - S/C
25f4ff12-ba42-560f-9558-9fb1d04ba7dd | note | Approval - E
40ae3f67-d148-5f83-909c-9d9271173210 | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
eeb50d65-64ce-572e-8456-9dd1f3e00c42 | checkpoint | Place M/4 AP40 Basecourse Material
d720d0c2-bebf-59a4-91e9-23eda93c776b | note | Controlling Documents - TNZ B/5 (section 7)
fa6a5f2e-e967-5ac6-8140-30ad65012df1 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
9b6de08e-b6fb-5243-b77f-d41e8648837f | note | Method - Visual Inspection
c8f9fe15-c250-5604-ad1c-0fd5496b00b1 | note | Frequency - On completion of placement
0d9dfe7e-80e1-523e-848e-31b30cf2e70f | note | Responsible Person - Quality Controller
afef3513-7bf6-548d-afb9-4ecfdaf55f08 | note | Verifying Document - Photographs and Daily Site Record
6746dd08-7b55-51e7-a3f9-86aa27222e84 | note | Conduct - S or C
1e387eea-c66b-5348-a74b-38ba3bc5269a | note | Produce Record - S or C
31447ff2-6709-588a-8608-09cf887f4578 | note | Approval - C
505cd4e0-7dc1-563d-b78c-f1b37b6664fd | note | Witness Point Y/N - Y
27c96781-3034-5bd6-8be1-9136ce336cf1 | checkpoint | Spreading of Cement
928ee523-8d2f-57a1-9677-6b765af14b15 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
819330eb-413c-50b0-90e9-865607d083db | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
15ef3ef1-4941-53a5-8bcf-45af36f86736 | note | Method - Mat test (1m² canvas) and Average Usage Test
92d7bf3c-8d96-5885-9d3d-afdaa642dceb | note | Frequency - per 400m² and upon emptying the spreader
edf40025-10ce-58d2-b140-c88b158655e8 | note | Responsible Person - Quality Controller
a9ddc955-f876-5d83-bae5-1f1e37fdfbbf | note | Verifying Document - Mat Test Form and truck dockets
5d0e5a6c-b165-565f-a0c5-d11866a61e82 | note | Conduct - S or Sp
44753d5d-68fe-51de-8016-2b183f0391d0 | note | Witness - C
851e4ead-af00-50e0-8be2-22858ed26fcc | note | Produce Record - S
810ff799-1acd-58a3-b0ef-3cbfb9f83f60 | note | Approval - E
c27a983e-28c5-56f7-8df5-2cd8a73800aa | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
900094a4-c351-5dbd-87dc-7e7ac5c7e651 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
c0bd7f21-8ab0-5043-95ec-3b074caf4b8d | note | Acceptance Criteria - 90-100% OWC
e2a72075-e93d-5174-a840-9f6d9ba5b2a8 | note | Method - Nuclear Densometer Testing prior to Stabilisation
1e350a1d-f302-5ed0-b165-020c3e9c050e | note | Frequency - ≥1 per 1000m² lot
29066f9c-9379-5a3f-82f9-719b5119e343 | note | Responsible Person - Quality Controller
07f2ad3b-4fa5-5d81-a58a-68d28727f97e | note | Verifying Document - NDM Record
cafa077e-a7a8-5827-af85-fa8ab62bf81c | note | Conduct - S
0242b76d-0de2-5559-97fd-f69140d79979 | note | Produce Record - S
9e50cc0a-41bf-56a0-be63-409d9b43ce87 | note | Approval - C
096fb259-d514-5b8c-9999-6e552ae4506d | note | Witness Point Y/N - Y
3aae6428-5972-5b13-a661-272c4bed881e | checkpoint | Cut Depth
a68edded-82f7-5c5a-b877-5c79793d034a | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
db4b9f91-a649-561b-9855-30410a283362 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
36dd2ccc-6f03-5cc3-8ba1-783899e82e62 | note | Method - Physical Measure and Visual Record
7d862ae9-edf2-5de8-90d0-4d38474105cd | note | Frequency - ≥1 per 200m of cut length
9b9a0e2b-12e7-5c0a-91d8-be4ceee04caf | note | Responsible Person - Quality Controller
7dbe1a17-27e1-54a0-8e58-a88ea2b4a6b7 | note | Verifying Document - Photographs and Daily Site Record
302190cd-713d-548a-8ab2-511b223ac90f | note | Conduct - S
0f4434c3-c78e-5923-8c29-51666d6a6dfc | note | Produce Record - S
487b7d49-c634-59a2-89fe-12d0e37d2ba8 | note | Approval - C
e09c6e4f-b88b-547b-95e6-948c39459a9b | note | Witness Point Y/N - Y
b4e8c8c0-519c-5ea3-a63c-d6e4e3e61d57 | checkpoint | Longitudinal Joints
4e9210f1-47fe-5ebb-a3ef-0912a01d1610 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
83f439b0-15c2-5ee7-8241-6f06b899d1b7 | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
06da9872-22eb-5f21-ae32-841f22ff0201 | note | Method - Visual Record
2cb325cc-7e25-5de8-aa18-300ddab329ec | note | Frequency - per sucessive cut
f9a35a76-e744-5c19-bbab-0d52dc1c4d55 | note | Responsible Person - Quality Controller
500f04ec-a1e9-5959-bb59-107e7a7e12e0 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
2a8806ae-0b53-533a-800d-7781f9353cb6 | note | Conduct - S
68bb535a-43df-5efb-be31-3c20561c0f70 | note | Produce Record - S
0e505e13-c2f9-5e8d-9da1-b67d9289ef5a | note | Approval - C
b7c574a9-e3b8-597f-acc9-52824bf6277b | note | Witness Point Y/N - Y
4adf91a5-413d-56e8-8c6a-9cb5dbaf546e | checkpoint | Continuity of Layer
0e5155e5-84eb-59ce-813b-10c955f8f354 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
d21bbf84-9b2f-5a08-b4a2-de2e499cf72c | note | Acceptance Criteria - Longitudinal overlap, 1m for cement, 5m for bituminous stabilising agents
428d4dd8-2b36-5e39-8653-f3ccba2cb4a8 | note | Method - Visual Record
72415d23-2263-589c-917f-1abfd7c0ff16 | note | Frequency - per sucessive cut
40279bd8-d6b4-5e2f-859d-8d6bca2f246a | note | Responsible Person - Quality Controller
dc846f8f-4af8-5c88-856e-d71ad710305e | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
d5ef8ae3-ff0d-5300-945d-a804ee51c0b9 | note | Conduct - S
1a6b3a52-feb7-5b6a-a864-9d897d28a939 | note | Produce Record - S
83985a08-60ec-5560-a327-ec7fe28a8b3f | note | Approval - C
221c9d86-3040-58d0-ae44-1d86f933c28d | note | Witness Point Y/N - Y
a3e7c399-2e95-59d2-b1ad-e3d1d43952bc | checkpoint | Stabilised Material Particle Size
557357aa-479b-5fa3-90c5-12067c8b75ce | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
b91491c1-efa4-5104-9805-89712de3cc8b | note | Acceptance Criteria - No excessive breakdown of stabilised material
7d91aef2-5e7c-5576-9dd7-92ee172b492f | note | Method - Visual Record
2b1dd5af-c555-5aeb-bf6c-f4590db39fcc | note | Frequency - within 20m of each section and then regularly based on material variability
2a79810d-4d07-5769-bc6e-3cf915e6fde4 | note | Responsible Person - Quality Controller
d76e1e83-e0f8-558e-b6fc-714608ce26dd | note | Verifying Document - Photographs
15d58e05-fc07-5916-9509-e2c1cc3c2d44 | note | Conduct - S or C
3349540f-a3be-5e34-bef4-41bf3144c20d | note | Produce Record - S or C
f20f122c-8061-552d-94b2-ccbacc07cf11 | note | Approval - C
6ac26779-2583-5a78-abbf-22a3a72a80e3 | note | Witness Point Y/N - Y
b2669c88-ac51-56ca-b8c1-ca203b10eac4 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
394931e6-5f45-52bc-9e3b-113ef1cf7606 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
834c8dd9-37df-543e-8d3f-0f31b5222af0 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
f97aa70f-dc18-5c8a-baf7-a9d3f947cb11 | note | Method - Plateau Density Testing
be7b284a-4f74-57b3-9ce9-585be5d7f3e8 | note | Frequency - 1 time, or additional tests when material changes visually
21c4f313-cb60-53a8-a5b8-d3cb3911bb5f | note | Responsible Person - Supervisor
37a61a7c-393b-5fad-871e-2c24d1001ed2 | note | Verifying Document - Test record
9c4268d6-92bd-5bad-8d2d-48beb1b84157 | note | Conduct - S or C
7e6f547d-24ab-592a-b38f-8dc6320fd75b | note | Produce Record - S or C
60a6f089-b4b5-5305-805d-d7a4a1b93918 | note | Approval - C
3c1fe4d5-e3d1-5dca-bf96-aec33dc469ca | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
008afb3b-0001-5910-983e-067f11881716 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
641228e8-c980-51a8-adcd-0029da539a6e | note | Acceptance Criteria - To provide MDD for NDM testing
2ce73971-5c2e-5b1c-a86f-b6ec398dc78d | note | Method - Plateau Density Testing
e071d0af-49fa-540d-87d6-6f2729c5158c | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
90c505b6-5954-5cce-ac03-e6e9eadb083a | note | Responsible Person - Quality Controller
9e77ef6a-25a8-5fa9-96c2-f103d9f3fe6c | note | Verifying Document - Test Record
701056ab-a52f-5506-aeaf-fbb53b096c8d | note | Conduct - S or C
7c6d70cf-f31a-5057-becf-7500dee82461 | note | Produce Record - S or C
4da2fa33-67f7-56cc-ab56-8299acc021bc | note | Approval - E
d553feca-f72d-5e42-8b79-6d1176dd1af4 | note | Witness Point Y/N - Y
1b96c1cd-dc03-50d2-9eeb-7acf490a611e | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
6a4d486a-5011-5d7f-bb63-13a165c27d0b | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
80043dca-8450-5ca9-ba26-d401ee520982 | note | Acceptance Criteria - To provide MDD for NDM testing
68769b62-b7fd-5a09-ad25-daaf5d05252c | note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
e1b221d6-0886-5cae-a9fa-c1b69ab183b4 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
afdced22-70fd-5232-a5e5-e07d02c56f37 | note | Responsible Person - Quality Controller
6428b68f-319e-5d1b-a068-6e1d1a13d78e | note | Verifying Document - Test Record
b5b5b3b6-96e1-5745-880f-6ab6dcbaf210 | note | Conduct - S or C
e57349a4-2188-5b16-a2ad-48ecc8afeef1 | note | Produce Record - S or C
c0389893-834a-579b-bfa3-7bbdd45ce884 | note | Approval - C
c9de54e1-3a75-5162-83a9-88c9419dcc53 | note | Witness Point Y/N - Y
9b641378-7dcd-5a3d-807c-a31562803710 | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
c1fc06af-5b28-5074-a6d5-ee8866ac42f6 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
5951b1c5-2014-539a-8baa-b71fc3f54b55 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
3855f0fe-ea0d-5a7a-bbea-c727c51beeff | note | Method - Plateau Density Testing, Lab. MDD
253a97c1-2a85-561d-8ee3-d45d20715936 | note | Frequency - At commencement of construction and whenever materials change
19be97da-fe16-5792-8a78-c39b85527081 | note | Responsible Person - Quality Controller, Engineer
3c1080df-58d2-5692-ad51-0b10da196b60 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
beb89dd6-135f-532d-963a-a2d44e842a9e | note | Conduct - S or C
b228748a-76b4-5ba3-9005-10e86a3a53a4 | note | Produce Record - S or C
b3507717-1a38-589a-8a51-e8ec7bb56b17 | note | Approval - E
9bbf0466-fdd4-501e-a3c9-10d7d590964e | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
5a6a345b-aa0d-5d77-89b5-9edc911cb5c5 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
142ab8ea-a126-5657-b7d8-c592e0d1f457 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
27d8bcfb-7a5c-5631-b446-363487f7998d | note | Method - Nuclear Densometer Testing
ca79358d-b428-55b4-a873-3f55c88142dc | note | Frequency - ≥ 5 tests per 1000m² lot
e949592b-4e62-54f4-861e-b77bc4e18aee | note | Responsible Person - Quality Controller
070a82f4-a578-50db-b2fe-bc84e7a159b4 | note | Verifying Document - NDM Record
436909df-8b68-547e-901b-6f3732d62cd9 | note | Conduct - S or C
612e5b11-1c10-5f90-ab10-6a2752839269 | note | Produce Record - S or C
a26b1bb6-602f-5105-843a-6c9bc20c3488 | note | Approval - E
1ae7a1b3-13a5-5cc0-913c-573fd513da0e | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
cd6daa60-e401-5df4-9c23-bd98b0efaa94 | checkpoint | Control Testing (if required)
f79504fe-b9bf-50fd-82ff-b075e2c28202 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
9139d3a5-a17f-565d-81df-220f225a07d9 | note | Acceptance Criteria - Nil
e5fbc45b-5c2a-5818-a07f-633e1753a06f | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
1989d390-d0b6-5dcb-bb2d-1e8c3d5e8453 | note | Frequency - when agreed with the Engineer
3daff192-40c4-5bca-9353-0a48a15879f8 | note | Responsible Person - Quality Controller
5801bcca-dbb9-580a-bebf-224ea2335dfd | note | Verifying Document - Test Report
d9598e4c-6c60-5daa-a349-03cc6fb4edd4 | note | Conduct - S or C
36ea0c9b-0a20-587b-a584-2a6e1b2ed8c4 | note | Produce Record - S or C
86e6d4f0-9555-5565-a638-63a616df36c8 | note | Approval - E
49354c3d-90b3-575c-afdd-8ffa9e6c1c94 | note | Witness Point Y/N - Y
63ac480a-f8b5-58f9-bbf7-a763b61d12c2 | checkpoint | Surface Smoothness
40ad8453-a541-51af-bf7b-7fdc63c58a16 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
21df0b69-b064-5e6c-acc6-914ac51bb44d | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
ec74d63d-ce29-5c93-8d95-5447ea105e3b | note | Method - 3m Straight Edge
9bc997ca-faba-5d73-a97a-c21a2a2f757f | note | Frequency - during construction and prior to seal
9545562d-89f4-5024-898e-7bbc5e4d3ffb | note | Responsible Person - Supervisor
e8a82b4d-3ec9-5b72-8408-1dd86a4f3ba8 | note | Verifying Document - Photographs
d7d84fef-cfb5-5dd9-8c1f-39a1b805425f | note | Conduct - S or C
edc06f9b-cee9-5c0f-9999-ca776865d755 | note | Witness - C and E
a0d8de9a-46f0-55a6-bf43-9c241896833a | note | Produce Record - S or C
1c1f7ac5-c222-5523-81b2-cb3c4dc469bb | note | Approval - E
61329608-9aa3-5839-8f70-ba5afc2bf516 | note | Witness Point Y/N - Y
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
598e69e5-9cfb-5d4c-a45e-e6e3c6b936ab | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
decf7c30-c6ab-563c-af22-f5d81c1f3650 | note | Acceptance Criteria - Between -5mm and +15mm
96866e46-7ee9-5b95-b3af-eb185988d62e | note | Method - String lines or Survey Asbuilt
5fe93a42-1537-5336-8583-78b99f6e2ec5 | note | Frequency - during construction and prior to seal
f88e763b-ddc4-5e15-a5d9-27b333fe9e63 | note | Responsible Person - Supervisor
45576869-1164-56a8-9ab0-067d9262f189 | note | Verifying Document - String Sheet/Survey Asbuilts
c0fabebf-4993-56d7-9602-bd14801ad262 | note | Conduct - S or C
7bb9b1e6-c98d-5958-b918-90d4492427d7 | note | Witness - C and E
65f96d0e-d30f-5a41-88e9-9256a1652c19 | note | Produce Record - S or C
852cb44e-f9db-580e-93c6-02b543d334ab | note | Approval - E
2ab7e535-b9cf-5d91-967d-c56a14545e7f | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
a2f4283f-a340-5ba5-86d9-72b14ed7e5f0 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
5ed97abc-9510-52c1-9205-85bb340a70d7 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
98ee1c45-c0e1-58b8-b182-1692db590a5d | note | Method - 3m straight edge or Survey Asbuilt
4a53e56e-c8bc-56cd-a1cb-361f8c027908 | note | Frequency - during construction and prior to seal
8d231682-82be-5540-86b0-10d5e63ce019 | note | Responsible Person - Supervisor
7b9b5283-1a1f-5a44-bfb7-9df632c1f684 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
40235c03-dfad-5827-88f0-bc8aea9a7bac | note | Conduct - S or C
2223993a-f879-5273-b042-957f00ac62a3 | note | Witness - C and E
400e2a18-1ba1-53fa-a231-a7235535230f | note | Produce Record - S or C
42de19fe-3097-5fca-8e0a-0229efe4ab8c | note | Approval - E
6fe97dc3-ed82-5927-ae5b-c6480fd23f95 | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
2d118ae3-7771-54a7-ab15-14adedf3588c | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
f5c1abc3-613b-574a-a948-beaa9af2f536 | note | Acceptance Criteria - Tightly bound matrix post sweep
80f46cb9-8405-51f3-9dc1-12d7828dc0be | note | Method - Visual inpsection
35d9f914-f72a-5792-9203-bd4ce4da6720 | note | Frequency - prior to seal
587cc9c6-86c6-5c3f-b04d-bda179e45a51 | note | Responsible Person - Supervisor
1548b5da-b9c1-54b1-bb75-d8bc5b562ee1 | note | Verifying Document - Pre-seal inspection sheet
944cc504-131c-552f-b827-8ce8726f2014 | note | Conduct - S or C
99877474-7032-5507-884b-08a3805b027a | note | Witness - C and E
0efe2d52-43d1-5f4d-b8da-d3b0eee4e999 | note | Produce Record - S or C
b2a5d770-2758-50dc-a310-ca010dd3a15b | note | Approval - E
d1c6c689-3860-5641-ae4f-65c8a04bee5b | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
9a4e12a8-17c3-5c12-a0ac-12067d232cf0 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
d4e0ddc6-82e6-57f9-99f0-986e80ce1b03 | note | Acceptance Criteria - ≤80%, however 65% is ideal
614a0238-666a-5cfd-a9b4-225d4d66f82e | note | Method - Nuclear Densometer Testing
03c9acca-e1fb-53e0-bdc6-ed346336f324 | note | Frequency - ≥5 tests per 1000m² lot
928685aa-95b9-5390-9de1-49f2bd1df9bb | note | Responsible Person - Quality Controller
923fd620-8025-5204-a408-24352b9e07ed | note | Verifying Document - NDM Record
4404a9cd-86d0-5998-9537-2bc92c48d032 | note | Conduct - S or C
e71d2a0c-2439-5b2a-9eef-de4ce7aa89ab | note | Witness - C and E
72295c6a-40bd-5370-984a-ff4240c1a660 | note | Produce Record - S or C
8abb5711-4dec-56ae-ace4-982580595e47 | note | Approval - E
13da43bb-bd38-5d86-b18b-29daf80f661e | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
3733b082-27e1-5387-a304-bc6209c5466d | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
db3a0cdb-01c5-5002-9716-ddcba0b08d45 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
69adcf66-1777-5c52-bb27-0ad2efb7f86b | note | Method - NZTA Maintainence specification section 6.1.2
8f7bceb5-e677-5781-a700-a67a26fb422c | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
84939dbc-6865-5426-90b7-8fab87cf2c9c | note | Responsible Person - Quality Controller
05089525-51d2-50f0-8224-48e358f4007c | note | Verifying Document - Test Records
443a170f-29f1-5404-b93a-f27a9f5a738f | note | Conduct - S or C
d767e540-0507-5ceb-8a45-d5ac2fd49e35 | note | Witness - C and E
38e8142f-cb5a-5a25-bd74-364e1cefc795 | note | Produce Record - S or C
939daa5d-1958-599b-bc8d-9a9bb0489361 | note | Approval - E
2041180c-94c9-59dc-91f8-8c0f2774a146 | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
f6ac91d4-5c0b-53d1-9e4e-00bc03939ff3 | section | 5. Chip Sealing - 5.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
af25efdc-27e2-5e18-935b-bd6ee45bc223 | note | Controlling Documents - TNZ M/1
7a1e6f0a-749e-5f2f-9924-da0dcb8b50aa | note | Acceptance Criteria - Table 1
6e2ef38d-885c-5bae-9946-86566c6e614b | note | Method - Property Test
1f1d7912-7886-5c07-a783-b94dbfdeccb6 | note | Frequency - Annual
e8655206-ca37-5205-b044-0fcac40bdaf6 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
432b2681-52d1-531f-8299-43acd94b5511 | note | Verifying Document - IANZ Report's
efb96498-7491-59db-86d8-660474a84bde | note | Conduct - C
0e27173f-c0b3-5de0-a8ce-0fa6207a3128 | note | Produce Record - C
5a8fa077-2df9-50a2-a120-8a411bade563 | note | Approval - N
64b53ab4-9771-536f-8a0d-3747add7b280 | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
fff9235c-21f0-5ef1-9499-4a1be31717e3 | note | Controlling Documents - Higgins Internal Specification
d801cf6e-0154-5c96-8b1f-2bbd52f63ae1 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
0cbde325-8d39-5e02-804c-c4d4df7034a4 | note | Method - Property Test
a9bb9f91-78a2-561d-a011-ced37f50465e | note | Frequency - 1/100,000 litres supplied
2e956199-de09-5bd3-b862-f6513b25fac5 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
0ad4c5fc-c5f3-5546-9001-1da5e19a3276 | note | Verifying Document - IANZ Report's
4da8962a-b5cc-5b15-8163-99be9bfc18ef | note | Conduct - C
a1597ce6-0771-5f4f-b283-341b0b2e1e32 | note | Produce Record - C
946c04d0-0b9d-5ece-a82c-d18bad959985 | note | Approval - N
8297e4e2-0fb3-5845-919d-3ad3fa82eb1e | note | Witness Point Y/N - Y
271433f5-90db-5716-947f-66b53e064a88 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
0512d2fc-6ae8-5a0f-a6e7-97660a9f2cbe | note | Controlling Documents - TNZ M6, RNZ 9805:2009
cb390cdc-a7e9-5cc7-84e0-4b6c9825575d | note | Acceptance Criteria - <10% fines under 230kN minimum
bcafc10e-e3d5-53d0-804a-82a08a0266a3 | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
19758481-de3d-5551-8bac-0363c7afe9ff | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
f5db346d-0ae3-5e6d-b247-b047f8af734e | note | Responsible Person - Surfacing Project Manager
376ebba2-4774-5c02-aa29-77124e5e3f0f | note | Verifying Document - IANZ Report's
e66c079b-517d-5eb1-8e22-23e1456211da | note | Conduct - C
7c7bbb8d-e060-5613-b8b2-26a5288181e5 | note | Produce Record - C
bc5ae33e-e1ad-513f-86c2-015dae05f6fc | note | Approval - N
d33f6c66-d34f-5f0d-8bd6-7e9c67b039b7 | note | Hold Point Y/N - Y
6001235b-048c-5705-ab46-316e6fddaf77 | signoff | HOLD POINT
b5105286-fa50-5f37-8ad8-ff00dc521109 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
7f350442-cd3e-518b-b647-abb0693050ea | note | Controlling Documents - TNZ M6, RNZ 9805:2009
10da445f-88bf-5a31-8650-bb8759d27ad1 | note | Acceptance Criteria - AA or BA
33bd4f1f-9adf-5941-a7f0-797684184f52 | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
18ba1461-0202-5de9-a834-7c2e04a3d31d | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
643b81d2-47fc-5505-b6a8-4d6929113043 | note | Responsible Person - Surfacing Project Manager
fae92580-a9ea-5bd3-8501-648f894b39ac | note | Verifying Document - IANZ Report's
f82c4ad1-5136-5f97-bd52-be7efe16040a | note | Conduct - C
f18c01bc-d98a-59e9-941f-a8abe6d44913 | note | Produce Record - C
17f286f3-a4cd-5f44-b4d5-a88c80d70979 | note | Approval - N
e932f074-b78b-5a59-b67e-b88148256e9e | note | Hold Point Y/N - Y
d36fb53c-673d-5ad9-bcd6-d21d23c23bfc | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
4a6eac88-4d2e-501d-8afd-0126de5986b0 | note | Controlling Documents - NZTA T/10
718c3752-5d7b-51eb-83f4-c0e62c46abdf | note | Acceptance Criteria - Meet Skid performance Requirement
098ea5b2-3029-5c3a-9898-e3a6712758ad | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
b62a6b33-6e79-513b-92c6-6ceb382e9ba5 | note | Frequency - Each Site
c173aad1-118f-5fd5-aeea-e64ddd6dedd4 | note | Responsible Person - Surfacing Project Manager
25a4c5fb-4ded-500e-b5ea-1e405c1b4ad6 | note | Verifying Document - IANZ Report's
2c478548-f816-5d00-9f3e-512aa5e2f153 | note | Conduct - C
0bcad152-e323-58d7-9a89-e8a858156304 | note | Produce Record - C
b0c4e4fe-50bb-5201-83fc-2dbfeb9a5d05 | note | Approval - N
5d1f2446-73bb-5a4a-b2a2-d353a69d240d | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
dbb0a260-d855-5c67-8ec4-93a3ac144a33 | note | Controlling Documents - NZTA P/17, M/6
d25f971c-fb51-5efa-bdaa-2b713a6d99e4 | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
bfe625f3-19d9-5afc-8936-75dd466bb430 | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
ce550123-0c38-5041-b73d-051a05558a8c | note | Frequency - Per Stockpile
398101bb-b342-5715-b893-be3f39eed7ea | note | ○ <100m3 - 1 Sample
1722cecd-a849-5a4f-8ffa-819b2bab60e4 | note | ○ 100-500m3 - 2 Samples
a817d773-3f50-5ffe-b3bf-d68aef2fa353 | note | ○ >500m3 - 3 Samples
ec0082ec-6c39-56c9-9255-8e17373793cb | note | Responsible Person - Surfacing Project Manager
9835847a-e3b2-5fc6-94c1-81d1c5935319 | note | Verifying Document - IANZ Report's
854551f4-b853-5189-8be9-07e38ce79eff | note | Conduct - C
7a104f7d-5758-5efd-8d86-1342ea0b608c | note | Produce Record - C
d4671e38-b296-5a1a-98a5-954698638c01 | note | Approval - N
bd7bec02-2f14-5016-89c8-2cb09f575301 | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
3bea6449-d7a0-51dd-a19e-33b3d7e20807 | note | Controlling Documents - NZTA P/17, M/6
3601f9ad-8f24-5069-9189-da538e7437d5 | note | Acceptance Criteria - As per Table 3 NZTA M/6
4587e66d-930b-5fe1-b32f-d51fa2a7cb36 | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
5edfec4f-d163-55b5-a22c-94bf4500f9df | note | Frequency - Per Stockpile
9728b56b-7c07-53a9-9a19-7ddf1a4bd01a | note | ○ <100m3 - 1 Sample
4e334eb0-42a0-594d-8cdf-bde0b876318c | note | ○ 100-500m3 - 2 Samples
5f5ff8f3-db1e-50ca-ae2c-0bfe90877e86 | note | ○ >500m3 - 3 Samples
8718d464-d707-54ce-a06a-f8676ca3bc48 | note | Responsible Person - Surfacing Project Manager
3bb1c063-adae-5702-8a48-31619612c0ba | note | Verifying Document - IANZ Report's
79b12619-7a5b-50cb-8a11-d9cc1afe418d | note | Conduct - C
018becee-3143-5544-9a3c-898b6d368482 | note | Produce Record - C
57ab607c-7000-53a9-ae0d-007c8db110a3 | note | Approval - N
4a3a605b-d93b-5a0b-a783-a41e02011267 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
df7238a0-3589-5297-91f3-b9796c7661dd | note | Controlling Documents - NZTA P/17, M/6
6ee17359-5290-516c-8806-2563c47fe21e | note | Acceptance Criteria - Min. 98%
f3f4d928-ba6b-5542-a503-8748ad0fbd06 | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
4c14cc08-930d-5e4f-8c0f-2c23533b9123 | note | Frequency - Per Stockpile
4a677032-2a81-59f2-9741-99191628d4eb | note | ○ <100m3 - 1 Sample
444d481a-388a-5380-9251-80c1a0d7b718 | note | ○ 100-500m3 - 2 Samples
3831a3dd-4d39-5122-8433-1ed7b4c1aaa9 | note | ○ >500m3 - 3 Samples
5995f2ff-654a-5b18-ba3e-c874088b8773 | note | Responsible Person - Surfacing Project Manager
3ed77456-f1a4-5139-a544-063f9d22790b | note | Verifying Document - IANZ Report's
abce80e3-41a3-5cf3-ba9b-da7a6e53ca24 | note | Conduct - C
8f8b943c-6262-58c4-9c1f-13e9bbdb4c75 | note | Produce Record - C
43de61b8-98a4-546b-9fcf-93eb0cc142cd | note | Approval - N
5fca5523-c1aa-5605-a802-852b104e222d | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
523f4799-3aea-57f9-bada-e223846d1e19 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
ca2e63b2-ad2d-5ac0-9bde-3795b8736ab3 | note | Acceptance Criteria - Client Approval
cd56213f-b9da-5988-8601-5dba7371dd5f | note | Method - Review
90b213f5-c28a-5f84-80e1-36fd0e81d91a | note | Frequency - Annual
5559fb94-b420-50cb-9280-8a0a4389f68c | note | Responsible Person - Surfacing Project Manager
a6d6fb30-0043-5d79-8283-708843fc834c | note | Verifying Document - EBOP NOC Design Report Acceptance
b24200e2-3d90-5898-b038-18eede94c84e | note | Conduct - C
a0308958-fd59-5164-bd08-29b2ca3368ab | note | Produce Record - C
eb2ab16d-34e8-557f-997a-730fd2568940 | note | Approval - N
39da249b-e6d5-55fe-a24c-ccbfe3d5e3d9 | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
2d90825f-40a1-55cc-9369-13e616f644fc | section | 5. Chip Sealing - 5.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
a2346acf-287c-501a-9d89-878cdf80cf63 | note | Controlling Documents - EBOP NOC Design Report
2e2e2ce7-16b6-5289-852c-1fc4d3c69114 | note | Acceptance Criteria - Visual Inspection
8da80c49-b3dc-52f1-bc73-428e52935c23 | note | Method - Visual
2361d5e6-0108-5123-aef2-053b85693304 | note | Frequency - Prior to start sealing each site
57b00810-564e-5ef7-b356-93aec73782cc | note | Responsible Person - Surfacing Supervisor
89745d73-defd-5ac3-8dbb-8865591464d7 | note | Verifying Document - Chip Sealing Quality and Site Record
02269a26-140b-5b04-a09a-612ee7ffcf72 | note | Conduct - C
29b22932-c65b-57f9-a84d-ed9c8c95b3a0 | note | Produce Record - C
98109510-f93f-51d3-96d5-94c177218c2e | note | Approval - C
d7838bff-f30b-54d2-919f-96281923d9ba | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
87330a60-8517-5654-a405-61b22916d253 | note | Controlling Documents - P/17
2476c80a-c771-5e75-a200-98fa99faead8 | note | Acceptance Criteria - Visual Inspection
f04e4380-297b-5b45-bdb1-143168f44974 | note | Method - Visual
850e999c-0fc9-57b3-967f-c21955c03658 | note | Frequency - Each site, prior to start of sealing
8680d2ad-c3ef-58a7-90fe-df1db3bce39e | note | Responsible Person - Surfacing Supervisor
8a15ed1e-9795-54b5-b155-93e32502d808 | note | Verifying Document - Chip Sealing Quality and Site Record
7aa93b4d-dc4f-50c7-a6c6-c87f183a5c0b | note | Conduct - C
6610d6ac-851c-5deb-9d9c-a81617174295 | note | Produce Record - C
0b80109e-b591-5018-9010-40a1abd5b238 | note | Approval - C
a54add57-aac7-58e6-bcd4-b248af6b0ae3 | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
47627050-b576-555b-b9f7-820c2df39f1f | note | Controlling Documents - N/A
9358a65c-5399-5a1f-b22e-dac6df702cd6 | note | Acceptance Criteria - Visual Inspection
5e559e8f-4cb8-5402-8e55-d4bf3e582cf9 | note | Method - Visual
dc6e3bf0-571f-5bf1-a1f3-139233918a09 | note | Frequency - Each site, prior to start of sealing
8d49cb79-86a3-5950-a066-995d34714b86 | note | Responsible Person - Surfacing Supervisor
74e6cc66-fc27-5405-b89b-bb81e08f1f8f | note | Verifying Document - Chip Sealing Quality and Site Record
1600942b-41fa-5a7a-98ae-63f6910b8044 | note | Conduct - C
ec570fc0-b118-5811-837c-bdbdf78686bb | note | Produce Record - C
f68e7d51-f92c-56e9-abd2-cdcd7ea86d3e | note | Approval - C
f896c862-0434-5e57-b233-fe0188e08065 | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
75100315-e63e-5314-a36a-76f052341545 | note | Controlling Documents - EBOP NOC Design Report
86a6b2d2-8127-529e-a4c2-85639a3e5590 | note | Acceptance Criteria - Details/chip correct
52d996ba-2769-5424-96b3-e6c65b49107a | note | Method - Visual
3ad66c2d-dea0-5aa5-a0d4-1295e40206d6 | note | Frequency - Each Site
abad29d3-f5a2-5cef-9d7d-c168c22dfcd1 | note | Responsible Person - Surfacing Supervisor
f9a317da-21ca-5e5c-a076-49686c851281 | note | Verifying Document - Chip Sealing Quality and Site Record
7f952432-585c-5f3f-a69d-7fecb62f6837 | note | Conduct - C
d699fded-be7a-563c-8be7-9009b6dfc926 | note | Produce Record - C
4ceb7ed8-9ca6-5ba0-8944-e59558f9ba21 | note | Approval - C
3c593d98-d5f5-511b-8d6f-778ab8dc7dbc | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
d340bd59-8a77-5135-b04c-c6f388f70ea8 | note | Controlling Documents - RNZ 9803_0513
f56dff36-c5b3-5244-9244-873ac248acd0 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
291008d6-3183-5f8a-b629-3e32299ce264 | note | Method - Sample and test
7584d496-bed4-5e47-9a1c-c9cd3e13cf12 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
76a025ce-6a1f-5558-905e-ec2e84c1e111 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
de6dd599-e0db-5594-93fb-73238ee71f8a | note | Verifying Document - IANZ Report's
f8a29fae-26cc-5b81-9a75-09d966948c60 | note | Conduct - C
4a531776-abe4-516d-a28b-c235457f9828 | note | Produce Record - C
0452f19d-dac2-57d6-897c-b88ea46ecd65 | note | Approval - C
95407205-b732-54b8-a8f0-75704436f48e | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
77e72b69-7235-578c-8fa1-e869efdaeb66 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
de7f37e8-d227-5ffb-95ac-fdd5fb8c9365 | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
139f8c7a-a2ee-5b3e-a25a-b961ebd5cd7b | note | Method - Test, Review
0ec1c617-729d-56cc-94fd-319cfd2cedbe | note | Frequency - Per Sprayer, Per Site
cb29b8fe-eb08-5010-a058-e645cd5e21a9 | note | Responsible Person - Surfacing Supervisor
98235e7e-97ad-5f1d-83d5-26b847428e3d | note | Verifying Document - E/2 Certificate. Spray Sheets
8be067f3-ed2d-5994-b0ac-c947bd74b6f4 | note | Conduct - C
8dd11200-4e1f-5d3c-b446-60d33a3e01ee | note | Produce Record - C
98f29f35-6740-50f0-9e20-f11b276dc211 | note | Approval - C
d372c92f-82b6-5bea-8af8-8057d0c61bc1 | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
e6a3f9b7-1d16-5911-8da1-33794a581099 | note | Controlling Documents - Chipsealing in NewZealand
e9518218-1565-51d0-aaf3-5d41f5ee8aaf | note | Acceptance Criteria - As per Chipping Guide
bb8dac13-6da2-5b83-b535-cf17da7f533a | note | Method - Visual
ff0da2bf-64b7-5a6f-8f55-ca0a339c4715 | note | Frequency - Each Site
1ac9995f-f24c-53cb-949a-887a80ce9d16 | note | Responsible Person - Surfacing Supervisor
c15abcca-8394-5357-9f18-e49354eef9bf | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
42d9ad4e-ceca-5494-b688-6410d88654dc | note | Conduct - C
00b5abdb-21be-5790-8ff0-db703020f624 | note | Produce Record - C
5d765101-8062-5553-a1c4-35b1815a85ec | note | Approval - C
58fd84c1-2cd0-5461-a30b-00abc704b205 | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
ca3c21a4-4045-500c-8c9e-5f15a43c44f6 | note | Controlling Documents - Chipsealing in NewZealand
65adf336-3b31-576e-8be6-c989d617dc67 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
d06493ac-aeab-5bcb-9b0b-9b1cdedd9b3a | note | Method - Visual
4aebcc0f-1ce3-551a-86fc-f724b7115227 | note | Frequency - Each Site
4a2fca16-9d91-557e-9aa1-18fc9ed2a232 | note | Responsible Person - Surfacing Supervisor
bf6ef0bf-ee6c-5e36-b995-0296eca06a7a | note | Verifying Document - Chip Sealing Quality and Site Record
d2b1ee07-585d-5455-ac03-c49af876842e | note | Conduct - C
5059159b-2a41-5d4d-a361-119dcce4662a | note | Produce Record - C
8de7d646-8dde-57bf-aacf-dde2399c5c3f | note | Approval - C
a05687fc-2673-501e-b2ec-3dbb2b3a3686 | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
0fa94f93-e07a-5076-968b-5bcedc99319e | note | Controlling Documents - Chipsealing in NewZealand
ecdac5fc-237b-5822-8657-33b0ed8f707d | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
986417b7-dc4c-5937-aedf-d55d82bb694d | note | Method - Visual
d26f482b-73d5-541b-9b4e-aba61276d03c | note | Frequency - Each Site
85449dba-54b7-596f-a223-132ea55b96ac | note | Responsible Person - Surfacing Supervisor
e5b969b6-3615-5f69-b338-a02ad6f223b7 | note | Verifying Document - Chip Sealing Quality and Site Record
42229aad-4e84-563c-8edf-749593d4278a | note | Conduct - C
73cf0597-2af9-5cd8-9bf3-176fc0564baf | note | Produce Record - C
bc6e7b50-4569-5fcd-b34d-3ef2e8a351cd | note | Approval - C
aa291875-8117-516f-a5df-14467bfef77b | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
90c1fda7-422c-577b-b20e-71364400584c | note | Controlling Documents - Chipsealing in NewZealand
28691db6-d077-50b6-ac54-834b3f3a73ce | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
cbbd7925-b49d-5df4-9775-894dd04be573 | note | Method - Visual
9af929f8-cde0-51d8-9151-0acec333f762 | note | Frequency - Each Site
16abd1af-9346-5458-a7e6-c5a6fde506f4 | note | Responsible Person - Surfacing Supervisor
765f5caa-206a-5216-bf8e-0aaca19b5d3c | note | Verifying Document - Site Record
3c039237-86eb-577e-862f-7a418b4079ee | note | Conduct - C
10a81e37-9d7e-5e78-8507-8336ecadb9fc | note | Produce Record - C
a0dddfef-50dd-5639-a1f6-fbcdbe59db71 | note | Approval - C
00ecf109-f024-5c6c-a835-33dac6944002 | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
412068fd-64b4-5576-96a2-d3708948609b | note | Controlling Documents - MOTSAM
c2cd8226-e245-5a56-aaea-dd7e3827cd6f | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
e91f0d54-4861-589d-a2b6-f5de5fa25d76 | note | Method - Visual
12936b54-a739-5953-9976-b3749bc56035 | note | Frequency - Each Site
441c2ecc-c653-533d-bddf-3fff6f1a79a1 | note | Responsible Person - Surfacing Supervisor
6122b9f4-d0e0-5d31-8a77-409ea29b1052 | note | Verifying Document - Site Record
fd9a3eb9-a984-530a-ab52-44d64390543d | note | Conduct - C
afbda08b-4377-5a2c-a942-4a09fdcb781d | note | Produce Record - C
eb6f849e-3c98-5038-baac-89c6cd13aef4 | note | Approval - C
9f949af6-d1c5-516e-843b-0da5bc387bf1 | note | Witness Point Y/N - Y
2fa24de8-fb07-5d57-947e-3eea20cf5b9a | section | 5. Chip Sealing - 5.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
d95346cb-1dcf-5caa-9863-021b82166c92 | note | Acceptance Criteria - Formal Agreement
a0680697-4a07-5952-af6f-5e4187f07c79 | note | Method - Visual Inspection
4e932cc2-0c62-5107-8768-b9975c1c3b76 | note | Frequency - Post seal sweep
2b1df8c5-df1b-58ca-a259-33775e25e88f | note | Responsible Person - Quality Controller, Supervisor and Engineer
901e3c30-e03b-5673-a10b-93144fdc078c | note | Verifying Document - Meeting Minutes
dd8884aa-d96b-5685-b321-b1ba1c91470e | note | Conduct - C
5b068c3c-d68d-5e86-97cf-722c1a8d41d2 | note | Witness - C, S and E
399d8b81-c546-5851-b5d8-c3d929f45ad2 | note | Produce Record - C
607c40fb-1916-5b06-a5a6-0e452707340b | note | Approval - E
98894a85-7bc9-5b32-8424-128973892bd7 | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
5a657970-5c66-5a7a-b78a-968074dfad40 | note | Controlling Documents - NOC; MS 6.1.3
2d846bc8-b3d8-5550-8116-5faa65ac421c | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
d560a0ef-5a67-5850-bd25-26d87e548b04 | note | Method - Record
32c01538-24fe-53f2-bbc6-7cec7ae29de9 | note | Frequency - Within 2 months of completing the annual resurfacing programme
513a7511-e345-5a65-981b-864f014eb1b9 | note | Responsible Person - Surfacing Manager
8b79c67e-8218-5133-9308-598b7f202961 | note | Verifying Document - Construction Completion Report
a36a260f-14f6-5c47-9b2d-ed53482d06c6 | note | Conduct - C
09565f05-344d-55c3-a9d7-61cd9b6bb6eb | note | Produce Record - C
2f371157-e127-5a70-9872-18071674d7f1 | note | Approval - C
c3c0cf6a-cfb9-5d78-8d4f-5b381e0f60a2 | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
08375837-02d9-5dd5-87fc-c2cb6dc78b88 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
caa44b6e-9cff-5b08-b269-f8d6d7f62f2f | note | Acceptance Criteria - Engineer Approval
59d0c7bb-1a46-5fc8-9b05-eb7fac4497d4 | note | Method - Visual Inspection
aa80680c-c046-58b0-b07d-73613629287c | note | Frequency - ≤2 months of 1st Coat Seal
14494421-3446-5d3c-a823-d5706f8f7420 | note | Responsible Person - Quality Controller/ Contract Manager
cc3b9dda-7b7e-510f-be03-64612ae2c750 | note | Verifying Document - Signed Report
282323d3-75cd-55a2-b5fc-57570a7b9a8a | note | Conduct - C
669cb594-f965-55bb-9687-04fb46912a3b | note | Witness - C, S and E
aa4ac7b8-626d-50ca-9839-b3cf25d0da30 | note | Produce Record - C
3229249e-0edc-53ee-bb03-67850cfd81d5 | note | Approval - E
6e325f7c-1dbf-5db1-8362-3259ade303fb | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
daa21d85-88f0-5a84-9492-2636215930d2 | checklist | ITP - Pavement Rehab - SH 30 - Sala Street | itp | ITP - Pavement Rehab - SH 30 - Sala Street
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
7fd9b05b-9d9b-5dac-807e-4c9bf1aae7a9 | checkpoint | Pavement Treatment Design
679e0504-8d34-520c-95b6-9b484ccae0a1 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
731d9ec1-efd8-5a8a-bb4d-aba985b08861 | note | Acceptance Criteria - Principal Approval
1ea596bc-4995-5199-8777-ce8e20aa799c | note | Method - Contractor and Principal peer review
e95ca6b7-db66-5258-b7ce-10c21f6177db | note | Frequency - per design
a7429845-b9d0-53aa-af60-bcf79d634068 | note | Verifying Document - Pavement Rehabilitation Design Report
83cd5c24-082f-54f1-a57e-9b1e9ee5e199 | note | Conduct - C or S
f9a8e594-86cc-53b2-8fbd-60b81a439b0c | note | Produce Record - C
182529ed-74e2-5df5-aa12-9c6b7a80e6b2 | note | Approval - E
ad591f97-2f72-5ee0-8761-cf200aee3ea0 | note | Hold Point Y/N - Y
d794d912-67b2-52c1-8ee8-020c2e439364 | signoff | HOLD POINT
36362436-b1e4-5e95-af81-437ff9bbd938 | checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
ed0babda-9b6f-5730-92f6-62bf80099e28 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
d0d417c6-a053-51ba-8aa0-521c3f897416 | note | Verifying Document - Sampling Worksheet
4c594585-0780-5f9b-86fb-0390d2d55236 | note | Conduct - C or S
eccf0d41-ba27-56a7-a7f2-c37b84254e04 | note | Approval - S
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
920cb6ed-28ff-5240-af50-c936e242fc71 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
90d4b182-6396-5ef3-93b5-c5b9c8278db2 | note | Acceptance Criteria - Soaked CBR ≥ 40
ec71d89b-8c76-5fc7-9a39-d51b54821ffc | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
3898afa3-12c1-5677-83a3-cdfce0526a72 | note | Responsible Person - Supervisor
feec31c6-a134-5d3c-a735-d13490e55f99 | note | Verifying Document - Test Report
a4a8c839-afdb-53c4-a02d-73f78e4772df | note | Conduct - Sp or C or S
072acb3c-4758-5710-8440-30a7dfc11452 | note | Produce Record - Sp or S
c8baa2b9-0182-5990-90db-224f602eebf6 | note | Approval - E
e631ae58-dc67-52b7-b931-198fde3f1aa5 | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
ae7e2d83-e996-5777-8251-1ac263229947 | checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
a4e1ea6a-9c35-52f8-87e0-6733b8ecb975 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
03e343a1-5b7b-578a-83a3-d92e699be760 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
9ba8f335-d24b-5aca-9634-9a50a0c228ea | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
7f602f2d-4267-55af-af42-051f12176bd3 | note | Responsible Person - Supervisor
ca1973c5-e7c4-5866-a2ee-c5f01224b56f | note | Verifying Document - Test Report
10b10ba0-20fc-5009-820f-9b52c19e25f1 | note | Conduct - Sp or C or S
944a62d7-4c71-598c-9b0f-ad74e7472226 | note | Produce Record - Sp or S
b36b6dda-f402-5983-927e-980f65e5bdd4 | note | Approval - E
82578646-e030-5722-9da8-fc73730ef560 | note | Hold Point Y/N - Y
59b9d644-63f9-5af7-bf31-75c1a6bf1a10 | signoff | HOLD POINT
41db2c6a-8df8-510d-b113-01208a63cb34 | checkpoint | Materials: M/4 AP40 Material - Aggregate Sampling
6261c58a-7484-5fc8-84ac-5d6204046307 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
8b059339-ead8-5278-ade7-53891bc4a123 | note | Verifying Document - Sampling Worksheet
49eece5e-eae0-597f-adf0-d62379505a8e | checkpoint | Materials: M/4 AP40 Material - Source Property Test (1)
20834aab-122e-5b60-9d95-d35bbe6c7f01 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
2ec56ed3-c5c2-515a-8910-1cb7fb9ef79a | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
44d54a0a-61ea-5130-8ca6-8c5ce6e5f0ec | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
3d7e87a6-45ae-5887-8868-094966f1902e | note | Frequency - One test for every 10,000m³ of source material
b57609a6-0b67-5755-913f-fc34d5e36b11 | note | Responsible Person - Quality Controller
17e63ac3-d8b3-5995-811d-0f38c6a46c15 | note | Verifying Document - Test Report
1cc14d1a-ee2e-51ea-a039-b2a426ac4e0f | note | Conduct - Sp or C or S
2554d563-6555-5297-9596-f017a2b2663c | note | Produce Record - Sp or S
5e1c427d-2325-5162-9017-74eb8cdb62fb | note | Approval - E
fff9176d-4241-53f6-9d66-6e438ae810c2 | note | Hold Point Y/N - Y
b8772c7d-daaf-51e1-ad5c-7b1e13617d64 | signoff | HOLD POINT
cc586658-6d23-5c2e-9750-1928dfcd027c | checkpoint | Materials: M/4 AP40 Material - Source Property Test (2)
54d2b37b-e4e3-53b5-9968-b934ff32fc34 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
bb13939d-4625-5cc2-bd68-a48756471aa3 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
6e3dbb50-c89a-58d2-bd08-0d0c0eefabca | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
dde55130-8c1f-5318-a8e2-956c3a455164 | note | Frequency - One test for every 10,000m³ of source material
e3dd173a-676a-56f6-a942-18dc42fb7ba2 | note | Responsible Person - Quality Controller
7f73f957-cf63-5ff1-805e-eef020e24f7b | note | Verifying Document - Test Report
7d0964d0-9683-5d07-ba3a-466e6ccbb2e1 | note | Conduct - Sp or C or S
fe2a5db0-aeca-5724-bf97-adc55518035c | note | Produce Record - Sp or S
08ca98b8-ab08-5505-8e00-32d19d0e9b14 | note | Approval - E
73f9467c-17cb-55ba-96d8-58eee4562e47 | note | Hold Point Y/N - Y
02481679-3f4e-5794-81b2-82c6dd191645 | signoff | HOLD POINT
c32e461e-12a1-5395-bf1c-ced115580aad | checkpoint | Materials: M/4 AP40 Material - Source Property Test (3)
a1f422a1-fff5-532c-b769-6503b8a84234 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
4b06b43b-e26d-56fa-89c2-8f86fc303818 | note | Acceptance Criteria - Soaked CBR ≥ 80%
3d5ff4de-2b9a-5701-bdf1-1f4c5a343b71 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
964afe30-d5d8-52ba-a7a0-e9ad9b414e83 | note | Frequency - One test for every 10,000m³ of source material
414bcd5a-68ec-537d-a3b6-2c8a22fb56e8 | note | Responsible Person - Quality Controller
a5c35018-00d9-5154-9f9d-16df26a03de4 | note | Verifying Document - Test Report
31d7b9ea-6065-5211-8604-7ce586c41cc5 | note | Conduct - Sp or C or S
8d816ea2-02ac-5f04-a0f6-f70daa86e93c | note | Produce Record - Sp or S
9726889a-0164-5299-88f8-c4e299f598b7 | note | Approval - E
7ba4a9ff-bd47-588f-87a8-4014bb0a002d | note | Hold Point Y/N - Y
b7864b7e-6209-5faa-a2b1-9beb40da9e0b | signoff | HOLD POINT
e3ac61e6-b75a-5cf5-b8d2-f7d2dffa71f7 | checkpoint | Materials: M/4 AP40 Material - Production Property Test (1)
a4257eed-6730-5705-a20d-c1bf02fd59e9 | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
3c16df60-e047-5440-a738-c696c2ee905a | note | Acceptance Criteria - Sand Equivalent ≥40; or
9526a9d4-bbc0-59bd-b21f-c0e7101c40cb | note | ○ Clay Index ≤3; or
37589e75-9104-59b6-b08b-b869a2dc67a3 | note | ○ Plasticity Index ≤5
3674beb5-0307-50cd-a1c1-925af08450e0 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
2b5c9c34-5b1c-571c-ad44-8b9aa3f79484 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
2072d4e4-5456-58a0-9e9d-ebd309649229 | note | Responsible Person - Quality Controller
1a829fe4-45b3-5761-9600-954b6c522cbc | note | Verifying Document - Test Report
ea6c418e-cb83-5b63-bd73-558274ebf95a | note | Conduct - Sp or C or S
e5722760-b008-5f1b-88c4-600ac8d23595 | note | Produce Record - Sp or S
de7a7e1e-a6ad-51c3-bd29-dcf16cf14786 | note | Approval - E
17194070-7ccc-55a8-a8dc-4f9c355c5f88 | note | Hold Point Y/N - Y
233fa51c-1731-5dfd-b0b0-a656c9465639 | signoff | HOLD POINT
6a21d0bd-ed4a-5600-8a81-32ed4cde52d2 | checkpoint | Materials: M/4 AP40 Material - Production Property Test (2)
9b16cea5-f8f7-50ae-a251-2e048650123d | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
5b8060b2-a7a5-5a3d-a007-0e11b195e2a4 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
6a21fb54-a9c0-5574-a1c5-983abf282423 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
66b1f1d5-ae09-5ecb-9e1f-88dc9f334929 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
f5d96dd0-a97f-51ef-9fd1-2575dc792b91 | note | Responsible Person - Quality Controller
f5614fbf-6774-5497-87b9-3a0474f91c45 | note | Verifying Document - Test Report
486198e6-8d9a-5faa-b831-ca09f792fc94 | note | Conduct - Sp or C or S
92569f9d-d452-51cd-ba76-587c2e1362d2 | note | Produce Record - Sp or S
64070725-42cf-53bb-ba91-02723dd1e344 | note | Approval - E
8eddd153-5c52-50fd-98ed-058e7b3e5edd | note | Hold Point Y/N - Y
9bae7e34-4a53-562e-8f24-fd6c4c3263ff | signoff | HOLD POINT
753f4278-94da-502a-9402-be5372b24e17 | checkpoint | Materials: M/4 AP40 Material - Production Property Test (3)
c9719d15-8023-5f55-9c6f-7635280273ef | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
7218e9a3-1212-55ef-b74f-761a58e810d9 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
d741a5ec-e336-578d-8d52-8446fd64e587 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
4d867506-9b93-58e8-9be6-4fe704a4e5da | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
64e50670-0ee8-548e-ab68-f6f586d91b24 | note | Responsible Person - Quality Controller
eb7446ee-55b2-5d13-887e-ee9c5a865fc3 | note | Verifying Document - Test Report
39b04a55-0569-5d8c-b413-037a7b71e60d | note | Conduct - Sp or C or S
cba76b6f-77d3-5bd9-8f6e-5f1b0217ed80 | note | Produce Record - Sp or S
56d18b99-ca6e-51bb-be5e-0294c3036fdf | note | Approval - E
891ae25b-b42b-569a-b3fc-665262f514d4 | note | Hold Point Y/N - Y
191cecde-6fc6-5d8e-a0f7-f2637dca35e5 | signoff | HOLD POINT
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
820d4028-e102-5695-be71-10606bb86b29 | note | Controlling Documents - TNZ F7 Specification
b9b2aba9-2cbd-59f3-a5e1-a2ee5099f76e | note | Acceptance Criteria - Details on Docket
8011eb91-d823-54cf-afbe-31f0b63dbaed | note | Method - Visual inspection
5629cc77-c65a-513d-9a27-f6adcde49df3 | note | Frequency - Per Delivery
a978bd38-07a8-598b-b281-7b4140cfc38d | note | Responsible Person - Quality Controller
c778af35-a269-5d1f-a81f-bcff36a3d7f2 | note | Verifying Document - MDS
78669afc-0724-53fa-b622-dc09a6e2a368 | note | Conduct - Sp or S
597f7e88-bc3d-5de3-a395-6d185274d80b | note | Produce Record - Sp or S
61baae56-366a-5f81-a69b-056034f237e8 | note | Approval - C
ab002ad8-6261-5fdc-8b7a-1e3b673bf647 | note | Witness Point Y/N - Y
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
3cbcad33-916c-583b-8548-b5e09634e85a | checkpoint | Production Testing of stabilised material - OMC/MDD
86e35c9c-8833-5b1b-9919-d780ff534ce1 | note | Controlling Documents - TNZ B/2 section 7.5
de3b1107-038d-5249-9bba-0b1b779b6c14 | note | Acceptance Criteria - To obtain OMC & MDD
561b918f-16fa-5197-93f1-806ac6484c1b | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
36363fac-0192-5582-a625-8ff5e994eda2 | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
4083ff2e-0bd1-505e-9b70-bcb438e5996f | note | Responsible Person - Quality Controller
474a453a-5daa-51ab-986a-58e7f90c1445 | note | Verifying Document - Test report
e13be6ee-ec17-539b-9509-5f0f1cc6efc0 | note | Conduct - S or C
5f3d40a3-df8a-5916-9c6c-38e9b2519a81 | note | Witness - C
563bc889-4276-5928-be45-e976ddf6441d | note | Produce Record - S or C
c3395103-4f82-5b4e-9694-66015aaf05c1 | note | Approval - C
069fc8bd-c825-5458-8f33-32074ed0d894 | note | Witness Point Y/N - Y
db166df1-f07e-5e98-a6bd-e46d84f52c3e | checkpoint | Production Testing of stabilised material - Solid Density
6da4f5b1-94f3-5459-a666-89f3b35e9ead | note | Controlling Documents - TNZ B/2 section 7.5
a1f0fa00-6bc9-5c46-8eb1-fe74bf2413d9 | note | Acceptance Criteria - For info. and use in MDD calculation
6145eef8-98cc-566e-8f70-c443da3ce0d7 | note | Method - NZS 4407; test 3.7.1
ac0542df-be25-5967-9e73-d19edbc54f3b | note | Frequency - Once on commencement and if any materials change
38c4b37c-9f15-524f-bcc4-ed660ecd0094 | note | Responsible Person - Quality Controller
38fe1bc4-588a-5896-be02-14fc07a5413e | note | Verifying Document - Test report
2662f7a6-9185-5ee5-bf86-5bdaff602e6a | note | Conduct - S or C
5d2e8007-2022-56ef-a3d8-17aef2bbf8ea | note | Witness - C
01cd8c91-90a4-59f9-bb9f-350ea1837fe9 | note | Produce Record - S or C
53c9eb39-8c1e-5d16-b7da-ab529c66eddc | note | Approval - C
652047d9-cce1-5958-887c-fdbb8255b70a | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
4751b568-937b-5e72-8bf9-cf5565f1cc3e | note | Controlling Documents - Reference from Project Drawings
6330c2b1-6613-54e8-a6e1-11459c874053 | note | Method - Survey/Mobile Roads, Marks with Dazzle
5aecd324-4fb2-5e79-9f93-2475277ab4ca | note | Frequency - Chainages for every different pavement sections
9a5ba943-de07-50fa-8d8c-e2a8c2b201dc | note | Responsible Person - Subcontractor/ Engineer
3e5b10e0-f547-53a6-8f88-9aa86a4a1f44 | note | Verifying Document - Construction drawings
df3df3bb-97a1-5627-87bd-a9fff8ee1a63 | note | Conduct - S or C
b2ebfc0c-a675-5004-b76b-394c3c9bd844 | note | Witness - C
0a696190-7c75-5550-9c98-40aa68a3dee1 | note | Produce Record - S or C
b32d809b-3c2e-519e-ac83-6dd0bd72efdf | note | Approval - C
c06df1a8-1f76-59c7-8c7c-6c0aa99db9be | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
4225f97f-ec78-5760-8783-cdfe065f11f1 | note | Controlling Documents - Site specifics to be confirmed
c5393c9e-8037-5c4f-a367-2c505452e060 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
625cf04c-c31d-53c9-a1b5-b5fa1aa67dd5 | note | Method - Scala Penetrometer on Excavation Floor
2f21b74b-f899-5228-8f51-13a84bb496bc | note | Frequency - As required
1b6b2637-3310-593a-ac58-d6cf6b5afe28 | note | Responsible Person - Quality Controller
40839f2e-e6e9-5ff9-aeda-67f170b80e66 | note | Verifying Document - Agreed treatment plan
8d9d5a55-5b96-5e7a-9406-05cdaa83a71c | note | Conduct - S
6b4ef0f9-2ade-50d6-8f07-54cf869c6331 | note | Witness - C
80b3419a-54c5-5806-9d5a-1fb8dfb9159e | note | Produce Record - S
d38aff68-fd05-5da1-b206-6958ba82c449 | note | Approval - E
b0bba800-a2b8-5ef3-810d-d4889781b0ee | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
cda9d0c9-875e-5b57-82c8-8f3b4d93864f | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
4a9f5ea6-4bcf-5aa3-8796-9dbbff0f4dc6 | note | Acceptance Criteria - 340mm deep
b186d5ed-eb27-5a47-9ea5-f2b9ce9765a4 | note | Method - Visual inspection
88f79be1-c6e0-5c01-a74d-4c5b36e32d39 | note | Frequency - As required
f7ceedf1-4e38-5ae3-b354-7e4b8e05f247 | note | Responsible Person - Quality Controller
e060d3c0-0218-56ea-a320-7d371559b1b9 | note | Verifying Document - Dig out site records/ Asbuilt
a2ad8e53-e35a-53db-8b6c-db1f9fa7c07a | note | Conduct - S
4bc8dda8-d1c5-51ce-abae-187db7b905fd | note | Witness - C
e354fd31-31cb-5229-b7fb-7d838d4db0eb | note | Produce Record - S
889f5f52-b7bc-56af-aeff-9dffffc957b2 | note | Approval - C
91ffb680-27ec-5f74-8f79-33afb53a2cc7 | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
9ba09b5b-7f31-5cdb-a6af-776604997429 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
8c02fa1c-b3b9-590a-b38a-022804f5d497 | note | Acceptance Criteria - Scala > 3 blows per 100mm or Proof roll <5mm
d58da7f2-fe41-5f07-9259-441870020187 | note | Method - Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful
98e3215c-7824-5290-81a6-d57e420758ac | note | Frequency - As required depending on size of digout
ffd9ca68-74d1-56ac-a5c8-f81c7ad6ada1 | note | Responsible Person - Quality Controller
1e5875c5-cdb0-5ae5-a5c8-b653067c22ca | note | Verifying Document - Test report
235e8049-691e-58bd-88e3-75327bce89d6 | note | Conduct - S/C
16930928-3066-5c68-b156-2a1ab9dce2b6 | note | Witness - C
251f3383-aa21-56fa-b394-c084abd95990 | note | Produce Record - S/C
5d280359-c5b3-5116-a5a6-dc3e1029c96b | note | Approval - E
c37a761a-4d2d-5e01-8142-8f9010959e6e | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
27be2e2c-6946-5445-a460-e4386097ec02 | note | Controlling Documents - TNZ F7 Specification
d91430cc-b00a-5793-92a1-1cd512dac3cd | note | Acceptance Criteria - Meet TNZ F7 Spec.
25ccc0ad-935c-5495-937e-16db8039967c | note | Method - Visual inspection
42c8e59e-c3da-5c7a-a270-1d37bd2d982a | note | Frequency - Per Delivery
daa965ea-24c6-5b15-adf7-18dde9253952 | note | Responsible Person - Quality Controller
ab5f8f00-8751-55d3-a5ef-770c8eb79c4e | note | Verifying Document - Certificate of conformance
5d22e88d-1864-50cf-8ff2-4469f3986e52 | note | Conduct - Sp or S
fcbff4e1-d687-555a-b580-b08ea33abbf3 | note | Produce Record - C
3fb2e57b-0f98-5dc5-927d-3540e9189bcc | note | Approval - C
3fd5f21e-55cd-569a-a6cb-a2726125c3ac | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
70581528-cac6-5ab6-9628-6e822be7198f | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
12a371af-f99c-58e5-9541-adb565d364b1 | note | Acceptance Criteria - Clegg value > 45
1f53fe47-b770-5387-99ff-15219fce2904 | note | Method - Clegg Test
55567bcb-ee69-56cf-a231-e955602dd11a | note | Frequency - Min. 2 per digout
e00753fd-e98f-5b1c-ac7c-e18e522e8fc1 | note | Responsible Person - Quality Controller
2355b33a-d3f6-589e-bda4-9dd9a7f6b361 | note | Verifying Document - Test report
21062626-1e2e-54d9-a1da-76d920897959 | note | Conduct - S/C
48135821-0165-5918-ab1f-bf70b46b452c | note | Witness - C
abb7fe3c-a628-5787-b2ee-d7b6e327faf5 | note | Produce Record - S/C
45794d40-63ca-55ec-b560-c39a31aa37ba | note | Approval - E
acc52ab2-e62a-5e72-9503-63ac07680770 | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
c687b48e-2058-590b-b2a6-8c3d88a00a27 | checkpoint | Place M/4 AP40 Material
e8177fcc-4f17-54ef-b265-e6bbda8373c5 | note | Controlling Documents - TNZ B/2 (section 7.2)
00671932-8b7c-579b-9a98-21491c5c3240 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
daf28cc3-192c-57d0-8b0a-f2ea1003b2fb | note | Method - Visual Inspection
d0c4227a-b6dd-52cc-b68e-2563c9c9d21e | note | Frequency - On completion of placement
264646e5-2e88-5aaf-8751-a53b75fcc8b0 | note | Responsible Person - Quality Controller
2aedd13e-a795-5a34-9808-b166f27722ef | note | Verifying Document - Photographs and Daily Site Record
e4114034-df9a-5fed-84f1-d4b9977cdc41 | note | Conduct - S or C
c9e781c3-de6c-5d36-8aca-655886ed3474 | note | Produce Record - S or C
9cf1dcd3-a114-5faa-813e-ddc9bc87ac98 | note | Approval - C
a37ba63c-dde4-5831-9d65-c80a3755c2e3 | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
c71aaae6-9f6e-57aa-a806-7fd04652bcc9 | note | Controlling Documents - TNZ B/2 (section 7.5)
f03c44bc-e0a6-5702-83b4-606d43eefa5b | note | Acceptance Criteria - 90-100% OWC
9eb24201-a6ed-55f3-af63-c80ce79f91c3 | note | Method - Nuclear Densometer Testing prior to Stabilisation
49461d92-0223-5658-9ff5-a1e7dcf29967 | note | Frequency - ≥1 per 1000m² lot
9f52d3b9-a9fc-5f39-a32c-9f18892d0870 | note | Responsible Person - Quality Controller
8331feb3-f56e-5ef8-8c92-26a61fd7b4fd | note | Verifying Document - NDM Record
060d18af-ae79-54f1-962b-49403eaa060e | note | Conduct - S or C
83aa9f8a-dd92-57d0-9f1f-79719874a702 | note | Produce Record - S
aad3f374-b2eb-5c8d-be90-57e2adc03d11 | note | Approval - S or C
41fa9f61-d04a-519f-bd89-f0441a8a67b1 | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
e740e9d6-7cd9-5a60-8cb4-3d837e5aa1a8 | note | Controlling Documents - Compaction (7.6) - TNZ B/2
1db036c6-bf11-593a-99a5-4bb6d156ce02 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
f4b5f40f-246c-5c16-8407-268096caac25 | note | Method - Nuclear Densometer Testing
952a02a9-051b-537e-8b52-0921343c3085 | note | Frequency - ≥ 5 tests per 1000m² lot
7810beeb-28b9-5192-9ad4-aa68818e729f | note | Responsible Person - Quality Controller
e9635f31-e173-5377-9b45-2e466511ad00 | note | Verifying Document - NDM Record
cd42557e-437b-50c7-98ef-c6f22ff118b4 | note | Conduct - S or C
ae798330-194e-545c-b4d4-3d61c5a304a3 | note | Produce Record - S or C
73fe9cd5-cd35-510e-9f0f-6492898ed45d | note | Approval - E
c8eab903-8042-5ef5-aaca-73f0183c9681 | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
3067e9ed-fa8b-51f3-993e-35172684c019 | note | Controlling Documents - Compaction (7.7) - TNZ B/2
b5439748-9533-53de-ad3d-18b9c6d0554a | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
d1a53a77-a25e-557a-b07c-9b5da7560025 | note | Method - 3m Straight Edge
87e48934-2687-5486-9553-20e54e4d5371 | note | Frequency - during construction and prior to seal
bd58b950-68c9-59ae-81a5-7fcc87343262 | note | Responsible Person - Supervisor
9b922fee-0b56-5a4a-bc01-c36856f75145 | note | Verifying Document - Photographs
2129a62a-7587-5a3c-b975-ab207b97aa27 | note | Conduct - S or C
d3255fc3-fa89-5338-b8b2-adbda07af1c1 | note | Witness - C and E
4fa529d9-579d-5a72-984c-838b065ce6ce | note | Produce Record - S or C
82dceb66-885c-50e1-a6c0-379e3969e33a | note | Approval - E
25eb6179-dd53-553d-acc7-d20fd999877b | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
f87d9603-14b5-51dd-b179-b16d6aca48a7 | note | Controlling Documents - Compaction (5.1) - TNZ B/2
4caf3b41-0a55-59d6-8096-b855e20d48e8 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
6c099697-6f55-52dd-b0b5-d3668fe43b01 | note | Method - 3m straight edge or Survey Asbuilt
4690121f-b5cb-56e3-a014-d8422ae9d48d | note | Frequency - during construction and prior to seal
3c83273f-0201-54d7-b51c-c24f9295787d | note | Responsible Person - Supervisor
94e68260-facc-5430-87cc-89f86ddcad08 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
62ea1d5e-c25f-5c46-a2ea-69fb3aa8bb31 | note | Conduct - S or C
18200ba7-507e-5310-8b5d-3452596f8b68 | note | Witness - C and E
a1662677-4ab0-5167-b410-0ddbf36b5cb9 | note | Produce Record - S or C
5b3a5280-f456-5cd1-86cd-9e172ec5dce4 | note | Approval - E
d8937afb-f94b-5e3c-82fc-65cc4322570d | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
1288fab3-57d2-5087-9b8e-ed29c0a57b43 | note | Controlling Documents - Pre-sealing requirements (12) - TNZ B/2 Notes: 2005
59d48e9f-ed74-5688-8c75-cb69df479030 | note | Acceptance Criteria - ≤80%, however 65% is ideal
7ae46e6b-7e6f-529e-8474-7338238cace3 | note | Method - Nuclear Densometer Testing
0f0001ad-cb7d-562e-a33f-c7e3a5fc11ad | note | Frequency - ≥5 tests per 1000m² lot
67bd7630-2294-572e-bea3-dcfba0693fd1 | note | Responsible Person - Quality Controller
24559e9b-e672-5b68-b6a4-d44c0598a191 | note | Verifying Document - NDM Record
e6ea7809-d41c-50ef-b59b-1eb13c26d559 | note | Conduct - S or C
b77c45de-d7c2-5882-93e9-96a485b63984 | note | Witness - C and E
0c96eeb9-a720-58ea-b58f-f86b6b8d4e86 | note | Produce Record - S or C
83fa158d-de6f-5f1d-afdb-d1167e8d032b | note | Approval - E
78c14a25-7724-58cd-ba22-2e3a0fc7d908 | note | Witness Point Y/N - Y
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
ec4cd5f1-4a1c-5373-8fd8-b940524cdcf9 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
5b4a48f8-84ba-5399-90fa-b359a42edb02 | note | Acceptance Criteria - Engineer Approval
19cb3b91-cec3-5fb2-8c32-43502075b011 | note | Method - Visual Inspection
90fa7d0f-eedc-5f09-9c8b-b462d09528e7 | note | Frequency - ≤2 months of 1st Coat Seal
7c6344ef-243d-5b15-a624-7a335ea63ccd | note | Responsible Person - Quality Controller/ Contract Manager
5a26ea84-56c5-58e7-a2ca-fec5941d6bac | note | Verifying Document - Signed Report
1153c0e1-3997-57ac-9f69-d48cdff77eb3 | note | Conduct - C
7291ae1b-f681-5e5d-8864-c52bd8628204 | note | Witness - C, S and E
31a48b0f-e4c2-5503-8d19-b215cf88b9e5 | note | Produce Record - C
a5c57208-722d-5700-aef8-cc893dedfd4e | note | Approval - E
a02c2914-de6c-5c21-a279-d81217f68456 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
59b973bb-257f-5414-be7b-972c58cc4142 | checklist | ITP - Pavement Rehab - SH 34 - Lambert Road Intersection | itp | ITP - Pavement Rehab - SH 34 - Lambert Road Intersection
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
09dfa698-6b7f-519e-b940-013fd716a19e | checkpoint | Design - Geometric Design
7e9f87a8-94bc-5acf-a0c0-d20a47608142 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
7e132571-2b6e-5291-a561-df8eb7f39b2f | note | Acceptance Criteria - Principal Approval
63e0a901-2416-5119-a0d7-820bcba57d6f | note | Method - Contractor and Principal peer review
c989254c-1d78-593e-a556-80014680f8b9 | note | Frequency - per design revision
d3aa513e-1361-5d0a-b750-1f971ab198ba | note | Conduct - C or S
a91f83f3-b4b9-5fbb-9983-1f6b65b7fa7b | note | Produce Record - C
107097d5-7263-5e84-9d31-1860a5cc707b | note | Approval - E
40afcd9c-3c3b-5ccf-9905-471f4aaf838d | note | Hold Point Y/N - Y
734b8921-df80-5868-90e2-320abcb6aec9 | signoff | HOLD POINT
fc457da0-71e7-5429-a676-cfa9f8ad8762 | checkpoint | Design - Pavement Treatment Design
fc20fc9e-49e7-5d6c-b622-ea1ba68a4efd | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
25f2bfcb-4ac6-5dec-b3f8-cae32e610681 | note | Acceptance Criteria - Principal Approval
97114f4b-5db7-53c2-9f6e-fe12f501deb7 | note | Method - Contractor and Principal peer review
9d1943f1-9d37-573c-92ff-91e4673f1a5a | note | Frequency - per design
ba0a46d5-b307-5b81-ad15-4f9f4da7eab3 | note | Verifying Document - Pavement Rehabilitation Design Report
8291b6ef-7638-596b-ad7a-a7c6c6f0ca87 | note | Conduct - C or S
2b836d15-8ea6-57d6-b652-e4c394627b41 | note | Produce Record - C
36ea5ee5-5c07-52e1-8387-6a3bd6b65931 | note | Approval - E
881a0601-b159-5153-9ea7-85515d973379 | note | Hold Point Y/N - Y
f7622f1f-ef56-5ab3-b6af-8b3b9e5d5f72 | signoff | HOLD POINT
36362436-b1e4-5e95-af81-437ff9bbd938 | checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
68cc8748-d726-5eda-a2a5-0449879df56f | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
473141e8-1c44-54e6-9da2-a96492fb8758 | note | Verifying Document - Sampling Worksheet
a2af7a35-caef-5ec8-b769-58ed646f2939 | note | Conduct - C or S
5eaed97b-ca45-525e-8029-f9d914448cc7 | note | Approval - S
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
16f27f1e-b147-5176-869a-77b95dfad506 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
8bce6a91-9e6d-5bd8-a5bf-4bed706981bf | note | Acceptance Criteria - Soaked CBR ≥ 40
f4c0363d-5c5c-5bd5-b2cf-bf2c0489e11c | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
097b6dc9-8319-5124-b00a-eb531cffbcf8 | note | Responsible Person - Supervisor
a07023f2-4e3d-5710-9457-3632c07222ac | note | Verifying Document - Test Report
c354bbe7-cef3-5709-a8b5-1ae20a5a917a | note | Conduct - Sp or C or S
6f3cf05e-141c-5e66-ac52-8c591a8e290a | note | Produce Record - Sp or S
cc7a8adf-f9ff-5148-a2a4-93bc95078452 | note | Approval - E
cac2d247-62ce-5528-8af3-db5eda9a3f9b | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
ae7e2d83-e996-5777-8251-1ac263229947 | checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
541276eb-96ab-5ec7-84db-bf603485f2fb | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
79082c6e-a663-58cc-b5d3-484cdc501d29 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
0e2bf848-aaec-5ed2-9ae8-0ef07486796f | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
325cf7ed-d2ac-5eaa-922b-6baafb840824 | note | Responsible Person - Supervisor
311b084c-c40b-5d36-9264-a3c4431503ee | note | Verifying Document - Test Report
ca335865-6feb-50db-a178-9defa987f17f | note | Conduct - Sp or C or S
ff8f18f7-76e0-5aca-ac0f-af128b1539a3 | note | Produce Record - Sp or S
4ecfca9d-b7f1-5f91-ac4c-65043237dc5f | note | Approval - E
cd868cf7-9534-5ba1-8c28-2828d100e1d9 | note | Hold Point Y/N - Y
59b9d644-63f9-5af7-bf31-75c1a6bf1a10 | signoff | HOLD POINT
282d13fa-6a2e-5570-b955-78f6c0062fd3 | checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
d3362af0-a9bd-59c4-826f-2eaa4b776304 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
0fbb50fe-f624-545d-83a7-c2c026b4c469 | note | Verifying Document - Sampling Worksheet
19b6d86b-bdd4-5d23-8c3b-38570c4103e5 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
de4900ee-9328-50db-a33c-e59081eafadc | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
308ebc34-b77d-5a6f-8f4f-8ca39e926fed | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
0a653710-ed81-5136-b52d-6bbce4137bb3 | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
8adffc6c-d285-5b1e-946e-3d6933e032b4 | note | Frequency - One test for every 10,000m³ of source material
938d2303-08b6-572d-92df-0fedf14cec51 | note | Responsible Person - Quality Controller
5c2fd9af-083b-59b1-ab0a-37c987fdc4e7 | note | Verifying Document - Test Report
fa14f2ae-46fe-50cd-a06e-b8062b825d66 | note | Conduct - Sp or C or S
0bbeef23-f463-5312-9570-51e14f6bf306 | note | Produce Record - Sp or S
b3f8aeef-2680-533e-8feb-c847468d6543 | note | Approval - E
4cdaac33-40cc-5140-b814-1e0c9deedbb2 | note | Hold Point Y/N - Y
2bce147b-57e0-5df2-aa19-d3114e0f900e | signoff | HOLD POINT
771bbcd5-e52e-5af5-9fc3-2a5ff6956b1d | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
3f7f9716-4f5e-5e03-bc2f-404f0948daae | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
b654e970-b68c-5ae7-a647-4ee38e54fbec | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
054a79a2-d600-5a47-956d-01c48dcae9f5 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
4c3864b7-2614-5b47-881a-bcf23d9c523d | note | Frequency - One test for every 10,000m³ of source material
39d03aa1-7053-5e25-806d-66b5282ffaf6 | note | Responsible Person - Quality Controller
eda78439-b911-57b2-815f-4c8dd6beb802 | note | Verifying Document - Test Report
b04d5b7c-eb29-5bf7-8dbd-ef0a089f52a6 | note | Conduct - Sp or C or S
dfcf85f4-fc0f-5a95-96b0-cc6cd120aedd | note | Produce Record - Sp or S
c7725d4a-2f83-57c0-a264-29e421743caa | note | Approval - E
3a85ed1e-d9cf-5217-8bcc-fc2fd7106382 | note | Hold Point Y/N - Y
5de343b7-b3e0-59f2-8f5e-085d4a8c0fdc | signoff | HOLD POINT
113f3833-1e06-55b9-9978-c5d36d530658 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
20b03a0f-de52-5e9c-9b63-4086538345eb | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
a59ddddc-ba61-528c-b325-d628d3612c09 | note | Acceptance Criteria - Soaked CBR ≥ 80%
a90130d4-837b-5ca1-86d7-798b4213c932 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
5e00a250-583b-50b4-a77e-35ab4f538cd0 | note | Frequency - One test for every 10,000m³ of source material
b4c94fc9-8f97-59c0-8cc8-92da45b418c4 | note | Responsible Person - Quality Controller
268d4167-7b03-5b2d-807d-be413889fc3a | note | Verifying Document - Test Report
faa56d41-f50e-567a-a74a-cb7893c4fed6 | note | Conduct - Sp or C or S
0baf64dd-58c9-57e8-a9f6-e4a18f2d98be | note | Produce Record - Sp or S
5ec41619-0e1c-5c31-a4bf-3972b2a3aa03 | note | Approval - E
75e80846-c422-5ba4-91f2-3b2e78c8e5f8 | note | Hold Point Y/N - Y
40c2302f-cce5-5c54-87be-1069cdfc7929 | signoff | HOLD POINT
976c9ab2-336e-5bd7-8941-60563e8cfc82 | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
315eff8a-9f4a-5ff4-8393-baf10a77cc7d | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
e00f2472-e802-5dde-aeb6-7d4da3e90333 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
4dd023ae-051d-5b6b-a947-e4bff4c11fe2 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
7f0b7d69-7d0e-5bd3-a589-0847a4d3e1c9 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
47fb4b00-0eb1-58fc-9789-b25cca7dea2a | note | Responsible Person - Quality Controller
7f308430-bc11-5821-a0c4-4323d4c17fdb | note | Verifying Document - Test Report
39aa19c6-a82e-5ca9-aa84-329250b166e9 | note | Conduct - Sp or C or S
330daf91-fcef-561d-8d98-931c208f2eef | note | Produce Record - Sp or S
10d461b0-98d2-5b26-ba75-4eec0eb2adc6 | note | Approval - E
afa7743f-cf8c-5da7-a465-aee02fa52431 | note | Hold Point Y/N - Y
8c291f12-658c-5f73-81d4-ac64eaf7be26 | signoff | HOLD POINT
21f389de-1666-5508-9d06-5a4f024a4cbe | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
0a4d5aba-307f-5918-9c97-af743738dcc1 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
a88ece8f-0c75-5977-81e9-2bf03a9684ad | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
c59546c4-9275-5d86-90ec-879ae2d9b410 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
7e9e3eaa-e7ff-5521-b474-fd826c2b9f33 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
3ae6ac93-561d-52c3-9a15-c020a6afdcc5 | note | Responsible Person - Quality Controller
d9c95df3-90ad-52be-b839-25f91282f6dc | note | Verifying Document - Test Report
f5218752-15c8-52a0-ac92-6eaca27e3407 | note | Conduct - Sp or C or S
cdcf63cd-dbdd-57e3-b15d-adc466b09bd6 | note | Produce Record - Sp or S
0fe67efe-40d1-5ca4-9fcd-146c58e6a32c | note | Approval - E
44ff1af7-f11e-5227-988e-280ada880abc | note | Hold Point Y/N - Y
f50c0087-ac9f-533c-9dad-f1906513e000 | signoff | HOLD POINT
66a6116e-307f-5697-aa3e-d266fb4bd96f | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
dc087d30-5f4d-5b67-b91d-463404fde4e5 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
03047de9-3b60-5536-87ee-25aa5d7d1f4b | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
c37ebaa0-caa0-578c-a01b-6e8de5bb3fb2 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
e39f51ec-ab62-55de-a1ef-b46274cdffa9 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
ddc8e3e5-49c1-5471-9c82-12d1ea835882 | note | Responsible Person - Quality Controller
6dc032d8-224c-5766-8592-b7b6ad05847b | note | Verifying Document - Test Report
0198f35c-0adc-560b-a4c0-503e970fed6c | note | Conduct - Sp or C or S
fbebc3b5-1dbd-5425-852e-3040635ff641 | note | Produce Record - Sp or S
a81c9031-68a1-5374-8623-77b1a346eb82 | note | Approval - E
678ba8d3-2292-54a9-9ad0-d4a2c4115e5b | note | Hold Point Y/N - Y
7ecc9215-ad8b-5530-b3e7-13982b2273e0 | signoff | HOLD POINT
47f1dbc4-d99e-5833-b152-43ed36e71943 | checkpoint | Materials: Foam Bitumen - Stabilising Agent Selection
08ecae2a-9b4c-54d6-a653-048df90abced | note | Controlling Documents - Foam Bitumen (4.0.0) - TNZ B/5: 2008
4fd16ae9-78b7-5d47-8481-948d699a1fbe | note | Acceptance Criteria - Foamed bitumen shall be produced from 80/100 or 180/200 penetrationgrade, The bitumen shall comply with TNZ M/1 and shall be able to achieve a minimum expansion of 10 times
1d1fe622-5c0f-585e-99c4-c0d24fa04533 | note | Method - Record binder grade. Conform to Specification
d3d6099d-45b5-524a-9ec4-d8a59c244622 | note | Frequency - Per Batch
f6824c8a-25e4-528d-bd3b-4c679077b360 | note | Responsible Person - Quality Controller
9ed952e1-f6c5-5cca-a206-70285be34fe0 | note | Verifying Document - Test Report
3466b5a2-2d04-5767-8949-1b14ae58ea0d | note | Conduct - Sp or S
82b474d1-d566-5e2d-a092-088e79eab49f | note | Produce Record - C
d0fff9dd-d8a5-545b-9064-ddef52eeca98 | note | Approval - E
5acbda05-7190-5095-a47b-7b6a90dd6a6a | note | Hold Point Y/N - Y
8bf5d5de-2f63-522d-88e9-a2b46f8468b1 | signoff | HOLD POINT
853dc2b2-bda9-5d6e-aa05-563f9498a100 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (1)
04c31a12-cf46-5faf-84e1-f0d6622e9857 | note | Controlling Documents - Bitumen (80/100 or 180/200)
7d8c0d40-7d5c-5590-9713-8088ece3e997 | note | Acceptance Criteria - Record binder grade. Conform to Specification
aefb8791-e375-5df0-a472-5a9345411c20 | note | Method - TNZ M/1
330bcfba-4be8-5057-9e95-731420f0180e | note | Frequency - Per Batch
1f612b1c-2f36-58b3-bc3c-089be23ad471 | note | Responsible Person - Quality Controller
26ffddf8-8fb9-5e15-9c4d-e7d46f78464e | note | Verifying Document - Test Report
10a7fafa-7b16-58b9-8cce-77fc04c2f332 | note | Conduct - Sp or S
f6114f59-3146-5bdf-b597-8496572d5afd | note | Witness - C
8cc52dad-729f-54b8-9b0d-2f9e9813106d | note | Produce Record - C
51540bf2-3701-5d76-817f-0c131c7b7348 | note | Witness Point Y/N - Y
3fd6ef94-12cf-5bfb-94de-9acc9543a90b | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (2)
f3d1bff9-512f-571c-9ca5-a308ba4fa7ca | note | Controlling Documents - Foaming Optimisation
9f279e6c-0592-53e1-b9a7-c1b2b3481e46 | note | Acceptance Criteria - Determination of optimum foam water content
ce34a53d-8c8f-509c-8daa-dc92ec551cce | note | Method - NZTA T/19: 2020
6af2188f-d0ad-59df-814c-0f4758eef612 | note | Frequency - Per Batch
0c1ef188-8dd1-54ad-91ab-11f00ee68e89 | note | Responsible Person - Quality Controller
7b04724e-f05d-5303-a5ca-387a6cff214a | note | Verifying Document - Lab report
e214b35e-1819-5bf3-9c20-6b3eff5e22c8 | note | Conduct - Sp or S
42c376bd-f6c4-5954-aa1d-4f91a45beaa2 | note | Witness - C
c756155f-8128-5fa6-a91c-9ad293df67c3 | note | Produce Record - C
4935d704-2906-57ea-8704-ce4b31caffb8 | note | Witness Point Y/N - Y
40bca1a5-6a69-5896-8fda-b91f19179928 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (3)
0da05b20-0812-5daf-866d-86c7f7aecc6c | note | Controlling Documents - Indirect Tensile Strength, ITS
a61b119d-b2b8-550b-9074-deed2b09816c | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa
8c94cebf-82b7-5e54-882c-3c13e04674af | note | ○ Soaked ITS: 150 kPa to 350 kPa
abd2805b-8cbc-5e87-bef2-c33825200011 | note | ○ TSR ≥ 70%
d1bded51-526d-5c99-80e3-cd24db86089e | note | Method - NZTA T/19: 2020
af5a7328-f5f7-550c-9d7d-68fbb1b2b138 | note | Frequency - 1 Optimisation test per aggregate type
6705dde3-1c0c-54d9-812e-1002fd836236 | note | Responsible Person - Quality Controller
bd94ad8d-3e7b-5c93-bb59-323ff9d707fb | note | Verifying Document - IANZ Report
76b73d89-b484-55a9-95f4-69f73e2ea7ca | note | Conduct - Sp or S
5510a9a4-5947-58d3-9415-0c55f5ff9591 | note | Witness - C
4d89af61-99ed-5e9b-9586-8ec87090e490 | note | Produce Record - C
a1c28e9b-a601-5d8d-a629-e360d3fea192 | note | Witness Point Y/N - Y
3cbf8630-db50-56bc-9962-d450a8e22cd1 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (4)
ba7e1fd7-db09-5c1d-875e-643187d82906 | note | Controlling Documents - Unconfined Compresive Strength, UCS
cc3fe082-e5f9-5e82-beff-489df682dca1 | note | Acceptance Criteria - UCS is used to calculate MR(Phase 1) and MR (Phase 2)
ef87a84f-1d1a-5be0-844a-e4ed3b8dc149 | note | Method - NPTG Guideline
8c4bb77d-a5ed-511f-84fe-ac2abb714e39 | note | Frequency - 1 Optimisation test per aggregate type
c9d8a529-fcf4-5f07-9d5d-af027b9846a6 | note | Responsible Person - Quality Controller
a23efd21-8230-5bfd-882d-03436cf98fff | note | Verifying Document - IANZ Report
efd6aedd-fefe-530a-bd76-5a27854aa7d8 | note | Conduct - Sp or S
16054920-8242-5e0c-8e04-4c84b9e2e674 | note | Witness - C
904eb8d9-bb1f-5d97-9cb8-952ed2540647 | note | Produce Record - C
5e05cd4f-a6a4-5be1-be95-bbd39ff3198a | note | Witness Point Y/N - Y
f6cb7864-6500-5312-94e3-70a53d1e9be5 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (5)
136f19c0-5470-5846-ae20-452bdbbeb097 | note | Controlling Documents - Modified Maximum Dry Density
49b33917-a3ad-58e7-a594-83297ba013e3 | note | Acceptance Criteria - To determine target density
7bbdeded-2e0d-5183-b0c1-a6a069ca26c7 | note | Method - NZS 4402.4.1.3
6410d3ac-549e-576d-9f1a-0fe7dc59ffe7 | note | Frequency - At Optimised Binder selection
bdbc6082-7f26-5ffd-b585-9699db44440a | note | Responsible Person - Quality Controller
7b479697-8e2d-5583-9ce7-4f722f04cff4 | note | Verifying Document - IANZ Report
d2365790-7c8f-5fc4-9f02-90b92c8458e8 | note | Conduct - Sp or S
0c366e49-233d-58a7-a056-64021906e2b8 | note | Witness - C
8e522c65-035a-5840-b3d1-57f4fac83179 | note | Produce Record - C
f998bc3d-a3e1-5bf4-9527-1a8eaea027b4 | note | Witness Point Y/N - Y
288f3247-2eba-55d4-ae79-89580bc4bef3 | checkpoint | Materials: Cement - Stabilising Agent Selection
4307e24f-8d59-5965-a8cc-49feae25cff4 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
34fdf84a-bf5e-518d-beb2-f9fc3026c4e1 | note | Acceptance Criteria - GP
75887c3b-91e5-56d6-950d-ba724aeb4351 | note | Method - Visual inspection of supplier docket
7ddc3680-2205-50d0-8a55-f9775dfc4c08 | note | Frequency - per truck load
afbf213c-270a-5c20-b50e-65562fcf2f72 | note | Responsible Person - Quality Controller
e8aa6e33-1f89-59d7-969f-a732477b38c8 | note | Verifying Document - Supplier Docket, Supplier Cert
2771181e-00a6-548d-8e32-1ba7e126e4f2 | note | Conduct - Sp or S
a68e9949-b386-5dd4-a7f1-340af75af711 | note | Produce Record - Sp or S
89f98c04-0c0b-511e-977b-35158adbb7ca | note | Approval - C
b7d964f7-ed54-5eff-9a66-a6166d6f948a | note | Witness Point Y/N - Y
5fe70724-8f32-50a2-8961-1dac348f79c6 | checkpoint | Materials: Water - Water draw for stabilising
0dd5f83e-ff40-59d5-a0ff-39f89f44037a | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
4a52a8a4-61af-5c01-b19a-8d8056f10b02 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
69b5a73b-81b2-5d00-b6e5-6ee3a44279a7 | note | Method - Visual inspection
57acdd2b-8b5d-583a-bac2-74214eb59ba6 | note | Frequency - per truck load
23b33ee4-b741-51d7-b5af-543f97806ffe | note | Responsible Person - Quality Controller
a2feb346-56e0-518a-9ba9-ca31008b9ab6 | note | Verifying Document - Hydrant use form
6acbd682-5df2-5e36-aeb7-15da57109fc4 | note | Conduct - Sp or S
9a707954-061f-599b-b5fd-0b97ed718a00 | note | Produce Record - Sp or S
6d6f5b3f-b587-53fb-b889-0d96f06d715d | note | Approval - C
b3d54d30-799e-5382-92f0-0ec4e8e6705d | note | Witness Point Y/N - Y
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
d2875f17-b13e-55f6-bfb1-b25aec69d8c8 | note | Controlling Documents - TNZ F7 Specification
bced87ad-9aec-579a-b7af-b2c5a79e0e76 | note | Acceptance Criteria - Details on Docket
b4ba9fab-69d4-5a30-a037-bfde5b8ea6ab | note | Method - Visual inspection
15886e82-3dab-59fb-a57e-7fc392039808 | note | Frequency - Per Delivery
3560c7b8-f05c-5e59-947c-dadee2c43bfc | note | Responsible Person - Quality Controller
baedd143-9185-58fa-b83d-5182a2d372d7 | note | Verifying Document - MDS
1f3b8dd1-6091-5480-ba16-8dcc92cdaf0d | note | Conduct - Sp or S
5f528dd0-9f85-5062-a2b4-1969ba67fd89 | note | Produce Record - Sp or S
0dfbf6c4-2d0a-5823-8c08-9140a963b125 | note | Approval - C
bbc4cd26-9021-522d-ab3e-5a09d3e91616 | note | Witness Point Y/N - Y
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
db166df1-f07e-5e98-a6bd-e46d84f52c3e | checkpoint | Production Testing of stabilised material - Solid Density
c056be29-9671-5532-b70e-41bd2e734748 | note | Controlling Documents - TNZ B/5 section 7.7
f341f76e-671d-5689-874f-a958e3755a7e | note | Acceptance Criteria - For info. and use in MDD calculation
3e5df7cc-695b-5050-9d09-49060e78d22c | note | Method - Calculated based on Virgin TNZ M/4 Specific Gravity and Bitumen added
b3c8cf66-76c8-525e-960d-877459a12c1e | note | Frequency - Once on commencement and if any materials chage
b2fb0b26-fed7-5e60-8fe4-084e760d9ccc | note | Responsible Person - Quality Controller
9a7ffa2f-3e37-5859-8c66-0d8fb7a193d4 | note | Verifying Document - Test report
6256295c-4f5f-5ec4-909f-c2acc31b1c19 | note | Conduct - C
94abd920-9e23-5802-96ca-8f56d601be6c | note | Witness - C
53ae57a9-6c17-56f6-85ac-0f752408423d | note | Produce Record - C
85443f2e-279b-5db8-b273-d11935498c79 | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
ca749d66-4a76-565b-b319-325eb08a55b2 | note | Controlling Documents - Reference from Project Drawings
ebcc0787-fca4-5050-a0e6-34cf6414e3df | note | Method - Survey/Mobile Roads, Marks with Dazzle
4d5828f4-1434-5e36-977b-db943d310200 | note | Frequency - Chainages for every different pavement sections
521dc68e-6323-50df-a6c0-0e8ab0020b38 | note | Responsible Person - Subcontractor/ Engineer
e8fde2c7-554b-52e0-8871-7303e3386803 | note | Verifying Document - Construction drawings
e3142c70-1354-55bd-ad1d-4b732e5713a6 | note | Conduct - C
b4216319-f31d-5786-9012-91ff8a482058 | note | Produce Record - C
86577490-d2b7-5576-abe3-8a29fed80c0d | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
9629c1c5-a4d2-5cef-a0f3-0c06f302369b | note | Controlling Documents - Site specifics to be confirmed
7008f290-8cf0-55f4-a35e-016f945e9ea8 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
e07dd3d8-cd45-55d7-94e2-71572a2b4ef0 | note | Method - Scala Penetrometer on Excavation Floor
0f1075b7-1030-5293-b7eb-0d9629f0dffa | note | Frequency - As required
3a211c3d-7d67-5ee3-8f3f-1437f5e5d13e | note | Responsible Person - Quality Controller
4d4efefd-ef64-5b74-b17b-f657c2db4702 | note | Verifying Document - Agreed treatment plan
16215450-5fa8-5788-a110-13d659fd4130 | note | Conduct - S
c9ff72a0-3676-5853-bfa5-9c763d61d3ad | note | Witness - C
aded5c9a-63f1-547c-b9a5-a4d362600843 | note | Produce Record - S
80a57cad-71be-52b5-80d4-013bc5165b6a | note | Approval - E
0c097a63-79e1-5ce5-bae3-7a97364179f1 | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
20b57f11-3a82-5ad1-8595-3f4f77eb880b | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
ff18e67f-1115-5c4c-aada-8a59974ca994 | note | Acceptance Criteria - 250mm deep unless specified
5db06adf-fc6b-5af0-b20c-ef08fc457332 | note | Method - Visual inspection
b0759acc-8734-5341-a991-dc80452d7592 | note | Frequency - As required
d7545eef-322a-5d46-a7a3-9b0f08c8bb38 | note | Responsible Person - Quality Controller
c5be59e5-95cb-585f-85cd-f60d8ab2b12e | note | Verifying Document - Dig out site records/ Asbuilt
f276dbf3-3fdf-529f-8f68-8d2b3a29373d | note | Conduct - S
66551684-aa9d-5d61-a468-30e2dfcfbddf | note | Witness - C
c49b1467-9420-545f-afce-9a498a0c75bc | note | Produce Record - S
7fea9ac8-6be4-52a2-99bb-2da038643f7f | note | Approval - C
171864e9-ab8c-5616-b439-d1aa9bdbc60f | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
c65cad50-7ed0-5aca-8994-79c542f30760 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
78a697c4-7647-5e67-9577-da914ec55de2 | note | Acceptance Criteria - Scala > 3 blows per 100mm
6a4d1adf-4075-51a2-9482-f86a1f422d36 | note | Method - Scala Penetrometer test on base of digout
dfe48948-ce16-561c-8491-cef579434867 | note | Frequency - As required depending on size of digout
8c0935a0-df9c-5a52-9702-d0ed7f148234 | note | Responsible Person - Quality Controller
93d12e35-df77-53fa-be8b-89bfe97f7981 | note | Verifying Document - Test report
0127484c-e5ae-50d9-b4f7-27b7f5d1b556 | note | Conduct - S/C
d82f3ad8-7a21-5336-ad22-8b5e0e81ef0c | note | Witness - C
45d559b3-cec6-5051-890c-1ad5e86a27b6 | note | Produce Record - S/C
f352a8f6-bed3-538b-bc6b-b1a6db0a7307 | note | Approval - E
8fd1ef61-8d32-5d37-a422-58ae7d82728e | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
41e4fcfc-1fc3-5c9c-bd9b-7e0f85aed2f7 | note | Controlling Documents - TNZ F7 Specification
7f265334-7736-5ca8-a5fb-766c305e7cc8 | note | Acceptance Criteria - Meet TNZ F7 Spec.
a82a1b5c-8614-523b-a621-8fb2de2fb9a7 | note | Method - Visual inspection
2eabf8f5-d57f-5594-8a5e-76f594e8ad11 | note | Frequency - Per Delivery
0004141c-7245-52f1-a195-29815f9085ad | note | Responsible Person - Quality Controller
05211498-baf1-5e65-abdd-921b9a03e5bb | note | Verifying Document - Certificate of conformance
156a0c2e-aa74-5654-8181-52252c86a0a0 | note | Conduct - Sp or S
702585db-e0c1-5f88-a5ee-f0377b6def3f | note | Produce Record - C
52c70e9a-9d40-5e7e-b047-30d63b819fcb | note | Approval - C
5bb62b2c-ad72-59b2-8e01-bafa4df9c62b | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
13431db8-89b3-5aaf-8183-9d54a55817bd | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
20db0207-f24d-5d37-bcc2-5cbc78d9640f | note | Acceptance Criteria - Clegg value > 45
21087fb5-e89a-5ab4-a25c-b3129cb3bbb2 | note | Method - Clegg Test
c7b25329-ae3e-5668-a7a5-819911160a5b | note | Frequency - Min. 2 per digout
05fbeaaa-e024-5309-bd23-081d47aefdaa | note | Responsible Person - Quality Controller
de2d4ad6-359e-5db8-9572-32bba64af3f2 | note | Verifying Document - Test report
6e2fcf7b-5659-54cd-b1cc-0c893e5935ce | note | Conduct - S/C
873487e7-db43-5ea8-aa1a-be93616a33f9 | note | Witness - C
cbfba0a6-bd30-513f-a9fb-ee8fd82014b5 | note | Produce Record - S/C
6d504545-82c3-5376-8a0b-89ef0a2adbe7 | note | Approval - E
f093339b-1955-5f86-b330-3a48e8ecc1fa | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
3732d630-8491-5d4a-9f08-4723776e9d88 | checkpoint | Stabilising Depth
2afea585-0ee3-54af-8188-1b39a2f3ccd4 | note | Controlling Documents - Rehab design report
81d94d38-a8ab-5ab0-b38f-13bc36375685 | note | Acceptance Criteria - -5mm + 15mm of design depth
a9b071ac-fb99-5c7b-9a9f-e6d7f815e3cf | note | Method - Depth measurement
05a8d3fe-89e6-5fc9-a192-8e64ed21cc6d | note | Frequency - every 200m
825ac38c-3d2f-5845-b45d-ea254270fb01 | note | Responsible Person - Quality Controller
0d3c3b6f-55ad-5902-9401-af239b69052b | note | Verifying Document - Daily Site Record
84e43414-d3ed-5b23-91d5-4b64cf7d965d | note | Conduct - S
8dad80e4-02c6-508f-b990-3d73d17b3434 | note | Approval - C
cb667f2d-aa01-5f1d-bd60-10d9eb7bdaee | note | Witness Point Y/N - Y
034e3d0a-6899-5057-8f7f-ded21de23dd6 | checkpoint | Visual Inspection post hoe (1)
b7b9f4fa-a025-5316-8a2b-29a011aa48cd | note | Controlling Documents - 6x4 truck fully loaded or similar equivelant
64aeab05-c252-595e-acc4-3bf87f40b90c | note | Acceptance Criteria - No identified movement of the pavement under proof rolling and for subgrade contamination
12ba50ec-70c4-55d8-8ecb-1787fe66b2d6 | note | Method - Visual Inspection
fbf24d6d-29b5-5bb8-a27f-8710330d2607 | note | Frequency - Each Subsection
193aff56-2e23-5ef2-9d4b-e37c922205c0 | note | Responsible Person - Quality Controller
e355e939-1efe-5bf2-9196-a5757e32b277 | note | Verifying Document - Daily Site Record
66f134a8-f31a-5a83-9e47-d309499c2902 | note | Conduct - S
72be6b8d-332d-5a40-a3fb-df2aee2d8d4d | note | Approval - C
13cbd78d-0435-57ed-9479-9bba221f7bd3 | note | Witness Point Y/N - Y
c59243b6-062b-52c8-bd6e-e7959a49d521 | checkpoint | Visual Inspection post hoe (2)
93b19a35-0a5f-5067-a8bd-c099081854f3 | note | Controlling Documents - Particle size to be 50mm or less
fc46f8de-44a0-547c-a68d-6f99b3f60e2f | note | Acceptance Criteria - Materials as described in design report - grading and PI suitable for FBS. No large slabs of existing wearing course or strongly bound base
6490bc93-0540-5d18-9e00-eb9511b255ae | note | Method - Visual Inspection
915d6f11-2827-5462-a11b-3776179cffbd | note | Frequency - Each Subsection
3ba8a735-e242-5036-9ef1-c2caff81d0dd | note | Responsible Person - Quality Controller
9e7dbc79-5efc-5216-95a6-e4025845edea | note | Verifying Document - Daily Site Record
0379113d-45ab-584c-8e20-5aa6f991b92d | note | Conduct - S
c7d37f9d-1113-5cc4-8452-372af9e08306 | note | Approval - C
f1a3a64d-381f-55b9-b510-f567d82053eb | note | Witness Point Y/N - Y
eeb50d65-64ce-572e-8456-9dd1f3e00c42 | checkpoint | Place M/4 AP40 Basecourse Material
21c5bc4c-1fd5-53f2-88cd-13fbfdf41b4b | note | Controlling Documents - TNZ B/5 (section 7)
d681a7df-9266-5172-9a73-cc68df224beb | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
dabd854b-d9e6-55c8-9f32-835ef51689ad | note | Method - Visual Inspection
d6d0db4a-efe1-57d1-aed1-e37a86fe3bfa | note | Frequency - On completion of placement
3641d297-27bf-51cc-bca8-57b62e962874 | note | Responsible Person - Quality Controller
e1b639ed-788d-5a9e-9bd8-b7f4db4fcea9 | note | Verifying Document - Photographs and Daily Site Record
ddd08e19-2c34-588c-8b5e-28b2e9f74e14 | note | Conduct - S
6f868a3e-10b8-5a06-939e-ef94a00d148f | note | Approval - C
441aea24-49cf-5c30-b1d8-2941adb11b8f | note | Witness Point Y/N - Y
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
b9e98a79-fed9-58d4-9aae-f86c64f862e2 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
c5ccda9c-7dd7-5f9c-9166-ed54f84af854 | note | Acceptance Criteria - Between -5mm and +15mm
3997c264-9c2c-53b9-8e58-9fafa70e911f | note | Method - Visual Inspection
746a4398-90a5-54c4-8885-88765221bf70 | note | Frequency - 1 per 20m
479b02ae-19ef-5aa6-94e2-f053b4491eb4 | note | Responsible Person - Supervisor
b767417f-122c-5297-9503-b110bb28881d | note | Verifying Document - String Sheet/Survey Asbuilts
e4e38743-ba4c-5a19-918a-774cff19ef85 | note | Conduct - S
9b8c3db9-f0e5-5c30-bba0-a18e46c48bb1 | note | Produce Record - S
dc4b966d-5de6-5562-a2f7-e55a6845fc53 | note | Approval - E
992793c8-65a0-589d-ad48-4eb6b878f2ea | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
0da23b78-7228-599b-8067-378a03c94e10 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
01ecc6a3-8abf-59c4-b0a5-23d57436ec54 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
b4586af4-4beb-525e-b752-18e664e98399 | note | Method - Visual Inspection
a30b42ff-1885-5b77-a6a1-7b4da30db346 | note | Frequency - 1 per 20m
2a7c9f64-954a-5199-9588-88cf5f74472d | note | Responsible Person - Supervisor
b3b6fe03-82bf-5aa5-9608-974644c0c954 | note | Verifying Document - String Sheet/Survey Asbuilts
8788c31e-7c76-58fb-9a36-844e5de01477 | note | Conduct - S
de2885e3-68e0-57fd-82b5-4b73113211e3 | note | Witness - C
9bccacb3-1a74-596c-8ba0-9ceec09f78dd | note | Produce Record - S
dc641f23-bcd6-5d3d-b14b-aa722370457c | note | Approval - E
4dd8a10c-a42c-5ca9-a168-543cf2c26e9a | note | Witness Point Y/N - Y
0bb40e61-e98e-5b2d-a01e-8a83ca21acf5 | checkpoint | Production and Injection of Foamed Bitumen (1)
0787432c-d66c-52c9-8e29-dffeae1374d6 | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
7a616773-3f8c-57ba-9176-71c191618f93 | note | Acceptance Criteria - Monitor bitumen pressure and bitumen flow on display. ± 5% of specified rate
95d6f043-e9bb-55ff-b9af-a4494b0c6139 | note | Method - Monitor
d1414c7a-65fa-5b48-9e78-90ec7300e969 | note | Frequency - Continous by operator
c39d840b-2cef-56a5-8a87-b6f1fd4df5ff | note | Responsible Person - Quality Controller
8760bc12-7ad0-5ecc-aba8-399399be9c0e | note | Verifying Document - Daily Site Record
34f5413a-fc8d-5469-a0a1-c5b6490c99b0 | note | Conduct - S
97da121a-e680-5fc5-ade7-91c0e0ddd094 | note | Produce Record - S
55ded80b-e530-5320-8417-06468578e793 | note | Approval - E
11129784-930a-5ce9-b0ce-6e5b2dfb1433 | note | Witness Point Y/N - Y
d3212d24-5c9d-503a-9631-79674682244d | checkpoint | Production and Injection of Foamed Bitumen (2)
ad8addd7-8501-59fa-b812-e2fa4bf14483 | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
7750e535-c1f2-5156-b8ba-f212c9051948 | note | Acceptance Criteria - Bitumen Application Rate. ± 3% of specified rate
7cc46d83-0071-5b43-9eb1-b607a2ab9431 | note | Method - Record
8f45a12f-c50d-5079-9706-dde04adc934e | note | Frequency - At the end of each run
4d1a6fd9-91ae-5b08-b183-4276128c50fb | note | Responsible Person - Quality Controller
22f3f945-bbfd-5c69-9f57-6f001b9b2167 | note | Verifying Document - Daily Site Record
43de4560-902c-5556-a67d-e2eb469b2ab4 | note | Conduct - S
ed0c7ff5-3582-59e5-8f24-c0697fa1397a | note | Produce Record - S
9dc73cc0-cee7-5835-8520-4e158f2f98a3 | note | Approval - E
faacd1f3-d649-5346-8a43-3b76027db985 | note | Witness Point Y/N - Y
e3d51234-d1bd-553f-8876-a60f857c3d8c | checkpoint | Production and Injection of Foamed Bitumen (3)
d75a9d2e-2f7c-560a-88d8-7b9904fb21c9 | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
a3fff577-cc8e-5c4b-959d-4e68ec8db213 | note | Acceptance Criteria - Average Bitumen use test per tanker. ± 2.5% of specified rate
ee749fd5-dd55-535e-a5b4-d8bd95d1ec8d | note | Method - Record
fbf9d1bc-e52e-5120-9bb3-fde34576e1f9 | note | Frequency - Reconcile daily bitumen use with Area Stabilised
a6198179-3963-56ba-b5ed-31316c8bf7e8 | note | Responsible Person - Quality Controller
8ff9ec12-f2a1-573f-95c4-8e71db2d0c03 | note | Verifying Document - Daily Site Record
77df7f65-676b-5388-85b2-6d72c3ab0cf9 | note | Conduct - S
4d7b0c6e-c4f4-5661-aceb-bb1fb92ea040 | note | Produce Record - S
7eaebd8c-b623-5e97-b548-d65875d3a5aa | note | Approval - E
36d8b609-22b9-518c-83c3-f9e751c240e2 | note | Witness Point Y/N - Y
3ca10252-2e89-5869-9e68-19e9e67dbf5d | checkpoint | Injection & Mixing of Water and Foamed Bitumen
7cb65465-38d1-5fc1-9792-958c0d1a6cf4 | note | Controlling Documents - Foam Bitumen - TNZ B/5: 2008
fc7e3c8a-849c-5f2d-aa69-c0d330e4666b | note | Acceptance Criteria - Mixed material free of bitumen blobs or streaks. Overlaps minimum of 100mm
2e551841-3495-5d56-9417-5466a8e36803 | note | Method - Visual and hand squeeze test
5e146176-81e6-5455-86b3-a253f6862755 | note | Frequency - On-going visual assessment
157f6bc0-a316-52aa-87c0-cb8588c7ced0 | note | Responsible Person - Quality Controller
d75e6fb4-a1e1-574e-9546-f80663039fc1 | note | Verifying Document - Daily Site Record
0408f4b9-a7db-566f-842e-c8ce49681812 | note | Conduct - S
2d68548d-1090-53c1-a35c-845b14fa4e6f | note | Witness Point Y/N - Y
27c96781-3034-5bd6-8be1-9136ce336cf1 | checkpoint | Spreading of Cement
01ccfb4e-0c49-5fed-a1d3-0b505fb19505 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
7f2c4983-e50d-596b-8c7b-c22ef42a846d | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
7ef34fa0-8e9a-59bd-8785-ce8c88330fc1 | note | Method - Mat test (1m² canvas) and Average Usage Test
f6dcb570-3e7f-5770-a3be-074b3d13f53a | note | Frequency - per 400m² and upon emptying the spreader
f5a02c9a-601e-55ba-8fb3-3c1d16e31056 | note | Responsible Person - Quality Controller
25150e0b-d59d-5da4-a749-b162e20f96f9 | note | Verifying Document - Mat Test Form and truck dockets
db4c3540-5ba8-5936-95de-e62fec1a09bc | note | Conduct - S or Sp
f08fe4a8-8cdc-5363-b58f-53f328c3db20 | note | Witness - C
b49eeeef-bdfd-5811-97a0-12608fe561e9 | note | Produce Record - S
4a42d774-1ffc-5e66-bcee-3e7b45d3937d | note | Approval - E
4a80da64-6bc2-5a74-b787-1b30688ae0b5 | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
e8cbeca5-975a-57f5-88d7-a0f7cd20e1b1 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
6fcfe044-de0f-5703-82ea-84249fb99402 | note | Acceptance Criteria - 90-100% OWC
d63b43d2-13bb-54f9-9f97-51303c42c46b | note | Method - Nuclear Densometer Testing prior to Stabilisation
3f5c9685-8eec-5193-87d1-1b016ebae4af | note | Frequency - ≥1 per 1000m² lot
a1a60caa-9712-57d8-a824-8f80844f6b6a | note | Responsible Person - Quality Controller
f0ec5550-cdad-5db4-ad79-d219dbe9e06e | note | Verifying Document - NDM Record
a4bfeeb5-cbfe-50bb-acb6-8df6d77bd5cc | note | Conduct - S
aad7331d-534a-577c-8ef3-deb8b9608bb0 | note | Produce Record - S
61fce15c-0bce-50bb-9ccd-430c0ac70035 | note | Approval - C
fa6d7525-eeab-5b17-b87d-0fa6815e3a5f | note | Witness Point Y/N - Y
3aae6428-5972-5b13-a661-272c4bed881e | checkpoint | Cut Depth
ebc55cb7-ee04-5ca9-87ad-2f8a52440bd5 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
b586279a-c5d4-545c-bba0-5b99949abdd0 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
6afd350f-33f8-5fda-a5d4-90decefff04f | note | Method - Physical Measure and Visual Record
94d5311c-2fb6-595d-a569-5520eac71ddf | note | Frequency - ≥1 per 200m of cut length
734e1b1a-372b-58ea-bea2-862470a27081 | note | Responsible Person - Quality Controller
572d8a70-c8ee-5727-8e25-fbe9ab54c841 | note | Verifying Document - Photographs and Daily Site Record
e3d43801-33d6-5699-952b-05f04155daf6 | note | Conduct - S
6548fbf9-b3bd-5df3-83da-612e46e0dacd | note | Produce Record - S
e771636c-bed8-536e-a921-4d23970f28d5 | note | Approval - C
64e27a63-bb79-5ee5-926f-a611dfec9d9c | note | Witness Point Y/N - Y
b4e8c8c0-519c-5ea3-a63c-d6e4e3e61d57 | checkpoint | Longitudinal Joints
9b5327ea-537e-5b38-99c6-5e59d8c3d7ab | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
0c85fa4e-c8dc-5d02-8086-ca7b5301c52b | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
32a20381-ae33-50fe-96a4-ef0d500f2153 | note | Method - Visual Record
66187f92-e66c-54c8-bdce-7402c3413912 | note | Frequency - per sucessive cut
b81cacf8-1ec6-5181-b369-c14fd378959c | note | Responsible Person - Quality Controller
62afa504-059c-5ae3-a1e1-3ed92e2cecd6 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
7c7229c5-00c1-5d45-8929-c2cbf43243f3 | note | Conduct - S
a441f553-3013-5f26-b514-0098c9580486 | note | Produce Record - S
1119caf6-5db9-50b8-ab08-39a1b830e34c | note | Approval - C
47cf2557-01ee-538d-ba8b-e62d9319f341 | note | Witness Point Y/N - Y
4adf91a5-413d-56e8-8c6a-9cb5dbaf546e | checkpoint | Continuity of Layer
c9d50993-7259-5628-afe1-b3c7028f8019 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
1b08175e-0ee5-5802-a517-bb3383da8f0c | note | Acceptance Criteria - Longitudinal overlap, 1m for cement, 5m for bituminous stabilising agents
24ac5396-0969-53a0-b81e-86c2010cdfca | note | Method - Visual Record
4daf123b-5ca0-5906-b8c9-c2b16738d042 | note | Frequency - per sucessive cut
f8817565-3b53-507d-a9da-b1b1e3646e7c | note | Responsible Person - Quality Controller
3fd73da4-511c-5094-8466-743164294688 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
da41b8e4-767e-5e8c-b8fb-ffe70283dcae | note | Conduct - S
8453cf06-7396-538b-93e7-15ab5a8b1385 | note | Produce Record - S
56fc7dce-5864-5a9d-9001-20df43ae960a | note | Approval - C
3284a205-f31a-518f-9c15-3d482ca92fb2 | note | Witness Point Y/N - Y
a3e7c399-2e95-59d2-b1ad-e3d1d43952bc | checkpoint | Stabilised Material Particle Size
66888246-25a9-598c-a7f3-85c05bd7033e | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
6af51b4a-e768-5db1-b26a-2820db568e25 | note | Acceptance Criteria - No excessive breakdown of stabilised material
956a8882-d895-534f-871e-bcc5486f6e75 | note | Method - Visual Record
ef19ff4a-409c-5f72-9038-f917d1042dc9 | note | Frequency - Within 20m of each section and then regularly based on material variability
0cefc096-aecb-5d26-9e01-3a51214a24a8 | note | Responsible Person - Quality Controller
abf72aee-6b9f-5e79-ba15-7d1b19ce8224 | note | Verifying Document - Photographs
214dcae1-16de-5d36-aa67-fd6fa6f63537 | note | Conduct - S or C
7b25bade-ecc9-53c1-9c3b-d5eecc0b8ed0 | note | Produce Record - S or C
0cb8993e-faf5-5185-8e9e-7ce2c530b759 | note | Approval - C
81ad647b-afd9-5cef-b884-c82bb09f9249 | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
c6822e3e-fd49-5b27-af72-fa81df87c9d6 | note | Controlling Documents - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
0f904c80-dc87-57e2-a1ab-e7a5034a4f42 | note | Acceptance Criteria - To provide MDD for NDM testing
091529bd-d9f3-54d4-9066-d6c2d56918a0 | note | Method - Plateau Density Testing
a49ef4c7-861c-5630-ad81-33ecd335b36b | note | Frequency - 1 Every 3000m2 or once daily, or additional tests when material changes visually
4a867cc6-f129-5605-8544-a1120831fa36 | note | Responsible Person - Quality Controller
b0c9544d-97e6-50ad-8814-9e12bdea2bb8 | note | Verifying Document - Test Record
6877d6ea-ea10-5f04-840a-2c8564d4b4c0 | note | Conduct - S
28317c3f-c3c5-55e0-b02d-e357938f1a84 | note | Produce Record - S
906d1113-ec27-5dd4-8514-04af4e07ecce | note | Approval - E
5fa76479-ce90-568f-b0d6-b2bd0cf7a3be | note | Witness Point Y/N - Y
c6afc49d-3e73-5118-bea3-61314ffe0972 | checkpoint | NDM Moisture Correction
43b8ce9c-9e9e-5921-a1f6-3dd81c60f023 | note | Acceptance Criteria - Correction offset to be applied
dd05b172-2244-507d-b073-304b64ee09dc | note | Method - Field Sample and Laboratory Moisture contents
cb8d379c-da21-56a4-85eb-5b5bfca8d2f5 | note | Frequency - 3x Moisture contents per single plateau test carried out
97f81a1a-15d5-540f-8d03-4d156c989484 | note | Responsible Person - Quality Controller
3292e681-a9eb-523a-bd81-8adb306c95cd | note | Verifying Document - NDM & Lab MC
e9683198-a3cb-518a-acb8-b36cb87b1f07 | note | Conduct - S
9aee35c8-4300-5fa9-968a-44574cef6ade | note | Produce Record - S
abb34566-52c6-50d1-b12c-a2dab7da535a | note | Witness Point Y/N - Y
6f0b2bf5-1da2-5691-9a2a-fd78c49c3a73 | checkpoint | Foamed Bitumen QA Sample (1)
220e6751-b8ce-55a7-9538-35c5d891c097 | note | Controlling Documents - Indirect Tensile Strength, ITS
7d356d9f-8c35-51d8-83ea-0582b7c4cd9e | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa
e3a81253-61de-5c9f-aa64-27c119841a08 | note | ○ Soaked ITS: 150 kPa to 350 kPa
a41082d6-7bea-5dee-bb01-c14eab18abca | note | ○ TSR ≥ 70%
38bd8f45-4251-5001-a6e7-e073d653227a | note | Method - NZTA T/19: 2020
4ff7875c-ddd4-5677-9dc7-d75807e8f2dd | note | Frequency - 1 Sample per 3000m2 or once daily, (1x ITS or 1x UCS per sample)
2d7c9cdd-2354-54b3-b3b9-2f75efdc1226 | note | Responsible Person - Quality Controller
00c88ba1-7c96-52a7-a05f-14dee7c4cd11 | note | Verifying Document - IANZ Report
f413ab7d-6d99-5f1a-94cc-f0408406dd69 | note | Conduct - S
f6335258-8588-5d91-a12a-e803e9057951 | note | Produce Record - S
fc2bee9c-6ef5-51d5-8cea-65f819791abc | note | Witness Point Y/N - Y
33f67571-f142-5f24-b0c6-1d3228675495 | checkpoint | Foamed Bitumen QA Sample (2)
c2c9f7e1-931f-5762-ac83-e4e24e91d5b2 | note | Controlling Documents - Unconfined Compresive Strength, UCS
85657bdb-5093-573f-8485-eb2600f19ca2 | note | Acceptance Criteria - UCS is used to calculate MR(Phase 1) and MR (Phase 2)
00f484a8-9eba-51e9-ba85-d89a4095d7c4 | note | Method - NPTG Guideline
e3851310-849a-55e6-87c2-36eb6c3444a2 | note | Responsible Person - Quality Controller
528252b0-43ba-59df-be14-4bee64cdaef6 | note | Verifying Document - IANZ Report
64c4ec58-9dc9-5a6e-8499-511b9498d0f2 | note | Conduct - S
4719ebc3-e490-5a67-b58a-db3ae4626c44 | note | Produce Record - S
a94189fe-af1e-5001-8a76-50cb5df82066 | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
26230965-20ee-564c-88bd-1cf030411f0d | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
8ad43ded-ec10-5cbe-b45e-7201f9131b49 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
0f77e7d7-7302-5646-b937-64d6ff660937 | note | Method - Nuclear Densometer Testing
e86c5bae-5c7a-5477-b256-bd3146dfff92 | note | Frequency - ≥ 5 tests per 1000m² lot
ea922664-38bd-5eff-8fdc-2b556735a888 | note | Responsible Person - Quality Controller
8e4c9933-be04-5c45-90e3-933ffc7aa301 | note | Verifying Document - NDM Record
11151ed7-16b1-511b-bbef-87443b7a4ac6 | note | Conduct - S or C
6f58539c-b5e2-57f4-977b-6607c5f8e9a0 | note | Produce Record - S or C
7b0004db-431d-58e1-9fdb-aeeceb29929d | note | Approval - E
1509704a-d0af-52a8-b378-23e9d2a3b917 | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
63ac480a-f8b5-58f9-bbf7-a763b61d12c2 | checkpoint | Surface Smoothness
ddfce2d0-9a98-5206-89d4-4515b499cba0 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
5bd80133-dfe8-5cea-9fa3-d2bc88f74a4f | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
4528f006-72af-588d-8d3b-93dd7f554075 | note | Method - 3m Straight Edge
93d423b2-53ad-571d-a7e7-5e39f2e51d37 | note | Frequency - During construction and prior to seal
a48cb531-df91-5e9d-b880-e8f2730fa549 | note | Responsible Person - Supervisor
16423559-7746-5259-80c7-3aa7ea1332be | note | Verifying Document - Photographs
712d59eb-4901-5dca-94dc-f5270217afca | note | Conduct - S or C
43cc2515-5ebb-54a3-beb6-bc0c67a58f5a | note | Witness - C and E
358efa70-27c2-59c2-96fe-574f9acace84 | note | Produce Record - S or C
924f2131-317c-5b93-a720-24c004fef9d5 | note | Approval - E
6a6d0959-50fd-539b-b39e-2f79949f5abc | note | Witness Point Y/N - Y
182df3d4-e0dc-4b70-9c08-b70cd7689fce | checkpoint | Surface Shape
812860b7-cdc9-54fe-8cb2-f22c3817afb5 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
a6283130-a7cd-54a2-ad4a-8f5e85c003aa | note | Acceptance Criteria - Between -5mm and +15mm
e0b09e8c-794f-5814-a0e1-8e5b45624697 | note | Method - String lines or Survey Asbuilt
c9dacc80-f542-5f1c-a86d-3d91cf6a387d | note | Frequency - During construction and prior to seal
7bdabb34-9ede-5dc7-b153-79f1ec56ca0b | note | Responsible Person - Supervisor
a5feb6be-ae4f-5f00-9b35-235b2c674417 | note | Verifying Document - String Sheet/Survey Asbuilts
b3e296a8-b071-5162-b662-836505beba5a | note | Conduct - S or C
87e37cdb-9cae-5999-a080-1ff095e2c971 | note | Witness - C and E
14055d37-7b80-59e2-b346-6417cd5027ff | note | Produce Record - S or C
3e0e9b98-2bae-5eaf-8d4b-6762e9f78645 | note | Approval - E
2b7039a1-c4bc-54b3-8422-fdabf38863a5 | note | Witness Point Y/N - Y
8a36fd7d-8663-47eb-a111-5497be6becb0 | checkpoint | Cross Fall
38a386ff-a2fa-5cc2-8ba6-ee57d50d34f0 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
6e064cac-b79b-583c-9ca5-4c76745ad06a | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
e4064444-8202-5b7e-bcfe-2dd30acae2b7 | note | Method - 3m straight edge or Survey Asbuilt
20f9906d-c848-50ce-b7c8-f4aaef50c0b1 | note | Frequency - During construction and prior to seal
6cc47985-395f-5925-9cf8-5ce36a2dcde3 | note | Responsible Person - Supervisor
609377c6-22c3-572f-ab5d-b575d00c79a4 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
e82b9204-9587-5956-a9ff-92fd76d03f81 | note | Conduct - S or C
8276e5d9-3540-5e1c-b5f6-e82cc43415a7 | note | Witness - C and E
21e378bd-6d01-5d0e-9ddb-f26b7557e83f | note | Produce Record - S or C
fc7ff48d-1552-5232-b36b-920da04a11d7 | note | Approval - E
1dcafe22-f3e0-55cc-b457-24c551c96022 | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
868726b6-492f-53ad-aa5b-7f4ce6112a7d | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
c9b260d5-b5fa-5d8f-a56b-8dba9797daa0 | note | Acceptance Criteria - Tightly bound matrix post sweep
13dccf09-db24-5738-8ff6-ce6704ef3034 | note | Method - Visual inpsection
29f6939c-1c0e-541d-ae33-4e4fedf0e025 | note | Frequency - Prior to seal
d73ef07a-8583-5f63-ada2-b24d65e075e4 | note | Responsible Person - Supervisor
60d7b473-9bfd-5aa9-abe9-16b6eb318ea1 | note | Verifying Document - Pre-seal inspection sheet
0b27f8c9-c0e3-557d-9358-11fd15730126 | note | Conduct - S or C
d8daaf21-088e-501c-92ba-ab01e4baa0b1 | note | Witness - C and E
087b265a-6d9f-53d4-9369-bc0ad69295de | note | Produce Record - S or C
a9ecfafa-c27c-59e3-8d52-3d544167ece0 | note | Approval - E
140ad576-fe6c-5e06-ba62-d24f824b1189 | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
7ec74b89-0f51-5afc-bfbc-f5d4d7fe9002 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
b27d4f77-10ca-5b23-bc08-fca152407b97 | note | Acceptance Criteria - ≤80%, however 65% is ideal
1f90d3b2-f3a3-5d5d-ab47-3a7be023e232 | note | Method - Nuclear Densometer Testing
cf15206b-21f0-5190-9dd7-b4650c86fbe4 | note | Frequency - ≥5 tests per 1000m² lot
2946e989-e77c-52bd-9e85-388d0ae65667 | note | Responsible Person - Quality Controller
57af6911-f454-51ff-952b-2dbee2e0b466 | note | Verifying Document - NDM Record
3ec993e5-0177-54c8-9228-a4f462b6e839 | note | Conduct - S or C
a96cdf61-1b54-5b83-9e6f-c5b51706f4e8 | note | Witness - C and E
c0e01208-3a82-5d77-8a4b-78a886a478c8 | note | Produce Record - S or C
81f8013d-cb46-5f82-9090-1010dccd309d | note | Approval - E
a9df603b-ecaf-5b11-9110-a72af183e2cd | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
2b0bdda5-02f0-5d4d-9a87-b0b053e4935d | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
d2af5a3e-31d1-583c-858b-d0b6c06392fd | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
a4d7565a-10b7-536f-aaed-6d6732d5449a | note | Method - NZTA Maintainence specification section 6.1.2
412e9453-3d32-5281-86c0-b34aa05aac7c | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
fd9f5a96-76ef-51d4-be0c-b96f99de653c | note | Responsible Person - Quality Controller
553a6213-90a1-535b-8bc3-6cf6c57a9d83 | note | Verifying Document - Test Records
de331983-49e6-5d81-8e3d-7903e9d3038e | note | Conduct - S or C
17b1ef23-00a6-5498-9dfb-e15717887028 | note | Witness - C and E
80788ec2-2e69-5af5-8ff0-4723ef39454b | note | Produce Record - S or C
e8deff9e-30d2-51a9-b322-b9719712c616 | note | Approval - E
39ff6523-a447-5e6f-8ea4-400268c51264 | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
f6ac91d4-5c0b-53d1-9e4e-00bc03939ff3 | section | 5. Chip Sealing - 5.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
8b2026e2-5b11-5d8e-85b7-641e09620f70 | note | Controlling Documents - TNZ M/1
be0db22b-1bdd-59b9-94ca-168995dc9cbc | note | Acceptance Criteria - Table 1
59b30edb-46b3-5fea-b432-3b259d11440b | note | Method - Property Test
229aac6c-5e20-5446-b964-0ee299be1b77 | note | Frequency - Annual
9fb11499-1889-5658-8794-ec37384fa741 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
e7f07254-5c65-541f-b458-bd7251dad088 | note | Verifying Document - IANZ Report's
6007b62b-3dfc-524e-84a9-16cf98bf2e32 | note | Conduct - C
d93a25cf-f88f-57c1-86a8-fd6e1771c64e | note | Produce Record - C
ea3ea4b5-d7cd-530e-a42d-299825b7fc19 | note | Approval - N
34cd4309-0e8c-5fe7-8c7b-7c872f276590 | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
4f130326-4ac6-5ad8-94bf-d1da4f6f853f | note | Controlling Documents - Higgins Internal Specification
ea84c8e6-d8da-5b66-9cf2-0046330144d6 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
51e6effb-4f57-5ff9-a3dc-cce3e0e6a95f | note | Method - Property Test
ab4ab284-ba13-5c33-aa62-58f420c63640 | note | Frequency - 1/100,000 litres supplied
8b8928df-d417-5343-98ef-e190ca92bd98 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
0a6a6752-3456-5e8a-815f-69f446b884ba | note | Verifying Document - IANZ Report's
47193936-997c-5df8-bf37-d79914c923d5 | note | Conduct - C
a02eaa3b-006d-5a1c-801f-872ffe6934da | note | Produce Record - C
d866e11e-5d26-52ae-87d7-beadf9f3c6f5 | note | Approval - N
89053006-b780-5109-91e5-5c98b8009e9a | note | Witness Point Y/N - Y
271433f5-90db-5716-947f-66b53e064a88 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
53bdd787-6abb-59e0-95a6-6f15986991af | note | Controlling Documents - TNZ M6, RNZ 9805:2009
5805228b-27b1-5deb-b304-4cea666ce82b | note | Acceptance Criteria - <10% fines under 230kN minimum
03f55fad-b473-5c2a-9625-a9a03892548d | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
3c35bcf8-3e17-5078-a4e1-95cd9fc8478e | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
493b8b36-9acf-575a-bea7-56e58e336de4 | note | Responsible Person - Surfacing Project Manager
29a38890-dab4-52cd-ada6-dbc43f641708 | note | Verifying Document - IANZ Report's
67c04894-90d3-547b-8737-7ecfce18596a | note | Conduct - C
7d1e485c-2520-5814-a215-e81fdaf3bffa | note | Produce Record - C
b53d1e8b-329d-55bd-ae3e-be21470291d1 | note | Approval - N
58473c41-c29c-5485-bc36-981a06c71a98 | note | Hold Point Y/N - Y
6001235b-048c-5705-ab46-316e6fddaf77 | signoff | HOLD POINT
b5105286-fa50-5f37-8ad8-ff00dc521109 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
58fa62a9-215d-5613-9bd9-9ab49e68b8f7 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
63c2cbcc-d06b-5c5f-8e38-e683cd3c21fe | note | Acceptance Criteria - AA or BA
c0b725be-8998-5409-af16-20a224d0622c | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
6ed7d5fa-4724-5ae7-b043-720c872f0afe | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
76562c23-102d-5b40-8462-46979e041c9b | note | Responsible Person - Surfacing Project Manager
6bff282c-1e51-5bc9-bb12-4f619d815429 | note | Verifying Document - IANZ Report's
cc78577e-0975-5d75-9839-b7ddc6c612f0 | note | Conduct - C
bfd165ea-9de0-50b6-92c0-90d9bd220e9d | note | Produce Record - C
4d8b8969-ab8e-5dc4-b597-0cae2ac7aeb0 | note | Approval - N
e3023068-e8a8-5c87-837d-1d61b79ccb5b | note | Hold Point Y/N - Y
d36fb53c-673d-5ad9-bcd6-d21d23c23bfc | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
b3fcdadc-47af-5046-b498-b600d99da170 | note | Controlling Documents - NZTA T/10
3bee80aa-778f-59f5-b27d-07d4c2d2b80b | note | Acceptance Criteria - Meet Skid performance Requirement
940bd552-0893-5542-8955-587de23dc15e | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
2fcb1c13-a902-5a81-adb3-e618b4de9fdc | note | Frequency - Each Site
394707f7-9057-588d-8570-80e0918c1cf4 | note | Responsible Person - Surfacing Project Manager
31c3a542-0ed2-56ae-8560-b63e2da24e03 | note | Verifying Document - IANZ Report's
98a5d76b-247f-5fec-84f8-411a556f396b | note | Conduct - C
0909bf17-0574-5130-9983-fa9549281587 | note | Produce Record - C
ab53e95c-99c1-5f12-9586-98ee6b1c31b7 | note | Approval - N
b570047d-b82f-50e3-ab93-a23853f9ce9a | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
d013ce30-a7e6-5498-9f1a-dad30a3593f5 | note | Controlling Documents - NZTA P/17, M/6
8ac5a65f-dff6-53a2-90cd-f27a0eb55a99 | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
42ba5bf8-81b0-5be5-b67c-1714c29e69f5 | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
ab1c3f03-1b62-59a0-b7be-35f5aaa45a88 | note | Frequency - Per Stockpile
1ddb6f11-0118-5632-a4a7-d289aabe3fc0 | note | ○ <100m3 - 1 Sample
0ece5cc0-c053-5ee4-8223-f317d4c88cff | note | ○ 100-500m3 - 2 Samples
8c67fac3-130b-524b-8054-50e825931b5e | note | ○ >500m3 - 3 Samples
1336dc3b-d8e3-521d-aba3-916b389df721 | note | Responsible Person - Surfacing Project Manager
3b594d53-9450-5e4f-a1e8-234f761807e9 | note | Verifying Document - IANZ Report's
007db50f-99eb-5dcc-bc81-4e530adebcdb | note | Conduct - C
03fe1fe4-33ef-50b5-bd10-0a3535ad5cf9 | note | Produce Record - C
d81a5951-f54c-527b-9143-4a2ca9982562 | note | Approval - N
84592c8b-8043-5cb0-8fd0-35db154d1acc | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
80b76e91-b34b-5780-95aa-fc9c1405cda0 | note | Controlling Documents - NZTA P/17, M/6
4201f73b-bda8-5187-b0c5-c38e35e231b8 | note | Acceptance Criteria - As per Table 3 NZTA M/6
9d471340-ecae-5049-9cde-d654db53e39e | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
96cc5a0f-2818-5188-bc12-5a5253c24535 | note | Frequency - Per Stockpile
bd89d0c1-d0b0-57df-90fd-7faddc94ccab | note | ○ <100m3 - 1 Sample
bc202df6-9386-5cc3-a3bb-d78c0ea7a0eb | note | ○ 100-500m3 - 2 Samples
9ed37431-615a-5dcf-9288-430f155bb036 | note | ○ >500m3 - 3 Samples
7fdeda30-12cd-5f45-9d66-00bb8ef83b33 | note | Responsible Person - Surfacing Project Manager
509a474e-20b6-550e-ac97-c8bd2f0be01d | note | Verifying Document - IANZ Report's
70f575ba-b170-5869-82d0-118f5bb9da66 | note | Conduct - C
f022fa0b-78cf-55e7-9561-c15f91841467 | note | Produce Record - C
1c2f736a-11ea-5a34-8e7c-86ff9c0112f0 | note | Approval - N
10558865-be43-56cf-b387-d406b2f2e288 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
21de5a0c-eba1-54d7-9a81-bfeb7bed89e8 | note | Controlling Documents - NZTA P/17, M/6
31af1d7c-29e1-5bc0-bace-66fbafed7e37 | note | Acceptance Criteria - Min. 98%
eb036cbf-9ef7-5268-88dd-46dcfab1837b | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
12e8bc99-57d9-5d2c-bdc6-1b4440336fcc | note | Frequency - Per Stockpile
357e6487-4a73-5787-b355-3fb31de7a90a | note | ○ <100m3 - 1 Sample
12fa72dd-5c3a-52d8-976b-9c826afa5aa7 | note | ○ 100-500m3 - 2 Samples
183ffe91-49ec-5024-9996-1bc1d4f52cf9 | note | ○ >500m3 - 3 Samples
b417e885-0b39-5ae6-8b01-254887b9859e | note | Responsible Person - Surfacing Project Manager
02064a31-e468-5c3c-b676-6a1806a30aa5 | note | Verifying Document - IANZ Report's
831009b1-4734-5cde-ad9c-51a34e05bdf7 | note | Conduct - C
ec7dd819-9d44-58e2-ba2e-c62b63e33af9 | note | Produce Record - C
cf2b5add-aa83-506d-b0ca-147774d7b5ea | note | Approval - N
02ee7ecd-f444-5759-b19b-582ad0386096 | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
50e2ed0d-0467-5ea1-9ce3-4f4d8743274c | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
b26317d9-c3e2-5f1a-82f1-1ac43545a0c9 | note | Acceptance Criteria - Client Approval
393a1de7-6369-5a72-bab5-03f9a1433644 | note | Method - Review
a6077899-cf0a-5ea8-80eb-0a854c4433c6 | note | Frequency - Annual
d05fefcf-3e76-5640-95b6-f1db228fe463 | note | Responsible Person - Surfacing Project Manager
72729b87-0e5e-5953-bb60-c1bf950e3adb | note | Verifying Document - EBOP NOC Design Report Acceptance
3da5f6b3-9eee-5466-9cbe-576634a11bf9 | note | Conduct - C
730c21ff-4ec9-53f4-8de5-1db40bcc30b7 | note | Produce Record - C
67defe1f-5934-5acb-93c4-251160f8de3f | note | Approval - N
85002e89-68ab-5197-93e8-5251b1fc7692 | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
2d90825f-40a1-55cc-9369-13e616f644fc | section | 5. Chip Sealing - 5.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
5f2c49e1-7583-5c4f-8e8e-55620301e720 | note | Controlling Documents - EBOP NOC Design Report
3478e702-e27e-5778-8ae3-14618c6f420f | note | Acceptance Criteria - Visual Inspection
a0872023-f428-5ca6-a55e-ebd11f6aff9c | note | Method - Visual
bbd9a1f4-d26f-5eaf-bcfd-a6d287c308b8 | note | Frequency - Prior to start sealing each site
bf749cb5-68bb-5a4d-85c6-fe49c7cf463e | note | Responsible Person - Surfacing Supervisor
a40b9a49-c342-5d41-b342-6c36600f4b17 | note | Verifying Document - Chip Sealing Quality and Site Record
ae1509bb-7c9d-5915-a86d-d3cd9276d75b | note | Conduct - C
2f25268c-aa4d-50a0-9dbb-de6183385b96 | note | Produce Record - C
bd1f95c0-4c72-56f0-962c-9d94f0c2ddc1 | note | Approval - C
ffaee45d-ac84-56b3-a7e4-11baa3ecdc10 | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
d7eb7377-000d-5d40-b20a-1523ca316e5f | note | Controlling Documents - P/17
ce3eb77d-2f72-537b-b7cd-7aeaf05bbe15 | note | Acceptance Criteria - Visual Inspection
4821db72-74a0-51b5-8294-70d10c3bff75 | note | Method - Visual
e5e600f4-289f-546b-9ed1-72147a0ec6a0 | note | Frequency - Each site, prior to start of sealing
ecfd6c83-1542-5bda-95fc-afb1199dfde9 | note | Responsible Person - Surfacing Supervisor
b5485047-1821-5034-87f3-761dc21bd532 | note | Verifying Document - Chip Sealing Quality and Site Record
54829eb4-71f1-508b-83ad-15a7b44c3f73 | note | Conduct - C
22489c14-653c-5519-8cc9-b9ee06525f33 | note | Produce Record - C
b8359286-726a-5f34-b782-995cdc5c0216 | note | Approval - C
90267b27-eb40-58eb-9bb6-c6c255671fd5 | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
9157cf6c-b418-5a2c-96c2-586c9cea78d3 | note | Controlling Documents - N/A
eedbacde-e58c-5d87-a9d4-b52cf15f4f62 | note | Acceptance Criteria - Visual Inspection
4f2e6f78-aca2-5db7-b417-7b1071ed55d3 | note | Method - Visual
97bae255-d555-58f8-9ade-3639342085b6 | note | Frequency - Each site, prior to start of sealing
cdfc37a7-e619-5a36-8021-a3d8a7c21b4c | note | Responsible Person - Surfacing Supervisor
46ec55f4-951d-5aec-b8cf-96cf1d9bee84 | note | Verifying Document - Chip Sealing Quality and Site Record
e4a6be97-c42a-52b6-badc-f4e7ca466e44 | note | Conduct - C
ccd0b951-54e8-5a31-bffe-e2ec015d700d | note | Produce Record - C
4b513bfc-05b0-54aa-9370-93f87822a82d | note | Approval - C
32978c62-9287-582c-a4a4-4dc2889ae94e | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
906ac6e9-f530-5b54-8d6c-8c5ff9f64def | note | Controlling Documents - EBOP NOC Design Report
3d090462-c4e4-5572-88d1-89946534fec7 | note | Acceptance Criteria - Details/chip correct
64954199-08fe-578f-9f8a-785d628b2842 | note | Method - Visual
8edf05ac-e0f8-557b-96d5-8a5e1f6ebcc7 | note | Frequency - Each Site
e6247393-eebd-5f09-83ca-8e55b9a51879 | note | Responsible Person - Surfacing Supervisor
defb12e4-6a6f-5556-be7a-cee7d3a59b1e | note | Verifying Document - Chip Sealing Quality and Site Record
a9533c8e-7c9e-5d6b-8bde-4bdbfbb4fb85 | note | Conduct - C
e0fb5485-e7cf-5c69-af31-5be2f8ff64f8 | note | Produce Record - C
3971ba94-0aca-5f66-a558-5def33ea8878 | note | Approval - C
d28cd91e-7122-56fb-be17-072558387214 | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
3bc3d8ab-318e-5d1a-a460-e81789623e83 | note | Controlling Documents - RNZ 9803_0513
82c52134-e0da-5918-8946-0a655708b59f | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
dbf69254-c62a-5823-bf90-1a3e18ef526d | note | Method - Sample and test
df32e95c-0be4-56e4-96fe-a19531524880 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
46b011d9-0194-50b7-bcb5-506a2a2ef1bc | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
9098daa9-b83e-5630-9f18-b41b4e0756b6 | note | Verifying Document - IANZ Report's
615aa981-9686-5d20-a3fd-ad0ddd411b1e | note | Conduct - C
3df1b566-65c9-5abe-a384-c4a4746121a2 | note | Produce Record - C
f1883738-5363-5375-814f-bebbf078feea | note | Approval - C
6deffba3-96dc-58f8-8ce5-3e7fb2fea657 | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
f9e3b871-1d7c-5628-a871-74df9e204736 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
ead0579c-c347-56a0-a5e4-3beac853dbfb | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
16c64f10-2a0c-5a37-99c8-b73c976b5eb4 | note | Method - Test, Review
38bb261d-9971-549a-b8a3-c2408c4667d2 | note | Frequency - Per Sprayer, Per Site
3b7f1ab4-bb84-5d6a-9e38-9f19bdd6260f | note | Responsible Person - Surfacing Supervisor
b6cb8d78-810b-5043-b6ba-3db12c4f3e0f | note | Verifying Document - E/2 Certificate. Spray Sheets
e8e118f5-dac0-5783-9203-82140ed00748 | note | Conduct - C
b7b22fea-4e9c-5c34-9c7a-0a89d830f1b1 | note | Produce Record - C
8244ccba-a37f-58e1-afbc-ff78dd4d19ae | note | Approval - C
a8e00db9-ceb7-57bc-adfa-7eb4edf5bf99 | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
7969e978-a16e-5943-9327-29e5e8411548 | note | Controlling Documents - Chipsealing in NewZealand
c9b54a69-3018-5138-be32-1012b1d19145 | note | Acceptance Criteria - As per Chipping Guide
348cecae-942e-5259-87be-373e0f62cd9c | note | Method - Visual
11b8dfd6-2066-5b0c-89d5-3f6941737b89 | note | Frequency - Each Site
29eb76d7-c97e-5ac4-ad65-ead4a5e24bc7 | note | Responsible Person - Surfacing Supervisor
d69e2065-2e79-5bd8-ae44-a3ceff948043 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
490f6de2-4fd4-5675-8ec0-54525948c2f5 | note | Conduct - C
287e9c6d-e46c-5dd5-ae9e-fea86c9ffcdb | note | Produce Record - C
ca5571b4-47b9-5b54-a388-cc520169a673 | note | Approval - C
852da67c-0774-5df1-a532-532b327ffdad | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
446e6fb9-3dcc-5330-acc5-622701083861 | note | Controlling Documents - Chipsealing in NewZealand
b003c0db-bb88-54b5-92a8-fdf209a476d1 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
2d25107c-9e07-55ff-a7b7-bd46c98b8094 | note | Method - Visual
f2828543-3649-54d9-b9a2-04edc1674498 | note | Frequency - Each Site
8a292f63-ee5a-5490-90b9-ed4d32dc8840 | note | Responsible Person - Surfacing Supervisor
be1ee723-b7bc-58e5-b829-fdde42c88c83 | note | Verifying Document - Chip Sealing Quality and Site Record
84125f97-b08c-5db5-b23c-de27512d7336 | note | Conduct - C
54bd0105-832c-5472-a9cb-fd0ec0c482d6 | note | Produce Record - C
b35c0851-f350-5d46-ae8b-d6cad18cd56f | note | Approval - C
70217257-2846-5809-a11b-5500837d2497 | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
86f2d3ee-fc93-5a17-97d9-2c6570b08f33 | note | Controlling Documents - Chipsealing in NewZealand
f512e867-1cfb-5149-b3c0-4fee3537f960 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
1a2da4b6-bd43-561d-830a-23de462be69d | note | Method - Visual
a74122d1-3cd0-560a-8b9f-f76c10a1e594 | note | Frequency - Each Site
08ed9c04-1aca-5f8c-b42b-47435ecda2f2 | note | Responsible Person - Surfacing Supervisor
ffe2a38d-f4c8-53c9-b2fd-e70ac718cbbd | note | Verifying Document - Chip Sealing Quality and Site Record
5421099d-3898-5980-aab8-6e8e45d494af | note | Conduct - C
f81dc0e6-e17c-551a-86a0-a659bfe498f2 | note | Produce Record - C
6b0b49a1-01bc-5f07-9dc7-1d22edd1379b | note | Approval - C
36f805ae-5b25-5f54-adad-762ce44f92b8 | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
1f1a9f02-94b2-5bfa-a5d7-84fa0db6093b | note | Controlling Documents - Chipsealing in NewZealand
a3510dac-4259-5de7-bb37-913c23062c23 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
d3ab391f-57e0-5f60-aacf-50fd0579f7e5 | note | Method - Visual
47747197-4d26-5f59-a5fb-74f696b4f43f | note | Frequency - Each Site
5cc8b2a7-8b3a-538f-8e27-e7b584f3f51b | note | Responsible Person - Surfacing Supervisor
a6d7feec-80f5-54f6-82f7-b041c5a88f4d | note | Verifying Document - Site Record
ff16e333-2c2c-567c-b9a8-302738dee534 | note | Conduct - C
62763e32-0afc-56d3-97b8-1fdf1c46e0b3 | note | Produce Record - C
56593a26-ea8d-5363-9d01-1af02cc693a4 | note | Approval - C
7fadde44-33aa-5a49-8031-ab8f81a8ee93 | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
0b6a5210-05fd-5cad-8309-ba7732385b3d | note | Controlling Documents - MOTSAM
c8962305-ef8d-54c6-9bf9-7197b325e3b6 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
c1c3232c-9368-5f2e-8e90-76419a13b3ef | note | Method - Visual
2be968fb-97ea-5b0d-8284-aaa1f63ec094 | note | Frequency - Each Site
59c23fa7-6a74-5bf9-b1f9-72f63c1d4f5b | note | Responsible Person - Surfacing Supervisor
629b86d0-41d2-5e06-88f0-75b404724809 | note | Verifying Document - Site Record
f52dfd0d-c3cf-513e-9aeb-78b283b75b28 | note | Conduct - C
fdc83e1c-65f7-588f-98b2-bd482ef2ba59 | note | Produce Record - C
a475342d-e024-5a03-8f17-d38850e97fcb | note | Approval - C
7073b69d-852c-5f6d-a856-6200d980c6e9 | note | Witness Point Y/N - Y
2fa24de8-fb07-5d57-947e-3eea20cf5b9a | section | 5. Chip Sealing - 5.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
5debb248-f10a-5ea9-9451-8c9668cf6009 | note | Acceptance Criteria - Formal Agreement
c3042c9e-17ca-587a-9eac-740ca8096809 | note | Method - Visual Inspection
0cc208e4-78f5-55cf-b5cb-39d62b42be63 | note | Frequency - Post seal sweep
a4f611b1-3b1c-507a-8cbb-23eab8aace1e | note | Responsible Person - Quality Controller, Supervisor and Engineer
c5cecbe5-f6d1-5c0a-bb85-759d0482276b | note | Verifying Document - Meeting Minutes
2815080c-7f1b-5e3e-b78f-47f72130eaca | note | Conduct - C
0eb0c0bc-6c99-5fa0-9c9c-bf426d0b4199 | note | Witness - C, S and E
5f6c4819-40b1-54aa-b113-7303025438b1 | note | Produce Record - C
53366934-1600-5174-ac34-35c371be1d60 | note | Approval - E
068d42d3-43f4-5a55-82f9-7ccfbd3cda38 | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
40341f67-aae2-539f-977f-95dd7a2f39c7 | note | Controlling Documents - NOC; MS 6.1.3
561575bc-f084-57f6-874d-379002789308 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
ac591eb7-7188-5ade-82b2-fb6a58f793d1 | note | Method - Record
2e6087ce-7f83-5b34-a076-4f21fe19f7f7 | note | Frequency - Within 2 months of completing the annual resurfacing programme
8f990d2a-dd7a-54ab-8851-1b460dc65b53 | note | Responsible Person - Surfacing Manager
7185d2c9-7fd8-55e7-8638-1c8f55975b7d | note | Verifying Document - Construction Completion Report
b7163495-e5e1-59be-beac-a1a6523cdc7b | note | Conduct - C
b9a05604-98bb-5bc4-aa4f-1fa160a60872 | note | Produce Record - C
7849c22c-823c-59a5-8b2c-4c7a4b40f736 | note | Approval - C
bf0b9895-3874-5d08-a962-72ec8a91764f | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
75e26f2c-aa50-5e48-8a31-e24affbf2e35 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
dfd2669b-0eb0-538d-8897-8b8a258a0f09 | note | Acceptance Criteria - Engineer Approval
5cd07deb-2529-50cf-9f6d-88d3eb434a6b | note | Method - Visual Inspection
54b9eb15-1bba-5dda-bc5a-dd3109c78ddf | note | Frequency - ≤2 months of 1st Coat Seal
cc65607f-a2cb-58ba-bd60-745cf97ed90e | note | Responsible Person - Quality Controller/ Contract Manager
b8bdd3d0-6905-581c-a960-c1c4dc25c61e | note | Verifying Document - Signed Report
037f3f02-fb44-5524-bc33-7d705aea5c89 | note | Conduct - C
5266263c-af52-53d5-8e18-8cc3f781a897 | note | Witness - C, S and E
ede57a9f-7fd6-54e8-84b8-c73b9bdd6bd8 | note | Produce Record - C
28fce2b0-dd87-580e-94cd-d94d36948e57 | note | Approval - E
aaca7b9c-6468-5b94-92d0-f9ac31da26a4 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
cfcb4faf-0493-5bcc-a3c0-153c4600ce4e | checklist | ITP - Pavement Rehab - SH 35 - Tukaki Marae East | itp | ITP - Pavement Rehab - SH 35 - Tukaki Marae East
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
09dfa698-6b7f-519e-b940-013fd716a19e | checkpoint | Design - Geometric Design
44eef280-c475-5d10-ad0a-f1b81b7d7822 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
439056bc-b2b9-5f73-8260-873347ed63f1 | note | Acceptance Criteria - Principal Approval
fbff4caa-a583-5d32-a1c6-3f84108ca090 | note | Method - Contractor and Principal peer review
25057938-efb2-56e2-97b7-9852c2a632a3 | note | Frequency - per design revision
7cc28890-ccf0-5d96-b986-804f622203c9 | note | Conduct - C or S
9c37af8e-7c8e-5919-90a8-10e952f34043 | note | Produce Record - C
45926d8c-9427-5cd8-abf5-d903ca3eb612 | note | Approval - E
446e474f-ad2c-5fcd-8a3b-20ea7bc05d6a | note | Hold Point Y/N - Y
734b8921-df80-5868-90e2-320abcb6aec9 | signoff | HOLD POINT
fc457da0-71e7-5429-a676-cfa9f8ad8762 | checkpoint | Design - Pavement Treatment Design
2b2da1f1-b155-5a07-bf2e-c9c83d21ada8 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
0177d536-56e0-570f-829d-239c1f892959 | note | Acceptance Criteria - Principal Approval
eab83aad-91f2-533b-8e4e-e1f51145c1c6 | note | Method - Contractor and Principal peer review
0aa4e7f2-6947-5cbc-8fea-49b61007571a | note | Frequency - per design
98b2dbda-6cf8-5b11-b5db-1a7023fb154e | note | Verifying Document - Pavement Rehabilitation Design Report
d8c79485-f8ec-5bf3-9321-d2cdac43bf7b | note | Conduct - C or S
618856c7-f6c0-5adb-be6c-280b8860a77c | note | Produce Record - C
d273086e-1cd3-55bc-8cff-5fdfc97f20dd | note | Approval - E
e28222ec-9dca-51c5-be00-f766189e2e64 | note | Hold Point Y/N - Y
f7622f1f-ef56-5ab3-b6af-8b3b9e5d5f72 | signoff | HOLD POINT
36362436-b1e4-5e95-af81-437ff9bbd938 | checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
b2d7f1ce-88b0-5a52-921b-5c4aa54eb1cc | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
5ec677f4-4147-5a6e-b423-ad9d627859b9 | note | Verifying Document - Sampling Worksheet
f984e05a-d583-532d-b960-61e0283a60e3 | note | Conduct - C or S
bcf19893-7a0d-5dcd-8370-2715aaf81042 | note | Approval - S
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
d954be3e-9239-5575-89c1-4eff096b42af | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
f6a97ec8-3aef-5f05-bbbc-53c6789205c9 | note | Acceptance Criteria - Soaked CBR ≥ 40
fe0460ae-712f-5932-b1a7-8300d88a9dbe | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
cb5dc202-fdbb-529e-965b-96620b72a0c2 | note | Responsible Person - Supervisor
47488c4f-395c-5e50-83d4-6a45c27e489f | note | Verifying Document - Test Report
c079c17c-f3d4-5ffc-818a-16223d4ef393 | note | Conduct - Sp or C or S
75d5f83e-9559-5a65-947a-8a8f0aaf7d7c | note | Produce Record - Sp or S
348f0638-7e5a-51ae-a5db-23ac018435b2 | note | Approval - E
9869283f-3d2d-5bd8-9a4b-c1a3ad86b5d0 | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
ae7e2d83-e996-5777-8251-1ac263229947 | checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
d87878a1-d942-5a03-ad23-ae2bd5354432 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
d812db64-fc4c-5ebd-bce6-41ff46faadd9 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
ba1bc25b-b11c-5a78-9c46-bccd7ec25fe8 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
62daa671-5c54-5c48-be46-25348c20af92 | note | Responsible Person - Supervisor
a4a1fe60-9392-5fa3-a2c4-6d2d30ab0a66 | note | Verifying Document - Test Report
e221c46e-9326-525d-b845-b0650609d845 | note | Conduct - Sp or C or S
c175ea53-2c09-59e9-b594-893c91439a4b | note | Produce Record - Sp or S
c1c87b9f-6241-56e0-bfb9-ecaf14a461c3 | note | Approval - E
6cb56481-b5ee-5546-9117-51dc84d58db7 | note | Hold Point Y/N - Y
59b9d644-63f9-5af7-bf31-75c1a6bf1a10 | signoff | HOLD POINT
282d13fa-6a2e-5570-b955-78f6c0062fd3 | checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
61e214d5-255d-50c3-b308-dda1cad2c3e7 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
6e7b73d6-180a-5629-a51b-a084a69d0f14 | note | Verifying Document - Sampling Worksheet
19b6d86b-bdd4-5d23-8c3b-38570c4103e5 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
63707399-ade6-53fa-a1c8-4d5c745e0aa3 | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
8092f186-9b57-513c-a069-6120f67308f6 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
99eea981-c110-5169-8f18-9719c9a34cd4 | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
f87f42fb-6e40-5fb7-b3c0-14eaf672cc75 | note | Frequency - One test for every 10,000m³ of source material
e44f4ac9-58cb-5ddb-98a8-cb86212d9637 | note | Responsible Person - Quality Controller
4a703fb0-52a9-55f4-bb9d-a5e4f68ebce2 | note | Verifying Document - Test Report
36537000-5af3-5637-b5b3-cfb9ee9a75ff | note | Conduct - Sp or C or S
ae0c4e10-ca18-5283-a351-75ee72c8ca05 | note | Produce Record - Sp or S
a7824590-a7c3-5ab0-a0db-269791212b3b | note | Approval - E
f894677b-73e6-54ca-81c2-12c3c4739203 | note | Hold Point Y/N - Y
2bce147b-57e0-5df2-aa19-d3114e0f900e | signoff | HOLD POINT
771bbcd5-e52e-5af5-9fc3-2a5ff6956b1d | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
97670e03-3ac1-50a3-bf5e-a3e6385e6428 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
6740fc3a-43a7-5787-9b85-1b5e6ac81200 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
128c9bd1-2c00-5039-b433-7eb1095729b7 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
188d90c0-5285-584a-9d0f-c61ce522c829 | note | Frequency - One test for every 10,000m³ of source material
2855ea3f-355b-5615-8539-31092763796b | note | Responsible Person - Quality Controller
746a1fa6-63f5-56a3-be7b-4b52bf59d94b | note | Verifying Document - Test Report
df5012b8-e207-5789-afef-6f75758a675d | note | Conduct - Sp or C or S
550c0c5d-045c-5f95-a648-bf5989ed7b3d | note | Produce Record - Sp or S
4c0e9036-0d17-5b36-bf68-e69742bb88fb | note | Approval - E
717400c2-2fa4-5a9b-8522-de2373cdb40a | note | Hold Point Y/N - Y
5de343b7-b3e0-59f2-8f5e-085d4a8c0fdc | signoff | HOLD POINT
113f3833-1e06-55b9-9978-c5d36d530658 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
1b1e7b32-62b3-5cd6-b8e2-633118db5ab0 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
77452450-f407-5684-9c00-40ba728c6d1b | note | Acceptance Criteria - Soaked CBR ≥ 80%
22e6caab-e916-54a3-b33e-2f761ce4f49a | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
acd0c9c3-a9da-5dd6-a9c3-86dce9535d64 | note | Frequency - One test for every 10,000m³ of source material
21c5a3ce-2b78-5227-9aa2-792350ecc6f3 | note | Responsible Person - Quality Controller
acc2f5e6-cc2c-560c-b040-748690dae1a0 | note | Verifying Document - Test Report
3951a8ed-e9cd-560b-bfa9-69191a458506 | note | Conduct - Sp or C or S
2c01c81d-40ec-526e-9a94-19677b31a4fb | note | Produce Record - Sp or S
2d2345a6-ac9b-588f-aafb-46426cbd11f6 | note | Approval - E
9f760686-2ee9-5ca8-90d9-ab3dbd4bbb64 | note | Hold Point Y/N - Y
40c2302f-cce5-5c54-87be-1069cdfc7929 | signoff | HOLD POINT
976c9ab2-336e-5bd7-8941-60563e8cfc82 | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
a6b08d5e-26f9-518d-826f-6e7d5e82517e | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
8db175d2-4ebf-540e-bb5f-403ebccfb398 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
08e8b00b-8e9f-5903-b290-26bf94221926 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
633e26f3-5313-5fe2-968c-aa65d6a8910b | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
68046b98-d319-587e-a0fa-8890181c0c3d | note | Responsible Person - Quality Controller
1905dc3c-3fc4-5742-9f0b-21f3a9ed6591 | note | Verifying Document - Test Report
036ca53c-bd01-58e4-a29e-e3b55bd17154 | note | Conduct - Sp or C or S
3b783366-9968-583a-8475-4747938417d8 | note | Produce Record - Sp or S
2d502b78-8f83-5888-a557-dc91db534b00 | note | Approval - E
bdfa4818-497d-550a-ae34-0ba1f01c3f89 | note | Hold Point Y/N - Y
8c291f12-658c-5f73-81d4-ac64eaf7be26 | signoff | HOLD POINT
21f389de-1666-5508-9d06-5a4f024a4cbe | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
7268c667-acf5-5e09-8365-8585ff0f3ae5 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
984dfd15-5b6e-5841-b943-ac372e717a40 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
bc3518a1-9b56-5d22-8086-d89fb331313e | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
5cc3bf83-1a17-5a5d-bf91-253d3c49d193 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
10372c80-4af1-5caf-b1ce-c72a84209c0f | note | Responsible Person - Quality Controller
71725999-f9f2-58e8-bc1c-4baea4f6dcb9 | note | Verifying Document - Test Report
07cfdda9-5e0a-5018-8fc5-043579eb9471 | note | Conduct - Sp or C or S
3e5a6b87-fb20-5296-9ed2-e9ef6caf5a86 | note | Produce Record - Sp or S
c6f6bc43-7ebd-5c73-be49-51d8c5c66193 | note | Approval - E
b974b838-7fed-582d-89ee-62a86a232900 | note | Hold Point Y/N - Y
f50c0087-ac9f-533c-9dad-f1906513e000 | signoff | HOLD POINT
66a6116e-307f-5697-aa3e-d266fb4bd96f | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
417286bd-56d5-51a1-b358-0fc2784bf202 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
5a81938e-caef-5fdb-a16c-464a9ba01adb | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
94794cda-3a38-5730-89ff-085a7596ba77 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
88306043-a3d8-5b38-9040-3019a16cc17e | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
a23c8447-5e92-55db-b132-71cd8c42e8c6 | note | Responsible Person - Quality Controller
38c6b818-0e65-5fa0-af38-29321542f140 | note | Verifying Document - Test Report
5c69728e-06a9-52a5-b0a9-8afd3b4c6fb7 | note | Conduct - Sp or C or S
523a5c43-a2d8-5f52-9dfc-9ddfccfb6b98 | note | Produce Record - Sp or S
b3941209-3ed6-50bc-8493-9eb9f0420069 | note | Approval - E
dc7b3082-6133-5816-b888-27974716f165 | note | Hold Point Y/N - Y
7ecc9215-ad8b-5530-b3e7-13982b2273e0 | signoff | HOLD POINT
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
35c8bf8d-3e2c-5267-acbd-f9c1e010016d | note | Controlling Documents - TNZ F7 Specification
75b59329-0c18-51d7-8a11-8545978d5d45 | note | Acceptance Criteria - Details on Docket
7f44b657-86e2-524e-a433-2b21dc0a1dab | note | Method - Visual inspection
1d05036d-9c0a-5555-a487-0d5b215b965c | note | Frequency - Per Delivery
aff6850e-d290-5ebe-b8ef-f917736ff17e | note | Responsible Person - Quality Controller
4023d2dc-b554-57c7-96c1-152147a0ceda | note | Verifying Document - MDS
bf5232af-9de3-5076-b5b9-7124f18cea39 | note | Conduct - Sp or S
66060d97-76d9-5495-96ca-c360305fcb94 | note | Produce Record - Sp or S
dbf3349c-f77d-5ad1-9423-35810ef1c3c0 | note | Approval - C
cc6eb961-d008-52e5-9633-a727a4a71952 | note | Witness Point Y/N - Y
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
3d0b4a49-4a8e-5287-905c-0bb04e4aff5b | checkpoint | Production Testing of base course material - OMC/MDD
6252c434-4349-58d5-9287-37008533de42 | note | Controlling Documents - TNZ B/2 section 7.5
d4a0a9f9-1b9a-545d-956c-3c11cccbf84d | note | Acceptance Criteria - To obtain OMC & MDD
00e00edf-519e-55c9-9bf5-b6f46e1bc328 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
432a9a0e-7c78-559f-be21-a6b18474858b | note | Frequency - Once on commencement and each layer at one test per 5000m2
572f3a10-09b0-5eae-b213-d233d79415d9 | note | Responsible Person - Quality Controller
79601b4c-98b0-5af2-adbc-6e01a8ec8b7d | note | Verifying Document - Test report
3f8dbb8b-3258-55e6-8ab9-24858b024e42 | note | Conduct - S or C
5c990d59-672d-5bb3-86be-f4aa6c4c099a | note | Witness - C
8467ed01-2868-5020-a3ef-dd7d3d506a8e | note | Produce Record - S or C
5b323fe9-b466-518c-90ee-ea17bb1b3e9e | note | Approval - C
d3e4c937-f668-58b8-8b16-5ee4a0e9d198 | note | Witness Point Y/N - Y
a3292128-f0c8-5f0d-8602-1c0f6463cdf8 | checkpoint | Production Testing of base course material - Solid Density
8c4339b5-a5f1-592b-9e49-d91bb905a371 | note | Controlling Documents - TNZ B/2 section 7.5
3c3dba30-0240-5341-9862-cd657de9f760 | note | Acceptance Criteria - For info. and use in MDD calculation
4fc9dfb5-1b40-51b9-bbd2-6e16856117e2 | note | Method - NZS 4407; test 3.7.1
67b04313-83b9-5a61-92ce-ed09d338b5b4 | note | Frequency - Once on commencement and if any materials change
630f981d-fde5-5587-a81c-76687d6dfed2 | note | Responsible Person - Quality Controller
764e4999-9844-50ec-b181-230d3f68acf4 | note | Verifying Document - Test report
4a4077ea-c08c-53db-9b72-b099c5e5e80e | note | Conduct - S or C
629e32a8-419b-544c-8ca2-d56df16aeae8 | note | Witness - C
97562277-b848-576f-965c-647b46a61d0a | note | Produce Record - S or C
6e57afeb-5d41-5185-b8ac-953ce9fcbb56 | note | Approval - C
1afa3e15-34f5-5668-baa5-e6b799618c47 | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
e8793f25-e244-549a-b9a5-512e359581a7 | note | Controlling Documents - Reference from Project Drawings
68685ef9-40d1-5f24-af14-8d969fde89ac | note | Method - Survey/Mobile Roads, Marks with Dazzle
3bacb3a7-fe7a-5e3b-bff0-f0833a9e2ea2 | note | Frequency - Chainages for every different pavement sections
0dbc592b-ec7e-5c47-8950-796c6513a834 | note | Responsible Person - Subcontractor/ Engineer
d9442a94-5361-560d-9fd7-ad85f4b41163 | note | Verifying Document - Construction drawings
ed6c2424-b035-52d7-a734-935148c7c769 | note | Conduct - S or C
e037db13-a5a4-5d89-a3cb-6f78e5a65934 | note | Witness - C
19dafc7c-82b2-543a-815e-08555fce4875 | note | Produce Record - S or C
b2a9eafa-a315-5b19-b836-865eba69c548 | note | Approval - C
a23219ab-91b3-5e13-b4ce-1f98a49f1d5e | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
8e6e32ac-c4ce-5dd1-a9c9-ff870554fb5f | note | Controlling Documents - Site specifics to be confirmed
0a5f95f8-966b-5f74-8081-0ee226ede856 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
49a33be6-da9c-55fc-aec4-d069f9c7a2f8 | note | Method - Scala Penetrometer on Excavation Floor
97efae73-0016-5d50-8670-7c24fc4ed3b2 | note | Frequency - As required
ff8f61c1-7d70-5fbe-9b8a-8cdccc2fee94 | note | Responsible Person - Quality Controller
ccc8c4e8-d6ce-5057-a5c9-39db702b2723 | note | Verifying Document - Agreed treatment plan
94466017-bd08-5e98-a7db-a102c703286d | note | Conduct - S
090bcf84-5651-570d-86f6-da490a567268 | note | Witness - C
bd62ff22-51cb-574f-a6b0-12ec118c313a | note | Produce Record - S
10d28421-b59e-5c9d-8a0f-a70cf79766c5 | note | Approval - E
1ffe0f06-4759-5b96-a338-7d67f1f15bc0 | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
2cf4a2ab-732e-58bb-9e4e-8f20e9d442ce | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
423d0a9c-b399-56e9-94aa-dd315952f02e | note | Acceptance Criteria - 250mm deep unless specified
bf97a9cb-4013-5f2a-91e9-59d4e7f021e0 | note | Method - Visual inspection
bfbf7315-a5ea-5d79-8fa2-fc96de4ef88a | note | Frequency - As required
8c158808-460a-52a7-b181-5fc1c303e4c0 | note | Responsible Person - Quality Controller
1e5be3d7-6622-5b15-8fbe-191440e149f4 | note | Verifying Document - Dig out site records/ Asbuilt
3116a10e-3549-5d2c-8fa6-fdaaa431ecc7 | note | Conduct - S
30772615-37ef-5bbd-b300-efd1bd92cf3d | note | Witness - C
2f163d2c-5292-5725-b490-7b3f959b84b4 | note | Produce Record - S
0fa3c301-96e5-54da-9880-5dbfc2b9ef22 | note | Approval - C
49649748-e06e-563d-955b-7abdd9c0cc4d | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
3d4dfad8-f1a4-5cbc-a4c4-537c3003ea85 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
3f3816bf-603b-539b-af62-3bcaedd05d64 | note | Acceptance Criteria - Scala > 3 blows per 100mm
76d9097b-4dc8-5e62-9f6d-71f38f4118ab | note | Method - Scala Penetrometer test on base of digout
ac69ae24-8bd4-5014-bdb5-88491f6b0524 | note | Frequency - As required depending on size of digout
adc50920-8277-5589-82e2-df7ec014c870 | note | Responsible Person - Quality Controller
7a2ee91d-20dd-5bdb-9cb2-fa9ece98103c | note | Verifying Document - Test report
ad83cc5f-4c1b-5cbd-8b4a-5f6217508bfb | note | Conduct - S or C
4bc218fc-46a1-59ad-81e3-9885cc895e1f | note | Witness - C
342f6671-d3e9-5b8f-bd98-51907541d739 | note | Produce Record - S or C
d9ef975f-07de-5386-926b-3a5f76a433df | note | Approval - E
61211475-c1d9-5738-b44a-d1a02308f316 | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
f278ea2c-8722-536d-9ac3-78e9adba6767 | note | Controlling Documents - TNZ F7 Specification
fabfa0a5-50ea-5034-8f5f-0b5cdae002b0 | note | Acceptance Criteria - Meet TNZ F7 Spec.
61c0944f-8b74-54b1-9069-21e9d1faf221 | note | Method - Visual inspection
781ee06a-b956-5e67-9dc3-2a9741a31e4f | note | Frequency - Per Delivery
ac8ecc12-73cd-5e0a-aa87-21817f5b09f3 | note | Responsible Person - Quality Controller
2417bc52-a9be-53b3-b114-44ba7a78935f | note | Verifying Document - Certificate of conformance
9f66d707-b63b-5350-9041-256df3fcb201 | note | Conduct - Sp or S
b25b5907-d3a2-5f31-9c69-443c36711eff | note | Produce Record - C
0cd6f476-7a69-5b21-a2b5-cf960906abd1 | note | Approval - C
5391173c-3ef1-558c-a3b2-443237bd7d88 | note | Witness Point Y/N - Y
7d2f776e-810e-556a-bdbf-14178fa90a28 | checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer(if rqd)
a7356183-fe00-5fba-b053-b6a6e117c8c2 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
2b77f723-2d1e-59ca-8c61-ff02336e6d0f | note | Acceptance Criteria - On the list of approved materials/suppliers
3ab7d448-cd58-568e-b6e6-8c43a123f79d | note | Method - Visual inspection
0c6a7a67-87a6-5e8a-9afe-03c621dccc62 | note | Frequency - Per Delivery
ba7fc88c-0c8f-58e0-b25d-889b8c23d18f | note | Responsible Person - Quality Controller
91bc491a-587a-5f8d-82b3-aaf4507cdd1d | note | Verifying Document - Certificate of conformance
26222acb-ea2a-55ce-906b-2737607a398a | note | Conduct - Sp or S
275610b3-cea4-532b-89ee-9bdab8775841 | note | Produce Record - C
1f50ff6a-9e2f-570e-a3f2-43d71b40a5e1 | note | Approval - C
9ca9fcf7-3988-50d1-929f-f6052b3cf088 | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
f585fdfc-91e3-549d-b1e1-cf46be38310f | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
1732d7c9-5b53-5292-bf9f-bdacc6dbd56d | note | Acceptance Criteria - Clegg value > 45
2da36249-1c4e-5363-b3b5-f9496e68e65e | note | Method - Clegg Test
c597860f-8dc6-5954-bad2-efdaa360e7cf | note | Frequency - Min. 2 per digout
b7c0422c-e8f8-56cd-a79c-f2f28076d7db | note | Responsible Person - Quality Controller
69647673-f5de-5c51-b0af-876540bdc7b8 | note | Verifying Document - Test report
393048e6-3ad5-5513-a19b-ceca5b5842a5 | note | Conduct - S/C
68d7bd5c-08de-5779-8567-38abe0ea5187 | note | Witness - C
3dd0ea73-7f71-5713-976c-19921187f8f5 | note | Produce Record - S/C
ed2dbf72-16de-59ef-b6ed-9670bd78e2ba | note | Approval - E
922b668e-7f2b-5965-96e2-f86d986fbe1a | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
eeb50d65-64ce-572e-8456-9dd1f3e00c42 | checkpoint | Place M/4 AP40 Basecourse Material
e525328b-9850-54c8-89c5-d47be427f9e7 | note | Controlling Documents - TNZ B/2 section 7.2
8e8ca409-c9ad-5470-a3af-de79d40ce2d8 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
712ccd34-392c-501f-b502-d0c4f97ba918 | note | Method - Visual Inspection
ff9aff39-311f-5142-ac0c-525dc9cd5d21 | note | Frequency - On completion of placement
a0fa7c5e-7a85-58f7-bb9c-fe5f7349b1c1 | note | Responsible Person - Quality Controller
99868cad-00e9-5ecd-bf1c-4edee0c2585e | note | Verifying Document - Photographs and Daily Site Record
b7072260-9e12-5cbf-95ca-24ade6822e6d | note | Conduct - S or C
918d268a-980d-5cec-9ced-e83ba591e076 | note | Produce Record - S or C
830ee424-3c16-5591-8cdd-ba3d68bd055f | note | Approval - C
35b59076-f779-5dff-96f3-6b5b40ecaba3 | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
9d591724-e25c-5c44-a4a9-0e5a78338ff4 | note | Controlling Documents - TNZ B/2 section 7.5
4d25134d-d4e9-5f6f-827d-3617b3f0b282 | note | Acceptance Criteria - 90-100% OWC
2552624c-2bed-5e68-8898-7aa48be2dc81 | note | Method - Nuclear Densometer Testing prior to Stabilisation
da754899-3ab9-5179-bf4f-f6f323f5c824 | note | Frequency - ≥1 per 1000m² lot
adb28918-743e-5c13-803f-5014d0e750e5 | note | Responsible Person - Quality Controller
0acf425f-ca44-535d-ac6d-618b75540b7b | note | Verifying Document - NDM Record
8d8b5408-6187-539c-8753-d783fe27cebf | note | Conduct - S or C
b073688b-9e48-56da-8c92-73f5d48aec71 | note | Produce Record - S or C
c4ac1b9a-209d-5033-b4c0-d06f7a34f6e6 | note | Approval - C
ff0eb303-4e63-5cd2-a6fb-522a5ad1018f | note | Witness Point Y/N - Y
b2669c88-ac51-56ca-b8c1-ca203b10eac4 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
1a29ae08-90e4-5132-ade7-ddff893c0fc6 | note | Controlling Documents - TNZ B/2 section 7.5
418738ed-0806-5d7e-9cc2-3c632005657b | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
8ab0f10d-67ca-584f-9dfb-64609c8a02f9 | note | Method - Plateau Density Testing
82d8763a-4932-5a99-a146-db8741ae5791 | note | Frequency - 1 time, or additional tests when material changes visually
dbaeb20f-3a72-58c3-ba36-e907ba27ab65 | note | Responsible Person - Supervisor
ca4b65dd-0c1c-5dc6-9d2e-b9b2e10e6000 | note | Verifying Document - Test record
ef9584f8-6f86-5e67-9eff-6fec4455b9df | note | Conduct - S or C
b9486c83-0f2a-5632-8573-fdeb0046d3e1 | note | Produce Record - S or C
5ba65fe4-4522-5063-b8bd-1be954fb1a79 | note | Approval - C
6562d0fe-3ef2-58c4-8f18-c05947447ff0 | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
f7d801a2-56d3-59ad-b9b8-748e9d9d038d | note | Controlling Documents - TNZ B/2 section 7.5
e8444794-fdd3-5054-9f37-e54f05e1377e | note | Acceptance Criteria - To provide MDD for NDM testing
fdeb6eb5-7f1c-52a3-9193-04eb92197211 | note | Method - Plateau Density Testing
a64ca076-d87a-5454-a46c-886bc3536061 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
88dfe2eb-74d0-5e79-b829-13700ea57a3d | note | Responsible Person - Quality Controller
ab7234fc-f152-5651-bab9-db327a17cd5a | note | Verifying Document - Test Record
b4ac3faf-ba14-585a-b0c9-836a17a4397d | note | Conduct - S or C
ad97aeb7-8f02-59df-b8d4-f9061308f23c | note | Produce Record - S or C
d92a516f-6718-54a1-b78f-68aea679715e | note | Approval - E
55aa2abc-f9fc-5e19-b1c2-2abaf99088fc | note | Witness Point Y/N - Y
1b96c1cd-dc03-50d2-9eeb-7acf490a611e | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
56f8bc94-8243-5b8e-b033-120495bb6d68 | note | Controlling Documents - TNZ B/2 section 7.6
b6d9c1d8-8546-5e9c-bd81-36f63f110a34 | note | Acceptance Criteria - To provide MDD for NDM testing
ca09810e-dd1c-559b-ab3e-fbb32b6a50a0 | note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
e3d68ce7-5566-5e79-b6ba-f3e264a1ccaa | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
b3651360-eeb5-5635-ab5a-b19bac52cd23 | note | Responsible Person - Quality Controller
4aa5ad36-8775-5bf4-ae9b-e483519a614f | note | Verifying Document - Test Record
5b7084d1-e166-5904-8380-ceceac198009 | note | Conduct - S or C
e2a84ff4-5cc3-5d1e-8945-b52f717153ad | note | Produce Record - S or C
07efa7a6-1527-5d3f-bce0-3f57c64e8d3e | note | Approval - C
aedab65a-8d6b-5a33-b7e9-bb7cf704ec57 | note | Witness Point Y/N - Y
9b641378-7dcd-5a3d-807c-a31562803710 | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
daadcf79-0141-53c1-aadd-c32d26cbb2f8 | note | Controlling Documents - TNZ B/2 section 7.6
af9134dc-c4f3-5e04-a8e1-381c50150e22 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
2b04338d-1f5b-587b-8c8b-8a3a4a9894a9 | note | Method - Plateau Density Testing, Lab. MDD
ebea0b36-2f97-50a0-9fe7-c65bdf754838 | note | Frequency - At commencement of construction and whenever materials change
0c97a646-5ad3-523a-9a26-2ec1e7ecf1c2 | note | Responsible Person - Quality Controller, Engineer
3f354415-bdd1-5d13-9759-6fdec1158382 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
7645a7cb-edc7-50ea-a288-e8f2c75fbad6 | note | Conduct - S or C
118e2085-b7f6-59e6-955c-116b41e218dd | note | Produce Record - S or C
f9406f4c-b415-52f2-908f-6427423d706c | note | Approval - E
b52f94b0-0cc7-59bc-b3e7-961dcbafcd39 | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
5cb21cc2-fc53-569d-a96e-8bf1c08da81f | note | Controlling Documents - TNZ B/2 section 7.6
b3c16422-10f0-51ad-a580-b4aa9b479293 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
9a219e89-942b-58d4-8244-47d1c7a29f61 | note | Method - Nuclear Densometer Testing
8044a213-6ec5-5586-b091-64517ee0c670 | note | Frequency - ≥ 5 tests per 1000m² lot
10946b06-e31c-5f5a-9efc-4047fa9149f0 | note | Responsible Person - Quality Controller
955f8187-ca3e-51c8-a639-4c58fe713bb9 | note | Verifying Document - NDM Record
658fb594-af6e-5561-b53e-735ed2abb04b | note | Conduct - S or C
1fdb9e9b-d46e-5759-80fe-727a4442a15f | note | Produce Record - S or C
5a33b1a2-ffa2-59f9-aa83-5741e1f573b1 | note | Approval - E
b8053cf4-075c-5199-a540-23d316a871e1 | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
7ac45865-2614-5682-bfc3-233e3ed0f080 | note | Controlling Documents - TNZ B/2 section 7.7
3007e1e6-9b11-55c2-9e14-1a20bd3752b9 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
21bd0476-26ab-57ad-9e43-faa2549a437b | note | Method - 3m Straight Edge
268126be-817c-5a13-b28b-1ec32958c3f2 | note | Frequency - during construction and prior to seal
2d20fc04-42d0-57f4-b378-d636cbf13db1 | note | Responsible Person - Supervisor
dbf97289-fad7-594e-92e3-636f17213a7b | note | Verifying Document - Photographs
d4b858f7-e463-5386-ac3c-d64907e61d77 | note | Conduct - S or C
efec639e-a9d0-5501-bdf9-826ab2d33af6 | note | Witness - C and E
d7433683-7563-56ba-9e77-5c494cc8e664 | note | Produce Record - S or C
5fa310a6-5b03-5ffd-b352-0144eb10bec6 | note | Approval - E
f0a13fb5-c21b-5c87-a338-442287bdf619 | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
4075c135-6a4c-5542-9d18-fb19b70266e3 | note | Controlling Documents - TNZ B/2 section 5.1
0d122420-1d2f-590d-97d2-ae5923012ddd | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
5c9cd700-ea5a-532e-8de3-1e2a21163586 | note | Method - 3m straight edge or Survey Asbuilt
518a71e4-aa14-5b1d-8d10-9b7ccd28b23c | note | Frequency - during construction and prior to seal
2fea4e75-6dd4-574d-bd7b-5ee260ff139c | note | Responsible Person - Supervisor
53a12e31-8516-5fa2-9d33-c7813f608826 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
c3b1fbef-5ed7-5e4a-acf2-9d7c2eca7769 | note | Conduct - S or C
14e2951e-4554-5a74-b925-94b37d8ec090 | note | Witness - C and E
e6a540de-4aac-5cfb-8faa-46fdaba008d4 | note | Produce Record - S or C
7e38f3a4-3800-5e99-8411-27505d52633d | note | Approval - E
c2415c4a-f09d-5cb6-a95d-2ca968acebee | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
6afc10e4-e511-5497-8a5e-6198b4fc539c | note | Controlling Documents - TNZ B/2 section 7.8
db512c41-816f-587c-8272-318fefc67a6b | note | Acceptance Criteria - Tightly bound matrix post sweep
392514e6-5ea8-5c27-a352-c917caf2e945 | note | Method - Visual inpsection
b59b70f7-19d7-5e21-bf53-485e658356d7 | note | Frequency - prior to seal
a4814e1e-e702-5e74-a534-c5fefa6f49bf | note | Responsible Person - Supervisor
56da7020-ce1f-560c-af3f-342ce47731bb | note | Verifying Document - Pre-seal inspection sheet
f7293da9-e360-5176-94aa-8706f5138f23 | note | Conduct - S or C
3736a829-2532-5687-ba0e-5c35954e39b8 | note | Witness - C and E
2db4a45c-3cf3-5a20-b872-fbe8139b5717 | note | Produce Record - S or C
5afcb950-6808-5d3f-bdb0-1c482a114ddb | note | Approval - E
2b35e38a-2c12-5797-812b-bdaa15b0d80a | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
97575d7d-edf1-507d-8d1c-a8ba7a4f9a08 | note | Controlling Documents - TNZ B/2 section 12
506291e9-9132-52aa-a246-f18d93fae6d8 | note | Acceptance Criteria - ≤80%, however 65% is ideal
35db170c-4445-5d79-a216-fe13c4c3c365 | note | Method - Nuclear Densometer Testing
0a4e95ac-d3b9-58ac-9b10-6a3176f76abe | note | Frequency - ≥5 tests per 1000m² lot
bc9a5b7d-554d-5382-958f-2c5f4b670cf2 | note | Responsible Person - Quality Controller
bda60633-7be9-55d8-b8b9-9ed6d9a62a14 | note | Verifying Document - NDM Record
7fcb48f2-4afd-558e-8fed-f6de1546839a | note | Conduct - S or C
00a748dc-984e-57d1-b35e-7090fffff629 | note | Witness - C and E
47dfc895-7474-5e85-b8e1-0a17e8643c38 | note | Produce Record - S or C
3f2bf003-b287-5340-bd4a-f1748b7f4307 | note | Approval - E
0bc9dfb0-b093-59ed-abca-9ed5ef23bd74 | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
bca3a7ec-0ed4-5114-a06b-d729564c6398 | note | Controlling Documents - (TNZ B/2 section 7.7) NZTA Maintainence specification section 6.1.2
8aaa8cd1-cb79-54c1-ad64-4fa24a26383f | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
a4c3cce0-c88f-5999-a891-c44baaa1a111 | note | Method - NZTA Maintainence specification section 6.1.2
1be170ba-2b7d-58d1-8601-ce91dbb537bb | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
7c848079-8c1c-57aa-a2c4-534fc1a6ddd6 | note | Responsible Person - Quality Controller
fba66798-4812-5188-a1d9-067da8065d45 | note | Verifying Document - Test Records
5b28b228-eed2-54be-a95c-9873790aaf9a | note | Conduct - S or C
19c06d8c-8957-5ec5-9512-c0e90c5d8809 | note | Witness - C and E
761415bb-4b65-5fb7-8d87-a59eeecea2c9 | note | Produce Record - S or C
6879d5e7-c481-538a-a028-41e5ca27c040 | note | Approval - E
3b57b407-a591-52ee-85c0-7288a27952e9 | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
f6ac91d4-5c0b-53d1-9e4e-00bc03939ff3 | section | 5. Chip Sealing - 5.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
dd4cd97a-84af-5dbe-993d-6ac07bf2326c | note | Controlling Documents - TNZ M/1
d395469a-d161-5f75-b312-7efe3259d6c7 | note | Acceptance Criteria - Table 1
9df09715-c172-5b41-8765-327942225bf6 | note | Method - Property Test
2402a37c-20e6-5f58-a339-06efe2685a53 | note | Frequency - Annual
7b60118e-a7ee-5162-b50c-b60b70927eee | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
2fb667bd-83ce-5d1c-b4d8-164ac89b6b05 | note | Verifying Document - IANZ Report's
9066f278-4417-5c76-bacf-1c07ea8fe36f | note | Conduct - C
412770dd-eb41-5b68-a7a7-4cca150d7be7 | note | Produce Record - C
68a7ab86-181c-51cf-b546-8ea0792b50b0 | note | Approval - C
2c1618d5-f1d1-551b-91e8-287fe8f5c2eb | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
a2a3f69d-7371-5225-b42b-0f2681075e2e | note | Controlling Documents - Higgins Internal Specification
0996bcbd-b9a2-5e74-91c7-d993cfb283ec | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
5b03fd54-370b-516a-99b8-09d7e6cb02c5 | note | Method - Property Test
a55f2969-55fc-5638-83fe-87f4be8a0eca | note | Frequency - 1/100,000 litres supplied
f245fbfe-d974-5225-96b1-73092ebc8e47 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
7594c718-1073-5141-a48f-2db3cc3126ff | note | Verifying Document - IANZ Report's
d09f1c61-abe9-5be3-9819-62b4a01fc39a | note | Conduct - C
f8836a92-679e-522d-8bb9-81a5870b2d50 | note | Produce Record - C
f31b7ee3-190b-5394-9481-6cd633cd06ec | note | Approval - C
04381ab2-2fdc-5188-8fad-04914ff95058 | note | Witness Point Y/N - Y
271433f5-90db-5716-947f-66b53e064a88 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
b612cc08-c32d-572f-a328-8ff5117c4c9f | note | Controlling Documents - TNZ M6, RNZ 9805:2009
2677f6ca-11ae-5aae-99ea-b17cdf20c41a | note | Acceptance Criteria - <10% fines under 230kN minimum
a68bc84a-3fec-513f-af6e-def9d8418b65 | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
aa9abf61-aee8-502f-a355-9549e9505eeb | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
fd57ea0f-8825-5988-9058-be92eda7a214 | note | Responsible Person - Surfacing Project Manager
3a7f5248-77e5-5534-8c81-49dd4694b6ea | note | Verifying Document - IANZ Report's
fef025e8-ff08-5088-b092-225061e01660 | note | Conduct - C
2a9cf07a-40f5-523a-b740-a39403c7f30b | note | Produce Record - C
0f2f442a-2b5b-574e-b1ad-be46e498b699 | note | Approval - E
cbe517d5-a125-5f2d-9f51-7200be7b57f8 | note | Hold Point Y/N - Y
6001235b-048c-5705-ab46-316e6fddaf77 | signoff | HOLD POINT
b5105286-fa50-5f37-8ad8-ff00dc521109 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
c5b218f7-9dd8-548f-b6b4-bd9bcc1dddf2 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
def06ef6-24dd-5c2f-8c34-f42f3b871a60 | note | Acceptance Criteria - AA or BA
f6a4d5c5-2223-5488-b272-c9663d6da774 | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
d551eba0-d4d3-5c75-89dd-0ad4efb04046 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
2bea4bf9-7ad2-5cda-9aaf-51e78b10a825 | note | Responsible Person - Surfacing Project Manager
6a3b82b2-0f4e-5da7-b7a7-4f07e148a16a | note | Verifying Document - IANZ Report's
e9535aad-ece6-5fb1-a52c-ff59c93dcbf0 | note | Conduct - C
e1ad6a6a-befd-57c7-a85b-1b17511c5533 | note | Produce Record - C
f7464b01-24a4-5dc0-a531-9f28f35d6d7e | note | Approval - E
9c5b54a5-c08e-5f59-93a3-5c59edc4f53d | note | Hold Point Y/N - Y
d36fb53c-673d-5ad9-bcd6-d21d23c23bfc | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
82f90eb8-e93b-5915-9be6-5257780a5a48 | note | Controlling Documents - NZTA T/10
e3f27a48-93c0-58cf-9d0a-190f15193430 | note | Acceptance Criteria - Meet Skid performance Requirement
3bb4cb0b-7243-5228-9fe8-c42d312ea47d | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
c89f5028-6ca1-504f-99a4-15b4d599d885 | note | Frequency - Each Site
1ee62058-3520-5133-8789-67775851b0b9 | note | Responsible Person - Surfacing Project Manager
929bf1d6-c985-5e76-abaf-6a7a0d4efe65 | note | Verifying Document - IANZ Report's
6250794c-f74a-5744-b75f-26d1ffde57b4 | note | Conduct - C
cd631a06-fc8b-5ac3-bca7-04f86f68626c | note | Produce Record - C
de209f36-4629-533e-9dd4-100f05486900 | note | Approval - E
0964cf0e-3db6-58ea-b9c7-f1fe5ab06f2d | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
b35775f2-0787-5a4d-8cb9-d4468d236e7e | note | Controlling Documents - NZTA P/17, M/6
ee65247e-bdbd-516a-a4df-2dac569216ad | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
01a2514e-a425-5de9-99b8-f4522146671c | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
e3f1357b-cbfe-513e-935b-31d013ec6401 | note | Frequency - Per Stockpile
87f14f76-f7de-5eb6-96dd-3896cba4158d | note | ○ <100m3 - 1 Sample
b27ac6d0-c731-5162-8d2e-e6bf6c1951c2 | note | ○ 100-500m3 - 2 Samples
08d5a140-9efc-5691-9a36-12be155af740 | note | ○ >500m3 - 3 Samples
858aa5c4-d469-5b05-aefb-6908a9af489c | note | Responsible Person - Surfacing Project Manager
c251c15c-caea-5584-9f44-68ae577326b1 | note | Verifying Document - IANZ Report's
4d448ec2-1dae-51e5-a9fb-07ddf073898b | note | Conduct - C
c67aa2b2-502f-5af9-9180-24eddd74bda7 | note | Produce Record - C
ec0d4855-657c-5ffb-a49a-91e4127b3056 | note | Approval - E
7004d593-f067-5eaa-a8db-88d310b94892 | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
9d999989-653e-575b-9807-567e954ab07d | note | Controlling Documents - NZTA P/17, M/6
aa5c9a41-3ee4-54be-bc5e-51ede55e6ef5 | note | Acceptance Criteria - As per Table 3 NZTA M/6
63073cbf-0436-5585-85a7-a8841726dcb6 | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
12469a86-094e-5330-8d9a-df430416f7ab | note | Frequency - Per Stockpile
20a44408-62b1-5141-bfb3-a3e13c54c1d8 | note | ○ <100m3 - 1 Sample
4bef86f0-9ae7-5e58-92a7-52f41bb5a6ee | note | ○ 100-500m3 - 2 Samples
acce9602-1197-5ba6-af88-333509e4526f | note | ○ >500m3 - 3 Samples
ddb1e252-1ea2-559d-807e-293f99a5446b | note | Responsible Person - Surfacing Project Manager
5ed9db79-1707-5201-b5b4-a8163041f21f | note | Verifying Document - IANZ Report's
9215d360-228d-5e26-a649-f8b58acbde1a | note | Conduct - C
a9c5cd46-9ac1-5d7e-b343-c716546d52e8 | note | Produce Record - C
d026b8ae-a4a9-563b-962f-f5c74e6b2bcf | note | Approval - E
8d11bdea-eae1-53f4-b3f4-8a24e7a5aaf5 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
fef358e4-4151-5549-bca8-77826ae53e63 | note | Controlling Documents - NZTA P/17, M/6
9aa4d4b5-554f-5390-bf7f-a69326f05275 | note | Acceptance Criteria - Min. 98%
abdf123f-6f3d-5dcf-8a0c-67e3c70dac8a | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
69be65d0-4e39-5ebd-b8ee-cd36e5e96b18 | note | Frequency - Per Stockpile
6d85e1a1-4d24-53b5-8747-52fa85f4216f | note | ○ <100m3 - 1 Sample
61769f63-9222-58e6-9c84-6589b203e198 | note | ○ 100-500m3 - 2 Samples
9c8d9abc-f7ec-525c-90b2-9215eab7e2ad | note | ○ >500m3 - 3 Samples
7ba816b7-013a-5545-95f4-6a6356bfe7ba | note | Responsible Person - Surfacing Project Manager
975b9fcc-89e6-5946-a2c4-14e97a8a1c5f | note | Verifying Document - IANZ Report's
23e3d69b-f628-5778-96fc-a97bab1c5af4 | note | Conduct - C
b3660fb3-5806-5755-a4ea-577cf240d724 | note | Produce Record - C
bc284c4a-ffa6-5f28-b1cf-7d86acff3c73 | note | Approval - E
3c557a56-5845-51f7-8e83-4d37e53be570 | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
89f17814-de41-5eaa-82e7-802f3e4d99d6 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
03ba49cb-3055-5e18-93f8-de44951f10ec | note | Acceptance Criteria - Client Approval
d107c28c-024a-5b32-afa5-9ef1e96bf202 | note | Method - Review
6cd370cb-74f5-5f93-b562-b3da502e58a7 | note | Frequency - Annual
f6b3d799-3e4b-5156-b01c-52a9a81c773a | note | Responsible Person - Surfacing Project Manager
64357aca-f866-5624-8293-3e802786cbea | note | Verifying Document - EBOP NOC Design Report Acceptance
639b0986-d476-56d4-bbf3-985a15c5332d | note | Conduct - C
e0be65e0-12b4-5fca-85c4-b44086158d76 | note | Produce Record - C
812d1477-e1f8-51b5-b93d-d81915fb0040 | note | Approval - E
44de4d34-3adf-5274-82ec-c0d94986b548 | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
2d90825f-40a1-55cc-9369-13e616f644fc | section | 5. Chip Sealing - 5.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
26acf77c-dcf0-5d09-9b8c-28a0022a12b1 | note | Controlling Documents - EBOP NOC Design Report
a898701b-5629-59d4-bab1-cee9acb21b24 | note | Acceptance Criteria - Visual Inspection
d609c32d-4742-567a-8a2a-52fa120ac441 | note | Method - Visual
1cb01a8c-8a57-57e3-8772-ed44dbe7dc64 | note | Frequency - Prior to start sealing each site
4eadf601-b60b-5252-975b-3977a14668ad | note | Responsible Person - Surfacing Supervisor
511433d6-6807-552d-9de9-73824b658687 | note | Verifying Document - Chip Sealing Quality and Site Record
c806b0a7-1741-51bf-a1a5-d808dd4f9c7c | note | Conduct - C
9875bf2e-22de-5129-a33f-f41dd1b57e2f | note | Produce Record - C
30f954bd-2fbe-50ae-b894-3a60a6b53b1d | note | Approval - C
a5b57988-2125-543c-8fcf-2db06272ea53 | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
25d42941-3bc6-581e-b76d-0b03379e4ddc | note | Controlling Documents - P/17
2b49ff95-e705-564c-accd-ef01522d5360 | note | Acceptance Criteria - Visual Inspection
31368fb8-c0dd-58cc-9ce8-ccb47fad5e14 | note | Method - Visual
9c10b0a1-36d3-52fc-8184-c1dc36b73cfe | note | Frequency - Each site, prior to start of sealing
30f14949-fce5-52f9-8d4d-ce932ffb2417 | note | Responsible Person - Surfacing Supervisor
3a0c59b7-848b-56cf-b241-1bbc58cf53b2 | note | Verifying Document - Chip Sealing Quality and Site Record
f75d61bb-d05a-5ef6-b6a0-97ee7ae48346 | note | Conduct - C
6b64f40e-0f16-5043-b1b0-888000f81b27 | note | Produce Record - C
d402b45f-70c1-5ca7-8b4f-b12a1a1f2c77 | note | Approval - C
4068b24e-4e7c-5be0-b02c-c1160d2bddd5 | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
c417d4d1-bcf0-5a02-a926-6986dd33407f | note | Controlling Documents - N/A
557742d1-cb7e-5a23-b550-2f1d12456a88 | note | Acceptance Criteria - Visual Inspection
3c189dce-30e9-5553-ad1b-b52aeb6582ce | note | Method - Visual
c1c5e9b8-5696-5d83-b39b-6e987a2ff19d | note | Frequency - Each site, prior to start of sealing
eb6b351e-de7e-5094-b263-863551b0dbf1 | note | Responsible Person - Surfacing Supervisor
795c979f-4f17-5959-bb1e-7d4c7c69718d | note | Verifying Document - Chip Sealing Quality and Site Record
b6ef148a-93e9-5941-b648-5ee5b484d7fc | note | Conduct - C
6d0c3174-0b8d-5e9e-841c-89b6f9d1ed02 | note | Produce Record - C
5b6fcffc-c5d8-597e-9498-5311738f9fea | note | Approval - C
3277b782-cf51-5747-b979-f5b749df8778 | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
ba54a58a-9a3e-59ff-b15c-0424bd9d3627 | note | Controlling Documents - EBOP NOC Design Report
b1bffc1d-7f39-5c82-b9fe-9310b93db1f0 | note | Acceptance Criteria - Details/chip correct
0c56dca5-e288-572d-8480-cfbd31128ee1 | note | Method - Visual
ceb8e9cc-f55f-5481-aa8e-cfc225d2277d | note | Frequency - Each Site
a88fe71f-9797-5260-8d47-8965be75f7d9 | note | Responsible Person - Surfacing Supervisor
721f8b3c-4317-582a-92ae-f07ff821b022 | note | Verifying Document - Chip Sealing Quality and Site Record
51495d5f-277f-5b94-8d32-a60cd695aec0 | note | Conduct - C
f57410e8-6bdd-52e5-b4a5-0e1ba4d045c4 | note | Produce Record - C
685a54af-a8a6-558a-bb7f-bf33b89af8e9 | note | Approval - C
fefdba9f-4760-55e6-a91b-189b2f76c122 | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
a6fc0d02-a81c-511b-a5d4-402ea3123296 | note | Controlling Documents - RNZ 9803_0513
5d93b935-7299-5cc3-8809-c0c9e7d8b195 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
ec8404f7-c0b3-5640-b35b-b4dd097822ab | note | Method - Sample and test
a17b6816-7402-5c61-906c-d22ac66e7009 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
612b1cde-c8b7-5098-a505-c435f0987b56 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
9ab69edf-86eb-5847-ba11-77ef13e00894 | note | Verifying Document - IANZ Report's
264d1b41-c3e1-5129-8bc4-2b74455183f6 | note | Conduct - C
07e934bb-0522-56e0-974d-938c16e47916 | note | Produce Record - C
02760a1f-09fc-5531-9ab4-11838bc57c28 | note | Approval - C
5b8b6462-a3f9-5ce3-8a78-a7614bcac864 | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
1eb0dba5-db03-5074-887c-df3d09667e64 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
3754f791-cf86-5ad3-90cf-f8a3f89123fd | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
8f48d830-df7c-58d8-80ee-e9c8902b2440 | note | Method - Test, Review
66367920-5920-5304-b7ba-b07eee438052 | note | Frequency - Per Sprayer, Per Site
ceeb6aa9-34da-57d3-9c10-0f57350fca4f | note | Responsible Person - Surfacing Supervisor
5c1cb51d-5aa1-5857-8678-31c9c0166f7d | note | Verifying Document - E/2 Certificate. Spray Sheets
be105b44-97a2-59fd-b77a-73461cb8a863 | note | Conduct - C
42e662d0-3b93-5352-9c35-303c0dec4401 | note | Produce Record - C
42138750-884b-5fd5-a7e5-90d568246b2e | note | Approval - C
3375f441-62d5-5721-b806-f6b280106509 | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
7b0a6389-4c5b-55bb-9ccf-d68ceff402ad | note | Controlling Documents - Chipsealing in NewZealand
1687fdad-6a7a-5aa8-8d2e-5211d0b26a3a | note | Acceptance Criteria - As per Chipping Guide
29d14b6b-0f23-53ed-a23d-11b1ec80982f | note | Method - Visual
10e4cd84-e42f-5c12-827a-a1729a194112 | note | Frequency - Each Site
51401d6d-f66b-5b68-87fc-325f81bf4ce3 | note | Responsible Person - Surfacing Supervisor
002c8fd5-a108-5474-af11-ae21c4d3a47a | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
5b1be743-2b14-5153-bdc9-c20c7512c3ba | note | Conduct - C
1af83243-7d65-5f02-a18b-8538d6850759 | note | Produce Record - C
f6dec7ca-244c-5d56-8ec5-f1e68a3fd55d | note | Approval - C
f6c4946a-092e-5525-9871-477b3e89a049 | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
d6eb29ef-1911-54d0-ad6d-b963c82d0a77 | note | Controlling Documents - Chipsealing in NewZealand
3695a82e-db4e-572e-96b6-4007d0d0e34e | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
a0db75b0-eba6-514a-a6a6-6b9e1cf7c134 | note | Method - Visual
03f7877d-b3ff-536b-a6aa-b450b449ae4a | note | Frequency - Each Site
8576b1e7-0f8e-5ff1-ad58-8cd7de7b045c | note | Responsible Person - Surfacing Supervisor
97d76107-a14b-5963-b7c7-10b35510d575 | note | Verifying Document - Chip Sealing Quality and Site Record
ef64ed53-258c-556e-bd28-74b5db4295cf | note | Conduct - C
97e4f6b9-20c9-541d-9092-99083cae0876 | note | Produce Record - C
eadbc117-1b03-52f1-ab75-ecccccf3da84 | note | Approval - C
9119b807-ba8b-56c4-b499-c077702a3736 | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
6d030944-d5fa-50bc-b303-c2c333a0b42e | note | Controlling Documents - Chipsealing in NewZealand
b052c1bf-e48c-5211-8e24-8665fd564a63 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
7799fffc-55e9-565e-8482-dfa774bc8b1b | note | Method - Visual
abeea87e-4a38-52ff-84ab-9e7d5326ed84 | note | Frequency - Each Site
a1cf94e8-09cb-5e77-843d-2f9a83535596 | note | Responsible Person - Surfacing Supervisor
f1835af3-9ae1-5838-8c89-f0556ee66e01 | note | Verifying Document - Chip Sealing Quality and Site Record
d73985ba-d04e-512c-b281-6641450a4b85 | note | Conduct - C
1865abec-23f1-5465-8cf7-8565acb35d91 | note | Produce Record - C
91801214-c125-5744-a22d-fd8217fa3dc7 | note | Approval - C
433f4b0d-0031-5278-bc6e-41b58997d7b9 | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
97e07ee2-642d-5a96-9308-28ce13dd6007 | note | Controlling Documents - Chipsealing in NewZealand
76cebbec-e8a5-58df-b129-c74ec48f1187 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
8b4d2214-3ed4-5442-ab66-d193bed418f7 | note | Method - Visual
9766ac77-2257-5b44-8459-a6b9f2044a53 | note | Frequency - Each Site
1ace602d-ea17-5b5c-8847-ac533d708a24 | note | Responsible Person - Surfacing Supervisor
2d79cce5-ad8e-5aa2-ad3e-039f0318fe49 | note | Verifying Document - Site Record
2a320f85-5e1c-53b7-8d34-8ce906a3c83e | note | Conduct - C
f7100938-1910-55ca-b555-cc65f172434d | note | Produce Record - C
d5653ec9-2ec6-5797-b7d8-434e8d7b6f4a | note | Approval - C
aa6d08f7-c358-54a1-a837-dc861ff728e7 | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
3d955b62-8717-57b3-a5b5-32ca34b7b339 | note | Controlling Documents - MOTSAM
026ddc0a-9ee3-5830-b9ac-e77ea7345de2 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
ec0115e7-428a-59c1-ae1a-76aae68d6f05 | note | Method - Visual
aea24905-6bba-526f-b679-7830fac70970 | note | Frequency - Each Site
607caedf-8e0d-5b1b-a45f-05604cffd9a4 | note | Responsible Person - Surfacing Supervisor
dc31764b-a83a-51f7-a300-9a25b65bacf9 | note | Verifying Document - Site Record
3e932fa4-0e85-5894-82a0-9228d26833d3 | note | Conduct - C
0a76e241-8e0d-5384-8915-0a41b1eddd17 | note | Produce Record - C
ff4d002b-ef81-5dea-9702-bde79d3a35da | note | Approval - C
4a66881c-93d5-5118-82a7-5a237eb47428 | note | Witness Point Y/N - Y
2fa24de8-fb07-5d57-947e-3eea20cf5b9a | section | 5. Chip Sealing - 5.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
870e55ac-01c9-5887-a0ee-51aa3da78b3d | note | Acceptance Criteria - Formal Agreement
86e1727e-b29c-55a8-9446-4f8c63e22003 | note | Method - Visual Inspection
c298df39-96fa-5c3a-8156-91893b4af539 | note | Frequency - Post seal sweep
3718e8ef-ade9-5c69-9ed4-afcc5cc3df7b | note | Responsible Person - Quality Controller, Supervisor and Engineer
bd6b2e5d-ce6b-593d-a845-71a07fe3d422 | note | Verifying Document - Meeting Minutes
753559ad-f95f-5e29-978e-00149d2f664e | note | Conduct - C
d6d1413e-a972-5f07-ad6f-4ffd01f6e953 | note | Witness - C, S and E
5f1c8548-3f2c-5959-a9ca-359708a79cba | note | Produce Record - C
640e64f1-3fe6-5550-9fa9-9200e1155de3 | note | Approval - E
a7d9fa0e-0ca3-504c-ad92-d970413c813d | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
c35c7546-1b73-5901-a9b2-fcaf88ab05c1 | note | Controlling Documents - NOC; MS 6.1.3
8f756629-b36c-5c11-af32-450db8b84a64 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
8d2864d4-ff1d-5d29-91cd-6b8f7e5b57c5 | note | Method - Record
ea92ace3-fecb-5d97-80e3-f307ba804f3c | note | Frequency - Within 2 months of completing the annual resurfacing programme
06c7dce1-e88e-521b-82c7-1cfb3638d4f9 | note | Responsible Person - Surfacing Manager
134d65ca-57df-524a-9ab4-f69c0b563694 | note | Verifying Document - Construction Completion Report
d7c1e5fd-c5d9-5d29-ab16-961c454a6a6c | note | Conduct - C
cd896b0f-d406-5cec-8e9d-be1c978ca2f8 | note | Produce Record - C
df55d226-2f2b-5713-8e9f-ee305c04ca3b | note | Approval - C
35ba184b-c97b-541c-a986-16f413f6712d | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
2fb47137-c1d0-5530-83f8-6fcbd6e32d37 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
84b43f21-5da7-5b66-ac65-9d6ddf78ad38 | note | Acceptance Criteria - Engineer Approval
1314589a-8c3c-513c-863e-77721cfd2b39 | note | Method - Visual Inspection
83d81f55-66cc-5301-81ad-dc53a0ccbf9a | note | Frequency - ≤2 months of 1st Coat Seal
9ab46b2d-0276-5dc0-941a-6835601e55a5 | note | Responsible Person - Quality Controller/ Contract Manager
129c5b6e-00c6-5217-95fd-2293a283bc93 | note | Verifying Document - Signed Report
9f068273-cfc1-5f91-adb9-6513b3673696 | note | Conduct - C
aa674436-94bb-5828-b31b-67714c1ebe66 | note | Witness - C, S and E
7749a29d-4378-5218-a1ad-7e4b86c63928 | note | Produce Record - C
1f23b2ef-6e8e-5ec8-9ba6-994d89c5e305 | note | Approval - E
1a0e9cfe-2f3a-5742-94c9-2c48afbecba9 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
89fbcfcf-ecf7-5cc3-a113-8a3d9556ef2d | checklist | ITP - Pavement Rehab - SH 36 - Awahou to Central | itp | ITP - Pavement Rehab - SH 36 - Awahou to Central
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
09dfa698-6b7f-519e-b940-013fd716a19e | checkpoint | Design - Geometric Design
eb5d570d-4c5c-53bb-9937-649ed6aa10f6 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
9b3171ca-2016-58a3-afff-d9cc4a0afa1c | note | Acceptance Criteria - Principal Approval
45e5ba71-e0d6-5d96-b99f-ca0998c5082c | note | Method - Contractor and Principal peer review
38a8fe85-bd6b-5bfb-8066-5487366c9b15 | note | Frequency - per design revision
3eaaf82e-e059-5d9e-83f9-cdad59420846 | note | Conduct - C or S
e0a99a16-7c4b-5f1c-bcef-00f9fc666ae9 | note | Produce Record - C
e4ccf28c-554d-5b28-a4d6-a2af62557c9a | note | Approval - E
5dc6ba6f-7bfc-5f0d-a732-da10141c6b8b | note | Hold Point Y/N - Y
734b8921-df80-5868-90e2-320abcb6aec9 | signoff | HOLD POINT
fc457da0-71e7-5429-a676-cfa9f8ad8762 | checkpoint | Design - Pavement Treatment Design
dcb79c3c-ff05-5858-a4b4-daeb0f2fc417 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
823884c1-7db2-5931-985b-fe01e4857437 | note | Acceptance Criteria - Principal Approval
1946f8f4-086d-5f75-a3b8-4eaa636bfe3e | note | Method - Contractor and Principal peer review
5d660a39-3636-58cf-bfbf-969990be644c | note | Frequency - per design
c4e89535-1d09-548e-8840-a3482694dde9 | note | Verifying Document - Pavement Rehabilitation Design Report
2212bdd1-73c9-5d4e-9278-a0484bbc9af0 | note | Conduct - C or S
29a83fa7-c738-56d9-877c-51d6c62c25a4 | note | Produce Record - C
e89aa07d-fca5-5ee6-80d3-607773afcfea | note | Approval - E
63058135-f3a3-523b-b2b9-4e7cf2f93ce9 | note | Hold Point Y/N - Y
f7622f1f-ef56-5ab3-b6af-8b3b9e5d5f72 | signoff | HOLD POINT
0dc678d7-3e4b-59b0-8f5a-e064ad96deda | checkpoint | Materials: GAP 65 Subbase Material - Aggregate Sampling
e8f1245d-c23f-57ce-9982-bcb3ec8fc896 | note | Verifying Document - Sampling Worksheet
d18277b1-7647-573b-8f38-28cc30a3e4ba | note | Conduct - C or S
2d83a991-ed05-533a-b28e-9b035b6c1cd5 | note | Approval - S
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
3312dddb-f0b0-5b47-af2f-f7b50894b028 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
bd147bff-f54a-5731-a129-aa8bb9340c17 | note | Acceptance Criteria - Soaked CBR ≥ 40
b582e548-57f5-5ba5-819c-3c33c043454b | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
750d514d-2998-500a-a525-aa996008c9a9 | note | Responsible Person - Supervisor
fdb9522b-78db-5ecc-9ee1-d74e5224eace | note | Verifying Document - Test Report
4ea65e7a-f2a5-5c4d-a2e8-a164e213ed53 | note | Conduct - Sp or C or S
481e22f0-b5aa-5b13-ba45-a4a46b5db012 | note | Produce Record - Sp or S
2692b0f5-0bd7-5ce0-be44-ba7ff42f763f | note | Approval - E
b8398973-d28a-5e8c-a233-844b8e4f0578 | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
69da1689-dad9-5fe7-b5c6-47fa5c59d476 | checkpoint | Materials: GAP 65 Subbase Material - Production Property Test
a5a68012-ed57-50fa-837b-8b65b58d6939 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
547fbdbb-d406-5348-846b-fc54cc84cb77 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
381a526e-aad6-5df3-bfd6-0cb1c584a501 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
f1163d70-cada-54fe-86bf-cc186a178393 | note | Responsible Person - Supervisor
b08017d3-2cb3-5a2f-b4a2-ead84f16a348 | note | Verifying Document - Test Report
ca8ccc52-a120-5713-b3d2-000c5ab6f376 | note | Conduct - Sp or C or S
097922ae-78a9-5f35-8d18-50b9369b55dc | note | Produce Record - Sp or S
c03fec90-961a-5bfd-91a2-60a630d67e55 | note | Approval - E
36267686-a3f4-59c3-8122-aad009dd9685 | note | Hold Point Y/N - Y
08edf7ab-7b66-571d-824e-fffdd78047e4 | signoff | HOLD POINT
282d13fa-6a2e-5570-b955-78f6c0062fd3 | checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
3b761e8c-afbc-5183-8010-8397c47cde1d | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
1e8196f8-6671-5e69-b8c2-25c75739aee8 | note | Verifying Document - Sampling Worksheet
19b6d86b-bdd4-5d23-8c3b-38570c4103e5 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
6e2fdcff-c1d6-5b86-b31f-85a59ec2efab | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
110517be-e8f1-5b91-b651-43128e11e8fe | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
53554b0e-2e19-5570-af07-89d031e69a79 | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
03ca2d88-dc75-5ddc-985f-7b29a4685cd2 | note | Frequency - One test for every 10,000m³ of source material
3830adb5-d824-5b83-a28a-c9389a008ce0 | note | Responsible Person - Quality Controller
1ea6545c-55f8-5348-a540-590ff1bc7c37 | note | Verifying Document - Test Report
77560bcd-d8eb-59e7-a7b9-b028e9b731c9 | note | Conduct - Sp or C or S
532d2c60-69bd-56dd-bc74-dc0f509ca506 | note | Produce Record - Sp or S
6ab942b9-3524-5406-83cb-1d84da5b6e52 | note | Approval - E
0ef2edf6-4086-5c68-9f59-895a05a6041e | note | Hold Point Y/N - Y
2bce147b-57e0-5df2-aa19-d3114e0f900e | signoff | HOLD POINT
771bbcd5-e52e-5af5-9fc3-2a5ff6956b1d | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
adf81c47-c9ab-5e2b-93cb-10bc778ad900 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
231f7be7-aebc-59e8-8d7b-c5580e3ab12a | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
3c88e1ea-75e0-5df0-b761-048454b3d595 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
30390df2-b1a1-5c81-8612-dc6463c522ee | note | Frequency - One test for every 10,000m³ of source material
1f607dd4-a19e-56ae-ba55-39b265cf1316 | note | Responsible Person - Quality Controller
f5a735cc-8b72-56b6-8875-fa87f91b987a | note | Verifying Document - Test Report
488f1241-d812-5668-a4a7-4dc89a614a11 | note | Conduct - Sp or C or S
c2be2436-c40b-50a8-8eca-f8622b2b5c57 | note | Produce Record - Sp or S
6908e46d-8a2b-5332-8929-6eb4ef254b50 | note | Approval - E
f5f16783-fc57-5111-a013-182ead9587e0 | note | Hold Point Y/N - Y
5de343b7-b3e0-59f2-8f5e-085d4a8c0fdc | signoff | HOLD POINT
113f3833-1e06-55b9-9978-c5d36d530658 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
5f86381b-1d41-53ce-b561-58bbc363dd91 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
ae189dd9-70e0-552f-ac6a-1e8bee94a4c2 | note | Acceptance Criteria - Soaked CBR ≥ 80%
858f179e-4740-5243-a776-953a26208ea3 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
da2389cd-5c54-56c3-9b00-e6c3fff12e30 | note | Frequency - One test for every 10,000m³ of source material
62d56026-9c63-5411-8e12-6c82d06ab268 | note | Responsible Person - Quality Controller
6680c5ac-2a72-516b-b933-cbfde3bb6303 | note | Verifying Document - Test Report
532c6ee0-cf9f-540d-918c-a6b9392b8f6e | note | Conduct - Sp or C or S
41dc0c05-e932-58a4-9ff9-8a74fc866066 | note | Produce Record - Sp or S
10bc4669-70f8-5687-a810-3843ba280206 | note | Approval - E
f5279df7-3fde-5898-9a13-0e95dd6a2890 | note | Hold Point Y/N - Y
40c2302f-cce5-5c54-87be-1069cdfc7929 | signoff | HOLD POINT
976c9ab2-336e-5bd7-8941-60563e8cfc82 | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
d95258d9-e8e7-50dc-a58e-de88f197067f | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
9ddba53a-6645-5962-8a0b-a72233a19aca | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
98b4c9a5-f2f7-55f8-9475-af0034752103 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
dcd08a75-0d00-5e2c-ae09-bccb2a3857a8 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
0f15a52c-f018-51e9-9187-646f32414f6d | note | Responsible Person - Quality Controller
a3434be4-2de9-5277-b452-1631b99fd191 | note | Verifying Document - Test Report
ce610b28-f22a-5d6c-b300-a50a6cc98df3 | note | Conduct - Sp or C or S
c7ed8fce-8637-5cc7-99e4-2e337e9a8f3a | note | Produce Record - Sp or S
cd96ea76-a07e-5e89-8ab9-669ef775a2c6 | note | Approval - E
4cc81fa6-60e0-5f90-a92f-f4c4e90a712f | note | Hold Point Y/N - Y
8c291f12-658c-5f73-81d4-ac64eaf7be26 | signoff | HOLD POINT
21f389de-1666-5508-9d06-5a4f024a4cbe | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
e42c4cb4-be2c-535f-a34b-56e5ee30f0ef | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
c16567a3-ab1b-5385-9197-6baee82fac71 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
94deb2b0-3d56-5f25-8570-379dd5541dff | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
dfbbdcdc-48ae-5216-88a3-450224378add | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
a0d73925-3c27-51af-9cc6-82dbc0f3e9b9 | note | Responsible Person - Quality Controller
5818f5cc-ea4e-5c7d-b6c5-28b94d98ce3c | note | Verifying Document - Test Report
286904e0-047b-53aa-ace4-007f272ed373 | note | Conduct - Sp or C or S
68c52959-bfdf-58c1-8d2e-0b822e06b6a4 | note | Produce Record - Sp or S
c2f49c9e-ef75-5295-a3f2-712a544ff12a | note | Approval - E
e31eb6c3-c44c-521e-b7b3-7786a180fe29 | note | Hold Point Y/N - Y
f50c0087-ac9f-533c-9dad-f1906513e000 | signoff | HOLD POINT
66a6116e-307f-5697-aa3e-d266fb4bd96f | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
2396121d-3407-51ed-b67f-2348b7428bff | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
0dc5f51f-3bce-5bda-a176-d0e0e441c1cf | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
7648e7c8-715a-5c67-92cd-1ffae181e800 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
c15602a1-a9b6-59c3-9c0c-c39c5c02233e | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
50652d63-97b5-5a06-8249-eaa8d6543300 | note | Responsible Person - Quality Controller
1643f3c4-c4c4-58c6-9052-4a0d6c065bbb | note | Verifying Document - Test Report
789267f8-ad13-510c-8130-52367403ea5b | note | Conduct - Sp or C or S
dbe47d0f-dd29-5467-9c17-7cb0720aa803 | note | Produce Record - Sp or S
cb158389-aa6c-53f8-a6ca-ab14180bdf01 | note | Approval - E
cdb190df-1512-5933-a557-3a3e9f7279b3 | note | Hold Point Y/N - Y
7ecc9215-ad8b-5530-b3e7-13982b2273e0 | signoff | HOLD POINT
288f3247-2eba-55d4-ae79-89580bc4bef3 | checkpoint | Materials: Cement - Stabilising Agent Selection
0c012fee-9e00-58c8-9ddf-c3c1ac3796ce | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
f18e6c84-49f5-5dd6-834f-36ff89965f7b | note | Acceptance Criteria - GP
d35d8547-607c-5489-8c1a-626a3104b812 | note | Method - Visual inspection of supplier docket
ece98410-a8d7-5c52-8efc-186cf14382a0 | note | Frequency - per truck load
b4aa9048-d2ab-5a9b-b559-74f2a6b7cb52 | note | Responsible Person - Quality Controller
6b48180b-c262-50d0-b6b1-0d1084a173c8 | note | Verifying Document - Supplier Docket, Supplier Cert
37a467a0-c257-517f-878d-f04c1e7a2f30 | note | Conduct - Sp or S
e97ba1ec-0141-5db1-b915-29b0fc92a9c8 | note | Produce Record - Sp or S
dc2024d1-093e-54aa-b91b-09d46ca11362 | note | Approval - C
9c71249b-9f09-5ecf-b524-13711cc79ec5 | note | Witness Point Y/N - Y
5fe70724-8f32-50a2-8961-1dac348f79c6 | checkpoint | Materials: Water - Water draw for stabilising
3b287b5f-4b86-50de-b669-2a873791b3b6 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
19cc44c3-cfdd-5ca5-afba-334b44779484 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
33c79b53-1886-55b5-a9c2-481e9d1259fa | note | Method - Visual inspection
73ea0ff9-151b-51cc-b66d-7d85b466da4e | note | Frequency - per truck load
6c8572c6-ee1e-5d4e-b9c5-e8299fbc52a4 | note | Responsible Person - Quality Controller
66a02040-2962-516e-8eb8-154ed20e02af | note | Verifying Document - Hydrant use form
13580efc-a387-513a-8ba8-851a4a746fef | note | Conduct - Sp or S
3697ec19-9a33-5f00-8e30-5276e6d39288 | note | Produce Record - Sp or S
e41aed75-1ddc-565e-9573-a199089afdec | note | Approval - C
cb463d89-755d-51fc-ab69-37a77d20c550 | note | Witness Point Y/N - Y
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
88cf8b6c-4ebc-574a-a711-361f57493270 | note | Controlling Documents - TNZ F7 Specification
4399b716-6767-574c-b4d7-5c42122fe41a | note | Acceptance Criteria - Details on Docket
d3e9ea32-6e40-5147-8fa9-2253a28d170f | note | Method - Visual inspection
5860a242-732b-57cd-a56f-7c43ee309447 | note | Frequency - Per Delivery
9358ec4d-d8af-5fe5-ae0e-52a900dc168e | note | Responsible Person - Quality Controller
f8e175f1-d712-5f3f-9c2c-6e78325831a9 | note | Verifying Document - MDS
d8b56b17-79bc-58e8-8984-cf0017d6bb06 | note | Conduct - Sp or S
9bbb2cd9-008b-576c-a8b7-5c1b14ba39e8 | note | Produce Record - Sp or S
fc178143-f68f-5021-8939-7bfadbd5b035 | note | Approval - C
e3d4e1e6-ef30-5002-8049-97a2b97c09ea | note | Witness Point Y/N - Y
f2243fec-ad92-567d-bb3c-12058747fa66 | checkpoint | Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent
3b300327-8190-5ab3-a4f3-7a0f317069ce | note | Controlling Documents - As per NZTA list of approved materials/suppliers
8c01fa3a-6cd0-52d1-99e1-063acb0b5f9c | note | Acceptance Criteria - Details on Docket
46c2771b-5b3c-5b1d-a3c1-70d7b330a2fa | note | Method - Visual inspection
5bc72f1b-d688-545f-bd40-2efb84ccc6fa | note | Frequency - Per Delivery
0eb2d412-8b4e-55f3-a322-a652d4ffb9e8 | note | Responsible Person - Quality Controller
14454438-0bf4-523c-8280-847d20e10b14 | note | Verifying Document - MDS
1881aaf8-1552-53ce-bd17-5810272039f0 | note | Conduct - Sp or S
7e39a9bf-a5ea-58a4-be49-bd6316c9ab3e | note | Produce Record - Sp or S
ea4ed84b-0ca1-5c9e-ae59-1020f3624f58 | note | Approval - C
285af570-f3dc-5616-9c69-f3ebff1d6c36 | note | Witness Point Y/N - Y
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
3cbcad33-916c-583b-8548-b5e09634e85a | checkpoint | Production Testing of stabilised material - OMC/MDD
ab88e9d6-f46e-5b50-aff2-20b8cb730ae6 | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
c6d8d75e-fc55-59a3-a014-331fa3f18864 | note | Acceptance Criteria - To obtain OMC & MDD
e500e350-b1a6-5841-9887-082be741c671 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
dbc3e78f-0cf3-57e1-a2bf-2c2dc3f9d999 | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
b235e127-2612-5fbe-8287-0c86919b09e1 | note | Responsible Person - Quality Controller
6b1d4348-5342-5cbb-84a3-a3e787135e3b | note | Verifying Document - Test report
f3ac426c-0484-5cc4-8921-340f9745823a | note | Conduct - S or C
e168769e-c676-5c40-9059-af21286d377d | note | Witness - C
8619518d-f78e-5668-9901-fb2572df6cb9 | note | Produce Record - S or C
39d4e0fe-9696-5c1a-af0c-8c438e08d38c | note | Approval - C
b957c5d7-f8e6-5952-a71d-671877be12c8 | note | Witness Point Y/N - Y
db166df1-f07e-5e98-a6bd-e46d84f52c3e | checkpoint | Production Testing of stabilised material - Solid Density
5409e6a6-0623-5237-ae1f-fc176a112eb3 | note | Controlling Documents - TNZ B/5 section 7.7
79edc855-b683-51d2-91e5-0939345d5e62 | note | Acceptance Criteria - For info. and use in MDD calculation
58eae3c3-7306-52d1-826f-12a3872a7a8a | note | Method - NZS 4407; test 3.7.1
e247fe19-0dcd-54ec-acd4-bd8481022e1d | note | Frequency - Once on commencement and if any materials change
4018396a-3594-5dec-a3b9-ae20872e7ce0 | note | Responsible Person - Quality Controller
2d4da368-3fe7-5d04-9ce2-6a2f72f12f30 | note | Verifying Document - Test report
68c69eac-b698-50b0-83b5-5f880df215df | note | Conduct - S or C
ae418709-e698-5c59-9d41-766387affbb8 | note | Witness - C
118dce52-9f16-55c9-8e0a-731a487c09f7 | note | Produce Record - S or C
8cab3c96-aa6f-57d1-903c-42701b39ee0c | note | Approval - C
bddcb5db-e8d2-5e3f-b760-925e78f3b380 | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
4179a253-a4a6-57e1-b1dd-4b01846fc105 | note | Controlling Documents - Reference from Project Drawings
af44c858-6da6-592f-8425-5a6f903d86b5 | note | Method - Survey/Mobile Roads, Marks with Dazzle
0396b186-b124-5858-b4ac-9141d392d349 | note | Frequency - Chainages for every different pavement sections
ae3e80d4-366f-5ea8-9cdd-e718e9c60a30 | note | Responsible Person - Subcontractor/ Engineer
2cbd8fb4-274b-50c7-9dfc-2eb6484838c3 | note | Verifying Document - Construction drawings
752fff65-5add-5777-af20-165e9b634809 | note | Conduct - S or C
601778dd-7b23-5842-98f7-9a2ca709a51f | note | Witness - C
4c28e685-31e8-5e57-8534-95ad7a67a7fe | note | Produce Record - S or C
4469d575-2601-5938-adb3-65a1d8096d71 | note | Approval - C
e0562ac6-10f1-591a-a913-01674d6c2a24 | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
cd7ad103-d8eb-5ab6-8aa2-acf577a9a9ea | note | Controlling Documents - Site specifics to be confirmed
524db947-6c4b-54ad-983c-987c29f14ab5 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
506ca678-fe33-57db-8dbf-e9c0b1838574 | note | Method - Scala Penetrometer on Excavation Floor
62955303-8ca7-5b23-8f8b-1d606b6df61a | note | Frequency - As required
c7a1d6e4-1312-518b-80a5-fae9d4accee2 | note | Responsible Person - Quality Controller
58a11b2c-a018-5405-acbf-8a15ce128b5b | note | Verifying Document - Agreed treatment plan
b1f2ff35-607c-5181-91bc-9ceed6a2fef4 | note | Conduct - S
508f7e56-a052-55a3-a7fc-f87bd2ecc0f0 | note | Witness - C
09c13f5f-9bb1-569b-8d63-506586d06e41 | note | Produce Record - S
91da0cfc-1465-5d6d-b7ba-00c260659098 | note | Approval - E
ee7f3b34-50dd-5c40-9900-f43777e1a8c3 | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
885bc306-fedf-51b1-b4f8-0328e04ca5d5 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
ba60d11b-74d4-55c8-a36e-70043933efa5 | note | Acceptance Criteria - 250mm deep unless specified
5c5d79cd-bd72-5015-ba02-c63262560408 | note | Method - Visual inspection
c882511a-d15f-5dd2-b732-ce1b643d1102 | note | Frequency - As required
fd1564ca-d80f-57d8-a49f-726e09dad58e | note | Responsible Person - Quality Controller
22077275-f776-5cc9-96a0-c3767434d15e | note | Verifying Document - Dig out site records/ Asbuilt
cc9ab00f-f6e2-5828-83f1-66c2e2d59307 | note | Conduct - S
e1e0893d-049f-5240-9767-8e9e55d91ee7 | note | Witness - C
6a213dba-feb9-5587-b9f9-c5bcba742863 | note | Produce Record - S
40a192a0-43ae-5d7a-9f11-325832ee2693 | note | Approval - C
515530e6-8fb6-52eb-851f-e4169808121a | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
7e17bb2d-28bf-5e86-b512-577183a50954 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
65506d61-8786-5120-9943-9bb8e0302713 | note | Acceptance Criteria - Scala > 3 blows per 100mm or Proof roll <5mm
9d2894c5-fc05-5fdd-803b-a77d81c015c1 | note | Method - Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful
f6730bda-0d00-52c2-a15b-6aa8516d1134 | note | Frequency - As required depending on size of digout
2bec60aa-0775-546d-947c-50c6aa19cbf4 | note | Responsible Person - Quality Controller
cedac27d-2b7b-5509-974d-798f6b930cc3 | note | Verifying Document - Test report
a84a637f-c324-5234-8053-d4f55400d5b9 | note | Conduct - S/C
f8af45c6-dce6-5e52-b0f6-a3cde39b0f3c | note | Witness - C
dae0ecae-061a-5067-b48c-211b9aa77eeb | note | Produce Record - S/C
a87b7d9d-0fa5-5c5f-ad3e-fb3574a6495c | note | Approval - E
cd35489c-5801-57cb-b8a8-ac157b22d60e | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
2074a827-f9a2-5633-be8f-6b720f7418d8 | note | Controlling Documents - TNZ F7 Specification
e98f7159-8bfb-5c5f-9216-e0fbb2bbcf01 | note | Acceptance Criteria - Meet TNZ F7 Spec.
c6b983e9-5005-5d13-864f-41d3313bbce0 | note | Method - Visual inspection
569f625e-ab17-5260-86e7-52922a28a237 | note | Frequency - Per Delivery
4ce4381c-d385-5606-894a-faee519fb50c | note | Responsible Person - Quality Controller
31436db4-08c9-558f-bf7f-ce63b6aadcd1 | note | Verifying Document - Certificate of conformance
befbcb31-84fb-500a-893d-f414c67de295 | note | Conduct - Sp or S
3c8f24f3-7dc3-544a-8b3a-cba83952f30a | note | Produce Record - C
fb3159d3-5be8-5ec6-9c86-e740734b4e18 | note | Approval - C
f52a8f73-cf11-53b9-a261-ceaccdec01ee | note | Witness Point Y/N - Y
33fd8fbe-9408-576a-8bf7-891431ad9e70 | checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer (if rqd)
6b0c46a0-24c1-5b68-9498-3aef77feda23 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
d22ca2b6-5937-599f-98e8-d488ffcc364b | note | Acceptance Criteria - On the list of approved materials/suppliers
c181dcc1-3ca9-5da2-a9fa-b2237d0bb0d5 | note | Method - Visual inspection
898f7ce7-a848-5895-a670-1ef1e1fd77f6 | note | Frequency - Per Delivery
2dcc63eb-3dfe-5abe-b104-45b501bdc779 | note | Responsible Person - Quality Controller
461c9734-d93f-533b-a2b7-fa0a74821e87 | note | Verifying Document - Certificate of conformance
af322b91-d1f1-5255-9451-7c647468a05b | note | Conduct - Sp or S
3bc1b341-d19d-51e7-8a44-6adf4cd6ff5f | note | Produce Record - C
2d1d2b6b-3fe9-51cb-8c7b-8b84be25c393 | note | Approval - C
6ed98bf2-cc8d-5fe8-b000-84fd75b873a6 | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
1b6f7132-0a9e-5292-ad8b-57e3c35a6610 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
05bd3471-e063-5924-891b-bff42b9f2f76 | note | Acceptance Criteria - Clegg value > 45
6858380e-2b5d-5c65-ace8-bdf18ca0c6fa | note | Method - Clegg Test
6e443a4c-bc87-5501-890b-5dccd2da06f9 | note | Frequency - Min. 2 per digout
218d4475-dcb2-5ebf-8139-6aa97fca3a4b | note | Responsible Person - Quality Controller
35830c22-79ea-5665-8f03-5d434e2e8886 | note | Verifying Document - Test report
50f54a26-7dd0-5ae7-9c07-21ae256bc1bb | note | Conduct - S/C
9d1b76b2-18bb-51d5-abbc-1ce7874991fb | note | Witness - C
cbaa0694-c6c9-5586-bf68-7ebd4fdae660 | note | Produce Record - S/C
228262fd-d570-54c1-8858-c6e36bcf8dd2 | note | Approval - E
c111cea4-9ab3-59ba-a036-4461902e6500 | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
44e855f0-d607-5cef-9464-9e02cfe35481 | checkpoint | Place GAP 65 Subbase Material
6cd9aac9-56eb-52a4-a8f3-6f1dfa3c830f | note | Controlling Documents - TNZ B/5 (section 7)
caf9a076-5ddc-5ffa-a719-585b3fc88664 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
72ce2125-8b04-59f0-ab69-8fb96690f8a2 | note | Method - Visual Inspection
4bc7eeea-ab68-521a-a102-e1b8c7935790 | note | Frequency - On completion of placement
706d4ba9-052d-56c1-86ad-b44e505ba57f | note | Responsible Person - Quality Controller
236fd54e-19cb-5037-8ca1-50bdf6c65b42 | note | Verifying Document - Photographs and Daily Site Record
33e53dc2-2a99-5e0d-be8a-662e918bd1ac | note | Conduct - S or C
c43b986f-b574-5db6-9b80-354b174eaee9 | note | Produce Record - S or C
5da1a737-1e84-5116-9a0b-e9bbb6ed6440 | note | Approval - C
7490dc33-9f26-5bd9-a3d7-33c9a9924885 | note | Witness Point Y/N - Y
27c96781-3034-5bd6-8be1-9136ce336cf1 | checkpoint | Spreading of Cement
5f0533d6-fda6-5ed7-b9f4-40e4899f677d | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
ea65be8a-cb74-5400-bcf0-467e71c2bf3e | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
33ac3b81-aefe-53b6-8dcd-67720ab407f1 | note | Method - Mat test (1m² canvas) and Average Usage Test
5d9b1eee-d059-5f78-9a47-cda2767b188e | note | Frequency - per 400m² and upon emptying the spreader
cb8198cb-5389-5dcc-9535-2ff5aed35a70 | note | Responsible Person - Quality Controller
c7fc24ef-1ddc-5ca5-a159-2a2e8781b460 | note | Verifying Document - Mat Test Form and truck dockets
a31adf13-b58d-5873-a8fc-da7bf1cf50ff | note | Conduct - S or Sp
fb3fe51b-25c0-5f42-9551-e43d43af57a4 | note | Witness - C
0d6d7fc0-d60d-58f2-b63e-46b2bbadbb68 | note | Produce Record - S
aca67e9b-3095-5b5e-b721-3cfbd35d2dbe | note | Approval - E
f3e054f5-6677-5d26-9f57-d077fb0960e2 | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
27aac6d2-59b2-5e1c-8f86-7e7b335e62df | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
e061c204-6d7f-52e9-bdc4-1e838d6d544d | note | Acceptance Criteria - 90-100% OWC
c4449c0c-c7a9-5e92-93aa-fd050890abf9 | note | Method - Nuclear Densometer Testing prior to Stabilisation
cea5e0ce-e8c9-5945-8a03-8adc3979d270 | note | Frequency - ≥1 per 1000m² lot
33f62886-e6e9-5fc1-8c05-fae15637264a | note | Responsible Person - Quality Controller
fe5e4298-d8d4-5aa5-97da-618f97e11d70 | note | Verifying Document - NDM Record
ccc72751-6c35-5dd4-bb5f-8dbb5f777672 | note | Conduct - S or C
b78263fa-85d2-56ca-ae5c-e5911bc3b970 | note | Produce Record - S
ec3804e8-62f3-5454-9694-7601ee2d3f13 | note | Approval - S or C
a6f9dbb1-fcf2-5e84-bb10-9a74f425bf36 | note | Witness Point Y/N - Y
3aae6428-5972-5b13-a661-272c4bed881e | checkpoint | Cut Depth
dac91828-22c9-556e-ac8d-b410ae4cd259 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
5244082c-2a98-56ab-8db6-cce0ff79fcb3 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
e01153ba-3804-5711-80ea-2fa81d31bdb3 | note | Method - Physical Measure and Visual Record
fd565e3f-381a-5711-8d15-f6c0b9c92048 | note | Frequency - ≥1 per 200m of cut length
717c0ddb-4210-5602-ab37-24b3226db05d | note | Responsible Person - Quality Controller
fbb2fb9b-c704-525c-a375-bc35df8c45b5 | note | Verifying Document - Photographs and Daily Site Record
0adca4fd-4a28-5b5e-b2cc-c0031beabc0e | note | Conduct - S or C
bb74dcf2-16a4-5268-b470-3a10a0309250 | note | Produce Record - S
7619bfe7-3eb1-5bba-9437-2d73cae09f43 | note | Approval - S or C
113f31d1-4290-5aaa-9f95-28d5c7815c22 | note | Witness Point Y/N - Y
b4e8c8c0-519c-5ea3-a63c-d6e4e3e61d57 | checkpoint | Longitudinal Joints
c0581198-b670-5409-9457-16156bdec762 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
b42bade6-f14e-5e43-bd73-b59e9479087a | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
0a70738a-f434-58cf-aa98-4bbd32c5f3a0 | note | Method - Visual Record
0fa240e6-46b1-5a0c-9d23-07e9ff7c93c3 | note | Frequency - per sucessive cut
5e65f2b2-4bfe-5ed9-a9f1-7ab41e07e543 | note | Responsible Person - Quality Controller
d1cb4740-55cf-54be-9299-b96730bd6e7f | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
8692a74b-c0ff-52f8-8b41-4deacc2dafc8 | note | Conduct - S or C
4b7ea3d3-70ac-5b2b-b773-fa5b47978d6e | note | Produce Record - S
25b9e823-a15d-595a-97b3-c3112a47d593 | note | Approval - S or C
b026672a-e8a0-50db-bb83-2e99aa02e1a2 | note | Witness Point Y/N - Y
4adf91a5-413d-56e8-8c6a-9cb5dbaf546e | checkpoint | Continuity of Layer
f1b47556-9bf0-5ee6-b477-867909ef7996 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
02d86085-2b25-52ca-a840-4628e30f3b47 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
05a8da2a-b811-5f3d-a0a1-4fd8ea1081af | note | Method - Visual Record
39dcfba2-e39a-538c-b6d2-59397f3c525c | note | Frequency - per sucessive cut
863d9550-5e30-5799-bfb5-b5ba468c9c85 | note | Responsible Person - Quality Controller
195b8f99-9d6a-557f-ae23-f2b75f1174ae | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
c825b745-13fb-52e9-a18e-aa4dddf5a633 | note | Conduct - S or C
0885ba3e-b2d1-5c77-b6d8-80ead51920ec | note | Produce Record - S
193dc919-c4b3-556d-8038-99d9d9751c6a | note | Approval - S or C
fbe15ab4-f710-5935-a1d0-13347306e7ab | note | Witness Point Y/N - Y
a3e7c399-2e95-59d2-b1ad-e3d1d43952bc | checkpoint | Stabilised Material Particle Size
b1d37bb7-a3f0-5227-8cb6-ee65e5de7252 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
89b2cf1c-66b5-5cc2-9334-9624628f3fd4 | note | Acceptance Criteria - No excessive breakdown of stabilised material
ba34b99b-fc20-593b-92a4-d8f170269d02 | note | Method - Visual Record
8656b1e0-3e9b-5b85-8724-67e94aa286e0 | note | Frequency - within 20m of each section and then regularly based on material variability
b431db6c-c131-5414-a76f-f5a2ecb29abd | note | Responsible Person - Quality Controller
026311ab-5f81-50f9-b162-73ce7a67f94e | note | Verifying Document - Photographs
50d213df-37f3-5d03-b686-590d557399db | note | Conduct - S or C
47e5309f-ffce-5069-ac0b-f8a4549bb959 | note | Produce Record - S or C
4ed990b2-4c3d-57ac-8190-a30a5a614f6d | note | Approval - C
6b4c886b-659c-5b6b-bc67-96eef723bbb2 | note | Witness Point Y/N - Y
b2669c88-ac51-56ca-b8c1-ca203b10eac4 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
766ed23d-c75b-5407-8dad-45d6c2677eda | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
7e8a3b3d-52e4-5585-958a-a8609a5bedac | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
716ebbd0-fd36-5a84-b875-8d32bc6300e9 | note | Method - Plateau Density Testing
c9771adf-21bb-5da6-82b7-59063f817780 | note | Frequency - 1 time, or additional tests when material changes visually
3833e2ef-cf1e-5289-b31c-63b1c1c0deea | note | Responsible Person - Supervisor
f41e57d9-f318-5eaf-912e-95352052586c | note | Verifying Document - Test record
251c23da-c0f8-599d-86f7-6307f2fc5e7f | note | Conduct - S or C
c76c009e-f433-581d-8817-3c2455515c1f | note | Produce Record - S or C
2b66fcb9-a355-597f-995f-d82e819cd1a3 | note | Approval - C
1d33ce63-a973-5739-a807-810c8e023fa2 | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
cb50cac6-b0f9-5eae-91ba-ff1a4ff521c9 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
3fc77614-0402-549c-9eaf-6441f8c424bd | note | Acceptance Criteria - To provide MDD for NDM testing
d1044f2a-2ce5-5d6b-98d1-b72142d58223 | note | Method - Plateau Density Testing
5482c426-78a1-57b9-93d5-b5008a973254 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
f0612776-ea38-5c01-9263-70c3af80adae | note | Responsible Person - Quality Controller
bfe61203-3980-5af7-a3c0-c31b2dab35e7 | note | Verifying Document - Test Record
2b6cd358-3406-5c1a-b878-e579129255a1 | note | Conduct - S or C
f344a7d1-1a25-5690-a323-70198b309368 | note | Produce Record - S or C
ff5846f6-7e1f-5cd9-a681-6b37752decaf | note | Approval - E
c0e7b1ae-cc22-5956-96d9-a5e7bcdd04b7 | note | Witness Point Y/N - Y
1b96c1cd-dc03-50d2-9eeb-7acf490a611e | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
385f7b0b-fb30-5453-a811-89db57744f46 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
503cd0ec-5f43-5d74-8cae-22f81670c2db | note | Acceptance Criteria - To provide MDD for NDM testing
d3ae7089-5315-5f51-a179-e1e5a67951d1 | note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
c5d22ab1-e8e9-500c-9332-34f366997e03 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
96770105-8fdd-56d4-8430-34ba4abda53f | note | Responsible Person - Quality Controller
1a892666-20f7-57a0-b2dd-e77307f755a0 | note | Verifying Document - Test Record
14730010-79f7-53d3-8895-7e215fcc92df | note | Conduct - S or C
4a59426f-5e8d-5ea2-8a8d-b3b2c8f8bc27 | note | Produce Record - S or C
3a25a000-32d2-570e-adcd-d32e4c1c5e58 | note | Approval - C
92be42d3-4636-5f13-ab93-9ab48d1281a9 | note | Witness Point Y/N - Y
9b641378-7dcd-5a3d-807c-a31562803710 | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
1fa83a87-4024-58c5-9855-61078afadbf2 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
6664015d-de55-5ac5-b042-2cc7aaecc8ba | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
efaf700d-c0c6-5a09-b359-202077aef76f | note | Method - Plateau Density Testing, Lab. MDD
f755f515-c822-5150-ad6f-2ed5b2fd6043 | note | Frequency - At commencement of construction and whenever materials change
93ce4b39-8eab-583e-bf07-196020d04ad8 | note | Responsible Person - Quality Controller, Engineer
e5e23534-58fa-5c50-acf0-10dd75124320 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
463e7a5c-cec4-5da8-a4c5-dd52a0a3d064 | note | Conduct - S or C
4d8b8096-058a-51c0-bddf-67e5cf3e7c9f | note | Produce Record - S or C
85434f21-d3be-54b1-9ebd-3bf669e1bf90 | note | Approval - E
0205cfd8-829f-5b0c-9464-819ae3549976 | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
f2927a50-5d05-5249-a368-2d906b4b0d60 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
987a412a-cf07-533f-924c-250d7deaca88 | note | Acceptance Criteria - Mean value ≥ 95% and Minimum Value ≥ 92%
7524ceb3-3b1d-55ae-a8c6-22af890ff889 | note | Method - Nuclear Densometer Testing
20e5f16b-cbc2-5dbd-bab8-80ffdb1633fb | note | Frequency - ≥ 5 tests per 1000m² lot
9fbadf58-ec25-586a-89bf-2b57053a4cf1 | note | Responsible Person - Quality Controller
d43ac756-58dd-5971-9211-965825fddf7c | note | Verifying Document - NDM Record
c55792d0-8b6a-59d4-af66-8047b9084d03 | note | Conduct - S or C
03343584-95ce-5d64-aec3-42a6cb1c7624 | note | Produce Record - S or C
82bfd9bb-738d-5b1a-a061-1ec09f42501e | note | Approval - E
99d5aeb8-499e-5d32-9b15-9f6869ef58fa | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
cd6daa60-e401-5df4-9c23-bd98b0efaa94 | checkpoint | Control Testing (if required)
051abecd-0e29-5fe5-87ee-9d3807fa5c75 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
cc19c1aa-efc6-5d4e-830d-6102a05b8b99 | note | Acceptance Criteria - Nil
9c063f1e-6fcf-59a4-a6e7-acce0f75bba5 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
b0ebad7b-6c12-55a5-b565-7ed3ce5d0652 | note | Frequency - when agreed with the Engineer
3844f92c-a3e1-585a-974a-df111c9040b3 | note | Responsible Person - Quality Controller
cedf4377-9381-5c00-ab35-8ac38c7e9e88 | note | Verifying Document - Test Report
dd09cc04-b3aa-5b8a-ac15-ed5dbb867344 | note | Conduct - S or C
723def10-057a-5887-a587-35beab6a7939 | note | Produce Record - S or C
d62f01a2-e9eb-5dc7-ae22-0d0cd6677083 | note | Approval - E
9eb00595-2dc5-53a3-b838-edbc0eddb20f | note | Witness Point Y/N - Y
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
93b45f3e-2065-5010-addb-d5a3039f2204 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
69f93476-7449-54e1-a75e-2553576aaddf | note | Acceptance Criteria - Between -25mm and +5mm
3249f23c-4aaa-59a6-bbee-5c3a9f43cede | note | Method - String lines or Survey Asbuilt
d3101fb6-effa-5819-befc-c57746b577da | note | Frequency - during construction and prior to seal
89ffe969-be37-5e22-8b75-3ba84ca2d170 | note | Responsible Person - Supervisor
d2651522-904c-5611-9e85-69801b65fbbd | note | Verifying Document - String Sheet/Survey Asbuilts
9ad27452-f66e-50ac-84d3-fd8a3805a46b | note | Conduct - S or C
6f153a24-92e5-55fb-92e6-582ff26c45c1 | note | Witness - C and E
22440550-81b6-5633-b9c1-bd006f1713da | note | Produce Record - S or C
55dc97ac-7ebd-5823-9772-a8a735e19db5 | note | Approval - E
50b09a8e-caa2-55d1-b39c-441ace88b8a8 | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
0171fab1-f8b6-5323-a892-28b9796ead0e | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
0c4f2c6d-b15f-5d19-b427-ab41a6659547 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
4d294284-7b5d-5f53-9d8a-35ab665231a7 | note | Method - 3m straight edge or Survey Asbuilt
00a36e15-9497-5d22-9d77-b7247edda7ad | note | Frequency - during construction and prior to seal
181562d6-573b-5519-8329-49033046b9d7 | note | Responsible Person - Supervisor
11580fc4-09e0-53ce-adc4-2aa7869353d0 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
7b9d842f-25bc-57ed-92b6-23a4a7dade57 | note | Conduct - S or C
011e990e-27a2-52b7-a0a8-c7b7206231b3 | note | Witness - C and E
71bcaefe-3ec5-559d-9002-c997f43a9cec | note | Produce Record - S or C
d1544e63-cf2d-501d-b663-ff332528b152 | note | Approval - E
337d222c-9a8f-5b2d-90c4-1cfd60614b6e | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
cd87e2cd-2f01-58f5-9aa5-6af4ace06703 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
f8e01080-67ea-5028-bc66-449a691b25e7 | note | Acceptance Criteria - ≤80%, however 65% is ideal
a0abbe7c-e01f-5755-80ed-e7a91f850b2f | note | Method - Nuclear Densometer Testing
cd28e498-b55f-5472-9048-d7c24be1a65c | note | Frequency - ≥5 tests per 1000m² lot
93fe709a-7291-5958-9b13-f4abcdc92b2d | note | Responsible Person - Quality Controller
d09770df-a060-53ad-ab17-5da0a3110de0 | note | Verifying Document - NDM Record
bec59297-6b36-59ef-8dd8-f6242a0bfa6e | note | Conduct - S or C
e2d87d04-f233-5851-81c2-4e7942e73905 | note | Witness - C and E
e1db5394-9b5d-5101-bf90-550cce463502 | note | Produce Record - S or C
c264121e-c036-59c8-bb96-b9506aabd4e1 | note | Approval - E
9b5705fb-b264-551a-917b-ddf0a7876749 | note | Witness Point Y/N - Y
eeb50d65-64ce-572e-8456-9dd1f3e00c42 | checkpoint | Place M/4 AP40 Basecourse Material
5c2f9a5e-3462-571f-8c13-446313e02585 | note | Controlling Documents - TNZ B/2 section 7.2
4805a4e0-3a93-57dc-9808-9c202f1efdea | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
c0cdf353-07fc-59cd-bc97-f9485b7e466e | note | Method - Visual Inspection
0e73dbd4-cb71-585e-8d20-9c05cf606473 | note | Frequency - On completion of placement
d76da394-ff7a-56dc-8547-777631da23b0 | note | Responsible Person - Quality Controller
a365d70a-c7d2-5f28-a0b7-cce528dc71a9 | note | Verifying Document - Photographs and Daily Site Record
c5288384-dce7-588f-b8b0-d5ac2f94874f | note | Conduct - S or C
2a03d700-21f9-5806-8c25-5510c530c654 | note | Produce Record - S or C
b052b750-ffde-540e-8343-67246db26ef0 | note | Approval - C
ddf95611-bcde-5d04-8732-846e3601b99d | note | Witness Point Y/N - Y
fa0abceb-9383-4490-8e22-beb1cc341849 | checkpoint | Addition of Water
6a5c6c18-6b1b-4335-829c-5e7bd31a478c | note | Controlling Documents - TNZ B/2 section 7.5
2f23fa8a-867f-44d5-9eb5-da99fef32323 | note | Acceptance Criteria - 90-100% OWC
b751e158-1df7-4fc9-9a99-29254cbb1e4c | note | Method - Nuclear Densometer Testing prior to Stabilisation
7e0518d6-c56b-4c9c-8e4a-3848379ce3d7 | note | Frequency - ≥1 per 1000m² lot
64d4dc51-53e9-4e2a-b6b2-bef56538f9bf | note | Responsible Person - Quality Controller
ed1c4caa-0b86-4711-9979-5e8a41022254 | note | Verifying Document - NDM Record
d121aef2-c390-4b15-8df5-166e731f18af | note | Conduct - S or C
198e991e-f273-4c95-80df-2f48699f56d1 | note | Produce Record - S or C
e826ca0f-4846-4ec1-9a03-e9ac2337dd30 | note | Approval - C
ab5e226b-3a8a-4a0f-af70-5729e673f1f8 | note | Witness Point Y/N - Y
6969e65f-8cbf-4355-91a0-bde451019432 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
745e57bc-d250-4539-a6c1-293412310f32 | note | Controlling Documents - TNZ B/2 section 7.5
68d74d52-e74c-4978-8b0c-debad373e952 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
e268dcdc-fbf9-4a82-92b9-76cfc753f4f3 | note | Method - Plateau Density Testing
4b6d6020-09da-46a4-978e-2bb8ada00039 | note | Frequency - 1 time, or additional tests when material changes visually
6fd0c68e-c69b-4e7f-9c1a-2e3d9bb4d78f | note | Responsible Person - Supervisor
346a4aa0-6948-46a3-830a-c7bb4c554a88 | note | Verifying Document - Test record
63a9d140-1983-4296-952c-20597fe49207 | note | Conduct - S or C
c44fb813-6e31-4b06-946b-7da5f7606ced | note | Produce Record - S or C
fac369a2-182c-436a-9262-6bda9b554817 | note | Approval - C
25b9e22c-c533-441b-8f66-1425e2d48fa0 | note | Witness Point Y/N - Y
d8d26218-c651-46cd-8ec2-574ff4ecb820 | checkpoint | Establish Compaction Target
e81c20e9-ed3c-564c-bb15-8551c67ffaab | note | Controlling Documents - TNZ B/2 section 7.5
e54c3c61-0e33-5301-9d70-1aa26328fb0d | note | Acceptance Criteria - To provide MDD for NDM testing
f7aedb73-59f1-5c2e-9873-6d5a3b56e727 | note | Method - Plateau Density Testing
c71b98e7-0205-55a5-abd3-e1734e229fd6 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
c6e3098b-29fd-5f54-9220-930a3b7f3641 | note | Responsible Person - Quality Controller
69b566de-4d02-588e-a3df-ae0ed27ca4eb | note | Verifying Document - Test Record
f8abe885-87d2-584a-a237-6f0464a279f2 | note | Conduct - S or C
23076cce-e510-5f09-89da-6ff49cae3954 | note | Produce Record - S or C
ea16a392-747e-5e5f-b7a4-68e19b9b719c | note | Approval - E
4528c325-12b7-5085-84c4-f7a19190cd99 | note | Witness Point Y/N - Y
c49384a7-df94-4e5c-abfe-ea8feae140c9 | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
d75b1dd3-0577-5af6-9407-9bf67cec2b2b | note | Controlling Documents - TNZ B/2 section 7.6
788a4a6a-4a11-5494-ad44-bf9e934c695c | note | Acceptance Criteria - To provide MDD for NDM testing
e953116e-d92a-50eb-ade3-f96a0eee4ce8 | note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
6137844b-8254-586d-956b-1c07ced1feb4 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
ee5c4216-fb77-58fa-b036-c5368672cb54 | note | Responsible Person - Quality Controller
a5341021-45f2-54af-8d1e-00e1bb7303fd | note | Verifying Document - Test Record
e1715ff5-06b3-55d4-8ad0-44d84b007cfa | note | Conduct - S or C
7532abcd-c776-5607-be76-6eacf8266fcb | note | Produce Record - S or C
596503ea-5d2c-5b56-934b-78f1a70f9f61 | note | Approval - C
d444be00-3f8c-5554-9994-4134590135d6 | note | Witness Point Y/N - Y
a635a6b3-ce84-48c7-ba67-b0a199baa750 | checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
306315fc-771b-5bc1-b4ca-a721100dc139 | note | Controlling Documents - TNZ B/2 section 7.6
bd81db0e-74f7-562d-970a-0e744f8011a8 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
e55c9646-5b87-59ac-99e7-3ba685fd8088 | note | Method - Plateau Density Testing, Lab. MDD
cf8a0314-9725-5cf8-8213-8ab335ff02b5 | note | Frequency - At commencement of construction and whenever materials change
23ddc785-b3f0-501b-b34a-dbeb044640d2 | note | Responsible Person - Quality Controller, Engineer
d7bce9de-d6d1-5d1a-8ea3-52802b2c5996 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
6b5e9668-6423-5a88-9e1a-6d612298505f | note | Conduct - S or C
cbff5990-40c6-57ea-86c6-048815ac3816 | note | Produce Record - S or C
17aa457c-ad55-5b71-b4bb-5c26226556af | note | Approval - E
84c2f40f-1155-51c5-a886-b7023595f2df | note | Witness Point Y/N - Y
3717e0a7-88b0-4593-834d-682cdcd7af0f | checkpoint | Compaction Acceptance
ca9b83ee-f2c0-5a6d-8edb-0bf8e75eee9d | note | Controlling Documents - TNZ B/2 section 7.6
ae8d38ed-fcbb-5082-9c83-b8602ac9ef20 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
5abf6b17-b63f-56cb-97c6-fc4f30fc55b2 | note | Method - Nuclear Densometer Testing
d990bbf1-d78a-5ee9-adda-e5c78e39ae22 | note | Frequency - ≥ 5 tests per 1000m² lot
7b902dac-bbc1-5929-95bd-1c8fb5d64581 | note | Responsible Person - Quality Controller
a4d43e53-763b-5a27-bdf1-96141715b3a7 | note | Verifying Document - NDM Record
aea12273-7f10-578e-8667-49f0414f8b06 | note | Conduct - S or C
90ec02a6-5326-530f-ae60-7d2e851d0f80 | note | Produce Record - S or C
cbeedc65-6fbc-5598-9a57-a9416c30f3eb | note | Approval - E
3a9219c5-47dd-5eba-b3d5-fa76ded0702f | note | Hold Point Y/N - Y
218db989-cbb7-5776-a709-0014d2f436a9 | signoff | HOLD POINT
7957ff0a-3052-49cb-9fce-26ad42da0cc1 | checkpoint | Surface Shape
627455d2-4356-5121-8145-66adfd59cb9e | note | Controlling Documents - TNZ B/2 section 7.7
42c34a7b-2e91-5269-839e-957b3a82d1f6 | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
be0af55c-9a1c-5c1a-b0db-9841a0ff4e7c | note | Method - 3m Straight Edge
02607c8e-edc7-5254-9246-d5f2be1640b3 | note | Frequency - during construction and prior to seal
958a2e1e-a6c8-5718-b839-6b875e249fa8 | note | Responsible Person - Supervisor
3a72a22d-35d7-553c-a1ed-af4ee3529f31 | note | Verifying Document - Photographs
1f79110a-1474-5245-976b-faa3ab138137 | note | Conduct - S or C
189d1399-d047-5b2a-9b69-46fc876535b7 | note | Witness - C and E
9fb57d9f-24d4-5fd5-abda-797613069006 | note | Produce Record - S or C
2bd6da5f-ec04-5c89-8c16-3b36d0bd5267 | note | Approval - E
79eae6b2-c881-5508-9779-5ed9f48d5c9c | note | Witness Point Y/N - Y
27a6bf9e-7426-4f48-abfb-c1dd3ede51d9 | checkpoint | Cross Fall
1535f875-8d40-5026-b68b-2b4ea214626d | note | Controlling Documents - TNZ B/2 section 5.1
c21dec49-2011-5fc3-bb2f-f0021c8f4411 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
19825539-a9c6-5ee8-943d-617d81317a36 | note | Method - 3m straight edge or Survey Asbuilt
aabb52ae-bbb5-501b-b524-d15b62a2c7d3 | note | Frequency - during construction and prior to seal
d6d0e60d-0fb5-5f25-95f2-215fcb3e2041 | note | Responsible Person - Supervisor
7c6ac4f9-d30c-5cec-9c32-a84370f54783 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
c472ddf7-7a9b-5e53-aacd-e93d1932928c | note | Conduct - S or C
46bb5241-ce75-54b1-8c4e-814bab02dc08 | note | Witness - C and E
77246342-ce8d-5e47-acdc-f9b52e2253a2 | note | Produce Record - S or C
718ed352-974b-51b0-96a1-5778033d6d35 | note | Approval - E
0e994b4d-f463-542e-815b-a188cb7d970d | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
68a45bcb-39e2-5d71-a704-7a2d10de106b | note | Controlling Documents - TNZ B/2 section 7.8
2cbc12b9-67be-550c-a618-3233e4babab9 | note | Acceptance Criteria - Tightly bound matrix post sweep
c3d3b122-0fc3-5ed9-a101-8e1bf9f8ace6 | note | Method - Visual inpsection
d0ad292b-b958-5aa3-b16e-39d968c6cfd7 | note | Frequency - prior to seal
724c3a11-112b-5ba9-b580-3d638bcca847 | note | Responsible Person - Supervisor
687d9232-55c0-5ca8-a033-e06484836cd7 | note | Verifying Document - Pre-seal inspection sheet
78f8374c-e4cf-5343-8e03-44f83aa1625a | note | Conduct - S or C
786f5229-91b7-585d-ad85-e59f3f9b495e | note | Witness - C and E
b95ce13d-b1b0-59e8-a4a2-b3becbe30ae7 | note | Produce Record - S or C
7afbe174-ae48-50fa-8cc3-046a539797fd | note | Approval - E
f65616c6-f361-5834-b43c-0b491c7ecea4 | note | Witness Point Y/N - Y
ec9e4e4c-71fb-4d53-af5d-7b837b8e6839 | checkpoint | Degree of Saturation, DOS
02a1a164-3a38-5d0b-bb3a-cc56b6895707 | note | Controlling Documents - TNZ B/2 section 12
05122b96-c66a-5caa-8313-6a3747a4e848 | note | Acceptance Criteria - ≤80%, however 65% is ideal
a038585f-880b-57d6-b195-857fa786922b | note | Method - Nuclear Densometer Testing
8a8dd441-fd4a-555a-bb6c-4db99d54f6ae | note | Frequency - ≥5 tests per 1000m² lot
91834670-6d30-5c84-b3e3-0a1c5043a67a | note | Responsible Person - Quality Controller
ddff222e-f2d1-50ad-a56c-f25f01e2a037 | note | Verifying Document - NDM Record
fd9e7f5f-a629-544f-b04d-484b39f02d3b | note | Conduct - S or C
ecc355d8-0ea4-502f-8ce3-2ee6ec1db0ce | note | Witness - C and E
8b2c0e7d-185e-5f21-9ed7-d51b77c78c75 | note | Produce Record - S or C
792f65e1-4ae6-5cdb-b2ab-82387e4fcce4 | note | Approval - E
0caeb65d-1028-55d9-8d4a-335e5662787b | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
db01c763-a4f5-540e-8c24-75d388004576 | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
aa1db764-a9a4-552c-93fa-5e2354177447 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
3d04b594-4580-53ed-9a6b-da762f9f0831 | note | Method - NZTA Maintainence specification section 6.1.2
79eff727-9780-5447-8cf3-2c0e9ec13b97 | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
7538d6ca-4c08-5934-8dfc-9087ba38693c | note | Responsible Person - Quality Controller
faae05d4-9e48-5d34-bbca-b2b86d8d1e5d | note | Verifying Document - Test Records
32668344-236d-568c-be25-deae334d3878 | note | Conduct - S or C
17119a05-6c66-56e8-81d4-93195eb4fbd0 | note | Witness - C and E
2f02ce29-1c6f-5976-9222-ca34a5fdab6c | note | Produce Record - S or C
c7047cb2-75ab-51fb-9aec-709a38b275bb | note | Approval - E
d6ed1d48-beca-5384-a2ef-0afed89f5ead | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
f6ac91d4-5c0b-53d1-9e4e-00bc03939ff3 | section | 5. Chip Sealing - 5.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
106bfefa-2d3d-5e2f-a702-f648dcf8e063 | note | Controlling Documents - TNZ M/1
93e0b427-df7e-50b3-9e18-3ac200651925 | note | Acceptance Criteria - Table 1
91327dcd-f1c1-5091-9de0-10bd77559040 | note | Method - Property Test
ca627b73-98c8-5262-aef0-a5c029de159c | note | Frequency - Annual
d8370045-811f-55c1-b2ae-f63a4e53c4d8 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
1842c9d1-12c7-534a-b5d1-29abad9744ab | note | Verifying Document - IANZ Report's
4caeda29-979c-5d43-b9ef-e27b0398e9eb | note | Conduct - C
bf565a17-1e1d-50a2-baa5-228fe386cd92 | note | Produce Record - C
1da30360-988d-5dec-a2ca-079d7a95a1a6 | note | Approval - C
0a0c1060-1e11-58b6-9eb6-de8ecc08a61a | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
34635e83-e838-570a-9072-9da1f91490e0 | note | Controlling Documents - Higgins Internal Specification
493487cd-ee1d-5fc8-a69f-fa20364d6de9 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
45734de5-39c5-535f-8653-c34fa0912c4b | note | Method - Property Test
a6546f4b-4b19-562d-8d19-d19986ea4341 | note | Frequency - 1/100,000 litres supplied
d177643f-0166-50bd-9a20-7f28d9dc1227 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
0b5e8fc9-3f08-5d50-86f6-974bb9e66955 | note | Verifying Document - IANZ Report's
8962ff59-7237-5b9c-aa22-5aaeedbf3c4f | note | Conduct - C
679253ef-b996-5cc6-8b88-d13a8b241270 | note | Produce Record - C
e713409a-102b-5ef8-9d42-73b3712e90b1 | note | Approval - C
d6261fdd-9f26-5052-9894-ff2969f21567 | note | Witness Point Y/N - Y
174951ef-f0e8-5f87-83c9-3694b3ba5a0c | checkpoint | Source Property - Coarse Aggregate - Crushing Resistance
e96a9f9f-c5ae-58c5-b5fd-70989cf03109 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
74f7a3e7-3d97-57c8-90f8-94669f249a00 | note | Acceptance Criteria - <10% fines under 230kN minimum
cf11763d-b01e-5686-bdd6-bef9343444e8 | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
8e483655-0924-54e5-9001-a79b974ee0c3 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
9b446521-035d-58fa-ac07-8fd36d218d26 | note | Responsible Person - Surfacing Project Manager
00918bad-eb2b-507f-8edc-3bb93946a861 | note | Verifying Document - IANZ Report's
d52bcc1d-5b15-5e06-8207-a795dc2dad7d | note | Conduct - C
290b0b37-1035-599e-ace7-bccc181f6806 | note | Produce Record - C
fbb1d986-0201-5987-a633-f855e90faeac | note | Approval - E
d9a9b99a-4115-5962-95c9-8cbe8940f3ed | note | Hold Point Y/N - Y
b8b2aebe-9a6c-5b72-97b2-e45898d8950e | signoff | HOLD POINT
5bc5dc00-5acc-503f-b6e7-c1b5d9afc85a | checkpoint | Source Property - Coarse Aggregate - Weathering Resistance
8c13ddfd-caf3-5de0-8f57-7f24a83f31b8 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
9627d1dc-09eb-5ff1-8547-e85aa1cb85b1 | note | Acceptance Criteria - AA or BA
3bdb9071-4b01-5642-8066-0ab1849b6b9b | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
ef87ba8e-3293-59a0-879e-16fd8ae70d6c | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
e6633395-f812-523f-9643-cd91b8dfdb27 | note | Responsible Person - Surfacing Project Manager
5f30435c-0aad-5b51-a628-447b079b03d9 | note | Verifying Document - IANZ Report's
69937f97-4b43-5e9e-b75f-e82a3106790d | note | Conduct - C
b87c0174-0287-5074-9af2-832d5ea311f5 | note | Produce Record - C
3528713e-9090-5f73-a010-66da617e3334 | note | Approval - E
2d7dd1ca-7297-52b8-a44e-f370f6bb4454 | note | Hold Point Y/N - Y
998e13d0-06ee-537b-924a-16d60188ab2d | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
c09c96e9-b583-5e1d-9e90-a08dc889fcf4 | note | Controlling Documents - NZTA T/10
4b977c22-5c5e-520e-bba7-1925e2837f90 | note | Acceptance Criteria - Meet Skid performance Requirement
75f65ad5-c867-5864-b3ad-2efa2e3246e8 | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
f509c758-436c-5cad-a1a7-0a5883731bee | note | Frequency - Each Site
7c33239c-7340-5757-9f5a-d3c2fad02b36 | note | Responsible Person - Surfacing Project Manager
6f0e4a50-4083-5b1a-90ff-879367ed88ab | note | Verifying Document - IANZ Report's
a35db03b-2e7d-52de-b3f0-3262bfc6a3d3 | note | Conduct - C
e86376e8-c38c-59bb-8189-43b1c1b2ecaa | note | Produce Record - C
bbc6b528-8cd4-598a-942e-a2f5bfbc0c08 | note | Approval - E
3f295b0c-aaf8-5025-bf5e-7dc7971f71b1 | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
900248fe-96b0-5f93-a8f7-1452facc6b79 | note | Controlling Documents - NZTA P/17, M/6
d48ec4f7-59a1-5d1c-a83b-4a14c6b5e25e | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
7fd32ad0-fde0-53eb-bed0-b240c3fc85d8 | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
22ded9dc-70f6-5f6c-8e78-62051ae5bfea | note | Frequency - Per Stockpile
9527adaf-93c8-5be9-9f7b-3f5cec601cd0 | note | ○ <100m3 - 1 Sample
28be1ca0-f11c-5dbf-9387-4448d653ffdb | note | ○ 100-500m3 - 2 Samples
567a0512-c6d1-5352-85e5-370f08f96131 | note | ○ >500m3 - 3 Samples
9b86177d-2eca-5799-8202-5cc611aa1ab8 | note | Responsible Person - Surfacing Project Manager
688a5437-5065-5776-9994-2b0f14356c0e | note | Verifying Document - IANZ Report's
7d922941-3ab8-5bfe-9a22-6fd446228927 | note | Conduct - C
6da0872a-9869-54f0-a284-e23928a30798 | note | Produce Record - C
303dc5e9-526a-5bcc-8f9b-ff6f51634f37 | note | Approval - E
04b90094-467f-56b3-a475-e76d60e437ed | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
b7eeef70-2d05-5844-b10b-4667b5e7e4f1 | note | Controlling Documents - NZTA P/17, M/6
299a2b37-d08c-56ac-a937-29c8ccd70aa6 | note | Acceptance Criteria - As per Table 3 NZTA M/6
034e181f-127a-55bc-8d72-2a9e62ee071e | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
a5af50c4-788b-5a6e-a4a4-3e67a86402da | note | Frequency - Per Stockpile
c41bbe30-1fbb-535f-89d0-5a3c1aeeb149 | note | ○ <100m3 - 1 Sample
04a2f188-5ae6-5875-b6a6-95b99b1de411 | note | ○ 100-500m3 - 2 Samples
c40cbcd5-ed0d-5f60-99c8-2e8a86827757 | note | ○ >500m3 - 3 Samples
0ac15e4b-bbe4-56e3-98b5-ef68d6b3d94d | note | Responsible Person - Surfacing Project Manager
b0fd733a-eaaa-504c-a3e8-ed27a294a068 | note | Verifying Document - IANZ Report's
96071617-ec9c-5eed-aa8a-af4248bcf30e | note | Conduct - C
28264bd6-5540-569a-b24e-cd430739bf87 | note | Produce Record - C
ee1d438c-6fcf-5c74-a9b4-3d9da24ffe40 | note | Approval - E
737cc71a-4d3b-5b13-aa3f-430dda7764f3 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
aa5f68af-9f43-5b0b-a357-a9087812716d | note | Controlling Documents - NZTA P/17, M/6
2ce185ec-da2e-5838-a606-a9f0105b5474 | note | Acceptance Criteria - Min. 98%
d850a165-7b0f-5570-8331-b93cc78acbe3 | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
54ba0df6-d9af-54f2-a0ff-810a2f3129c3 | note | Frequency - Per Stockpile
1464e7e8-14c6-5fca-8271-54e88545421e | note | ○ <100m3 - 1 Sample
93716464-3a91-5cfe-8042-c1f0f7f01e4e | note | ○ 100-500m3 - 2 Samples
5668943b-29bb-5b9b-93d8-39607e479da3 | note | ○ >500m3 - 3 Samples
75a03c2b-d37e-5e8b-8732-4e951453102e | note | Responsible Person - Surfacing Project Manager
39376965-bfd4-5d29-b022-c56a51df71e1 | note | Verifying Document - IANZ Report's
fe82d55d-5467-59e0-acd1-bb03a0fbdf82 | note | Conduct - C
ac668177-0312-541a-8582-30d8b4e9c302 | note | Produce Record - C
52840833-745f-5138-96b8-1344bec5afd9 | note | Approval - E
f98dc905-57ac-5027-ae8a-59ca433a293c | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
773c5a97-db24-5183-aca8-50f9fe1065b6 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
5b0dc83d-5bc3-5fa7-bc3a-f719ec7bfdbc | note | Acceptance Criteria - Client Approval
572b2a27-7775-543a-9e53-8e8ff79f875c | note | Method - Review
6d9be3ff-47ef-5f02-a4ae-955b5122c83a | note | Frequency - Annual
3c73a5ea-3f08-5ba3-b39e-0a4a6923cfde | note | Responsible Person - Surfacing Project Manager
fc8b3c5c-aafb-5255-8ff4-517be60d2d17 | note | Verifying Document - EBOP NOC Design Report Acceptance
46bb3865-4575-50e7-9b54-9ffeba7b4e10 | note | Conduct - C
6f5fc6a6-7e40-52a6-bfed-9a3c82743b75 | note | Produce Record - C
f8f9941c-ca46-5c7c-814f-bf4c6e36797e | note | Approval - E
3bd94641-db9f-5b6a-88c6-4a177e3ffd25 | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
2d90825f-40a1-55cc-9369-13e616f644fc | section | 5. Chip Sealing - 5.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
83b9af8f-6cda-5ccd-b706-5f6e25736772 | note | Controlling Documents - EBOP NOC Design Report
10afed5f-cac6-5b5e-baf1-313c6bacc46d | note | Acceptance Criteria - Visual Inspection
06bffddd-dadb-59c4-ada5-ee8b0adc0bb5 | note | Method - Visual
be7f5202-f060-55d2-89d8-fca49c0c14a1 | note | Frequency - Prior to start sealing each site
79f2ea97-3f93-5dd2-9792-73f8a4377ba4 | note | Responsible Person - Surfacing Supervisor
7aeb5c8f-920e-5a7e-9773-ea66a558dab3 | note | Verifying Document - Chip Sealing Quality and Site Record
834ab158-c757-53e0-ae82-b8e504b76b9e | note | Conduct - C
68c11a34-e7fb-5077-9262-0e000d69a0ef | note | Produce Record - C
f9a3ae95-2f70-5240-945e-7f9406b2f7c5 | note | Approval - C
6b6d646c-7e66-53df-87c0-48f2cf57e2f1 | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
0dcf653c-dbac-5ba1-b0d3-88ea8889d10c | note | Controlling Documents - P/17
bc224447-b472-5ade-be2d-3b366d54506e | note | Acceptance Criteria - Visual Inspection
0c9789d2-6466-55f9-a2d5-76e755de4d69 | note | Method - Visual
2b74c182-e597-59a3-ad41-779ecc352d85 | note | Frequency - Each site, prior to start of sealing
84ab21b4-b2a3-53b9-9888-e7c854bdcf23 | note | Responsible Person - Surfacing Supervisor
fa6f52d3-c899-50c8-bf9c-2c0100d43b6d | note | Verifying Document - Chip Sealing Quality and Site Record
ff3a4b8c-6bdb-502e-b9ad-9375b1526b5b | note | Conduct - C
e5c01e48-37eb-5dbb-9e64-2c430354daff | note | Produce Record - C
36a04b4c-1965-510d-a2c2-ab65757df0cb | note | Approval - C
0536b12b-d8c8-5522-8e8b-21d6bedc5c2f | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
3dc78d41-502a-5450-b564-20319728751d | note | Controlling Documents - N/A
de708775-6c79-54b4-8b31-ad7ce145c22f | note | Acceptance Criteria - Visual Inspection
967493ac-7971-5811-bcc9-6d76f392847b | note | Method - Visual
fb61febf-a208-5a85-9ee6-ff8cb6b026b4 | note | Frequency - Each site, prior to start of sealing
83cc63fb-e08c-5655-bf25-c713dd7c3761 | note | Responsible Person - Surfacing Supervisor
2fad295a-2362-5863-a192-d9bbe0ddb5a2 | note | Verifying Document - Chip Sealing Quality and Site Record
24d9dec2-ee9a-5167-8424-cf4e7e7f28aa | note | Conduct - C
c071fd57-18cf-5339-af50-74176e128de9 | note | Produce Record - C
e3e52af0-e35c-542c-9804-7954136f3231 | note | Approval - C
8c472a9d-74fc-55b5-9bf3-efad4302cdcd | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
3fc8d859-c773-59b2-aa61-f9b262d9734d | note | Controlling Documents - EBOP NOC Design Report
b111173a-d676-5d2c-8713-02da934044f6 | note | Acceptance Criteria - Details/chip correct
d5d0f92b-1555-5cf8-adc3-8a657e370f57 | note | Method - Visual
b90731b8-bd67-5cae-a01c-03762cf10d62 | note | Frequency - Each Site
9226b789-1ce9-52b8-bc98-213eb27627b1 | note | Responsible Person - Surfacing Supervisor
506cda9d-0fdc-596a-bef3-4170758b496d | note | Verifying Document - Chip Sealing Quality and Site Record
274b497f-fdf5-5183-9111-75d1e40a882d | note | Conduct - C
221b7a94-5ffe-5aba-9c8b-0aeb4f36964b | note | Produce Record - C
3af54043-a32a-5af2-9c49-210f0862116b | note | Approval - C
910cabee-f3e3-5751-9932-e4f5bae42939 | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
988f5889-3d64-5784-9254-e779de78b31c | note | Controlling Documents - RNZ 9803_0513
4b048d46-47bc-56e7-944f-5d484537d586 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
3acfdd2d-d76c-5888-9254-3348451160ee | note | Method - Sample and test
b26e18fa-a68f-55aa-a619-8481a3cf5a8b | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
1ad3507c-6cdf-509a-af6b-715f4ea60c60 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
64ba1057-b3e5-5b3b-a67d-a87ddd9f489d | note | Verifying Document - IANZ Report's
1d62e4c9-f616-5bb8-9f53-229783fbabb3 | note | Conduct - C
13ad352f-a2c1-5cd1-a623-78c77850e59e | note | Produce Record - C
3e784a99-6b5c-56c0-9ead-f66b203d49e7 | note | Approval - C
f1b890f2-1eb9-588e-8d05-89711c651272 | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
7fd99544-0377-5f93-8050-a10c8d633385 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
4bc75e23-ce7c-5059-88cb-1b51b0d2a6aa | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
982202ff-1b71-5a62-a0f4-c140512d7eca | note | Method - Test, Review
53e08aae-2453-5d38-96cd-b1f2900ab452 | note | Frequency - Per Sprayer, Per Site
ba253db4-7e95-5f77-842d-7bbeca078e13 | note | Responsible Person - Surfacing Supervisor
7a7cf6ec-9bff-56de-959c-5081d0c220cc | note | Verifying Document - E/2 Certificate. Spray Sheets
74911001-9877-542f-81de-b3890b2d78d9 | note | Conduct - C
e1776c08-90e0-5be5-b603-4124f1c73ed8 | note | Produce Record - C
573a5774-6e15-57a4-9a5f-f86ab8ea73d8 | note | Approval - C
10eb03c4-7ce9-5b63-8cfa-b8461f9e9fa5 | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
977caac1-d785-5020-aba0-3c15cdcba6d4 | note | Controlling Documents - Chipsealing in NewZealand
0864d9bd-5327-52e9-b417-e27065f3bb77 | note | Acceptance Criteria - As per Chipping Guide
b2c6f21b-8537-517e-961e-33979a021f89 | note | Method - Visual
49cd8409-b273-5c90-92bd-8293739a98e4 | note | Frequency - Each Site
048f8209-510f-5c13-b432-ba0d9e04f12a | note | Responsible Person - Surfacing Supervisor
a2d91f66-efba-5002-ad54-af513fdaf544 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
397fea85-60d8-5407-bf05-965cccdfff4f | note | Conduct - C
ae92843f-ba18-5c72-ad9b-5199cbcf63d6 | note | Produce Record - C
cd0b0839-7f9c-5029-b3a5-7c825bb26e2c | note | Approval - C
a0d4417e-f3fb-5ccd-a4e1-07f867967cfe | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
a654d364-c3a8-5b67-b346-b959f3649894 | note | Controlling Documents - Chipsealing in NewZealand
36251c0f-ad37-5be1-810e-c9bedeeb825b | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
46918674-2395-55be-9d75-37126d6f1ebf | note | Method - Visual
30ed342f-0819-5d68-9618-07fd5acac87a | note | Frequency - Each Site
1d382f0e-d787-5f0f-aa49-bc2745f4bac2 | note | Responsible Person - Surfacing Supervisor
d08447a9-9e1c-5e9b-8a8e-59b6bf1fc594 | note | Verifying Document - Chip Sealing Quality and Site Record
2a4344e7-e5e9-5216-a58d-fb1e6700f8be | note | Conduct - C
87a05e2e-4db3-5570-b1c4-fe6eff4161d9 | note | Produce Record - C
faad68ce-8875-59eb-ac28-1e7c5dbaa3e8 | note | Approval - C
96c5b7aa-4829-5512-8bb4-72ab5d8a3864 | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
33afa5e4-b921-5b67-bf46-527867654857 | note | Controlling Documents - Chipsealing in NewZealand
c39be899-7be9-5aa6-b31b-b3c77b32026a | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
03d278a3-6ea4-51b4-aa4b-41e396f904bb | note | Method - Visual
23b6a573-5d5a-54e8-b4d5-e538a6a2db90 | note | Frequency - Each Site
c2447066-fe88-5011-8c0b-7741bab686c6 | note | Responsible Person - Surfacing Supervisor
6f184dd1-8cd3-5a2c-a62a-d4f62f6707f4 | note | Verifying Document - Chip Sealing Quality and Site Record
ecef6417-11aa-5fca-83ff-188d48e243fd | note | Conduct - C
b313a2cf-db20-5644-a313-ed040df429a8 | note | Produce Record - C
bf544032-3363-5bed-acf0-383b79ddfcce | note | Approval - C
98cec6f8-ad2a-58af-86cb-7c33798a2552 | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
5927cbac-304d-5b30-861a-2bfa85416e43 | note | Controlling Documents - Chipsealing in NewZealand
6dfa25a3-4b66-5d07-b730-0b26e33b9850 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
a5fa5613-f862-5bd6-8cd4-a439e1b3427f | note | Method - Visual
832777a6-ebd0-517c-96db-6d803f0fbccb | note | Frequency - Each Site
829d6670-7d8c-546a-8776-da79db296991 | note | Responsible Person - Surfacing Supervisor
9de8bd14-08b5-5b95-b9c5-9b5ce4b697a0 | note | Verifying Document - Site Record
800ec965-519d-5c30-a33a-0af6c37c4d9f | note | Conduct - C
1aa60f63-0e21-5da0-97b1-79df72056480 | note | Produce Record - C
424a8242-21c5-5b07-8011-8c8d8dfe096c | note | Approval - C
a366d32e-c084-565d-b97a-23004d64355d | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
eb222bbc-dbaa-5d93-9afc-15479fdae1b7 | note | Controlling Documents - MOTSAM
cb11433c-60af-5af6-bd38-87dab6c4981b | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
748d47db-eac4-5b02-a7f6-f881d89919a9 | note | Method - Visual
5c128e1d-8767-56f5-b136-9f1911a677b6 | note | Frequency - Each Site
8da71cd3-642a-57a5-b196-202cead79706 | note | Responsible Person - Surfacing Supervisor
b845cfb2-4a3d-5539-b566-c29dd7dea456 | note | Verifying Document - Site Record
e2978566-2d03-592a-810e-818b0409f6fa | note | Conduct - C
0869f03b-8352-543f-ad61-ec408a96af33 | note | Produce Record - C
fb471c14-60a8-505a-87ab-4775b6a2cd66 | note | Approval - C
3df3d75a-44f0-52e6-b24b-6386be9c6fd9 | note | Witness Point Y/N - Y
2fa24de8-fb07-5d57-947e-3eea20cf5b9a | section | 5. Chip Sealing - 5.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
f3bae9b0-cffa-53bb-aa58-804783cfb983 | note | Acceptance Criteria - Formal Agreement
571b05ba-4eeb-567b-a767-5ceb968bd444 | note | Method - Visual Inspection
cfb88bd9-74e8-5364-9ac3-49a5774fcf4c | note | Frequency - Post seal sweep
609545cf-efc1-5686-b7e0-54d46157ccdf | note | Responsible Person - Quality Controller, Supervisor and Engineer
3a935f3d-cd39-5e41-bdc6-190b88843f66 | note | Verifying Document - Meeting Minutes
5d18cc9a-a669-551c-aedf-4feb663f115c | note | Conduct - C
fc871a13-99ed-528a-a5d7-1de8b646c917 | note | Witness - C, S and E
713ced36-2c0a-5466-b45e-f93b9b2a660b | note | Produce Record - C
8a3c5b29-ad9c-58ad-a888-abc7b7951415 | note | Approval - E
3f20c9f0-9148-50ed-87da-1dc37d2a72c9 | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
a8719cf7-e163-56b8-8168-acc1e9552819 | note | Controlling Documents - NOC; MS 6.1.3
5a54e316-cce3-5545-aace-a5a4c4b1b557 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
39a9d47d-e48a-576b-855f-1fc999f5bfe8 | note | Method - Record
167602ff-f167-5c97-b7e0-b03ff3b5790c | note | Frequency - Within 2 months of completing the annual resurfacing programme
e2c0a9a6-caa9-561d-84b5-80adbe00e655 | note | Responsible Person - Surfacing Manager
8640257c-3ae7-5fe5-8134-e944106d0529 | note | Verifying Document - Construction Completion Report
4e3ebea8-4ff5-532f-9d9d-c5090b83ef39 | note | Conduct - C
f3840b11-ec73-543f-a39f-72742f27e866 | note | Produce Record - C
179b928f-fd75-515f-8eee-2ec50509ef83 | note | Approval - C
922c0796-1134-5ee7-b903-3ef81494aadc | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
a3afcae1-802d-5a4f-9abc-4bef5880e007 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
4da15e35-c6e7-5767-bf9a-abc1a4cd78e8 | note | Acceptance Criteria - Engineer Approval
fde4e76c-08b7-57e6-ae03-e0643a0c8c4b | note | Method - Visual Inspection
9b5dcc39-1467-5a29-b0e3-4aa921bbc2ff | note | Frequency - ≤2 months of 1st Coat Seal
a59ad839-8f56-5440-8278-11f4c2042d07 | note | Responsible Person - Quality Controller/ Contract Manager
7e60e1ae-c5ff-511c-af01-c01212fa430f | note | Verifying Document - Signed Report
84d52170-ba47-533c-b4e6-f9bcc31a555c | note | Conduct - C
ba5a9d79-ae08-5925-902b-6cd2705fa82a | note | Witness - C, S and E
df56814d-1fb7-5015-91e4-c618e8f55529 | note | Produce Record - C
0f75c79e-3692-520e-9b22-913726cd4ee2 | note | Approval - E
0bb903c8-29b0-5313-9b7f-b8f23095c818 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
22c69647-2c26-55f6-993f-cd9d396dbb32 | checklist | Overarching ITP items | itp | Overarching ITP items
482c5180-9e7d-518a-ad31-85eb432d587d | section | 1.0 Overarching items
803d1ba7-68b5-5f2b-9840-1962a1303d31 | checkpoint | ITP submitted and approved
0fc1927b-50e5-5171-8c53-40457058b89a | note | Type - H
b36af855-4be7-5802-b7be-6a96f571ecdd | note | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020, head contract
e16469a1-d802-5e4e-af63-5164e6e898cb | note | Method/Test Required - Confirm ITP approved
63053c66-e5ca-5580-b641-87d6d7a8ac12 | note | How Often? - prior to start of season
2a17914a-dc68-545e-8085-9710291c422d | note | Records Required - Copy of ITP and acceptance from Waka Kotahi
98a788e3-048f-5e4c-ac86-3e0a73f0aca3 | note | Responsibility - Project engineer/Renewals manager
484dd672-9963-5b0f-9243-44046b4ae548 | signoff | HOLD POINT
c2054842-2893-5e89-85e0-b42acac72a08 | checkpoint | QMP submitted and approved
10ac3274-17ac-50a2-b25f-569d5033026a | note | Type - H
fdfc044d-320d-54fd-a765-c01fa07c1e2a | note | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020, head contract
56681101-7a9b-5576-87a3-296bb27898bd | note | Method/Test Required - Confirm QMP approved
25066255-614e-5aa4-8d19-6e400a0cfd05 | note | How Often? - prior to start of season
d6d14c20-3472-5f69-8e80-a779c40d6a65 | note | Records Required - Copy of QMP and acceptance from Waka Kotahi
a9ba89e5-ebca-505e-a368-b216d111609e | note | Responsibility - Project engineer/Renewals manager
290324df-d601-548c-8883-2477898c115c | signoff | HOLD POINT
376fc906-d17b-5a2d-8671-fcf42783ce45 | checkpoint | QA pack submitted and approved
fdfe89e2-1e34-52ab-bff2-45efb64a37d9 | note | Type - H
9875edc5-cbc2-5105-9abb-04dcafd83c6d | note | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020, head contract
99c95b22-d229-5a67-83bd-f460c6a59b11 | note | Method/Test Required - Confirm QA pack approved
a61d59c6-3b3d-5cdc-afed-2a9c2ecf606a | note | How Often? - prior to start of season
8590dc90-2aea-5c02-ab4d-865c73f71461 | note | Records Required - Copy of QA pack and acceptance from Waka Kotahi
76286729-a87e-5847-a568-c0b076552f94 | note | Responsibility - Project engineer/Renewals manager
2a4a0934-df79-5efa-90d2-31a951351458 | signoff | HOLD POINT
51f4645d-39cd-5b32-adff-c73925523d7b | checkpoint | Final approved program received
8265e0bf-8d61-5404-9b3f-e0de7c47aa76 | note | Type - H
63dc3e84-e6d3-5fa2-9350-9e3a63e47429 | note | Reference or Specification -
e8cd8367-8915-5a4a-ada0-7cc8c056c916 | note | Method/Test Required - Confirm final program
211c2e12-2c5f-5a38-9b96-579ed72acfc9 | note | How Often? - prior to start of season
70afeed8-d02a-5d9b-be56-de7f49609ef6 | note | Records Required - Copy of final approved program; TAC, SAC and SCRIM
13aec8c0-a08d-5964-8edd-f9ddd69aa52e | note | Responsibility - Renewals manager
67932d51-23d7-55bf-b352-88303e06497e | signoff | HOLD POINT
3ba2c1bb-9d15-5bc5-a59b-80f8a9ee3514 | checkpoint | Ensure accuracy of tracker with final program
4be23902-250a-5104-836a-47e566649437 | note | Type - I
fc393106-f791-5da4-a525-26d5f28ee834 | note | Reference or Specification -
2087a90c-8027-5577-9212-e25145ad1c89 | note | Method/Test Required - Crosscheck tracker with program
45f77a92-c08f-5b06-8ff9-c2f2cad8a609 | note | How Often? - prior to start of season
8178a054-d435-5b89-9fa8-38d87ad7b332 | note | Records Required -
36917c08-5fe1-5d2f-8eb4-b0398f8a66df | note | Responsibility - Renewals manager
610765e4-7bc0-52f0-a526-8d50d5a32525 | checkpoint | Pre commencement meeting with asphalt delivery team
1589e8de-af9e-557f-9961-94b29a5a9b5c | note | Type - H
ed3d311e-42f5-58a6-a7a3-d3e5c6f40588 | note | Reference or Specification - QMP
7b6472c7-ef8f-553f-a45e-6b88646e5f59 | note | Method/Test Required - in person meeting
b3aaee3c-c909-5049-b7fb-1f5a01b90ae0 | note | How Often? - prior to start season
fef34b34-a29b-59d3-bc61-1e2ee10a1a27 | note | Records Required - signed attendance register
52da9fa2-352a-5838-a128-acd3f3c3c811 | note | Responsibility - Paving manager/Project engineer
a92edb0c-32b2-56f6-8bc0-c5515543c85d | signoff | HOLD POINT
3512d8b1-4667-58da-bba4-4a841e47305e | checkpoint | JSEA submitted and communicated to team
11827823-c1be-553b-aa21-05f2f2529636 | note | Type - H
2c55c58a-b041-5332-990c-40c0aad8f4a8 | note | Reference or Specification - QMP
51f9dc20-f107-551f-ad9c-8d7bd3d9cb94 | note | Method/Test Required - JSEA approved
5c1c041d-9733-5765-8dd3-4f9b5723b9b5 | note | How Often? - prior to start season, updates when required or site specific additions; To be signed on by every person working on the site
777a127e-922f-58b1-83d9-7aa7b5b11f23 | note | Records Required - Copy of JSEA signed by AC delivery team
71dc3076-1335-5e4d-9b9f-47c1ea3eefb7 | note | Responsibility - Paving manager/Project engineer/Supervisor
7fa5883f-80ea-5611-bf0a-0f754a5e0d7c | signoff | HOLD POINT
4fe59c90-0c1b-5df1-9587-8e06672c7e1e | checkpoint | Approved JMF for Strengthening Repairs Mix
a98402d0-9580-5ec3-8e84-c128b7e15c66 | note | Type - H
b604525c-7ba4-5ca5-9e05-589f957db204 | note | Reference or Specification - Design Report
e961a2c0-2c2b-57c9-a455-8fcac62cbca1 | note | Method/Test Required - Confirm validity JMF and conformance with Design report
15640ec6-1723-57f0-9d83-71d4df17ab5d | note | How Often? - Each mix
b6089f28-50a6-5190-bdf0-2698c90028ba | note | Records Required - Copy of Approved JMF
0670c16c-706d-5461-909e-3f043300a26c | note | Responsibility - Plant manager/Project engineer
d44cba0e-e515-5d99-b775-834bfea24892 | signoff | HOLD POINT
a6395029-d25a-5e08-8872-3b56c7965d81 | checkpoint | Production testing for strenghthening repair mix
09331878-3958-5f95-8359-605b7898091c | note | Type - T
72b35e45-c2ce-58ba-a265-37708d1ab33f | note | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020
74ac57bc-d122-5bce-84a0-cc451e44760b | note | Method/Test Required - Binder grading testing Volumetric testing
62979243-1112-5bc6-a2e8-c47fd53308fc | note | How Often? - 1 test per 200T of Mix produced 1 test per 600T of mix produced
08052a9b-bb8a-5926-a7f3-c482725d2f40 | note | Records Required - copy of IANZ accredited lab test report
51457d6e-8ade-5e2d-8e79-2216c49fe5d0 | note | Responsibility - Plant manager/Project engineer
e279e5a7-7698-57df-94f0-50781a0cae6f | checkpoint | Approved JMF for Wearing Course Mix
5691ae3a-d2b3-5364-b88f-191b7d1f8913 | note | Type - H
544b3f8d-a8e1-5e68-b51a-4b32c9d0d785 | note | Reference or Specification - Design Report
02ab0525-68a3-518a-865d-0b4f311b4e8b | note | Method/Test Required - Confirm validity JMF and conformance with Design report
2e5e43ab-a47c-501a-800a-1a152a5798a2 | note | How Often? - Each mix
7f6a1ae5-b8a8-5c4d-918e-fb36c97625be | note | Records Required - Copy of Approved JMF
96f74df3-6100-54b4-8ea6-a7be3d71a40f | note | Responsibility - Plant manager/Project engineer
20ed2ea5-7cd0-5853-adc7-9e673ae2b42d | signoff | HOLD POINT
d4b7a4c3-ece8-5c4d-aea8-510b008e2103 | checkpoint | Production testing for wearing course mixes
9fd17f12-5fde-596e-896c-d9b3bd24901b | note | Type - T
9cf506f4-4566-5e43-8a8f-aeced2fa6cf5 | note | Reference or Specification - NZTA M10: 2020, NZTA M27: 2020
a9552e6a-6870-5c6b-9e5d-c2f33596c44c | note | Method/Test Required - Binder grading testing Volumetric testing
1e7af889-47ed-5956-95c0-bae22a27e9fa | note | How Often? - 1 test per 200T of Mix produced 1 test per 600T of mix produced
f87718cc-8020-5fdf-a672-d8d9ef151753 | note | Records Required - Copy of IANZ accredited Lab test report
5b894ac6-00ae-51e5-85d2-efb48ce51eb8 | note | Responsibility - Plant manager/Project engineer
36a9c5be-4485-5f56-9f88-9f8eecd524a9 | checkpoint | Confirm or establish , NDM offset and rolling patterns
4b54077b-6f6d-5fc5-b84b-d16ad68f0e9f | note | Type - I/T
13afb9e6-dda0-5fbe-aa2d-bb34fb1dfdee | note | Reference or Specification -
bbed31d7-d56e-5fa2-a44b-019d3cffee35 | note | Method/Test Required - Lay down trial or establish a rolling pattern on site
434a1d95-4fc5-5dd0-9cc6-2d54cd2df4ac | note | How Often? - each mix
443d65e3-1658-5310-9e26-54fc1abb9122 | note | Records Required - Lay down trial report or plateau testing
8e01e37a-a61d-5ca7-86d3-f11fe39801fd | note | Responsibility - Paving manager/Project engineer/Site engineer
4432f45a-36a3-5c4d-a755-6c3857da571b | checkpoint | Post construction drive over
4e8bfcfc-1ecf-5ba7-9bff-63a607ad5ba8 | note | Type - I
243fd4b6-0e86-5072-81dd-964ee1e7f438 | note | Reference or Specification -
55524a6e-f951-51d9-9fdb-0522cefeb785 | note | Method/Test Required - Visual inspection
3ebc9005-c72f-5b7e-a222-524576b7bab6 | note | How Often? - end of season
388d25c3-c056-5f83-808d-a6fcd79096d8 | note | Records Required -
2dc9552a-1ba2-50a5-b37d-b87333111af0 | note | Responsibility - Renewals manager/Paving manager/ Project engineer
6a87952c-ba80-50fa-a9b3-cc8de15a0070 | section | 2.0 Out Of Season Paving
93ff069e-d97e-5eef-9efa-65d7e7b89d92 | checkpoint | Out of Season Paving
78208beb-0365-5705-a6a9-646494b14e3f | note | Type - H
2c4a3477-9673-5720-b37c-7f6dbaf0a02d | note | Reference or Specification - Winter Surfacing Site Note
b1511bd1-52b3-5322-8f30-a975ef3c810e | note | Method/Test Required - Waka Kotahi Approval
2b4e0d09-a98e-56c6-99b2-0671d326ab10 | note | How Often? - Per Applicable Site
46f9d6bb-af20-59bf-a2a3-3b5192c2262e | note | Records Required - Copy of Waka Kotahi Approval
37dd7586-6b65-5bb1-bace-5034b812a8af | note | Responsibility - Renewals manager/Paving manager
6bdddd88-f486-58d9-ae35-2a0b4c9d9222 | signoff | HOLD POINT
033e08f7-363d-54cd-88a1-4e89db8ab48b | checkpoint | Dispatching Temperature compliance
5f77712d-b18c-5355-82d5-af2c02b82502 | note | Type - T
429fe6e5-fe1c-5a4f-b504-7c566891af8f | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
0f0c016c-c9d9-5544-bec1-2d755d9cff90 | note | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
d003382f-7300-5597-aa84-2a6d6f17eeca | note | How Often? - Per Load
409d1e70-c810-500e-8eb1-dbc3429c5692 | note | Records Required - Asphalt dockets
bb2991f8-8304-52b4-ad60-1eefb3e225fe | note | Responsibility - Asphalt Plant Manager/ operator
0f786247-01c5-5c27-95cc-736d530e7ce0 | checklist | Production and Testing ITPs |  | Production and Testing ITPs
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1a94bcc9-a030-5360-8448-2177318180e3 | checkpoint | Production and Testing ITPs
4b167613-2f05-5bfd-ac7a-77884c720850 | checklist | QMP |  | QMP
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1da6f88a-c56b-5402-9f89-4627f837359e | checkpoint | QMP
7a58883f-a9e8-5568-8c66-3786b34c4497 | checklist | Site specific ITP items | itp | Site specific ITP items
833bae5f-520f-507b-8241-cbb732637bcb | section | 1.0 Pre-Work
b34ac1ea-d920-54d9-9cd9-6c1faf4fa917 | checkpoint | Approved Design Report
67a64a6d-55f3-5fa2-b741-67b464e7b4d6 | note | Type - H
66c69efd-7e60-5431-9fdb-734cf2103f12 | note | Reference or Specification - Site design Report
616275f5-d525-5a93-9465-8e9115f96074 | note | Method/Test Required - Confirm document uploaded
d2561bb2-4097-5119-84a2-33b554df49c2 | note | How Often? - Each site prior to establishment
50784ac0-5164-5cee-afca-9cfbb34c2762 | note | Records Required - Copy of Approved Design Report
0f421f13-5d8f-51fd-bfba-318625a11d3b | note | Responsibility - Renewals manager/Project Engineer
786e8204-0d60-5bd2-a8ca-e150d298f707 | signoff | HOLD POINT
52609d48-16dd-5276-9aa9-9c8729245e19 | checkpoint | Pre seal inspection completed:
722a4348-39d1-5ba0-9fc5-fd0258e722ab | note | – Confirm RP's and markouts align with design report
78f439aa-af47-57db-9c00-8fe4befb8c6f | note | – Establish methodology and amount of shifts
78dfdd21-21ee-5577-ab7a-403bf25e1efe | note | – Confirm any environmental protection required
e6365d45-8ff4-56de-aa4b-10512b19ee41 | note | – Confirm any service cover adjustment requirements
ad4800d0-c50e-5634-acdf-5ef9da77f46f | note | – Identify potential milling dumpsites and plant parking area's
07b9b60e-af7f-5c63-a80f-2a728588abcf | note | – Identify TM requirements
33bd177d-8a99-52f1-a249-8ddc3e566479 | note | Type - H
977e60a4-d2cb-57f2-9b8e-9b44b2817468 | note | Reference or Specification - Preseal inspection checksheet
731b3379-3879-5570-9a1d-547301678444 | note | Method/Test Required - Confirm document uploaded
dafbc764-80ae-5aee-b542-d6dc1290d519 | note | How Often? - Each site prior to establishment
9764c31f-6d44-5f3e-a39a-e2e13eeb8e2b | note | Records Required - Copy of pre seal inspection
ea0f002f-72bf-5d9a-80db-2f9a8ff46c9b | note | Responsibility - Site engineer/Supervisor
a2b0b4d9-2aa5-5adc-94ac-72d41d141277 | signoff | HOLD POINT
d510b888-7ac4-5a5a-9001-107c5a01424d | checkpoint | Stakeholder Management Requirements met
90e632a7-6728-5e5d-b9ba-db3eaf9c6ad4 | note | Type - H
c066671c-4c60-583d-be11-135e93ecdbf6 | note | Reference or Specification - CSCMP
e40f75fc-ec2b-54b8-bfd8-5e301b306d9c | note | Method/Test Required - Confirm requirements followed
447b125c-5829-54fa-88c5-5f65da7d80a5 | note | How Often? - Each site
b586f748-717f-5390-bf73-ba69c4f90388 | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
ef605de5-5b1e-52b0-9ab4-57aacd854f22 | note | Responsibility - Network manager/Renewals manager/Project engineer
cb8f9138-18e8-518b-9cfb-c3084f87e9ca | signoff | HOLD POINT
e079a435-95f5-522c-8a35-d9f47819d079 | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work and weather forecast is compliant; confirm type of plant to be used
6b75d7ff-4dc9-55fd-a080-a05d8e201d5c | note | Type - H
8e1ca850-1b35-5092-a14b-8138a9b06758 | note | Reference or Specification - QMP
875cac57-323b-5ac8-83ef-6ca6d3f1a679 | note | Method/Test Required - Brief all team members on day’s work plan
01a3069a-8c6d-53a4-b69f-7de2d81a29c3 | note | How Often? - Each shift
3cb9b3e5-6241-556b-9b49-9635a3967e4d | note | Records Required - Job brief, updated forward works program and screenshot of weather forecast
319b496d-71b0-57b3-aa5c-8cf517f1742e | note | Responsibility - Site engineer/supervisor
8c5afb3f-4e0e-55c4-a5d3-58d3f99b6fee | signoff | HOLD POINT
3fd4182c-dfef-537e-8d31-9fe2ef06c6f5 | checkpoint | Confirm Traffic management requirements met
c127ee37-a4c5-5598-b7d3-64f4a9ede6e1 | note | Type - H
fd923b05-dd05-5906-8537-7f48b2d0a156 | note | Reference or Specification - CoPTTM/NZGTTM
6372398b-b469-5621-a4e1-0c1246fcaf5a | note | Method/Test Required - Confirm Approved TMP in place
de66ca41-ce34-5003-8921-5d454c330a1e | note | How Often? - Each site
2816806c-360c-5fdd-9725-cc18bfa47758 | note | Records Required - TMP
aae7dd95-9386-57d0-b9ba-c2ec90be9a92 | note | Responsibility - Project Engineer/Site engineer
48f18c57-c81c-51de-9a30-acb1ded956ab | signoff | HOLD POINT
7114ffe9-d748-5105-9716-7a768ba83abb | section | 2.0 Site set up
de0dc68e-6d76-59c1-88ce-5f4f8c9d1805 | checkpoint | Ambient Conditions: Min Pavement Surface Temp 5ºC (Intermediate or structural layers) and 10ºC (wearing course) and forecast to be rising/stay above
6a8d570e-a6b2-5474-ad34-6aaa8617d4e2 | note | Type - H
589c7bf9-fde1-5169-be03-7fe8d13e892b | note | Reference or Specification - NZTA M10: 2020 9.5.2
5bb7c103-be06-58b6-baeb-6b65494cda76 | button | Method/Test Required - Temperature Gun Check | Acceptable,Unacceptable
61d94a46-a3f5-5095-a361-7cf4e5a55a20 | note | How Often? - Each site
78472b1e-3dc3-5bae-b7a1-f1e57fae793a | note | Records Required - Ground temp record sheet in QA pack
6a85551b-26af-5e76-a250-f2c161725bfa | note | Responsibility - QA/Supervisor
a7cb3c04-47fd-59f3-9c02-671f58c9c090 | signoff | HOLD POINT
6f355f2c-df11-59ed-bd97-25b614509738 | checkpoint | Job start, identify risks and controls, communicated to team
d6e424c9-ca69-5b4b-8033-b285f8dbd5b1 | note | Type - H
1dc35d80-9619-5d20-bcea-eb2c01d4efe3 | note | Reference or Specification - HSMP
638d4d24-8b51-5779-bdc2-71c967f55041 | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
4a56f8e6-577c-5248-9fec-b4d5761af00d | note | How Often? - Each site
b7c332d1-7c71-556e-8201-238edf44e502 | note | Records Required - Daily pre start briefing Form D02.05
cd7887c7-fe9d-5c84-b033-ed2fe2cd189b | note | Responsibility - Site Supervisor/Foreman
1343757c-7bab-5f16-9893-71c8c675b1b0 | signoff | HOLD POINT
39b3ac28-bb99-5723-a25d-70f5fe36ee0f | checkpoint | Establish traffic management to plan
87f52dd2-4bcc-5ae0-aa54-18a53efb23d6 | note | Type - H
68a5ac44-3c8c-5a13-8100-d622db95b288 | note | Reference or Specification - TMP
5e3a3ea3-bb7e-591e-afac-d81688ecf102 | note | Method/Test Required - Site audit post set up
b3e0d6f4-11c6-503d-918f-f45975b20158 | note | How Often? - Each site
ae6b0a36-3235-53e0-9143-fbf02ee320fc | note | Records Required - on site record
bc612a21-378f-5a77-9dfd-3c3a6ecea404 | note | Responsibility - STMS/Site engineer
38c57964-067f-571d-b082-eaaefae973fb | signoff | HOLD POINT
028f162e-7d1f-5a0f-a158-87e16181b18e | checkpoint | Identification of Services: Service Plans on-site, Shallow Services marked
a2e935c6-01f6-5260-84be-8ae5fa177262 | note | Type - H
209719da-c559-55cd-b14d-96decbf2fec2 | note | Reference or Specification - JSEA/Permit to dig
e6008d26-affd-5571-b9bd-97091234dec4 | note | Method/Test Required - Confirm document on-site / Visual check
1acb66be-e868-529b-8076-f7d19e951220 | note | How Often? - Each site
4785a214-fcf1-5654-9eea-00e8ba7c1136 | note | Records Required - Permit to dig/ service plans
4fa25446-9f8f-56bd-8df2-356fc33c6196 | note | Responsibility - Site Supervisor/Site engineer
be866769-364b-5ddf-9a73-7d4807451cb9 | signoff | HOLD POINT
b7eed7b9-d43d-519c-b61f-51ba920f023c | checkpoint | Photograph environmental protection measures installed
bc2cb891-24c5-59d2-ad8e-3a72c4536e59 | note | Type - I
748e5025-6e1c-56f0-bb41-60c0d71df463 | note | Reference or Specification - ESMP
e8012926-60eb-530c-a750-b45ce318361d | note | Method/Test Required - Record temporary measures
80765160-1872-5e26-8ff0-d553a811ec68 | note | How Often? - Each site
6ac18269-e6e1-5579-997e-6920c3314101 | note | Records Required - Photograph
bfbc762e-d192-5b1a-b4e7-8a45d6664f4e | note | Responsibility - Site Supervisor / Site engineer
88275af2-2ff3-5c13-a94c-1117c6d6fae9 | section | 3.0 Milling (If Required)
197a9123-6e50-59e4-a55f-7f6c67707e0a | checkpoint | Milling undertaken to correct depth: up to +10mm nominal thickness for each layer, however If applicable final surface can not end up more than 5mm above lip of channel unless specified otherwise in the Design Report
d9c421ed-783e-5e14-9761-a135307682f5 | note | Type - I
2284c655-b080-599d-90a0-c2f8af10bc17 | note | Reference or Specification - site design Report; NZTA M10: 2020 10.1
7290ec93-0830-5c71-9d34-99406db22722 | note | Method/Test Required - Dip checks
8e39c945-b202-54c1-814c-cf24312b0e80 | note | How Often? - Per site
acf29efc-d456-5e07-90c2-3fadd44ec567 | note | Records Required - Stringline sheet from QA pack
e45d93b3-c2c7-57ad-9dba-ec365703dc21 | note | Responsibility - Site Supervisor / Site QA/site engineer
c5b3600a-a67c-540f-b706-39b8978c81db | checkpoint | Proofrolling to be done on milled surface: Use PTR or loaded Asphalt truck, to proofrol milled area's. Area's showing movement or loose materials shall received additional strenghtening at the specified depth in design report, for up to a maximum cost of 10% from the total site cost.
39860272-fb4a-532b-9f34-4df2c034ae7a | note | Type - T/I
ca7bd7b6-020a-51e9-ad9a-edd9266d67df | note | Reference or Specification - Site design report
eb4ef437-1cb9-5dc8-b072-bed84ec40de8 | note | Method/Test Required - Proofrolling with PTR or loaded truck
976bb8d7-c58d-5383-93c4-ae91834c4f42 | note | How Often? - Per site
26ec9d3d-c72f-515b-882d-25b09bffd42d | note | Records Required - Pictures or video, if additional strengthening required a site diagram showing measurements, RP's and location within site
dc54f1e3-44c3-5106-a75e-087862933c35 | note | ○ Any additional strengthening required over the allowance of 10% for the total cost needs to have received written approval of Renewals manager or NOC Contract manager
fab3dc97-24b6-55fa-be3a-fd41d9849b3f | note | Responsibility - Site supervisor/Site engineer
8ae6c3c5-9eb3-5f48-b52f-e5bacb8c5bce | section | 4.0 Membrane (If Required)
e8fdf3ed-8e3d-5207-b76b-a7aeb51d9c9a | checkpoint | Application as per Design Requirements (Chip size / binder application rate)
ab78f7e6-cf3c-5c82-9b38-f188f304e622 | note | Type - I
8b97dc27-7dfe-5628-8424-4244a8da2e15 | note | Reference or Specification - Design Report
387162d4-da4d-5bf8-ac77-c5d5e2fe989a | note | Method/Test Required - Spray Sheet's
62e996f5-7e4f-5a5e-bb8f-5eb594afb0c5 | note | How Often? - Per site
fe240653-ad83-5943-b4f5-517dd168f6b3 | note | Records Required - Spraysheets
82355b60-9fb9-5568-95d2-60c9db55318b | note | Responsibility - Site Supervisor / Site Engineer
29805cbc-009c-5194-a80f-7dbbf9b0dbea | section | 5.0 Strengthening Repairs (If Required)
ab69beb0-2b92-509f-991c-7e03cc738b3b | checkpoint | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver.
f1d070be-8588-59f0-8e17-5b9b7b24f5a1 | note | Manager to be notified if temperature falls below:
6fb1149b-a314-51b4-8130-46e39ad07b61 | note | ○ AC20 PMB 130°C
d56b6218-59b3-5197-a671-e5e2a782a4ac | note | ○ AC20 Hi-Mod 140°C
5deeb10e-6f1c-543d-a3c1-f017b1a34f5f | note | ○ AC20 60/70 125°C
302ab503-efba-5792-9829-2aed58d2ebd4 | note | Type - T
436af045-fc51-51fa-be3f-47dae512df91 | note | Reference or Specification - NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
c9f827bd-7518-577e-98af-cbdee8466901 | button | Method/Test Required - Temperature Gun Check | Acceptable,Unacceptable
1a3c80bb-0d56-507a-9a97-4f5679a553c7 | note | How Often? - Per load
388a3be3-d2bf-53d3-80eb-877e99f595a4 | note | Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp
079227a6-70eb-52df-ac03-3010a2b9b60b | note | Responsibility - Site Supervisor/QA
29c86285-d0d8-5421-a9a5-d8ae2603653e | checkpoint | Structural Asphalt Layer Thickness: Each Layer >80mm with a max discrepency of +10mm nominal thickness
f9b381fb-0c05-5466-9163-2822b6bd8eb2 | note | Type - T
f7518f4f-b976-5906-9c40-8454030f7c42 | note | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
2630a0ef-1868-5ae0-8b92-9e62aad6cf9b | note | Method/Test Required - Dip checks and spreadrates
0b9bd9be-52a2-56cf-b3fb-d3d85bb8a1f4 | note | How Often? - each truckload
60a0f5eb-2f07-5b47-ba24-22dd45329f8c | note | Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks
b4b6fa3c-aa55-5033-a805-cd650264aee2 | note | Responsibility - Site Supervisor / Site QA /Site engineer
d19188b7-c611-5601-b6a3-fae5719b16cf | checkpoint | Compaction and Air Voids
b7dd6af9-6069-5f19-8bef-43f1bd89eeb4 | note | Type - T
da108fa0-198e-52ce-95b2-07591196f6e7 | note | Reference or Specification - QMP and NDM SOP
7660addd-89c2-57ae-9f5c-523e8120b4e7 | note | Method/Test Required - NDM for Quality Control
75248ad6-db53-52ce-a76f-c843f1bc3a95 | note | How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints
70801f98-6b34-58d8-9821-4b597c90168e | note | Records Required - NDM sheet in QA pack
301674ee-5264-58b3-848d-ad5f09817c94 | note | Responsibility - Site Supervisor / Site QA / Site Engineer
3ddb2191-fc7f-5463-90fa-8b4c2c651f10 | checkpoint | Proven layer thickness and compaction
100f1b23-b86c-542e-ad16-613f096a4511 | note | Type - T
b0c160c0-df3d-53a4-8e0a-d427fdfa2006 | note | Reference or Specification - NZTA M10: 2020 9.9
82928143-4b44-5a3a-8f07-263d9cb87c1c | note | Method/Test Required - 150mm Diameter Cores where:
2f82e6df-0566-51de-a10e-81af238d7a0d | note | 1. >30tonnes
115b3fa4-bf87-5da0-a381-e1d3ca38c6ec | note | 2. >=45mm lift thickness
80357d7f-ebeb-5174-bf6e-1cecb9323d37 | note | ○ 100mm Diameter Cores where:
68a4dedc-9847-5dcc-8734-248cfec34b3f | note | 1. >30tonnes
c1fb8c9e-67f6-54cf-9f86-059bcca3cb61 | note | 2. >=35mm and <45mm lift thickness
f2863fab-6452-59bb-a816-71606d101d2f | note | ○ NDM (only where accepted by the Engineer in writing along with the testing plan.)
fb7b4d55-dfe4-5fb9-8705-2d22071c125f | note | How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
142dc7e2-a97f-5807-9fe3-15a2d8809490 | note | ○ Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
e9534e2e-b69d-5a8e-a128-33b923cc5f6c | note | ○ NDM (only where accepted by then Engineer as per agreed testing plan.)
e3cbc663-9f7b-5f87-a39f-07fc70c196dd | note | Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report
58eddde5-c5e7-5ecc-acba-e6f119e57f21 | note | ○ A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF
69678f7f-8970-557d-a7f3-d23aba52022f | note | Responsibility - Site Supervisor / Site QA/ Site engineer
77d06082-e4b8-5b74-8eee-d32396d68831 | section | 7.0 Wearing Course
c711851e-05cb-528b-b4a9-fd5d8d9dbf86 | checkpoint | Delivery and compaction temperature: ±30 degrees from the recommended mixing temperature of 150-175°C To be recorded when mix is tipped into the paver.
04d58a6a-0a7c-5d12-a6ce-33034a1b84f7 | note | Manager to be notified if temperature falls below:
22b40bae-ba9a-505d-9342-847544a9f6b4 | note | ○ AC PMB 130°C
5717a665-6a2c-5cd0-b608-3dc33bd13872 | note | ○ AC 60/70 125°C
7d34fc2c-58a7-50b9-82d9-4433f7fb4a02 | note | ○ SMA PMB 125°C SMA 60/70 120°C
346e33b8-ab09-584c-a531-6219e6667e5b | note | Type - T
d1971c3b-c6e3-5a4a-8a00-e67145ba1035 | note | Reference or Specification - NZTA M10: 2020 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
15dd4509-a7ad-5122-afc4-b2b8737296b6 | button | Method/Test Required - Temperature Gun Check | Acceptable,Unacceptable
6be430f7-236e-56db-8389-9bc0c671324f | note | How Often? - Per load
71c5c7f9-0c31-5df5-8c64-83f5475b5371 | note | Records Required - Temperature record sheet; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp
dc63cef3-1c37-5520-9df2-49aafb4819ee | note | Responsibility - Site Supervisor/ QA/Site engineer
37d27913-38a9-53b9-9a9e-d05d052aadec | checkpoint | Surface layer thickness: Each Layer >min. layer thickness with a max discrepency of +10mm nominal thickness. If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report.
582e09cc-0c14-58ad-9247-38e5e36d07fa | note | Type - T
f76b20b3-aee7-5af8-bec6-d20fab320569 | note | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4
549b51e6-7f00-5748-92c8-5884d7aa78a1 | note | ○ NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
9397c846-e0fc-53f1-9aa9-c66b0a2ffb4a | note | Method/Test Required - Dip checks and spreadrates
b12225d4-3389-5d7e-ab00-f38297cbd659 | note | How Often? - each truckload
1217015f-fc8c-5d7e-aa2f-fa9277649eb8 | note | Records Required - Layer sheet and site diagram in QA pack and photographic evidence for dipchecks
99921e92-7bc2-5853-8e69-50dc920b23e9 | note | Responsibility - Site Supervisor / Site QA /Site engineer
10c006e0-71a8-4328-8525-c702a728967f | checkpoint | Compaction and Air Voids
cc9266c0-66d4-5ddd-a6ba-a1fa61cae166 | note | Type - T
23dd1599-a73d-5de9-9dd1-e3f535bfb24d | note | Reference or Specification - QMP and NDM SOP
c404432d-6a05-5444-a64b-51d1c0ecd5c6 | note | Method/Test Required - NDM for Quality Control
84671f0a-875b-5852-8219-edb678d380cc | note | How Often? - Minimum of 1 test per 20 lineair meter per run and minimum 1 every 100m on joints
e200a279-e69a-5755-bf6b-241f0c9db9b4 | note | Records Required - NDM sheet in QA pack
afc60a72-da16-5f5d-a68e-9bbd677f3b75 | note | Responsibility - Site Supervisor / Site QA / Site Engineer
3ed8514f-894b-47cd-b5d9-2ad0984feec7 | checkpoint | Proven layer thickness and compaction
308c02f9-a095-5651-b954-3e604e6cfdf5 | note | Type - T
89457f02-86f2-5d68-a8e2-d1920d1f676b | note | Reference or Specification - NZTA M10: 2020 9.9 or NZTA M27: 2020 9.9
ec18d3a6-4f09-584c-87d5-1f4e0f2387ff | note | Method/Test Required - 150mm Diameter Cores where:
b9413142-6b48-537e-ae49-f6064cf7e052 | note | 1. >30tonnes
14f693cf-eb44-5d61-919e-914613297708 | note | 2. >=45mm lift thickness
9cf74c2b-942f-5fc1-97c2-04173ae97f02 | note | ○ 100mm Diameter Cores where:
597c043d-0a7d-5cb3-8298-2ffee49664a7 | note | 1. >30tonnes
8b22e937-f3be-5691-b0ee-33abfbf31133 | note | 2. >=35mm and <45mm lift thickness
0e3c7a84-12ad-5ad1-9030-fb3be180f14b | note | ○ NDM (only where accepted by the Engineer in writing along with the testing plan.)
a9e0f001-c2b7-5b64-8719-0df26de9e8d5 | note | How Often? - when a lot ≥ 30T; Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
453c4afd-e76d-5a67-8d7c-ef5ab9414810 | note | ○ Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
3138b60c-82f2-5a03-9227-14c9d845d85e | note | ○ NDM (only where accepted by then Engineer as per agreed testing plan.)
271d30af-1e60-5f7b-a148-6b99c0d9d74e | note | Records Required - Photograph of each core; random coring sheet from QA pack and IANZ accredited lab report.
b5327a89-a9ce-5dd8-b21a-5c70ee709d50 | note | ○ A lot is deemed acceptable when the Characteristic values of the mat come back within the range of +3,-2 and from the joints +5,-2 from the design airvoids listed on the applicable JMF
c56c99a6-b012-5f70-baa9-1c0e7f001e65 | note | Responsibility - Site Supervisor / Site QA/ Site engineer
e4575d87-06de-5c92-afc2-3aace438d13d | section | 8.0 Post-Construction
e92f8773-ed06-5683-869e-28df8c8cb28d | checkpoint | Supervisor to provide an update regarding site completion per shift
e2db09eb-99eb-5eba-8cc6-0d2899051a74 | note | Reference or Specification - QMP
28cc5005-c6e9-56bb-8453-507fb408e6b4 | note | Method/Test Required - email
47705d8c-1514-5b4b-9576-b98bf5695f6d | note | How Often? - Per site
ade9d45f-f0f0-5666-a0a0-418b9199b741 | note | Records Required - Email
6bfedd57-8008-56b2-96d6-04e4a7197959 | note | Responsibility - Site Supervisor/site engineer
33b84639-aa8b-5019-b6fb-c520effb3f69 | checkpoint | Linemarking and RRPM Reinstated: Matches previous linemarking - within 48 hours of sealing
fbe0bea2-8b62-5cac-97dc-78e4ef9eb0a1 | note | Type - H
fff18fe5-b0f2-5d6d-b51d-3cb60bce425b | note | Reference or Specification - MOTSAM
b2369524-b555-5645-8b89-c028100510af | note | Method/Test Required - Visual check
21d2cf73-d37c-5336-8483-67b74046deb7 | note | How Often? - Per site
fbb78f1c-fbdc-5a00-b744-fb67caf990b1 | note | Records Required - Job Sheet record & photograph
1d5f8ae8-b00d-56ea-a8c6-f219d1aaa989 | note | Responsibility - Site Engineer
eb787fc6-bb44-514e-996c-505eef1b238a | signoff | HOLD POINT
04c37a06-47df-53da-9392-6053f2c7cdda | checkpoint | Post seal inspection completed:
6c5b4288-6405-5f67-9760-ab7ba50961ac | note | – Driveability of site acceptable
912d7540-6f15-57e3-b4e8-bbdfd1037f41 | note | – Quality of paved surface
cbe3d842-1458-5279-9918-ba8571e08cd8 | note | – Linemarking correctly reinstated, including cat's eyes?
5d574d0f-efef-5bce-a74e-09c11de4895d | note | – All TTM signs removed
5495ce28-88fc-5450-a8d6-4129f47936c2 | note | – Site; stockpile and parking area left in tidy condition
f5721957-b3a7-55aa-879e-56651afc2353 | note | – Required service cover adjustments completed; covers to be flush to +10mm with surface
d218507e-e43b-5d00-86d3-e23c178df678 | note | – environmental protection removed
71eecd12-f495-5bb1-95fd-010dd3e93aa5 | note | Type - I
3f9354b6-d6f5-5879-bb19-9454f99ab67f | note | Reference or Specification - Post seal inspection checksheet
05a52648-38c1-592c-8d83-54a69df53fbc | note | Method/Test Required - Confirm document uploaded
b847605f-56be-56dd-9891-790a6d94d930 | note | How Often? - Each site within 1 week of completion
c60a1d53-188a-5c56-be6c-e3d318bbc7be | note | Records Required - Copy of post seal inspection
eac98d1a-d914-5858-add2-98098205c1d7 | note | Responsibility - Site engineer/Supervisor
213242cc-4f06-5282-865b-4b6b2c1077c4 | checkpoint | As-Built records – structural patches
3ef9911c-b238-5e9d-b4d7-49c4fc932f7a | note | Type - H
9f4d7c58-ad1d-560f-b309-1e1269cccb3d | note | Reference or Specification - Site design report
4797f188-65e7-569a-9d99-2ecafb0bcda1 | note | Method/Test Required - Record as-built patch dimensions & RPs
7a641816-fbf6-588f-94a2-57855fca739f | note | How Often? - Per site
15465855-1288-58ea-860d-20db9288d88d | note | Records Required - Final site diagram from QA pack
7d57a08b-b8d5-5841-974d-5ce6fcb345ef | note | Responsibility - Site engineer/QA
473ee603-cff2-5998-b0a2-4abb9280d08f | signoff | HOLD POINT
37f5eede-bd17-52f7-84c6-1e5b51cc4b39 | checkpoint | Collect RAMM data
81a0c46c-d999-50b5-9c94-7f53e3ec2083 | note | Type - H
4c20b555-17f3-5f56-9800-f652c70b181e | note | Reference or Specification - Comply with Waka Kotahi format
d4b255bd-6b97-5d19-9e59-4e14f70864a3 | note | Method/Test Required - Correct data supplied
00667eeb-2dad-56b7-a248-8faceb76ba4a | note | How Often? - Per site
7b321d32-405a-5026-8770-6bfbb538b23a | note | Records Required - Job Sheet record + As-Builts + photographs
dd25eb5d-b737-53cf-81b4-6b54f6d58fc2 | note | Responsibility - Renewals manager/Project Engineer
20ea02df-a402-5c38-ac8b-f3172fb0a3f7 | signoff | HOLD POINT
218d643e-d3b2-56a9-995e-209bbc1f1ae4 | checklist | SYS - ITP - Pavement Rehab - SH 34 - Lambert Road Intersection | itp | ITP - Pavement Rehab - SH 34 - Lambert Road Intersection
6caa621c-a543-5613-9dfc-8d8612bd4720 | section | 1. Procurement
09dfa698-6b7f-519e-b940-013fd716a19e | checkpoint | Design - Geometric Design
7e9f87a8-94bc-5acf-a0c0-d20a47608142 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
7e132571-2b6e-5291-a561-df8eb7f39b2f | note | Acceptance Criteria - Principal Approval
63e0a901-2416-5119-a0d7-820bcba57d6f | note | Method - Contractor and Principal peer review
c989254c-1d78-593e-a556-80014680f8b9 | note | Frequency - per design revision
d3aa513e-1361-5d0a-b750-1f971ab198ba | note | Conduct - C or S
a91f83f3-b4b9-5fbb-9983-1f6b65b7fa7b | note | Produce Record - C
107097d5-7263-5e84-9d31-1860a5cc707b | note | Approval - E
40afcd9c-3c3b-5ccf-9905-471f4aaf838d | note | Hold Point Y/N - Y
734b8921-df80-5868-90e2-320abcb6aec9 | signoff | HOLD POINT
fc457da0-71e7-5429-a676-cfa9f8ad8762 | checkpoint | Design - Pavement Treatment Design
fc20fc9e-49e7-5d6c-b622-ea1ba68a4efd | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
25f2bfcb-4ac6-5dec-b3f8-cae32e610681 | note | Acceptance Criteria - Principal Approval
97114f4b-5db7-53c2-9f6e-fe12f501deb7 | note | Method - Contractor and Principal peer review
9d1943f1-9d37-573c-92ff-91e4673f1a5a | note | Frequency - per design
ba0a46d5-b307-5b81-ad15-4f9f4da7eab3 | note | Verifying Document - Pavement Rehabilitation Design Report 2023/24
8291b6ef-7638-596b-ad7a-a7c6c6f0ca87 | note | Conduct - C or S
2b836d15-8ea6-57d6-b652-e4c394627b41 | note | Produce Record - C
36ea5ee5-5c07-52e1-8387-6a3bd6b65931 | note | Approval - E
881a0601-b159-5153-9ea7-85515d973379 | note | Hold Point Y/N - Y
f7622f1f-ef56-5ab3-b6af-8b3b9e5d5f72 | signoff | HOLD POINT
36362436-b1e4-5e95-af81-437ff9bbd938 | checkpoint | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
68cc8748-d726-5eda-a2a5-0449879df56f | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
473141e8-1c44-54e6-9da2-a96492fb8758 | note | Verifying Document - Sampling Worksheet
a2af7a35-caef-5ec8-b769-58ed646f2939 | note | Conduct - C or S
5eaed97b-ca45-525e-8029-f9d914448cc7 | note | Approval - S
9a8cfa60-cccb-5d73-950b-f3d3631017f7 | checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
16f27f1e-b147-5176-869a-77b95dfad506 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
8bce6a91-9e6d-5bd8-a5bf-4bed706981bf | note | Acceptance Criteria - Soaked CBR ≥ 40
f4c0363d-5c5c-5bd5-b2cf-bf2c0489e11c | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
097b6dc9-8319-5124-b00a-eb531cffbcf8 | note | Responsible Person - Supervisor
a07023f2-4e3d-5710-9457-3632c07222ac | note | Verifying Document - Test Report
c354bbe7-cef3-5709-a8b5-1ae20a5a917a | note | Conduct - Sp or C or S
6f3cf05e-141c-5e66-ac52-8c591a8e290a | note | Produce Record - Sp or S
cc7a8adf-f9ff-5148-a2a4-93bc95078452 | note | Approval - E
cac2d247-62ce-5528-8af3-db5eda9a3f9b | note | Hold Point Y/N - Y
00ff5837-9d0e-5679-af00-cd2a9fbc6cf6 | signoff | HOLD POINT
ae7e2d83-e996-5777-8251-1ac263229947 | checkpoint | Materials: GAP 65 Pre-treatment Material - Production Property Test
541276eb-96ab-5ec7-84db-bf603485f2fb | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
79082c6e-a663-58cc-b5d3-484cdc501d29 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
0e2bf848-aaec-5ed2-9ae8-0ef07486796f | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
325cf7ed-d2ac-5eaa-922b-6baafb840824 | note | Responsible Person - Supervisor
311b084c-c40b-5d36-9264-a3c4431503ee | note | Verifying Document - Test Report
ca335865-6feb-50db-a178-9defa987f17f | note | Conduct - Sp or C or S
ff8f18f7-76e0-5aca-ac0f-af128b1539a3 | note | Produce Record - Sp or S
4ecfca9d-b7f1-5f91-ac4c-65043237dc5f | note | Approval - E
cd868cf7-9534-5ba1-8c28-2828d100e1d9 | note | Hold Point Y/N - Y
59b9d644-63f9-5af7-bf31-75c1a6bf1a10 | signoff | HOLD POINT
282d13fa-6a2e-5570-b955-78f6c0062fd3 | checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
d3362af0-a9bd-59c4-826f-2eaa4b776304 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
0fbb50fe-f624-545d-83a7-c2c026b4c469 | note | Verifying Document - Sampling Worksheet
19b6d86b-bdd4-5d23-8c3b-38570c4103e5 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
de4900ee-9328-50db-a33c-e59081eafadc | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
308ebc34-b77d-5a6f-8f4f-8ca39e926fed | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
0a653710-ed81-5136-b52d-6bbce4137bb3 | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
8adffc6c-d285-5b1e-946e-3d6933e032b4 | note | Frequency - One test for every 10,000m³ of source material
938d2303-08b6-572d-92df-0fedf14cec51 | note | Responsible Person - Quality Controller
5c2fd9af-083b-59b1-ab0a-37c987fdc4e7 | note | Verifying Document - Test Report
fa14f2ae-46fe-50cd-a06e-b8062b825d66 | note | Conduct - Sp or C or S
0bbeef23-f463-5312-9570-51e14f6bf306 | note | Produce Record - Sp or S
b3f8aeef-2680-533e-8feb-c847468d6543 | note | Approval - E
4cdaac33-40cc-5140-b814-1e0c9deedbb2 | note | Hold Point Y/N - Y
2bce147b-57e0-5df2-aa19-d3114e0f900e | signoff | HOLD POINT
771bbcd5-e52e-5af5-9fc3-2a5ff6956b1d | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
3f7f9716-4f5e-5e03-bc2f-404f0948daae | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
b654e970-b68c-5ae7-a647-4ee38e54fbec | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
054a79a2-d600-5a47-956d-01c48dcae9f5 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
4c3864b7-2614-5b47-881a-bcf23d9c523d | note | Frequency - One test for every 10,000m³ of source material
39d03aa1-7053-5e25-806d-66b5282ffaf6 | note | Responsible Person - Quality Controller
eda78439-b911-57b2-815f-4c8dd6beb802 | note | Verifying Document - Test Report
b04d5b7c-eb29-5bf7-8dbd-ef0a089f52a6 | note | Conduct - Sp or C or S
dfcf85f4-fc0f-5a95-96b0-cc6cd120aedd | note | Produce Record - Sp or S
c7725d4a-2f83-57c0-a264-29e421743caa | note | Approval - E
3a85ed1e-d9cf-5217-8bcc-fc2fd7106382 | note | Hold Point Y/N - Y
5de343b7-b3e0-59f2-8f5e-085d4a8c0fdc | signoff | HOLD POINT
113f3833-1e06-55b9-9978-c5d36d530658 | checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
20b03a0f-de52-5e9c-9b63-4086538345eb | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
a59ddddc-ba61-528c-b325-d628d3612c09 | note | Acceptance Criteria - Soaked CBR ≥ 80%
a90130d4-837b-5ca1-86d7-798b4213c932 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
5e00a250-583b-50b4-a77e-35ab4f538cd0 | note | Frequency - One test for every 10,000m³ of source material
b4c94fc9-8f97-59c0-8cc8-92da45b418c4 | note | Responsible Person - Quality Controller
268d4167-7b03-5b2d-807d-be413889fc3a | note | Verifying Document - Test Report
faa56d41-f50e-567a-a74a-cb7893c4fed6 | note | Conduct - Sp or C or S
0baf64dd-58c9-57e8-a9f6-e4a18f2d98be | note | Produce Record - Sp or S
5ec41619-0e1c-5c31-a4bf-3972b2a3aa03 | note | Approval - E
75e80846-c422-5ba4-91f2-3b2e78c8e5f8 | note | Hold Point Y/N - Y
40c2302f-cce5-5c54-87be-1069cdfc7929 | signoff | HOLD POINT
976c9ab2-336e-5bd7-8941-60563e8cfc82 | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
315eff8a-9f4a-5ff4-8393-baf10a77cc7d | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
e00f2472-e802-5dde-aeb6-7d4da3e90333 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
4dd023ae-051d-5b6b-a947-e4bff4c11fe2 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
7f0b7d69-7d0e-5bd3-a589-0847a4d3e1c9 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
47fb4b00-0eb1-58fc-9789-b25cca7dea2a | note | Responsible Person - Quality Controller
7f308430-bc11-5821-a0c4-4323d4c17fdb | note | Verifying Document - Test Report
39aa19c6-a82e-5ca9-aa84-329250b166e9 | note | Conduct - Sp or C or S
330daf91-fcef-561d-8d98-931c208f2eef | note | Produce Record - Sp or S
10d461b0-98d2-5b26-ba75-4eec0eb2adc6 | note | Approval - E
afa7743f-cf8c-5da7-a465-aee02fa52431 | note | Hold Point Y/N - Y
8c291f12-658c-5f73-81d4-ac64eaf7be26 | signoff | HOLD POINT
21f389de-1666-5508-9d06-5a4f024a4cbe | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
0a4d5aba-307f-5918-9c97-af743738dcc1 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
a88ece8f-0c75-5977-81e9-2bf03a9684ad | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
c59546c4-9275-5d86-90ec-879ae2d9b410 | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
7e9e3eaa-e7ff-5521-b474-fd826c2b9f33 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
3ae6ac93-561d-52c3-9a15-c020a6afdcc5 | note | Responsible Person - Quality Controller
d9c95df3-90ad-52be-b839-25f91282f6dc | note | Verifying Document - Test Report
f5218752-15c8-52a0-ac92-6eaca27e3407 | note | Conduct - Sp or C or S
cdcf63cd-dbdd-57e3-b15d-adc466b09bd6 | note | Produce Record - Sp or S
0fe67efe-40d1-5ca4-9fcd-146c58e6a32c | note | Approval - E
44ff1af7-f11e-5227-988e-280ada880abc | note | Hold Point Y/N - Y
f50c0087-ac9f-533c-9dad-f1906513e000 | signoff | HOLD POINT
66a6116e-307f-5697-aa3e-d266fb4bd96f | checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
dc087d30-5f4d-5b67-b91d-463404fde4e5 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
03047de9-3b60-5536-87ee-25aa5d7d1f4b | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
c37ebaa0-caa0-578c-a01b-6e8de5bb3fb2 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
e39f51ec-ab62-55de-a1ef-b46274cdffa9 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
ddc8e3e5-49c1-5471-9c82-12d1ea835882 | note | Responsible Person - Quality Controller
6dc032d8-224c-5766-8592-b7b6ad05847b | note | Verifying Document - Test Report
0198f35c-0adc-560b-a4c0-503e970fed6c | note | Conduct - Sp or C or S
fbebc3b5-1dbd-5425-852e-3040635ff641 | note | Produce Record - Sp or S
a81c9031-68a1-5374-8623-77b1a346eb82 | note | Approval - E
678ba8d3-2292-54a9-9ad0-d4a2c4115e5b | note | Hold Point Y/N - Y
7ecc9215-ad8b-5530-b3e7-13982b2273e0 | signoff | HOLD POINT
47f1dbc4-d99e-5833-b152-43ed36e71943 | checkpoint | Materials: Foam Bitumen - Stabilising Agent Selection
08ecae2a-9b4c-54d6-a653-048df90abced | note | Controlling Documents - Foam Bitumen (4.0.0) - TNZ B/5: 2008
4fd16ae9-78b7-5d47-8481-948d699a1fbe | note | Acceptance Criteria - Foamed bitumen shall be produced from 80/100 or 180/200 penetrationgrade, The bitumen shall comply with TNZ M/1 and shall be able to achieve a minimum expansion of 10 times
1d1fe622-5c0f-585e-99c4-c0d24fa04533 | note | Method - Record binder grade. Conform to Specification
d3d6099d-45b5-524a-9ec4-d8a59c244622 | note | Frequency - Per Batch
f6824c8a-25e4-528d-bd3b-4c679077b360 | note | Responsible Person - Quality Controller
9ed952e1-f6c5-5cca-a206-70285be34fe0 | note | Verifying Document - Test Report
3466b5a2-2d04-5767-8949-1b14ae58ea0d | note | Conduct - Sp or S
82b474d1-d566-5e2d-a092-088e79eab49f | note | Produce Record - C
d0fff9dd-d8a5-545b-9064-ddef52eeca98 | note | Approval - E
5acbda05-7190-5095-a47b-7b6a90dd6a6a | note | Hold Point Y/N - Y
8bf5d5de-2f63-522d-88e9-a2b46f8468b1 | signoff | HOLD POINT
853dc2b2-bda9-5d6e-aa05-563f9498a100 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (1)
04c31a12-cf46-5faf-84e1-f0d6622e9857 | note | Controlling Documents - Bitumen (80/100 or 180/200)
7d8c0d40-7d5c-5590-9713-8088ece3e997 | note | Acceptance Criteria - Record binder grade. Conform to Specification
aefb8791-e375-5df0-a472-5a9345411c20 | note | Method - TNZ M/1
330bcfba-4be8-5057-9e95-731420f0180e | note | Frequency - Per Batch
1f612b1c-2f36-58b3-bc3c-089be23ad471 | note | Responsible Person - Quality Controller
26ffddf8-8fb9-5e15-9c4d-e7d46f78464e | note | Verifying Document - Test Report
10a7fafa-7b16-58b9-8cce-77fc04c2f332 | note | Conduct - Sp or S
f6114f59-3146-5bdf-b597-8496572d5afd | note | Witness - C
8cc52dad-729f-54b8-9b0d-2f9e9813106d | note | Produce Record - C
51540bf2-3701-5d76-817f-0c131c7b7348 | note | Witness Point Y/N - Y
3fd6ef94-12cf-5bfb-94de-9acc9543a90b | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (2)
f3d1bff9-512f-571c-9ca5-a308ba4fa7ca | note | Controlling Documents - Foaming Optimisation
9f279e6c-0592-53e1-b9a7-c1b2b3481e46 | note | Acceptance Criteria - Determination of optimum foam water content
ce34a53d-8c8f-509c-8daa-dc92ec551cce | note | Method - NZTA T/19: 2020
6af2188f-d0ad-59df-814c-0f4758eef612 | note | Frequency - Per Batch
0c1ef188-8dd1-54ad-91ab-11f00ee68e89 | note | Responsible Person - Quality Controller
7b04724e-f05d-5303-a5ca-387a6cff214a | note | Verifying Document - Lab report
e214b35e-1819-5bf3-9c20-6b3eff5e22c8 | note | Conduct - Sp or S
42c376bd-f6c4-5954-aa1d-4f91a45beaa2 | note | Witness - C
c756155f-8128-5fa6-a91c-9ad293df67c3 | note | Produce Record - C
4935d704-2906-57ea-8704-ce4b31caffb8 | note | Witness Point Y/N - Y
40bca1a5-6a69-5896-8fda-b91f19179928 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (3)
0da05b20-0812-5daf-866d-86c7f7aecc6c | note | Controlling Documents - Indirect Tensile Strength, ITS
a61b119d-b2b8-550b-9074-deed2b09816c | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa
8c94cebf-82b7-5e54-882c-3c13e04674af | note | ○ Soaked ITS: 150 kPa to 350 kPa
abd2805b-8cbc-5e87-bef2-c33825200011 | note | ○ TSR ≥ 70%
d1bded51-526d-5c99-80e3-cd24db86089e | note | Method - NZTA T/19: 2020
af5a7328-f5f7-550c-9d7d-68fbb1b2b138 | note | Frequency - 1 Optimisation test per aggregate type
6705dde3-1c0c-54d9-812e-1002fd836236 | note | Responsible Person - Quality Controller
bd94ad8d-3e7b-5c93-bb59-323ff9d707fb | note | Verifying Document - IANZ Report
76b73d89-b484-55a9-95f4-69f73e2ea7ca | note | Conduct - Sp or S
5510a9a4-5947-58d3-9415-0c55f5ff9591 | note | Witness - C
4d89af61-99ed-5e9b-9586-8ec87090e490 | note | Produce Record - C
a1c28e9b-a601-5d8d-a629-e360d3fea192 | note | Witness Point Y/N - Y
3cbf8630-db50-56bc-9962-d450a8e22cd1 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (4)
ba7e1fd7-db09-5c1d-875e-643187d82906 | note | Controlling Documents - Unconfined Compresive Strength, UCS
cc3fe082-e5f9-5e82-beff-489df682dca1 | note | Acceptance Criteria - UCS is used to calculate MR(Phase 1) and MR (Phase 2)
ef87a84f-1d1a-5be0-844a-e4ed3b8dc149 | note | Method - NPTG Guideline
8c4bb77d-a5ed-511f-84fe-ac2abb714e39 | note | Frequency - 1 Optimisation test per aggregate type
c9d8a529-fcf4-5f07-9d5d-af027b9846a6 | note | Responsible Person - Quality Controller
a23efd21-8230-5bfd-882d-03436cf98fff | note | Verifying Document - IANZ Report
efd6aedd-fefe-530a-bd76-5a27854aa7d8 | note | Conduct - Sp or S
16054920-8242-5e0c-8e04-4c84b9e2e674 | note | Witness - C
904eb8d9-bb1f-5d97-9cb8-952ed2540647 | note | Produce Record - C
5e05cd4f-a6a4-5be1-be95-bbd39ff3198a | note | Witness Point Y/N - Y
f6cb7864-6500-5312-94e3-70a53d1e9be5 | checkpoint | Materials: Foam Bitumen - Optimisation of Stabilising Agent(s) (5)
136f19c0-5470-5846-ae20-452bdbbeb097 | note | Controlling Documents - Modified Maximum Dry Density
49b33917-a3ad-58e7-a594-83297ba013e3 | note | Acceptance Criteria - To determine target density
7bbdeded-2e0d-5183-b0c1-a6a069ca26c7 | note | Method - NZS 4402.4.1.3
6410d3ac-549e-576d-9f1a-0fe7dc59ffe7 | note | Frequency - At Optimised Binder selection
bdbc6082-7f26-5ffd-b585-9699db44440a | note | Responsible Person - Quality Controller
7b479697-8e2d-5583-9ce7-4f722f04cff4 | note | Verifying Document - IANZ Report
d2365790-7c8f-5fc4-9f02-90b92c8458e8 | note | Conduct - Sp or S
0c366e49-233d-58a7-a056-64021906e2b8 | note | Witness - C
8e522c65-035a-5840-b3d1-57f4fac83179 | note | Produce Record - C
f998bc3d-a3e1-5bf4-9527-1a8eaea027b4 | note | Witness Point Y/N - Y
288f3247-2eba-55d4-ae79-89580bc4bef3 | checkpoint | Materials: Cement - Stabilising Agent Selection
4307e24f-8d59-5965-a8cc-49feae25cff4 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
34fdf84a-bf5e-518d-beb2-f9fc3026c4e1 | note | Acceptance Criteria - GP
75887c3b-91e5-56d6-950d-ba724aeb4351 | note | Method - Visual inspection of supplier docket
7ddc3680-2205-50d0-8a55-f9775dfc4c08 | note | Frequency - per truck load
afbf213c-270a-5c20-b50e-65562fcf2f72 | note | Responsible Person - Quality Controller
e8aa6e33-1f89-59d7-969f-a732477b38c8 | note | Verifying Document - Supplier Docket, Supplier Cert
2771181e-00a6-548d-8e32-1ba7e126e4f2 | note | Conduct - Sp or S
a68e9949-b386-5dd4-a7f1-340af75af711 | note | Produce Record - Sp or S
89f98c04-0c0b-511e-977b-35158adbb7ca | note | Approval - C
b7d964f7-ed54-5eff-9a66-a6166d6f948a | note | Witness Point Y/N - Y
5fe70724-8f32-50a2-8961-1dac348f79c6 | checkpoint | Materials: Water - Water draw for stabilising
0dd5f83e-ff40-59d5-a0ff-39f89f44037a | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
4a52a8a4-61af-5c01-b19a-8d8056f10b02 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
69b5a73b-81b2-5d00-b6e5-6ee3a44279a7 | note | Method - Visual inspection
57acdd2b-8b5d-583a-bac2-74214eb59ba6 | note | Frequency - per truck load
23b33ee4-b741-51d7-b5af-543f97806ffe | note | Responsible Person - Quality Controller
a2feb346-56e0-518a-9ba9-ca31008b9ab6 | note | Verifying Document - Hydrant use form
6acbd682-5df2-5e36-aeb7-15da57109fc4 | note | Conduct - Sp or S
9a707954-061f-599b-b5fd-0b97ed718a00 | note | Produce Record - Sp or S
6d6f5b3f-b587-53fb-b889-0d96f06d715d | note | Approval - C
b3d54d30-799e-5382-92f0-0ec4e8e6705d | note | Witness Point Y/N - Y
3af1b080-0c35-5dbb-b356-8d2091fa96a2 | checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
d2875f17-b13e-55f6-bfb1-b25aec69d8c8 | note | Controlling Documents - TNZ F7 Specification
bced87ad-9aec-579a-b7af-b2c5a79e0e76 | note | Acceptance Criteria - Details on Docket
b4ba9fab-69d4-5a30-a037-bfde5b8ea6ab | note | Method - Visual inspection
15886e82-3dab-59fb-a57e-7fc392039808 | note | Frequency - Per Delivery
3560c7b8-f05c-5e59-947c-dadee2c43bfc | note | Responsible Person - Quality Controller
baedd143-9185-58fa-b83d-5182a2d372d7 | note | Verifying Document - MDS
1f3b8dd1-6091-5480-ba16-8dcc92cdaf0d | note | Conduct - Sp or S
5f528dd0-9f85-5062-a2b4-1969ba67fd89 | note | Produce Record - Sp or S
0dfbf6c4-2d0a-5823-8c08-9140a963b125 | note | Approval - C
bbc4cd26-9021-522d-ab3e-5a09d3e91616 | note | Witness Point Y/N - Y
8c822512-98e3-51a0-8b11-c9b150f3aaa6 | section | 2. Pre-Implementation
db166df1-f07e-5e98-a6bd-e46d84f52c3e | checkpoint | Production Testing of stabilised material - Solid Density
c056be29-9671-5532-b70e-41bd2e734748 | note | Controlling Documents - TNZ B/5 section 7.7
f341f76e-671d-5689-874f-a958e3755a7e | note | Acceptance Criteria - For info. and use in MDD calculation
3e5df7cc-695b-5050-9d09-49060e78d22c | note | Method - Calculated based on Virgin TNZ M/4 Specific Gravity and Bitumen added
b3c8cf66-76c8-525e-960d-877459a12c1e | note | Frequency - Once on commencement and if any materials chage
b2fb0b26-fed7-5e60-8fe4-084e760d9ccc | note | Responsible Person - Quality Controller
9a7ffa2f-3e37-5859-8c66-0d8fb7a193d4 | note | Verifying Document - Test report
6256295c-4f5f-5ec4-909f-c2acc31b1c19 | note | Conduct - C
94abd920-9e23-5802-96ca-8f56d601be6c | note | Witness - C
53ae57a9-6c17-56f6-85ac-0f752408423d | note | Produce Record - C
85443f2e-279b-5db8-b273-d11935498c79 | note | Witness Point Y/N - Y
826553b6-b163-5607-b691-87b055e09068 | checkpoint | Project survey setting out
ca749d66-4a76-565b-b319-325eb08a55b2 | note | Controlling Documents - Reference from Project Drawings
ebcc0787-fca4-5050-a0e6-34cf6414e3df | note | Method - Survey/Mobile Roads, Marks with Dazzle
4d5828f4-1434-5e36-977b-db943d310200 | note | Frequency - Chainages for every different pavement sections
521dc68e-6323-50df-a6c0-0e8ab0020b38 | note | Responsible Person - Subcontractor/ Engineer
e8fde2c7-554b-52e0-8871-7303e3386803 | note | Verifying Document - Construction drawings
e3142c70-1354-55bd-ad1d-4b732e5713a6 | note | Conduct - C
b4216319-f31d-5786-9012-91ff8a482058 | note | Produce Record - C
86577490-d2b7-5576-abe3-8a29fed80c0d | note | Witness Point Y/N - Y
abc015c9-179a-5a76-beb9-5b601a298f57 | section | 3. Construction - Pre-treatment Digouts
88b4d3ef-fdc4-5400-9bb9-5af07797732e | checkpoint | Pre-treatment Repair Method Selection
9629c1c5-a4d2-5cef-a0f3-0c06f302369b | note | Controlling Documents - Site specifics to be confirmed
7008f290-8cf0-55f4-a35e-016f945e9ea8 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
e07dd3d8-cd45-55d7-94e2-71572a2b4ef0 | note | Method - Scala Penetrometer on Excavation Floor
0f1075b7-1030-5293-b7eb-0d9629f0dffa | note | Frequency - As required
3a211c3d-7d67-5ee3-8f3f-1437f5e5d13e | note | Responsible Person - Quality Controller
4d4efefd-ef64-5b74-b17b-f657c2db4702 | note | Verifying Document - Agreed treatment plan
16215450-5fa8-5788-a110-13d659fd4130 | note | Conduct - S
c9ff72a0-3676-5853-bfa5-9c763d61d3ad | note | Witness - C
aded5c9a-63f1-547c-b9a5-a4d362600843 | note | Produce Record - S
80a57cad-71be-52b5-80d4-013bc5165b6a | note | Approval - E
0c097a63-79e1-5ce5-bae3-7a97364179f1 | note | Witness Point Y/N - Y
853b83b3-9eb3-526d-a0fb-1c8d51e67b04 | checkpoint | Digout of Patches to repair
20b57f11-3a82-5ad1-8595-3f4f77eb880b | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
ff18e67f-1115-5c4c-aada-8a59974ca994 | note | Acceptance Criteria - 250mm deep unless specified
5db06adf-fc6b-5af0-b20c-ef08fc457332 | note | Method - Visual inspection
b0759acc-8734-5341-a991-dc80452d7592 | note | Frequency - As required
d7545eef-322a-5d46-a7a3-9b0f08c8bb38 | note | Responsible Person - Quality Controller
c5be59e5-95cb-585f-85cd-f60d8ab2b12e | note | Verifying Document - Dig out site records/ Asbuilt
f276dbf3-3fdf-529f-8f68-8d2b3a29373d | note | Conduct - S
66551684-aa9d-5d61-a468-30e2dfcfbddf | note | Witness - C
c49b1467-9420-545f-afce-9a498a0c75bc | note | Produce Record - S
7fea9ac8-6be4-52a2-99bb-2da038643f7f | note | Approval - C
171864e9-ab8c-5616-b439-d1aa9bdbc60f | note | Witness Point Y/N - Y
8e48528a-bbcf-5395-91cb-584d300e401b | checkpoint | Subgrade material hardness, Check base of excavation
c65cad50-7ed0-5aca-8994-79c542f30760 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
78a697c4-7647-5e67-9577-da914ec55de2 | note | Acceptance Criteria - Scala > 3 blows per 100mm
6a4d1adf-4075-51a2-9482-f86a1f422d36 | note | Method - Scala Penetrometer test on base of digout
dfe48948-ce16-561c-8491-cef579434867 | note | Frequency - As required depending on size of digout
8c0935a0-df9c-5a52-9702-d0ed7f148234 | note | Responsible Person - Quality Controller
93d12e35-df77-53fa-be8b-89bfe97f7981 | note | Verifying Document - Test report
0127484c-e5ae-50d9-b4f7-27b7f5d1b556 | note | Conduct - S/C
d82f3ad8-7a21-5336-ad22-8b5e0e81ef0c | note | Witness - C
45d559b3-cec6-5051-890c-1ad5e86a27b6 | note | Produce Record - S/C
f352a8f6-bed3-538b-bc6b-b1a6db0a7307 | note | Approval - E
8fd1ef61-8d32-5d37-a422-58ae7d82728e | note | Witness Point Y/N - Y
cb3534f3-395f-5580-b603-5ab529439459 | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
41e4fcfc-1fc3-5c9c-bd9b-7e0f85aed2f7 | note | Controlling Documents - TNZ F7 Specification
7f265334-7736-5ca8-a5fb-766c305e7cc8 | note | Acceptance Criteria - Meet TNZ F7 Spec.
a82a1b5c-8614-523b-a621-8fb2de2fb9a7 | note | Method - Visual inspection
2eabf8f5-d57f-5594-8a5e-76f594e8ad11 | note | Frequency - Per Delivery
0004141c-7245-52f1-a195-29815f9085ad | note | Responsible Person - Quality Controller
05211498-baf1-5e65-abdd-921b9a03e5bb | note | Verifying Document - Certificate of conformance
156a0c2e-aa74-5654-8181-52252c86a0a0 | note | Conduct - Sp or S
702585db-e0c1-5f88-a5ee-f0377b6def3f | note | Produce Record - C
52c70e9a-9d40-5e7e-b047-30d63b819fcb | note | Approval - C
5bb62b2c-ad72-59b2-8e01-bafa4df9c62b | note | Witness Point Y/N - Y
85caa254-93f0-5f78-96a5-4514c435218f | checkpoint | Place and compact GAP65 in digout area
13431db8-89b3-5aaf-8183-9d54a55817bd | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
20db0207-f24d-5d37-bcc2-5cbc78d9640f | note | Acceptance Criteria - Clegg value > 45
21087fb5-e89a-5ab4-a25c-b3129cb3bbb2 | note | Method - Clegg Test
c7b25329-ae3e-5668-a7a5-819911160a5b | note | Frequency - Min. 2 per digout
05fbeaaa-e024-5309-bd23-081d47aefdaa | note | Responsible Person - Quality Controller
de2d4ad6-359e-5db8-9572-32bba64af3f2 | note | Verifying Document - Test report
6e2fcf7b-5659-54cd-b1cc-0c893e5935ce | note | Conduct - S/C
873487e7-db43-5ea8-aa1a-be93616a33f9 | note | Witness - C
cbfba0a6-bd30-513f-a9fb-ee8fd82014b5 | note | Produce Record - S/C
6d504545-82c3-5376-8a0b-89ef0a2adbe7 | note | Approval - E
f093339b-1955-5f86-b330-3a48e8ecc1fa | note | Witness Point Y/N - Y
04b33b51-b3a0-57f0-ba01-9ad59a1cc9af | section | 4. Construction - Granular make up and In-situ Modification
3732d630-8491-5d4a-9f08-4723776e9d88 | checkpoint | Stabilising Depth
2afea585-0ee3-54af-8188-1b39a2f3ccd4 | note | Controlling Documents - Rehab design report
81d94d38-a8ab-5ab0-b38f-13bc36375685 | note | Acceptance Criteria - -5mm + 15mm of design depth
a9b071ac-fb99-5c7b-9a9f-e6d7f815e3cf | note | Method - Depth measurement
05a8d3fe-89e6-5fc9-a192-8e64ed21cc6d | note | Frequency - every 200m
825ac38c-3d2f-5845-b45d-ea254270fb01 | note | Responsible Person - Quality Controller
0d3c3b6f-55ad-5902-9401-af239b69052b | note | Verifying Document - Daily Site Record
84e43414-d3ed-5b23-91d5-4b64cf7d965d | note | Conduct - S
8dad80e4-02c6-508f-b990-3d73d17b3434 | note | Approval - C
cb667f2d-aa01-5f1d-bd60-10d9eb7bdaee | note | Witness Point Y/N - Y
034e3d0a-6899-5057-8f7f-ded21de23dd6 | checkpoint | Visual Inspection post hoe (1)
b7b9f4fa-a025-5316-8a2b-29a011aa48cd | note | Controlling Documents - 6x4 truck fully loaded or similar equivelant
64aeab05-c252-595e-acc4-3bf87f40b90c | note | Acceptance Criteria - No identified movement of the pavement under proof rolling and for subgrade contamination
12ba50ec-70c4-55d8-8ecb-1787fe66b2d6 | note | Method - Visual Inspection
fbf24d6d-29b5-5bb8-a27f-8710330d2607 | note | Frequency - Each Subsection
193aff56-2e23-5ef2-9d4b-e37c922205c0 | note | Responsible Person - Quality Controller
e355e939-1efe-5bf2-9196-a5757e32b277 | note | Verifying Document - Daily Site Record
66f134a8-f31a-5a83-9e47-d309499c2902 | note | Conduct - S
72be6b8d-332d-5a40-a3fb-df2aee2d8d4d | note | Approval - C
13cbd78d-0435-57ed-9479-9bba221f7bd3 | note | Witness Point Y/N - Y
c59243b6-062b-52c8-bd6e-e7959a49d521 | checkpoint | Visual Inspection post hoe (2)
93b19a35-0a5f-5067-a8bd-c099081854f3 | note | Controlling Documents - Particle size to be 50mm or less
fc46f8de-44a0-547c-a68d-6f99b3f60e2f | note | Acceptance Criteria - Materials as described in design report - grading and PI suitable for FBS. No large slabs of existing wearing course or strongly bound base
6490bc93-0540-5d18-9e00-eb9511b255ae | note | Method - Visual Inspection
915d6f11-2827-5462-a11b-3776179cffbd | note | Frequency - Each Subsection
3ba8a735-e242-5036-9ef1-c2caff81d0dd | note | Responsible Person - Quality Controller
9e7dbc79-5efc-5216-95a6-e4025845edea | note | Verifying Document - Daily Site Record
0379113d-45ab-584c-8e20-5aa6f991b92d | note | Conduct - S
c7d37f9d-1113-5cc4-8452-372af9e08306 | note | Approval - C
f1a3a64d-381f-55b9-b510-f567d82053eb | note | Witness Point Y/N - Y
eeb50d65-64ce-572e-8456-9dd1f3e00c42 | checkpoint | Place M/4 AP40 Basecourse Material
21c5bc4c-1fd5-53f2-88cd-13fbfdf41b4b | note | Controlling Documents - TNZ B/5 (section 7)
d681a7df-9266-5172-9a73-cc68df224beb | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
dabd854b-d9e6-55c8-9f32-835ef51689ad | note | Method - Visual Inspection
d6d0db4a-efe1-57d1-aed1-e37a86fe3bfa | note | Frequency - On completion of placement
3641d297-27bf-51cc-bca8-57b62e962874 | note | Responsible Person - Quality Controller
e1b639ed-788d-5a9e-9bd8-b7f4db4fcea9 | note | Verifying Document - Photographs and Daily Site Record
ddd08e19-2c34-588c-8b5e-28b2e9f74e14 | note | Conduct - S
6f868a3e-10b8-5a06-939e-ef94a00d148f | note | Approval - C
441aea24-49cf-5c30-b1d8-2941adb11b8f | note | Witness Point Y/N - Y
eef430b9-576a-5732-b169-7eee15c58335 | checkpoint | Surface Shape
b9e98a79-fed9-58d4-9aae-f86c64f862e2 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
c5ccda9c-7dd7-5f9c-9166-ed54f84af854 | note | Acceptance Criteria - Between -5mm and +15mm
3997c264-9c2c-53b9-8e58-9fafa70e911f | note | Method - Visual Inspection
746a4398-90a5-54c4-8885-88765221bf70 | note | Frequency - 1 per 20m
479b02ae-19ef-5aa6-94e2-f053b4491eb4 | note | Responsible Person - Supervisor
b767417f-122c-5297-9503-b110bb28881d | note | Verifying Document - String Sheet/Survey Asbuilts
e4e38743-ba4c-5a19-918a-774cff19ef85 | note | Conduct - S
9b8c3db9-f0e5-5c30-bba0-a18e46c48bb1 | note | Produce Record - S
dc4b966d-5de6-5562-a2f7-e55a6845fc53 | note | Approval - E
992793c8-65a0-589d-ad48-4eb6b878f2ea | note | Witness Point Y/N - Y
f18dc5a2-4f34-5cff-86fe-8227470b0629 | checkpoint | Cross Fall
0da23b78-7228-599b-8067-378a03c94e10 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
01ecc6a3-8abf-59c4-b0a5-23d57436ec54 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
b4586af4-4beb-525e-b752-18e664e98399 | note | Method - Visual Inspection
a30b42ff-1885-5b77-a6a1-7b4da30db346 | note | Frequency - 1 per 20m
2a7c9f64-954a-5199-9588-88cf5f74472d | note | Responsible Person - Supervisor
b3b6fe03-82bf-5aa5-9608-974644c0c954 | note | Verifying Document - String Sheet/Survey Asbuilts
8788c31e-7c76-58fb-9a36-844e5de01477 | note | Conduct - S
de2885e3-68e0-57fd-82b5-4b73113211e3 | note | Witness - C
9bccacb3-1a74-596c-8ba0-9ceec09f78dd | note | Produce Record - S
dc641f23-bcd6-5d3d-b14b-aa722370457c | note | Approval - E
4dd8a10c-a42c-5ca9-a168-543cf2c26e9a | note | Witness Point Y/N - Y
0bb40e61-e98e-5b2d-a01e-8a83ca21acf5 | checkpoint | Production and Injection of Foamed Bitumen (1)
0787432c-d66c-52c9-8e29-dffeae1374d6 | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
7a616773-3f8c-57ba-9176-71c191618f93 | note | Acceptance Criteria - Monitor bitumen pressure and bitumen flow on display. ± 5% of specified rate
95d6f043-e9bb-55ff-b9af-a4494b0c6139 | note | Method - Monitor
d1414c7a-65fa-5b48-9e78-90ec7300e969 | note | Frequency - Continous by operator
c39d840b-2cef-56a5-8a87-b6f1fd4df5ff | note | Responsible Person - Quality Controller
8760bc12-7ad0-5ecc-aba8-399399be9c0e | note | Verifying Document - Daily Site Record
34f5413a-fc8d-5469-a0a1-c5b6490c99b0 | note | Conduct - S
97da121a-e680-5fc5-ade7-91c0e0ddd094 | note | Produce Record - S
55ded80b-e530-5320-8417-06468578e793 | note | Approval - E
11129784-930a-5ce9-b0ce-6e5b2dfb1433 | note | Witness Point Y/N - Y
d3212d24-5c9d-503a-9631-79674682244d | checkpoint | Production and Injection of Foamed Bitumen (2)
ad8addd7-8501-59fa-b812-e2fa4bf14483 | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
7750e535-c1f2-5156-b8ba-f212c9051948 | note | Acceptance Criteria - Bitumen Application Rate. ± 3% of specified rate
7cc46d83-0071-5b43-9eb1-b607a2ab9431 | note | Method - Record
8f45a12f-c50d-5079-9706-dde04adc934e | note | Frequency - At the end of each run
4d1a6fd9-91ae-5b08-b183-4276128c50fb | note | Responsible Person - Quality Controller
22f3f945-bbfd-5c69-9f57-6f001b9b2167 | note | Verifying Document - Daily Site Record
43de4560-902c-5556-a67d-e2eb469b2ab4 | note | Conduct - S
ed0c7ff5-3582-59e5-8f24-c0697fa1397a | note | Produce Record - S
9dc73cc0-cee7-5835-8520-4e158f2f98a3 | note | Approval - E
faacd1f3-d649-5346-8a43-3b76027db985 | note | Witness Point Y/N - Y
e3d51234-d1bd-553f-8876-a60f857c3d8c | checkpoint | Production and Injection of Foamed Bitumen (3)
d75a9d2e-2f7c-560a-88d8-7b9904fb21c9 | note | Controlling Documents - Foam Bitumen (7.4 Table 3) - TNZ B/5: 2008
a3fff577-cc8e-5c4b-959d-4e68ec8db213 | note | Acceptance Criteria - Average Bitumen use test per tanker. ± 2.5% of specified rate
ee749fd5-dd55-535e-a5b4-d8bd95d1ec8d | note | Method - Record
fbf9d1bc-e52e-5120-9bb3-fde34576e1f9 | note | Frequency - Reconcile daily bitumen use with Area Stabilised
a6198179-3963-56ba-b5ed-31316c8bf7e8 | note | Responsible Person - Quality Controller
8ff9ec12-f2a1-573f-95c4-8e71db2d0c03 | note | Verifying Document - Daily Site Record
77df7f65-676b-5388-85b2-6d72c3ab0cf9 | note | Conduct - S
4d7b0c6e-c4f4-5661-aceb-bb1fb92ea040 | note | Produce Record - S
7eaebd8c-b623-5e97-b548-d65875d3a5aa | note | Approval - E
36d8b609-22b9-518c-83c3-f9e751c240e2 | note | Witness Point Y/N - Y
3ca10252-2e89-5869-9e68-19e9e67dbf5d | checkpoint | Injection & Mixing of Water and Foamed Bitumen
7cb65465-38d1-5fc1-9792-958c0d1a6cf4 | note | Controlling Documents - Foam Bitumen - TNZ B/5: 2008
fc7e3c8a-849c-5f2d-aa69-c0d330e4666b | note | Acceptance Criteria - Mixed material free of bitumen blobs or streaks. Overlaps minimum of 100mm
2e551841-3495-5d56-9417-5466a8e36803 | note | Method - Visual and hand squeeze test
5e146176-81e6-5455-86b3-a253f6862755 | note | Frequency - On-going visual assessment
157f6bc0-a316-52aa-87c0-cb8588c7ced0 | note | Responsible Person - Quality Controller
d75e6fb4-a1e1-574e-9546-f80663039fc1 | note | Verifying Document - Daily Site Record
0408f4b9-a7db-566f-842e-c8ce49681812 | note | Conduct - S
2d68548d-1090-53c1-a35c-845b14fa4e6f | note | Witness Point Y/N - Y
27c96781-3034-5bd6-8be1-9136ce336cf1 | checkpoint | Spreading of Cement
01ccfb4e-0c49-5fed-a1d3-0b505fb19505 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
7f2c4983-e50d-596b-8c7b-c22ef42a846d | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
7ef34fa0-8e9a-59bd-8785-ce8c88330fc1 | note | Method - Mat test (1m² canvas) and Average Usage Test
f6dcb570-3e7f-5770-a3be-074b3d13f53a | note | Frequency - per 400m² and upon emptying the spreader
f5a02c9a-601e-55ba-8fb3-3c1d16e31056 | note | Responsible Person - Quality Controller
25150e0b-d59d-5da4-a749-b162e20f96f9 | note | Verifying Document - Mat Test Form and truck dockets
db4c3540-5ba8-5936-95de-e62fec1a09bc | note | Conduct - S or Sp
f08fe4a8-8cdc-5363-b58f-53f328c3db20 | note | Witness - C
b49eeeef-bdfd-5811-97a0-12608fe561e9 | note | Produce Record - S
4a42d774-1ffc-5e66-bcee-3e7b45d3937d | note | Approval - E
4a80da64-6bc2-5a74-b787-1b30688ae0b5 | note | Witness Point Y/N - Y
cd42d518-c789-5f9f-a050-acc6478d5f21 | checkpoint | Addition of Water
e8cbeca5-975a-57f5-88d7-a0f7cd20e1b1 | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
6fcfe044-de0f-5703-82ea-84249fb99402 | note | Acceptance Criteria - 90-100% OWC
d63b43d2-13bb-54f9-9f97-51303c42c46b | note | Method - Nuclear Densometer Testing prior to Stabilisation
3f5c9685-8eec-5193-87d1-1b016ebae4af | note | Frequency - ≥1 per 1000m² lot
a1a60caa-9712-57d8-a824-8f80844f6b6a | note | Responsible Person - Quality Controller
f0ec5550-cdad-5db4-ad79-d219dbe9e06e | note | Verifying Document - NDM Record
a4bfeeb5-cbfe-50bb-acb6-8df6d77bd5cc | note | Conduct - S
aad7331d-534a-577c-8ef3-deb8b9608bb0 | note | Produce Record - S
61fce15c-0bce-50bb-9ccd-430c0ac70035 | note | Approval - C
fa6d7525-eeab-5b17-b87d-0fa6815e3a5f | note | Witness Point Y/N - Y
3aae6428-5972-5b13-a661-272c4bed881e | checkpoint | Cut Depth
ebc55cb7-ee04-5ca9-87ad-2f8a52440bd5 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
b586279a-c5d4-545c-bba0-5b99949abdd0 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
6afd350f-33f8-5fda-a5d4-90decefff04f | note | Method - Physical Measure and Visual Record
94d5311c-2fb6-595d-a569-5520eac71ddf | note | Frequency - ≥1 per 200m of cut length
734e1b1a-372b-58ea-bea2-862470a27081 | note | Responsible Person - Quality Controller
572d8a70-c8ee-5727-8e25-fbe9ab54c841 | note | Verifying Document - Photographs and Daily Site Record
e3d43801-33d6-5699-952b-05f04155daf6 | note | Conduct - S
6548fbf9-b3bd-5df3-83da-612e46e0dacd | note | Produce Record - S
e771636c-bed8-536e-a921-4d23970f28d5 | note | Approval - C
64e27a63-bb79-5ee5-926f-a611dfec9d9c | note | Witness Point Y/N - Y
b4e8c8c0-519c-5ea3-a63c-d6e4e3e61d57 | checkpoint | Longitudinal Joints
9b5327ea-537e-5b38-99c6-5e59d8c3d7ab | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
0c85fa4e-c8dc-5d02-8086-ca7b5301c52b | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
32a20381-ae33-50fe-96a4-ef0d500f2153 | note | Method - Visual Record
66187f92-e66c-54c8-bdce-7402c3413912 | note | Frequency - per sucessive cut
b81cacf8-1ec6-5181-b369-c14fd378959c | note | Responsible Person - Quality Controller
62afa504-059c-5ae3-a1e1-3ed92e2cecd6 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
7c7229c5-00c1-5d45-8929-c2cbf43243f3 | note | Conduct - S
a441f553-3013-5f26-b514-0098c9580486 | note | Produce Record - S
1119caf6-5db9-50b8-ab08-39a1b830e34c | note | Approval - C
47cf2557-01ee-538d-ba8b-e62d9319f341 | note | Witness Point Y/N - Y
4adf91a5-413d-56e8-8c6a-9cb5dbaf546e | checkpoint | Continuity of Layer
c9d50993-7259-5628-afe1-b3c7028f8019 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
1b08175e-0ee5-5802-a517-bb3383da8f0c | note | Acceptance Criteria - Longitudinal overlap, 1m for cement, 5m for bituminous stabilising agents
24ac5396-0969-53a0-b81e-86c2010cdfca | note | Method - Visual Record
4daf123b-5ca0-5906-b8c9-c2b16738d042 | note | Frequency - per sucessive cut
f8817565-3b53-507d-a9da-b1b1e3646e7c | note | Responsible Person - Quality Controller
3fd73da4-511c-5094-8466-743164294688 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
da41b8e4-767e-5e8c-b8fb-ffe70283dcae | note | Conduct - S
8453cf06-7396-538b-93e7-15ab5a8b1385 | note | Produce Record - S
56fc7dce-5864-5a9d-9001-20df43ae960a | note | Approval - C
3284a205-f31a-518f-9c15-3d482ca92fb2 | note | Witness Point Y/N - Y
a3e7c399-2e95-59d2-b1ad-e3d1d43952bc | checkpoint | Stabilised Material Particle Size
66888246-25a9-598c-a7f3-85c05bd7033e | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
6af51b4a-e768-5db1-b26a-2820db568e25 | note | Acceptance Criteria - No excessive breakdown of stabilised material
956a8882-d895-534f-871e-bcc5486f6e75 | note | Method - Visual Record
ef19ff4a-409c-5f72-9038-f917d1042dc9 | note | Frequency - Within 20m of each section and then regularly based on material variability
0cefc096-aecb-5d26-9e01-3a51214a24a8 | note | Responsible Person - Quality Controller
abf72aee-6b9f-5e79-ba15-7d1b19ce8224 | note | Verifying Document - Photographs
214dcae1-16de-5d36-aa67-fd6fa6f63537 | note | Conduct - S or C
7b25bade-ecc9-53c1-9c3b-d5eecc0b8ed0 | note | Produce Record - S or C
0cb8993e-faf5-5185-8e9e-7ce2c530b759 | note | Approval - C
81ad647b-afd9-5cef-b884-c82bb09f9249 | note | Witness Point Y/N - Y
1c499f10-3060-5072-811c-06e6877fc457 | checkpoint | Establish Compaction Target
c6822e3e-fd49-5b27-af72-fa81df87c9d6 | note | Controlling Documents - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
0f904c80-dc87-57e2-a1ab-e7a5034a4f42 | note | Acceptance Criteria - To provide MDD for NDM testing
091529bd-d9f3-54d4-9066-d6c2d56918a0 | note | Method - Plateau Density Testing
a49ef4c7-861c-5630-ad81-33ecd335b36b | note | Frequency - 1 Every 3000m2 or once daily, or additional tests when material changes visually
4a867cc6-f129-5605-8544-a1120831fa36 | note | Responsible Person - Quality Controller
b0c9544d-97e6-50ad-8814-9e12bdea2bb8 | note | Verifying Document - Test Record
6877d6ea-ea10-5f04-840a-2c8564d4b4c0 | note | Conduct - S
28317c3f-c3c5-55e0-b02d-e357938f1a84 | note | Produce Record - S
906d1113-ec27-5dd4-8514-04af4e07ecce | note | Approval - E
5fa76479-ce90-568f-b0d6-b2bd0cf7a3be | note | Witness Point Y/N - Y
c6afc49d-3e73-5118-bea3-61314ffe0972 | checkpoint | NDM Moisture Correction
43b8ce9c-9e9e-5921-a1f6-3dd81c60f023 | note | Acceptance Criteria - Correction offset to be applied
dd05b172-2244-507d-b073-304b64ee09dc | note | Method - Field Sample and Laboratory Moisture contents
cb8d379c-da21-56a4-85eb-5b5bfca8d2f5 | note | Frequency - 3x Moisture contents per single plateau test carried out
97f81a1a-15d5-540f-8d03-4d156c989484 | note | Responsible Person - Quality Controller
3292e681-a9eb-523a-bd81-8adb306c95cd | note | Verifying Document - NDM & Lab MC
e9683198-a3cb-518a-acb8-b36cb87b1f07 | note | Conduct - S
9aee35c8-4300-5fa9-968a-44574cef6ade | note | Produce Record - S
abb34566-52c6-50d1-b12c-a2dab7da535a | note | Witness Point Y/N - Y
6f0b2bf5-1da2-5691-9a2a-fd78c49c3a73 | checkpoint | Foamed Bitumen QA Sample (1)
220e6751-b8ce-55a7-9538-35c5d891c097 | note | Controlling Documents - Indirect Tensile Strength, ITS
7d356d9f-8c35-51d8-83ea-0582b7c4cd9e | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa
e3a81253-61de-5c9f-aa64-27c119841a08 | note | ○ Soaked ITS: 150 kPa to 350 kPa
a41082d6-7bea-5dee-bb01-c14eab18abca | note | ○ TSR ≥ 70%
38bd8f45-4251-5001-a6e7-e073d653227a | note | Method - NZTA T/19: 2020
4ff7875c-ddd4-5677-9dc7-d75807e8f2dd | note | Frequency - 1 Sample per 3000m2 or once daily, (1x ITS or 1x UCS per sample)
2d7c9cdd-2354-54b3-b3b9-2f75efdc1226 | note | Responsible Person - Quality Controller
00c88ba1-7c96-52a7-a05f-14dee7c4cd11 | note | Verifying Document - IANZ Report
f413ab7d-6d99-5f1a-94cc-f0408406dd69 | note | Conduct - S
f6335258-8588-5d91-a12a-e803e9057951 | note | Produce Record - S
fc2bee9c-6ef5-51d5-8cea-65f819791abc | note | Witness Point Y/N - Y
33f67571-f142-5f24-b0c6-1d3228675495 | checkpoint | Foamed Bitumen QA Sample (2)
c2c9f7e1-931f-5762-ac83-e4e24e91d5b2 | note | Controlling Documents - Unconfined Compresive Strength, UCS
85657bdb-5093-573f-8485-eb2600f19ca2 | note | Acceptance Criteria - UCS is used to calculate MR(Phase 1) and MR (Phase 2)
00f484a8-9eba-51e9-ba85-d89a4095d7c4 | note | Method - NPTG Guideline
e3851310-849a-55e6-87c2-36eb6c3444a2 | note | Responsible Person - Quality Controller
528252b0-43ba-59df-be14-4bee64cdaef6 | note | Verifying Document - IANZ Report
64c4ec58-9dc9-5a6e-8499-511b9498d0f2 | note | Conduct - S
4719ebc3-e490-5a67-b58a-db3ae4626c44 | note | Produce Record - S
a94189fe-af1e-5001-8a76-50cb5df82066 | note | Witness Point Y/N - Y
cb4f8a2e-61f1-5299-a81a-a0ab0ed04652 | checkpoint | Compaction Acceptance
26230965-20ee-564c-88bd-1cf030411f0d | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
8ad43ded-ec10-5cbe-b45e-7201f9131b49 | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
0f77e7d7-7302-5646-b937-64d6ff660937 | note | Method - Nuclear Densometer Testing
e86c5bae-5c7a-5477-b256-bd3146dfff92 | note | Frequency - ≥ 5 tests per 1000m² lot
ea922664-38bd-5eff-8fdc-2b556735a888 | note | Responsible Person - Quality Controller
8e4c9933-be04-5c45-90e3-933ffc7aa301 | note | Verifying Document - NDM Record
11151ed7-16b1-511b-bbef-87443b7a4ac6 | note | Conduct - S or C
6f58539c-b5e2-57f4-977b-6607c5f8e9a0 | note | Produce Record - S or C
7b0004db-431d-58e1-9fdb-aeeceb29929d | note | Approval - E
1509704a-d0af-52a8-b378-23e9d2a3b917 | note | Hold Point Y/N - Y
99c521dc-d410-59cb-b783-f46873fd86c0 | signoff | HOLD POINT
63ac480a-f8b5-58f9-bbf7-a763b61d12c2 | checkpoint | Surface Smoothness
ddfce2d0-9a98-5206-89d4-4515b499cba0 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
5bd80133-dfe8-5cea-9fa3-d2bc88f74a4f | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
4528f006-72af-588d-8d3b-93dd7f554075 | note | Method - 3m Straight Edge
93d423b2-53ad-571d-a7e7-5e39f2e51d37 | note | Frequency - During construction and prior to seal
a48cb531-df91-5e9d-b880-e8f2730fa549 | note | Responsible Person - Supervisor
16423559-7746-5259-80c7-3aa7ea1332be | note | Verifying Document - Photographs
712d59eb-4901-5dca-94dc-f5270217afca | note | Conduct - S or C
43cc2515-5ebb-54a3-beb6-bc0c67a58f5a | note | Witness - C and E
358efa70-27c2-59c2-96fe-574f9acace84 | note | Produce Record - S or C
924f2131-317c-5b93-a720-24c004fef9d5 | note | Approval - E
6a6d0959-50fd-539b-b39e-2f79949f5abc | note | Witness Point Y/N - Y
fe8bbdd1-7874-46e9-9fc4-5b0a4cd62d96 | checkpoint | Surface Shape
812860b7-cdc9-54fe-8cb2-f22c3817afb5 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
a6283130-a7cd-54a2-ad4a-8f5e85c003aa | note | Acceptance Criteria - Between -5mm and +15mm
e0b09e8c-794f-5814-a0e1-8e5b45624697 | note | Method - String lines or Survey Asbuilt
c9dacc80-f542-5f1c-a86d-3d91cf6a387d | note | Frequency - During construction and prior to seal
7bdabb34-9ede-5dc7-b153-79f1ec56ca0b | note | Responsible Person - Supervisor
a5feb6be-ae4f-5f00-9b35-235b2c674417 | note | Verifying Document - String Sheet/Survey Asbuilts
b3e296a8-b071-5162-b662-836505beba5a | note | Conduct - S or C
87e37cdb-9cae-5999-a080-1ff095e2c971 | note | Witness - C and E
14055d37-7b80-59e2-b346-6417cd5027ff | note | Produce Record - S or C
3e0e9b98-2bae-5eaf-8d4b-6762e9f78645 | note | Approval - E
2b7039a1-c4bc-54b3-8422-fdabf38863a5 | note | Witness Point Y/N - Y
a6020578-54c7-4ef7-92ce-73a03f11f05a | checkpoint | Cross Fall
38a386ff-a2fa-5cc2-8ba6-ee57d50d34f0 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
6e064cac-b79b-583c-9ca5-4c76745ad06a | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
e4064444-8202-5b7e-bcfe-2dd30acae2b7 | note | Method - 3m straight edge or Survey Asbuilt
20f9906d-c848-50ce-b7c8-f4aaef50c0b1 | note | Frequency - During construction and prior to seal
6cc47985-395f-5925-9cf8-5ce36a2dcde3 | note | Responsible Person - Supervisor
609377c6-22c3-572f-ab5d-b575d00c79a4 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
e82b9204-9587-5956-a9ff-92fd76d03f81 | note | Conduct - S or C
8276e5d9-3540-5e1c-b5f6-e82cc43415a7 | note | Witness - C and E
21e378bd-6d01-5d0e-9ddb-f26b7557e83f | note | Produce Record - S or C
fc7ff48d-1552-5232-b36b-920da04a11d7 | note | Approval - E
1dcafe22-f3e0-55cc-b457-24c551c96022 | note | Witness Point Y/N - Y
59326368-fba8-5b82-badd-9e7d3256fe02 | checkpoint | Surface Finish
868726b6-492f-53ad-aa5b-7f4ce6112a7d | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
c9b260d5-b5fa-5d8f-a56b-8dba9797daa0 | note | Acceptance Criteria - Tightly bound matrix post sweep
13dccf09-db24-5738-8ff6-ce6704ef3034 | note | Method - Visual inpsection
29f6939c-1c0e-541d-ae33-4e4fedf0e025 | note | Frequency - Prior to seal
d73ef07a-8583-5f63-ada2-b24d65e075e4 | note | Responsible Person - Supervisor
60d7b473-9bfd-5aa9-abe9-16b6eb318ea1 | note | Verifying Document - Pre-seal inspection sheet
0b27f8c9-c0e3-557d-9358-11fd15730126 | note | Conduct - S or C
d8daaf21-088e-501c-92ba-ab01e4baa0b1 | note | Witness - C and E
087b265a-6d9f-53d4-9369-bc0ad69295de | note | Produce Record - S or C
a9ecfafa-c27c-59e3-8d52-3d544167ece0 | note | Approval - E
140ad576-fe6c-5e06-ba62-d24f824b1189 | note | Witness Point Y/N - Y
fad17651-ad27-59a2-9891-8148a12d4957 | checkpoint | Degree of Saturation, DOS
7ec74b89-0f51-5afc-bfbc-f5d4d7fe9002 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
b27d4f77-10ca-5b23-bc08-fca152407b97 | note | Acceptance Criteria - ≤80%, however 65% is ideal
1f90d3b2-f3a3-5d5d-ab47-3a7be023e232 | note | Method - Nuclear Densometer Testing
cf15206b-21f0-5190-9dd7-b4650c86fbe4 | note | Frequency - ≥5 tests per 1000m² lot
2946e989-e77c-52bd-9e85-388d0ae65667 | note | Responsible Person - Quality Controller
57af6911-f454-51ff-952b-2dbee2e0b466 | note | Verifying Document - NDM Record
3ec993e5-0177-54c8-9228-a4f462b6e839 | note | Conduct - S or C
a96cdf61-1b54-5b83-9e6f-c5b51706f4e8 | note | Witness - C and E
c0e01208-3a82-5d77-8a4b-78a886a478c8 | note | Produce Record - S or C
81f8013d-cb46-5f82-9090-1010dccd309d | note | Approval - E
a9df603b-ecaf-5b11-9110-a72af183e2cd | note | Witness Point Y/N - Y
c00b2f95-9cd0-54cd-a721-7d16d11f1667 | checkpoint | Roughness (NAASRA)
2b0bdda5-02f0-5d4d-9a87-b0b053e4935d | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
d2af5a3e-31d1-583c-858b-d0b6c06392fd | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
a4d7565a-10b7-536f-aaed-6d6732d5449a | note | Method - NZTA Maintainence specification section 6.1.2
412e9453-3d32-5281-86c0-b34aa05aac7c | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
fd9f5a96-76ef-51d4-be0c-b96f99de653c | note | Responsible Person - Quality Controller
553a6213-90a1-535b-8bc3-6cf6c57a9d83 | note | Verifying Document - Test Records
de331983-49e6-5d81-8e3d-7903e9d3038e | note | Conduct - S or C
17b1ef23-00a6-5498-9dfb-e15717887028 | note | Witness - C and E
80788ec2-2e69-5af5-8ff0-4723ef39454b | note | Produce Record - S or C
e8deff9e-30d2-51a9-b322-b9719712c616 | note | Approval - E
39ff6523-a447-5e6f-8ea4-400268c51264 | note | Hold Point Y/N - Y
cd1b9311-7976-5fbc-b77f-054ed37f9e9f | signoff | HOLD POINT
f6ac91d4-5c0b-53d1-9e4e-00bc03939ff3 | section | 5. Chip Sealing - 5.1. Procurement
498da6b6-9f54-512a-8531-43f73bba1b43 | checkpoint | Binder - Penetration Grade
8b2026e2-5b11-5d8e-85b7-641e09620f70 | note | Controlling Documents - TNZ M/1
be0db22b-1bdd-59b9-94ca-168995dc9cbc | note | Acceptance Criteria - Table 1
59b30edb-46b3-5fea-b432-3b259d11440b | note | Method - Property Test
229aac6c-5e20-5446-b964-0ee299be1b77 | note | Frequency - Annual
9fb11499-1889-5658-8794-ec37384fa741 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
e7f07254-5c65-541f-b458-bd7251dad088 | note | Verifying Document - IANZ Report's
6007b62b-3dfc-524e-84a9-16cf98bf2e32 | note | Conduct - C
d93a25cf-f88f-57c1-86a8-fd6e1771c64e | note | Produce Record - C
ea3ea4b5-d7cd-530e-a42d-299825b7fc19 | note | Approval - N
34cd4309-0e8c-5fe7-8c7b-7c872f276590 | note | Witness Point Y/N - Y
fc70564f-95e3-59cf-8349-820febf11e53 | checkpoint | Binder - Polymer Modified Emulsion
4f130326-4ac6-5ad8-94bf-d1da4f6f853f | note | Controlling Documents - Higgins Internal Specification
ea84c8e6-d8da-5b66-9cf2-0046330144d6 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
51e6effb-4f57-5ff9-a3dc-cce3e0e6a95f | note | Method - Property Test
ab4ab284-ba13-5c33-aa62-58f420c63640 | note | Frequency - 1/100,000 litres supplied
8b8928df-d417-5343-98ef-e190ca92bd98 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
0a6a6752-3456-5e8a-815f-69f446b884ba | note | Verifying Document - IANZ Report's
47193936-997c-5df8-bf37-d79914c923d5 | note | Conduct - C
a02eaa3b-006d-5a1c-801f-872ffe6934da | note | Produce Record - C
d866e11e-5d26-52ae-87d7-beadf9f3c6f5 | note | Approval - N
89053006-b780-5109-91e5-5c98b8009e9a | note | Witness Point Y/N - Y
271433f5-90db-5716-947f-66b53e064a88 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
53bdd787-6abb-59e0-95a6-6f15986991af | note | Controlling Documents - TNZ M6, RNZ 9805:2009
5805228b-27b1-5deb-b304-4cea666ce82b | note | Acceptance Criteria - <10% fines under 230kN minimum
03f55fad-b473-5c2a-9625-a9a03892548d | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
3c35bcf8-3e17-5078-a4e1-95cd9fc8478e | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
493b8b36-9acf-575a-bea7-56e58e336de4 | note | Responsible Person - Surfacing Project Manager
29a38890-dab4-52cd-ada6-dbc43f641708 | note | Verifying Document - IANZ Report's
67c04894-90d3-547b-8737-7ecfce18596a | note | Conduct - C
7d1e485c-2520-5814-a215-e81fdaf3bffa | note | Produce Record - C
b53d1e8b-329d-55bd-ae3e-be21470291d1 | note | Approval - N
58473c41-c29c-5485-bc36-981a06c71a98 | note | Hold Point Y/N - Y
6001235b-048c-5705-ab46-316e6fddaf77 | signoff | HOLD POINT
b5105286-fa50-5f37-8ad8-ff00dc521109 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
58fa62a9-215d-5613-9bd9-9ab49e68b8f7 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
63c2cbcc-d06b-5c5f-8e38-e683cd3c21fe | note | Acceptance Criteria - AA or BA
c0b725be-8998-5409-af16-20a224d0622c | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
6ed7d5fa-4724-5ae7-b043-720c872f0afe | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
76562c23-102d-5b40-8462-46979e041c9b | note | Responsible Person - Surfacing Project Manager
6bff282c-1e51-5bc9-bb12-4f619d815429 | note | Verifying Document - IANZ Report's
cc78577e-0975-5d75-9839-b7ddc6c612f0 | note | Conduct - C
bfd165ea-9de0-50b6-92c0-90d9bd220e9d | note | Produce Record - C
4d8b8969-ab8e-5dc4-b597-0cae2ac7aeb0 | note | Approval - N
e3023068-e8a8-5c87-837d-1d61b79ccb5b | note | Hold Point Y/N - Y
d36fb53c-673d-5ad9-bcd6-d21d23c23bfc | signoff | HOLD POINT
09367c8c-c6d5-5493-9e5b-f99474f4f8d8 | checkpoint | Source Property - Skid Resistance
b3fcdadc-47af-5046-b498-b600d99da170 | note | Controlling Documents - NZTA T/10
3bee80aa-778f-59f5-b27d-07d4c2d2b80b | note | Acceptance Criteria - Meet Skid performance Requirement
940bd552-0893-5542-8955-587de23dc15e | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
2fcb1c13-a902-5a81-adb3-e618b4de9fdc | note | Frequency - Each Site
394707f7-9057-588d-8570-80e0918c1cf4 | note | Responsible Person - Surfacing Project Manager
31c3a542-0ed2-56ae-8560-b63e2da24e03 | note | Verifying Document - IANZ Report's
98a5d76b-247f-5fec-84f8-411a556f396b | note | Conduct - C
0909bf17-0574-5130-9983-fa9549281587 | note | Produce Record - C
ab53e95c-99c1-5f12-9586-98ee6b1c31b7 | note | Approval - N
b570047d-b82f-50e3-ab93-a23853f9ce9a | note | Hold Point Y/N - Y
66b59dc2-239e-5b57-9d6f-f6c2d5459c10 | signoff | HOLD POINT
93104285-bf3b-5c5d-b811-2cd0e5a6e9b3 | checkpoint | Production Property - Cleaness Value
d013ce30-a7e6-5498-9f1a-dad30a3593f5 | note | Controlling Documents - NZTA P/17, M/6
8ac5a65f-dff6-53a2-90cd-f27a0eb55a99 | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
42ba5bf8-81b0-5be5-b67c-1714c29e69f5 | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
ab1c3f03-1b62-59a0-b7be-35f5aaa45a88 | note | Frequency - Per Stockpile
1ddb6f11-0118-5632-a4a7-d289aabe3fc0 | note | ○ <100m3 - 1 Sample
0ece5cc0-c053-5ee4-8223-f317d4c88cff | note | ○ 100-500m3 - 2 Samples
8c67fac3-130b-524b-8054-50e825931b5e | note | ○ >500m3 - 3 Samples
1336dc3b-d8e3-521d-aba3-916b389df721 | note | Responsible Person - Surfacing Project Manager
3b594d53-9450-5e4f-a1e8-234f761807e9 | note | Verifying Document - IANZ Report's
007db50f-99eb-5dcc-bc81-4e530adebcdb | note | Conduct - C
03fe1fe4-33ef-50b5-bd10-0a3535ad5cf9 | note | Produce Record - C
d81a5951-f54c-527b-9143-4a2ca9982562 | note | Approval - N
84592c8b-8043-5cb0-8fd0-35db154d1acc | note | Hold Point Y/N - Y
4db47e52-e5d4-598e-a435-403f51d7f0ce | signoff | HOLD POINT
b9b36eb5-b5d8-5759-aaac-93619136de7f | checkpoint | Production Property - Particle Size/Shape
80b76e91-b34b-5780-95aa-fc9c1405cda0 | note | Controlling Documents - NZTA P/17, M/6
4201f73b-bda8-5187-b0c5-c38e35e231b8 | note | Acceptance Criteria - As per Table 3 NZTA M/6
9d471340-ecae-5049-9cde-d654db53e39e | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
96cc5a0f-2818-5188-bc12-5a5253c24535 | note | Frequency - Per Stockpile
bd89d0c1-d0b0-57df-90fd-7faddc94ccab | note | ○ <100m3 - 1 Sample
bc202df6-9386-5cc3-a3bb-d78c0ea7a0eb | note | ○ 100-500m3 - 2 Samples
9ed37431-615a-5dcf-9288-430f155bb036 | note | ○ >500m3 - 3 Samples
7fdeda30-12cd-5f45-9d66-00bb8ef83b33 | note | Responsible Person - Surfacing Project Manager
509a474e-20b6-550e-ac97-c8bd2f0be01d | note | Verifying Document - IANZ Report's
70f575ba-b170-5869-82d0-118f5bb9da66 | note | Conduct - C
f022fa0b-78cf-55e7-9561-c15f91841467 | note | Produce Record - C
1c2f736a-11ea-5a34-8e7c-86ff9c0112f0 | note | Approval - N
10558865-be43-56cf-b387-d406b2f2e288 | note | Hold Point Y/N - Y
e0a1bebf-91d6-5602-8dfc-01655256ebd2 | signoff | HOLD POINT
d316d2aa-fe2b-57df-9e4c-5d8d8f3e9be2 | checkpoint | Production Property - Broken Faces
21de5a0c-eba1-54d7-9a81-bfeb7bed89e8 | note | Controlling Documents - NZTA P/17, M/6
31af1d7c-29e1-5bc0-bace-66fbafed7e37 | note | Acceptance Criteria - Min. 98%
eb036cbf-9ef7-5268-88dd-46dcfab1837b | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
12e8bc99-57d9-5d2c-bdc6-1b4440336fcc | note | Frequency - Per Stockpile
357e6487-4a73-5787-b355-3fb31de7a90a | note | ○ <100m3 - 1 Sample
12fa72dd-5c3a-52d8-976b-9c826afa5aa7 | note | ○ 100-500m3 - 2 Samples
183ffe91-49ec-5024-9996-1bc1d4f52cf9 | note | ○ >500m3 - 3 Samples
b417e885-0b39-5ae6-8b01-254887b9859e | note | Responsible Person - Surfacing Project Manager
02064a31-e468-5c3c-b676-6a1806a30aa5 | note | Verifying Document - IANZ Report's
831009b1-4734-5cde-ad9c-51a34e05bdf7 | note | Conduct - C
ec7dd819-9d44-58e2-ba2e-c62b63e33af9 | note | Produce Record - C
cf2b5add-aa83-506d-b0ca-147774d7b5ea | note | Approval - N
02ee7ecd-f444-5759-b19b-582ad0386096 | note | Hold Point Y/N - Y
51cf9266-7ca9-52d0-81e1-7b1a620965d6 | signoff | HOLD POINT
37a2a4ed-b2c4-5c88-8c5e-3371b5a553f0 | checkpoint | Chipseal Designs
50e2ed0d-0467-5ea1-9ce3-4f4d8743274c | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
b26317d9-c3e2-5f1a-82f1-1ac43545a0c9 | note | Acceptance Criteria - Client Approval
393a1de7-6369-5a72-bab5-03f9a1433644 | note | Method - Review
a6077899-cf0a-5ea8-80eb-0a854c4433c6 | note | Frequency - Annual
d05fefcf-3e76-5640-95b6-f1db228fe463 | note | Responsible Person - Surfacing Project Manager
72729b87-0e5e-5953-bb60-c1bf950e3adb | note | Verifying Document - EBOP NOC Design Report Acceptance
3da5f6b3-9eee-5466-9cbe-576634a11bf9 | note | Conduct - C
730c21ff-4ec9-53f4-8de5-1db40bcc30b7 | note | Produce Record - C
67defe1f-5934-5acb-93c4-251160f8de3f | note | Approval - N
85002e89-68ab-5197-93e8-5251b1fc7692 | note | Hold Point Y/N - Y
873d9ac3-b39c-5dd8-bf2d-3eccb8b07d89 | signoff | HOLD POINT
2d90825f-40a1-55cc-9369-13e616f644fc | section | 5. Chip Sealing - 5.2. Construction
27519b95-4241-59e2-b5ac-988fd28163d4 | checkpoint | Ensure limits of site are marked
5f2c49e1-7583-5c4f-8e8e-55620301e720 | note | Controlling Documents - EBOP NOC Design Report
3478e702-e27e-5778-8ae3-14618c6f420f | note | Acceptance Criteria - Visual Inspection
a0872023-f428-5ca6-a55e-ebd11f6aff9c | note | Method - Visual
bbd9a1f4-d26f-5eaf-bcfd-a6d287c308b8 | note | Frequency - Prior to start sealing each site
bf749cb5-68bb-5a4d-85c6-fe49c7cf463e | note | Responsible Person - Surfacing Supervisor
a40b9a49-c342-5d41-b342-6c36600f4b17 | note | Verifying Document - Chip Sealing Quality and Site Record
ae1509bb-7c9d-5915-a86d-d3cd9276d75b | note | Conduct - C
2f25268c-aa4d-50a0-9dbb-de6183385b96 | note | Produce Record - C
bd1f95c0-4c72-56f0-962c-9d94f0c2ddc1 | note | Approval - C
ffaee45d-ac84-56b3-a7e4-11baa3ecdc10 | note | Witness Point Y/N - Y
0191fb96-f13b-5303-93df-b15eb545e1a3 | checkpoint | Sweep surface clean of deleterious material
d7eb7377-000d-5d40-b20a-1523ca316e5f | note | Controlling Documents - P/17
ce3eb77d-2f72-537b-b7cd-7aeaf05bbe15 | note | Acceptance Criteria - Visual Inspection
4821db72-74a0-51b5-8294-70d10c3bff75 | note | Method - Visual
e5e600f4-289f-546b-9ed1-72147a0ec6a0 | note | Frequency - Each site, prior to start of sealing
ecfd6c83-1542-5bda-95fc-afb1199dfde9 | note | Responsible Person - Surfacing Supervisor
b5485047-1821-5034-87f3-761dc21bd532 | note | Verifying Document - Chip Sealing Quality and Site Record
54829eb4-71f1-508b-83ad-15a7b44c3f73 | note | Conduct - C
22489c14-653c-5519-8cc9-b9ee06525f33 | note | Produce Record - C
b8359286-726a-5f34-b782-995cdc5c0216 | note | Approval - C
90267b27-eb40-58eb-9bb6-c6c255671fd5 | note | Witness Point Y/N - Y
dfbab4e1-ff06-56ac-a7b3-4ef83a267950 | checkpoint | Record ATP's on site
9157cf6c-b418-5a2c-96c2-586c9cea78d3 | note | Controlling Documents - N/A
eedbacde-e58c-5d87-a9d4-b52cf15f4f62 | note | Acceptance Criteria - Visual Inspection
4f2e6f78-aca2-5db7-b417-7b1071ed55d3 | note | Method - Visual
97bae255-d555-58f8-9ade-3639342085b6 | note | Frequency - Each site, prior to start of sealing
cdfc37a7-e619-5a36-8021-a3d8a7c21b4c | note | Responsible Person - Surfacing Supervisor
46ec55f4-951d-5aec-b8cf-96cf1d9bee84 | note | Verifying Document - Chip Sealing Quality and Site Record
e4a6be97-c42a-52b6-badc-f4e7ca466e44 | note | Conduct - C
ccd0b951-54e8-5a31-bffe-e2ec015d700d | note | Produce Record - C
4b513bfc-05b0-54aa-9370-93f87822a82d | note | Approval - C
32978c62-9287-582c-a4a4-4dc2889ae94e | note | Witness Point Y/N - Y
4eb5a901-1986-5562-be64-20d7083dff9b | checkpoint | Confirm correct treatment(s) and chip
906ac6e9-f530-5b54-8d6c-8c5ff9f64def | note | Controlling Documents - EBOP NOC Design Report
3d090462-c4e4-5572-88d1-89946534fec7 | note | Acceptance Criteria - Details/chip correct
64954199-08fe-578f-9f8a-785d628b2842 | note | Method - Visual
8edf05ac-e0f8-557b-96d5-8a5e1f6ebcc7 | note | Frequency - Each Site
e6247393-eebd-5f09-83ca-8e55b9a51879 | note | Responsible Person - Surfacing Supervisor
defb12e4-6a6f-5556-be7a-cee7d3a59b1e | note | Verifying Document - Chip Sealing Quality and Site Record
a9533c8e-7c9e-5d6b-8bde-4bdbfbb4fb85 | note | Conduct - C
e0fb5485-e7cf-5c69-af31-5be2f8ff64f8 | note | Produce Record - C
3971ba94-0aca-5f66-a558-5def33ea8878 | note | Approval - C
d28cd91e-7122-56fb-be17-072558387214 | note | Hold Point Y/N - Y
54c677c4-689b-5272-95d6-0dbb84402707 | signoff | HOLD POINT
a3e5bd64-9ae2-5457-8dcc-7fa942c6904f | checkpoint | Cutback Bitumen Blend
3bc3d8ab-318e-5d1a-a460-e81789623e83 | note | Controlling Documents - RNZ 9803_0513
82c52134-e0da-5918-8946-0a655708b59f | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
dbf69254-c62a-5823-bf90-1a3e18ef526d | note | Method - Sample and test
df32e95c-0be4-56e4-96fe-a19531524880 | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
46b011d9-0194-50b7-bcb5-506a2a2ef1bc | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
9098daa9-b83e-5630-9f18-b41b4e0756b6 | note | Verifying Document - IANZ Report's
615aa981-9686-5d20-a3fd-ad0ddd411b1e | note | Conduct - C
3df1b566-65c9-5abe-a384-c4a4746121a2 | note | Produce Record - C
f1883738-5363-5375-814f-bebbf078feea | note | Approval - C
6deffba3-96dc-58f8-8ce5-3e7fb2fea657 | note | Witness Point Y/N - Y
08cad3d2-eb17-574c-9444-b0dcda22403e | checkpoint | Bitumen Application Rate
f9e3b871-1d7c-5628-a871-74df9e204736 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
ead0579c-c347-56a0-a5e4-3beac853dbfb | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
16c64f10-2a0c-5a37-99c8-b73c976b5eb4 | note | Method - Test, Review
38bb261d-9971-549a-b8a3-c2408c4667d2 | note | Frequency - Per Sprayer, Per Site
3b7f1ab4-bb84-5d6a-9e38-9f19bdd6260f | note | Responsible Person - Surfacing Supervisor
b6cb8d78-810b-5043-b6ba-3db12c4f3e0f | note | Verifying Document - E/2 Certificate. Spray Sheets
e8e118f5-dac0-5783-9203-82140ed00748 | note | Conduct - C
b7b22fea-4e9c-5c34-9c7a-0a89d830f1b1 | note | Produce Record - C
8244ccba-a37f-58e1-afbc-ff78dd4d19ae | note | Approval - C
a8e00db9-ceb7-57bc-adfa-7eb4edf5bf99 | note | Witness Point Y/N - Y
55319508-1830-5e1b-8e4a-92461565e15c | checkpoint | Chip Application Rates
7969e978-a16e-5943-9327-29e5e8411548 | note | Controlling Documents - Chipsealing in NewZealand
c9b54a69-3018-5138-be32-1012b1d19145 | note | Acceptance Criteria - As per Chipping Guide
348cecae-942e-5259-87be-373e0f62cd9c | note | Method - Visual
11b8dfd6-2066-5b0c-89d5-3f6941737b89 | note | Frequency - Each Site
29eb76d7-c97e-5ac4-ad65-ead4a5e24bc7 | note | Responsible Person - Surfacing Supervisor
d69e2065-2e79-5bd8-ae44-a3ceff948043 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
490f6de2-4fd4-5675-8ec0-54525948c2f5 | note | Conduct - C
287e9c6d-e46c-5dd5-ae9e-fea86c9ffcdb | note | Produce Record - C
ca5571b4-47b9-5b54-a388-cc520169a673 | note | Approval - C
852da67c-0774-5df1-a532-532b327ffdad | note | Witness Point Y/N - Y
4d258c20-da33-5e7d-a61e-1cd91a622326 | checkpoint | Rolling
446e6fb9-3dcc-5330-acc5-622701083861 | note | Controlling Documents - Chipsealing in NewZealand
b003c0db-bb88-54b5-92a8-fdf209a476d1 | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
2d25107c-9e07-55ff-a7b7-bd46c98b8094 | note | Method - Visual
f2828543-3649-54d9-b9a2-04edc1674498 | note | Frequency - Each Site
8a292f63-ee5a-5490-90b9-ed4d32dc8840 | note | Responsible Person - Surfacing Supervisor
be1ee723-b7bc-58e5-b829-fdde42c88c83 | note | Verifying Document - Chip Sealing Quality and Site Record
84125f97-b08c-5db5-b23c-de27512d7336 | note | Conduct - C
54bd0105-832c-5472-a9cb-fd0ec0c482d6 | note | Produce Record - C
b35c0851-f350-5d46-ae8b-d6cad18cd56f | note | Approval - C
70217257-2846-5809-a11b-5500837d2497 | note | Witness Point Y/N - Y
a7254d71-44f8-555c-8c31-ededc73623ff | checkpoint | Cleanup
86f2d3ee-fc93-5a17-97d9-2c6570b08f33 | note | Controlling Documents - Chipsealing in NewZealand
f512e867-1cfb-5149-b3c0-4fee3537f960 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
1a2da4b6-bd43-561d-830a-23de462be69d | note | Method - Visual
a74122d1-3cd0-560a-8b9f-f76c10a1e594 | note | Frequency - Each Site
08ed9c04-1aca-5f8c-b42b-47435ecda2f2 | note | Responsible Person - Surfacing Supervisor
ffe2a38d-f4c8-53c9-b2fd-e70ac718cbbd | note | Verifying Document - Chip Sealing Quality and Site Record
5421099d-3898-5980-aab8-6e8e45d494af | note | Conduct - C
f81dc0e6-e17c-551a-86a0-a659bfe498f2 | note | Produce Record - C
6b0b49a1-01bc-5f07-9dc7-1d22edd1379b | note | Approval - C
36f805ae-5b25-5f54-adad-762ce44f92b8 | note | Witness Point Y/N - Y
15f0d51f-06be-5dbb-80dc-d2b8dea19da3 | checkpoint | Post Sweeping
1f1a9f02-94b2-5bfa-a5d7-84fa0db6093b | note | Controlling Documents - Chipsealing in NewZealand
a3510dac-4259-5de7-bb37-913c23062c23 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
d3ab391f-57e0-5f60-aacf-50fd0579f7e5 | note | Method - Visual
47747197-4d26-5f59-a5fb-74f696b4f43f | note | Frequency - Each Site
5cc8b2a7-8b3a-538f-8e27-e7b584f3f51b | note | Responsible Person - Surfacing Supervisor
a6d7feec-80f5-54f6-82f7-b041c5a88f4d | note | Verifying Document - Site Record
ff16e333-2c2c-567c-b9a8-302738dee534 | note | Conduct - C
62763e32-0afc-56d3-97b8-1fdf1c46e0b3 | note | Produce Record - C
56593a26-ea8d-5363-9d01-1af02cc693a4 | note | Approval - C
7fadde44-33aa-5a49-8031-ab8f81a8ee93 | note | Witness Point Y/N - Y
61cc6ff1-7882-529a-bd70-ffec5ff5c86a | checkpoint | Linemarking and RRPM Reinstated
0b6a5210-05fd-5cad-8309-ba7732385b3d | note | Controlling Documents - MOTSAM
c8962305-ef8d-54c6-9bf9-7197b325e3b6 | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
c1c3232c-9368-5f2e-8e90-76419a13b3ef | note | Method - Visual
2be968fb-97ea-5b0d-8284-aaa1f63ec094 | note | Frequency - Each Site
59c23fa7-6a74-5bf9-b1f9-72f63c1d4f5b | note | Responsible Person - Surfacing Supervisor
629b86d0-41d2-5e06-88f0-75b404724809 | note | Verifying Document - Site Record
f52dfd0d-c3cf-513e-9aeb-78b283b75b28 | note | Conduct - C
fdc83e1c-65f7-588f-98b2-bd482ef2ba59 | note | Produce Record - C
a475342d-e024-5a03-8f17-d38850e97fcb | note | Approval - C
7073b69d-852c-5f6d-a856-6200d980c6e9 | note | Witness Point Y/N - Y
2fa24de8-fb07-5d57-947e-3eea20cf5b9a | section | 5. Chip Sealing - 5.3. Post Construction
dc202d08-60bf-5984-ad2a-9d04e4df9611 | checkpoint | Post Construction Walkover
5debb248-f10a-5ea9-9451-8c9668cf6009 | note | Acceptance Criteria - Formal Agreement
c3042c9e-17ca-587a-9eac-740ca8096809 | note | Method - Visual Inspection
0cc208e4-78f5-55cf-b5cb-39d62b42be63 | note | Frequency - Post seal sweep
a4f611b1-3b1c-507a-8cbb-23eab8aace1e | note | Responsible Person - Quality Controller, Supervisor and Engineer
c5cecbe5-f6d1-5c0a-bb85-759d0482276b | note | Verifying Document - Meeting Minutes
2815080c-7f1b-5e3e-b78f-47f72130eaca | note | Conduct - C
0eb0c0bc-6c99-5fa0-9c9c-bf426d0b4199 | note | Witness - C, S and E
5f6c4819-40b1-54aa-b113-7303025438b1 | note | Produce Record - C
53366934-1600-5174-ac34-35c371be1d60 | note | Approval - E
068d42d3-43f4-5a55-82f9-7ccfbd3cda38 | note | Hold Point Y/N - Y
f1d7dde2-7e81-5af6-8d82-b5d0d7167970 | signoff | HOLD POINT
bf9dec03-0c36-56ce-9fad-16f1ef493188 | checkpoint | Resurfacing Construction Completion report
40341f67-aae2-539f-977f-95dd7a2f39c7 | note | Controlling Documents - NOC; MS 6.1.3
561575bc-f084-57f6-874d-379002789308 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
ac591eb7-7188-5ade-82b2-fb6a58f793d1 | note | Method - Record
2e6087ce-7f83-5b34-a076-4f21fe19f7f7 | note | Frequency - Within 2 months of completing the annual resurfacing programme
8f990d2a-dd7a-54ab-8851-1b460dc65b53 | note | Responsible Person - Surfacing Manager
7185d2c9-7fd8-55e7-8638-1c8f55975b7d | note | Verifying Document - Construction Completion Report
b7163495-e5e1-59be-beac-a1a6523cdc7b | note | Conduct - C
b9a05604-98bb-5bc4-aa4f-1fa160a60872 | note | Produce Record - C
7849c22c-823c-59a5-8b2c-4c7a4b40f736 | note | Approval - C
bf0b9895-3874-5d08-a962-72ec8a91764f | note | Hold Point Y/N - Y
eb5e5f37-0a48-53b2-a9dd-87c334206fbf | signoff | HOLD POINT
772657ca-829a-5f5f-a3c8-38687cdab16d | section | 6. Close Out
c9aac42b-68e9-539c-a9b9-5b3306d615a4 | checkpoint | Pavement Rehabilitation Construction Completion Report
75e26f2c-aa50-5e48-8a31-e24affbf2e35 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
dfd2669b-0eb0-538d-8897-8b8a258a0f09 | note | Acceptance Criteria - Engineer Approval
5cd07deb-2529-50cf-9f6d-88d3eb434a6b | note | Method - Visual Inspection
54b9eb15-1bba-5dda-bc5a-dd3109c78ddf | note | Frequency - ≤2 months of 1st Coat Seal
cc65607f-a2cb-58ba-bd60-745cf97ed90e | note | Responsible Person - Quality Controller/ Contract Manager
b8bdd3d0-6905-581c-a960-c1c4dc25c61e | note | Verifying Document - Signed Report
037f3f02-fb44-5524-bc33-7d705aea5c89 | note | Conduct - C
5266263c-af52-53d5-8e18-8cc3f781a897 | note | Witness - C, S and E
ede57a9f-7fd6-54e8-84b8-c73b9bdd6bd8 | note | Produce Record - C
28fce2b0-dd87-580e-94cd-d94d36948e57 | note | Approval - E
aaca7b9c-6468-5b94-92d0-f9ac31da26a4 | note | Hold Point Y/N - Y
9423d158-01da-51d7-85dd-76a94cfbc0ae | signoff | HOLD POINT
ab3528a4-fb20-5552-bd10-c2f98b62b8d5 | checklist | Verified Program |  | Verified Program
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
021a233a-3e30-5c50-9650-7a3d71241f43 | checkpoint | Verified Program