## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Pavement Rehab - SH 36 - Defence Area | itp |  |  |  |  | ITP - Pavement Rehab - SH 36 - Defence Area
section | 1. Procurement - Design
checkpoint | Geometric Design
label | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
label | Acceptance Criteria - Principal Approval
label | Method - Contractor and Principal peer review
label | Frequency - per design revision
label | Conduct - C or S
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Pavement Treatment Design
label | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
label | Acceptance Criteria - Principal Approval
label | Method - Contractor and Principal peer review
label | Frequency - per design
label | Verifying Document - Pavement Rehabilitation Design Report
label | Conduct - C or S
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
section | 1. Procurement - Materials: M/4 AP40 Basecourse Material
checkpoint | Aggregate Sampling
label | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
label | Verifying Document - Sampling Worksheet
checkpoint | Source Property Test (1)
label | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
label | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
label | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
label | Frequency - One test for every 10,000m³ of source material
label | Responsible Person - Quality Controller
label | Verifying Document - Test Report
label | Conduct - Sp or C or S
label | Produce Record - Sp or S
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Source Property Test (2)
label | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
label | Acceptance Criteria - AA, AB, AC, BA, BB or CA
label | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
label | Frequency - One test for every 10,000m³ of source material
label | Responsible Person - Quality Controller
label | Verifying Document - Test Report
label | Conduct - Sp or C or S
label | Produce Record - Sp or S
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Source Property Test (3)
label | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
label | Acceptance Criteria - Soaked CBR ≥ 80%
label | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
label | Frequency - One test for every 10,000m³ of source material
label | Responsible Person - Quality Controller
label | Verifying Document - Test Report
label | Conduct - Sp or C or S
label | Produce Record - Sp or S
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Production Property Test (1)
label | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
label | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
label | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
label | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
label | Responsible Person - Quality Controller
label | Verifying Document - Test Report
label | Conduct - Sp or C or S
label | Produce Record - Sp or S
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Production Property Test (2)
label | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
label | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
label | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
label | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
label | Responsible Person - Quality Controller
label | Verifying Document - Test Report
label | Conduct - Sp or C or S
label | Produce Record - Sp or S
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Production Property Test (3)
label | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
label | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
label | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
label | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
label | Responsible Person - Quality Controller
label | Verifying Document - Test Report
label | Conduct - Sp or C or S
label | Produce Record - Sp or S
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
section | 1. Procurement - Materials: Geotextile
checkpoint | Geotextile (Strength Class C) A29 or greater
label | Controlling Documents - TNZ F7 Specification
label | Acceptance Criteria - Details on Docket
label | Method - Visual inspection
label | Frequency - Per Delivery
label | Responsible Person - Quality Controller
label | Verifying Document - MDS
label | Conduct - Sp or S
label | Produce Record - Sp or S
label | Approval - C
label | Witness Point Y/N - Y
section | 2. Pre-Implementation
checkpoint | Geotextile (Strength Class C) A29 or greater
label | Controlling Documents - TNZ B/2 section 7.5
label | Acceptance Criteria - To obtain OMC & MDD
label | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
label | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
label | Responsible Person - Quality Controller
label | Verifying Document - Test report
label | Conduct - S or C
label | Witness - C
label | Produce Record - S or C
label | Witness Point Y/N - Y
checkpoint | Production Testing of subbase material - Solid Density
label | Controlling Documents - TNZ B/2 section 7.5
label | Acceptance Criteria - For info. and use in MDD calculation
label | Method - NZS 4407; test 3.7.1
label | Frequency - Once on commencement and if any materials change
label | Responsible Person - Quality Controller
label | Verifying Document - Test report
label | Conduct - S or C
label | Witness - C
label | Produce Record - S or C
label | Witness Point Y/N - Y
checkpoint | Project survey setting out
label | Controlling Documents - Reference from Project Drawings
label | Method - Survey/Mobile Roads, Marks with Dazzle
label | Frequency - Chainages for every different pavement sections
label | Responsible Person - Subcontractor/ Engineer
label | Verifying Document - Construction drawings
label | Conduct - S or C
label | Witness - C
label | Produce Record - S or C
label | Witness Point Y/N - Y
section | 3. Construction - Pre-treatment Digouts
checkpoint | Digout of Patches to repair
label | Controlling Documents - Pavement Design report
label | Acceptance Criteria - 200mm deep as specified
label | Method - Visual inspection
label | Frequency - As required
label | Responsible Person - Quality Controller
label | Verifying Document - Dig out site records/ Asbuilt
label | Conduct - S
label | Witness - C
label | Produce Record - S
label | Approval - C
checkpoint | Subgrade material hardness Check base of excavation
label | Controlling Documents - Higgins SOP 0128 - Digout Repair
label | Acceptance Criteria - Scala > 3 blows per 100mm
label | Method - Scala Penetrometer test on base of digout
label | Frequency - As required depending on size of digout
label | Responsible Person - Quality Controller
label | Verifying Document - Test report
label | Conduct - S/C
label | Witness - C
label | Produce Record - S/C
label | Approval - E
checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
label | Controlling Documents - TNZ F7 Specification
label | Acceptance Criteria - Meet TNZ F7 Spec.
label | Method - Visual inspection
label | Frequency - Per Delivery
label | Responsible Person - Quality Controller
label | Verifying Document - Certificate of conformance
label | Conduct - Sp or S
label | Produce Record - C
label | Approval - C
checkpoint | Place and compact TNZ M4 AP 40 in digout area
label | Controlling Documents - Pavement Design report
label | Acceptance Criteria - Clegg value > 45
label | Method - Clegg Test
label | Frequency - Min. 2 per digout
label | Responsible Person - Quality Controller
label | Verifying Document - Test report
label | Conduct - S/C
label | Witness - C
label | Produce Record - S/C
label | Approval - E
section | 4. Construction - Granular make up and In-situ Modification
checkpoint | Place M/4 AP40 Basecourse Material
label | Controlling Documents - TNZ B/2 (section 7.2)
label | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
label | Method - Visual Inspection
label | Frequency - On completion of placement
label | Responsible Person - Quality Controller
label | Verifying Document - Photographs and Daily Site Record
label | Conduct - S or C
label | Produce Record - S or C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Addition of Water
label | Controlling Documents - TNZ B/2 (section 7.5)
label | Acceptance Criteria - 90-100% OWC
label | Method - Nuclear Densometer Testing prior to Stabilisation
label | Frequency - ≥1 per 1000m² lot
label | Responsible Person - Quality Controller
label | Verifying Document - NDM Record
label | Conduct - S or C
label | Produce Record - S or C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
label | Controlling Documents - TNZ B/2 (section 7.5)
label | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
label | Method - Plateau Density Testing
label | Frequency - 1 time, or additional tests when material changes visually
label | Responsible Person - Supervisor
label | Verifying Document - Test record
label | Conduct - S or C
label | Produce Record - S or C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Establish Compaction Target
label | Controlling Documents - TNZ B/2 (section 7.5)
label | Acceptance Criteria - To provide MDD for NDM testing
label | Method - Plateau Density Testing
label | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
label | Responsible Person - Quality Controller
label | Verifying Document - Test Record
label | Conduct - S or C
label | Produce Record - S or C
label | Approval - E
label | Witness Point Y/N - Y
checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (1)
label | Controlling Documents - TNZ B/2 (section 7.6)
label | Acceptance Criteria - To provide MDD for NDM testing
label | Method - Laboratory MDD at OMC NZS 4402 test 4.1.3.
label | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
label | Responsible Person - Quality Controller
label | Verifying Document - Test Record
label | Conduct - S or C
label | Produce Record - S or C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (2)
label | Controlling Documents - TNZ B/2 (section 7.6)
label | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
label | Method - Plateau Density Testing Lab. MDD
label | Frequency - At commencement of construction and whenever materials change
label | Responsible Person - Quality Controller Engineer
label | Verifying Document - Notice to Contractor/ Notice to Engineer
label | Conduct - S or C
label | Produce Record - S or C
label | Approval - E
label | Witness Point Y/N - Y
checkpoint | Compaction Acceptance
label | Controlling Documents - Compaction (7.6) - TNZ B/2
label | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
label | Method - Nuclear Densometer Testing
label | Frequency - ≥ 5 tests per 1000m² lot
label | Responsible Person - Quality Controller
label | Verifying Document - NDM Record
label | Conduct - S or C
label | Produce Record - S or C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Surface Shape
label | Controlling Documents - Compaction (5.1) - TNZ B/2
label | Acceptance Criteria - -5 mm +15 mm
label | Method - String line/Survey
label | Frequency - during construction and prior to seal
label | Responsible Person - Supervisor
label | Verifying Document - String Sheet/Survey Asbuilts
label | Conduct - S or C
label | Witness - C and E
label | Produce Record - S or C
label | Approval - E
label | Witness Point Y/N - Y
checkpoint | Cross Fall
label | Controlling Documents - Compaction (5.1) - TNZ B/2
label | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
label | Method - 3m straight edge or Survey Asbuilt
label | Frequency - during construction and prior to seal
label | Responsible Person - Supervisor
label | Verifying Document - Cross Fall Records/Survey Asbuilts
label | Conduct - S or C
label | Witness - C and E
label | Produce Record - S or C
label | Approval - E
label | Witness Point Y/N - Y
checkpoint | Surface Finish
label | Controlling Documents - Compaction (7.8) - TNZ B/2
label | Acceptance Criteria - Tightly bound matrix post sweep
label | Method - Visual inpsection
label | Frequency - prior to seal
label | Responsible Person - Supervisor
label | Verifying Document - Pre-seal inspection sheet
label | Conduct - S or C
label | Witness - C and E
label | Produce Record - S or C
label | Approval - E
label | Witness Point Y/N - Y
checkpoint | Degree of Saturation, DOS
label | Controlling Documents - Pre-sealing requirements (12) - TNZ B/2 Notes: 2005
label | Acceptance Criteria - ≤80%, however 65% is ideal
label | Method - Nuclear Densometer Testing
label | Frequency - ≥5 tests per 1000m² lot
label | Responsible Person - Quality Controller
label | Verifying Document - NDM Record
label | Conduct - S or C
label | Witness - C and E
label | Produce Record - S or C
label | Approval - E
label | Witness Point Y/N - Y
checkpoint | Roughness (NAASRA)
label | Controlling Documents - Compaction (7.7) - TNZ B/2 'NZTA Maintainence specification section 6.1.2
label | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
label | Method - NZTA Maintainence specification section 6.1.2
label | Frequency - Average of three replica runs for each lane reported at 20m intervals.
label | Responsible Person - Quality Controller
label | Verifying Document - Test Records
label | Conduct - S or C
label | Witness - C and E
label | Produce Record - S or C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
section | 5. Chip Sealing - 5.1. Procurement
checkpoint | Binder - Penetration Grade
label | Controlling Documents - TNZ M/1
label | Acceptance Criteria - Table 1
label | Method - Property Test
label | Frequency - Annual
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Binder - Polymer Modified Emulsion (1)
label | Controlling Documents - Higgins Internal Specification
label | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
label | Method - Property Test
label | Frequency - 1/100,000 litres supplied
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Binder - Polymer Modified Emulsion (2)
label | Controlling Documents - TNZ M6, RNZ 9805:2009
label | Acceptance Criteria - <10% fines under 230kN minimum
label | Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
label | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
label | Controlling Documents - TNZ M6, RNZ 9805:2009
label | Acceptance Criteria - AA or BA
label | Method - Weathering Quality Index NZS 4407 Test 3.10
label | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Source Property - Skid Resistance
label | Controlling Documents - NZTA T/10
label | Acceptance Criteria - Meet Skid performance Requirement
label | Method - Aggregate Perfomance Method TNZ T/10 section 12.3
label | Frequency - Each Site
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Production Property - Cleaness Value
label | Controlling Documents - NZTA P/17, M/6
label | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
label | Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
label | Frequency - Per Stockpile
label | ○ <100m3 - 1 Sample
label | ○ 100-500m3 - 2 Samples
label | ○ >500m3 - 3 Samples
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Production Property - Particle Size/Shape
label | Controlling Documents - NZTA P/17, M/6
label | Acceptance Criteria - As per Table 3 NZTA M/6
label | Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
label | Frequency - Per Stockpile
label | ○ <100m3 - 1 Sample
label | ○ 100-500m3 - 2 Samples
label | ○ >500m3 - 3 Samples
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Production Property - Broken Faces
label | Controlling Documents - NZTA P/17, M/6
label | Acceptance Criteria - Min. 98%
label | Method - Sample Test - Broken Faces NZS 4407 Test 3.14
label | Frequency - Per Stockpile
label | ○ <100m3 - 1 Sample
label | ○ 100-500m3 - 2 Samples
label | ○ >500m3 - 3 Samples
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Chipseal Designs
label | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
label | Acceptance Criteria - Client Approval
label | Method - Review
label | Frequency - Annual
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - EBOP NOC Design Report Acceptance
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
section | 5. Chip Sealing - 5.2. Construction
checkpoint | Ensure limits of site are marked
label | Controlling Documents - EBOP NOC Design Report
label | Acceptance Criteria - Visual Inspection
label | Method - Visual
label | Frequency - Prior to start sealing each site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Sweep surface clean of deleterious material
label | Controlling Documents - P/17
label | Acceptance Criteria - Visual Inspection
label | Method - Visual
label | Frequency - Each site, prior to start of sealing
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Record ATP's on site
label | Controlling Documents - N/A
label | Acceptance Criteria - Visual Inspection
label | Method - Visual
label | Frequency - Each site, prior to start of sealing
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Confirm correct treatment(s) and chip
label | Controlling Documents - EBOP NOC Design Report
label | Acceptance Criteria - Details/chip correct
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Cutback Bitumen Blend
label | Controlling Documents - RNZ 9803_0513
label | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
label | Method - Sample and test
label | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
label | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Bitumen Application Rate
label | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
label | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
label | Method - Test, Review
label | Frequency - Per Sprayer, Per Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - E/2 Certificate. Spray Sheets
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Chip Application Rates
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - As per Chipping Guide
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Rolling
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Cleanup
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Site including adjacent surfaces free of loose chip
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Post Sweeping
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Site including adjacent surfaces free of loose chip
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
checkpoint | Linemarking and RRPM Reinstated
label | Controlling Documents - MOTSAM
label | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point Y/N - Y
section | 5. Chip Sealing - 5.3. Post Construction
checkpoint | Post Construction Walkover
label | Acceptance Criteria - Formal Agreement
label | Method - Visual Inspection
label | Frequency - Post seal sweep
label | Responsible Person - Quality Controller, Supervisor and Engineer
label | Verifying Document - Meeting Minutes
label | Conduct - C
label | Witness - C, S and E
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
checkpoint | Resurfacing Construction Completion report
label | Controlling Documents - NOC; MS 6.1.3
label | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
label | Method - Record
label | Frequency - Within 2 months of completing the annual resurfacing programme
label | Responsible Person - Surfacing Manager
label | Verifying Document - Construction Completion Report
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Hold Point Y/N - Y
holdpoint | HOLD POINT
section | 6. Close Out
checkpoint | Pavement Rehabilitation Construction Completion Report
label | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
label | Acceptance Criteria - Engineer Approval
label | Method - Visual Inspection
label | Frequency - ≤2 months of 1st Coat Seal
label | Responsible Person - Quality Controller/ Contract Manager
label | Verifying Document - Signed Report
label | Conduct - C
label | Witness - C, S and E
label | Produce Record - C
label | Approval - E
label | Hold Point Y/N - Y
holdpoint | HOLD POINT