## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e4245192-4076-48e8-bd5c-3ae8dead3324 | checklist | Add Documents & Photos |  | Add Documents & Photos
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0e56f51a-898f-4c46-83e4-15f33021466a | checkpoint | Please upload the relevant document(s) / photos and press PASS.
6f6ab7fe-f932-4a33-b56d-5d6048ee33ac | checklist | ITP - Wastewater drainage | itp | ITP - Wastewater drainage
7fdb6cf7-d085-488f-9e35-49a53a82f141 | section | WW1.0 - Set Out
00ec3a94-6c06-488f-a763-aeffb1ce447c | checkpoint | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
e0205a98-3cee-5a23-a974-3c2c74e4b155 | note | Spec Reference/Special Conditions - NZS 3107
bd91c262-919e-5778-b02f-649f277fdaba | note | Acceptance Criteria - CI
bae44149-273b-5d37-bb11-2a97ecc0efbb | textbox | Verifying Document - Drawing Register
82528da5-d43f-4fde-8690-1e8f99e7b71b | checkpoint | 1.2 - Confirm existing and proposed drainage locations
17c320ef-d40b-5db5-b48f-96849fb4d4bb | note | Acceptance Criteria - CI
690a1aaa-1cf4-50dc-8d35-ec6c62d8e7f1 | textbox | Verifying Document - Survey Layout; Drawing:
ffef9033-6396-4d19-a4a4-98e1bbcdc166 | section | WW2.0 - Wastewater
1e22bd41-d3fe-4993-a5a7-8fbd25afeb3d | checkpoint | 2.1 - Complete council Kick-off meeting
55f84e12-dde0-5735-b68a-1858bbd44308 | note | Acceptance Criteria - HP
17c1156c-0d54-5dca-9a24-fd46f5d3bb7b | note | Verifying Document - Council inspection report
9e96e271-5f1e-4dd6-aff1-47420b84d875 | signoff | HOLD POINT
2902be5a-db8e-48f7-b18e-0fd769e335ae | checkpoint | 2.2 - All wastewater pipes and manholes shall be placed in accordance with surveyor's layout and locations given in design drawings.
d6b9a640-b20e-5f03-8ca2-3dbe889c86f5 | note | Spec Reference/Special Conditions - NZA/AS 1260
52e39f6c-062e-53ac-a22d-95e375eee9cb | note | Acceptance Criteria - CI
0e0a79eb-7bd9-506a-a541-4a88d5aa101e | note | Verifying Document - M&P drainage long section sheet, M&P manhole sheet
92078f9b-cf67-499c-ac75-d0a88faef146 | checkpoint | 2.3 - Wastewater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth. Use trench shield if battered cannot be achieve.
335e98cd-911c-53f3-bbea-e1c7e599ddcc | note | Spec Reference/Special Conditions - Drawing C-C401 and C-C402
04694494-793a-5bb0-b018-2c04f79a3573 | note | Acceptance Criteria - HP
c244c5fd-9afa-554f-b65b-518a5a9f9c59 | note | Verifying Document - M&P drainage long section sheet, M&P manhole sheet
58b5c947-a4ff-434c-8ffc-6b928b9a3bad | signoff | HOLD POINT
550d3ab0-43c7-4ce0-af3c-7da182e39dc4 | checkpoint | 2.4 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
5d2c2567-bcfa-5aa6-9e15-d5184a843bbe | note | Acceptance Criteria - HP
14a0c66d-5f6a-5741-9206-c7779e71d252 | note | Verifying Document - Geotech signoff
08cbf244-bddc-46dc-8845-b6885f5b48c4 | signoff | HOLD - Continue only if the above is signed off.
972d1bae-ac4d-42a8-858a-9bf589c20e23 | checkpoint | 2.5 - Breakout to commence only once Client have issued a site instruction
2c2e1457-1361-5d45-b4f4-1ebe77b2611d | note | Acceptance Criteria - WP
e5a51349-8fb4-5123-8aa9-0a4067a9f908 | note | Verifying Document - H&R Site Instruction
67e85e5a-4cc1-49d9-931f-876c21c69fbb | signoff | HOLD - Continue only if the above is signed off.
dcc28b2c-5344-455b-8e63-3188fe5f2f93 | section | WW3.0 - Wastewater Installation
6c966cf1-9da8-44b1-bb2d-f7400f319240 | checkpoint | 3.1 - All manholes shall be installed with accordance to locations shown on civil drawings. Any variations to be approved by Client prior to installation.
ea3ba29a-e899-51c8-bff8-e51fd8370984 | note | Spec Reference/Special Conditions - Drawing C-C401 and C-C402
b125f193-18bc-58d0-8158-b0cfa47f1092 | note | Acceptance Criteria - CI
113849df-499b-5803-88c8-bb07c388f19f | note | Verifying Document - Survey Layout
2167f884-5bd9-4a4a-abad-bd32650565bc | checkpoint | 3.2 - Wastewater mains and downpipes to be laid out in accordance with design drawings. Any Variations to be approved by Client before installation.
3c4b98ac-ecf7-534d-bdba-2f815a2ba898 | note | Spec Reference/Special Conditions - Drawing C-C401 and C-C402
8b4913e9-868f-52f9-b4f5-2d73b29d4a82 | note | Acceptance Criteria - HP
3fb50803-b4c7-549f-8fe6-6205e0b436fd | note | Verifying Document - Survey Layout
5a3fed96-251e-457b-b1de-50b530e1a1d8 | signoff | HOLD POINT
be5afc43-9157-4e63-bce2-b79bb199f448 | checkpoint | 3.3 - Pipes shall be laid true to alignment and with inverts true to grade. All manhole connections shall be in accordance with civil engineering specifications and Auckland Council standard drawings.
97b744b6-5460-5bad-9f73-42105229f542 | note | Spec Reference/Special Conditions - WWCoP DWG No.
e2c3ee82-016d-5659-a618-51b6eb07a7fb | note | Acceptance Criteria - CI
b8ff0d3a-cead-55d0-a470-76e64c7fded6 | textbox | Verifying Document - M&P Long Section Sheet, M&P Manhole Check Sheets: Drawing:
42ef16af-5fa4-4900-ae56-0e1e988f269e | signoff | HOLD - Continue only if the above is signed off.
e31c3e90-4be2-4ea5-b69f-b1ba1c06ec11 | checkpoint | 3.4 - M&P Drainage long section and Manhole sheets to be completed.
6fd851aa-f918-5ec5-bf81-471f667b1b0a | note | Acceptance Criteria - CI
916a74b5-06f3-507c-bbcb-c234be0bd6e6 | note | Verifying Document - M&P drainage long section sheet, M&P manhole sheet
2b804cf7-79e6-48ed-aeed-91148c9d5b12 | checkpoint | 3.5 - Pipes shall be bedded on 100mm minimum depth of approved fine granular material.
3907319c-8a7e-5dab-99f9-fd3af6a4abf2 | note | Spec Reference/Special Conditions - NZS 2566 Part 2: 2002
7c52c465-cf4a-5d93-8a99-3ebda285fe4f | note | Acceptance Criteria - CI
89541f53-ca98-5296-b645-dc68cc567aae | note | Verifying Document - M&P Long Section Sheet, M&P Manhole Check Sheets
8c48f6ee-06b6-4c99-a9da-2d42f09a860e | checkpoint | 3.6 - Lower surface to 1/4 of the pipe diameter shall be on the compacted material. From this point up to 300mm above the crown of the pipe, selected filling material (with 20mm maximum partial size) shall be rammed & tamped in layers of no more than 150mm depth.
3c4855a5-ef28-5cfe-a85b-a77a6bdef567 | note | Spec Reference/Special Conditions - NZS 2566 Part 2: 2002
71768b87-cb0c-5754-a95c-c37d5c1bccd2 | note | Acceptance Criteria - CI
1b8789ab-a32e-4663-a0b2-4db20a5763b2 | checkpoint | 3.7 - All pipework to be inspected by clients engineer and Council inspector and signed off before trench can be backfilled
5821bfd7-bef0-5632-828b-910b530747ef | note | Acceptance Criteria - HP
b927b727-4218-5f75-8cdf-abbd5bac02c6 | note | Verifying Document - Council & Engineer inspection and/or Approval report
ac73bb5f-2739-4568-9701-bea4a3abefce | signoff | HOLD - Continue only if the above is signed off.
31bab9c4-db5f-4ab3-864b-3fc7f9881c59 | checkpoint | 3.8 - Any pipe with less than 600mm cover must be noted to the client and wait approval to proceed
742f763b-cdd8-5ad1-a83a-4ae6aab8a65e | note | Acceptance Criteria - CI
cf22d9a6-0767-5e5a-a227-41de8bee387b | note | Verifying Document - Site Instruction
ac861d48-3f68-4026-a86e-79ebee391624 | checkpoint | 3.9 - Trench to be backfilled with approved granular material and compacted sufficiently
21811ab9-9ab9-558e-8e23-d75423d0e34d | note | Spec Reference/Special Conditions - NZS 2566 Part 2: 2002
46748ecd-2add-57ed-ae87-265e1f206a48 | note | Acceptance Criteria - CI
6b55547f-0ad2-49d5-9028-27d68328857e | checkpoint | 3.1 - Backfill materials must be compacted correctly and tested in 150mm - 300mm lifts
88d9f4a5-d6f8-528d-980c-236674d58eda | note | Acceptance Criteria - CI
c6f9e33e-66b2-5cc3-9180-d90facf86c30 | note | Verifying Document - Council & Engineer inspection and/or Approval report
ed1b2d7b-eb78-43db-bf4b-8f649ae1282f | section | WW4.0 - Handover to client with PS3
2ebf0dec-4af1-4b11-a8ed-ecabae12bbb9 | checkpoint | 4.1 - Complete Council final drainage inspection
202bb4d0-1fad-516b-a958-977e8d55e5bc | note | Acceptance Criteria - HP
13e695d9-3d3a-5886-bde8-d22193e8f92b | note | Verifying Document - Council inspection report
5bc92650-eb78-4a76-bb4e-478bbe54dd58 | signoff | HOLD POINT
f658ee19-99e4-435f-8d2a-29301ea0dd68 | checkpoint | 4.2 - Completed pipe sections to be CCTV'd
b96e340b-2e13-5461-b31d-ac12d2ddee33 | note | Acceptance Criteria - CI
b79ca3fc-2f54-5815-bbbd-26560ba563da | note | Verifying Document - CCTV Footage
205fabce-4840-4284-a2a4-ce98cc41e7fd | checkpoint | 4.3 - As build all pipe invert levels in manholes and CP and lid levels
a2206825-d801-5f32-9ac0-fdcf20f69982 | note | Acceptance Criteria - HP
63949894-71e6-534c-be89-2ae13427ae9d | note | Verifying Document - As build report
c844a3c8-94d7-4155-8cc9-655029683646 | signoff | HOLD POINT
7dd47829-6c18-4b20-bc02-6024be00b0a6 | checkpoint | 4.4 - Handover to client with CS3
bab6db8f-e055-5420-8234-d1eda80383df | note | Spec Reference/Special Conditions - CS3 Drainage
94bb960d-97f3-5bf8-84ee-75f701072aca | note | Acceptance Criteria - HP
b0c45578-59bc-5636-9986-fcd33530fe20 | note | Verifying Document - Hander documents
222597fb-e48d-4014-858b-d4e7756f091e | signoff | HOLD POINT
8c5f21b1-acee-4335-ad85-9eadae262a61 | checkpoint | Comments / Required Actions:
a9d1d08d-b7d9-5642-bc28-f713a75647b9 | textbox | Rev. Status
c0b5850f-2841-563e-a421-e4c609d88d50 | date | Date
da5240d6-de53-5be4-8c4b-b66d0fb42b4c | textbox | Reason for Rev.
1702f23b-0cae-4139-8ba9-683596edeaca | checkpoint | Signed by:
3c472167-7178-5d70-ad86-7d0c7895ea06 | note | Contractors Representative
f91f0e15-1442-5a21-93e3-08168f48d88a | textbox | Print:
4fa17c0d-0530-5248-bba9-14310750617e | date | Date:
b2031b7e-bbfc-5f26-b828-ed0dcdfe1719 | note | Clients Representative
d604cc5a-9586-5bbf-95d3-14b90885246d | textbox | Print:
fb4337da-269c-586a-bd42-834044b64bd6 | date | Date:
85958616-3f00-42a6-8174-a2037a6afe70 | signoff | Signatures: