## Sheet1
1.1 | Ensure that the latest revision of the relevant drawing is being used. |  | CI | Current Plan and Longsection revisions being used to install | 1.1 - Ensure that the latest revision of the relevant drawing is being used. | Spec Reference/Special Conditions - | Acceptance Criteria - CI | Verifying Document - Current Plan and Longsection revisions being used to install | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
1.2 | Confirm Datum for Survey Setout |  | CI | Correspondence of Datum to use | 1.2 - Confirm Datum for Survey Setout | Spec Reference/Special Conditions - | Acceptance Criteria - CI | Verifying Document - Correspondence of Datum to use | Spec Reference/Special Conditions -
1.3 | Confirm existing and proposed drainage locations |  | CI | Asbuilt of Existing Manholes | 1.3 - Confirm existing and proposed drainage locations | Spec Reference/Special Conditions - | Acceptance Criteria - CI | Verifying Document - Asbuilt of Existing Manholes | Acceptance Criteria - CI
1.4 | All wastewater pipes and manholes shall be placed in accordance with Engineer's model and locations given in design drawings. | Prelet | CI | Drainage Models provided by Engineer | 1.4 - All wastewater pipes and manholes shall be placed in accordance with Engineer's model and locations given in design drawings. | Spec Reference/Special Conditions - Prelet | Acceptance Criteria - CI | Verifying Document - Drainage Models provided by Engineer | Verifying Document - Current Plan and Longsection revisions being used to install
1.5 | Complete council Kick-off meeting | Building Consent | HP | Council inspection report | 1.5 - Complete council Kick-off meeting | Spec Reference/Special Conditions - Building Consent | Acceptance Criteria - HP | Verifying Document - Council inspection report | 1.2 - Confirm Datum for Survey Setout
2.1 | Wastewater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth. Use trench shield if battered cannot be achieve. | NZS 4404:2010 AS/NZS 2566.2 WorkSafe NZ – Good Practice Guidelines: Excavation Safety | CI | Photos | 2.1 - Wastewater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth. Use trench shield if battered cannot be achieve. | Spec Reference/Special Conditions - NZS 4404:2010 AS/NZS 2566.2 WorkSafe NZ – Good Practice Guidelines: Excavation Safety | Acceptance Criteria - CI | Verifying Document - Photos | Spec Reference/Special Conditions -
2.2 | IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout. |  | HP | Geotech signoff | 2.2 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout. | Spec Reference/Special Conditions - | Acceptance Criteria - HP | Verifying Document - Geotech signoff | Acceptance Criteria - CI
2.3 | Breakout to commence only once Client have issued a site instruction |  | WP | HCHAR(AMP)R Site Instruction | 2.3 - Breakout to commence only once Client have issued a site instruction | Spec Reference/Special Conditions - | Acceptance Criteria - WP | Verifying Document - HCHAR(AMP)R Site Instruction | Verifying Document - Correspondence of Datum to use
3.1 | The position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design. | Watercare C3.1.1 | CI | MCHAR(AMP)P longsection sheet | 3.1 - The position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design. | Spec Reference/Special Conditions - Watercare C3.1.1 | Acceptance Criteria - CI | Verifying Document - MCHAR(AMP)P longsection sheet | 1.3 - Confirm existing and proposed drainage locations
3.2 | Ensure grade with digital spirit level matches design grade along pipe alignment | Auckland Council Requirement | CI | Photos along alignment | 3.2 - Ensure grade with digital spirit level matches design grade along pipe alignment | Spec Reference/Special Conditions - Auckland Council Requirement | Acceptance Criteria - CI | Verifying Document - Photos along alignment | Spec Reference/Special Conditions -
3.3 | Asbuilt of pipe invert levels prior to Auckland Council Inspection | Auckland Council Requirement | CI | Asbuilt Drawing | 3.3 - Asbuilt of pipe invert levels prior to Auckland Council Inspection | Spec Reference/Special Conditions - Auckland Council Requirement | Acceptance Criteria - CI | Verifying Document - Asbuilt Drawing | Acceptance Criteria - CI
3.4 | Allow Auckland Council opportunity to inspect pipeline prior to backfill | Auckland Council Requirement | CI | Council inspection report | 3.4 - Allow Auckland Council opportunity to inspect pipeline prior to backfill | Spec Reference/Special Conditions - Auckland Council Requirement | Acceptance Criteria - CI | Verifying Document - Council inspection report | Verifying Document - Asbuilt of Existing Manholes
3.7 | Backfill line in 200mm layers and conduct Clegg Hammer Impact Tests for Hardfill achieving CIV 25 | Watercare C2.21 row 12 | CI | Clegg Hammer Results Sheet | 3.7 - Backfill line in 200mm layers and conduct Clegg Hammer Impact Tests for Hardfill achieving CIV 25 | Spec Reference/Special Conditions - Watercare C2.21 row 12 | Acceptance Criteria - CI | Verifying Document - Clegg Hammer Results Sheet | 1.4 - All wastewater pipes and manholes shall be placed in accordance with Engineer's model and locations given in design drawings.
3.8 | Backfill line in 300mm layers and conduct Shearvanes for clay fill achieving average value not less than 150KPA | Engenium Excavation and Hardfil Spec. Item 2.4 | CI | Shear Vane Results Sheet | 3.8 - Backfill line in 300mm layers and conduct Shearvanes for clay fill achieving average value not less than 150KPA | Spec Reference/Special Conditions - Engenium Excavation and Hardfil Spec. Item 2.4 | Acceptance Criteria - CI | Verifying Document - Shear Vane Results Sheet | Spec Reference/Special Conditions - Prelet
3.9 | Pipework shall be CCTV inspected for defects, in particular pipe joints and to identify ponding areas for correction in gravity systems | SWCOP | CI | CCTV Footage and Reports | 3.9 - Pipework shall be CCTV inspected for defects, in particular pipe joints and to identify ponding areas for correction in gravity systems | Spec Reference/Special Conditions - SWCOP | Acceptance Criteria - CI | Verifying Document - CCTV Footage and Reports | Acceptance Criteria - CI
4.1 | Complete Council final drainage inspection |  | HP | Council inspection report | 4.1 - Complete Council final drainage inspection | Spec Reference/Special Conditions - | Acceptance Criteria - HP | Verifying Document - Council inspection report | Verifying Document - Drainage Models provided by Engineer
4.2 | Complete Engineer final drainage inspection |  | HP | Correspondence Engineer | 4.2 - Complete Engineer final drainage inspection | Spec Reference/Special Conditions - | Acceptance Criteria - HP | Verifying Document - Correspondence Engineer | 1.5 - Complete council Kick-off meeting
4.2 | As built all pipe invert levels in manholes and CP and lid levels |  | HP | As built report | 4.2 - As built all pipe invert levels in manholes and CP and lid levels | Spec Reference/Special Conditions - | Acceptance Criteria - HP | Verifying Document - As built report | Spec Reference/Special Conditions - Building Consent
4.4 | Handover to client with CS3 | CS3 Drainage | HP | Handover documents | 4.4 - Handover to client with CS3 | Spec Reference/Special Conditions - CS3 Drainage | Acceptance Criteria - HP | Verifying Document - Handover documents | Acceptance Criteria - HP
Verifying Document - Council inspection report
2.1 - Wastewater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth. Use trench shield if battered cannot be achieve.
Spec Reference/Special Conditions - NZS 4404:2010 AS/NZS 2566.2 WorkSafe NZ – Good Practice Guidelines: Excavation Safety
Acceptance Criteria - CI
Verifying Document - Photos
2.2 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
Spec Reference/Special Conditions -
Acceptance Criteria - HP
Verifying Document - Geotech signoff
2.3 - Breakout to commence only once Client have issued a site instruction
Spec Reference/Special Conditions -
Acceptance Criteria - WP
Verifying Document - HCHAR(AMP)R Site Instruction
3.1 - The position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
Spec Reference/Special Conditions - Watercare C3.1.1
Acceptance Criteria - CI
Verifying Document - MCHAR(AMP)P longsection sheet
3.2 - Ensure grade with digital spirit level matches design grade along pipe alignment
Spec Reference/Special Conditions - Auckland Council Requirement
Acceptance Criteria - CI
Verifying Document - Photos along alignment
3.3 - Asbuilt of pipe invert levels prior to Auckland Council Inspection
Spec Reference/Special Conditions - Auckland Council Requirement
Acceptance Criteria - CI
Verifying Document - Asbuilt Drawing
3.4 - Allow Auckland Council opportunity to inspect pipeline prior to backfill
Spec Reference/Special Conditions - Auckland Council Requirement
Acceptance Criteria - CI
Verifying Document - Council inspection report
3.7 - Backfill line in 200mm layers and conduct Clegg Hammer Impact Tests for Hardfill achieving CIV 25
Spec Reference/Special Conditions - Watercare C2.21 row 12
Acceptance Criteria - CI
Verifying Document - Clegg Hammer Results Sheet
3.8 - Backfill line in 300mm layers and conduct Shearvanes for clay fill achieving average value not less than 150KPA
Spec Reference/Special Conditions - Engenium Excavation and Hardfil Spec. Item 2.4
Acceptance Criteria - CI
Verifying Document - Shear Vane Results Sheet
3.9 - Pipework shall be CCTV inspected for defects, in particular pipe joints and to identify ponding areas for correction in gravity systems
Spec Reference/Special Conditions - SWCOP
Acceptance Criteria - CI
Verifying Document - CCTV Footage and Reports
4.1 - Complete Council final drainage inspection
Spec Reference/Special Conditions -
Acceptance Criteria - HP
Verifying Document - Council inspection report
4.2 - Complete Engineer final drainage inspection
Spec Reference/Special Conditions -
Acceptance Criteria - HP
Verifying Document - Correspondence Engineer
4.2 - As built all pipe invert levels in manholes and CP and lid levels
Spec Reference/Special Conditions -
Acceptance Criteria - HP
Verifying Document - As built report
4.4 - Handover to client with CS3
Spec Reference/Special Conditions - CS3 Drainage
Acceptance Criteria - HP
Verifying Document - Handover documents