## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-229-CIV-Ferris-Subsoil Drainage
ITP Description: |  | Ferris-Subsoil Drainage
Discipline (e.g. CIV/STR/RAIL: |  | 229-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-01-23
ITP created by: |  | Kamel ALSHOBAKI
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Ferris only
Inspection & Test Plan - Subsurface Drainage (Supply and Install)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-01-23
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 702 (May '19) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Material
2.1 | Pipes | IFC Drawiings VR 702.04 | All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | PE/Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.2 | Granular material: Filter Sand | IFC Drawings VR 702.05 | Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads. [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | PE/Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.3 | Granular Material: No Fines Concrete | IFC Drawings VR 702.05 (e ) | No Fines Concrete: Shall comply with 702.05 e) [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | PE/Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.4 | Geo textile | IFC Drawings VR 702.06 | Geotextiles: Shall comply with table 702.061 [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | PE/Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.5 | SSD Pits, Pit Lids, Flushout Risers | IFC Drawings Section 702.04, 702.05 & 702.06 | Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611 Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit Flushout risers: As per SD 1631 [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | PE/Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set Out | Section 702.03 | Survey to set out Subsurface Drainage line. | Visual inspection | Each Lot | HP* | SE/Site Supervisor | This ITP
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set Out | IFC Drawings Section 702.03 | Survey to set out Subsurface Drainage line. | Visual inspection | Each Lot | IP | SE/Site Supervisor Surveyor | This ITP Signed-off
5 | Construction / Installation Activities
5.1 | Trench Excavation | IFC Drawings Section 702.08 | The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe. There shall be no departures from the grade of the base of the trench that would allow ponding of water. Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed. Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile. | Visual Inspection | Each lot | IP | SE | This ITP
5.2 | Trench Excavation | Section 702.08 | The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection. | Visual Inspection | Each lot | HP | SE/Nominated Authority | Nominated Authorith sign off ThisLine
5.3 | Placement of bedding | Section 702.09 c) | Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
5.4 | Traficable Pavements | IFC Drawings SD 1601 EDCM 201 | Choose pass when applicable All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and MCC202B | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
5.5 | Outside trafficable pavement | IFC Drawings SD 1601 EDCM 201 | Choose pass when applicable pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
5.6 | Pipe and Geotextile Installation (if required) | Section 702.03, 702.09 | Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap) | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
5.7 | Backfill Installation (Granular Filter Material) | Section 702.09 (g) | Material shall be placed moist and compacted in layers not exceeding 300mm. The method of compaction shall be in accordance with the procedures and reviewed by the NA. | Visual, Doc. Review | Each lot | HP | SE, Nominated Authority | Nominated Authorith sign off This Line
5.8 | Backfill Installation (No Fines) | Section 702.09 (g) | All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing ATTACH: No Fines Delivery Dockets | Visual | Each lot | HP | SE, Nominated Authority | Nominated Authorith sign off This Line
5.9 | Install Pits and Flushouts | Section 702.10 | Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings. | Visual | Each lot | WP | SE/Site Supervisor | This ITP
5.10 | Marker Points | Section 702.11 | At all fill batter and drain outlets, supply and erect marker posts as shown on drawings | Visual | Each outlet | IP | SE/Site Supervisor | This ITP
6 | Post-construction / Post-installation Activities
6.1 | As Built Information | Section 702.03 | The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length | Document Review | Each lot | IP | Surveyor SE/PE/SPE | Attach Survey Conformance Report
6.2 | Flushing | Section 702.09 (h) | Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture. | Record Review | Each lot | HP | SE, Nominated Authority | Nominated Authorith sign off This Line
6.3 | CCTV | Section 702.09 (g) | Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA. | Record Review | Each lot | HP | SE, Nominated Authority | Nominated Authorith sign off This Line
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /