## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-225-CIV-Ferris-Subgrade Preparation - Road | itp |  |  |  |  | ITP-225-CIV-Ferris-Subgrade Preparation - Road Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-225-CIV-Ferris-Subgrade Preparation - Road
label | ITP Description: Ferris-Subgrade Preparation - Road
label | Discipline (e.g. CIV/STR/RAIL): 225-CIV
label | Revision Number: 0
label | Revision Date: 29/01/2025
label | ITP created by: Kamel ALSHOBAKI
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 204
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 173
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Material Approval
label | Reference - VR 204.4 ©
label | Acceptance Criteria - Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
label | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each mix material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documentations
checkpoint-no-value | 3.1 - Non Dependent
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Area has been set out in accordance with the drawings
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | Method - Verify
label | Frequency - Prior to commencement of excavation
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | Reference - Section 204.06 (c), Section 204.06 (e) IFC Drawings
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | ○ Assigned CBR ≥ 2.0%
label | ○ Assigned Swell less than 2.5%
label | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
label | ○ If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type A/B Fill - Road is to be utilised.
label | ○ Attach: Laboratory testing Verification:
textbox | Enter: Type A/B fill Lot Number:
label | Method - Verify-Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - This ITP/Test Report/Referenced Lot number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Material classified as silt
label | Reference - Section 204.04 b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | Method - Document Review
label | Frequency - Prior to commencing
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | Reference - Section 204.06 f)
label | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | Method - Site Inspection/ Document Review
label | Frequency - Prior construction of the regulating layer
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Unsuitable Material
label | Reference - Section 204.07 d)
label | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Groundwater
label | Reference - Section 204.06 h)
label | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Cut to Fill Zones
label | Reference - Section 204.06 g)
label | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A/B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A/B material.
label | Method - Site Inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.7 - Proof Roll
label | Reference - Section 173
label | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Site Engineer/Superintendent
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Compaction Testing
label | Reference - Table 204.131
label | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | ○ Scale B: Characteristic Density Ratio 98%.
label | ○ Attach: Compaction Test Result:
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Test Records, Lot Register
date | Date Completed:
section | 6. Post Construction Activities
checkpoint | 6.1 - Post Compaction Material Property Testing
label | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
label | Acceptance Criteria - Material Properties:
label | — CBR ≥ 2% and Swell ≤ 1.5%
label | — Max Permeability = 5X10-9 m/s
label | ○ Grading:
label | — 75.0mm 100%
label | — 4.75mm 40-80%
label | — 0.075mm 10-40%
label | — Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ○ Scale B:
label | — 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | — Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | ○ Attach: Post compaction test results:
label | Method - Review Document
label | Frequency - Refer to Section 204
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Sign ITP, Attach Material Property Test Report
date | Date Completed:
checkpoint | 6.2 - Survey Conformance
label | Reference - VicRoads 204.03f,g and h
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances (Scale B):
label | — Range x = +5, -25mm
label | — Max S = 15 mm
label | — 40 measurements per lot
label | Method - Review Document
label | Frequency - Each lot
label | Category - SCP
label | Responsibility - SE/Surveyor
label | Verifying Documents - Sign ITP, Attach Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-227-CIV-Ferris-Kerb & Channel (Supply and Install) | itp |  |  |  |  | ITP-227-CIV-Ferris-Kerb & Channel (Supply and Install) Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-227-CIV-Ferris-Kerb and Channel (Supply and Install)
label | ITP Description: Ferris-Kerb and Channel (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): 227-CIV
label | Revision Number: 0
label | Revision Date: 23/01/2025
label | ITP created by: Kamel ALSHOBAKI
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section
label | ○ 703 (August 2021)
label | ○ VR SD2001
label | ○ VR SD2102
label | ○ AS 2876
label | ○ AS1379
section | 2. Preliminary - Materials
checkpoint | 2.2 - Mix design
label | Reference - Section 703.05, 703.06, 703.07
label | Acceptance Criteria - Approved VR mix design to be used.
label | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
label | ○ Attach: TeamBinder Material Approval Ref No.
label | Method - Verify, Document Review
label | Frequency - Prior to commencing any activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bedding Material
label | Reference - Section 703.21 IFC Drawings
label | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | ○ Attach: TeamBinder Material Approval Ref No.
label | Method - Verify, Document Review
label | Frequency - Prior to commencing any activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Curing Compound
label | Reference - Section 703.10
label | Acceptance Criteria - Curing compound shall comply with AS3799
label | ○ Attach: TeamBinder Material Approval Ref No.
label | Method - Verify
label | Frequency - Prior to commencing any activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminary - Documentation
checkpoint | 3.1 - Check for correct documentation
label | Reference - IFC Drawings
label | Acceptance Criteria - Ensure that all employee and sub contractors are:
label | – Using the correct and complete set of drawings
label | – All drawings are the latest version
label | Method - Visual inspection
label | Frequency - Prior to commencing any activity
label | Category - HP*
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | Lot Map
label | Reference - MRPA Lot Management Procedure
label | Acceptance Criteria - Upload a Marked up drawing which indicates the Location of this Lot:
label | ○ Attach: Lot Map
label | Method - Document Review
label | Frequency - For Each Lot
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - Lot Map
date | Date Completed:
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Setting out
label | Reference - Section 703.17 IFC Drawings
label | Acceptance Criteria - Set out work in accordance with IFC Drawings.
label | ○ The superintendent will review and confirm set out.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
label | Method - Verify
label | Frequency - Prior to start
label | Category - HP
label | Responsibility - Surveyor/Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Temporary drainage provisions
label | Reference - Section 703.18, CEMP
label | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | ○ Attach: relevant written approval from relevant stakeholder.
label | Method - Visual inspection, Document Review
label | Frequency - Prior to start (where required)
label | Category - HP*
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Bedding
label | Reference - Section 703.21
label | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.2 - Formwork
label | Reference - Section 703.12 AS3610
label | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.3 - Pre Pour Check
label | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
label | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | ○ Attach: Pre-pour Inspection Record
label | Method - Verify
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.4 - Concrete placement
label | Reference - Section 703.08, Section 703.23
label | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | ○ Attach: Concrete Pour Records
label | Method - Site inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.5 - Transitions
label | Reference - Section 703.24
label | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | Method - Site inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.6 - Surface Finish
label | Reference - Section 703.25
label | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Renderings shall be applied within 30 minutes of extrusion.
label | ○ Concrete to have a neat appearance and uniform colour.
label | ○ Class 3 finish required for external surfaces.
label | ○ Class 4 finish required for permanently hidden surfaces.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/ Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.7 - Formwork Stripping
label | Reference - Section 703.12 AS3610
label | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
label | – External faces 2 days
label | – Permanently hidden faces 1 day
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE/ Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.8 - Tolerance
label | Reference - Section 703.15
label | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
label | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | ○ Attach: Post-pour Inspection Records
label | Method - Verify
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.9 - Curing
label | Reference - Section 703.10
label | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.10 - Joints
label | Reference - Section 703.26
label | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | Method - Verify
label | Frequency - Each joint
label | Category - IP
label | Responsibility - SE / Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.11 - Protection of Concrete
label | Reference - Section 703.27
label | Acceptance Criteria - All concrete shall be protected from damage from early loading.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Backfilling
label | Reference - Section 703.29
label | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | Method - Verify
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 6.2 - Cracking of Concrete
label | Reference - Section 703.30
label | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | ○ Attach: Pot-pour Inspection Record
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 6.3 - Survey Conformance
label | Reference - Section 703.15
label | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
label | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | Method - Document Review
label | Frequency - Completion of each lot
label | Category - WP
label | Responsibility - Project Engineer/ Surveyor
label | Verifying Documents - As-built survey records
date | Date Completed:
checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-228-CIV-Ferris-Unbound Flexible Pavement Construction | itp |  |  |  |  | ITP-228-CIV-Ferris-Unbound Flexible Pavement Construction Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-228-CIV-Ferris-Unbound Flexible Pavement
label | ITP Description: Ferris-Unbound Flexible Pavement
label | Discipline (e.g. CIV/STR/RAIL): 228-CIV
label | Revision Number: 0
label | Revision Date: 23/01/2025
label | ITP created by: Kamel ALSHOBAKI
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - Reference Documents: IFC Drawings
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 173 (10/9/2008)
label | ○ VicRoads Section 304 (13/8/13)
label | ○ VicRoads Section 801 (19/07/18)
label | ○ VicRoads Section 812 (13/07/16)
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Crushed Rock Mix Design
label | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
label | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Material conformance as per Table 812.121
label | Category - HP
label | Responsibility - NA
label | Verifying Documents - TeamBinder Material Approval Number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documentation
checkpoint | 3.1 - Subgrade Preparation
label | Reference - 304.04
label | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
textbox | Reference: Subgrade Preparation/Type fill Lot Number:
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - Underlying layer Lot number
date | Date Completed:
checkpoint | 3.2 - Select Scale
label | Reference - Project Requirement Specifications, IFC Drawings
label | Acceptance Criteria - Specify site specific scale:
textbox | Enter: Site Specific Scale (A, B or C)
label | Method - Document Review
label | Frequency - Prior to Commencement, Each lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-out and Lot size
label | Reference - IFC Drawings Section 304.06
label | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
label | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | Method - Survey, Document Review, Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Surveyor, SE
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Crushed Rock Delivery Dockets
label | Reference - 304.04
label | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
label | ○ ATTACH: Delivery Docket(s)
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Attached Docket, Sign ITP
date | Date Completed:
checkpoint | 5.2 - Placement of Material
label | Reference - Section 304.03, Section 304.06, Section 304.08
label | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | ○ At no location shall water pond on the surface of any pavement layer.
label | Method - Visual and Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.3 - Construction - Jointing
label | Reference - Section 304.07
label | Acceptance Criteria - The layout of joints shall conform to the following requirements:
label | (a) material shall be spread in such a manner as to minimize the number of joints;
label | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | Method - Visual and Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.4 - Compaction test (Frequency)
label | Reference - 304 .11 (b)
label | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | ○ Scales A and B: 6 samples
label | ○ Scale C: 3 Samples
label | ○ Pass: Tested
label | ○ NA: Not Tested
label | Method - Visual
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
label | Reference - 304.11 (c)
label | Acceptance Criteria - SCALE A:
label | — The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
label | ○ Compaction:
label | — Lower Subbase: none
label | — Upper Subbase: 1 in 4
label | — Base: 1 in 2
label | ○ PI:
label | — Upper Subbase and Lower Base: 1 (two samples) in 8
label | — Upper Base: 1 (two samples) in 4
label | ○ SCALE B:
label | — the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | ○ SCALE C:
label | — Post compaction grading and PI testing is not required (CHOOSE NA)
label | Method - Visual
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.6 - Proof Roll
label | Reference - Section 304.08
label | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | Method - Visual
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Protection of compacted layer
label | Reference - Section 304.09
label | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Compaction Testing (results)
label | Reference - Section 173, Section 304.08 Table 304.081
label | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
label | ○ Scale B:
label | — Subbase Layer CDR ≥ 97%
label | — Base Layer CDR ≥ 98%
label | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | ○ Scale C:
label | — Mean Value of Density Ratio (3 tests):
label | — Subbase Layers >98%
label | — Base Layers >100%
label | ○ ATTACH: Compaction Test Results
label | Method - Document Review
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Compaction Test Rersults
date | Date Completed:
checkpoint | 6.2 - Post Compaction Materials Testing (Results)
label | Reference - Section 304.10, Section 304.11, RC 500.02
label | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | ○ 20mm Class 3:
label | Grading
label | — 26.5mm 100%
label | — 19.0mm 95-100%
label | — 13.2mm 75-95%
label | — 9.5mm 60-90%
label | — 4.75mm 42-76%
label | — 2.36mm 28-61%
label | — 0.425mm 14-29%
label | — 0.075mm 6-14%
label | — PI between 0 to 10
label | ○ 20mm Class 4:
label | Grading
label | — 26.5mm 100%
label | — 4.75mm 42-76%
label | — 0.425mm 10-28%
label | — 0.075mm 2-14%
label | — PI between 0 to 20
label | — PI x % passing 0.425 mm sieve (max) 450
label | ○ Scale C: Post compaction material testing is not required (Choose NA)
label | Method - Document Review
label | Frequency - Each Lot Where applicable
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Compaction Test Rersults
date | Date Completed:
checkpoint | 6.3 - Survey As-Built - Surface Level
label | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
label | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
label | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | ○ Scale B: A minimum of 40 measurements per lot
label | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | ○ Scale C:
label | — Lower Subbase (mm) +15/ -25
label | — Upper Subbase (mm) +10/ -25
label | — Base (mm) +/-15
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/Surveyor
label | Verifying Documents - Survey Conformance Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-229-CIV-Ferris-Subsoil Drainage | itp |  |  |  |  | ITP-229-CIV-Ferris-Subsoil Drainage Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-229-CIV-Ferris-Subsoil Drainage
label | ITP Description: Ferris-Subsoil Drainage
label | Discipline (e.g. CIV/STR/RAIL): 229-CIV
label | Revision Number: 0
label | Revision Date: 23/01/2025
label | ITP created by: Kamel ALSHOBAKI
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 702 (May '19)
section | 2. Preliminaries-Material
checkpoint | 2.1 - Pipes
label | Reference - IFC Drawings VR 702.04
label | Acceptance Criteria - All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Granular material: Filter Sand
label | Reference - IFC Drawings VR 702.05
label | Acceptance Criteria - Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Granular Material: No Fines Concrete
label | Reference - IFC Drawings VR 702.05 (e)
label | Acceptance Criteria - No Fines Concrete: Shall comply with 702.05 e)
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Geo textile
label | Reference - IFC Drawings VR 702.06
label | Acceptance Criteria - Geotextiles: Shall comply with table 702.061
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
label | Reference - IFC Drawings Section 702.04, 702.05 & 702.06
label | Acceptance Criteria - Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
label | ○ Flushout risers: As per SD 1631
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set Out
label | Reference - Section 702.03
label | Acceptance Criteria - Survey to set out Subsurface Drainage line.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set Out
label | Reference - IFC Drawings Section 702.03
label | Acceptance Criteria - Survey to set out Subsurface Drainage line.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor, Surveyor
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Trench Excavation
label | Reference - IFC Drawings Section 702.08
label | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
label | Method - Visual Inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Trench Excavation
label | Reference - Section 702.08
label | Acceptance Criteria - The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
label | Method - Visual Inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Nominated Authorith sign off ThisLine
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Placement of bedding
label | Reference - Section 702.09 c)
label | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Traficable Pavements
label | Reference - IFC Drawings SD 1601, EDCM 201
label | Acceptance Criteria - Choose pass when applicable
label | ○ All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and MCC202B
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Outside trafficable pavement
label | Reference - IFC Drawings SD 1601, EDCM 201
label | Acceptance Criteria - Choose pass when applicable pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Pipe and Geotextile Installation (if required)
label | Reference - Section 702.03, 702.09
label | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding.
label | ○ Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.7 - Backfill Installation (Granular Filter Material)
label | Reference - Section 702.09 (g)
label | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
label | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | Method - Visual, Doc. Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE, Nominated Authority
label | Verifying Documents - Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Backfill Installation (No Fines)
label | Reference - Section 702.09 (g)
label | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
label | ○ ATTACH: No Fines Delivery Dockets
label | Method - Visual
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE, Nominated Authority
label | Verifying Documents - Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.9 - Install Pits and Flushouts
label | Reference - Section 702.10
label | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | Method - Visual
label | Frequency - Each lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.10 - Marker Points
label | Reference - Section 702.11
label | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | Method - Visual
label | Frequency - Each outlet
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As Built Information
label | Reference - Section 702.03
label | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Attach Survey Conformance Report
date | Date Completed:
checkpoint | 6.2 - Flushing
label | Reference - Section 702.09 (h)
label | Acceptance Criteria - Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | Method - Record Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE, Nominated Authority
label | Verifying Documents - Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - CCTV
label | Reference - Section 702.09 (g)
label | Acceptance Criteria - Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
label | Method - Record Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE, Nominated Authority
label | Verifying Documents - Nominated Authorith sign off This Line
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation | itp |  |  |  |  | ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation
label | ITP Description: Stormwater Drainage Supply & Installation
label | Discipline (e.g. CIV/STR/RAIL): Ferris-CIV
label | Revision Number: 0
label | Revision Date: 23/01/2025
label | ITP created by: Kamel ALSHOBAKI
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 701 (May 2020)
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 705 (June 2021)
label | 1.3 - Non Dependent
label | Reference - IFC Drawings
label | 1.4 - Non Dependent
label | Reference - CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
label | Reference - VR Section 701.04, VR Section 701.05, VR Section 701.09
label | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and VR Sections 701.05 & 701.09
label | ○ Precast reinforced concrete box culverts shall comply with the requirements of VR Section 701.04
label | ○ Rubber ring joints shall comply with the requirements of AS 1646
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Drainage Flexible Pipes
label | Reference - Section 701.08
label | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Precast Drainage Pit
label | Reference - VR Section 705.07, VR Section 705.04, VR Section 705.09
label | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705.07 & 705.09
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04. Concrete grades shall comply with Table 705.041
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Cast in Place Drainage Pit
label | Reference - VR Section 705.06 IFC Drawings
label | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of VR Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Drainage Pit - Step Irons
label | Reference - VR Section 705.04, VR Section 705.12
label | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705.12
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Drainage Bedding Material
label | Reference - VR Section 701.09
label | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Drainage Backfill Material
label | Reference - VR Section 701.09, VR Section 701.19
label | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documents
checkpoint | 3.1 - Subcontractor ITP (where required)
label | Reference - Subcontractor ITP
label | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | ○ Attach: Approved Subcontractor ITP
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Survey Set Out - Pits & Pipes
label | Reference - IFC Drawings VR Section 701.10
label | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | Method - Survey
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Pits - Excavation
label | Reference - IFC Drawings VR Section 705.05
label | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.2 - Pits - Placement of Bedding Material
label | Reference - IFC Drawings VR Section 705.05
label | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | ○ > 80mm for clay foundations
label | ○ > 150mm for rock foundations
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.3 - Pits - Bedding Testing
label | Reference - IFC Drawings VR Section 701.20
label | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | Method - Compaction Test
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
label | Reference - IFC Drawings VR Section 701.10
label | Acceptance Criteria - Survey pick-up to verify:
label | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
label | Reference - IFC Drawings VR Section 705.06, VR Section 610, VR Section 611
label | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of VR Section 610 and 611.
label | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | Method - Survey, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.6 - Pits - Jointing & Drainage Connections
label | Reference - VR Section 705.11
label | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with VR Section 705.11.
label | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.7 - Pits - Shaping of Floor
label | Reference - VR Section 705.13
label | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Section 705.13.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.8 - Pits - Step Irons
label | Reference - IFC Drawings VR Section 705.12
label | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.9 - Pits - Fitting of Covers
label | Reference - IFC Drawings VR Section 705.17
label | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | ○ Height shall be within 10mm of the design level.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.10 - Pits - Pit Lids
label | Reference - IFC Drawings
label | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
label | Reference - VR Section 705.18
label | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.12 - Pipes - Trench Excavation
label | Reference - IFC Drawings VR Section 701.15
label | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | ○ > 300mm, < 600mm for RCP
label | ○ > 150mm for Flexible Pipe
label | — The base of the trench shall be compacted to refusal using mechanical plant.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.13 - Pipes - Bedding Placement
label | Reference - IFC Drawings VR Section 701.16
label | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | ○ > 100mm where D<1500mm
label | ○ > 200mmwhwere D≥1500mm
label | — Bedding material shall be placed and compacted in layers <150mm loose thickness
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.14 - Pipes - Bedding Testting
label | Reference - IFC Drawings VR Section 701.20
label | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | Method - Compaction Test
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
label | Reference - IFC Drawings VR Section 701.17, VR Section 701.20
label | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
label | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.16 - Pipes - Lifting Holes
label | Reference - VR Section 701.18
label | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.17 - Pipes - As-built survey pick-up
label | Reference - IFC Drawings VR Section 710.10
label | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
label | – Offset pits to kerb +/- 20mm
label | – Plan location pits not adjacent to kerb +/- 100mm
label | – Invert level of pipes at pits +/- 50mm
label | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | Method - Survey
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.18 - Pipes - Backfill Placement
label | Reference - IFC Drawings VR Section 701.16
label | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.19 - Pipes - Backfill Testing
label | Reference - IFC Drawings VR Section 701.20, VR Section 701.29
label | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Flushing & CCTV
label | Reference - VR Section 701.28, VR Section 701.30
label | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | ○ Attach: Flushing Record, CCTV Reports
label | Method - Record Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release, Flushing Record, CCTV Reports
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - As Built Survey
label | Reference - VR Section 701.10
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
label | ○ Attach: As-Built Survey Conformance
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ConQA HP Release, As Built Survey Report
date | Date Completed:
checkpoint | 6.3 - Repairs to Damaged Pipes
label | Reference - VR Section 701.31
label | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | — cracks wider than 0.5 mm
label | — spalling of concrete
label | — exposed reinforcement
label | — joints that are not fully engaged.
label | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
label | — longitudinal cracks greater than 2 mm
label | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked VR Sections exceeding 3 mm
label | — circumferential cracks around part of the circumference with width greater than 4 mm
label | — penetrations with area greater than 400 mm2
label | — pipe joints that are separated.
label | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of VR Section 689.
label | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA HP Release, Approved Repair Procedure, Post Repair CCTV Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP