## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-236-CIV-SSB-Landscaping-Ground Preparation | itp |  |  |  |  | ITP-236-CIV-SSB-Landscaping-Ground Preparation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-236-CIV-SSB-Landscaping-Ground Preparation
label | ITP Description: SSB-Landscaping-Ground Preparation
label | Discipline (e.g. CIV/STR/RAIL): 236-CIV
label | Revision Number: 0
label | ITP created by: Mike Freeman
label | ITP approved for use by: VM
label | 1.1 Referenced Documentation
label | Reference: VicRoads 720
label | ○ AS 4454
label | ○ AS 4419
label | ○ IFC Drawings
label | ○ Sub Contractor ITP
section | Preliminaries
checkpoint | 1.1 Check for correct documentation
label | REFERENCE: Drawings and drawing registers
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – Using the correct and complete set of IFC drawings
label | – All drawings are the latest revision
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 1.2 Submission and records
label | REFERENCE: Section 720.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
label | Following information shall be provided to the NA:
label | ○ Samples
label | — Mulch
label | — Imported topsoil
label | ○ Records
label | — Details of suppliers
label | — Soil tests on imported topsoil
label | — Copies/Photos of fertiliser labels
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Issue to TeamBinder
label | ○ Attach: Records & certificates
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 Supply of topsoil
label | REFERENCE: Section 720.04, Table 720.042 IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
label | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings .
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Doc. Review if applicable
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach material conformance docs/Test Report
date | Date Completed:
checkpoint | 1.4 Supply of Mulch
label | REFERENCE: Section 720.04, Table 720.044, AS4454 IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
label | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
label | ○ Imported Wood Mulch shall comply with Table 720.044.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify, Doc. Review if applicable
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach material conformance docs (if applicable)
date | Date Completed:
section | Site Preparation
checkpoint | 2.1 Subcontractor ITP
label | REFERENCE: Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Subcontractor ITP to be reviewed and approved by MRPA.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach completed Subcontractor ITP
date | Date Completed:
checkpoint | 2.2 Soil Additives
label | REFERENCE: Section 720.07 a) AS 4419
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach Test Report
label | ○ Attached Delivery Docket (if applicable)
date | Date Completed:
checkpoint | 2.3 Ripping of subsoil
label | REFERENCE: Section 720.07, Table 720.071
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP.
label | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach Lot Map/Marked Up Area Inspected
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Topsoil application
label | REFERENCE: Section 720.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Site topsoil shall be used wherever possible, in preference to imported topsoil. Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in table 720.071.
label | ○ Situation
label | — Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
label | — Planting Areas in disturbed areas steeper than 3h:1v = 100mm Minimum
label | — Grassing in disturbed areas =75 mm, except 100 mm in swales
label | — Individual Tree Planting within grassed areas =150 mm in disturbed grassed areas
label | ○ Topsoil shall be spread on planting areas and grassed areas.
label | ○ Note: Topsoil shall not be compacted.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach Delivery Dockets if applicable
date | Date Completed:
checkpoint | 2.6 Topsoil FSL - Topsoilling and Cultivation
label | REFERENCE: Section 720.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, NA
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach Lot Map/Marked Up Area Inspected
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 Mulching
label | REFERENCE: Section 720.08 a) IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Attach Delivery Dockets
date | Date Completed:
checkpoint | 2.7 Weed and Erosion Control Mat
label | REFERENCE: Section 720.04 i) IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE, Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
label | ○ Reference TeamBinder Material Approval No. if applicable
label | ○ Attach Delivery Dockets
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-237-CIV-SSB-Landscaping-Planting | itp |  |  |  |  | ITP-237-CIV-SSB-Landscaping-Planting Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-237-CIV-SSB-Landscaping-Planting
label | ITP Description: SSB-Landscaping-Planting
label | Discipline (e.g. CIV/STR/RAIL): 237-CIV
label | Revision Number: 0
label | ITP created by: Mike Freeman
label | ITP approved for use by: VM
label | 1.1 Referenced Documentation
label | Reference: IFC Drawings Vic Roads Section 720 (Nov '18)
section | Preliminaries
checkpoint | 2.1 Check for correct documentation
label | REFERENCE: Drawings and Drawing Register
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using:
label | – The correct and complete set of drawings
label | – All drawings are the latest revision
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: N/A
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.2 Submission and records
label | REFERENCE: VicRoads Spec.
label | – Cl.720.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
label | ○ Following information shall be provided to the superintendent:
label | ○ Inspections of plant stock for all plant species
label | ○ Records:
label | — Evidence of origin of indigenous provenance plant material
label | — Analysis certificates for grass seed
label | — Details of suppliers
label | — Copies/Photos of fertiliser labels
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE,Superintendent
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
label | ○ Attach Records to TeamBinder Approval Form
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Supply of Plant Stock
label | REFERENCE: VicRoads Spec.
label | – Cl.720.04
label | – Table 720.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
label | – Plants are to conform to the supply properties specified in Table 720.041
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: N/A
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.4 Supply of indigenous plant stock
label | REFERENCE: VicRoads Spec.
label | – Cl.720.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
label | – The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
label | – species name
label | – storage code
label | – collection locality – Latitude/longitude or AMG
label | – approximate number of parent plants sampled
label | – approximate number of plants in that local population
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: N/A
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.5 Supply of grass seed
label | REFERENCE: VicRoads Spec.
label | – Cl.720.04
label | – Table 720.045
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grass seed shall comply with Table 720.045
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: N/A
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Pre-Construction Activities
checkpoint | 3.1 Planting Section Approval
label | REFERENCE: VicRoads Spec.
label | – Cl.720.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Pest and Weed Control
label | REFERENCE: Cl.720.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
label | ○ Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.3 Setting out planting areas
label | REFERENCE: VicRoads Spec.
label | – Cl.720.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Planting areas are to be set out to the location and shape specified in the landscape drawings.
label | – Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
label | – Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: N/A
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction
checkpoint | 4.1 Planting
label | REFERENCE: VicRoads Spec.
label | – Cl.720.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All planting will be undertaken in accordance to Subcontractor approved ITP
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Applicable Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: NA
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE,Foreman
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Completion
checkpoint | 5.1 Site Final Inspection
label | REFERENCE: Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Subcontractor ITP signed and completed
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review & Site Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Following completion of planting works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: N/A
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sub-Contractor ITP completed, signed and to be attached
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP