## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Prestart Inspections
section | Details
checkpoint | Site has been cleaned in advance of our arrival on site
checkpoint | Walls are plumb and level
label | IMPORTANT
checkpoint | Tiling works running to programme - prior trades completed
checkpoint | Has prior trades QA been signed off by main contractor
checkpoint | Gib compound and sanding cleaned up from rooms
checkpoint | Task Analysis signed onto by tilers and provided to main contractor
checkpoint | Inductions completed
checkpoint | Site Inspection checklist has been completed
checkpoint | All tools tagged and tested - (photo's required)
checkpoint | Tiler has current site safe - Input number and expiry
checkpoint | Tiler has correct PPE
checkpoint | Correct drawings supplied as per onsite
checklist | QA - Floor Prep Bathrooms
section | Floor Preparation
checkpoint | Is the area clean, and cleared, ready for necessary preparation
checkpoint | Tile and slate underlay installed to bathroom floors
checkpoint | Are flanges installed at correct depth in accordance with specified wastes
checkpoint | Has screeding been completed to shower at correct height and falls - R4 screed
checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
checklist | QA - Waterproofing
checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
checkpoint | Waterproofing coat # 1 applied to floors and walls (take photos)
checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
checkpoint | Flood tests, if required, undertaken and photos provided.
checklist | QA - Tiling Installation
section | Tiling bathroom floor and walls
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install tiles to floor including atlantis shower tray
checkpoint | Skirting tiles done to perimeter of bathroom outside shower
checkpoint | Wall tiles set out to match floor grout lines or as per drawings install tiles to shower walls
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | QA - Kitchen Splashback Installation
section | Splashback Installation
checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Splashback Tiles set out as per drawings
checkpoint | Tiles to walls
checkpoint | Tiling is completed, checked and supervisor to sign on
checkpoint | Silicone nominated is the correct colour and applied evenly and correctly
checkpoint | Correct tiles trim is supplied and installed as per drawings
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | QA - Vanity Splashback Installation
section | Vanity Splashback Installation
checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Splashback Tiles set out as per drawings
checkpoint | Tiles to walls
checkpoint | Tiling is completed, checked and supervisor to sign on
checkpoint | Silicone nominated is the correct colour and applied evenly and correctly
checkpoint | Correct tiles trim is supplied and installed as per drawings
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | QA - Laundry Splashback Installation
section | Laundry Splashback Installation
checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Splashback Tiles set out as per drawings
checkpoint | Tiles to walls
checkpoint | Tiling is completed, checked and supervisor to sign on
checkpoint | Silicone nominated is the correct colour and applied evenly and correctly
checkpoint | Correct tiles trim is supplied and installed as per drawings
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed