## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | c42f1037-d014-43ef-a5f0-7259545e5f42 |  | checklist | Progress Claim |  |  |  |  | Yes | Progress Claim Checklist - Tower 2 | 083457ea-1169-4878-a784-a1d41f34aee3
checkpoint-status | bf5e8847-56dd-4d75-9da5-7d81f3fb6d57 |  | checkpoint | Please add Comments / Photos
select | 66375522-c206-5ded-bcfe-e6073061498e |  | dropdown | General | Site Establishment / Prefab, Systems, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning.
select | d27152c0-b6a5-521c-88ba-f9a1119ce08e |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 5aef40a8-3752-5289-a79a-799a3b0ceaf3 |  | textbox | General Notes
checkpoint-status | a4278a96-d4ce-4bd3-bee8-da1e5e5fb80e |  | checkpoint | Please add Comments / Photos
select | 25255036-1793-5f96-947f-d4c51560b121 |  | dropdown | Level | Level 1, 2, 3, 4 - 25, Roof Plant Deck
select | ebcdfeb0-a9d7-5d85-b07c-e48c49c6a761 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | e0561d85-303b-52fa-9477-1cbd2f81639a |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | bdc89d57-6b12-568e-a2dc-1660c4faa8c2 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | c6faae17-36b1-5c72-b48e-e6bfa9d1a9ea |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 4b6cf2c4-98e2-53cc-85a9-efb1de3d1c66 |  | textbox | General Notes
checkpoint-status | d85e7abe-b944-4798-a399-4e87278ead8a |  | checkpoint | Please add Comments / Photos
select | 9910ff72-1793-54fe-96a1-d6ed64cc4d2d |  | dropdown | Level | Level 1, 2, 3, 4 - 25, Roof Plant Deck
select | 7e5a04e9-cf65-5b52-a412-b4a7a5e4b4e6 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 4d9d27a5-dba2-5313-8a25-799b1631b886 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 171e6453-1eae-58b3-a2cf-a5407d9edff2 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 0b0d480d-5779-5203-830a-c1864508a47d |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 0e99b554-9ebe-5ea5-8aed-7019f6908c33 |  | textbox | General Notes
checkpoint-status | 5295cfab-af5d-490b-9baf-f0f5d7ac1197 |  | checkpoint | Please add Comments / Photos
select | 8ff600c3-784b-52e3-91c9-e89c005240c0 |  | dropdown | Level | Level 1, 2, 3, 4 - 25, Roof Plant Deck
select | 9007997d-aaa4-5177-a1c8-de36a7385672 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 65539320-b92b-549e-a48b-19aa31228d80 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 9371d73f-480a-5516-bc71-52888c93aa5f |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 1b1b304f-233b-5cd7-8f7d-fedda1047d99 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 390983db-6055-501b-9533-a6ebb323310d |  | textbox | General Notes
checkpoint-status | a254b1ac-421d-4680-911f-88530491d764 |  | checkpoint | Please add Comments / Photos
select | 70d634de-c1c5-5515-a8ba-31685e88a8d2 |  | dropdown | Level | Level 1, 2, 3, 4 - 25, Roof Plant Deck
select | 853bc1df-a862-518a-aec4-bc9620b84753 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | cd513fc1-f03d-5615-95d5-5df4b829d350 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 5322840c-4fb4-5558-ac32-77239a77da79 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 09b66a03-4dd2-5b80-8e82-6e561c5676fa |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 9a6d8d19-0128-5374-bfe6-8f71ccca4fe7 |  | textbox | General Notes
checkpoint-status | 56e70ce5-e867-4de2-bd38-a8cdd9562b1d |  | checkpoint | Please add Comments / Photos
select | 6a10015b-596b-5db5-9d7f-3b80a7871864 |  | dropdown | Level | Level 1, 2, 3, 4 - 25, Roof Plant Deck
select | 9b43aee2-417d-53ac-8ab8-7f1b6b6da2b4 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 3e65ab67-4eac-5032-9a4d-7f4f1cdded80 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 1b10b126-66f4-5b35-a77d-19fa51d89cd8 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 5b33d8ae-ca05-5168-8e54-74149f1657e3 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | c3c2fbd4-04a2-5ce6-b9ed-6452a8c3194e |  | textbox | General Notes
checkpoint-status | f6c2cb83-f349-45b9-add8-e957c7a961b0 |  | checkpoint | Please add Comments / Photos
select | df236846-5dc4-5211-89a2-0dcfdde28c4a |  | dropdown | Level | Level 1, 2, 3, 4 - 25, Roof Plant Deck
select | bcfec5ba-7143-5f55-a464-e5c3e18a885d |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | f6720aff-2768-5bf8-86bf-15e80cc726cf |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 8d91481f-7da7-5615-a851-824eda761441 |  | textbox | General Notes
checkpoint-status | a8ac2587-589b-4e21-abd0-ce333895747d |  | checkpoint | Please add Comments / Photos
select | 286d0179-c741-5194-9fe5-491ccddc68e6 |  | dropdown | Level | Level 1, 2, 3, 4 - 25, Roof Plant Deck
select | f2f8b893-7785-5570-9473-96afa0157d47 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 38862953-af54-5c08-a90d-efca1b0af9f2 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 0ed36e0b-f465-5d32-8500-f96ac55ffe44 |  | textbox | General Notes
checklist-flat | 1e8042f7-2433-4546-bab8-43fe426ea6d2 |  | checklist | Suspended Slab Checklist |  |  |  |  | Yes | Suspended Slab Checklist | 0bc46be2-240c-45e8-bdd2-862737482110
checkpoint-status | 2531d26e-1f95-4a91-86aa-043dc6c66e69 |  | checkpoint | Area accessible & ready
checkpoint-status | 97838870-4628-47c1-8fb3-919bf2bc0fe4 |  | checkpoint | Drawing references entered
checkpoint-status | 9b1e09a3-05d9-4b8b-9ef1-c48e5e949d7e |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 63405465-fbed-498f-855d-be4caf265308 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | 087e27a6-172b-4734-8a43-a9d4f6269609 |  | checkpoint | Grids marked by builder
checkpoint-status | 9bfff1c8-b10b-4fa3-8ee2-105ef0cc8d53 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | e8009d3e-44ba-4beb-b9c1-e0494c2fec0d |  | checkpoint | Fillet & drip mould installed
checkpoint-status | 9c2d77fa-9556-4b52-8b05-9e390782d4b6 |  | checkpoint | Check set down position & RL
checkpoint-status | e9dafd1c-4679-417e-9367-123617c6b4d3 |  | checkpoint | Check penetrations installed
checkpoint-status | 8a614ad3-0de2-491c-801d-96d809bbd765 |  | checkpoint | Prop drop head wedges are secure
checkpoint-status | ab87cc8f-3eac-4edf-a6df-b0faa4f7b86b |  | checkpoint | Column blockouts installed
holdpoint | 726be3fb-9db2-451e-9d71-4e9e48679b3f |  | signoff | Inspection by site engineer
checkpoint-status | f6f31665-b9eb-4349-828d-c709a69b0ea5 |  | checkpoint | check back propping as per design
checkpoint-status | e52a5a43-04b8-435e-a587-e484cdb862a2 |  | checkpoint | Blow off deck
holdpoint | bc86d222-e8d8-4172-b5b0-0c23504bccd9 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 1a1ede70-5500-46a8-b5b9-35e23055d047 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | 19fe50df-9519-453d-868d-195234409611 |  | checkpoint | Correct Class of Finish
checkpoint-status | ba586d5c-ec04-4eb2-a843-c23ce624b2f8 |  | checkpoint | Stripping, cleaning & materials removed
checklist-flat | 262b9658-82fc-4cd9-9b2a-a848966f6d5c |  | checklist | [5 empty] | Yes | ZSYS - Progress Claims Checklist (old) | 15696a4b-7863-4fdc-a08b-bef5a7b7a36b
checkpoint-status | 2eb8c286-e234-43a0-9406-7ed9a0f28dcc |  | checkpoint | Please add Comments / Photos
select | ba53567f-f7de-587a-b974-f41c42834ae0 |  | dropdown | General | Site Establishment / Prefab, Systems
select | 1ae524ba-17fe-5acf-9f74-56d238520574 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | a71cfa12-5712-562b-b11a-6712acb5843e |  | textbox | General Notes
checkpoint-status | 9dab67d7-e50d-40c6-8c7b-003bd91afa8d |  | checkpoint | Please add Comments / Photos
select | 4f92dd9c-3c17-52f6-a6d9-8b39aaa74cfa |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | e2a9a067-40ad-5f5a-a2d3-9e0218539c8c |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 3104b06d-4ff8-5450-be6a-4c0c887eb2ec |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 95e72335-ddc5-5c98-8d72-4ab8760fe36b |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 437e82b4-eb2f-5f55-9800-9f581e22966d |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 989e4ae5-8dce-513d-9d68-48a7155319f3 |  | textbox | General Notes
checkpoint-status | 946e23cf-e4c1-4445-a93b-ed31827639dc |  | checkpoint | Please add Comments / Photos
select | 7c32e543-713e-581a-b680-1c1be723cea7 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | 4ffda3dd-38b0-5282-a2ea-12383d4d2504 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | c38b8157-f4cc-5cfc-b2f8-1b87e09f46f4 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | fb55c999-dcf6-5012-b258-e76bb23ca44c |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | b0ab38ac-bcf5-59fc-a9bb-d894579db014 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 01a253a5-3bc6-53e6-80e1-03f691474e1e |  | textbox | General Notes
checkpoint-status | 1fdd09b7-384e-46a0-9d14-8cbd22e3cbde |  | checkpoint | Please add Comments / Photos
select | d0e32371-349d-5a67-98a1-2d4a86d8ac88 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | fe6dcf6b-2e22-5c03-87c8-f54a6acf766c |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | a1e9a222-2e64-5555-84fb-fadce56f8008 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | f340997a-5faa-5dd5-b345-4e5b4022eea2 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 42acfaf4-12ac-5954-8202-5c99f6a2df46 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 6d39650c-c1b2-5d77-a41e-c4542e77b958 |  | textbox | General Notes
checkpoint-status | a149ce6c-df00-4698-bc3e-1e66632e0a3b |  | checkpoint | Please add Comments / Photos
select | 9b1749c7-1e42-510f-874e-40f850df1a31 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | 3db1a47d-e47b-52b8-9441-2ea12c3c9072 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 5b6d324e-fe67-537c-b05e-9a9c498b5f6e |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 99e9a9c5-0720-59eb-a8f8-a3fa87b88c72 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 8a5891f0-65e3-5059-90de-351aadd6b9bb |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | f6e3121f-25db-5385-ad20-691a98781a60 |  | textbox | General Notes
checkpoint-status | e0e7ae7f-0214-4a15-b077-409ac31e3eeb |  | checkpoint | Please add Comments / Photos
select | c95e3feb-1987-5103-aed8-e78097aa28fa |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | 42e1b6d7-86bd-56d6-8882-7616f4d14fd8 |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | bd430d0f-e153-5687-abd6-ef8a933837f3 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 1a894085-62ec-57e3-b835-0bade156b0af |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 83c9ca5e-7521-50de-9c7c-9f1663bd0e88 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 9b848eeb-1cc6-5c2f-9ba2-af914c6c0eed |  | textbox | General Notes
checkpoint-status | 6d7a8259-6382-4671-bece-c5699edd5050 |  | checkpoint | Please add Comments / Photos
select | f7f42367-1fc3-56c7-8381-4b4ba972c5a9 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | 5373d5e7-54d0-535b-888c-3c329fbc376e |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 6225f83c-a2d5-51ad-8696-a0dc57b01983 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | e58ea885-74d4-50a1-88e5-12e1e2ab00c3 |  | textbox | General Notes
checkpoint-status | b1e079a8-4f20-4e9b-a127-f6d887b24c9f |  | checkpoint | Please add Comments / Photos
select | 26d0dda5-f7db-597a-960c-25a251102f50 |  | dropdown | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | 6cded88f-2bb6-5232-bd14-3ef8e6605e2a |  | dropdown | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | 605160b9-9276-5ab1-b5a9-269089decbdb |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 58fa5de5-0f8f-5f42-b50e-c530322ee9b2 |  | textbox | General Notes
checklist-sectioned | c327d3e8-9b21-44fa-bdb9-735be23a0b3c |  | checklist | Jump System / Climb Track Checklist |  |  |  |  | Yes | Jump System / Climb Track Checklist | 1db247db-3e19-4f48-af2c-189ceb441235
checkpoint-group | 9d27170f-02a6-4f08-8f06-1e26787874d5 |  | section | Pre Lift
checkpoint-status | 3a5e80b4-27c5-41a6-9909-618e2820c353 |  | checkpoint | Confirm concrete strength MPA 15 has been reached at connection points (Builder to supply)
checkpoint-status | 53b8a7ff-8752-453d-86a0-12d832595136 |  | checkpoint | Signage in place (Stripping in progress/Jumping in progress/ No access)
checkpoint-status | ae11d52e-79c6-4968-8b28-be9b3eef2a56 |  | checkpoint | Exclusion Zone in place
checkpoint-status | 240ca621-9f1d-45ed-a182-982b39fb0000 |  | checkpoint | Spotters in place on slab below jump (outside exclusion zone)
checkpoint-status | bb96e7fe-aa79-4213-8ec7-e39f9ffa473d |  | checkpoint | All Platforms cleaned and clear from rubbish
checkpoint-status | b9a3be68-896f-40a7-adde-37f9e8dfd926 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 15ee3ecc-16f8-4d86-a6c7-bc71be704afd |  | checkpoint | Clear communication between team leaders and Crane crew (toolbox talk)
checkpoint-status | 1676019e-c501-4e2b-8446-ce87a2b5fa67 |  | checkpoint | Ladders available and secured
checkpoint-status | 0c844d60-4f5e-41d9-8d58-ca69582aeaa6 |  | checkpoint | Flipper systems lubricated
checkpoint-status | e62ce937-3d2e-47fc-8363-da1545c3fe1f |  | checkpoint | Trailing Decks clean of debris
checkpoint-status | c18410a6-29b6-4150-8c4d-e3ea02b31d5c |  | checkpoint | Trailing decks clear of protruding ferrals in walls above
checkpoint-status | fa89bca4-56d5-4fb6-8b2f-633294891d6c |  | checkpoint | Check exclusion zones in pit below are in place
checkpoint-status | e4c9002d-03d8-42b2-9e3c-8c927b55b50c |  | checkpoint | Plumber to check pipes to water cooler
checkpoint-status | 5cc168af-151b-4967-8a78-44fa169f33d1 |  | checkpoint | Transfer RL heights
checkpoint-group | b2af69d7-7575-484e-a8ee-ecd04dfbe2b8 |  | section | Post Lift
checkpoint-status | 158f6e69-fe6d-42b8-858a-ef4b07c9b6b9 |  | checkpoint | Confirm connection points are secure and all engaged
checkpoint-status | 118fda9c-c11a-4e4d-a007-f4890aef539a |  | checkpoint | Confirm mesh secured to doors and penetrations
checkpoint-status | 602e5102-a2c7-48ce-a2b2-55517769da91 |  | checkpoint | Signage in place
checkpoint-status | c4d174be-b873-4012-a3a1-2f891599555f |  | checkpoint | Screens and mesh infills are in place and secure
checkpoint-status | 4b8f64eb-693d-4037-83c3-edaf08e62d5f |  | checkpoint | Loose materials are stacked and secure each day
checkpoint-status | 63a7c859-489f-47d9-b6d6-04291c9812e4 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 6dabe77d-b63a-4086-a876-0ab112b21775 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 6d713c51-05d4-46bb-81f5-04fcca6e0d8b |  | checkpoint | Loads on platforms not exceeded
checkpoint-status | df4de61a-aedb-41b5-9239-4cf9d4c556f6 |  | checkpoint | Ladders available and secured
checkpoint-status | e7887a18-f83f-4097-9275-d69773f9d099 |  | checkpoint | Access is clear and marked
checkpoint-status | 21a72b6e-5b2f-407c-a2a9-5b91c1ddb044 |  | checkpoint | Power Board connected
checkpoint-status | 47186d12-c254-43f5-bc69-d9f11bdd928d |  | checkpoint | Confirm ready for lift with all involved - Team Leaders
checklist-flat | 50904041-285b-406b-9d21-257cee5c7aad |  | checklist | Site Diary |  |  |  |  | Yes | Site Diary | 2b2eb83b-36db-47f1-bc16-cdc25ee91d78
checkpoint-status | 0e05d06d-81b1-4e19-b176-588b4129983f |  | checkpoint | Areas of work accessible for the day
select | b06f0f69-00f6-5ead-9706-c79811533df3 |  | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | fb22b6e9-53f3-571e-9d98-cdcd220f42e0 |  | textbox | Date
text | 92e22407-6431-52b9-80b7-c33c67673121 |  | textbox | Year
text | 83c10f8c-e5e7-5ad5-96c8-97a7edcf44cb |  | textbox | Number of workers on site
text | 1bda683e-5325-5875-9737-9ff3ee6abb48 |  | textbox | HSR on site today enter name
text | 3379c77e-89da-5766-a440-38686f653ead |  | textbox | First Aider on site today enter name
text | fe70f0b4-b2f0-5d04-bf92-db49fce7e66c |  | textbox | Injury on site today enter name
checkpoint-no-status | 00163d2a-711c-4fb4-bfb9-a1893c500c6a |  | checkpoint | Work area 1 details entered
text | 00b1f9d7-6be6-59f6-9be0-57b5054dc8e6 |  | textbox | Area
select | 88fb2cc6-772e-5242-99db-6758e9d28300 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 32353fb8-182e-5717-a863-76efbfb9ff9e |  | textbox | Comments
checkpoint-no-status | 4883e8ff-5a3e-4fb5-854f-bfe1438bdd71 |  | checkpoint | Work area 2 details entered
text | 38196250-2100-587b-ae96-393597776f95 |  | textbox | Area
select | 057cb05a-5261-5488-91ac-6001d06bb7c5 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 1431a06b-2fd8-5799-9457-25a3c6ea5866 |  | textbox | Comments
checkpoint-no-status | a7b8df71-8e6e-43fd-8ea6-1056bbe168b8 |  | checkpoint | Work area 3 details entered
text | 1d214007-282b-523f-8859-956ce59bd0e1 |  | textbox | Area
select | 43dbe32f-629f-58e7-84c2-3fd2e6e3de3b |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 5b0db666-e1d1-50af-b71f-202ee228d354 |  | textbox | Comments
checkpoint-no-status | e8cb941f-a438-4b02-bec8-4cd8fc7dabae |  | checkpoint | Work area 4 details entered
text | e725815e-8b78-54d5-8e35-e058565c41f4 |  | textbox | Area
select | 2fc61c7e-3486-505c-bec7-987179f7e7b1 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 4ed1c02c-9ca4-572b-b509-0d2c8a40a742 |  | textbox | Comments
checkpoint-no-status | 45884c03-7e5f-4b90-85dd-4b846936d61d |  | checkpoint | Work area 5 details entered
text | c912a636-41bc-559e-ae3a-3a9e6f973257 |  | textbox | Area
select | 8724f978-bc3c-5cd3-b852-7e2e4a6a2c33 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 9d74ef12-3baf-5c48-9428-a10b314802d4 |  | textbox | Comments
checkpoint-no-status | d5646f38-ebbd-4960-8c49-f851561dfee6 |  | checkpoint | Work area 6 details entered
text | 56d2bdbd-ab6c-5e6e-8fb2-8bee2de30551 |  | textbox | Area
select | 88779ddf-39e4-50cd-a4d8-22d007cf3928 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | d469c6ca-e0f9-55df-b302-4a61e55b0ee2 |  | textbox | Comments
checkpoint-no-status | 7c8b571b-57c7-45df-97e4-d14bd23f383b |  | checkpoint | Work area 7 details entered
text | bb0b8a0b-084d-563c-a72a-c5e88a28c0a3 |  | textbox | Area
select | 150ceac7-26d3-5eb7-a340-4112883dadf1 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | c1cb452a-55bc-5675-bba4-c77958edf408 |  | textbox | Other
checkpoint-no-status | 4a1996de-a7ee-4f59-bc37-970685babf24 |  | checkpoint | Work area 8 details entered
text | 0c15f1a5-e7e9-599d-8f26-1cbfdcf8ca01 |  | textbox | Area
select | b1c0dff8-66fa-5a67-90de-8a839c83f938 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 55338b6e-9c71-5576-94dd-44f5a5d77a3f |  | textbox | Comments
checkpoint-no-status | 5ba55681-9d4a-48f3-9dc1-235d1ce59544 |  | checkpoint | Weather conditions entered
select | 6a1ecaaf-ea0c-50ac-80bd-53cf95c71b62 |  | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | f491c210-aea0-5985-92ce-12c6d907344d |  | textbox | Min temp predicted
text | 1c316b66-3678-5d6d-bb62-206fa40e2e8a |  | textbox | Max temp predicted
checkpoint-no-status | 5859fec3-25e7-4729-a93e-cdfa70f1c4d2 |  | checkpoint | Delays from inclemency
text | 93b8d544-1433-53d8-8215-b2e1a2792767 |  | textbox | Total Hours of delay
select | 8483bac4-27d0-564f-8709-aeef801fea1f |  | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | b5364654-f44d-4acd-897a-ef118676cdfb |  | checkpoint | Delays from Builders or Others
text | c43eab40-b0f2-5b08-9fe0-c6d68fe4e551 |  | textbox | Total Hours of delay
select | 9909b08f-2bdd-59d2-b6fe-8541157d3e83 |  | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist-sectioned | 25bde00c-e68b-4c54-9fa5-5ccaed9d67c8 |  | checklist | Screens |  |  |  |  | Yes | Screens | 4af1e8c5-ac62-4e5e-848b-99f50cc86311
checkpoint-group | c9f5c570-6867-4274-a63d-60baf9205877 |  | section | Pre Lift
checkpoint-status | d81af3b3-7986-4e67-a589-3c5e0bc05902 |  | checkpoint | Area accessible & ready
text | de508add-fe97-511e-ad39-f6a1e193f518 |  | textbox | Screen number
checkpoint-status | 9f4862c3-ced0-49ee-be9b-0a0081717052 |  | checkpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 47afdce2-69d7-4b00-91e9-1ab2bb78b497 |  | checkpoint | Signage in place
checkpoint-status | 2e703dc2-2ce4-4f56-92a4-1a676ef39df7 |  | checkpoint | Exclusion Zone with name and number of supervisor– Ground level and Slab level
checkpoint-status | 39a04895-696e-4dea-a006-a2f318ef3fb3 |  | checkpoint | Spotters in place
checkpoint-status | 264016a0-5e9d-4c60-a89b-87d7ef6c77fd |  | checkpoint | WMS ready and signed on to
checkpoint-status | ce2666b0-c91a-488b-8220-551235c72c11 |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 9f003e3b-623e-4d4c-b0ad-38029658abda |  | checkpoint | All loose materials removed from edge
checkpoint-status | 14b27158-792d-4ea2-8ff4-6cf181418974 |  | checkpoint | Edge protection installed on Level/s to be exposed once lifted
checkpoint-status | b013088e-5ab4-487c-a599-722594388485 |  | checkpoint | Deflector shields removed
checkpoint-status | f50c7ea6-4bf7-4000-a43d-1b8f0dbb7899 |  | checkpoint | Radio communication woking between screen crew
checkpoint-status | e865c5ff-09a9-43bd-a949-8f5a8edeaa52 |  | checkpoint | Hydraulic lifting Apparatus installed correctly if using lifter
checkpoint-status | 56106757-9b1e-4c87-a461-cb20f87588da |  | checkpoint | Screen Free from Debris
checkpoint-status | 3c1941ab-c21c-42fe-a12c-9bdf4348e33d |  | checkpoint | All wire infills detached
checkpoint-status | 96ac1ad2-0698-4df2-94b3-cda919b8466c |  | checkpoint | Confirm ready for lift with all involved - Team Leader
checkpoint-status | 4d1c9946-1a0b-431c-987f-f7fe6798311a |  | checkpoint | Work at heights permit completed - attach or take photo of permit
checkpoint-group | 67c6f022-ebea-4eac-896f-88a02e3e91d3 |  | section | Post Lift
checkpoint-status | d0d8fadf-81ca-44bc-a4b2-fb8fbf0bd670 |  | checkpoint | Ensure all gaps are closed
checkpoint-status | d311e143-8f4d-4290-9e61-4b7d15424052 |  | checkpoint | Mesh to be install where required
checkpoint-status | d3d4bd3a-4419-4ecc-9b9c-8efa073b6764 |  | checkpoint | Double check all needles are secure and double nuts in place
checkpoint-status | 49ba07bf-468d-4d1f-914f-b17448b30a9a |  | checkpoint | Clean and clear area
checkpoint-status | 31bfbf28-f7e9-4141-ae3d-c1c36a221758 |  | checkpoint | Remove exclusion zones and barricades
checkpoint-status | eed6cff8-0e14-4a98-a274-876050bc3af8 |  | checkpoint | Bar caps for protruding z bars
checklist-flat | 7daa7c42-b9eb-46be-a516-76dc6e8f827c |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Toolbox Meeting | 5cf70d38-4213-4189-8fae-6fb1d30bbb18
checkpoint-status | 1dafbab3-24e3-47bd-bd2f-04b61ab4616b |  | checkpoint | Toolbox signed off - Attach an forms
text | 88728194-79ad-5a71-8d3f-48042ab55106 |  | textbox | Work area
text | b10e8ac9-55aa-5422-abc6-f2ef8b8c611d |  | textbox | Supervisor
text | a1b76d16-b3b4-5997-929a-79c372104f8d |  | textbox | Date
text | f35b17f2-be54-5edf-a5dc-537bf814be01 |  | textbox | Time am / pm
text | a9fd8a6e-e3ec-578c-9f3e-893ca44e933f |  | textbox | Actions from last meeting
text | 7eb70c9b-2cb1-5aea-b419-27d15dc946a6 |  | textbox | Injuries last week
text | fdb7fda7-79bf-51b2-be0c-d99dc8dce9f2 |  | textbox | Near misses last week
text | f150d728-dd94-5f7f-8975-400108ad786f |  | textbox | Safety Items discussed
text | 34ed1812-73a2-5aca-9256-790ad623b2c8 |  | textbox | Comments from the floor
text | cc569ebc-ba8a-5293-95cb-cd621ba5626a |  | textbox | New business
text | 5ef18e6d-8090-5b6d-a46d-48b3bb756b6d |  | textbox | Attendees
checkpoint-status | fb61a5c9-a896-4901-b216-0ea6a0ba2fc0 |  | checkpoint | Attendance verified
checklist-flat | 45353e4a-7337-4877-b7b6-1bc2e0672ebb |  | checklist | Weekly Labour Hire Control |  |  |  |  | Yes | Weekly Labour Hire Control | 6e252318-b25c-47e2-acbe-56d8814cbad8
checkpoint-status | 1b2ad7e1-ac54-4d23-aa49-1a34cae00e23 |  | checkpoint | Tuesday
text | 4789f9ce-e72b-5b6a-b253-43cb8168bbd1 |  | textbox | Date
text | a726a51b-64d6-5c2e-8ecc-1e0bd31c752c |  | textbox | General Comments
checkpoint-status | a438b8a1-2cc7-4c46-b6aa-1734cca7c13f |  | checkpoint | Wednesday
text | 8b5f7802-686c-5a37-9704-a073d0176263 |  | textbox | Date
text | 18e69dee-e856-5eee-a685-90d131ced27d |  | textbox | General Comments
checkpoint-status | 487f33c0-b125-4d5b-8fe4-917fb81e5ee3 |  | checkpoint | Thursday
text | f9934c09-401b-57c0-a4d1-f8f25bbb2b73 |  | textbox | Date
text | dc008c4a-0f17-598a-ac50-024034d0bd71 |  | textbox | General Comments
checkpoint-status | 442b8407-736c-4439-a4ee-51371b28b0b6 |  | checkpoint | Friday
text | 71ab73f1-2681-5e7f-ba0a-080c898ef9d1 |  | textbox | Date
text | ccf6c910-514f-5f1e-9b21-5fd731fb342a |  | textbox | General Comments
checkpoint-status | 35325450-8db2-44cd-88a6-6bf60c255a5d |  | checkpoint | Saturday
text | 81f977e0-b038-5eac-b2bd-7f7f3361d691 |  | textbox | Date
text | dee44996-51d3-554b-983a-2f70b9e0fa11 |  | textbox | General Comments
checkpoint-status | 3cde2797-b5ef-4a14-8eee-31a9b08af618 |  | checkpoint | Monday
text | ec38d5ae-b48a-50c5-a9d7-549b3f4042d6 |  | textbox | Date
text | 5a2c3bad-9ffe-5f72-8d68-a5c30d2cd87d |  | textbox | General Comments
checkpoint-status | 45cd816f-ee79-4920-8151-e54b8face2a6 |  | checkpoint | Tuesday
text | 4b2122c5-fdf7-5fdb-950e-0a1922fde037 |  | textbox | Date
text | cfdeef05-134f-5a31-a424-2ffdb647f360 |  | textbox | General Comments
checkpoint-status | 526bbc22-dc68-4472-b691-2ab0556ac0d7 |  | checkpoint | Please Attach Time Sheet
holdpoint | f035939f-b83f-462e-be15-5ff12efed340 |  | signoff | Client Confirmation Signature
checklist-sectioned | 7ca7b413-d36a-4e69-b6c1-2fdd533a7694 |  | checklist | Core Lids Checklist |  |  |  |  | Yes | Core Lids Checklist | 73975c9a-06d7-4074-8a98-168d585577a3
checkpoint-group | 1102938d-3fe4-4990-83a8-55b028c97380 |  | section | Phase 1
checkpoint-status | cba04ef3-a1fa-4631-95a7-ab7c8a94b338 |  | checkpoint | Area accessible & ready
checkpoint-status | 02fbe395-2df1-4a21-b2ba-8b9195ed8b15 |  | checkpoint | Drawing references entered
text | 88fba8fb-dcbb-5dbb-91b2-dfa586b01297 |  | textbox | Architectural
text | 87803838-793d-543a-9bf8-60d332498db4 |  | textbox | Structural
text | dd18cd5e-6d65-5af4-895d-c032486bffe1 |  | textbox | Other
checkpoint-status | e5603959-94ac-427b-be81-e80068c9312b |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 53449631-15d9-40f9-982f-9b851d469238 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | 96e99a09-4469-42ee-b209-90e03091cb19 |  | checkpoint | Grids marked by builder
checkpoint-status | 70bd037b-a0ce-4dbd-9fc9-4c1457f4826f |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 943d1889-4d52-433b-abef-a3c0eb316aea |  | checkpoint | Fillet & drip mould installed
checkpoint-status | e33c79c1-e182-4392-85ef-6ca6a3d70c51 |  | checkpoint | Check set down position & RL
checkpoint-status | 81466309-2e84-4565-b736-1a0c89fb7700 |  | checkpoint | Check penetrations installed
checkpoint-status | 2c8fd8d9-e67d-4b7e-9e94-667453bb42fb |  | checkpoint | Column blockouts installed
checkpoint-group | b276a311-e7d5-4306-92f6-c0b1fe66c79c |  | section | Phase 2
checkpoint-status | 5f0c5567-4a84-4346-a8f9-36a56385f5e1 |  | checkpoint | Check back propping as per design
checkpoint-status | d687eb26-7a19-46eb-95e2-34e1582dc86b |  | checkpoint | Blow off deck
holdpoint | bfc5db5d-074e-4d60-b033-5ec45bc1379e |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 338b5307-0761-42c3-b4de-eef75af5bca5 |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | 39a5ac76-e5bf-41fc-b183-26409cac6136 |  | checkpoint | Correct Class of Finish
checkpoint-status | 79e93a65-1a05-442c-a24c-a195bff9fc31 |  | checkpoint | Stripping, cleaning & materials removed
checklist-flat | 10ad3ad7-3636-4a2f-8db3-eaff5affab66 |  | checklist | Injury Form |  |  |  |  | Yes | Injury Form | 785edb6f-ba50-4fbb-92ad-518a4f8591a4
checkpoint-status | 49fde0dd-1832-46a3-a8d2-870bef8a8a41 |  | checkpoint | Injury form completed
text | fa64d857-d141-57ac-936c-1b77f861f61f |  | textbox | Date of incident
text | 951ca7c2-1f9d-5a97-aa60-8d105c116156 |  | textbox | Time
text | 9681b080-540e-5092-a2b1-1b182936abf9 |  | textbox | Site location of the accident / incident
text | e25153b4-3a96-511d-b1b7-014f5705d517 |  | textbox | Detail of how the accident / incident happened
label | 4a73ecff-b021-575e-8163-eadde89622c9 |  | note | Details of injured person
text | dae72c08-63b5-5e53-ac30-869a0eae06db |  | textbox | First name
text | fb635cfa-b95e-56ce-b2e1-ae06436518ac |  | textbox | Last name
text | a4a87b83-abbf-5bd1-8318-abb7b8cf9136 |  | textbox | DOB
text | e6fd13c0-dea5-5e78-9624-e50fd5fa647f |  | textbox | Contact No
text | 03fb3be6-25cc-5dea-84f3-3fff5e20a126 |  | textbox | Address
text | 33c07d4b-0494-5b58-95fc-a2f752b5aa7c |  | textbox | Company
text | 42ec0339-b8d7-5160-a023-315e27fa8464 |  | textbox | Trade
text | 4bb99da3-d472-568a-a338-6a86eb2ba1f5 |  | textbox | Date Inducted
select | 790ba309-32cd-5cfa-8cfa-22f2bb055001 |  | dropdown | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
select | 3721d053-cd3f-5114-804d-5dad094698c9 |  | dropdown | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
select | 32473e28-5514-5e78-817a-05997f236290 |  | dropdown | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
text | 3204e41f-91ea-5f01-9018-47e192217d89 |  | textbox | Initial treatment given
text | 4205ee24-99b6-5b42-abd2-d57c2d809cb5 |  | textbox | Was follow up treatment provided
text | 952bf7b6-0ba0-50dc-af2d-88d36587e97f |  | textbox | Medical centre / Doctor / Hospital attended
text | 9ecf770b-98e4-5795-91af-598c3e2d139e |  | textbox | Date / time attended
button | cbb71ce2-6c01-5722-ad75-b4cbbb551fbc |  | button | Regulator notified | Yes, No
label | 8ed02a1f-4081-5bb7-b3a9-9d70b486de5c |  | note | Witness details
text | 1a6d7db7-8b38-5d20-8150-45f3a372a4f4 |  | textbox | Witness name & contact details
text | a333a051-b84c-5ee5-86cf-408215806b8b |  | textbox | Witness name & contact details
select | 11d9993a-24ae-5b07-a45d-076396cc1b4a |  | dropdown | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
text | 7e36e07c-267a-59dc-8851-833735b6e72c |  | textbox | Other
label | 53efdcaf-55e7-50bc-8cf1-bb52cc35aad7 |  | note | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
checkpoint-status | 93705cca-fbce-4866-ae06-682c007818da |  | checkpoint | Signature of injured worker
checkpoint-status | b94dbae7-db88-4429-97c6-cb0d6cae5f7b |  | checkpoint | Person completing this form
checklist-flat | 2548d2b4-4b3e-424c-bdf7-3f0cc75a2946 |  | checklist | Columns Checklist |  |  |  |  | Yes | Columns Checklist | 7be37b06-6185-41f9-b32c-6c99b1eb5c43
checkpoint-status | 799ddeb7-09c7-4630-837d-d6111e258b93 |  | checkpoint | Area accessible & ready
checkpoint-status | 00884b25-4074-480a-92c8-7eba5e625d98 |  | checkpoint | Drawing references entered
text | 2387bc5f-48bb-5895-9efa-d6b17a627a96 |  | textbox | Architectural
text | a4b12480-52f3-506e-ae48-644e3c6ea4f6 |  | textbox | Structural
text | 35b29bab-01db-56ea-b311-7d9ee04f5329 |  | textbox | Other
text | dfd50382-29cb-5006-9847-56fac96cc4b7 |  | textbox | Column No
checkpoint-status | d5de6705-066b-4a78-a653-b69463c3a190 |  | checkpoint | Current plans in use / Latest drawings checked and referenced
checkpoint-status | 59fd10ec-a457-48aa-8caa-de8aededbaff |  | checkpoint | Survey points given for 2 points
checkpoint-status | 3ae34abb-4589-4573-b30c-ab51e830e4b2 |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status | 853e9731-017e-434e-b779-f98bbd604626 |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint | df971efb-e0a9-483f-af06-b2a20f19cbb4 |  | signoff | Inspection from site engineer
checkpoint-status | 2cecc855-827b-457c-9db1-3aac973cf29a |  | checkpoint | Column box cleaned & oiled
checkpoint-status | a80d051a-deb2-4d85-ac21-03301513d8a2 |  | checkpoint | Placement of column box over cage
checkpoint-status | bb96edab-addd-4cc4-870c-9e75624bf721 |  | checkpoint | Bracing props secured
checkpoint-status | 32a2d597-56eb-46e8-806c-579157fe49c1 |  | checkpoint | Column plumbed
checkpoint-status | 06c6ae79-e86f-4662-89d6-315185f4be1c |  | checkpoint | Correct class of finish
checklist-flat | bab4b7ed-a559-43b2-a0e3-6d324dcd6496 |  | checklist | Variation / Site Instruction |  |  |  |  | Yes | Variation / Site Instruction | 98e7e6fc-0a54-4cf2-b8ed-19ce860e596e
checkpoint-status | 1b2fd3d6-024b-4ed6-9ae7-4e3350f1d3c4 |  | checkpoint | Variation / SI Details Entered
label | 4abb0d56-cee4-5259-84d4-c4f640e6bca6 |  | note | Please take before photos
radio | 16f7a902-e56c-504e-94c1-19f7afbec248 |  | radio | Work type: | Site Instruction, Variation Work
text | a19659f1-52fa-585b-b9cb-f0febf52f745 |  | textbox | Attention:
text | 0f18477f-c35e-530a-a232-5ece762aca19 |  | textbox | Area/Location
text | bbee3a5c-a7e3-5480-9643-cb5340a074d6 |  | textbox | Date
text | 66c861c8-4cd8-5244-b6e0-2fa0152443af |  | textbox | Scope of work
text | 23954ba6-bd80-5d7e-8ea7-87a116d835bd |  | textbox | Normal Hours
text | 2d0df80f-8dcb-55f5-b424-6b4eaad289f0 |  | textbox | Overtime Hours
text | fca7876a-d1e3-5dbc-acd7-1b520849f108 |  | textbox | Material to complete task
checkpoint-status | 351f124a-8042-4a1a-9c83-d75f29a70c01 |  | checkpoint | Reference/SI Number Entered
text | 93977b49-035c-56f0-b2fc-b45e227018ef |  | textbox | Reference/SI Number
checkpoint-status | 6cac8a4d-7f57-4db4-8f1a-aa0a8626e725 |  | checkpoint | Variation / SI Work Completed
checkpoint-status | 61649388-c84f-4682-b9dd-9fa68d0031ee |  | checkpoint | Values added (Office use only)
text | c9b35c11-d62d-597a-8d95-73d2ba7de150 |  | textbox | Labour Value
text | 714f591d-074c-5e25-897a-e74bc7401cf7 |  | textbox | Material Value
text | ad5dfd3c-c0d6-5c5a-bf7c-299b9b85025a |  | textbox | Measured Items
text | 4ba7e92e-0c2b-50e2-9cbd-72ac449b5241 |  | textbox | Total Variation Value
checklist-sectioned | 33ad0949-478b-4a22-9a73-16241e80a0eb |  | checklist | Stairs (in-situ) Checklist |  |  |  |  | Yes | Stairs (in-situ) Checklist | 99f54a08-799e-4ffb-80b4-84ffa8ed41d9
checkpoint-group | d404413a-916a-4704-9f87-c76ad2b09353 |  | section | Phase 1
checkpoint-status | 376ce375-7a44-4c75-8823-567ea774a29d |  | checkpoint | Area accessible & ready
checkpoint-status | 71d6874e-9b7e-4516-bab7-cd0ca6c4725e |  | checkpoint | Drawing references entered
text | 8d7dc3c0-851d-5279-9de2-5dd9267cf5d1 |  | textbox | Architectural
text | c64055b3-15a1-5ff1-ae37-dd291517fd87 |  | textbox | Structural
text | 598877c6-5f82-5d1b-ab8b-1964dc74863a |  | textbox | Other
checkpoint-status | d20932a2-5ac8-4268-917d-35d03cb52936 |  | checkpoint | Current plans in use
checkpoint-status | 4b8039af-f022-4b4f-ac4f-2a702931eec2 |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | aa85a7ae-2d75-476a-8b27-fb0c4539b6bf |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 9cb5c0f3-cbea-4e19-b644-2ed4da8762e7 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 35003060-65a0-447e-88ae-80e3492535ab |  | checkpoint | Base of stairs cleaned
checkpoint-status | 63a4f3a7-5cdf-4413-bf60-cb56dc85f3a9 |  | checkpoint | Riser heights confirmed
checkpoint-status | fb015f17-15cd-4749-8500-977cb8f8c4cc |  | checkpoint | Going lengths confirmed
checkpoint-status | 4fde085e-565a-4be2-8716-50a7599944da |  | checkpoint | Correct Class of Finish
checkpoint-group | 323ff40f-425d-450f-947f-7df37d43c00e |  | section | Phase 2
checkpoint-status | 390b1c88-f968-4f82-95fa-31117c47de4d |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | e824fce2-6808-4d0a-bed4-045eca299fa2 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 5bad577f-9f3f-4f52-9fe2-70243e66a898 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 9d92570e-43a0-4f48-8007-d247f1f095ec |  | checkpoint | Riser heights confirmed
checkpoint-status | a925a7e8-645e-42ea-a237-2e247d48efed |  | checkpoint | Going lengths confirmed
checkpoint-status | e3202374-6c15-4a7f-9322-4434ad1b411a |  | checkpoint | Correct Class of Finish
checklist-flat | 52e936f1-a89e-4a41-80c8-04d0df3ba901 |  | checklist | Walls Checklist |  |  |  |  | Yes | Walls Checklist | 9a8be8e4-e6c9-42ae-b5be-31d979328c03
checkpoint-status | 6fd8ae3c-f6df-448a-a35b-0bed3d5cf998 |  | checkpoint | Area accessible & ready
checkpoint-status | efc30749-cbad-4150-bb5a-f65f2f4cf686 |  | checkpoint | Drawing references entered
text | 98e4468a-d680-5b25-a7f3-b044a2d1eb64 |  | textbox | Architectural
text | cffd7903-d2ee-533f-a445-d39e931f6a21 |  | textbox | Structural
text | 8f7f1fca-469d-5b84-89d5-483e3003250c |  | textbox | Other
checkpoint-status | c7ba4527-e57e-4eeb-87af-c4b1c32164d3 |  | checkpoint | Current plans in use
checkpoint-status | d3222772-859e-4476-9647-f232d77bf06b |  | checkpoint | Survey points given for 2 points
checkpoint-status | 4b778ed9-afce-4212-9969-7493e4c91b4f |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status | d558c379-f315-406b-90d5-1a335be24187 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 19005ad2-22f8-4abd-a4b3-b67fb3511035 |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status | 310a54de-7476-4c3c-8d51-aa60a25b3c57 |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status | adbd5ac0-9932-4934-b9da-8a9deae12067 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | c5ce453c-ec2d-4df8-b848-d26a8a10a5fc |  | checkpoint | Base of walls cleaned
holdpoint | efafd0c1-c3d1-4922-8ba8-46430617b9c6 |  | signoff | Inspection by site engineer
checkpoint-status | 4b3877e2-f700-4e09-94c6-5ce3c56e2bdb |  | checkpoint | Closing shutter installed
checkpoint-status | 7df031ee-53fe-41f3-93eb-bfea62f0c846 |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status | 75b58d6b-66ed-4ab1-b015-e243dd6e9923 |  | checkpoint | Correct Class of Finish
checklist-sectioned | 90c47f2b-b88b-401b-9cf0-2d4e77ff57dd |  | checklist | Stairs Checklist |  |  |  |  | Yes | Stairs Checklist | c2f575f1-3a61-4512-9541-78c645d681b3
checkpoint-group | cd7451aa-05ad-4d01-92d0-0c5cd7bfb3fc |  | section | Phase 1
checkpoint-status | d4688d81-8e3d-4e81-b3c2-7d692f1587df |  | checkpoint | Area accessible & ready
checkpoint-status | 60c455fc-a7ee-485c-88e8-a438af975644 |  | checkpoint | Drawing references entered
text | 8faf627d-bc73-5547-8e6f-c5ced3e1aad1 |  | textbox | Architectural
text | 7eb44fce-f840-59fa-a074-cebbada8bf28 |  | textbox | Structural
text | 0f5cd90b-5d49-5194-a8f7-09e9217ba3d6 |  | textbox | Other
checkpoint-status | 739696a7-8e70-426d-853b-d12f883f0593 |  | checkpoint | Current plans in use
checkpoint-status | d042e123-ffe6-4ea4-abe2-66ed2b2e7153 |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | 1d1e44ba-f4d8-4805-80d0-cf01b32f64ec |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | b848f860-378c-419a-a7a8-f59de4ea66c5 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 706605d7-4db2-45b7-8276-ef6be6e1b12c |  | checkpoint | Base of stairs cleaned
checkpoint-status | e542812d-d437-47ba-97e4-7a2ea5cdddbc |  | checkpoint | Riser heights confirmed
checkpoint-status | bf4e9575-54ab-44f4-bbc3-142ddba37a42 |  | checkpoint | Going lengths confirmed
checkpoint-status | 1cfb20f3-f07f-49a9-bfa9-54caa92aae90 |  | checkpoint | Correct Class of Finish
checkpoint-group | 7bbbef3f-6f25-41d3-834e-01e1b29a7bf6 |  | section | Phase 2
checkpoint-status | 3f9c88be-4e19-4a5d-8887-b33c9060fdcc |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | a1a15de0-8627-4b4a-95d3-b90805f87565 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 1f30452a-c172-47a6-940f-922d19366413 |  | checkpoint | Base of stairs cleaned
checkpoint-status | dc85e584-d654-4bda-bff5-9d97b1f3343b |  | checkpoint | Riser heights confirmed
checkpoint-status | 5baaa859-5f43-44e8-bf3e-33dbb9be6cb4 |  | checkpoint | Going lengths confirmed
checkpoint-status | d4050b4a-5745-4079-9f8d-48a5b4597863 |  | checkpoint | Correct Class of Finish
checklist-flat | 6b4a504d-abdf-498d-9b1a-4c81d1300211 |  | checklist | Deck Handover |  |  |  |  | Yes | Deck Handover | c422c5a7-9e6f-4d3b-811b-ec1db45649ff
checkpoint-status | b9e1d85e-1fc2-4385-a505-2f086173f2bd |  | checkpoint | Communication between all trades
checkpoint-status | e081d9ba-b630-43e2-80d1-dfe2c1c877d5 |  | checkpoint | Signage and barricades in place
checkpoint-status | dd9bc217-ec71-4c0c-b302-6f9b407bfa4a |  | checkpoint | Deck clean and clear of materials
checkpoint-status | 5bc9f80f-a9af-4fe2-ae65-5c8641dffaee |  | checkpoint | Loose materials are stacked and secure
checkpoint-status | aacdb401-1c5b-42d0-a22b-62af796313f2 |  | checkpoint | Any backpropping required to handle loads of reo and other equipment
checkpoint-status | 3eff61d8-5fd7-4c80-8f23-6b5c9455546a |  | checkpoint | Designated walkways established
checkpoint-status | 016883ef-f046-44d4-8cf6-7efc40801e19 |  | checkpoint | All loose materials removed from edge
checkpoint-status | fc6929dd-0f3e-487e-96f2-9224af10509a |  | checkpoint | Are all penetrations covered and secured
checkpoint-status | 527810aa-9acb-47ab-83a4-f41ebd5c5274 |  | checkpoint | Rubbish bin on Deck
checkpoint-status | 6fd27a4d-002f-4e60-ba92-fb4eb226e419 |  | checkpoint | Perimeter Screens / Edge protection installed
checkpoint-status | 4a52aa88-a04f-43bf-bbaa-f8cc2441884a |  | checkpoint | Correct spacing of frames, props and timbers
checkpoint-status | 03ee8706-3013-4c5a-96bb-a1f437b16f48 |  | checkpoint | Correct joist and bearer sizes
checkpoint-status | 107eb357-bc52-4771-97cb-97579f30915e |  | checkpoint | Acceptable jack extensions
checkpoint-status | b0b9b2dd-641e-4fca-8c35-efb45e0db5ba |  | checkpoint | Quality of materials
checkpoint-status | e0053338-3dfa-4ecd-bb58-28097ea62a12 |  | checkpoint | Adequate bracing to ensure stability
holdpoint | 2a371c08-67f7-4fc5-b1e1-d4ed2e89426f |  | signoff | Deck Handover signed off
checklist-flat | fcf5a6f7-d88f-433b-ae8a-f0104c5a5161 |  | checklist | S.O.G Checklist |  |  |  |  | Yes | S.O.G Checklist | c75e15a9-46db-480d-9bc1-777ce7f06803
checkpoint-status | 075dd6d2-2780-4fd2-ad35-1baf6bc545ab |  | checkpoint | Area accessible & ready
checkpoint-status | 6415c0a3-9471-4947-bfdb-e1168dc11440 |  | checkpoint | Drawing references entered
text | 159265ed-d408-5c1b-88d4-4f2fdac8deba |  | textbox | Architectural
text | c96dfa64-556d-5aa0-a891-c2c96adec8cf |  | textbox | Structural
text | 78bc1269-8987-5ec7-9ab1-76a4dda2cb11 |  | textbox | Other
checkpoint-status | 09aa81e7-4a66-44b6-b0fb-5800513fc006 |  | checkpoint | Current plans in use
checkpoint-status | 6a2d54c6-f369-43fb-8482-a78d66e381b2 |  | checkpoint | Survey points give for grids
checkpoint-status | 25ef03aa-9d01-4bab-9867-6869ee98c34e |  | checkpoint | Surveyors points given for edge boards
checkpoint-status | 3f06d677-ac1a-4858-840f-37c838c74d13 |  | checkpoint | Datum RL supplied by surveyor
checkpoint-status | ffc4d3c3-ed8c-405d-96fd-492bc3c1608d |  | checkpoint | Edge boards plumb & straight
checkpoint-status | 252fe5e5-a737-4b63-a89f-4326c8219a4d |  | checkpoint | Step downs secure & correct RL
checkpoint-status | 4053fd14-6e21-42f3-9dac-12ab340e2ec3 |  | checkpoint | Dowels installed on pour joins
checkpoint-status | 2834bc8d-f4ca-4e3b-bfcb-26da3b8ae0a9 |  | checkpoint | Column blockouts installed
checkpoint-status | a3186f0c-55a5-412d-b9d7-f772585c581f |  | checkpoint | Correct Class of Finish
checklist-flat | 2a453106-9474-4f13-86b5-072cdf4aeae8 |  | checklist | Progress Claim |  |  |  |  | Yes | Progress Claim Checklist - Tower 1 | d4c79c50-23e0-40aa-840c-70a013d57902
checkpoint-status | 730552f2-ab9d-4c51-9a4f-c80a5ef2955c |  | checkpoint | Please add Comments / Photos
select | 4e1623b0-3f3b-5e31-a0af-859cb29b0931 |  | dropdown | General | Site Establishment / Prefab, Systems, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning.
select | 76a7160e-0364-53e5-9376-098cf116880d |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | fa055e96-8615-57ad-916f-fcf0c4b8b3af |  | textbox | General Notes
checkpoint-status | d3235f58-0cf7-4cff-9e91-60572f8264d9 |  | checkpoint | Please add Comments / Photos
select | 87c94906-6d34-5478-8188-312d96413dd5 |  | dropdown | Level | Below SOG, SOG, Basement 3, Basement 2, Basement 1,Ground, Mezz, 1, 2, 3, 4 - 32, Roof Plant Deck
select | 0baea644-8a14-5b52-86e0-0ff53a7165de |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 2397f571-9e55-5d5e-bc29-a3e4a63f36d3 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 5617df55-3c99-50cb-8901-b458371de14a |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 3c3abdbe-3836-5142-9464-f459c8464121 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 332a687e-7db8-5801-baf5-ef9d833efc8a |  | textbox | General Notes
checkpoint-status | 576eeccf-8a6f-480a-abff-ccaa345f2693 |  | checkpoint | Please add Comments / Photos
select | d239b322-4106-5c43-9e54-5d5d146b925c |  | dropdown | Level | Below SOG, SOG, Basement 3, Basement 2, Basement 1,Ground, Mezz, 1, 2, 3, 4 - 32, Roof Plant Deck
select | 9c7c2db2-559e-5012-8099-3a58cb243d9e |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 8b989d21-3be7-526d-a3b0-8efae9bd4753 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 025f03cf-0bfb-59f4-8ea5-7c96815c1a89 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 75a04a5d-081e-5db8-a9f5-2cd880d816ae |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | d9692a7b-1fa3-5125-ab0a-800c6f04b810 |  | textbox | General Notes
checkpoint-status | 6417cb8c-174a-4624-8739-35da52394767 |  | checkpoint | Please add Comments / Photos
select | 442b6471-f1cb-5772-9717-1a569dfbe4bf |  | dropdown | Level | Below SOG, SOG, Basement 3, Basement 2, Basement 1,Ground, Mezz, 1, 2, 3, 4 - 32, Roof Plant Deck
select | f1a7a141-ba8e-541b-8c5f-2e2b09da3e45 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 619af8d9-9bd5-58a7-9d54-8baa16850aa3 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 93a1b224-0bf3-5d52-bec9-dff3caeae57c |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | b39260b4-da97-5779-91a2-5aa9a90b3cbb |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 733909f6-a54f-5a91-a3f3-7b33c192c66f |  | textbox | General Notes
checkpoint-status | 394f97ed-7a83-40f4-b3be-3b66ee3f6de0 |  | checkpoint | Please add Comments / Photos
select | 12cf73b0-ae76-561d-a935-b84b26f1b938 |  | dropdown | Level | Below SOG, SOG, Basement 3, Basement 2, Basement 1,Ground, Mezz, 1, 2, 3, 4 - 32, Roof Plant Deck
select | 9c036221-b9a2-5b7c-b30c-84d769742ad1 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | b8e8e896-c74b-548b-8b60-d4b426431d5f |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | 30823953-73c4-5602-8ebb-67dc8a9dda63 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | b5e4063e-2c91-5ce8-8ec3-901a3e934733 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 0c544a63-ec39-51c4-b98c-c409d64d9345 |  | textbox | General Notes
checkpoint-status | 34aed5a5-723b-454b-9295-0235e659e787 |  | checkpoint | Please add Comments / Photos
select | 8dd5f749-fad2-58f0-903d-b3919a0952cc |  | dropdown | Level | Below SOG, SOG, Basement 3, Basement 2, Basement 1,Ground, Mezz, 1, 2, 3, 4 - 32, Roof Plant Deck
select | 555c9ea3-aed4-5791-bb4c-4d65ad6dee94 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | 650d509b-f7db-5e69-81da-a95ff37b9596 |  | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | de683465-cff1-5def-9a43-59db240d7d01 |  | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | f90f2edb-18ce-524d-8cab-a8923b57b115 |  | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | 65f53afe-4ee1-5b4f-aa12-d0545dee9a20 |  | textbox | General Notes
checkpoint-status | ad4753de-4386-44e7-8cb1-6eac4e250fb9 |  | checkpoint | Please add Comments / Photos
select | 121409dd-df4f-53b4-890e-c8bebe0dec80 |  | dropdown | Level | Below SOG, SOG, Basement 3, Basement 2, Basement 1,Ground, Mezz, 1, 2, 3, 4 - 32, Roof Plant Deck
select | b2e977aa-41a6-587c-bdcd-d920b4817951 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | d95040c0-9832-5c26-8319-ce1e5726f36d |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | e651625c-2edc-5270-bb46-0fa4cdac6870 |  | textbox | General Notes
checkpoint-status | ef46b32c-d526-484f-a4cd-fe7505bf1ff5 |  | checkpoint | Please add Comments / Photos
select | 512fb24a-e13c-599b-b1de-fc2134d875fd |  | dropdown | Level | Below SOG, SOG, Basement 3, Basement 2, Basement 1,Ground, Mezz, 1, 2, 3, 4 - 32, Roof Plant Deck
select | f714acb0-7878-5a9c-9dca-ce73b230d3b2 |  | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
select | b77e27ba-e20e-58b9-abb8-61965e323801 |  | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | c068b3f0-f5aa-572e-9cb2-187d659044a5 |  | textbox | General Notes
checklist-flat | f3d02536-de92-40af-b7e6-c16fd8601f99 |  | checklist | Daily Pre Start |  |  |  |  | Yes | Daily Pre Start | d9796ab1-4ae1-4d8a-9acd-a5fff491299b
checkpoint-status | 73b222ab-7c2a-4d52-83ca-95ca8184aca7 |  | checkpoint | Daily pre start meeting completed
text | bd6972e4-e22c-52af-b6be-ffc1ad237345 |  | textbox | Date
text | 48ad71bf-614d-53e9-b7cd-723ed8819b8f |  | textbox | Time
text | 521c25ed-f181-5a6b-bc5a-9017a2202d59 |  | textbox | Location
text | 715a8c61-e68f-5e9d-a102-3a238e9276ab |  | textbox | Supervisor / meeting leader
text | a7f87d7e-6853-5bf3-a402-182abdafd84c |  | textbox | Project Manager & Construction Supervisor attending
select | bce4bd5c-8fb0-5a82-9298-5f15585623f1 |  | dropdown | Current weather | Rain, Wind
text | c296fa45-8ecc-5092-b451-7e45443ca3d8 |  | textbox | Temp
select | 00d1e212-093a-514f-9999-4faece3bb7ec |  | dropdown | Forecast | Rain, Wind
text | 233e2e93-62cf-5970-8dac-432bcc647bb2 |  | textbox | Temp
button | ae0939e8-5c41-58e5-99aa-493f068104c9 |  | button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
button | 9517e3a4-b565-51e3-b5b3-40e824ef4fdc |  | button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
text | df69c607-ad82-521f-96ba-df1906347847 |  | textbox | Any issues from the previous day
button | 11279286-06b6-58a2-9e90-e6293fe23371 |  | button | Do you need to change SWMS | Yes, No
text | e99b0d9a-0727-56c3-b572-86efc039550d |  | textbox | First aiders on site today
text | 6a925889-9cf5-5c24-a3c4-6d92154f5f5d |  | textbox | Apprentice & who are they assigned to
text | 476b16a5-0fab-517e-9499-2dd9a6e69bba |  | textbox | Apprentice & who are they assigned to
text | 8bf0d9a6-d56b-5867-8950-b78ab5e7e7b5 |  | textbox | Apprentice & who are they assigned to
text | 6e92e418-2fd4-596e-b50f-29aaf003d4bf |  | textbox | Todays tasks / jobs
select | 1d923984-7034-5b34-bf3d-d5688abc000a |  | dropdown | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
button | a1461713-0634-5046-a920-8ee9a6a0bb50 |  | button | SWMS in place for all activities | Yes, No
button | 94fa8d71-23d1-5f69-84ad-68a6bb40ca96 |  | button | Hot works | Yes, No
button | 04eca232-1ce2-569d-bf21-90aa29e474a7 |  | button | Excavation | Yes, No
button | 07c7a680-ca7d-5c62-9773-09e4b982485b |  | button | Ladder | Yes, No
button | b05b4d05-c4b1-5b69-8de3-a44cb9790a99 |  | button | Core | Yes, No
button | d9ede5be-d323-5037-a1c0-ce1476ccd7c0 |  | button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
text | df121f48-4c61-5a3a-ad39-d1074423b2e7 |  | textbox | If yes, list the substances
text | 642939f0-7aa3-5d96-8cd7-2ee7d0ecf165 |  | textbox | Attendees
checklist-sectioned | 5141973f-a12b-48da-acff-5dbc3f68c8e6 |  | checklist | Hoist |  |  |  |  | Yes | Hoist | e02cd5fd-2bc4-4fe6-be68-9c1eb313a845
checkpoint-group | fd1b4eb8-716e-4d16-81bb-e5ec026af264 |  | section | Install
checkpoint-status | 5cfac240-2675-45fa-83cc-1806aea97ae9 |  | checkpoint | Area accessible & ready to receive hoist
text | 38998819-5949-5a85-8a6d-637934658372 |  | textbox | Hoist ID. Number
checkpoint-status | f93ca276-3703-42f8-b4e7-3932d7ec4ffd |  | checkpoint | Adequate Crane or Franna to install (heaviest lift required 4.5 tonne)
button | cb606995-4107-5425-a325-e42292f55d72 |  | button | Copy the Certificate of service and service history onsite | Yes, No
text | 9ad51bb2-5762-5742-8bdc-9f822ff22da7 |  | textbox | Name and Number of Rigger
checkpoint-status | dd6dd8df-cd57-45f4-bb9d-bb869c1638b2 |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
holdpoint | 04211cb3-5e4b-4d06-bd2a-0c54a1e7d06b |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | ab461de9-3e8e-4ca0-822e-15923f3b8485 |  | checkpoint | Scaffolder on site to assist in edge protection if required
checkpoint-status | 6a651cc8-b8dd-42ac-aa99-dcccb47ae7bd |  | checkpoint | Signage in place
button | a8318178-3435-56cd-ad67-b603141196c6 |  | button | 3 Phase power accessible and adequate circuit breaker 75 start Amps at power sorce | Yes, No
checkpoint-status | 854a275b-2e77-4175-9f9f-6bd23eecb375 |  | checkpoint | Exclusion Zone around required area
checkpoint-status | a4091698-0ca2-405d-8c93-dd4e0c3a3ca9 |  | checkpoint | WMS ready and signed on to
checkpoint-status | 8ee7f86f-8c05-4b60-8647-102f1c93604f |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | 63ba651a-9161-4d17-9431-c79bd6622d67 |  | checkpoint | All loose materials removed from edge
checkpoint-status | fa3cc23f-a99f-4bc5-a345-b7745675b8e5 |  | checkpoint | Gates installed
holdpoint | 928b4fdd-029a-48d5-8c61-c8fdd8740da4 |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | deab3a59-bfa2-49cf-bb40-3effef741cd7 |  | checkpoint | Log book for hoist is onsite and in good condition
button | d406fc34-12d3-5a5b-be57-e19ab9408ece |  | button | Copy of Bosform commissioning sheet on site and completed | Yes, No
checkpoint-group | dd5542fb-df9d-47b6-8eb3-e55787a54ffa |  | section | Hoist Jump and Dismantle
checkpoint-status | 2ce186f5-681e-4318-8b13-c33c91293f05 |  | checkpoint | Ensure exclusion zones are in place
checkpoint-status | b3bf23b5-8bd2-4300-a069-3e020aab82cc |  | checkpoint | Platforms cleaned and clear from rubbish
checkpoint-status | cab339b3-623b-40b2-a260-b2b185d33f75 |  | checkpoint | All loose materials removed from edge
text | a5d807db-8275-5db4-bf0b-26cceb712471 |  | textbox | Name and Number of Rigger
checkpoint-status | 00c3ec5f-cb57-42e8-8d23-ed8cf8c8612e |  | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
checkpoint-status | b5aeead2-6ccf-490d-94e2-716874bc8a63 |  | checkpoint | Scaffolder on site to assist in edge protection if required
text | c2a18d4c-4bec-592d-b244-f777e3340801 |  | textbox | Level Number to be Jumped to
checkpoint-status | c59e6129-47ce-4227-b286-5952eabed135 |  | checkpoint | Gates installed on Level/s to be exposed once lifted
holdpoint | b884a553-6836-4f8c-af67-592e366561e4 |  | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint-status | 82b9f5c2-3996-4592-be7e-7cddd1af3404 |  | checkpoint | Signage in place
button | c9fced8a-ad15-5526-95ce-01a015787a42 |  | button | Hoist Screen installed if required | Yes, No
holdpoint | 6370dc69-011f-4f37-becc-794464056067 |  | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint-status | 8e144d7a-cf6a-4c01-b4b1-d4e37cbec490 |  | checkpoint | Remove exclusion zones and barricades