## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP 003 Installation of Internal Partitions |  |  |  |  | Yes | ITP 003 Installation of Internal Partitions
checkpoint-group | Wall Framing
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Wall framing completed to Rondo designs, checked for square, plumb and twisting
label | Acceptance Criteria: 20mm clearance between the slab and the top track;slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Allowance for access panels and service penetration
label | Acceptance Criteria: Bridging Track supported by offcut studs
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | Acceptance Criteria: Jamb header or sill used correct components
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
holdpoint | HOLD POINT - Signed by Lendlease
checkpoint-status | Plywood Noggins and structural stud installed for all fixtures
label | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | Acceptance Criteria: Plumb, square and same height, core-filled
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
holdpoint | HOLD POINT - Signed by Lendlease
checkpoint-group | Wall Sheeting
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Caulking to acoustic / fire / smoke/ details.
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Penetration sheeted and sealed as per builder' drawings
label | Acceptance Criteria: Opening square and flush, fully sealed
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
holdpoint | HOLD POINT - Signed by Lendlease
checkpoint-status | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
holdpoint | HOLD POINT - Signed by Lendlease
checkpoint-status | Insulation completed as per acoustic report, partition plans and spec
label | Acceptance Criteria: As required Insulation, no gap can be seen
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Plywood Noggins and structural stud installed for all FFE
label | Acceptance Criteria: Checked against current RLS
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL2Internal Architectural Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Close wall
label | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Caulking to acoustic / fire / smoke/ details
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
holdpoint | HOLD POINT - Signed by Lendlease
checkpoint-status | Set and sand ready for painting
label | Acceptance Criteria: Meet Level 4 of finish requirement
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
holdpoint | HOLD POINT - Signed by Lendlease
checkpoint-status | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Siniat & Rondo Inspection
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
holdpoint | HOLD POINT - Signed by Lendlease
checklist-flat | ITP 008 Y-Junction Installation
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | In-filled fire-rating boards installed as per wall detail interface plan
label | Acceptance Criteria: The thickness and quantity used as specified as in drawing
label | References: Series:BR3ADL3 Wall & Partition Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | 15mm compressible backing rod installed as per wall detail interface plan
label | Acceptance Criteria: quantity used as specified as in drawing; sealant applies to all gaps
label | References: Series:BR3ADL3 Wall & Partition Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | The right junction is installed as per wall detail interface plan
label | Acceptance Criteria: Inspected and confirmed
label | References: Series:BR3ADL3 Wall & Partition Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Fully sealed joints to junctions
label | Acceptance Criteria: Continuous sealant applied to all exposed surfaces as in drawing
label | References: Series:BR3ADL3 Wall & Partition Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Installation of 3mm Flat Bar
label | Acceptance Criteria: as specified as in drawing
label | References: Series:BR3ADL3 Wall & Partition Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Setting Angle Beading
label | Acceptance Criteria: Inspected and confirmed
label | References: Series:BR3ADL3 Wall & Partition Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease