## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP- Retention Piling Rev1 |  |  |  |  | Yes | ITP- Retention Piling Rev1 | 3936ff89-951f-497b-973a-57e60b591536
checkpoint-status |  |  | checkpoint | PRIOR TO COMMENCEMENT
label | 15e94859-ceba-5990-928e-0a60018c830a |  | note | Operational Activities - · Drilling quality procedure for review · Boring Operations
label | e81766ad-03ac-5821-babe-4b932e4d554d |  | note | Reference - QA Plan
label | b4d63df7-cedb-5e5e-83b6-eb13746661c9 |  | note | Acceptance Criteria - Submit quality plan to KANE Obtain permit to work, sign SWMS Contract drawings, surveyor
label | 2475a534-ff4c-5778-97fa-d86757a43612 |  | note | Inspection Method & Frequency - 1weeks prior 3 days prior 3 days prior
label | 787051a3-c07f-5841-b4fb-4e8bc81d6aca |  | note | Sign by whom - LTE Surveyor
checkpoint-status |  |  | checkpoint | 1 - Set-up over pile location
label | 85136834-1f3e-5c0e-9ea7-684ebc080952 |  | note | Operational Activities - · Offset pegs – position · Drill and Mast plumb – spirit level · Correct pile diameter
label | a143ba89-37e3-5568-b968-5619b95426c5 |  | note | Reference - AS2159
label | 8a7bb5fc-2f1d-5c05-8186-f67870027ace |  | note | Acceptance Criteria - 2 at 90°, long offsets if req’d 150mm / 15m or equivalent.
label | f7cac8a3-c6b3-5a20-9f2e-93cee94c18e3 |  | note | Inspection Method & Frequency - Measure Visual Measure
label | 1bf83a0b-9833-52c1-9e78-5cfbaf9b0b58 |  | note | Sign by whom - LTE Foreman
checkpoint-status |  |  | checkpoint | 2 - Drill to the required depth
label | 26b1f473-4e66-5de7-8f06-c57ff84b543c |  | note | Operational Activities - · Protection of adjacent piles · Suitable founding requirements
label | 9bd9b9ab-acb0-5fc9-910c-d14660fe2f2f |  | note | Acceptance Criteria - Adjacent piles at 15MPa minimum Weather rock Required Pile Depth Refer to LTE Design(LT1082 S00-S06)
label | 6826af94-1c8a-5780-ad6e-f5c90d562f24 |  | note | Inspection Method & Frequency - Measure Observe Record
label | 1628bc31-cf4b-51c0-be18-49e70aa5d201 |  | note | Sign by whom - LTE Foreman
checkpoint-status |  |  | checkpoint | 3 - Install reinforcement
label | d2e15a84-a1ee-5692-adaa-1505f8ab7b02 |  | note | Operational Activities - · Correct cage dia, length, reo bars,ligs · Correct level /orientation
label | 845c177d-3a7f-5f32-96f5-ec0213a821fb |  | note | Reference - LTE Pile QA
label | c52c43ab-4e83-51b5-9f3e-05bd3415245c |  | note | Acceptance Criteria - Refer to LTE Design(LT1082 S00-S06)
label | f5306523-bd2b-5c55-b2d2-451061b8ee13 |  | note | Inspection Method & Frequency - Measure Measure
label | 7e8a5543-264b-5575-81d7-8b0e19c8c050 |  | note | Sign by whom - LTE Foreman
checkpoint-status |  |  | checkpoint | 4 - Concrete Pile
label | 6da79b90-af53-5ded-af80-1e17c20a20ac |  | note | Operational Activities - · Weather check · Number of tests (Tester) · Test slump (tremie) collect cylinders · Concrete to level
label | 1d9cedde-d2e9-54c6-8ea7-81395b071418 |  | note | Reference - AS3600 Pile Schedule Concrete test reports
label | d971c563-66a7-5b34-8afc-db33865bf135 |  | note | Acceptance Criteria - Between 5°C and above 35°C. 1test/50m3 1 @ 7days, 2 @ 28 days and 180mm slump Refer pile record sheet for concrete levels 50/65MPa strength at 28 days
label | bb124124-0058-5b42-b89c-be37c7001873 |  | note | Inspection Method & Frequency - Witness Review Review Witness Witness
label | e30f93f0-cc5f-5c47-8d96-1b33d195d10f |  | note | Sign by whom - LTE Foreman LTE Engineer
label | d27f76fa-c391-54ac-b16e-71723b0725ad |  | note | Comments - See attached concrete test results.
button | fd033352-8740-51d1-8361-55ea50ae7d0f |  | button | Test results | Pass, Fail