## res_Ashburton - ITP Bored Reten
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Bored Retention Piles | [5 empty] | ITP - Bored Retention Piles Rev 0
checkpoint | 1. Existing Service search
label | APPLICABLE STANDARD: N/A
label | CONFORMANCE CRITERIA: Locate and Identify existing underground services
label | FREQUENCY: Entire Site
label | METHOD OF INSPECTION: Visual Inspection of drawings and identify
label | PERSONNEL RESPONSIBLE: Client
label | DOCUMENTATION & VERIFICATION: Service plans from client
holdpoint | SIGN OFF - LTE
checkpoint | 2. Piling Platform
label | APPLICABLE STANDARD: N/A
label | CONFORMANCE CRITERIA: Working platform adequate for piling rigs
label | FREQUENCY: Entire Site
label | METHOD OF INSPECTION: DCP testing undertaken to confirm in situ soil adequate for Piling rig
label | PERSONNEL RESPONSIBLE: LTE Engineer, LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: DCP test results, Working Platform Certificate
holdpoint | SIGN OFF - LTE
checkpoint | 3. Pile Set out
label | APPLICABLE STANDARD: Construction Drawings and Pile design document
label | CONFORMANCE CRITERIA: Set-out of Pile locations as shown of drawings
label | FREQUENCY: Each pile
label | METHOD OF INSPECTION: Visual Inspection, survey set out
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: Pile QA document
holdpoint | SIGN OFF - LTE
checkpoint | 4. Drilling pile
label | APPLICABLE STANDARD: Construction Drawings, Pile design document, Pile QA document, AS2159
label | CONFORMANCE CRITERIA: Ensure hole dia, depth, all as per design documentation and QA document, hole within positional tolerance as per AS2159
label | FREQUENCY: Each pile
label | METHOD OF INSPECTION: Visual Inspection, tape measure
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: Pile QA document
holdpoint | SIGN OFF - LTE
checkpoint | 5. Placement of Reinforcement cage
label | APPLICABLE STANDARD: Construction Drawings, Pile design document, Pile QA document, AS2159
label | CONFORMANCE CRITERIA: Reo cage as per design/Pile QA document, placed to correct RL, spacers used to ensure cover to cage
label | FREQUENCY: Each pile
label | METHOD OF INSPECTION: Visual Inspection
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: Pile QA document
holdpoint | SIGN OFF - LTE
checkpoint | 6. Placement of Concrete
label | APPLICABLE STANDARD: Construction Drawings, Pile design document, Pile QA document, AS2159, AS3600
label | CONFORMANCE CRITERIA: Concrete 50 MPa, superplasticised for piling application. Positively guided away from reinforcement during pouring. Concrete testing undertaken min 3 cylinders per 50m3 poured on site
label | FREQUENCY: Each pile
label | METHOD OF INSPECTION: Visual Inspection
label | ○ Concrete dockets
label | ○ Concrete test report
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: Pile QA document
label | ○ Concrete dockets
label | ○ Concrete test report
holdpoint | SIGN OFF - LTE