## res_Ashburton - ITP Bored Reten
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Capping Beam | [5 empty] | ITP - Capping Beam Rev 0
checkpoint | 1. Existing Service search
label | APPLICABLE STANDARD: N/A
label | CONFORMANCE CRITERIA: Locate and Identify existing underground services
label | FREQUENCY: Entire Site
label | METHOD OF INSPECTION: Visual Inspection of drawings and identify
label | PERSONNEL RESPONSIBLE: Client
label | DOCUMENTATION & VERIFICATION: Service plans from client
holdpoint | SIGN OFF - LTE
checkpoint | 2. Detailed Excavation of Capping beam
label | APPLICABLE STANDARD: Construction Drawings
label | CONFORMANCE CRITERIA: Excavation to line/levels and dimensions as per drawings
label | FREQUENCY: Entire Site
label | METHOD OF INSPECTION: Survey/setout
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: This ITP
holdpoint | SIGN OFF - LTE
checkpoint | 3. Placement of Blinding (if required)
label | APPLICABLE STANDARD: Construction Drawings
label | CONFORMANCE CRITERIA: Blinding placed to correct level
label | FREQUENCY: Each pour
label | METHOD OF INSPECTION: Visual Inspection, survey set out, laser level
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: This ITP
holdpoint | SIGN OFF - LTE
checkpoint | 4. Placement of reinforcement
label | APPLICABLE STANDARD: Construction Drawings, AS3600
label | CONFORMANCE CRITERIA: Ensure reo placed as per design, main bar and side bar laps as per design drawings, lig spacing as per design drawings, starter bars as per structural drawings
label | ○ Ensure concrete cover as per design
label | FREQUENCY: Each pour
label | METHOD OF INSPECTION: Visual Inspection, tape measure
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: This ITP
holdpoint | SIGN OFF - LTE
checkpoint | 5. Placement of Concrete (shotcrete)
label | APPLICABLE STANDARD: Construction Drawings, AS3600
label | CONFORMANCE CRITERIA: Concrete strength as per design 40 MPa and 50 MPa, Concrete testing undertaken min 3 cylinders per 50m3 poured on site
label | FREQUENCY: Each pour
label | METHOD OF INSPECTION: Visual Inspection
label | ○ Concrete dockets
label | ○ Concrete test report
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: Concrete dockets, Concrete test report
holdpoint | SIGN OFF - LTE