## res_Ashburton - ITP Bored Reten
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Shotcrete Walls | [5 empty] | ITP - Shotcrete Walls Rev 0
checkpoint | 1. Existing Service search
label | APPLICABLE STANDARD: N/A
label | CONFORMANCE CRITERIA: Locate and Identify existing underground services
label | FREQUENCY: Entire Site
label | METHOD OF INSPECTION: Visual Inspection of drawings and identify
label | PERSONNEL RESPONSIBLE: Client
label | DOCUMENTATION & VERIFICATION: Service plans from client
holdpoint | SIGN OFF - LTE
checkpoint | 2. Detailed Excavation of Shotcrete wall
label | APPLICABLE STANDARD: Construction Drawings
label | CONFORMANCE CRITERIA: Excavation to line/levels as per drawings
label | FREQUENCY: Entire Site
label | METHOD OF INSPECTION: Survey/setout
label | PERSONNEL RESPONSIBLE: LTE
label | DOCUMENTATION & VERIFICATION: This ITP
holdpoint | SIGN OFF - LTE
checkpoint | 3. Placement of dowels/mesh/stripdrain/starter bars
label | APPLICABLE STANDARD: Construction Drawings, AS3600
label | CONFORMANCE CRITERIA: Ensure stripdrain installed as per design
label | ○ Ensure reo placed as per design, mesh laps as per design drawings, dowels drilled and epoxied as per design drawings, starter bars as per structural drawings
label | ○ Ensure concrete cover as per design
label | FREQUENCY: Each pour
label | METHOD OF INSPECTION: Visual Inspection, tape measure
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: This ITP
holdpoint | SIGN OFF - LTE
checkpoint | 4. Placement of Concrete (shotcrete)
label | APPLICABLE STANDARD: Construction Drawings, AS3600
label | CONFORMANCE CRITERIA: Concrete strength as per design, Concrete testing undertaken min 3 cylinders per 50m3 poured on site
label | FREQUENCY: Each pour
label | METHOD OF INSPECTION: Visual Inspection
label | ○ Concrete dockets
label | ○ Concrete test report
label | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | DOCUMENTATION & VERIFICATION: Concrete dockets, Concrete test report
holdpoint | SIGN OFF - LTE