## Project Structure
The Grey |  |  |  |  | Checklists needed
| Scope of work | Sub Area | Checklist
Site QA
Underslab
Basement / Level 0
|  |  | Undserslab | prepopulate | QA - Basement Underslab
|  |  | Common Waste & Stacks Checklist | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
|  |  | Manholes | prepopulate | QA - Manhole
First Fix
Level 0
|  |  | Common Waste & Stacks | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
Level 1
|  |  | Common Waste & Stacks | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
Level 2
|  |  | Common Waste & Stacks | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
Level 3
|  |  | Common Waste & Stacks | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
Level 4
|  |  | Common Waste & Stacks | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
Level 5
|  |  | Common Waste & Stacks | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
Level 6
|  |  | Common Waste & Stacks | prepopulate | QA - Waste / Stacks
|  |  | Main Water Reticulation | prepopulate | QA - Main Water Reticulation
Second Fix
Sump Pump
|  | Basement / Level 0 | sump | prepopulate | QA - Sump Pump
|  |  | lift | prepopulate | QA - Sump Pump
Booster pump
|  | Basement / Level 0 |  | prepopulate | QA - Cold Water Booster Pump
Testing
First Fix
Basement / Level 0
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 0
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 1
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 2
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 3
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 4
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 5
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 6
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Second Fix
Basement / Level 0
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 0
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 1
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 2
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 3
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 4
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 5
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Level 6
Testing - Waste / Stacks
Testing - Cold Water Main
Testing - Hot Water Main
Booster pump
|  | Level 1 |  | prepopulate | Testing - Cold Water Booster Pump
Sump Pump
|  | Basement / Level 0 | sump | prepopulate | Test - Sump Pump
|  |  | lift | prepopulate | test - Sump Pump

## Checklists
checklist | QA - Basement Underslab
section | Area Prestart / Acceptance & Drawings
text | Zone / Area
checkpoint | Area ready for works (grids setout, area accessible and approval to start)
checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
section | Under Slab Pipe install
checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | Zone / Area
text | Start Invert
text | Finish Invert
text | Grade of Pre-Line %
text | Product Type
checkpoint | Pipe supported
checkpoint | Install Tests completed, reviewed & approved
text | Test method used
text | Duration
checkpoint | Local Authority Inspection Passed
text | Witnessed by
holdpoint | Signoff required
text | Representing (Company)
text | Date
checkpoint | All relevant test plugs removed where applicable
checkpoint | Open ends sealed
checkpoint | General photos, comments and observations
checkpoint | Pipe Laying Completed
text | Laid by
bool | Bedding Sound
bool | Soil Removed
bool | Trench Compacted
bool | Hard Filled
section | Area Completion/Signoff
checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint | All Measurements Double Checked
checkpoint | As-Built Drawings recorded (drawing & revision number(s)
checkpoint | All relevant under slab works completed, reviewed and approved
text | Completion Date
checklist | QA - Manhole
section | Manhole Install
checkpoint | Latest consented drawings
text | Drawing Ref No.
checkpoint | Setout Completed checked and accurate
checkpoint | Excavation Accurate - Location & Depth
checkpoint | Ground conditions checked & acceptable
checkpoint | Bedding depth and material correct & compacted
checkpoint | Correct manhole installed to specified height and sitting level
checkpoint | Manhole Risers Installed (if applicable)
checkpoint | Joints & connections correctly sealed as specified
checkpoint | Manhole benching completed and acceptable
checkpoint | Concrete Lid Installed and sitting appropriately
checkpoint | Cast Iron Lid Installed and sitting flush
checkpoint | Signoff on Completed Work (Council etc)
section | Backfill
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct
checklist | QA - Main Water Reticulation
section | Cold Water Main
checkpoint-no-status | Zone / Area
text | Zone / Area
checkpoint | Connections welded/crimped correctly
checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint | Lagging installed and neat
checkpoint | Labels installed
checkpoint | Correct valves fitted correctly
checkpoint | Seismic bracing completed
checkpoint | Tested
section | Hot Water Main
checkpoint-no-status | Zone / Area
text | Zone / Area
checkpoint | Connections welded/crimped correctly
checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint | Lagging installed and neat
checkpoint | Labels installed
checkpoint | Correct valves fitted correctly
checkpoint | Seismic bracing completed
checkpoint | Tested
checklist | QA - Sump Pump
section | Unit check
checkpoint | Area acceptable and ready for work to begin
checkpoint | Pump mounted on base, & housing condition good - no leaks
checkpoint | Alignment checked (field alignment performed where required)
checkpoint | Pump impeller works correctly
section | Pipework
checkpoint | Strainer installed & cleaned
checkpoint | All isolation valves set correctly - non return valve, isolation valve
section | Electrical
checkpoint | Local isolator located
checkpoint | All power and control wiring correctly installed
checkpoint | All electrical connections correct and tight
checkpoint | Controls point to point check completed
section | Float levels
checkpoint | invert - low level alarm
checkpoint | invert - mid level for dual pump operation
checkpoint | invert - high level alarm
checkpoint | Rail / lifting chains installation
checklist | QA - Cold Water Booster Pump
section | Zone / Area
checkpoint-no-status | Details
text | Zone / Area
section | Pumpset mainfold
checkpoint | Connections welded correctly
checkpoint | Clip Spacing to manufactures specs horizontal/ vertical
checkpoint | Valves fitted correctly
checkpoint | Line strainer fitted between pump & tank
section | Pumps
checkpoint | Pump 1 Startup KPA
checkpoint | Pump 1 kick out pressure KPA
checkpoint | Pump 2 Startup KPA
checkpoint | Pump 2 kick out pressure KPA
checkpoint | Pressure vessell pressure
section | General
checkpoint | Mains water change over
checkpoint | Flow test pump
checkpoint | Pressure tests pipework
checkpoint | Visual check (for leaks form valves, tees, saddles, etc)
checkpoint | Non return valves fitted
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checklist-flat | Testing - Waste / Stacks
checkpoint-no-status | Details
text | Zone / Area
text | Area / Stack
checkpoint | Flood Test in accordance with ASNZ 3500 (15.2)
text | Duration
text | Notes
checkpoint | Install Tests completed, reviewed & approved
checkpoint | Local Authority Inspection Passed
text | Witnessed by
text | Representing (Company)
text | Date
checklist-flat | Testing - Cold Water Main
checkpoint-no-status | Details
text | Zone / Area
checkpoint | Pressure 1500 kpa or as per spec
text | Duration
checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
label | Attach photos of completed area
checkpoint | Pre Line Inspection Passed - Foreman
checkpoint | Pre Line Inspection Passed - Inspector
checklist-flat | Testing - Hot Water Main
checkpoint-no-status | Details
text | Zone / Area
checkpoint | Pressure 1500 kpa or as per spec
text | Duration
checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
label | Attach photos of completed area
checkpoint | Pre Line Inspection Passed - Foreman
checkpoint | Pre Line Inspection Passed - Inspector
checklist-flat | Testing - Cold Water Booster Pump
section | Installer Details
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checklist-flat | Testing - Sump Pump
section | Installer Details
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date