## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | First Fix Checklist |  |  |  |  | Yes | First Fix Checklist | 185886ea-06a3-4ff0-bb74-e1d6222965a6
checkpoint-status |  |  | checkpoint | Correct set out for all fixtures
checkpoint-status |  |  | checkpoint | Checked for crossovers
checkpoint-status |  |  | checkpoint | All pipes clipped securely
checkpoint-status |  |  | checkpoint | All pipework pressure tested
checkpoint-status |  |  | checkpoint | All waste pipes flood tested
checkpoint-status |  |  | checkpoint | Fixing for all fixtures
checkpoint-status |  |  | checkpoint | Hot water supply lagged
checkpoint-status |  |  | checkpoint | FWG flanges installed and construction capped fitted
checkpoint-status |  |  | checkpoint | Shower tray and mixer installed to manufacturers instruction. Chrome Tray Rite removed, and Cardboard installed securely for protection
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Heat Pump (Roof Level) - Second Fix Checklist |  |  |  |  | Yes | Heat Pump (Roof Level) - Second Fix Checklist | 3b17627e-d1c4-4fad-9045-d36d96e67c0b
checkpoint-status |  |  | checkpoint | Correct sizing to Heat Pump units as per Semtex shop drawing
checkpoint-status |  |  | checkpoint | Correct vavles installed as per Semtex shop drawing
checkpoint-status |  |  | checkpoint | Thermal Insulation to DHW line only
checkpoint-status |  |  | checkpoint | Commissioned to manufacturers instruction
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | DCW/DHW Water Risers Checklist GL C/3 |  |  |  |  | Yes | DCW/DHW Water Risers Checklist GL C/3 | 500d2f7b-f45a-4c13-9179-148a118aa21d
checkpoint-status |  |  | checkpoint | Floor Isolation Valves installed
checkpoint-status |  |  | checkpoint | Thermal insulation to DHW
checkpoint-status |  |  | checkpoint | Ke Kelit pressed and witness mark visible
checkpoint-status |  |  | checkpoint | Tested to 1500kpa and passed
checkpoint-status |  |  | checkpoint | Clips installed at correct spacing
checkpoint-status |  |  | checkpoint | Riser installed as per plan
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | DCW/DHW Water Risers Heat Pump GL D/7 Inc Return at GL C/7 |  |  |  |  | Yes | DCW/DHW Water Risers Heat Pump GL D/7 Inc Return at GL C/7 | 5207d0bf-e1b1-44ea-b4ef-fc2518aeed17
checkpoint-status |  |  | checkpoint | All Pipe clipped securely
checkpoint-status |  |  | checkpoint | Installed to level seven tested to 1500 kpa and inspected by WCC
checkpoint-status |  |  | checkpoint | Thermal Insulation installed to DHW only
checkpoint-status |  |  | checkpoint | Area left Clean and tidy
checklist-flat |  |  | checklist | Basement Checklist |  |  |  |  | Yes | Basement Checklist | 60e9e781-fc5d-416b-bd4a-f04f030c5e4f
checkpoint-status |  |  | checkpoint | Main drainage installed as per plan
checkpoint-status |  |  | checkpoint | Drainage risers installed as per drawings
checkpoint-status |  |  | checkpoint | Clips at correct spacing
checkpoint-status |  |  | checkpoint | Air tested and passed by council
checkpoint-status |  |  | checkpoint | Seismic installed to Drainage where required
checkpoint-status |  |  | checkpoint | DCW main run co-ordinated as per plan and seismic bracketing where required
checkpoint-status |  |  | checkpoint | Thermal insulation (DHW Only)
checkpoint-status |  |  | checkpoint | Ke Kelit pressed and witness mark visible
checkpoint-status |  |  | checkpoint | Tested to 1500kpa and passed by council
checkpoint-status |  |  | checkpoint | DCV installed to DCW and pressure set at 500kpa
checkpoint-status |  |  | checkpoint | Riser installed as per plan
checklist-flat |  |  | checklist | Balcony Drainage/External Stormwater Drainage - Second Fix - Checklist |  |  |  |  | Yes | Balcony Drainage/External Stormwater Drainage - Second Fix - Checklist | 63a7ffcf-7cc9-45e5-aa74-b7c6f4f0ef12
checkpoint-status |  |  | checkpoint | Balconies overflow terminated to underside of soffit
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Substration Checklist |  |  |  |  | Yes | Substration Checklist | 851e1719-aefb-47b0-b65f-4c625f127fde
checkpoint-status |  |  | checkpoint | Flanges installed
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Balcony Drainage/External Stormwater Drainage - First Fix - Checklist |  |  |  |  | Yes | Balcony Drainage/External Stormwater Drainage - First Fix - Checklist | 95557453-308a-43e9-a034-7d26cb3f514c
checkpoint-status |  |  | checkpoint | Setout and position checked and confirmed
checkpoint-status |  |  | checkpoint | Pipework installed as per specification
checkpoint-status |  |  | checkpoint | Pipe test booked and test ready
checkpoint-status |  |  | checkpoint | As built plans complete
checkpoint-status |  |  | checkpoint | Clamp ring and dome installed to outlet and overflow
checkpoint-status |  |  | checkpoint | Clamp ring and allthrough flange installed to outlet
checkpoint-status |  |  | checkpoint | Stormwater riser installed to allthrough outlet
checkpoint-status |  |  | checkpoint | Pipework complete & ready for sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Underslab Checklist |  |  |  |  | Yes | Underslab Checklist | 9ec899a1-a60e-4126-bfe7-14914bd30b9d
checkpoint-status |  |  | checkpoint | Pipework Material as specified/scheduled/drawn
checkpoint-status |  |  | checkpoint | Grid lines and fitting dimensions confirmed
checkpoint-status |  |  | checkpoint | Drain invert checked
checkpoint-status |  |  | checkpoint | Gully position checked
checkpoint-status |  |  | checkpoint | Floor levels established
checkpoint-status |  |  | checkpoint | Falls checked
checkpoint-status |  |  | checkpoint | Drainlayer/Plumber interface Points established
checkpoint-status |  |  | checkpoint | Penetrations co-ordinated with main contractor
checkpoint-status |  |  | checkpoint | Pipework backfilled correctly
checkpoint-status |  |  | checkpoint | Identification strip installed if required
checkpoint-status |  |  | checkpoint | Open ends of pipework capped off to prevent dirt ingress
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Second Fix Checklist |  |  |  |  | Yes | Second Fix Checklist | b52b07f0-f81a-4f06-bfe5-824fd6c3c20f
checkpoint-status |  |  | checkpoint | Escutcheons/flanges installed to all fixtures
checkpoint-status |  |  | checkpoint | Heights checked as per plan for all fixtures
checkpoint-status |  |  | checkpoint | Testing of all installed fixtures (flood test)
checkpoint-status |  |  | checkpoint | Silicone applied is neat and tidy
checkpoint-status |  |  | checkpoint | Fixtures installed are to spec/clean and tidy
checkpoint-status |  |  | checkpoint | Kitchen has univalve installed for dishwasher
checkpoint-status |  |  | checkpoint | Laundry box is ready for washing machine installation
checkpoint-status |  |  | checkpoint | Temperature test to sanitary fixtures/kitchen
checkpoint-status |  |  | checkpoint | Aerator to basin mixer/kitchen sink checked and cleaned
checkpoint-status |  |  | checkpoint | Stickers removed from WC
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Plant Room - Basement - First Fix - Checklist |  |  |  |  | Yes | Plant Room - Basement - First Fix - Checklist | cf57b288-e108-4a27-915a-3109f3e6be20
checkpoint-status |  |  | checkpoint | Ke kelit pipework pressed and witness mark visible
checkpoint-status |  |  | checkpoint | Pressure tested to 1500kpa and passed by council
checkpoint-status |  |  | checkpoint | Plant room installed as per engineer schematic (valves installed, gauges, control valves)
checkpoint-status |  |  | checkpoint | Plant room layout to Semtex shop drawing
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Corridor DHW/DCW Ke Kelit Checklist |  |  |  |  | Yes | Corridor DHW/DCW Ke Kelit Checklist | f5a86ae0-ae62-43cd-b74d-239f467ab1a8
checkpoint-status |  |  | checkpoint | TMV Installed to RCP plan
checkpoint-status |  |  | checkpoint | Isolation valves installed to valve set & tested to 1500 kpa
checkpoint-status |  |  | checkpoint | Thermal Insulation installed to DHW
checkpoint-status |  |  | checkpoint | Ke Kelit pressed and witness marks visible
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Plant Room - Second Fix - Checklist |  |  |  |  | Yes | Plant Room - Second Fix - Checklist | f5db86ec-0f8e-409a-9404-62dc09c0138e
checkpoint-status |  |  | checkpoint | Thermal insulation stalled
checkpoint-status |  |  | checkpoint | Plant room commissioned correctly and checked for leaks/correct operation
checkpoint-status |  |  | checkpoint | Area left clean and tidy