## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Panel Installation |  |  |  |  | Yes | Panel Installation Checklist | ca4f7f3e-a8cf-48eb-8671-603eeffc8c3b
checkpoint-status |  |  | checkpoint | (PHOTO for incorrect locations) Confirm Unit struct is in position and size is correct
checkpoint-status |  |  | checkpoint | Surveyor setout has been completed & Bracket is in position and level. Checked T-bolts are used and nuts tightened.
checkpoint-status |  |  | checkpoint | Check if hooks are in position, if not, install hook according to instruction appendix 1: hook install instruction
checkpoint-status |  |  | checkpoint | (PHOTO) Check horizontal & vertical fins amount/ code is correlated with panel code, fins weld and fabrication correctly (Initial on panel label)
checkpoint-status |  |  | checkpoint | (PHOTO) Check end strip capping is installed within tolerance and fully caulked
checkpoint-status |  |  | checkpoint | Check fin fixing types are correct and fixed with loctite, A4 stainless screw material used(Initial on panel label)
checkpoint-status |  |  | checkpoint | Check bracket sealant (Initial on panel label)
checkpoint-status |  |  | checkpoint | Glass in good condition
checkpoint-status |  |  | checkpoint | Check 500 vertical fins fixed tightly (Initial on panel label)
checkpoint-status |  |  | checkpoint | Check vertical fins alignment (Initial on panel label)
checkpoint-status |  |  | checkpoint | All gasket installed (visual) and gutter has been cleaned
checkpoint-status |  |  | checkpoint | (PHOTO) Panel installation- installed and fixed in position, aluminium stopping blocked installed if required
checkpoint-status |  |  | checkpoint | (PHOTO) Gutter plate and sleeve installed and sealed
checkpoint-status |  |  | checkpoint | (PHOTO) Bolts nuts are torqued correctly
checkpoint-status |  |  | checkpoint | (PHOTO) Smoke seal insulation installed & Smoke flashing installed and sealed, bottoms sills installed, Four way caulk applied
checkpoint-status |  |  | checkpoint | (PHOTO) If patching required, check patching plate, screws are caulked
checkpoint-status |  |  | checkpoint | Four way caulk applied
checkpoint-status |  |  | checkpoint | (PHOTO) Skirting fixed and sealed in position
checkpoint-status |  |  | checkpoint | Pelmet fixed and sealed in position
checkpoint-status |  |  | checkpoint | Protection tape in good condition
checkpoint-status |  |  | checkpoint | Auto equipment (louvre/vent) operable
checkpoint-status |  |  | checkpoint | Defects