## Ceilings & Walls Sign-Off
Ceilings & Walls Sign-Off Status
Ceilings | ICU | Electrical | Hydraulic | Mechanical | Comments
Bed 17
Bed 18
Walls | Service Block - Level 1 | Electrical | Hydraulic | Mechanical
Lift Lobby
Ceilings | Service Block - Level 1 | Electrical | Hydraulic | Mechanical
| Lift Lobby |  |  |  | CMS - Airdivision to site measure (C.V 17/01)
Walls | Service Block - Level 2 | Electrical | Hydraulic | Mechanical
Lift Lobby (001)
Office 1P (002)
Office 1P (003)
Office
Executive Office
Lift Lobby (006)
Store
Electrical DB
Corridor (254)
Corridor (255)
Ceilings | Service Block - Level 2 | Electrical | Hydraulic | Mechanical
Lift Lobby (001)
Office 1P (002)
Office 1P (003)
Office
Executive Office
Lift Lobby (006)
Store
Electrical DB
| Corridor (254) |  |  |  | Fredon - Electrical not complete / accessible yet (I.G 13/01)
Corridor (255)
Walls | Service Block - Level 3 | Electrical | Hydraulic | Mechanical
Lift Lobby (001)
General Store
Lift Lobby (005)
Store (006)
Store (007)
Electrical DB
| Corridor (254) |  |  |  | GG - Remove hoarding
| Corridor (255) |  |  |  | GG - Remove hoarding
| Corridor (256) |  |  |  | GG - Remove hoarding
Ceilings | Service Block - Level 3 | Electrical | Hydraulic | Mechanical
Lift Lobby (001)
General Store
Lift Lobby (005)
| Store (006) |  |  |  | CMS - Existing duct modification; awaiting delivery of F/D & ductwork (C.V 13/01)
Store (007)
Electrical DB
Corridor (254)
Corridor (255)
Corridor (256)
Walls | Service Block - Level 4 | Electrical | Hydraulic | Mechanical
| Room Annexe (001) |  |  |  | GG - Works on hold; awaiting updated drawings (L.S 13/01)
| Lift Lobby (002) |  |  |  | GG - Works on hold; awaiting updated drawings (L.S 13/01)
| Imprest Store |  |  |  | Accord - IHR cabinet not complete (T.H 19/12)
General Store
Lift Lobby (005)
Room Annexe (006)
Electrical DB
Corridor (254)
Corridor (255)
Ceilings | Service Block - Level 4 | Electrical | Hydraulic | Mechanical
| Room Annexe (001) |  |  |  | GG - Works on hold; awaiting updated drawings (L.S 13/01)
| Lift Lobby (002) |  |  |  | GG - Works on hold; awaiting updated drawings (L.S 13/01)
| Imprest Store |  |  |  | Accord - IHR cabinet not complete (T.H 19/12)
General Store
Lift Lobby (005)
Room Annexe (006)
Electrical DB
Corridor (254)
Corridor (255)
Walls | Kitchen Stage 3 | Electrical | Hydraulic | Mechanical
| Bulk Cooking |  |  |  | Accord - excludes elevation 2. CMS - excludes elevation 3.
Store
Cleaners Room
Cool Room 5
Ingredients Prep
Utensil Washing
Cool Room 3
Freezer Room 3
Dry Store
Cool Room 4
Bulk Dry Store
Corridor (254)
Corridor (256)
Corridor (257)
Ceilings | Kitchen Stage 3 | Electrical | Hydraulic | Mechanical
Bulk Cooking
Store
Cleaners Room
Cool Room 5
| Ingredients Prep |  |  | 2023-01-25 | CMS - awaiting Siemans cabling for Coolroom (C.V 24/01)
Utensil Washing
Cool Room 3
Freezer Room 3
| Dry Store |  |  |  | CMS - TBC (C.V 24/01)
Cool Room 4
| Bulk Dry Store |  |  |  | CMS - TBC (awaiting Siemans) (C.V 24/01) & Accord - TBC
Corridor (254)
| Corridor (256) |  |  |  | Accord - Awaiting part in front of Cleaners Room (T.H 24/01)
Corridor (257)
| Service Block - Level 5 |  |  |  | Southern lobby on critical path
Service Block - Level 6
Service Block - Level 7