## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | SJGSH-CHW-CP-04.007- Walls | [5 empty] | ITP - SJGSH-CHW-CP-04.007- Walls
checkpoint | Submission and approval of samples & technical data. Approved SWMS prior to commencement.
label | INSPECT. METHOD: V
label | ACCEPTANCE CRITERIA: A00.03.00.701-703 & SJGSH WP02 Specification
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: H
textbox | Date:
checkpoint | Setout and establish lines and levels
label | INSPECT. METHOD: V
label | ACCEPTANCE CRITERIA: Architectural Drawings A70.03.01.301
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: W
textbox | Date:
checkpoint | Check materials are as drawing and specification
label | INSPECT. METHOD: V
label | ACCEPTANCE CRITERIA: Architectural Drawings A70.03.01.301 & SJGSH WP02 Specification
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: W
textbox | Date:
checkpoint | Install stud, sheet one side of wall, install insulation and noggings (if required)
label | INSPECT. METHOD: V
label | ACCEPTANCE CRITERIA: Architectural Drawings A70.03.01.301 & SJGSH WP02 Specification
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: W
textbox | Date:
checkpoint | Services Install (1)
label | INSPECT. METHOD: P
label | ACCEPTANCE CRITERIA: Services trades install & sign-off
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: H
textbox | Date:
holdpoint | HOLD POINT
checkpoint | Services Install (1)
label | INSPECT. METHOD: P
label | ACCEPTANCE CRITERIA: Services trades install & sign-off
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: H
textbox | Date:
holdpoint | HOLD POINT
checkpoint | Services Install (2)
label | INSPECT. METHOD: P
label | ACCEPTANCE CRITERIA: Electrical (including dry fire and communications)
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: H
textbox | Date:
holdpoint | HOLD POINT
checkpoint | Services Install (3)
label | INSPECT. METHOD: P
label | ACCEPTANCE CRITERIA: Hydraulic (including wet fire)
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: H
textbox | Date:
holdpoint | HOLD POINT
checkpoint | Services Install (4)
label | INSPECT. METHOD: P
label | ACCEPTANCE CRITERIA: Mechanical
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: H
textbox | Date:
holdpoint | HOLD POINT
checkpoint | Required wall treatment (fire or acoustic sealing, etc.) if required
label | INSPECT. METHOD: P
label | ACCEPTANCE CRITERIA: Architectural Drawings A70.03.01.301 & SJGSH WP02 Specification
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: W
textbox | Date:
checkpoint | Close up; sheet, set & sand
label | INSPECT. METHOD: V
label | ACCEPTANCE CRITERIA: Architectural Drawings A70.03.01.301 & SJGSH WP02 Specification
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: H
label | ITEM VERIFICATION ACTION COMPLETE - Builder: W
textbox | Date:
checkpoint | Cleaning of walls and columns
label | INSPECT. METHOD: V
label | ACCEPTANCE CRITERIA: Finished to specification
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: S
label | ITEM VERIFICATION ACTION COMPLETE - Builder: W
textbox | Date:
checkpoint | Final Inspection and handover
label | INSPECT. METHOD: V
label | ACCEPTANCE CRITERIA: Architectural Drawings A70.03.01.301 and specification
label | ITEM VERIFICATION ACTION COMPLETE - Subcontractor: S
label | ITEM VERIFICATION ACTION COMPLETE - Builder: W
textbox | Date:
checkpoint | VERIFICATION - Completed by Subcontractor at end of work
label | This is to confirm C & L Ceilings Pty Ltd (Name of subcontractor personnel responsible for work) have carried out all necessary inspections and verify that the work has been completed and conforms to the contract specification.
label | ATTACHMENTS
tickbox | Inspection Report/Checklist
tickbox | Product Details
tickbox | Sample Material
tickbox | Test Results / Certificates
tickbox | Dockets
tickbox | Other
textbox
textbox | Date:
holdpoint | SIGNATURE