## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 - Hotmix Asphalt | itp |  |  |  |  | ITP-001 - Hotmix Asphalt Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Mix Design approval
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Mix design to be used has been approved by project superintendent, prior to use
label | REFERENCE DOCUMENTS: 407.09 Mix Design Registration
label | INSPECTION/TEST METHOD: Approval Correspondance
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Project Engineer/ Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.17, AS2150 10.1 AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Asphalt Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | ○ Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
label | REFERENCE DOCUMENTS: 407.17
label | INSPECTION/TEST METHOD: Infrared Thermometer
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints for the final Wearing Course are located on lane lines
label | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines
label | REFERENCE DOCUMENTS: 407.21
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Project engineer FHC
date | Date Completed:
checkpoint | 1.5 - Tack Coat
label | FREQUENCY: Prior to Commencing paving
label | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.25-0.50 L/m2 of CRS60. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure .
label | ○ NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces
label | ○ Photographical evidence must be obtained (with an identifiable landmark)
label | *from 1st July 2023, "trackless Tack Coat" must be used
label | REFERENCE DOCUMENTS: 407.19 AS2150 11
label | INSPECTION/TEST METHOD: Spray area and inspect
label | RECORD OF CONFORMITY: Completed ITP, Photograph
label | IP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
section | 2 - Photos
checkpoint-no-status | Thermometer
checkpoint-no-status | Tack Coat
section | 3 - Asphalt Placement works
checkpoint | 3.1 - Commencement of Placing
label | FREQUENCY: Prior to Commencing paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
label | REFERENCE DOCUMENTS: 407.23
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Delivery of Mix
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Check correct mix design has been supplied, as per pavement design.
label | REFERENCE DOCUMENTS: Pavement Design Details 407.20
label | INSPECTION/TEST METHOD: Check asphalt delivery docket
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.3 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: 407.11 Table 407.111
label | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.4 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Measure and Record on Daily Lot Record
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan Foreman/ Engineer
date | Date Completed:
checkpoint | 3.5 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: Pavement Design Details 407.25(a),(b)
label | INSPECTION/TEST METHOD: Dips using ruler or dip stick
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.6 - Paver Stoppages
label | FREQUENCY: If paver stops
label | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | REFERENCE DOCUMENTS: 407.25 (c)
label | INSPECTION/TEST METHOD: Thermometer
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.7 - Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: 407.25 (c)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.8 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: 407.29 (a)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection & Measurement
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.9 - Trafficking pavement after placment
label | FREQUENCY: After final roll
label | ACCEPTANCE CRITERIA: Trafficking or placement of asphalt over type SF asphalt is not permitted unless the majority of the SF asphalt has a surface temperature of 50°C or less and Falling. Where trafficking of SF aspahlt results in deformation, further trafficking shall cease until such time that the type SF asphalt has adequately cooled to allow works to continue without further damage.
label | ○ For Stone Mastic Asphalt, this must be 40°C
label | REFERENCE DOCUMENTS: 407.28, 404.14
label | INSPECTION/TEST METHOD: Visual Inspection & Thermometert
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Testing
checkpoint | 4.1 - Compaction Testing (Dense Graded Apshalt)
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
label | >50mm layer depth = 96.0%
label | <50mm layer depth = 95.0%
label | Additional Test must be undertaken on the longitudinal joints for wearing courses
label | ○ Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
label | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
label | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
label | REFERENCE DOCUMENTS: Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
label | INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
label | RECORD OF CONFORMITY: Completed ITP, Compaction rerports
label | TP
label | RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
date | Date Completed:
checkpoint | 4.2 - Level Conformance
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
label | ○ Scale A: +/- 5mm Range, +/- 8mm standard deviation
label | REFERENCE DOCUMENTS: 407.30, 407.29
label | INSPECTION/TEST METHOD: Survey Results
label | RECORD OF CONFORMITY: Completed ITP, Survey Conformance Results
label | WP
label | RESPONSIBILITY: Surveyor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-002 - Construction of Underground Stormwater Drainage | itp |  |  |  |  | ITP-002 - Construction of Underground Stormwater Drainage Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Precast Materials Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | REFERENCE DOCUMENTS: 701.04b
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.4 - Precast Pipe Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
label | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl.619
label | ○ Cl. 701.04(a)
label | ○ Cl. 701.04(b)(i)
label | ○ Cl. 705.04(d)
label | ○ Cl. 705.11
label | ○ AS4058
label | ○ AS4680
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.5 - Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Material used as per specification
label | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Pre registed mix registration
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.6 - Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Material used as per specification
label | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Pre registed mix registration
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Verge removal and drain pulling
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: verge and drain pulling to be approved by superintendent
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: DTP / Project engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Set out drainage
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance (between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts.
label | ○ Trench walls to be vertical where practical
label | ○ Depth of trench:
label | — >100mm below underside of pipe (for pipe width < 1500 mm)
label | — >200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.15 Table 701.151
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.5 - Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
label | ○ 100mm under pipes.
label | ○ 80mm (earth foundation)
label | ○ 150mm (rock foundation)
label | REFERENCE DOCUMENTS: 701.19
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.7 - Place pipes
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings 701.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Place & compact backfill material over pipes
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area:
label | — fill trench with selected back fill material to subgrade level
label | ○ Backfill under area not paved:
label | — Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.14, 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.10 - Repairs to damaged pipes
label | FREQUENCY: Each damaged pipe
label | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
label | ○ All repair procedures undertaken in accordance with Cl 701.25
label | REFERENCE DOCUMENTS: 701.31
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | FREQUENCY: as required/requested
label | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
label | ○ Bedding material shall be compacted using a compaction plated to refusal.
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-005 - Crushed Rock Class 3 | itp |  |  |  |  | ITP-005 - Crushed Rock Class 3
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Crushed Rock Mix design
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Placing Fill
checkpoint | 2.1 - Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Proof Roll
label | FREQUENCY: After placing material
label | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
label | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
label | ○ VicRoads Spec. Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i) Table 304.111
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Modified Compactive Effort
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale B) 6 lot test Initial FrequencyTest No
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Permeability Testing
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Class 3 Crushed rock max 5x10^-9 m/sec.
label | ○ Where the Class 3 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051 and allows FH to use 9x10-9 m/s Max permeability
label | REFERENCE DOCUMENTS: Project Spec. Cl.3040.05(a) Table 3040.051, RFI-0085.01
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: