## Sheet1
1.1 | Access Documentation | Relevant ATW LARS / PTA Cultural Heritage Clearance Request (Works Notice) | Prior to Start | Review | All documents in place and correct. | LARS / PTA Landholder Notification Weed Washdown Cert. Species and Fauna Management Cultural Heritage Induction Attendance Register Cultural Heritage Clearance Report / Form | H | H | 1.1 - Access Documentation | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW LARS / PTA Cultural Heritage Clearance Request (Works Notice) | Frequency - Prior to Start | Test Method - Review | Acceptance Criteria - All documents in place and correct. | Verifying Documents - LARS / PTA Landholder Notification Weed Washdown Cert. Species and Fauna Management Cultural Heritage Induction Attendance Register Cultural Heritage Clearance Report / Form | Responsibility: RSA - H | Responsibility: Senex - H | 1.1 - Access Documentation
1.2 | Mobilise Machinery CHAR(AMP) Fit For Purpose (FFP) Inspection | Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP) | Prior to Start | Review | Valid Weed Hygiene Certification for all vehicles and plant. | Weed Declaration Certificate. Appenate FFP Form | H | W | 1.2 - Mobilise Machinery CHAR(AMP) Fit For Purpose (FFP) Inspection | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP) | Frequency - Prior to Start | Test Method - Review | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant. | Verifying Documents - Weed Declaration Certificate. Appenate FFP Form | Responsibility: RSA - H | Responsibility: Senex - W | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW LARS / PTA Cultural Heritage Clearance Request (Works Notice)
1.3 | Gravel Compliance | Senex Specifications OPS-QLDS-CI-SPE-002: Section 6 | Each Quarry | Lab Testing | Grading C | NATA Test Report | R | W | 1.3 - Gravel Compliance | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6 | Frequency - Each Quarry | Test Method - Lab Testing | Acceptance Criteria - Grading C | Verifying Documents - NATA Test Report | Responsibility: RSA - R | Responsibility: Senex - W | Frequency - Prior to Start
2.1 | CH and FDM Clearance | SOW | Each Track | Visual Inspection | CH FDM clearance certificate | Access Track FIC | H | W | 2.1 - CH and FDM Clearance | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - CH FDM clearance certificate | Verifying Documents - Access Track FIC | Responsibility: RSA - H | Responsibility: Senex - W | Test Method - Review
2.2 | Identify work area, boundaries and survey requirement | IFC and GIS | Each Track | Set out by Licensed Surveyer | In accordance with IFC Drawing | Access Track FIC | M | W | 2.2 - Identify work area, boundaries and survey requirement | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC and GIS | Frequency - Each Track | Test Method - Set out by Licensed Surveyer | Acceptance Criteria - In accordance with IFC Drawing | Verifying Documents - Access Track FIC | Responsibility: RSA - M | Responsibility: Senex - W | Acceptance Criteria - All documents in place and correct.
2.3 | Confirm dimensions | Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Each Track | Visual Inspection | Standard road is 6m wide and maximum disturbed area is 10m | Access Track FIC | M | W | 2.3 - Confirm dimensions | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - Standard road is 6m wide and maximum disturbed area is 10m | Verifying Documents - Access Track FIC | Responsibility: RSA - M | Responsibility: Senex - W | Verifying Documents - LARS / PTA Landholder Notification Weed Washdown Cert. Species and Fauna Management Cultural Heritage Induction Attendance Register Cultural Heritage Clearance Report / Form
2.4 | Clear CHAR(AMP) grade | Senex Specifications OPS-QLDS-CI-SPE-002: Section 3.2 | Each Track | Visual Inspection | Cleared vegetation stockpiled at regular intervals. | Access Track FIC | M | W | 2.4 - Clear CHAR(AMP) grade | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 3.2 | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - Cleared vegetation stockpiled at regular intervals. | Verifying Documents - Access Track FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: RSA - H
2.5 | Form track profile | Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Each Track | Visual Inspection | Roads flat grade and rills blended into shoulders | Access Track FIC | M | W | 2.5 - Form track profile | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - Roads flat grade and rills blended into shoulders | Verifying Documents - Access Track FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: Senex - H
2.6 | Construct erosion and sediment controls | ESC IFC, SOW Section 4.3.2, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Each Track | Visual Inspection | Ensure site specific erosion and sediment control plan implemented. | Access Track FIC | M | W | 2.6 - Construct erosion and sediment controls | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - ESC IFC, SOW Section 4.3.2, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - Ensure site specific erosion and sediment control plan implemented. | Verifying Documents - Access Track FIC | Responsibility: RSA - M | Responsibility: Senex - W | 1.2 - Mobilise Machinery CHAR(AMP) Fit For Purpose (FFP) Inspection
2.7 | Install water way barriers | IFC GAR, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2.12, SOW section 4.3.2, OPS-ATLS-CS-DWG-021 WP28 HILLANDALE CROSSING CID | Each Crossing | Visual Inspection | Crossings shall be battered to permit heavy vehicle access, bases may be boxed out and backfilled with compacted gravel as detailed in specific construction design and approved by Senex. | Access Track FIC | M | W | 2.7 - Install water way barriers | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC GAR, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2.12, SOW section 4.3.2, OPS-ATLS-CS-DWG-021 WP28 HILLANDALE CROSSING CID | Frequency - Each Crossing | Test Method - Visual Inspection | Acceptance Criteria - Crossings shall be battered to permit heavy vehicle access, bases may be boxed out and backfilled with compacted gravel as detailed in specific construction design and approved by Senex. | Verifying Documents - Access Track FIC | Responsibility: RSA - M | Responsibility: Senex - W | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
2.8 | Gravel cap access track | Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Each Track | Visual Inspection | Compacted to 80 mm and from approved source. | Access Track FIC | M | W | 2.8 - Gravel cap access track | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - Compacted to 80 mm and from approved source. | Verifying Documents - Access Track FIC | Responsibility: RSA - M | Responsibility: Senex - W | Frequency - Prior to Start
2.9 | RSA QA inspection | Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Each Track | Visual Inspection | RSA Supervisor to inspect and accept the works are complete. | Access Track FIC | H | N/A | 2.9 - RSA QA inspection | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete. | Verifying Documents - Access Track FIC | Responsibility: RSA - H | Responsibility: Senex - N/A | Test Method - Review
2.1 | Final inspection of access tracks | Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Each Track | Visual Inspection | Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised. | Access Track FIC | N/A | H | 2.1 - Final inspection of access tracks | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2 | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised. | Verifying Documents - Access Track FIC | Responsibility: RSA - N/A | Responsibility: Senex - H | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
3.1 | CH and FDM Clearance | SOW | Each Track | Visual Inspection | CH FDM clearance certificate | Grid CHAR(AMP)Fence Installation FIC | H | W | 3.1 - CH and FDM Clearance | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - CH FDM clearance certificate | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - H | Responsibility: Senex - W | Verifying Documents - Weed Declaration Certificate. Appenate FFP Form
3.2 | Identify work area, boundaries and survey requirement | Senex Specification/SOW/IFC | Each Fence ID | Set out by Licensed Surveyer | GIS Survey Data | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.2 - Identify work area, boundaries and survey requirement | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC | Frequency - Each Fence ID | Test Method - Set out by Licensed Surveyer | Acceptance Criteria - GIS Survey Data | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: RSA - H
3.3 | Inspect fencing materials | OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Each Delivery | Visual Inspection | AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680. | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.3 - Inspect fencing materials | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Frequency - Each Delivery | Test Method - Visual Inspection | Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680. | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: Senex - W
3.4 | Installation of Fencing | OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Each Fence ID | Visual Inspection | Holes shall be a minimum of 250mm in diameter and 900mm deep, protude heights for strainer CHAR(AMP) coners posts shall be 1300mm, for stay blocks 300mm, for star pickets 1250mm, nominal depth for star pickets 550mm, Spacing between any 2 posts shall not be less than 3m or greater than 5m. | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.4 - Installation of Fencing | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Frequency - Each Fence ID | Test Method - Visual Inspection | Acceptance Criteria - Holes shall be a minimum of 250mm in diameter and 900mm deep, protude heights for strainer CHAR(AMP) coners posts shall be 1300mm, for stay blocks 300mm, for star pickets 1250mm, nominal depth for star pickets 550mm, Spacing between any 2 posts shall not be less than 3m or greater than 5m. | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | 1.3 - Gravel Compliance
3.5 | Concrete for base of fencing | OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Each Fence ID | Visual Inspection | Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.5 - Concrete for base of fencing | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Frequency - Each Fence ID | Test Method - Visual Inspection | Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
3.6 | Welding | OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Each Fence ID | Visual Inspection | Stays shall be fully welded to posts and stay blocks, Gate hinges shall be fully welded to gates and posts, Welded joints to be coated with a zinc rich coating. | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.6 - Welding | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3 | Frequency - Each Fence ID | Test Method - Visual Inspection | Acceptance Criteria - Stays shall be fully welded to posts and stay blocks, Gate hinges shall be fully welded to gates and posts, Welded joints to be coated with a zinc rich coating. | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Frequency - Each Quarry
3.7 | Box out Grid Footings and Prep Site | Senex Specification/SOW/IFC | Each Grid | Visual Inspection | No more than 150mm | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.7 - Box out Grid Footings and Prep Site | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - No more than 150mm | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Test Method - Lab Testing
3.8 | Inspect Grid materials | OPS-QLDS-CI-SPE-003 REV 0: Section 4.4 | Each Delivery | Visual Inspection | AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680. | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.8 - Inspect Grid materials | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4 | Frequency - Each Delivery | Test Method - Visual Inspection | Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680. | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Acceptance Criteria - Grading C
3.9 | Compaction for Grid Base | OPS-QLDS-CI-SPE-003 REV 0: Section 4.3 | Each Grid | Visual Inspection | Compact sub-grade adequately to provide a firm foundation. | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.9 - Compaction for Grid Base | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.3 | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - Compact sub-grade adequately to provide a firm foundation. | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Verifying Documents - NATA Test Report
3.1 | Concrete Abutment/Install Base Slab (if required) | OPS-QLDS-CI-SPE-003 REV 0: Section 4.4 | Each Grid | Visual Inspection | Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.1 - Concrete Abutment/Install Base Slab (if required) | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4 | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: RSA - R
3.11 | Position and Install Grid | OPS-QLDS-CI-SPE-003 REV 0: Section 4.4 | Each Grid | Visual Inspection | Loaction and position in accordance with drawings as applicable | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.11 - Position and Install Grid | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4 | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - Loaction and position in accordance with drawings as applicable | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: Senex - W
3.12 | Install and Compact Gravel Ramps | Std Drawings | Each Grid | Visual Inspection | Ramps adequateley compacted | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.12 - Install and Compact Gravel Ramps | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - Ramps adequateley compacted | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | 2.1 - CH and FDM Clearance
3.13 | Attach Fence and Gates to Box Assembly | Std Drawings | Each Grid | Visual Inspection | In accordance with drawings | Grid CHAR(AMP)Fence Installation FIC | M | W | 3.13 - Attach Fence and Gates to Box Assembly | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - In accordance with drawings | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - M | Responsibility: Senex - W | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
3.14 | RSA QA inspection | OPS-QLDS-CI-SPE-003 REV 0: Section 4 | Each Grid | Visual Inspection | RSA Supervisor to inspect and accept the works are complete. | Grid CHAR(AMP)Fence Installation FIC | H | N/A | 3.14 - RSA QA inspection | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4 | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete. | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - H | Responsibility: Senex - N/A | Frequency - Each Track
3.15 | Client Signoff | OPS-QLDS-CI-SPE-003 REV 0: Section 4 | Each Grid | Visual Inspection | Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised. | Grid CHAR(AMP)Fence Installation FIC | N/A | H | 3.15 - Client Signoff | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4 | Frequency - Each Grid | Test Method - Visual Inspection | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised. | Verifying Documents - Grid CHAR(AMP)Fence Installation FIC | Responsibility: RSA - N/A | Responsibility: Senex - H | Test Method - Visual Inspection
4.1 | CH and FDM Clearance | SOW | Each Track | Visual Inspection | CH FDM clearance certificate | Lease Pad FIC | H | W | 4.1 - CH and FDM Clearance | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW | Frequency - Each Track | Test Method - Visual Inspection | Acceptance Criteria - CH FDM clearance certificate | Verifying Documents - Lease Pad FIC | Responsibility: RSA - H | Responsibility: Senex - W | Acceptance Criteria - CH FDM clearance certificate
4.2 | Identify work area, boundaries and survey requirement | Senex Specification/SOW/IFC | Each Pad | Set out by Licensed Surveyer | GIS Survey data | Lease Pad FIC | M | W | 4.2 - Identify work area, boundaries and survey requirement | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC | Frequency - Each Pad | Test Method - Set out by Licensed Surveyer | Acceptance Criteria - GIS Survey data | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Verifying Documents - Access Track FIC
4.3 | Clear CHAR(AMP) grade | OPS-QLDS-CI-SPE-002: Section 3.2 CHAR(AMP) 4 | Each Pad | Visual Inspection | Cleared vegetation and topsoil stockpiled at regular intervals. | Lease Pad FIC | M | W | 4.3 - Clear CHAR(AMP) grade | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.2 CHAR(AMP) 4 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Cleared vegetation and topsoil stockpiled at regular intervals. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: RSA - H
4.4 | Lease Entry Construction | OPS-QLDS-CI-SPE-002: Section 5 | Each Pad | Visual Inspection | Access points into the lease pad shall be 12.0m wide minimum. | Lease Pad FIC | M | W | 4.4 - Lease Entry Construction | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Access points into the lease pad shall be 12.0m wide minimum. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: Senex - W
4.5 | Lease construction | OPS-QLDS-CI-SPE-002 Rev 0 Sections 5 | Each Pad | Laser Level and Visual Inspection | Lease pad shall be minimum 78m long and 66m wide. Lease pad surface shall have a crossfall of between 0.65% to 1% | Lease Pad FIC | M | W | 4.5 - Lease construction | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002 Rev 0 Sections 5 | Frequency - Each Pad | Test Method - Laser Level and Visual Inspection | Acceptance Criteria - Lease pad shall be minimum 78m long and 66m wide. Lease pad surface shall have a crossfall of between 0.65% to 1% | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | 2.2 - Identify work area, boundaries and survey requirement
4.6 | Earthworks compaction of layers in 300m layers | OPS-QLDS-CI-SPE-002: Section 3.3.5 | Each Pad | Visual Inspection | AS1289.5.2.1, AS1289.5.1.1, AS1289.5.6.1, AS1289.5.1.1 | Lease Pad FIC | M | W | 4.6 - Earthworks compaction of layers in 300m layers | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.3.5 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - AS1289.5.2.1, AS1289.5.1.1, AS1289.5.6.1, AS1289.5.1.1 | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC and GIS
4.7 | Proof Roll | OPS-QLDS-CI-SPE-002: Section 4 CHAR(AMP) 5 | Each Pad | Visual Inspection | Proof roll the pad surface to identify any soft or loose zones which shall be stripped and stockpiles or tined, dried out and re-compacted. | Lease Pad FIC | H | H | 4.7 - Proof Roll | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 4 CHAR(AMP) 5 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Proof roll the pad surface to identify any soft or loose zones which shall be stripped and stockpiles or tined, dried out and re-compacted. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - H | Responsibility: Senex - H | Frequency - Each Track
4.8 | Verification of cross falls/laser set ups | OPS-QLDS-CI-SPE-002: Section 5 | Each Pad | Laser Level and Visual Inspection | The lease pad surface shall have a crossfall of 0.4% along pad width and 0.5% along pad length | Lease Pad FIC | M | W | 4.8 - Verification of cross falls/laser set ups | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5 | Frequency - Each Pad | Test Method - Laser Level and Visual Inspection | Acceptance Criteria - The lease pad surface shall have a crossfall of 0.4% along pad width and 0.5% along pad length | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Test Method - Set out by Licensed Surveyer
4.9 | Final Trim | OPS-QLDS-CI-SPE-002: Section 5 | Each Pad | Visual Inspection | Surface levels are in accordance wth drawings | Lease Pad FIC | H | H | 4.9 - Final Trim | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Surface levels are in accordance wth drawings | Verifying Documents - Lease Pad FIC | Responsibility: RSA - H | Responsibility: Senex - H | Acceptance Criteria - In accordance with IFC Drawing
4.1 | DCP test on hardstand | OPS-QLDS-CI-GAR-001 Rev 1A OPS-QLDS-CI-SPE-002 Rev 0 Sections 3.5 and 6 | Each Pad | DCP Test Record | Testing undertaken by Senex Representative on the final Layer. Minimum 4 blows per 100 mm. | Lease Pad FIC | W | H | 4.1 - DCP test on hardstand | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A OPS-QLDS-CI-SPE-002 Rev 0 Sections 3.5 and 6 | Frequency - Each Pad | Test Method - DCP Test Record | Acceptance Criteria - Testing undertaken by Senex Representative on the final Layer. Minimum 4 blows per 100 mm. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - W | Responsibility: Senex - H | Verifying Documents - Access Track FIC
4.11 | Gravel cap works (where required) | OPS-QLDS-CI-GAR-001 Rev 1A | Each Pad | Visual Inspection | Required 100-millimetre hardstand thickness | Lease Pad FIC | M | W | 4.11 - Gravel cap works (where required) | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Required 100-millimetre hardstand thickness | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: RSA - M
4.12 | Install ESC | SENEX-QLDS-EN-PRC-003 Rev 1 | Each Pad | Visual Inspection | As per IFC drawings | Lease Pad FIC | M | W | 4.12 - Install ESC | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-EN-PRC-003 Rev 1 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - As per IFC drawings | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Responsibility: Senex - W
4.13 | Cellar Installation | SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001 | Each Pad | Visual Inspection | Install cellar and conductor as per Senex Specifcations | Lease Pad FIC | M | W | 4.13 - Cellar Installation | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Install cellar and conductor as per Senex Specifcations | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | 2.3 - Confirm dimensions
4.14 | Conductor installation | SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001 | Each Pad | Visual Inspection | Install cellar and conductor as per Senex Specifcations | Lease Pad FIC | M | W | 4.14 - Conductor installation | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Install cellar and conductor as per Senex Specifcations | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
4.15 | Conductor cemented in place | SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001 | Each Pad | Visual Inspection | Conductor shall be concreted into the conductor bore with Neat Class A concrete with a compressive strength of 25MPa-32MPa. | Lease Pad FIC | M | W | 4.15 - Conductor cemented in place | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Conductor shall be concreted into the conductor bore with Neat Class A concrete with a compressive strength of 25MPa-32MPa. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Frequency - Each Track
4.16 | 4 x cattle panels to be installed | SENEX-QLDS-DR-SPE-001 | Each Pad | Visual Inspection | Installed approriately to barricade cellar. | Lease Pad FIC | M | W | 4.16 - 4 x cattle panels to be installed | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Installed approriately to barricade cellar. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - M | Responsibility: Senex - W | Test Method - Visual Inspection
4.17 | Well signage and pipeline entry mark completed | SENEX-QLDS-DR-SPE-001 | Each Pad | Visual Inspection | Senex supervisor to install Well signage. | Lease Pad FIC | N/A | W | 4.17 - Well signage and pipeline entry mark completed | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Senex supervisor to install Well signage. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - N/A | Responsibility: Senex - W | Acceptance Criteria - Standard road is 6m wide and maximum disturbed area is 10m
4.18 | As Built drawings | IFC Well Pad Cut Fill Lease Pad Layout Drawing,SOW | Each Pad | As Built Measurement | As built Lease Pad Layout Drawing including ESCP | Lease Pad FIC | N/A | W | 4.18 - As Built drawings | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC Well Pad Cut Fill Lease Pad Layout Drawing,SOW | Frequency - Each Pad | Test Method - As Built Measurement | Acceptance Criteria - As built Lease Pad Layout Drawing including ESCP | Verifying Documents - Lease Pad FIC | Responsibility: RSA - N/A | Responsibility: Senex - W | Verifying Documents - Access Track FIC
4.19 | RSA Supervispr inspection | SENEX-QLDS-DR-SPE-001 CHAR(AMP) OPS-QLDS-CI-SPE-002 | Each Pad | Visual Inspection | RSA Supervisor to inspect and accept the works are complete. | Lease Pad FIC | H | N/A | 4.19 - RSA Supervispr inspection | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 CHAR(AMP) OPS-QLDS-CI-SPE-002 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - H | Responsibility: Senex - N/A | Responsibility: RSA - M
4.2 | Client Signoff | SENEX-QLDS-DR-SPE-001 CHAR(AMP)OPS-QLDS-CI-SPE-002 | Each Pad | Visual Inspection | Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised. | Lease Pad FIC | N/A | H | 4.2 - Client Signoff | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 CHAR(AMP)OPS-QLDS-CI-SPE-002 | Frequency - Each Pad | Test Method - Visual Inspection | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised. | Verifying Documents - Lease Pad FIC | Responsibility: RSA - N/A | Responsibility: Senex - H | Responsibility: Senex - W
2.4 - Clear CHAR(AMP) grade
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 3.2
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - Cleared vegetation stockpiled at regular intervals.
Verifying Documents - Access Track FIC
Responsibility: RSA - M
Responsibility: Senex - W
2.5 - Form track profile
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - Roads flat grade and rills blended into shoulders
Verifying Documents - Access Track FIC
Responsibility: RSA - M
Responsibility: Senex - W
2.6 - Construct erosion and sediment controls
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - ESC IFC, SOW Section 4.3.2, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - Ensure site specific erosion and sediment control plan implemented.
Verifying Documents - Access Track FIC
Responsibility: RSA - M
Responsibility: Senex - W
2.7 - Install water way barriers
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC GAR, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2.12, SOW section 4.3.2, OPS-ATLS-CS-DWG-021 WP28 HILLANDALE CROSSING CID
Frequency - Each Crossing
Test Method - Visual Inspection
Acceptance Criteria - Crossings shall be battered to permit heavy vehicle access, bases may be boxed out and backfilled with compacted gravel as detailed in specific construction design and approved by Senex.
Verifying Documents - Access Track FIC
Responsibility: RSA - M
Responsibility: Senex - W
2.8 - Gravel cap access track
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - Compacted to 80 mm and from approved source.
Verifying Documents - Access Track FIC
Responsibility: RSA - M
Responsibility: Senex - W
2.9 - RSA QA inspection
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
Verifying Documents - Access Track FIC
Responsibility: RSA - H
Responsibility: Senex - N/A
2.1 - Final inspection of access tracks
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised.
Verifying Documents - Access Track FIC
Responsibility: RSA - N/A
Responsibility: Senex - H
3.1 - CH and FDM Clearance
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - CH FDM clearance certificate
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - H
Responsibility: Senex - W
3.2 - Identify work area, boundaries and survey requirement
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
Frequency - Each Fence ID
Test Method - Set out by Licensed Surveyer
Acceptance Criteria - GIS Survey Data
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.3 - Inspect fencing materials
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
Frequency - Each Delivery
Test Method - Visual Inspection
Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680.
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.4 - Installation of Fencing
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
Frequency - Each Fence ID
Test Method - Visual Inspection
Acceptance Criteria - Holes shall be a minimum of 250mm in diameter and 900mm deep, protude heights for strainer CHAR(AMP) coners posts shall be 1300mm, for stay blocks 300mm, for star pickets 1250mm, nominal depth for star pickets 550mm, Spacing between any 2 posts shall not be less than 3m or greater than 5m.
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.5 - Concrete for base of fencing
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
Frequency - Each Fence ID
Test Method - Visual Inspection
Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.6 - Welding
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
Frequency - Each Fence ID
Test Method - Visual Inspection
Acceptance Criteria - Stays shall be fully welded to posts and stay blocks, Gate hinges shall be fully welded to gates and posts, Welded joints to be coated with a zinc rich coating.
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.7 - Box out Grid Footings and Prep Site
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - No more than 150mm
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.8 - Inspect Grid materials
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
Frequency - Each Delivery
Test Method - Visual Inspection
Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680.
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.9 - Compaction for Grid Base
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.3
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - Compact sub-grade adequately to provide a firm foundation.
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.1 - Concrete Abutment/Install Base Slab (if required)
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.11 - Position and Install Grid
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - Loaction and position in accordance with drawings as applicable
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.12 - Install and Compact Gravel Ramps
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - Ramps adequateley compacted
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.13 - Attach Fence and Gates to Box Assembly
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - In accordance with drawings
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - M
Responsibility: Senex - W
3.14 - RSA QA inspection
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - H
Responsibility: Senex - N/A
3.15 - Client Signoff
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
Frequency - Each Grid
Test Method - Visual Inspection
Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
Verifying Documents - Grid CHAR(AMP)Fence Installation FIC
Responsibility: RSA - N/A
Responsibility: Senex - H
4.1 - CH and FDM Clearance
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
Frequency - Each Track
Test Method - Visual Inspection
Acceptance Criteria - CH FDM clearance certificate
Verifying Documents - Lease Pad FIC
Responsibility: RSA - H
Responsibility: Senex - W
4.2 - Identify work area, boundaries and survey requirement
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
Frequency - Each Pad
Test Method - Set out by Licensed Surveyer
Acceptance Criteria - GIS Survey data
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.3 - Clear CHAR(AMP) grade
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.2 CHAR(AMP) 4
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Cleared vegetation and topsoil stockpiled at regular intervals.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.4 - Lease Entry Construction
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Access points into the lease pad shall be 12.0m wide minimum.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.5 - Lease construction
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002 Rev 0 Sections 5
Frequency - Each Pad
Test Method - Laser Level and Visual Inspection
Acceptance Criteria - Lease pad shall be minimum 78m long and 66m wide. Lease pad surface shall have a crossfall of between 0.65% to 1%
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.6 - Earthworks compaction of layers in 300m layers
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.3.5
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - AS1289.5.2.1, AS1289.5.1.1, AS1289.5.6.1, AS1289.5.1.1
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.7 - Proof Roll
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 4 CHAR(AMP) 5
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Proof roll the pad surface to identify any soft or loose zones which shall be stripped and stockpiles or tined, dried out and re-compacted.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - H
Responsibility: Senex - H
4.8 - Verification of cross falls/laser set ups
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
Frequency - Each Pad
Test Method - Laser Level and Visual Inspection
Acceptance Criteria - The lease pad surface shall have a crossfall of 0.4% along pad width and 0.5% along pad length
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.9 - Final Trim
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Surface levels are in accordance wth drawings
Verifying Documents - Lease Pad FIC
Responsibility: RSA - H
Responsibility: Senex - H
4.1 - DCP test on hardstand
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A OPS-QLDS-CI-SPE-002 Rev 0 Sections 3.5 and 6
Frequency - Each Pad
Test Method - DCP Test Record
Acceptance Criteria - Testing undertaken by Senex Representative on the final Layer. Minimum 4 blows per 100 mm.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - W
Responsibility: Senex - H
4.11 - Gravel cap works (where required)
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Required 100-millimetre hardstand thickness
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.12 - Install ESC
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-EN-PRC-003 Rev 1
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - As per IFC drawings
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.13 - Cellar Installation
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Install cellar and conductor as per Senex Specifcations
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.14 - Conductor installation
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Install cellar and conductor as per Senex Specifcations
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.15 - Conductor cemented in place
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001 SENEX-QLDS-DR-SPE-001
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Conductor shall be concreted into the conductor bore with Neat Class A concrete with a compressive strength of 25MPa-32MPa.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.16 - 4 x cattle panels to be installed
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Installed approriately to barricade cellar.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - M
Responsibility: Senex - W
4.17 - Well signage and pipeline entry mark completed
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Senex supervisor to install Well signage.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - N/A
Responsibility: Senex - W
4.18 - As Built drawings
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC Well Pad Cut Fill Lease Pad Layout Drawing,SOW
Frequency - Each Pad
Test Method - As Built Measurement
Acceptance Criteria - As built Lease Pad Layout Drawing including ESCP
Verifying Documents - Lease Pad FIC
Responsibility: RSA - N/A
Responsibility: Senex - W
4.19 - RSA Supervispr inspection
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 CHAR(AMP) OPS-QLDS-CI-SPE-002
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - H
Responsibility: Senex - N/A
4.2 - Client Signoff
Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 CHAR(AMP)OPS-QLDS-CI-SPE-002
Frequency - Each Pad
Test Method - Visual Inspection
Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
Verifying Documents - Lease Pad FIC
Responsibility: RSA - N/A
Responsibility: Senex - H