## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RSA.WP28.ITP | itp |  |  |  |  | RSA.WP28.ITP
section | 1 - Preliminary
checkpoint | 1.1 - Access Documentation
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW
label | ○ LARS / PTA
label | ○ Cultural Heritage Clearance Request (Works Notice)
label | Frequency - Prior to Start
label | Test Method - Review
label | Acceptance Criteria - All documents in place and correct.
label | Verifying Documents - LARS / PTA
label | ○ Landholder Notification
label | ○ Weed Washdown Cert.
label | ○ Species and Fauna Management
label | ○ Cultural Heritage Induction Attendance Register
label | ○ Cultural Heritage Clearance Report / Form
label | Responsibility: RSA - H
label | Responsibility: Senex - H
holdpoint | HOLD POINT
checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
label | Frequency - Prior to Start
label | Test Method - Review
label | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
label | Verifying Documents - Weed Declaration Certificate.
label | ○ Appenate FFP Form
label | Responsibility: RSA - H
label | Responsibility: Senex - W
holdpoint | HOLD POINT
checkpoint | 1.3 - Gravel Compliance
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
label | Frequency - Each Quarry
label | Test Method - Lab Testing
label | Acceptance Criteria - Grading C
label | Verifying Documents - NATA Test Report
label | Responsibility: RSA - R
label | Responsibility: Senex - W
section | 2 - Access Tracks
checkpoint | 2.1 - CH and FDM Clearance
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - CH FDM clearance certificate
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - W
holdpoint | HOLD POINT
checkpoint | 2.2 - Identify work area, boundaries and survey requirement
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC and GIS
label | Frequency - Each Track
label | Test Method - Set out by Licensed Surveyer
label | Acceptance Criteria - In accordance with IFC Drawing
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 2.3 - Confirm dimensions
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - Standard road is 6m wide and maximum disturbed area is 10m
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 2.4 - Clear & grade
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 3.2
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - Cleared vegetation stockpiled at regular intervals.
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 2.5 - Form track profile
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - Roads flat grade and rills blended into shoulders
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 2.6 - Construct erosion and sediment controls
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - ESC IFC, SOW Section 4.3.2, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - Ensure site specific erosion and sediment control plan implemented.
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 2.7 - Install water way barriers
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC GAR, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2.12, SOW section 4.3.2, OPS-ATLS-CS-DWG-021 WP28 HILLANDALE CROSSING CID
label | Frequency - Each Crossing
label | Test Method - Visual Inspection
label | Acceptance Criteria - Crossings shall be battered to permit heavy vehicle access, bases may be boxed out and backfilled with compacted gravel as detailed in specific construction design and approved by Senex.
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 2.8 - Gravel cap access track
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - Compacted to 80 mm and from approved source.
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 2.9 - RSA QA inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - N/A
holdpoint | HOLD POINT
checkpoint | 2.10 - Final inspection of access tracks
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised.
label | Verifying Documents - Access Track FIC
label | Responsibility: RSA - N/A
label | Responsibility: Senex - H
holdpoint | HOLD POINT
section | 3 - In Field, Property Fencing and Grid (Fencing)
checkpoint | 3.1 - CH and FDM Clearance
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - CH FDM clearance certificate
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - W
holdpoint | HOLD POINT
checkpoint | 3.2 - Identify work area, boundaries and survey requirement
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
label | Frequency - Each Fence ID
label | Test Method - Set out by Licensed Surveyer
label | Acceptance Criteria - GIS Survey Data
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.3 - Inspect fencing materials
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
label | Frequency - Each Delivery
label | Test Method - Visual Inspection
label | Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680.
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.4 - Installation of Fencing
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
label | Frequency - Each Fence ID
label | Test Method - Visual Inspection
label | Acceptance Criteria - Holes shall be a minimum of 250mm in diameter and 900mm deep, protude heights for strainer & coners posts shall be 1300mm, for stay blocks 300mm, for star pickets 1250mm, nominal depth for star pickets 550mm, Spacing between any 2 posts shall not be less than 3m or greater than 5m.
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.5 - Concrete for base of fencing
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
label | Frequency - Each Fence ID
label | Test Method - Visual Inspection
label | Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.6 - Welding
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
label | Frequency - Each Fence ID
label | Test Method - Visual Inspection
label | Acceptance Criteria - Stays shall be fully welded to posts and stay blocks, Gate hinges shall be fully welded to gates and posts, Welded joints to be coated with a zinc rich coating.
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
section | 3 - In Field, Property Fencing and Grid (Grid)
checkpoint | 3.7 - Box out Grid Footings and Prep Site
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - No more than 150mm
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.8 - Inspect Grid materials
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
label | Frequency - Each Delivery
label | Test Method - Visual Inspection
label | Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680.
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.9 - Compaction for Grid Base
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.3
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - Compact sub-grade adequately to provide a firm foundation.
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.10 - Concrete Abutment/Install Base Slab (if required)
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.11 - Position and Install Grid
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - Loaction and position in accordance with drawings as applicable
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.12 - Install and Compact Gravel Ramps
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - Ramps adequateley compacted
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.13 - Attach Fence and Gates to Box Assembly
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - In accordance with drawings
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 3.14 - RSA QA inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - N/A
holdpoint | HOLD POINT
checkpoint | 3.15 - Client Signoff
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
label | Frequency - Each Grid
label | Test Method - Visual Inspection
label | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
label | Verifying Documents - Grid &Fence Installation FIC
label | Responsibility: RSA - N/A
label | Responsibility: Senex - H
holdpoint | HOLD POINT
section | 4 - Lease Pads
checkpoint | 4.1 - CH and FDM Clearance
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
label | Frequency - Each Track
label | Test Method - Visual Inspection
label | Acceptance Criteria - CH FDM clearance certificate
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - W
holdpoint | HOLD POINT
checkpoint | 4.2 - Identify work area, boundaries and survey requirement
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
label | Frequency - Each Pad
label | Test Method - Set out by Licensed Surveyer
label | Acceptance Criteria - GIS Survey data
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.3 - Clear & grade
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.2 & 4
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Cleared vegetation and topsoil stockpiled at regular intervals.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.4 - Lease Entry Construction
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Access points into the lease pad shall be 12.0m wide minimum.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.5 - Lease construction
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002 Rev 0 Sections 5
label | Frequency - Each Pad
label | Test Method - Laser Level and Visual Inspection
label | Acceptance Criteria - Lease pad shall be minimum 78m long and 66m wide. Lease pad surface shall have a crossfall of between 0.65% to 1%
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.6 - Earthworks compaction of layers in 300m layers
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.3.5
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - AS1289.5.2.1, AS1289.5.1.1, AS1289.5.6.1, AS1289.5.1.1
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.7 - Proof Roll
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 4 & 5
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Proof roll the pad surface to identify any soft or loose zones which shall be stripped and stockpiles or tined, dried out and re-compacted.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - H
holdpoint | HOLD POINT
checkpoint | 4.8 - Verification of cross falls/laser set ups
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
label | Frequency - Each Pad
label | Test Method - Laser Level and Visual Inspection
label | Acceptance Criteria - The lease pad surface shall have a crossfall of 0.4% along pad width and 0.5% along pad length
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.9 - Final Trim
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Surface levels are in accordance wth drawings
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - H
holdpoint | HOLD POINT
checkpoint | 4.10 - DCP test on hardstand
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A
label | ○ OPS-QLDS-CI-SPE-002 Rev 0 Sections 3.5 and 6
label | Frequency - Each Pad
label | Test Method - DCP Test Record
label | Acceptance Criteria - Testing undertaken by Senex Representative on the final Layer. Minimum 4 blows per 100 mm.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - W
label | Responsibility: Senex - H
holdpoint | HOLD POINT
checkpoint | 4.11 - Gravel cap works (where required)
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Required 100-millimetre hardstand thickness
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.12 - Install ESC
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-EN-PRC-003 Rev 1
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per IFC drawings
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.13 - Cellar Installation
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001
label | ○ SENEX-QLDS-DR-SPE-001
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Install cellar and conductor as per Senex Specifcations
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.14 - Conductor installation
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001
label | ○ SENEX-QLDS-DR-SPE-001
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Install cellar and conductor as per Senex Specifcations
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.15 - Conductor cemented in place
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001
label | ○ SENEX-QLDS-DR-SPE-001
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Conductor shall be concreted into the conductor bore with Neat Class A concrete with a compressive strength of 25MPa-32MPa.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.16 - 4 x cattle panels to be installed
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Installed approriately to barricade cellar.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - M
label | Responsibility: Senex - W
checkpoint | 4.17 - Well signage and pipeline entry mark completed
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Senex supervisor to install Well signage.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - N/A
label | Responsibility: Senex - W
checkpoint | 4.18 - As Built drawings
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC Well Pad Cut Fill Lease Pad Layout Drawing,SOW
label | Frequency - Each Pad
label | Test Method - As Built Measurement
label | Acceptance Criteria - As built Lease Pad Layout Drawing including ESCP
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - N/A
label | Responsibility: Senex - W
checkpoint | 4.19 - RSA Supervispr inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 & OPS-QLDS-CI-SPE-002
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - H
label | Responsibility: Senex - N/A
holdpoint | HOLD POINT
checkpoint | 4.20 - Client Signoff
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 &OPS-QLDS-CI-SPE-002
label | Frequency - Each Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
label | Verifying Documents - Lease Pad FIC
label | Responsibility: RSA - N/A
label | Responsibility: Senex - H
holdpoint | HOLD POINT
section | Reference Documents
checkpoint-no-status | Reference Documents:
label | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
label | OPS-QLDS-CI-SPE-003 REV 0 (Fencing, Grids and Gateways Civil Specification)
label | OPS-QLDS-CI-SPE-002 Rev 0 (Lease Pads, Hardstands, Access Roads Civil Specification)
label | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
label | SENEX-QLDS-CI-GDL-001 Rev D (Whoa-Boy Construction Guidelines)
label | SENEX-QLDS-DR-SPE-001 Rev 4 (Conductor and Cellar Installation Specification)
label | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
label | OPS-QLDS-CI-GAR-001 Rev 1A (Well Lease Layout Standard Drill Rig Civil General Arrangement)
section | To be completed upon completion of all work activities
checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
label | Completed By:
textbox | Contractor Representative - Name:
textbox | Contractor Representative - Position:
textbox | Senex Construction Representative - Name:
textbox | Senex Construction Representative - Position:
label | Approved By:
textbox | Client Representative - Name:
textbox | Client Representative - Position:
date | Date:
signoff | Add Signature