## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RSA.WP28.FIC - ACCESS TRACK | itp |  |  |  |  | RSA.WP28.FIC - ACCESS TRACK - Rev1.0
section | FIELD INSPECTION CHECKLIST ACCESS TRACK
checkpoint | CH and FDM clearance
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - Witness
holdpoint | HOLD POINT
checkpoint | Identify extent of work area, clearance boundaries and any required surveying works
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Measure access road dimensions as per IFC
label | Checked By: RSA - Monitor
label | Checked By: SENEX - N/A
checkpoint | Clear & Grub
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Form track profile
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Construct erosion and sediment controls
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Construct water way barriers crossings
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Gravel cap access track (if applicable)
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | RSA QA Inspection
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - N/A
holdpoint | HOLD POINT
checkpoint | Final Inspection of Access Tracks
label | Checked By: RSA - N/A
label | Checked By: SENEX - Hold Point
holdpoint | HOLD POINT
checkpoint | Verification of Work Completed:
textbox | RSA Supervisor - Name:
textbox | RSA Supervisor - Position:
textbox | Senex Representative - Name:
textbox | Senex Representative - Position:
date | Date:
signoff | Signature:
checklist | RSA.WP28.FIC - FENCING & GRIDS | itp |  |  |  |  | RSA.WP28.FIC - FENCING & GRIDS - Rev1.0
section | FIELD INSPECTION CHECKLIST FENCING & GRIDS
checkpoint | CH & FDM Clearance
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - Witness
holdpoint | HOLD POINT
checkpoint | Identify Work Area, boundaries of Fencing
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Inspect fencing materials
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Installation of fencing
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Concrete for base of fencing
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Welding
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Box Out Grid Footings and Prep Site
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Inspect grid materials
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Compaction for Grid base
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Concrete Abutment / Install Base Slab (if required)
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Position and Install Grid
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Install and Compact Gravel Ramps
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Attach Fence to Box Assembly
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | RSA QA inspection
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - N/A
holdpoint | HOLD POINT
checkpoint | Client Signoff
label | Checked By: RSA - N/A
label | Checked By: SENEX - Hold Point
holdpoint | HOLD POINT
checkpoint | Verification of Work Completed:
textbox | RSA Supervisor - Name:
textbox | RSA Supervisor - Position:
textbox | Senex Representative - Name:
textbox | Senex Representative - Position:
date | Date:
signoff | Signature:
checklist | RSA.WP28.FIC - LEASE PADS | itp |  |  |  |  | RSA.WP28.FIC - LEASE PADS - Rev1.0
section | FIELD INSPECTION CHECKLIST LEASE PADS
checkpoint | CH and FDM clearance
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - Witness
holdpoint | HOLD POINT
checkpoint | Identify work area, boundaries and survey requirement
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Clear & Grub Topsoil and stack timber
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Lease Entry Construction
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Lease construction
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Compaction of layers in 300mm layers
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Proof roll
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - Hold Point
holdpoint | HOLD POINT
checkpoint | Verification of cross falls/laser set ups
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Final Trim
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - Hold Point
holdpoint | HOLD POINT
checkpoint | DCP Testing
label | Checked By: RSA - Witness
label | Checked By: SENEX - Hold Point
holdpoint | HOLD POINT
checkpoint | Gravel Cap (as required)
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Install ESC
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Cellar Installation
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Conductor Installation – Record plumb
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Conductor cemented in place
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | 4 x cattle panels to be installed
label | Checked By: RSA - Monitor
label | Checked By: SENEX - Witness
checkpoint | Well signage and Pipeline entry mark completed
label | Checked By: RSA - N/A
label | Checked By: SENEX - Witness
checkpoint | As Built Completed
label | Checked By: RSA - N/A
label | Checked By: SENEX - Witness
checkpoint | RSA supervisor inspection
label | Checked By: RSA - Hold point
label | Checked By: SENEX - N/A
holdpoint | HOLD POINT
checkpoint | Client Signoff
label | Checked By: RSA - N/A
label | Checked By: SENEX - Hold Point
holdpoint | HOLD POINT
checkpoint | Verification of Work Completed:
textbox | RSA Supervisor - Name:
textbox | RSA Supervisor - Position:
textbox | Senex Representative - Name:
textbox | Senex Representative - Position:
date | Date:
signoff | Signature:
checklist | RSA.WP28.FIC - PRELIMINARY | itp |  |  |  |  | RSA.WP28.FIC - PRELIMINARY - Rev1.0
section | FIELD INSPECTION CHECKLIST LEASE PADS
checkpoint | Access documentation of relevant ATW, LARs/PTA, Cultural Heritage, Clearance Request
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - Hold Point
holdpoint | HOLD POINT
checkpoint | Mobilisation of Machinery & Fit for Purpose inspection
label | Checked By: RSA - Hold Point
label | Checked By: SENEX - Witness
holdpoint | HOLD POINT
checkpoint | Gravel Compliance
label | Checked By: RSA - Review
label | Checked By: SENEX - Witness
checkpoint | Verification of Work Completed:
textbox | RSA Supervisor - Name:
textbox | RSA Supervisor - Position:
textbox | Senex Representative - Name:
textbox | Senex Representative - Position:
date | Date:
signoff | Signature: