## Asphalt - Surfacing
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1101A - Te Ngarue Bridge |  | CPS Approver | Quality Approver | CPS Eng. | Greg Bailey
|  |  |  | Procedure: | Asphalt - Surfacing |  | Name / Signature | Name / Signature | Site Engineer | Craiug Klindsey
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Eddy Mardle
Lot No: B1101A - Te Ngarue Bridge |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 626 RP 0.009
Rev 2 - 13 September 2024
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Pre Construction
1.1 | Survey Setout - Milling | WITNESS | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report | Prior to commencement | Mark out on site | Visual inspection, Survey | Subcontractor QA, Photos, COR | Site Engineer
1.2 | Milling & Existing AC | MONITOR | Milling undertaken to correct depth of nominal thickness (<200m) | During operation | Maeasurements | Visual Inspection | Sub-contractor QA, Photos, COR | Site Engineer
2 | Material Compliance
2.1 | Binder Penetration Grade | WITNESS | To comply with NZTA M01: 2020 - Table 6.1 | Prior to commencement | Property Test | NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements | Lab Report | Site Engineer
2.2 | Coarse Aggregate Source | WITNESS | To comply with NZTA M10 - Refer to Section 2 | Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates. | Table 2.1 in NZTA M10 | Property Test | IANZ Report | Site Engineer
2.3 | Fine Aggregate Sources | WITNESS | To comply with NZTA M10 - Refer to Section 2 | Testing frequency shall be in accordance with CCNZ BPG05 Quality Assurance of Aggregates. | Table 2.2 in NZTA M10 | Property Test | IANZ Report | Site Engineer
3 | Construction
3.1 | Survey Setout - Paving | WITNESS | Determine paving run start/stop locations | Prior to commencement | Survey, Visual Inspection | Ensure accurate survey setting out is in place. | Subcontractor QA, Photos, COR | Site Engineer
3.2 | Weather Check | WITNESS | Ensure weather conditions are acceptable for work to proceed | Prior to commencement | Weather Forecast | Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C | Subcontractor QA, Photos, COR | Site Engineer
3.3 | Surface Preparation | WITNESS | Ensure previous layer is broomed clean. | Prior to commencement | Truck broom to have been used and surface approved by CPS Engineer | Visual inspection | Subcontractor QA, Photos, COR | Site Engineer
3.4 | Membrane seal | WITNESS | Application as per Design Requirements (Chip size / binder application rate) | Prior to asphalt Spray sheet for everyday. | Spray sheet, QA records | Application as per Design Requirements (Chip size / binder application rate) | Subcontractor QA, Photos, COR | Site Engineer
3.5 | Temperature of Asphalt for paving | WITNESS | The temperature of the asphalt shall enable compaction required to achieve air voids %.. | 1 test per 20m of a | Temperature Check | The asphalt shall have a minimum temperature of 80 degrees Celsius on completion of compaction. | Subcontractor QA, Photos, COR | Site Engineer
3.6 | Thickness (Cores) | HOLD | Layer thickness measured from core samples. | Each core taken for density | Core Test | ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications | Lab test report | Site Engineer | CPS Engineer
3.7 | Compaction and air voids | HOLD | To comply with NZTA M10: or project specification | AS per specification | NDM for Quality Control Only | NZTA M/10:Section 9.9.3 | IANZ Report, QA Records | Site Engineer | CPS Engineer
3.8 | Surface Finish and Roughness | HOLD | No visible cracks, defects related to poorly constructed joints, water ponding, | Post Construction Site walkover. | Visual inspection. | No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding. Good ride quality. | Subcontractor QA, Photos, COR | Site Engineer | CPS Engineer
4 | Post-Construction Closeout | [6 empty] | Assignee 1 | Assignee 2 | Assignee 2
4.1 | Construction Walkover (Snags) | HOLD | The Construction Walkover must be scheduled at least one week before the site's completion or demobilisation. Walkover must be attended by Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Before site works end | Construction Walkover Report: with date, list of attendees and full defect/snag list. Defect List closed by Final Approver or Transferred to Master Snag List. | Visual Inspection Quality Site Inspection Report (QSIR) | Walkover Report (COR or QSIR) Procore Defect List | Quality Engineer | CPS Engineer
4.2 | As-Built Survey & Red-Line Markups | HOLD | Redline mark-up drawings are to be reviewed and accepted by CPS. A survey of completed work must be requested and completed by the survey team. | At the completion of the ITP of work | All RFI, NCRs and site changes must be recorded on the red-line drawing. Signed and dated by author. Approved by CPS | Closed ABMS Survey Confirmation | Redline Markups Closed ABMS Survey Confirmation | Site Engineer | CPS Engineer
4.3 | Quality Assurance Deliverables | WITNESS | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the ITP | Ensure all QA is uploaded into Procore | Document Review | NCRs RFI's Approved Redline mark-ups | Quality Engineer
4.4 | Final Approvals | HOLD | Signoffs by Project Manager, Quality Manager and CPS Manager | At the completion of the ITP | Ensure all parties have signed and approved the ITP QA records as being complete. | Document Review | Signatures | Project Manager | Quality Manager | CPS Manager