## Sheet1
SOURCE TEXT | [8 empty] | CONCAT FIELDS | [8 empty] | OUTPUT
2.1 | Aggregate | VR 408.11 (a) VR 831.05 (c) | Aggregate shall comply with VR 831 - Aggregate for Sprayed Seal Bituminous Surfacing. Enter: Teambinder Approval number [free text box] | Document Review | Each Material | HP | PE/Nominated authority | This ITP TeamBinder Approval | 2.1 Aggregate | REFERENCE: VR 408.11 (a) VR 831.05 (c) | ACCEPTANCE CRITERIA: Aggregate shall comply with VR 831 - Aggregate for Sprayed Seal Bituminous Surfacing. Enter: Teambinder Approval number [free text box] | METHOD: Document Review | FREQUENCY: Each Material | CATEGORY: HP | RESPONSIBILITY: PE/Nominated authority | VERIFYING DOCUMENTS: This ITP TeamBinder Approval | Date Completed: | 2.1 Aggregate
REFERENCE: VR 408.11 (a) VR 831.05 (c)
ACCEPTANCE CRITERIA: Aggregate shall comply with VR 831 - Aggregate for Sprayed Seal Bituminous Surfacing. Enter: Teambinder Approval number [free text box]
METHOD: Document Review
FREQUENCY: Each Material
CATEGORY: HP
RESPONSIBILITY: PE/Nominated authority
VERIFYING DOCUMENTS: This ITP TeamBinder Approval
Date Completed:
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All text from the source ITP go to these columns. Remember to replace any ampersand characters (&) and less than symbols (<) with a placeholder string that’s easy to replace before importing it here!
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These fields concatenate everything from columns A-I (where the original source text is).
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the FILTERXML function that concatenates everything from columns K-S. Copy the output here and paste it into the checklist template.