## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-159-CIV-PSDS-Line marking
ITP Description: |  | PSDS-Line marking
Discipline (e.g. CIV/STR/RAIL: |  | 159-CIV
Revision Number: |  | 0
Revision Date: |  | 2023-10-13
ITP created by:
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Progress Street
Inspection & Test Plan - Line Marking
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-10-13
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | Vicroads Section 721February 2017 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | Vicroads Section 175November 2019 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | Vicroads Section 853 February 1994 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.2 | Type of marking material as shown on design drawings and shall conform to the Standard | Vicroads 721.A05 | Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier Provide the principle a list of materials that to be used with a certificate of conformance with associated test report | Document Review | Once | IP | SE/PE/SPE | Material certificate
2.3 | Raised Pavement Markers | Vicroads 721.A05 | Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175. (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.4 | Adhesive | Vicroads 721.A05 | Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation. Other types of adhesive materials shall only be used with the approval of the Superintendent | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.5 | Line marking and Road marking Paint | Vicroads 721.A05 | All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175. | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.6 | Glass beads | Vicroads 721.A05 | Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042. | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.7 | Pristine glass beads (Type B-HR) | Vicroads 721.A05 | Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042. Pristine glass beads (Type B-HR) Type B-HR glass beads shall comply with the properties of Type B (AS 2009:2006) drop-on glass beads, with an additional high performance retro reflectivity requirement, requiring the delivery of a minimum 450 mcd/lux.m², when tested in accordance with a modified Appendix M | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
3 | Preliminaries - Procedures & Documentation
3.1 | Accreditation to Painting Contractors Certification Program | Vicroads 721.D01 | Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO. Enter: Teambinder Approval number [free text box] | Document Review | Once | HP | Nominated Authority | ConQA Hold Point Release PCCP Accreditation
4 | Post-construction Activities
4.1 | Retroreflectivity Report | Vicroads 721.B06 (b) | Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12. | Document Review | Per lot | HP* | SE/PE/SPE | This ITP
4.2 | Job Completion Report | Vicroads 721.B06 (a) | For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings). | Document review | Per lot When applicable | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /