## Sheet1
Enviro Systems Checklist - Enviro B-LV+HP1200+700X+250NS
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | CIDD Alerts
SECTION | BATCH DETAIL NUMBER OF PRODUCTS
Checkpoint | Enviro B-LV
Label | Record Batch Number
Checkpoint | Sika Flex FC/ Enviro Flex FC
Label | Record Batch Number
Checkpoint | Enviro HP1200
Label | Record Batch Number
Checkpoint | Enviro 700X
Label | Record Batch Number
Checkpoint | Enviro 250NS
Label | Record Batch Number
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | Samples Submitted
Label | Submit samples for approval as per Specific Material Requirements.
Label | Records - Subcontractor Contracts Admin Confirmation
Label | Sample Approval Ref.
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Records - Site Engineer/ Foreman Confirmation
Checkpoint | Material Management & Storage - Envirosystems TDS
Label | Store materials in a dry, clean place away from direct sunlight as per TDS
Label | Records - Time stamped photograph
Checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
Label | Records - Time stamped photograph
Checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
Label | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
Label | Records - Time stamped photograph
checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
Label | FC sheeting to have max 6mm gap at floor/wall junction. Sheets to be set with manufacturers base coat, including all nails, penetrations and corners. Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
Label | Records - Time stamped photograph
Checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
Label | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
Label | Records - Site Engineer/ Foreman Confirmation
Checkpoint | Cracks in Substrate - AS2870 Table 2.10
Label | Ensure no substrate cracks greater than 1.6mm.
Label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
Label | Records - Time stamped photograph
SECTION | SUBSTRATE PREPERATION: AS 4654.2-2012
Checkpoint | Substrate Preperation - Witness Point
Label | Ensure Surface is prepared to receive primer application. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary. - Record by timestamped photograph.
SECTION | EPOXY B-LV - PRIME COAT
Checkpoint | Moisture Content - Witness Point
Label | Check Moisture content of substrate, not to exceed 6% ( Min.1 test per 10m2.) - Record with Tramex Moisture Reader - Provide timestamped photograph
Checkpoint | Weather/RH - Witness Point
Label | Apply within 5-35°C RH must be 0-85% - Provide screenshot of weather reading.
Checkpoint | Product Mixing - Witness Point
Label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | Primer Application - Witness Point
Label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns. Ensure Primer is dry and tack free (within 24 hours) prior to next coat. - Record by timestamped photograph.
SECTION | BOND BREAKER
Checkpoint | Primer Application - Witness Point
Label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Bond breaker to be tack free prior to coating. - Record thickness with a fillet gauge. - Provide timestamped photograph.
SECTION | ENVIRO HP1200- BASE COAT
Checkpoint | Weather/RH - Witness Point
Label | Apply within 5-35°C RH must be 0-85% - Provide screenshot of weather reading.
Checkpoint | Product mixing - Witness Point
Label | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
Checkpoint | HP1200 Application - Witness Point
Label | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing. Mix Part B thoroughly with a mechanical power mixer before use. - Provide timestamped photographs.
CheckPoint | QA TESTING - Hold Point
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2) - Conduct Electronic Leak Testing ( ELT) and rectify as required. - Record DFT with Positector. - Provide timestamped photograph.
SECTION | ENVIRO 700X COATING - PRIME COAT
Checkpoint | Weather/RH
Label | • Product to be applied at temperatures no less than 10C or no more than 35C. • RH must be between 35-85%
Checkpoint | Product Mixing
Label | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | 700X Application
Label | • Enviro 700X to be applied by squeegee, roller or brush on substrate. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
SECTION | ENVIRO 700X COATING - SECOND COAT
Checkpoint | Weather/RH
Label | • Product to be applied at temperatures no less than 10C or no more than 35C. • RH must be between 35-85%
Checkpoint | Product Mixing
Label | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | 700X Application
Label | • Enviro 700X to be applied by roller or brush to finished membrane. • Allow each coat to sufficiently dry before proceeding to the next step.
Checkpoint | QA TESTING
Label | • Inspect after installation of finishes to check for any damages to waterproofing. • Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.(1 test per 10m2) • Conduct Electronic Leak Testing ( ELT) to entire area.
SECTION | 250NS APPLICATION
Checkpoint | Weather/RH
Label | • Product to be applied at temperatures no less than 10C or no more than 35C. • RH must be between 35-85%
Checkpoint | Mixing
Label | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
Checkpoint | 250NS Application
` | • 250NS to be applied using roller and brush. •Ensure Product is cured for 24 hours prior to second coat.
SECTION | 250NS APPLICATION-SECOND COAT
Checkpoint | Weather/RH
Label | • Product to be applied at temperatures no less than 10C or no more than 35C. • RH must be between 35-85%
Checkpoint | Mixing
Label | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
Checkpoint | 250NS Application
` | • 250NS to be applied using roller and brush. •Ensure Product is cured for 24 hours prior to second coat.
SECTION | DETAILING- EACH LOCATION
CHECKPOINT | Vertical Termination Detailing - AS 4654.2
Label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
Label | Records - time stamped photograph
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman Detailing inspection review
SIGNOFF | Site Engineer/foreman inspection sign off