## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Rectification Works Checklist |  |  |  |  | Yes | Rectification Works Checklist | 037adf84-0c1c-4b3a-947f-3972f89dec53
checkpoint-status |  |  | checkpoint | Damage identification
checkpoint-status |  |  | checkpoint | Repair and Test
checkpoint-status |  |  | checkpoint | Area sign off complete
checklist-flat |  |  | checklist | PVC Sheet Membrane |  |  |  |  | Yes | PVC Sheet Membrane | 0b641beb-a132-48ac-b62b-964f53277f4d
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 1b464033-50fe-5045-bc3d-7bc23ed84976 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 4e48b173-a3e5-51f6-a2c6-b96cf8722e42 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Liquid Membranes Checklist |  |  |  |  | Yes | Liquid Membranes Checklist | 287c30b8-391a-4655-aac3-5acb68f0c012
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | e317d3f5-635d-5f69-a18a-3bd0c0286754 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 9143fd72-4c47-543b-ab73-722a836f330a |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | 3 Coat Checklist |  |  |  |  | Yes | 3 Coat Checklist | 2f1866f8-1a1d-4ef7-97d9-732fea09b682
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 7ff0cfb0-7f10-512c-bfff-e61879d59aac |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | f0f35ec9-c1b9-51cf-8587-928e302f1766 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | 2d3b7556-e45f-5a0a-84e0-c095b3cd740a |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 372d3bd7-2ef0-5282-95d5-3284f9f2e45c |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 3rd Coat
select | 4d3647db-a577-544b-8ff7-1b4647f4840b |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | 74005109-6eee-54da-ac13-e093c302cb27 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 73bb0bec-31a0-5260-ad20-6955897b7d99 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 073fef58-690a-56de-8236-db30030f37da |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Trafficable Liquid Membrane |  |  |  |  | Yes | Trafficable Liquid Membrane | 6e88aea9-19a4-4d80-acc5-6b785fce5b1c
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 76f96476-33fb-5465-81b3-514d802b7a2a |  | note | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of Top Coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Screed Checklist |  |  |  |  | Yes | Screed Checklist | 7506d012-7d58-4103-b538-8f2fbfb786ad
checkpoint-status |  |  | checkpoint | Mixing of Topcem Pronto
checkpoint-status |  |  | checkpoint | Application of Topcem Pronto
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Planters Checklist |  |  |  |  | Yes | Planters Checklist | 7a6aaebf-5136-4acb-9c9e-27fdc0ee1d39
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | a165b21d-15cb-58e9-a730-c980323205c0 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Installation of Corflute Protection Board Completed
checkpoint-status |  |  | checkpoint | Installation of Drainage Cell Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Waterstop-Penebar |  |  |  |  | Yes | Waterstop-Penebar | 8efe88c1-0a37-4949-9ad8-513340ffb3b2
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Penetron Penebar SW55
checkpoint-status |  |  | checkpoint | Ensure all Butt Joints are completed as per TDS
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checklist-flat |  |  | checklist | 2 Coat Checklist |  |  |  |  | Yes | 2 Coat Checklist | 90745591-1776-4d4e-a6ca-6904f173ea37
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | a6b3bf57-bd3d-5d3a-b4da-1e18d7b5841b |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 35fdb900-ac83-5960-88b5-ac944b77c42d |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
label | d5811fbd-30f4-5234-bd46-b250676ccfbc |  | note | Cementious Coving completed (if required)
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | 4a1cdb1d-154b-5efd-8b9a-013a95eb45d5 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | ab3bdbb7-4d84-5575-bf12-2203fc060c0c |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | 3e413fd0-70ba-59f5-acb3-a030cca2aff4 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 657f04a6-3009-5639-b679-49aacec6962e |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | e177f318-5e57-570c-96ef-61ac63f74251 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | External Liquid Membrane Checklist |  |  |  |  | Yes | External Liquid Membrane Checklist | 974b42cb-5811-471e-ac0c-e589ca91093e
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 05b5270d-ebcf-5f4a-b622-a3227e2369e6 |  | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of top coat (if required)
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board completed (if required)
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Sika Sarnafil PVC Sheet Membrane Checklist |  |  |  |  | Yes | Sika Sarnafil PVC Sheet Membrane Checklist | ba492212-1953-4866-a47d-862314c9b1b3
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 6cee6c8e-69bb-5b5c-92b8-a5e421150d30 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 9ee4381e-2257-5384-8422-e6c36cb671ca |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Sarnacol Adhesive to substrate
checkpoint-status |  |  | checkpoint | Application of Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | Application of Non-Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Sarnabar Termination
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Windows and Doors |  |  |  |  | Yes | Windows and Doors | bece64ff-fbc5-437a-a500-b675a7ba39a5
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
label | f83d838f-3210-59e2-b205-5539dd2c8267 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Internal Wet Areas Checklist |  |  |  |  | Yes | Internal Wet Areas Checklist | c276b7d4-c835-437a-bc40-32fe069e72f7
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 1af5b040-1b77-5aac-a946-afe5edb38ad5 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat |  |  | checklist | Polyurea Spray Checklist |  |  |  |  | Yes | Polyurea Spray Checklist | cc7e1d9e-7bad-49da-92df-394857b3eb9a
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | 4fed111a-731e-55b6-8b77-7942895989a5 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Atmospheric conditions
label | 0920899c-e7f2-5706-8c58-eb447e46279b |  | note | Note ambient temp, Relative Humidity, Dew Point
checkpoint-status |  |  | checkpoint | Product Batch Numbers
label | 68b50a90-bbf0-5bab-a4aa-1b17ed94ada9 |  | note | Note batch numbers for products used
checkpoint-status |  |  | checkpoint | Equipment used
label | 1c6763b5-1360-5b36-a9fc-64d199a691a2 |  | note | Note equipment used like rollers etc.
checkpoint-status |  |  | checkpoint | Fixing/Repairing
label | 04cc1233-219b-5024-8642-d8d7537e23eb |  | note | All voids/cracks to be sealed
checkpoint-status |  |  | checkpoint | Priming & Sanding
label | 9a7fb444-b8e9-5332-8647-db49ffb77b5c |  | note | Primer coat to be applied and Sand to be spread across surface
checkpoint-status |  |  | checkpoint | Polyurea Spray
label | a99dc12c-6814-52c3-96ca-93ac50e4ccd4 |  | note | Polyurea spray coat to be applied uniformly across surface
checklist-flat |  |  | checklist | Polyglass Spider P Checklist |  |  |  |  | Yes | Polyglass Spider P Checklist | dfb34ef3-b5a4-4a72-8092-1791bea31873
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | e1d75dde-149d-5b89-8e77-d61d4596b3af |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Atmospheric conditions
label | 3f894024-2501-55f6-b491-c507ba3751bc |  | note | Note ambient temp, Relative Humidity, Dew Point
checkpoint-status |  |  | checkpoint | Product Batch Numbers
label | c40724f8-81b2-5c8c-8b2a-c785632b896a |  | note | Note batch numbers for products used
checkpoint-status |  |  | checkpoint | Equipment used
label | a9afca6a-6abd-5d79-9fe1-9aa873edc5fd |  | note | Note equipment used like rollers etc.
checkpoint-status |  |  | checkpoint | Apply Primer to substrate
label | a6551b2b-cd61-589d-a2e2-00f3ef4f0b35 |  | note | Primer coat to be applied uniformly across surface
checkpoint-status |  |  | checkpoint | Apply Polyglass Spider P Membrane
label | 441c4d69-05c8-508f-8b43-d6f9e76c25b4 |  | note | Check that all laps are correct and use heavy duty roller on the seams
checklist-flat |  |  | checklist | PVC Tanks Checklist |  |  |  |  | Yes | PVC Tanks Checklist | e93a47d2-798e-46c2-8ad0-47596f62d48a
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | c600cdab-d0b3-5a71-b51a-3307d4e66ab3 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | a37f85dd-4c86-526f-ba18-a32678c15e6c |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Probe Test
checkpoint-status |  |  | checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Balconies Checklist |  |  |  |  | Yes | Balconies Checklist | ed45e6f1-7662-44ab-8499-71839a315b43
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | b7dfa74e-3587-5d46-bd6b-c08bba625987 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | abc59bd2-a391-59b8-a7a7-0144a7ca7435 |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per spec
checkpoint-status |  |  | checkpoint | Application of Caulking or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-1st Coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-2nd Coat
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.