## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Liquid Membranes Checklist |  |  |  |  | Yes | Liquid Membranes Checklist | 0a73eb1e-1584-4060-a483-b83f46ba811c
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 31b15020-ecc7-5655-9f59-e70711f0b7f8 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 3dad1b7b-4f7c-5a4c-baf0-e9fd0880de9f |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | PVC Sheet Membrane |  |  |  |  | Yes | PVC Sheet Membrane | 416a80a4-c0d3-4ee9-aafd-78cd97a5bc71
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 0a07b854-0c83-543c-ba45-b0c01da2b25d |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | cb85a521-fc1a-5104-bce3-fda6e102702e |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Sika Sarnafil PVC Sheet Membrane Checklist |  |  |  |  | Yes | Sika Sarnafil PVC Sheet Membrane Checklist | 674efd21-9f90-4156-a630-c27c4377da42
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 2654c583-d24d-57c0-aa5b-cdf57a527493 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 371d5c0a-b7d3-51eb-8606-ef996486c6cd |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Sarnacol Adhesive to substrate
checkpoint-status |  |  | checkpoint | Application of Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | Application of Non-Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Sarnabar Termination
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Screed Checklist |  |  |  |  | Yes | Screed Checklist | 8429729c-623f-4ba1-9401-2c7e3f2136dd
checkpoint-status |  |  | checkpoint | Mixing of Topcem Pronto
checkpoint-status |  |  | checkpoint | Application of Topcem Pronto
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Internal Wet Areas Checklist |  |  |  |  | Yes | Internal Wet Areas Checklist | 8541d1ba-e751-4755-9342-ba952ea9365e
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | e1f68993-2201-535d-85db-22dd0fa37fca |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat |  |  | checklist | Rectification Works Checklist |  |  |  |  | Yes | Rectification Works Checklist | 86336a76-c933-449e-96c2-7d26351cdc66
checkpoint-status |  |  | checkpoint | Damage identification
checkpoint-status |  |  | checkpoint | Repair and Test
checkpoint-status |  |  | checkpoint | Area sign off complete
checklist-flat |  |  | checklist | Waterstop-Penebar |  |  |  |  | Yes | Waterstop-Penebar | 903fe810-be62-4b11-a6f0-d84c9549e08c
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Penetron Penebar SW55
checkpoint-status |  |  | checkpoint | Ensure all Butt Joints are completed as per TDS
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checklist-flat |  |  | checklist | External Liquid Membrane Checklist |  |  |  |  | Yes | External Liquid Membrane Checklist | 950c7925-cd9f-403d-b1d1-d5d2217c5220
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 0e7ab9a6-1b19-5564-b44c-9582fe038692 |  | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of top coat (if required)
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board completed (if required)
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Planters Checklist |  |  |  |  | Yes | Planters Checklist | b9121402-f1f2-44a4-98f0-c0138df8598a
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | afaace47-8903-51be-9fcc-6a1fac1a8881 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Installation of Corflute Protection Board Completed
checkpoint-status |  |  | checkpoint | Installation of Drainage Cell Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | 2 Coat Checklist |  |  |  |  | Yes | 2 Coat Checklist | c576525b-fc4b-445f-89b4-884491b39b4b
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 43d65a05-6b8e-5a22-8afb-2d1ae8d7f61c |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | a2950da8-c07c-5c31-ae60-747db1a0fd20 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
label | 63a37a95-c693-526c-ab70-30f1c93f565e |  | note | Cementious Coving completed (if required)
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | af843f05-d969-5506-9c2d-6dd446fbc0e7 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 0fd54e2f-f67f-58b0-8d2d-4f7a5f0c0c69 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | 2f3c797c-e299-56c5-94b6-ec24344185b4 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | c01d04de-7044-50ac-9282-abe666fe9c24 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 42e1c011-37ea-5e66-9ae5-dfbc11fbac1d |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Polyurea Spray Checklist |  |  |  |  | Yes | Polyurea Spray Checklist | cc7e1d9e-7bad-49da-92df-394857b3eb9a
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | 4fed111a-731e-55b6-8b77-7942895989a5 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Atmospheric conditions
label | 0920899c-e7f2-5706-8c58-eb447e46279b |  | note | Note ambient temp, Relative Humidity, Dew Point
checkpoint-status |  |  | checkpoint | Product Batch Numbers
label | 68b50a90-bbf0-5bab-a4aa-1b17ed94ada9 |  | note | Note batch numbers for products used
checkpoint-status |  |  | checkpoint | Equipment used
label | 1c6763b5-1360-5b36-a9fc-64d199a691a2 |  | note | Note equipment used like rollers etc.
checkpoint-status |  |  | checkpoint | Fixing/Repairing
label | 04cc1233-219b-5024-8642-d8d7537e23eb |  | note | All voids/cracks to be sealed
checkpoint-status |  |  | checkpoint | Priming & Sanding
label | 9a7fb444-b8e9-5332-8647-db49ffb77b5c |  | note | Primer coat to be applied and Sand to be spread across surface
checkpoint-status |  |  | checkpoint | Polyurea Spray
label | a99dc12c-6814-52c3-96ca-93ac50e4ccd4 |  | note | Polyurea spray coat to be applied uniformly across surface
checklist-flat |  |  | checklist | Trafficable Liquid Membrane |  |  |  |  | Yes | Trafficable Liquid Membrane | d6bd9082-7886-4885-9eb4-a28946e443f2
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 9806bb1a-eba7-5639-81a0-9e0fb6779fb9 |  | note | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of Top Coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Polyglass Spider P Checklist |  |  |  |  | Yes | Polyglass Spider P Checklist | dfb34ef3-b5a4-4a72-8092-1791bea31873
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | e1d75dde-149d-5b89-8e77-d61d4596b3af |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Atmospheric conditions
label | 3f894024-2501-55f6-b491-c507ba3751bc |  | note | Note ambient temp, Relative Humidity, Dew Point
checkpoint-status |  |  | checkpoint | Product Batch Numbers
label | c40724f8-81b2-5c8c-8b2a-c785632b896a |  | note | Note batch numbers for products used
checkpoint-status |  |  | checkpoint | Equipment used
label | a9afca6a-6abd-5d79-9fe1-9aa873edc5fd |  | note | Note equipment used like rollers etc.
checkpoint-status |  |  | checkpoint | Apply Primer to substrate
label | a6551b2b-cd61-589d-a2e2-00f3ef4f0b35 |  | note | Primer coat to be applied uniformly across surface
checkpoint-status |  |  | checkpoint | Apply Polyglass Spider P Membrane
label | 441c4d69-05c8-508f-8b43-d6f9e76c25b4 |  | note | Check that all laps are correct and use heavy duty roller on the seams
checklist-flat |  |  | checklist | Windows and Doors |  |  |  |  | Yes | Windows and Doors | ebcd6d93-10df-4b2d-acd4-71a947bc4f6a
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
label | 10c4e1cf-7a19-56c5-96d4-1bab75e00944 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | PVC Tanks Checklist |  |  |  |  | Yes | PVC Tanks Checklist | f10b8ad3-ca4f-4999-96c5-c8fcacdea530
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 41e20c81-f65a-55ba-a3c3-eaf4ab88679e |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | e65f5b53-696a-53d3-ad37-1ecaa49131cf |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Probe Test
checkpoint-status |  |  | checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Balconies Checklist |  |  |  |  | Yes | Balconies Checklist | fa201187-b56b-4b74-9bd7-fbdca705ff77
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 8b825064-3996-5bbd-b786-334766361ef9 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 36f86351-322e-560b-8f04-8fbe9e034fb9 |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per spec
checkpoint-status |  |  | checkpoint | Application of Caulking or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-1st Coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-2nd Coat
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
checklist-flat |  |  | checklist | 3 Coat Checklist |  |  |  |  | Yes | 3 Coat Checklist | fd804e45-26fa-4b9d-8989-8017e3eedb7a
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | c630055d-9789-5a2b-b402-391b441f013a |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 085df708-2d61-5315-93c6-e8504bd94f28 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | d9731044-b767-55e3-a9b0-1b8ae6bc6c3e |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 19031bb5-add2-5342-ad7d-65dffa59ee06 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 3rd Coat
select | 77c7b76a-e390-5b8e-b4fc-d2944258a8a4 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | ce8b8572-8795-5fd0-a9cf-b88c6435e92e |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 53214781-59cd-5b0f-afc4-3345e57b522b |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | cc7f644f-685a-5273-90e6-63f0f8004cfb |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable