## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | 2 Coat Checklist |  |  |  |  | Yes | 2 Coat Checklist | 05928985-c9af-4f60-8433-88fafe4970af
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | d3b33646-f15d-574a-8476-28c4b545fe9a |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | d660e689-cd79-5cd6-9fef-6270b9f47d8f |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
label | 552870b5-975a-57ed-adb6-9044170b8f93 |  | note | Cementitious Coving completed (if required)
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | 9c6035b7-1c87-51f5-b4e1-4492ab97237b |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 4ad0fe28-1fe2-5c23-ba7c-0297d34437d9 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | 2dc72630-69f1-5e32-a90a-051072046ab1 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 3e96cd2e-0dbc-54b4-8d36-da8827e2950c |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | aa5182cf-7c6d-55a9-8bef-05bd689260ba |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Internal Wet Areas Checklist |  |  |  |  | Yes | Internal Wet Areas Checklist | 075891e2-a17e-4fc9-9a2d-0925e2c7d0c1
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | ec9a814e-dd8f-5647-aea8-6bf895d4fcca |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat |  |  | checklist | PVC Sheet Membrane |  |  |  |  | Yes | PVC Sheet Membrane | 3022c42e-2f69-432e-937d-2019ba897a24
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 0911c42f-919e-5034-90ec-fba343d57f8d |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | c68a1b3c-8073-519e-a632-f91cc4c090d5 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Waterstop-Penebar |  |  |  |  | Yes | Waterstop-Penebar | 34d78705-d22c-4d07-ac8a-fd49b5e68b21
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Penetron Penebar SW55
checkpoint-status |  |  | checkpoint | Ensure all Butt Joints are completed as per TDS
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checklist-flat |  |  | checklist | Polyglass Spider P Checklist |  |  |  |  | Yes | Polyglass Spider P Checklist | 3b746d33-c85f-45ea-9be6-6f7208c6299a
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | f0e9bf44-f8e6-5b80-9eb3-5116cf387a5d |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Apply Primer to substrate
label | a619962a-6abb-5c6a-a075-1530ff42a110 |  | note | Primer coat to be applied uniformly across surface
checkpoint-status |  |  | checkpoint | Apply Polyglass Spider P Membrane
label | 64aa08de-61ad-5e04-b97b-b2d39737a261 |  | note | Check that all laps are correct and use heavy duty roller on the seams
checklist-flat |  |  | checklist | Balconies Checklist |  |  |  |  | Yes | Balconies Checklist | 54906266-408c-43ad-88b0-1c1f6deb63d5
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | d5feb80e-0320-5311-8e5b-e4ff3d595d2b |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 28676aed-07a1-55ae-a4ff-72e4d01488f3 |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per spec
checkpoint-status |  |  | checkpoint | Application of Caulking or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-1st Coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-2nd Coat
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
checklist-flat |  |  | checklist | External Liquid Membrane Checklist |  |  |  |  | Yes | External Liquid Membrane Checklist | 584a642a-bcd4-4d02-b318-f86a74acca39
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 31859021-0dc2-52c7-a89b-d228ad3e58b0 |  | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of top coat (if required)
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corflute Protection Board completed (if required)
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Windows and Doors |  |  |  |  | Yes | Windows and Doors | 5f0cab4b-a085-4d90-aea9-fc4c36399042
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
label | 14633ca7-b6e6-5d69-843e-62d2b5da92fe |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Polyurea Spray Checklist |  |  |  |  | Yes | Polyurea Spray Checklist | 7cb4a331-768f-4667-a786-73e8bfc5e3a9
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | d25cd77c-3094-5f8d-948a-ed990eb89008 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Fixing/Repairing
label | daa0d57b-ed8e-51a0-b7f8-30f47428c471 |  | note | All voids/cracks to be sealed
checkpoint-status |  |  | checkpoint | Priming & Sanding
label | 41501d92-02ad-5c74-8698-2c8a847db349 |  | note | Primer coat to be applied and Sand to be spread across surface
checkpoint-status |  |  | checkpoint | Polyurea Spray
label | b643fa46-7268-55d7-8e33-010f5c4e7821 |  | note | Polyurea spray coat to be applied uniformly across surface
checklist-flat |  |  | checklist | Liquid Membranes Checklist |  |  |  |  | Yes | Liquid Membranes Checklist | 99b9541d-40f7-426b-aed7-2bd0df9dfa97
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 2bf0e9a8-496d-58a3-a241-f5f0077f464c |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 1635ee37-85d3-54c6-92ea-4519e67d8ba0 |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Trafficable Liquid Membrane |  |  |  |  | Yes | Trafficable Liquid Membrane | c86724f1-51df-4f72-9477-90a23f068039
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 721b312d-156c-5f32-b9a4-9e371a02eac8 |  | note | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of Top Coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corflute Protection Board Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Rectification Works Checklist |  |  |  |  | Yes | Rectification Works Checklist | d5368771-e579-4dd2-b6a9-3ba77b09186f
checkpoint-status |  |  | checkpoint | Damage identification
checkpoint-status |  |  | checkpoint | Repair and Test
checkpoint-status |  |  | checkpoint | Area sign off complete
checklist-flat |  |  | checklist | Planters Checklist |  |  |  |  | Yes | Planters Checklist | d602af84-805f-4069-b828-0baf4dccb0e2
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 14881c1f-686d-5466-a212-0f1619dac62c |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Installation of Corflute Protection Board Completed
checkpoint-status |  |  | checkpoint | Installation of Drainage Cell Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | PVC Tanks Checklist |  |  |  |  | Yes | PVC Tanks Checklist | eab83168-1306-4fb8-8b7f-0a6542418606
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 00540b36-4244-555d-9763-63f6ed147c77 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | cb5de948-977b-531e-8bb0-d58626e59983 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Probe Test
checkpoint-status |  |  | checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Sika Sarnafil PVC Sheet Membrane Checklist |  |  |  |  | Yes | Sika Sarnafil PVC Sheet Membrane Checklist | ef7c9988-1e52-4e92-9d8f-50e38c47aaad
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 3de27a56-452b-5532-b692-2a2ef025ccdb |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 2b93ef16-ac1a-5fec-9e3a-0a10567c72a9 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Sarnacol Adhesive to substrate
checkpoint-status |  |  | checkpoint | Application of Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | Application of Non-Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Sarnabar Termination
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Screed Checklist |  |  |  |  | Yes | Screed Checklist | faeb070d-bc43-47c0-bafc-931b0c11af6c
checkpoint-status |  |  | checkpoint | Mixing of Topcem Pronto
checkpoint-status |  |  | checkpoint | Application of Topcem Pronto
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | 3 Coat Checklist |  |  |  |  | Yes | 3 Coat Checklist | fe4c0e95-c9c9-4745-88d4-37153975bdb6
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 79e4c507-76c9-5acd-9947-b84b9b34fe0a |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | a0d30985-313a-54de-b0fa-127de2bc4c07 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | 024314b0-6c57-5761-8e4a-026be9b3039f |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | fe3c77a6-ca6a-5160-862c-15b2b30b23b0 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 3rd Coat
select | 8e547dad-b190-5547-b2dd-c56623e2a247 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | 8ccbbf4d-00f8-55eb-804f-2b1d4327f322 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | abf8b90d-aeba-5e9c-becd-07d5d7c71655 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 28ed52ab-2ad0-54a8-9b88-383655c65239 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable