## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Internal Wet Areas Checklist |  |  |  |  | Yes | Internal Wet Areas Checklist | 00e1ccda-4d6c-46a6-aaef-7f2b06fecc87
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | f2870832-2cbc-5172-9a89-678705ea5f5e |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat |  |  | checklist | Sika Sarnafil PVC Sheet Membrane Checklist |  |  |  |  | Yes | Sika Sarnafil PVC Sheet Membrane Checklist | 2fb87d65-93b4-4d81-a10d-cb7016114f24
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 9b1b1b72-22f8-5712-99dd-b27afbd42563 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | f1d09094-2654-5283-9f4b-db6619289d67 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Sarnacol Adhesive to substrate
checkpoint-status |  |  | checkpoint | Application of Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | Application of Non-Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Sarnabar Termination
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Corflute Protection Board - Supply and Install Checklist |  |  |  |  | Yes | Corflute Protection Board - Supply and Install Checklist | 543c7a03-4bf2-4fa7-961d-64d411175fef
checkpoint-status |  |  | checkpoint | Install Corflute Protection Board
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 7b21c5c7-1479-58f7-aabb-61428cd5f7de |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 144f6a02-2bde-530c-ba2c-e7b5d1132d66 |  | button | Builder final inspection - If applicable attach signature below | Yes, No
button | 204e5c68-3d66-5d36-bcbc-917c40f2cbd4 |  | button | SSQLD final inspection - If applicable attach signature below | Yes, No
checklist-flat |  |  | checklist | PVC Tanks Checklist |  |  |  |  | Yes | PVC Tanks Checklist | 6e9e822f-8467-4c9d-a7b1-196cd217840f
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 2fc09f82-5db2-5f61-8a17-99aafebb080d |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | c55935b3-05d7-53b6-b2df-d1648ca01c32 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Probe Test
checkpoint-status |  |  | checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Liquid Membranes Checklist |  |  |  |  | Yes | Liquid Membranes Checklist | 840aba35-f030-46e4-b17f-5c2c2ebb6850
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 1964fe18-d6b0-5bda-b287-871ca1afa13c |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 6412e0d9-bf1c-5827-9e4b-8301981a41b8 |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Rectification Works Checklist |  |  |  |  | Yes | Rectification Works Checklist | 90a4478e-ba8b-4eaf-9dac-70b9a55ecb49
checkpoint-status |  |  | checkpoint | Damage identification
checkpoint-status |  |  | checkpoint | Repair and Test
checkpoint-status |  |  | checkpoint | Area sign off complete
checklist-flat |  |  | checklist | Windows and Doors |  |  |  |  | Yes | Windows and Doors | 92383c66-5437-4a1a-8789-ccff96385d01
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
label | cfba8a00-1ec7-5a46-a812-78e1c70c574c |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-sectioned |  |  | checklist | Waterproofing Installation Checklist |  |  |  |  | Yes | Waterproofing Installation Checklist | 9c003869-f493-44fc-b259-93aa06bb381e
checkpoint-group |  |  | section | Surface Preparation
checkpoint-status |  |  | checkpoint | Surface Temperature: pass
checkpoint-status |  |  | checkpoint | Dew Point: pass
checkpoint-status |  |  | checkpoint | Moisture Test: pass
label | 78d19610-65e3-58e5-8547-92cc6609f87d |  | note | Must be below 5% to pass - enter moisture % below
text | d9d1f385-aeac-5dfc-ad0c-7aee51b19a8c |  | textbox | Moisture Test %
checkpoint-status |  |  | checkpoint | RH %: pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 8cfa3b80-3a55-55dd-a250-b25db6c1fed4 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | c933dbce-5162-551b-a4fe-25c185b7374c |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 268b201f-63b4-581b-a78e-408f5e29e869 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system
checkpoint-status |  |  | checkpoint | Additional products installed / used - select from below and pass
select | 264ebb65-a7d2-5955-b98b-a99e6a7d7542 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 274ad0d4-20e1-546e-8b94-e00fa1bc7791 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 9b443bf5-6b5f-5256-bcc4-34574f8430e5 |  | button | Builder final inspection - If applicable attach signature below | Yes, No
button | 1af5d971-440f-5868-b52b-5895205d17ec |  | button | SSQLD final inspection - If applicable attach signature below | Yes, No
checklist-flat |  |  | checklist | Waterstop - Supply and Install Checklist |  |  |  |  | Yes | Waterstop - Supply and Install Checklist | 9c0e2cc4-135b-41df-a937-5a72a82562c7
checkpoint-status |  |  | checkpoint | Install waterstop
select | 1aa898c7-bd08-5af4-b275-86d459622ff5 |  | dropdown | Product Used | Penetron Penebar SW55 hydrophilic waterstop - dual layer,Waterstop Angle,Aluminium Waterstop Angle
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | fd533d0f-f1f8-5adc-8837-4b89f180d0b9 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | fcdf3d0c-3fe5-5a5c-abec-345abd5a2bd2 |  | button | Builder final inspection - If applicable attach signature below | Yes, No
button | 6bba6f01-75ed-557b-ab36-52d630fc9597 |  | button | SSQLD final inspection - If applicable attach signature below | Yes, No
checklist-flat |  |  | checklist | 2 Coat Checklist |  |  |  |  | Yes | 2 Coat Checklist | af23dcf2-3b42-4e71-b674-8702ae8c8eb1
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | ba693508-9c5c-597d-b903-1f96e65111f2 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 23b21969-7f06-5113-b661-85e7b16c8bf1 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
label | 13c9fd79-4484-5dce-a8d6-99bc3e317853 |  | note | Cementious Coving completed (if required)
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | d38fd967-970b-5885-8234-a809e0c25ad2 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 5d5f3288-72ba-590c-9a05-dfb12aa07fcb |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | fd492ab2-7e62-5023-b1fd-b49a255b3e00 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 5e4d25ca-0b1e-505c-80d8-472dea828b82 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 72180436-86ba-55de-9a94-8256c9a7fdbb |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Planters Checklist |  |  |  |  | Yes | Planters Checklist | c0572df0-d3a8-48fb-98ec-b84873d57fbc
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 78176596-80b7-5893-9793-78cdaccc208c |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Installation of Corflute Protection Board Completed
checkpoint-status |  |  | checkpoint | Installation of Drainage Cell Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Waterstop-Penebar |  |  |  |  | Yes | Waterstop-Penebar | c1fb28bf-2c83-46d1-aa07-c0fd45930ad2
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Penetron Penebar SW55
checkpoint-status |  |  | checkpoint | Ensure all Butt Joints are completed as per TDS
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checklist-flat |  |  | checklist | Screed Checklist |  |  |  |  | Yes | Screed Checklist | d0a875e9-6009-455e-a00f-06d6629d5ed8
checkpoint-status |  |  | checkpoint | Mixing of Topcem Pronto
checkpoint-status |  |  | checkpoint | Application of Topcem Pronto
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | 3 Coat Checklist |  |  |  |  | Yes | 3 Coat Checklist | d9f5b2b3-b518-4fb4-838b-48ea9610c868
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | ec100b6b-0a26-5513-9d15-a417cedf8187 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | fca4cad7-7e2c-5f41-9274-09dd8afdd128 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | 9b424664-c69f-537d-a0f2-d81276cddbe2 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | acf772ac-5a6f-532e-8b5b-68e0bae2d79c |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 3rd Coat
select | 39388fb7-2eae-5372-b71f-5d5ea29ee841 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | dc619e8f-3e9d-594a-a74d-e217be0bbff2 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | eea23393-fc38-5e2a-be82-f6360a52b338 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 22ce95df-069f-5a88-94e2-2e0df46fb1a2 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | PVC Sheet Membrane |  |  |  |  | Yes | PVC Sheet Membrane | dbd0c5f1-9384-4132-a796-9eb985a78bc9
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | ea77a153-cf02-55fc-899c-d3cd07dc6088 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 263b2162-9b15-5de3-bf58-d69a1bddf64e |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Balconies Checklist |  |  |  |  | Yes | Balconies Checklist | f3b1e266-f47e-4f66-abf6-fbec072458e8
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 993a0c6c-32aa-53e5-931a-bc6b36c8004c |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 30a3a734-3c02-560d-aeb2-ddb67c3684cc |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per spec
checkpoint-status |  |  | checkpoint | Application of Caulking or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-1st Coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-2nd Coat
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
checklist-flat |  |  | checklist | External Liquid Membrane Checklist |  |  |  |  | Yes | External Liquid Membrane Checklist | f3dd5478-960b-4b34-8ab2-f56e62300947
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | e8669840-d412-5c66-8c0d-d08fe943b50a |  | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of top coat (if required)
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board completed (if required)
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Trafficable Liquid Membrane |  |  |  |  | Yes | Trafficable Liquid Membrane | f8b99df8-26ea-422f-9bdd-12b68dcae9a2
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 45b3aee5-b19b-5848-8dd1-ec91dff871a7 |  | note | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of Top Coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable