## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Waterstop - Supply and Install Checklist |  |  |  |  | Yes | Waterstop - Supply and Install Checklist | 14aa0488-e0ef-4606-bf8f-b881e36ec806
checkpoint-status |  |  | checkpoint | Install waterstop
select | 6a9d48e3-8741-51e2-b62d-370faf2633a6 |  | dropdown | Product Used | Penetron Penebar SW55 hydrophilic waterstop - dual layer,Waterstop Angle,Aluminium Waterstop Angle
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 88a71e1a-094f-537f-8375-e35724e8bd8b |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | eb49b334-bd8e-5069-93fd-a807b1d5d73e |  | button | Builder final inspection - If applicable attach signature below | Yes, No
button | e1645db4-78a9-5085-89e2-cc8be606da1a |  | button | SSQLD final inspection - If applicable attach signature below | Yes, No
checklist-flat |  |  | checklist | Planters Checklist |  |  |  |  | Yes | Planters Checklist | 1a8a7261-1e35-4f19-91f9-014bfdf7371b
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 38a266cf-b164-5e6c-aa5d-8743e8ac0937 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Installation of Corflute Protection Board Completed
checkpoint-status |  |  | checkpoint | Installation of Drainage Cell Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Screed Checklist |  |  |  |  | Yes | Screed Checklist | 238c9c43-bee7-4899-89d9-16dda7888399
checkpoint-status |  |  | checkpoint | Mixing of Topcem Pronto
checkpoint-status |  |  | checkpoint | Application of Topcem Pronto
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-sectioned |  |  | checklist | Waterproofing Installation Checklist |  |  |  |  | Yes | Waterproofing Installation Checklist | 451ec03a-c0b9-4325-8200-ba31a14b7c64
checkpoint-group |  |  | section | Surface Preparation
checkpoint-status |  |  | checkpoint | Surface Temperature: pass
checkpoint-status |  |  | checkpoint | Dew Point: pass
checkpoint-status |  |  | checkpoint | Moisture Test: pass
label | f1bf4aaf-5126-555d-865b-c03e444594e4 |  | note | Must be below 5% to pass - enter moisture % below
text | b02c08f9-32d3-55ad-b888-09f7ca19064e |  | textbox | Moisture Test %
checkpoint-status |  |  | checkpoint | RH %: pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | e440b76b-0ebc-5bb2-b15a-6f6ec717d3df |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | 54eb11cd-a818-563d-b918-6a8fc4612d22 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | ce7a92a3-7305-5ba9-a40d-5a3eb1ecd17a |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system
checkpoint-status |  |  | checkpoint | Additional products installed / used - select from below and pass
select | 2970b22d-dad3-51ef-8adf-a9b0c014e2de |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | a2ad1e55-0445-5176-becc-1f4dd38324b1 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | da86e4f6-4af3-55b5-bfc6-7f20f035b02c |  | button | Builder final inspection - If applicable attach signature below | Yes, No
button | 7c9ec915-b3bf-5302-9674-96a44479080b |  | button | SSQLD final inspection - If applicable attach signature below | Yes, No
checklist-flat |  |  | checklist | Windows and Doors |  |  |  |  | Yes | Windows and Doors | 4757ac37-351d-406b-a52b-f4af777496d2
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
label | ff9e366f-e141-5af1-be09-4eac7d8853da |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | External Liquid Membrane Checklist |  |  |  |  | Yes | External Liquid Membrane Checklist | 4e716f8b-f73c-43d6-8fc0-d9ac0d05d8ae
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 6e125b4e-bd08-5ae5-922c-0fc745df598f |  | note | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of top coat (if required)
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board completed (if required)
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | 2 Coat Checklist |  |  |  |  | Yes | 2 Coat Checklist | 5c28b947-a04c-4ad8-b2c8-5c0caa69eb22
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 83883d95-ed52-541e-9b44-fcae31fa7c9d |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 79c58791-4953-57ff-b23b-6ebad6cc63b2 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
label | 9c6543f9-4629-5701-b244-6671e5db3814 |  | note | Cementious Coving completed (if required)
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | 8f3658a6-b26e-5028-b750-1a1936538bd2 |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 3d8f93de-152e-5290-acc8-32986f18673a |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | ffb53e54-dbe1-54ee-8f91-3a95cad84c68 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | d0b606c9-586f-55ce-b44f-f118a3f3a932 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 58f6dcce-9337-534a-b785-f3751464f75e |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Corflute Protection Board - Supply and Install Checklist |  |  |  |  | Yes | Corflute Protection Board - Supply and Install Checklist | 5cdc2e5d-66cf-4767-ad65-789148e69bb8
checkpoint-status |  |  | checkpoint | Install Corflute Protection Board
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | 6341425f-ceaf-51f9-b4e5-a3f4f86c2782 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 9ddf2b62-1865-5fbb-bd8c-aa9b1fd5cd52 |  | button | Builder final inspection - If applicable attach signature below | Yes, No
button | d98a000b-676c-595d-9ec5-0d561d63950b |  | button | SSQLD final inspection - If applicable attach signature below | Yes, No
checklist-flat |  |  | checklist | PVC Tanks Checklist |  |  |  |  | Yes | PVC Tanks Checklist | 60e03176-44b2-4c89-be38-3ee406827239
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | c5db6621-e82a-5324-8ce2-95afc5f18d06 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | be3fba22-9b9a-540e-bbea-f0e26ef8e151 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Probe Test
checkpoint-status |  |  | checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Internal Wet Areas Checklist |  |  |  |  | Yes | Internal Wet Areas Checklist | 703364a3-d8b4-45c4-9096-4dee8b639712
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 43652320-d73a-5280-9671-c73363ab041a |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat |  |  | checklist | Sika Sarnafil PVC Sheet Membrane Checklist |  |  |  |  | Yes | Sika Sarnafil PVC Sheet Membrane Checklist | 7a166913-324f-4f62-aa47-3a53280df53c
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 38d7175b-d22e-582a-aee4-8e9bd51027aa |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 5d0b8310-4b46-5027-91fe-559aa87f34ab |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Sarnacol Adhesive to substrate
checkpoint-status |  |  | checkpoint | Application of Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | Application of Non-Felt PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Sarnabar Termination
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | PVC Sheet Membrane |  |  |  |  | Yes | PVC Sheet Membrane | 8ac443fe-48f1-43a2-bfe3-8258bf6dcb3c
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete-result in comments below
label | 8363dafa-4966-5d82-8e38-5c19fb6b781c |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | cca76789-cee7-5935-a535-fdf60ef114bc |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Geofabric to substrate
checkpoint-status |  |  | checkpoint | Application of PVC Sheet Membrane
checkpoint-status |  |  | checkpoint | PVC Sheet Membrane Detailing as required
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checkpoint-status |  |  | checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat |  |  | checklist | Waterstop-Penebar |  |  |  |  | Yes | Waterstop-Penebar | 9247cff6-8ada-4bb1-9ee1-27b1ffdb2527
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Penetron Penebar SW55
checkpoint-status |  |  | checkpoint | Ensure all Butt Joints are completed as per TDS
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint-status |  |  | checkpoint | Test 1 Probe Test Pass/Fail
checklist-flat |  |  | checklist | Balconies Checklist |  |  |  |  | Yes | Balconies Checklist | cb479c2d-3950-4d31-b9bf-e6fa93f4d85f
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 5ed5707d-2de4-58d1-8401-2ebbe3b07318 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | b8a1c783-2fd6-5eab-854e-13fd1310e799 |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per spec
checkpoint-status |  |  | checkpoint | Application of Caulking or Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-1st Coat
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet
checkpoint-status |  |  | checkpoint | Application of membrane as per project spec-2nd Coat
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
checklist-flat |  |  | checklist | Polyurea Spray Checklist |  |  |  |  | Yes | Polyurea Spray Checklist | cc7e1d9e-7bad-49da-92df-394857b3eb9a
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | 4fed111a-731e-55b6-8b77-7942895989a5 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Atmospheric conditions
label | 0920899c-e7f2-5706-8c58-eb447e46279b |  | note | Note ambient temp, Relative Humidity, Dew Point
checkpoint-status |  |  | checkpoint | Product Batch Numbers
label | 68b50a90-bbf0-5bab-a4aa-1b17ed94ada9 |  | note | Note batch numbers for products used
checkpoint-status |  |  | checkpoint | Equipment used
label | 1c6763b5-1360-5b36-a9fc-64d199a691a2 |  | note | Note equipment used like rollers etc.
checkpoint-status |  |  | checkpoint | Fixing/Repairing
label | 04cc1233-219b-5024-8642-d8d7537e23eb |  | note | All voids/cracks to be sealed
checkpoint-status |  |  | checkpoint | Priming & Sanding
label | 9a7fb444-b8e9-5332-8647-db49ffb77b5c |  | note | Primer coat to be applied and Sand to be spread across surface
checkpoint-status |  |  | checkpoint | Polyurea Spray
label | a99dc12c-6814-52c3-96ca-93ac50e4ccd4 |  | note | Polyurea spray coat to be applied uniformly across surface
checklist-flat |  |  | checklist | Trafficable Liquid Membrane |  |  |  |  | Yes | Trafficable Liquid Membrane | d5f261f7-b976-41ba-99d5-d94b907e477f
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 65dd3f36-e644-544e-bdec-691c3b0e2c7a |  | note | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint-status |  |  | checkpoint | Application of Primer (if required) as per specification
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-1st coat
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint-status |  |  | checkpoint | Application of Top Coat
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Installation of Corlute Protection Board Completed
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | Polyglass Spider P Checklist |  |  |  |  | Yes | Polyglass Spider P Checklist | dfb34ef3-b5a4-4a72-8092-1791bea31873
checkpoint-status |  |  | checkpoint | Substrate inspected, cleaned if required and accepted
label | e1d75dde-149d-5b89-8e77-d61d4596b3af |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Atmospheric conditions
label | 3f894024-2501-55f6-b491-c507ba3751bc |  | note | Note ambient temp, Relative Humidity, Dew Point
checkpoint-status |  |  | checkpoint | Product Batch Numbers
label | c40724f8-81b2-5c8c-8b2a-c785632b896a |  | note | Note batch numbers for products used
checkpoint-status |  |  | checkpoint | Equipment used
label | a9afca6a-6abd-5d79-9fe1-9aa873edc5fd |  | note | Note equipment used like rollers etc.
checkpoint-status |  |  | checkpoint | Apply Primer to substrate
label | a6551b2b-cd61-589d-a2e2-00f3ef4f0b35 |  | note | Primer coat to be applied uniformly across surface
checkpoint-status |  |  | checkpoint | Apply Polyglass Spider P Membrane
label | 441c4d69-05c8-508f-8b43-d6f9e76c25b4 |  | note | Check that all laps are correct and use heavy duty roller on the seams
checklist-flat |  |  | checklist | Liquid Membranes Checklist |  |  |  |  | Yes | Liquid Membranes Checklist | e02de842-5089-41aa-971a-a46f9cad77ab
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 4f23ab5b-06d5-5a5a-9956-46eebc36434e |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Moisture Test Result (if required)
label | 766b9d35-814a-5615-88bd-762db09ef1dd |  | note | Provide moisture test results if concrete placement<28 days
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Bond Breaker completed
checkpoint-status |  |  | checkpoint | Application of Membrane as per project specification
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checklist-flat |  |  | checklist | 3 Coat Checklist |  |  |  |  | Yes | 3 Coat Checklist | efe08e3d-148e-4647-b02c-d58478d6f1f3
checkpoint-status |  |  | checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint-status |  |  | checkpoint | Moisture test complete - result in comments below
label | 4268cedc-3419-5099-978e-66156cb31520 |  | note | Must be below 5% to pass
checkpoint-status |  |  | checkpoint | Substrate inspected and accepted
label | 4b50112b-b6da-5663-80e4-b9c2f560d669 |  | note | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint-status |  |  | checkpoint | Application of Primer as per specification
checkpoint-status |  |  | checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 1st Coat
select | f29e9cda-31bb-5779-ae69-c33677511d1a |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 2nd Coat
select | 0d176bca-1b84-5b86-b020-7bc6b10b4b6b |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Application of membrane as per project specification - 3rd Coat
select | e5b4e658-67a6-51f4-9cbd-36677f0f025f |  | dropdown | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint-status |  |  | checkpoint | Additional products / elements installed - selected all that apply below
select | f5a21636-e9f4-5ba8-8bbd-5c7a8d263fff |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 75aae9c8-d607-56f6-bc06-556b587d9f31 |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | 3f52e381-771a-5257-9b40-e1f733467e9a |  | dropdown | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint-status |  |  | checkpoint | Final DFT Thickness of Membrane
checkpoint-status |  |  | checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint-status |  |  | checkpoint | Test 1 Flood Test
checkpoint-status |  |  | checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat |  |  | checklist | Rectification Works Checklist |  |  |  |  | Yes | Rectification Works Checklist | fbf80d01-d9d4-414a-950f-af9c7bb13681
checkpoint-status |  |  | checkpoint | Damage identification
checkpoint-status |  |  | checkpoint | Repair and Test
checkpoint-status |  |  | checkpoint | Area sign off complete