## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
Project Name: | SH58 Safety Improvements, Stage 2B - M2TG | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi (NZTA) | [5 empty] | B | Report by Breach | CM | Construction Manager
Contract Number: | DS2681 | [5 empty] | C | Check | ER | Engineers Representative (Assisstant)
Area/ Sub-System: | Bridge 7 |  |  | Lot ID Number: | TBC |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | DS2681-SH58-ITP-C-029 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Bored Piles | [5 empty] | I | Inspection | PM | Project Manager
Discipline: | Infrastructure | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | SH58 Project Specification - M2TG | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | 80510096-02B-330 Series. | [5 empty] | S | Subcontractor | SP | Supervisor (Piling)
[7 empty] | V | Visual Verification | ST | Superintendent (Piling)
Prepared By: | Jamie Nisbet |  |  | Date: | 2025-09-04 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [6 empty] | T | Field Testing
SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  |  |  |  | Date: | 2025-09-07
Downer Approval |  | Name: | Diliban Sengottian |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Sam Parkinson |  |  | Signature: |  |  |  |  | Date:

## Construction
SECTION 2 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location/ Hold Points
2.01 | Open Drilling | Pile Card | ASG (SESOC NZGS) Bored Pile Spec Cl 3.9 | • Pile location (offsets) • Drilling Start and Finish Time • Depth of water encountered. • Description of material encountered at regular 1m intervals and when new layers encountered (Specifically record depth at which Rock level is found) • Time and depth at which obstructions were encountered. | Pile Card | Per Pile | Witness Point | W | SE
2.02 | Installation of casing | Check verticality using digital level | PS CL 24.5.4 | Verticality Tolerance - No greater than 1:75 (Horizontal: Vertical) Casing Length | Pile Card/Photos | Per Pile | Witness Point | W | SE
2.03 | Drilling of Rock Socket | Agreement of Final Socket Depth | PS CL 24.5.4 | Rock depth to be confirmed by the Engineer with guidance from the contractor and drill operators. Rock depth to be noted on the pile card. Pile card shall be signed by Engineer. Following establishment of Rock Depth, Engineer to confirm socket depth | Pile Card & ConQA Sign-off | Per Pile | Hold Point | H | ER
2.04 | CCTV of Rock Socket | Shaft cleanliness CCTV | ASG (SESOC NZGS) Bored Pile Spec Cl 3.8 & PS CL 24.5.5 | Casing inspected visually using mirrors and spotlights as required. CCTV to be used for rock socket. Suitable flocculant to be used, as necessary, | CCTV Footage & ConQA Sign-off | Per Pile | Hold Point | H | ER
2.05 | Following Completion of Rock Socket | Final measurement of pile length | ASG (SESOC NZGS) Bored Pile Spec Cl 3.8 & PS CL 24.5.4 | Following completion of rock socket and cleaning. Pile depth to be measured and noted on the pile card | Pile Card | Per Pile | Witness Point | W | SE
2.06 | Reinforcement Cage - Placement | Reinforcing cage placing | PS Cl 24.5.4 | Nominal cover = 75mm Cage length measure and trimmed to size to maintain bottom cover Lengthen as required by Engineer. | Pile Card & ConQA Sign-off | Per pile | Witness Point | W | SE
2.07 | Reinforcement Cage - Spacers | Spacer Wheel Installation | PS Cl 24.5.4 | 4no. wheels per 4-5m vertically (2x sets on pile P2) and on 4 sides of the cage Horizontally i.e. at 12, 3, 6 & 9 on a clock face | Pile Card, Photos & ConQA Sign-off | Per pile | Witness Point | W | SE
2.08 | Reinforcement Cage - Survey | Top hook level/cage levelling | PS Cl 24.5.4 | Measure top of pile concrete to top of hooks to ensure correct cage level. | Pile Card | Per pile | Witness Point | W | SE
2.09 | Pre-pour Inspection | Pre-pour Inspection | PS Cl 24.1.17 | Pre-pour inspection with Engineer Sign-off | ConQA Sign-off | Per Pile | Hold Point | H | ER
2.1 | Concrete Pour - Cylinders | Test Cylinders | PS Cl 24.5.5 | A set of specimens for compression tests shall consist of 4 specimens from each sample of concrete. 1no. tested at 7 days and 3no. tested at 28 days. (Actual spec requirement is 3no. At 28days) Strength of pile concrete = 40MPa Slump test must also be carried out | Lab Report | Per batch | Witness Point | W | SE
2.11 | Concrete Pour - Dockets | Tremie pour mix Bored Piles and Hard Piles | PS Cl 24.5.5 | Correct mix design brought to site Concrete Docket Showing: • Mix Design Item Code • 28 day specified strength = 40MPa • concrete placement method that the mix was designed for - Tremie • type of supplementary cementitious materials (if used); • slump (target and actual slump when measured); • Order and Delivery Quantity • Load Time out of plant • To site time • Unload Time • Associated Products e.g. cement and additives | Concrete Docket | Per truckload | Witness Point | W | SE
2.12 | Concrete Pour - Slump | Slump Test | PS Cl 24.5.5 | Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm | Photos | Per truckload | Witness Point | W | SE
2.13 | Concrete Pour - Pour Height Measure | Pour Height above top of pile | PS Cl 24.5.5 | Minimum over-cast of 0.3m to be measured against mark on casing. | Pile Card | Per pile | Witness Point | W | SE
2.14 | Pile Card Sign-off | Engineer Sign-off | N/A | Sign off of Pile Card | Pile Card | Per Pile | Hold Point | H | ER
2.15 | PIT Testing | PIT Testing | PS Cl 24.5.5 | Specialist external testing contractor to provide analysis of the pile identifying any flaws, the method used to determine them, and an interpretation of their significance. Report to be sent to the Engineer for review. | Test Report | Per Pile - min 7 days Post Pour | Hold Point | H | ER
2.16 | Survey as-built | Survey as-built | PS Cl 26.4 & AS2159 (Page 167) | Not more than 75mm horizontally and 25mm vertically from their true position. Top of casing level. | As-built survey CAD File | Per pile | Witness Point | W | SE