## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
Project Name: | SH58 Safety Improvements, Stage 2B - M2TG | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi (NZTA) | [5 empty] | B | Report by Breach | CM | Construction Manager
Contract Number: | DS2681 | [5 empty] | C | Check | ER | Engineers Representative (Assisstant)
Area/ Sub-System: | Bridge 7 |  |  | Lot ID Number: | TBC |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | DS2681-SH58-ITP-M-013 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Bored Piles Materials | [5 empty] | I | Inspection | PM | Project Manager
Discipline: | Infrastructure | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | SH58 Project Specification - M2TG | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | 80510096-02B-330 Series. | [5 empty] | S | Subcontractor | SP | Supervisor (Piling)
[7 empty] | V | Visual Verification | ST | Superintendent (Piling)
Prepared By: | Jamie Nisbet |  |  | Date: | 2025-09-04 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [6 empty] | T | Field Testing
SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  |  |  |  | Date: | 2025-09-07
Downer Approval |  | Name: | Diliban Sengottian |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Sam Parkinson |  |  | Signature: |  |  |  |  | Date:

## Materials
SECTION 1 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location/ Hold Points
1.01 | Methodology Statement | Prior to works | PS Cl24.5.2 | Must include but not limited to: • Pile equipment and plant; • Pile casing/sleeve/liner fabrication details; • Pile casing installation methodology and equipment; • Bored pile spoil excavation methodology and equipment, including disposal requirements; • Cover Spacers type and detail sheet; • Methodology for pile base clean-out and inspection requirements; • Methodology for placement of concrete underwater; • Pile testing requirements. | Method Statement | Prior to Construction | Hold Point | H | ER
1.02 | Pile Cage | Prior to installation | PS Cl 24.5.3 | Reinforcing bars shall be cut and bent according to NZS 3109, Section 3 and NZS 3101, Section 8.4 to the dimensions and shapes as shown or indicated on the Drawings. Bend diameters for longitudinal reinforcing shall be in accordance with Table 3.1, NZS 3109 and Table 8.1, NZS 3101. Stirrups shall be bent to standard shapes as shown in NZS 3109. Cage Inspection with Engineer at Fabrication Yard | ConQA HP | Prior to delivery | Hold Point | H | ER
1.03 | Pile Casing | Prior to installation | PS Cl 24.5.3 | The external diameter at any section, measured using a steel tape on the circumference, shall not differ from the theoretical diameter by more than ±1%. The deviation from straightness on any longitudinal face shall not exceed 1/600 of the length of the pile, nor 5 mm in any 3000mm length. The out-of- round (i.e. difference in measurements of two diagonals at right angles) of a casing must not exceed 1% of the internal diameter, provided that the concrete cover specified on the Drawings is maintained. Steel cast numbers, mill certificates, test certificates and ladle analyses to be retained and included in As-built details | Dockets, Mill Certs, Site Measurements | Per Casing | Witness Point | W | SE