## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-C-029 Bored Piles | itp |  |  |  |  | DS2681-SH58-ITP-C-029 Bored Piles
section | SECTION 2 – IN-PROCESS INSPECTIONS
checkpoint | 2.01 - Open Drilling
label | Inspection Point: Quality Control Activity - Pile Card
label | Specification Reference - ASG (SESOC NZGS) Bored Pile Spec Cl 3.9
label | Acceptance Criteria - Pile location (offsets)
label | ○ Drilling Start and Finish Time
label | ○ Depth of water encountered.
label | ○ Description of material encountered at regular 1m intervals and when new layers encountered (Specifically record depth at which Rock level is found)
label | ○ Time and depth at which obstructions were encountered.
label | Verifying Document - Pile Card
label | Frequency - Per Pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.02 - Installation of casing
label | Inspection Point: Quality Control Activity - Check verticality using digital level
label | Specification Reference - PS CL 24.5.4
label | Acceptance Criteria - Verticality Tolerance - No greater than 1:75 (Horizontal: Vertical)
label | ○ Casing Length
label | Verifying Document - Pile Card/Photos
label | Frequency - Per Pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.03 - Drilling of Rock Socket
label | Inspection Point: Quality Control Activity - Agreement of Final Socket Depth
label | Specification Reference - PS CL 24.5.4
label | Acceptance Criteria - Rock depth to be confirmed by the Engineer with guidance from the contractor and drill operators. Rock depth to be noted on the pile card. Pile card shall be signed by Engineer.
label | ○ Following establishment of Rock Depth, Engineer to confirm socket depth
label | Verifying Document - Pile Card & ConQA Sign-off
label | Frequency - Per Pile
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - CCTV of Rock Socket
label | Inspection Point: Quality Control Activity - Shaft cleanliness CCTV
label | Specification Reference - ASG (SESOC NZGS) Bored Pile Spec Cl 3.8 & PS CL 24.5.5
label | Acceptance Criteria - Casing inspected visually using mirrors and spotlights as required. CCTV to be used for rock socket. Suitable flocculant to be used, as necessary,
label | Verifying Document - CCTV Footage & ConQA Sign-off
label | Frequency - Per Pile
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Following Completion of Rock Socket
label | Inspection Point: Quality Control Activity - Final measurement of pile length
label | Specification Reference - ASG (SESOC NZGS) Bored Pile Spec Cl 3.8 & PS CL 24.5.4
label | Acceptance Criteria - Following completion of rock socket and cleaning. Pile depth to be measured and noted on the pile card
label | Verifying Document - Pile Card
label | Frequency - Per Pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.06 - Reinforcement Cage - Placement
label | Inspection Point: Quality Control Activity - Reinforcing cage placing
label | Specification Reference - PS Cl 24.5.4
label | Acceptance Criteria - Nominal cover = 75mm
label | ○ Cage length measure and trimmed to size to maintain bottom cover
label | ○ Lengthen as required by Engineer.
label | Verifying Document - Pile Card & ConQA Sign-off
label | Frequency - Per pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.07 - Reinforcement Cage - Spacers
label | Inspection Point: Quality Control Activity - Spacer Wheel Installation
label | Specification Reference - PS Cl 24.5.4
label | Acceptance Criteria - 4no. wheels per 4-5m vertically (2x sets on pile P2) and on 4 sides of the cage Horizontally i.e. at 12, 3, 6 & 9 on a clock face
label | Verifying Document - Pile Card, Photos & ConQA Sign-off
label | Frequency - Per pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.08 - Reinforcement Cage - Survey
label | Inspection Point: Quality Control Activity - Top hook level/cage levelling
label | Specification Reference - PS Cl 24.5.4
label | Acceptance Criteria - Measure top of pile concrete to top of hooks to ensure correct cage level.
label | Verifying Document - Pile Card
label | Frequency - Per pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.09 - Pre-pour Inspection
label | Inspection Point: Quality Control Activity - Pre-pour Inspection
label | Specification Reference - PS Cl 24.1.17
label | Acceptance Criteria - Pre-pour inspection with Engineer Sign-off
label | Verifying Document - ConQA Sign-off
label | Frequency - Per Pile
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Concrete Pour - Cylinders
label | Inspection Point: Quality Control Activity - Test Cylinders
label | Specification Reference - PS Cl 24.5.5
label | Acceptance Criteria - A set of specimens for compression tests shall consist of 4 specimens from each sample of concrete. 1no. tested at 7 days and 3no. tested at 28 days. (Actual spec requirement is 3no. At 28days)
label | ○ Strength of pile concrete = 40MPa
label | ○ Slump test must also be carried out
label | Verifying Document - Lab Report
label | Frequency - Per batch
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.11 - Concrete Pour - Dockets
label | Inspection Point: Quality Control Activity - Tremie pour mix Bored Piles and Hard Piles
label | Specification Reference - PS Cl 24.5.5
label | Acceptance Criteria - Correct mix design brought to site
label | Concrete Docket Showing:
label | ○ Mix Design Item Code
label | ○ 28 day specified strength = 40MPa
label | ○ Concrete placement method that the mix was designed for - Tremie
label | ○ Type of supplementary cementitious materials (if used);
label | ○ Slump (target and actual slump when measured);
label | ○ Order and Delivery Quantity
label | ○ Load Time out of plant
label | ○ To site time
label | ○ Unload Time
label | ○ Associated Products e.g. cement and additives
label | Verifying Document - Concrete Docket
label | Frequency - Per truckload
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.12 - Concrete Pour - Slump
label | Inspection Point: Quality Control Activity - Slump Test
label | Specification Reference - PS Cl 24.5.5
label | Acceptance Criteria - Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken.
label | ○ Slump spread test if slump could exceed 210mm
label | Verifying Document - Photos
label | Frequency - Per truckload
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.13 - Concrete Pour - Pour Height Measure
label | Inspection Point: Quality Control Activity - Pour Height above top of pile
label | Specification Reference - PS Cl 24.5.5
label | Acceptance Criteria - Minimum over-cast of 0.3m to be measured against mark on casing.
label | Verifying Document - Pile Card
label | Frequency - Per pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.14 - Pile Card Sign-off
label | Inspection Point: Quality Control Activity - Engineer Sign-off
label | Specification Reference - N/A
label | Acceptance Criteria - Sign off of Pile Card
label | Verifying Document - Pile Card
label | Frequency - Per Pile
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.15 - PIT Testing
label | Inspection Point: Quality Control Activity - PIT Testing
label | Specification Reference - PS Cl 24.5.5
label | Acceptance Criteria - Specialist external testing contractor to provide analysis of the pile identifying any flaws, the method used to determine them, and an interpretation of their significance. Report to be sent to the Engineer for review.
label | Verifying Document - Test Report
label | Frequency - Per Pile - min 7 days Post Pour
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.16 - Survey as-built
label | Inspection Point: Quality Control Activity - Survey as-built
label | Specification Reference - PS Cl 26.4 & AS2159 (Page 167)
label | Acceptance Criteria - Not more than 75mm horizontally and 25mm vertically from their true position.
label | ○ Top of casing level.
label | Verifying Document - As-built survey CAD File
label | Frequency - Per pile
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checklist | DS2681-SH58-ITP-M-013 Bored Piles Materials | itp |  |  |  |  | DS2681-SH58-ITP-M-013 Bored Piles Materials
section | SECTION 1 – RECEIVING INSPECTIONS
checkpoint | 1.01 - Methodology Statement
label | Inspection Point: Quality Control Activity - Prior to works
label | Specification Reference - PS Cl24.5.2
label | Acceptance Criteria - Must include but not limited to:
label | ○ Pile equipment and plant;
label | ○ Pile casing/sleeve/liner fabrication details;
label | ○ Pile casing installation methodology and equipment;
label | ○ Bored pile spoil excavation methodology and equipment, including disposal requirements;
label | ○ Cover Spacers type and detail sheet;
label | ○ Methodology for pile base clean-out and inspection requirements;
label | ○ Methodology for placement of concrete underwater;
label | ○ Pile testing requirements.
label | Verifying Document - Method Statement
label | Frequency - Prior to Construction
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Pile Cage
label | Inspection Point: Quality Control Activity - Prior to installation
label | Specification Reference - PS Cl 24.5.3
label | Acceptance Criteria - Reinforcing bars shall be cut and bent according to NZS 3109, Section 3 and NZS 3101, Section 8.4 to the dimensions and shapes as shown or indicated on the Drawings.
label | ○ Bend diameters for longitudinal reinforcing shall be in accordance with Table 3.1, NZS 3109 and Table 8.1, NZS 3101. Stirrups shall be bent to standard shapes as shown in NZS 3109.
label | ○ Cage Inspection with Engineer at Fabrication Yard
label | Verifying Document - ConQA HP
label | Frequency - Prior to delivery
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Pile Casing
label | Inspection Point: Quality Control Activity - Prior to installation
label | Specification Reference - PS Cl 24.5.3
label | Acceptance Criteria - The external diameter at any section, measured using a steel tape on the circumference, shall not differ from the theoretical diameter by more than ±1%.
label | ○ The deviation from straightness on any longitudinal face shall not exceed 1/600 of the length of the pile, nor 5 mm in any 3000mm length.
label | ○ The out-of- round (i.e. difference in measurements of two diagonals at right angles) of a casing must not exceed 1% of the internal diameter, provided that the concrete cover specified on the Drawings is maintained.
label | ○ Steel cast numbers, mill certificates, test certificates and ladle analyses to be retained and included in As-built details
label | Verifying Document - Dockets, Mill Certs, Site Measurements
label | Frequency - Per Casing
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE