## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
8a93363f-338a-4f80-b8b6-17318d2d7e50 | checklist | FHC-ITP-028 - Street Furniture (Supply & Installation) Rev 0 | itp | FHC-ITP-028 - Street Furniture (Supply & Installation)
85c71817-2664-44c0-bfcd-324d0d81d7c6 | section | Preliminaries
c8ae6134-43e0-4a88-8575-3f4990423e70 | checkpoint | 1.1 IFC Drawings
800393fe-a0d7-564d-b2c0-65f49be1d45e | note | REFERENCE: Fulton Hogan Quality Management Plan
ca200422-1a51-54a0-b376-20aadec83a24 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
8f03324f-416d-5c3e-a0c4-3434fcd24a17 | note | METHOD: Document Review
f7a3db05-cd07-5b68-8a77-3926a814427d | note | FREQUENCY: Prior to starting Works and at regular intervals
f2cbdadb-2312-5025-b4f9-fd34f85b2333 | note | HP*
c6da24e8-3126-5b09-bf25-d4ac45a9e315 | note | RESPONSIBILITY: All
fbca2c15-f361-53a2-8e69-0577814ea97b | note | VERIFYING DOCUMENTS: This ITP
0c33fcd6-5a89-5e98-b610-f37a7efb6c14 | textbox | Date Completed:
39a5da17-58d4-48d7-a988-72e4cf041046 | checkpoint | 1.2 Componentry
e1b601d1-22fb-5863-a031-7a0dffc92832 | note | REFERENCE: IFC Drawings
6e21c24e-e637-5562-a63f-33bccd4390f9 | note | ○ Manufacturer's Drawings & Installation Recommendations
6d0bbc0c-735a-5601-b30c-9a799e8e21eb | note | ○ Fulton Hogan Quality Management Plan
21115aa7-efd2-5932-8e05-02c8e9f07b22 | note | ACCEPTANCE CRITERIA: Product to be as per the Drawings, or where applicable, be selected based on the following criteria:
7c143c14-4903-5c41-a23b-9dd15d47aa52 | note | i. A like-for-like equivalent to those shown on the IFC Drawings
11825b9f-0d5d-5d36-b9a0-69c7ba5a7a14 | note | ii. Able to withstand the load conditions (where specified)
4a27d6ff-a8dd-5291-b8a5-69219df41529 | note | v. Have a protective coating or be manufactured from a material that aligns with the atmosphere it will be erected in
d1e5fe11-2b17-59ac-b8ee-06662150030a | note | ○ Where a product has deviated from the IFC Drawings, details of the nominated equivalent proprietary system to be submitted for review to the Superintendent.
0260b2f9-beba-574f-9036-f9962d98a7d5 | textbox | Enter: Teambinder Material Approval number
5c5daeed-1d9e-52f4-afe1-4f7bf1e0cfff | note | or
efbe716a-9c37-5b9b-ad56-d2a6bbcf9a20 | note | ○ Attach: Product Details
3aa57c2e-8a8d-52d3-9f1c-23e611924d1a | note | METHOD: Document Review
12b259b7-2495-5aaa-be16-7c5b8a3edc63 | note | FREQUENCY: Each component
b56de8a9-1157-584a-a37b-56f99dae5816 | note | IP
2182fef3-cd29-52a6-ba90-d80afd98e5a4 | note | RESPONSIBILITY: PE/SE/SPE
1f605e9a-fd62-58b7-8831-30a4d867f97f | note | VERIFYING DOCUMENTS: This ITP
f2368223-69a5-5551-8cb5-7b3dc9570137 | textbox | Date Completed:
315256fc-ded6-4b41-aca0-b8e1f512ced4 | checkpoint | 1.3 Fixing Detail
87e6c86c-cf4f-5d4e-8b34-2f04ec33c64a | note | REFERENCE: IFC Drawings
eceddb89-031f-59de-91e1-bd702fbf191b | note | ○ Manufacturer's Drawings & Installation Recommendations
58f22637-9cd1-5462-9525-547d3fdc20ab | note | ACCEPTANCE CRITERIA: Fixing detail to be as per the IFC Drawings or Manufacturer's Drawings & Installation Recommendations.
fe6b77ba-9d9f-5576-ba25-afb823845fe7 | note | ○ Changes to the approved Drawings shall be accompanied with approval from the Designers or Manufacturer's Representative.
69297f6d-17cb-59dd-8902-4fd702ab7573 | textbox | Enter: Teambinder Request for Approval number
24adc15b-6dca-5123-a080-2ccc9bc29614 | note | or
4a612f90-704d-53ed-b8a6-38c86f39e59a | note | ○ Attach: Written approval from Manufacturer's Representative
182a3236-d762-57e9-a320-5dff63e325a4 | note | METHOD: Document Review
c9e0d833-daff-5352-94c1-38010bcb5f6c | note | FREQUENCY: Each component
1823a686-11b9-55c4-bd9e-cb701adf985b | note | IP
1328c557-8673-5ee9-af65-679fa7288441 | note | RESPONSIBILITY: PE/SE/SPE
3f2be48e-eb35-582d-9aaa-271799726afa | note | VERIFYING DOCUMENTS: This ITP
30328509-554e-5227-9286-fed674531e4c | textbox | Date Completed:
afe8cb14-369c-42c8-9322-3bfa1bbeda90 | section | Pre-installation Activities
f30071ee-3bee-40c3-96bf-d3e74ba4fd04 | checkpoint | 2.1 Materials Inspection Checklist
20a3d380-203b-5772-948b-0b4df383b378 | note | REFERENCE: IFC Drawings
d247955e-0477-55b2-935a-c1af7989f22f | note | ○ Fulton Hogan Quality Management Plan
5d423a1a-6a62-51e5-851e-76dce4d32893 | note | ACCEPTANCE CRITERIA: General inspection of components for defects including cracks, chips, handling and storage damage & distortion.
5a90efba-8ea6-52bd-83fc-4108c11e59b7 | note | ○ Coating shall have no damage, loss of adhesion, fading, blisters, roughness, sharp points or residues and be of the specified colour.
01597daf-727d-5abd-82a4-7a3170d50c0b | note | ○ Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
df3f7018-86d6-5b17-bcad-953812e76226 | note | ○ Complete: Materials Inspection Checklist in ConQA
5a340a19-f13b-5944-b964-061c5693e787 | note | METHOD: Measure, Visual
7c79ccce-4357-5130-a8ec-3f660354f02c | note | FREQUENCY: Each component
cf1943b7-ca89-5d87-8597-f555df60cc73 | note | IP
c65c74e7-6d2e-5d9b-8945-8580122c8a3d | note | RESPONSIBILITY: SE/PE/SPE
6e83b163-fed3-5a93-9923-e3494dbed7d4 | note | VERIFYING DOCUMENTS: This ITP
43213a35-8366-558a-939e-69628a4a1db3 | textbox | Date Completed:
5ba2925d-b838-4264-9102-6d2d28f79f73 | checkpoint | 2.2 Survey Set-out
49e78c01-e25b-5c4a-b5ee-50170ad0c60b | note | REFERENCE: IFC Drawings
0b30de87-d2ab-5f8f-a428-c7a88b1afd7b | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within any specified tolerances as applicable to the component.
fa5930df-02fc-5606-85d8-762c147177fe | note | METHOD: Measure, Visual
429c0d0b-c718-5657-bbb8-b028f53dc706 | note | FREQUENCY: Each component
44f29ded-2c65-5458-a280-a4cf22cbe84a | note | IP
8051a68c-7365-53f4-83b8-09922c3ca9fc | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
1928867b-e21f-5fc0-a40a-ca917e5f8157 | note | VERIFYING DOCUMENTS: This ITP
76817fcf-fe05-59cc-9857-bcf3d3655b5b | textbox | Date Completed:
0c4e75ec-8fa4-4c68-abbc-387a66864731 | section | Installation Activities
8fbd4483-a275-4a8c-bdf5-1b08a27f9a1f | checkpoint | 3.1 Mounting Surface Preparation
47daa958-02cd-5817-8add-01ac79208290 | note | REFERENCE: Manufacturer's Drawings & Installation Recommendations
0c178030-287d-5764-b5b6-1f18d0ecc5a5 | note | ACCEPTANCE CRITERIA: As a minimum, ensure that the bearing surface is clean and free from loose particles and residues.
0d6ce54b-5be1-56d3-9598-1ac4fdd47a1f | note | METHOD: Visual
680233c9-e10c-53b4-83c9-8e4262b8d3fc | note | FREQUENCY: Each component location
dbeb1bf1-3f43-5114-9855-6f330970b031 | note | IP
6a14bc71-a8e9-52c1-8bce-cf78fcda1a0c | note | RESPONSIBILITY: SE/PE/SPE
afee452c-60bc-538f-af5b-9399a9bdf22f | note | VERIFYING DOCUMENTS: This ITP
5bb4bfd9-8790-544c-b2b9-b25fee94a21a | textbox | Date Completed:
ae201763-69ee-4998-8287-d5dbc5805b06 | checkpoint | 3.2 Component Handling
c3660985-2c7f-520b-9e72-a614765e44c3 | note | REFERENCE: Manufacturer's Drawings & Installation Recommendations
64b5857e-89d9-5fed-b61a-d89f97daca6c | note | ACCEPTANCE CRITERIA: The method of handling and erection of the components shall ensure that there is no damage to the protective coating during these operations.
478277dd-6840-58b2-8541-70d3366f15d2 | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
37c6f91e-cbcc-5992-9112-4088df57203f | note | METHOD: Visual
c4b9b61b-d137-5fdf-90ee-4989f42b13db | note | FREQUENCY: Each component
16ee5197-530a-566a-a139-88931af15d0e | note | IP
a31148d4-cd52-52d4-9433-c089659451a4 | note | RESPONSIBILITY: SE/PE/SPE
468d59fd-a099-5695-ae35-d114a5fbf276 | note | VERIFYING DOCUMENTS: This ITP
a3224f2a-3073-50ff-8f69-268beaac6613 | textbox | Date Completed:
5c6be0b3-6775-4854-a0e1-fe458528732d | checkpoint | 3.3 Component Installation
09afd695-30fd-57fe-ada1-f4339105e402 | note | REFERENCE: IFC Drawings
0d682303-404c-50e9-bdfe-efe79f2048de | note | ○ Manufacturer's Drawings & Installation Recommendations
33e0f0d3-cf40-5054-96aa-67b48a3231a1 | note | ACCEPTANCE CRITERIA: Place component into position, ensuring that it is plumb, level, square and within tolerances shown on the IFC drawings or Manufacturer's Drawings and installation recommendations.
1ef0b8a6-1212-5416-bd03-f88817201ac2 | note | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
9efe17fb-27fc-54ce-b4e4-047950e03507 | note | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
b6c2d189-9948-51cc-a119-3e4b28e58a54 | note | ○ Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
61d19443-3833-566c-a93a-5bea1ee8ec3b | note | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
1de1ca57-c4de-5602-acca-881b4b1edf14 | note | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
747f327a-981e-537d-9551-62e185f0153b | note | METHOD: Measure, Visual
6f81b23e-85b5-50e1-b5de-6fa8254a4c5a | note | FREQUENCY: Each component
5a42bfe7-6803-501f-b467-80e33fdf470e | note | IP
f1719788-6eda-5893-ba3a-aab2ac9027cd | note | RESPONSIBILITY: SE/PE/SPE
feebf88a-8711-527c-b28a-a0511e2ed03f | note | VERIFYING DOCUMENTS: This ITP
5ac8c8f4-0120-592c-8c4d-53a5203b4212 | textbox | Date Completed:
491f1b9c-11ff-45b7-be5e-6d923e6ff28b | checkpoint | 3.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
a17672a8-3bfe-5038-99f6-6f093c7f2786 | note | REFERENCE: IFC Drawings
a794f18e-9a33-5a73-9e1e-b268fbcde3ee | note | ○ Manufacturer's Drawings & Installation Recommendations
ac08d419-629d-5eee-9065-8e0d9ca20da3 | note | ○ AS4100, Clause 14.3.3.1
0715e413-0a07-5dd1-9065-327bd1b6ef14 | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the drawings.
f1e0014a-03df-5760-a829-a0918a79f629 | note | ○ At least 1 no. washer shall be used underneath the rotating part unless this is not part of the hand rail system.
c8594764-30e7-503f-b4b3-55303e11ea06 | note | ○ Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
fa786f86-fe08-5a97-8ae3-f1f618c7d6bb | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
9cf2dfd1-608c-5c0a-a55b-5ac410f4dfb7 | note | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
9a22d2f4-9a9e-5b18-88ca-ada433485a1f | note | ○ Protrusion to be at least 1 clear thread pitch and any thread run-off beyond the nut.
1f028ffc-5ad6-5378-9ad6-48eb43eb4265 | note | ○ Note: No maximum projection length is stated in the Australian Standards.
064c8b90-20f9-534f-9516-0f3db5086c06 | note | METHOD: Measure, Visual
97c31790-a05f-5e57-a7b7-041fdc5e2435 | note | FREQUENCY: Where applicable, each bolted connection
e692e42b-957c-54bb-af64-4228451d66fb | note | IP
4591b472-283e-5c63-a54e-6b2ea04b5e62 | note | RESPONSIBILITY: SE/PE/SPE
58161e27-1069-53da-aadb-fa9a5150ceea | note | VERIFYING DOCUMENTS: This ITP
842369d3-6348-5159-9e0f-0a98f5b6514a | textbox | Date Completed:
833b6a55-4771-4df0-8a11-60cccbaab370 | section | Post-installation Activities
5763ddc9-7ebe-4dd9-9e29-4bf22182da80 | checkpoint | 4.1 Inspection of Coating (where applicable)
ebb24ab6-469e-5315-bca1-bbedef6fc2fd | note | REFERENCE: IFC Drawings
7167cae5-424e-580c-968d-ff636ab73f61 | note | ○ Manufacturer's Drawings & Installation Recommendations
22bae86e-2df0-572e-974a-6c41a3e49bb8 | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
62b9bebf-5f22-5ac0-970f-fa631d8dae3b | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
5d06f3b9-d8e9-54db-a917-c1fb71283cb0 | note | METHOD: Visual
34bb930b-c7a4-5a21-8cae-dfecff827627 | note | FREQUENCY: Each component
ef43f2ea-70aa-5403-8643-4bfb8c99a12d | note | IP
41b0543e-9722-5a99-bfd6-7b4840aed6cd | note | RESPONSIBILITY: SE/PE/SPE
2a900839-6e96-5e67-ade8-f859a50911e9 | note | VERIFYING DOCUMENTS: This ITP
d84af467-ac15-5166-b6b8-90756605557e | textbox | Date Completed:
2f471fce-3269-43ef-89c6-4efaa54718ee | checkpoint | 4.2 As-built Survey
3034662a-0e59-5bd3-9179-bf2504e5c9ac | note | REFERENCE: IFC Drawings
e73bc33c-fc81-5fde-ba3d-6c56c9de480d | note | ○ Manufacturer's Drawings & Installation Recommendations
39708677-5483-5821-a1d7-f060cd0f2291 | note | ○ Fulton Hogan Quality Management Plan
cdc45029-7d23-5e65-9b7c-78d731014a4c | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within any specified tolerances.
06159dde-0348-5754-b1a9-c2fdc5271db2 | note | ○ Attach: Survey As-builts / Survey Report / Photos
44e43663-93cd-5f37-8bd2-8897ecb90801 | note | METHOD: Document Review
8d289f20-b3dc-504f-ab6c-d820813323b4 | note | FREQUENCY: Each component
ee26a699-8f99-542b-b892-f9057e2aefef | note | IP
ab3715bc-f5fe-580e-b58c-6c96df24be03 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
a873003a-5da4-5c82-bf05-d77af738b9ac | note | VERIFYING DOCUMENTS: This ITP
60fb9052-559c-5bb9-b579-c2e654984fca | textbox | Date Completed:
cd2f63fc-cd85-4ff5-a396-88e76f2a9945 | checkpoint | 4.3 Non-conformance Report (NCR) Closure
919ac672-c327-5f6b-929f-acab3f87920f | note | REFERENCE: Fulton Hogan Quality Management Plan
f9f5edb2-92f2-53c0-a9de-f9d192ee2972 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
48d1236d-895b-5e24-b2c2-0fa3065ac401 | note | METHOD: Document Review
b5f11504-a285-54ef-95c9-a2f1f9e0146d | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
785594a4-1a3f-5060-8334-f5647131bfa7 | note | HP*
98aa3058-bc83-5e87-a062-dd44cfcaf258 | note | RESPONSIBILITY: SE/PE/SPE
5a558615-3fa2-5852-846c-71fe2c871dce | note | VERIFYING DOCUMENTS: This ITP
637a9c90-5e5d-5803-90b7-3ee51593b60f | textbox | Date Completed:
04786a95-0c18-4d89-afe1-aee268201622 | checkpoint | Final Inspection
a82bf809-3b3d-5811-b368-09c77ca72f48 | note | On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
87b1d8ba-8756-5889-a26c-b49baa607451 | textbox | Print Name:
c6844213-065f-5202-beec-c9302d8d8644 | textbox | Position:
47ba97c5-c8e3-5399-b695-29efb0135664 | textbox | Date: