## ITP-016
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-016
[11 empty] | Revision : 00 | Date : 08/09/25
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Vic & Eliz St Stage 2 |  | Platform Bluestone Kerb |  | Name: | Jake Cardillo | Name: | Patrick Fagan |  | Name: Shaun Kent
Contract No: |  | 8B5600 |  | Specifications: Yarra Trams STD_T6111
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Vic and Elizabeth St |  | Date : 08/09/25 |  | Date : 08/09/25 |  |  | Date : 08/09/25
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Activity | •Ensure that employees and sub-contractors are using the most current and complete set of drawings | Contract Drawings and Registers | Visual Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Commencing Activity | •All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP | Work Procedure | Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check Condition of Material |  | Prior to Commencing Activity | •All bluestones shall be inspected at delivery for visible damage | Work Procedure | Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Lifting method |  | Prior to Commencing Activity | Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter. | Work Procedure | Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Base Course |  | Each Lot | •Class 2 compacted rock (98% modified density) shall be compacted to min 100mm thickness. •Soft or areas deemed unsatisfactory shall be removed and rectified | STD_T6111 | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Concrete Placement |  | Each Lot | •Bedding shall be >100mm 32MPa concrete with 6mm aggregate. To match the blinding layer of the edge beam | STD_T6111 | Visual Inspection | This ITP Signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Setting |  | Each Lot | •Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone •Tie rods shall be installed with bond breaking compound specified by superintendent •Bluestone shall be laid 150mm below finished surface level | STD_T6111 | Visual Inspection | This ITP Signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Sealant |  | Each Lot | •Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour •Loose materials shall be removed as not to impair adhesions | Work Procedure | Visual Inspection | This ITP Signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Platform line marking |  | Each Lot | 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb. | YT Construction Standard | Visual Inspection | This ITP Signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.