## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-018
[11 empty] | Revision : 0 | Date : 08/09/25
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Vic & Eliz St Stage 2 |  | Energy Absorbing Bollards |  | Name: | Jake Cardillo | Name: | Damon Bromwich |  | Name: Shaun Kent
Contract No: |  | 8B5600 |  | Specifications: Automotive Safety Engineering Technical Specification (ASE TS)
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Vic and Elizabeth St |  | Date : 08/09/25 |  | Date : 08/09/25 |  |  | Date : 08/09/25
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to Commenciing any Activity | •All employees and subcontractors shall have the most current and complete set of drawings | Design Drawings and Register | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Commenciing any Activity | •All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Service proving |  | Prior to Commenciing any Activity | •Service locating shall be conducted in form of DBYD and service location | DBYD Service Locator, Service Chart | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Excavation permit |  | Prior to Commenciing any Activity | •Ensure excavation permit has been obtained for the specified tasks | Fulton Hogan Procedure | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.5 | Materials |  | Prior to Commenciing any Activity | •All materials shall comply as per technical specification •Ensure materials are not damaged | ASE TS | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.6 | Setting out |  | Prior to Commenciing any Activity | •Ensure location of bollards conforms to design drawings •Mark hole centre position at location | ASE TS cl1.1 | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation |  | Each lot | •Care shall be taken in excavation •Hole shall be minimum 600mm dia and 1000mm in depth | ASE TS 2.2 | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Base preparation |  | Each lot | •Ensure base is supported by solid ground, and block is level | ASE TS 3.1 | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Installation of reo cage |  | Each lot | •EAB cage shall be placed level | ASE TS 4.1 | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Pre pour checklist |  | Each lot | •Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level | Fulton Hogan Procedure | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Concrete placement |  | Each lot | •32MPa concrete shall be placed to cover reinforcement cage and fill hole •Concrete shall be compacted by use of vibrator •If surface pavers are to be used, allow 25mm gap from finished surface •Ensure reo cage is level post compaction | ASE TS 4.2 | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.6 | Installation of Bollard |  | Each lot | •Ensure bollard is installed, and bolts are tightened adequately if required •Concrete, pavers or bitumen shall be finished to specified requirements | ASE TS 5.2 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.