## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-015 - Sign Installation | itp |  |  |  |  | ITP-015 - Sign Installation Rev1
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Signage Conformance
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
label | REFERENCE DOCUMENTS: Drawings AS 1742
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Service Identification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | REFERENCE DOCUMENTS: DBYD, Service chart
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Post & Foundations
label | FREQUENCY: Prior to Start
label | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | REFERENCE DOCUMENTS: 714.06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Signage Install
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
label | ○ Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
label | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | REFERENCE DOCUMENTS: AS 1742, TS 1313 Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-016 - Platform Bluestone Installation | itp |  |  |  |  | ITP-016 - Platform Bluestone Installation Rev0
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Condition of Material
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: •All bluestones shall be inspected at delivery for visible damage
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Lifting method
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Bluestones can be moved with excavator and grabs/slings or with a vacuum lifter.
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Base Course
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Class 2 compacted rock (98% modified density) shall be compacted to min 100mm thickness.
label | ○ Soft or areas deemed unsatisfactory shall be removed and rectified
label | REFERENCE DOCUMENTS: STD_T6111
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Concrete Placement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding shall be >100mm 32MPa concrete with 6mm aggregate. To match the blinding layer of the edge beam
label | REFERENCE DOCUMENTS: STD_T6111
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Setting
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Tie rods shall be N12 (300mm long) and chemset 100mm into kerb, 2 per stone
label | ○ Tie rods shall be installed with bond breaking compound specified by superintendent
label | ○ Bluestone shall be laid 150mm below finished surface level
label | REFERENCE DOCUMENTS: STD_T6111
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Sealant
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Sealant at construction and expansion joints at back of kerb shall be 'Gun Grade THC 900' by Tremco, of black colour
label | ○ Loose materials shall be removed as not to impair adhesions
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Platform line marking
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: 50mm yellow lines shall be placed along the edge of platform, one on the top face and one on the front face of the kerb.
label | REFERENCE DOCUMENTS: YT Construction Standard
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-018 - Energy Absorbing Bollards | itp |  |  |  |  | ITP-018 - Energy Absorbing Bollards Rev0
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Design Drawings and Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Service proving
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: Service locating shall be conducted in form of DBYD and service location
label | REFERENCE DOCUMENTS: DBYD Service Locator, Service Chart
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Excavation permit
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: Ensure excavation permit has been obtained for the specified tasks
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Materials
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: All materials shall comply as per technical specification
label | ○ Ensure materials are not damaged
label | REFERENCE DOCUMENTS: ASE TS
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.6 Setting out
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: Ensure location of bollards conforms to design drawings
label | ○ Mark hole centre position at location
label | REFERENCE DOCUMENTS: ASE TS cl1.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Care shall be taken in excavation
label | ○ Hole shall be minimum 600mm dia and 1000mm in depth
label | REFERENCE DOCUMENTS: ASE TS 2.2
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure base is supported by solid ground, and block is level
label | REFERENCE DOCUMENTS: ASE TS 3.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Installation of reo cage
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: EAB cage shall be placed level
label | REFERENCE DOCUMENTS: ASE TS 4.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Pre pour checklist
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Concrete placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: 32MPa concrete shall be placed to cover reinforcement cage and fill hole
label | ○ Concrete shall be compacted by use of vibrator
label | ○ If surface pavers are to be used, allow 25mm gap from finished surface
label | ○ Ensure reo cage is level post compaction
label | REFERENCE DOCUMENTS: ASE TS 4.2
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Installation of Bollard
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure bollard is installed, and bolts are tightened adequately if required
label | ○ Concrete, pavers or bitumen shall be finished to specified requirements
label | REFERENCE DOCUMENTS: ASE TS 5.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-019 - Fencing Installation | itp |  |  |  |  | ITP-019 - Fencing Installation Rev0
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished
label | ○ Welding shall be in accordance with AS1554
label | ○ Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
label | REFERENCE DOCUMENTS: STD_T6000, CE-021-ST-0012, cl 4.3.1.4
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Confirm Footings position
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
label | REFERENCE DOCUMENTS: Construction Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Bonds
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation.
label | ○ Lug shall be fitted to baseplate at specified fencing location
label | REFERENCE DOCUMENTS: STD_T6000
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Footing Installation
label | FREQUENCY: Prior to Asphalt
label | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20
label | ○ 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
label | REFERENCE DOCUMENTS: STD_T6002
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Post Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level
label | ○ Installed to footings with bolt assembly
label | ○ All bolts shall be insulated from base plates, using non metallic sleeves and washers
label | ○ The top of fence base plate shall be level with surrounding pavement
label | REFERENCE DOCUMENTS: STD_T6002
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Grout Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application
label | ○ 50mm of Non shrink dry pack grout shall be placed under base plate
label | REFERENCE DOCUMENTS: STD_T6002
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Continuous Handrails
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns
label | ○ All sections to be welded as per AS 1554
label | ○ All sharp edges and welds to be ground back to smooth finish
label | ○ Domed buttons to be welded on top of handrail 150mm from the post centreline
label | REFERENCE DOCUMENTS: STD_T6001 & T6002
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Wire Rope Tensioners
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
label | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-021 - Line Marking | itp |  |  |  |  | ITP-021 - Line Marking Rev0
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Position of Markings
label | FREQUENCY: Prior to application
label | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
label | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2.
label | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010,
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Tolerance of Pavement Markings
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings. The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Raised Pavement Markings
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
label | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-025 - Structural Concrete Construction | itp |  |  |  |  | ITP-025 - Structural Concrete Construction Rev1
section | Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Approval of mix design
label | FREQUENCY: Prior to the first concrete pour
label | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
label | REFERENCE DOCUMENTS: 610.07
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Reinforcement schedule
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | REFERENCE DOCUMENTS: 611.04
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction/Erection of Formwork
checkpoint | 2.1 Excavation
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | REFERENCE DOCUMENTS: Contract Drawings
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Construction Methodology
label | FREQUENCY: Prior to erection
label | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | REFERENCE DOCUMENTS: 614.04, 614.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Pre-Pour Planning and Inspection
checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
label | ○ Hold Point released by the Superintendent.
label | REFERENCE DOCUMENTS: 602.03
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Fulton Hogan / VicRoads
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Formwork levels and position
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
label | REFERENCE DOCUMENTS: 614.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | SCP, HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.3 Location of splices
label | FREQUENCY: Schedule Review
label | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
label | REFERENCE DOCUMENTS: 611.11
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 3.4 Cleaning formwork
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
label | REFERENCE DOCUMENTS: 610.18 (a) (iii)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
label | ○ Pre-pour checklist completed and signed.
label | REFERENCE DOCUMENTS: 610.18 (a)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
label | HP
label | RESPONSIBILITY: Fulton Hogan / VicRoads
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 Reinforcement assembly of piles
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 Monitoring weather
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
label | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Placing and Finishing Concrete
checkpoint | 4.1 Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
label | REFERENCE DOCUMENTS: 610.16
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.2 Discharge time
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.3 Methodology of placement (structural)
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
label | ○ Concrete shall not be moved horizontally by vibrators
label | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
label | REFERENCE DOCUMENTS: 610.18
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Post-Pour Details and Inspection
checkpoint | 5.1 Curing
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
label | REFERENCE DOCUMENTS: 610.23
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.2 Formwork removal
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | REFERENCE DOCUMENTS: 610.25
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
label | REFERENCE DOCUMENTS: AS3600 Cl 17.5, 607.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.4 Concrete Sampling and Testing
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
label | REFERENCE DOCUMENTS: 610.16
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.5 As Built Drawings
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Recorded of as-built drawings
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-029 - PVC TGSI Installation | itp |  |  |  |  | ITP-029 - PVC TGSI Installation Rev0
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Materials
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection List
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
label | ○ Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable).
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer, Client
textbox | Date Completed:
section | Construction
checkpoint | 2.1 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: TGSI should be laid in accordance with the site specific application and applicable standards before fixing
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Placement of TGSI
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure the placement of the TGSI are in accordance with IFC drawings and are compliant to AS1428.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Completion
checkpoint | 3.1 Completion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure pavement area is free of debris and waste.
label | REFERENCE DOCUMENTS: Visual Inspection
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath | itp |  |  |  |  | ITP-036 - Kerb Access Ramp Bluestone Footpath Rev1
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Existing Bluestone Kerb Demolition
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
label | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
label | ○ Bluestone shall be salvaged and re-used in new kerb alignment where possible
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Check Materials
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection List
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
label | ○ Line and level of bluestone pavers, tactiles and inlay shall be set out according to design levels to suit new kerb heights.
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction of Access Ramp Bluestone Footpath
checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels.
label | ○ Bluestone kerb shall be placed on a bed of low slump, 20 Mpa concrete of 75mm minimum thickness.
label | REFERENCE DOCUMENTS: IFC Drawings, CoM Bluestone Paving Specification
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.1 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling
label | ○ After placing and vibration, the concrete shall be screeded and trowelled to the correct level.
label | REFERENCE DOCUMENTS: CoM Bluestone Paving Specification
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Mortar Bed
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base
label | ○ All pavers shall be coated in mortar slurry on rear face before laying
label | REFERENCE DOCUMENTS: Dwg 1P50201
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Cutting of Pavers
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Placement of bluestone pavers
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402.
label | ○ Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
label | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.7 Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic
label | ○ Where required, ply shall be laid over area of works
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.8 Grouting
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.9 Installation of Versatac Granite Tactiles and Granite Inlay
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201.
label | REFERENCE DOCUMENTS: Dwg 1P50201
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Completion
checkpoint | 4.1 Completion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste
label | ○ Bluestone pavement is free of mortar stains and cleaned to satisfaction
label | REFERENCE DOCUMENTS: Visual Inspection
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-028 - Street Furniture (Supply & Installation) | itp |  |  |  |  | ITP-028 - Street Furniture (Supply & Installation) Rev0
section | Preliminaries
checkpoint | 1.1 IFC Drawings
label | REFERENCE: Fulton Hogan Quality Management Plan
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | METHOD: Document Review
label | FREQUENCY: Prior to starting Works and at regular intervals
label | HP*
label | RESPONSIBILITY: All
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 1.2 Componentry
label | REFERENCE: IFC Drawings
label | ○ Manufacturer's Drawings & Installation Recommendations
label | ○ Fulton Hogan Quality Management Plan
label | ACCEPTANCE CRITERIA: Product to be as per the Drawings, or where applicable, be selected based on the following criteria:
label | i. A like-for-like equivalent to those shown on the IFC Drawings
label | ii. Able to withstand the load conditions (where specified)
label | v. Have a protective coating or be manufactured from a material that aligns with the atmosphere it will be erected in
label | ○ Where a product has deviated from the IFC Drawings, details of the nominated equivalent proprietary system to be submitted for review to the Superintendent.
textbox | Enter: Teambinder Material Approval number
label | or
label | ○ Attach: Product Details
label | METHOD: Document Review
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: PE/SE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 1.3 Fixing Detail
label | REFERENCE: IFC Drawings
label | ○ Manufacturer's Drawings & Installation Recommendations
label | ACCEPTANCE CRITERIA: Fixing detail to be as per the IFC Drawings or Manufacturer's Drawings & Installation Recommendations.
label | ○ Changes to the approved Drawings shall be accompanied with approval from the Designers or Manufacturer's Representative.
textbox | Enter: Teambinder Request for Approval number
label | or
label | ○ Attach: Written approval from Manufacturer's Representative
label | METHOD: Document Review
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: PE/SE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Pre-installation Activities
checkpoint | 2.1 Materials Inspection Checklist
label | REFERENCE: IFC Drawings
label | ○ Fulton Hogan Quality Management Plan
label | ACCEPTANCE CRITERIA: General inspection of components for defects including cracks, chips, handling and storage damage & distortion.
label | ○ Coating shall have no damage, loss of adhesion, fading, blisters, roughness, sharp points or residues and be of the specified colour.
label | ○ Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | ○ Complete: Materials Inspection Checklist in ConQA
label | METHOD: Measure, Visual
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.2 Survey Set-out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within any specified tolerances as applicable to the component.
label | METHOD: Measure, Visual
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Installation Activities
checkpoint | 3.1 Mounting Surface Preparation
label | REFERENCE: Manufacturer's Drawings & Installation Recommendations
label | ACCEPTANCE CRITERIA: As a minimum, ensure that the bearing surface is clean and free from loose particles and residues.
label | METHOD: Visual
label | FREQUENCY: Each component location
label | IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.2 Component Handling
label | REFERENCE: Manufacturer's Drawings & Installation Recommendations
label | ACCEPTANCE CRITERIA: The method of handling and erection of the components shall ensure that there is no damage to the protective coating during these operations.
label | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | METHOD: Visual
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.3 Component Installation
label | REFERENCE: IFC Drawings
label | ○ Manufacturer's Drawings & Installation Recommendations
label | ACCEPTANCE CRITERIA: Place component into position, ensuring that it is plumb, level, square and within tolerances shown on the IFC drawings or Manufacturer's Drawings and installation recommendations.
label | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | ○ Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
label | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | METHOD: Measure, Visual
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | REFERENCE: IFC Drawings
label | ○ Manufacturer's Drawings & Installation Recommendations AS4100, Clause 14.3.3.1
label | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the drawings.
label | ○ At least 1 no. washer shall be used underneath the rotating part unless this is not part of the hand rail system.
label | ○ Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | ○ Protrusion to be at least 1 clear thread pitch and any thread run-off beyond the nut.
label | ○ Note: No maximum projection length is stated in the Australian Standards.
label | METHOD: Measure, Visual
label | FREQUENCY: Where applicable, each bolted connection
label | IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-installation Activities
checkpoint | 4.1 Inspection of Coating (where applicable)
label | REFERENCE: IFC Drawings
label | ○ Manufacturer's Drawings & Installation Recommendations
label | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
label | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | METHOD: Visual
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.2 As-built Survey
label | REFERENCE: IFC Drawings
label | ○ Manufacturer's Drawings & Installation Recommendations
label | ○ Fulton Hogan Quality Management Plan
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within any specified tolerances.
label | ○ Attach: Survey As-builts / Survey Report / Photos
label | METHOD: Document Review
label | FREQUENCY: Each component
label | IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Non-conformance Report (NCR) Closure
label | REFERENCE: Fulton Hogan Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
textbox | Date: